## Project list
Assumptions:
[15 empty] | 9500 | 10000 | DT Productivity sq m per month in AP areas
[16 empty] | 17000 | DT Productivity sq m per month in AT areas
[16 empty] | 110000 | DT Productivity sq m per month in BF areas
[16 empty] | 17000 | MDS Productivity sq m in AP areas
[16 empty] | 16000 | MDS Productivity sq m in AT areas
[16 empty] | 10000 | MDU Productivity sq m per month in AP areas
[16 empty] | 45000 | MDU Productivity sq m per month in AT areas
[16 empty] | 27000 | MDU Productivity sq m per month in BF areas |  |  |  |  | AP | AT
[22 empty] | 0.12191 | 0.11997
[16 empty] | 12500 | Monthly running cost of DT |  |  |  |  | 0.094162 | 0.13095
[16 empty] | 8000 | Monthly running cost of MDU |  |  |  |  | 0.14016 | 0.097445
[16 empty] | 20500 | Monthly running cost of MDU+DT in AT |  |  |  |  | 0.15415 | 0.12224
[16 empty] | 5000 | Monthly running cost of MDS
S/No | Task ID | Project Name | Project Status | Project device type | Ottawa Rank | Year | Region | Province | District | No of Hazard |  |  |  | Area (sqm) | Hazard Area Type |  |  | Planned Area Status |  |  | UNDSS Security Level | Secure/ Insecure | Beneficiary | Anticipated Cost ($) | Equipment Cost | Annual Inflation Cost (4%) | Total Cost without Equipment | Total cost | Donor | Planned Agency | Additional information
[10 empty] | Total | AP | AT | ERW |  | AP MF | AT MF | BF | No of Hazard | Planned Area | Remained area
1 | MBT Project-029 | Baghlan Demining Project-10 | Complete | AP | 2,3 | 1391 | NE | Baghlan and Balkh | Khinjan | 19 | 18 | 1 |  | 1184955 | 1179755 | 5200 | 0 | 19 | 1184955 |  | 17 L | secure | 130 | 1181558.1182 | 144451.663 | 47262.3247 | 1228820.4429 | 1373272.1059 |  | HALO Trust | Cleared by HT in 1391
2 | MBT Project-031 | Baghlan Demining Project-14 | Complete | AP,ERW | 2,3,4 | 1391 | NE | Baghlan | Dushi | 10 | 10 |  |  | 271330 | 271330 | 0 | 0 | 10 | 271330 |  | 13 L | Secure | 5167 | 271172.0742 | 33078.7381 | 10846.883 | 282018.9571 | 315097.6952 |  | HALO Trust | Cleared by HT in 1391
4 | MBT Project-289 | Hilmand Demining Project-07 AT | Closed | AT | 5 |  | SA | Hilmand | Nad Ali, Lashkar Gah | 4 |  | 4 |  | 243200 | 0 | 243200 | 0 | 4 | 243200 | 0 | 4 H | Secure | 6 | 116445.4118 | 29175.9216 | 4657.8165 | 121103.2282 | 150279.1499 |  |  | The project hazards canceled
5 | MBT Project-012 | Logar Demining Project-01 | Complete | AP | 2 | 1392 | CA | Loger | Mohammad Agha | 2 | 2 |  |  | 394063 | 394063 | 0 | 0 | 2 | 394063 | 0 | 2 Sub | Secure | 60 | 393833.6383 | 48041.5242 | 15753.3455 | 409586.9838 | 457628.508 | DOS RFP | ATC
6 | MBT Project-090 | Samangan Demining Project-5 | Complete | AP, ERW | 3,5 | 1392 | NA | Samangan | Darai Suf Payan | 10 | 10 |  | 0 | 192910 | 192910 |  | 0 | 10 | 192910 | 0 | 9 Mod | Secure | 209 | 192797.718 | 23518.2964 | 7711.9087 | 200509.6267 | 224027.9232 | DOS | HALO Trust
7 | MBT Project-286 | Kandahar Demining Project-05 AT | Complete | AT | 1,2 | 1392 | SA | Kandahar | Zhari | 9 |  | 9 |  | 2005538 | 0 | 2005538 | 0 | 9 | 2005538 | 0 | 6H | Secure | 326 | 960261.917 | 240597.9422 | 38410.4767 | 998672.3937 | 1239270.3359 | VTF/Japan | DAFA
8 | MBT Project-035 | Takhar Demining Project-06 | Complete | AP | 1,2,3 | 1392 | NE | Takhar | Khwaja Ghar and Rustaq | 7 | 7 |  |  | 674172 | 674172 | 0 | 0 | 7 | 674172 | 0 | 5 L, 9 Min | Secure | 110 | 673779.6027 | 82190.5393 | 26951.1841 | 700730.7868 | 782921.326 | DOS RFP | MDC
9 | MBT Project-047 | Paktya Demining Project-05 | Complete | AP,AT | 3,4 | 1392 | SE | Paktya | Sayed Karam, Ahmad Abad | 28 | 13 | 15 |  | 1773436 | 893086 | 880350 | 0 | 28 | 1773436 | 0 | 23 Sub | Secure | 10870 | 1314082.2965 | 214491.8268 | 52563.2919 | 1366645.5883 | 1581137.4152 | VTF/ Aus | DAFA
10 | MBT Project-089/A | Samangan Demining Project-3/A | Complete | AP | 3,5 | 1392 | NA | Balkh, Samangan | Darai Suf Bala,Hazat Sultan, Firoz Hakhshi,Darai Suf Paian, Charkent, Kaldar | 6 | 6 | 0 | 0 | 220840 | 220840 | 0 | 0 | 6 | 220840 | 0 | 6 Mod | Secure | 129 | 220711.4615 | 26923.3351 | 8828.4585 | 229539.92 | 256463.2551 | Germani | HALO Trust
11 | MBT Project-139/A | Hirat Demining Project-10 (AT)/A | Complete | AT | 5 | 1392 | WA | Hirat | Kohsan | 7 | 0 | 7 | 0 | 692900 | 0 | 692900 | 0 | 7 | 692900 | 0 | 7 Mod | Secure | 125 | 331764.0864 | 83124.984 | 13270.5635 | 345034.6499 | 428159.6339 | Germani | HALO Trust
12 | MBT Project-201/A | Nangarhar Demining Project-03/A | Complete | AP | 2 | 1392 | EA | Nangarhar | Hesarak, Nazyan | 4 | 4 | 0 |  | 511728 | 511728 |  | 0 | 4 | 511728 | 0 | 5 H, 5 Sub | Secure | 60 | 511430.1521 | 62386.4537 | 20457.2061 | 531887.3582 | 594273.8119 | DOS | DAFA
13 | MBT Project-021 | Kabul Demining Project-03 (AT) | Complete | AP,AT | 1,2,3,4,5 | 1392 | CA | Kabul | Shakardara, Guldara,Khaki Jabar, Qarabagh, Kabul | 26 | 14 | 12 |  | 1730434 | 929691 | 800743 | 0 | 26 | 1730434 | 0 | 2 L, 3 Sub, 14 Mod, 4 Man | secure | 4525 | 1312549.7494 | 209404.2678 | 52501.99 | 1365051.7394 | 1574456.0072 | German & DOS | MDC
14 | MBT Project-091 | Samangan Demining Project-6 | Complete | AP,AT,ERW | 3,4,5 | 1392 | NA | Samangan | Darai Suf Payan & Darai Suf Bala | 15 | 12 | 2 | 1 | 275111 | 271781 | 3130 | 200 | 15 | 275111 | 0 | 21 Mod | Secure | 1508 | 273142.5839 | 33509.217 | 10925.7034 | 284068.2873 | 317577.5043 | VTF/Aus | HALO Trust
15 | MBT Project-129/A | Samangan Demining Project-4/A | Complete | AP,AT | 5 | 1392 | NA | Samangan | Darai Suf Bala | 5 | 5 | 0 | 0 | 166337 | 166337 | 0 | 0 | 5 | 166337 | 0 | 28 Mod | Secure | 237 | 166240.1847 | 20278.6941 | 6649.6074 | 172889.792 | 193168.4861 | CIDA | HALO Trust
16 | MBT Project-036 | Takhar Demining Project-08 | Complete | AP,AT | 1,2,3,4,5 | 1392 | NE | Takhar | Khwaja Ghar and Rustaq,Bangi, Hazarsomoch, taloqan, Kalfagan | 71 | 69 | 2 |  | 2057514 | 2049379 | 8135 | 0 | 71 | 2057514 | 0 | 16 L, 31 Min | Secure | 10559 | 2052081.2525 | 250822.5048 | 82083.2501 | 2134164.5026 | 2384987.0073 | German | MDC
17 | MBT Project-137 | Hirat Demining Project-06 (AT) | Complete | AT | 2, 4, 5 | 1392 | WA | Hirat | Hirat, Kohsan | 17 | 0 | 17 | 0 | 839434 | 0 | 839434 | 0 | 17 | 839434 | 0 | 6 Mod, 9 Sub | Secure | 20067 | 401925.3198 | 100704.1966 | 16077.0128 | 418002.3326 | 518706.5292 | VTF/CIDA | HALO Trust
18 | MBT Project-182 | Kandahar Demining Project-03 AT | Complete | AT | 1 | 1392 | SA | Kandahar | Zhari | 10 |  | 10 |  | 1638430 | 0 | 1638430 | 0 | 10 | 1638430 | 0 | 2 H | Secure | 0 | 784488.7171 | 196557.1764 | 31379.5487 | 815868.2658 | 1012425.4422 | DOS | DAFA
19 | MBT Project-083 | Baghlan Demining Project-16 | Complete | AP | 2 | 1392 | NE | Baghlan | Pul-i-Khumri | 12 | 12 |  |  | 804603 | 804603 | 0 | 0 | 12 | 804603 | 0 | 10 Sub | Secure | 762 | 804134.6862 | 98091.814 | 32165.3874 | 836300.0736 | 934391.8877 | VTF/Japan | OMAR
20 | MBT Project-040 | Samangan Demining Project-1 | Complete | AP,AT,ERW | 2,3,4 | 1392 | NA | Samangan | Hazrat Sultan & Khuram wa Sarbagh | 8 | 6 | 2 | 0 | 126170 | 112200 | 13970 | 0 | 8 | 126170 | 0 | 12 L | Secure | 1020 | 118823.6026 | 15354.6092 | 4752.9441 | 123576.5467 | 138931.156 | JaVTF/Japan | OMAR
21 | Project-132 | Panjshir DOS Demining Project 1391/1392 | Complete | AP | 1,2,4,5 | 1392 | CA | Parwan,Panjshir | Bagram, Bazarak, Sutul Unaba | 7 | 7 |  |  | 664863 | 664863 |  |  | 7 | 664863 | 0 | 2 Mi,1 Mod | Secure | 1984 | 664476.0209 | 81055.6483 | 26579.0408 | 691055.0618 | 772110.71 | DOS | DDG
22 | MBT Project-066 | Logar Demining Project-03 | Complete | AP,AT | 3,4 | 1392 | CA | Loger | Mohammad Agha | 4 | 3 | 1 |  | 539654 | 3933 | 535721 | 0 | 4 | 539654 | 0 | 5 Sub | Secure | 1998 | 260436.683 | 64748.21 | 10417.4673 | 270854.1503 | 335602.3604 | VTF/CIDA | MDC
23 | MBT Project-058/B | Kabul Demining Project-07/B | Complete | AP | 4 | 1392 | CA | Kabul | Farza, Shakardara & Guldara | 10 | 10 |  |  | 323000 | 323000 | 0 | 0 | 10 | 323000 | 0 | 8 Min | Secure | 1860 | 322812 | 39377.9988 | 12912.48 | 335724.48 | 375102.4788 | Diffirent Donors | HALO Trust
24 | MBT Project-108 | Parwan Demining Project-07 | Complete | AP | 3,5 | 1392 | CA | Parwan | Jabalussaraj | 12 | 12 |  |  | 327554 | 327554 | 0 | 0 | 12 | 327554 | 0 | 13 L, 25 Min | Secure | 428 | 327363.3494 | 39933.192 | 13094.534 | 340457.8833 | 380391.0753 | Diffirent Donors | HALO Trust
25 | MBT Project-108/A | Parwan Demining Project-07/A | Complete | AP | 2,3,5 | 1392 | CA | Parwan | Bagram and Charikar | 10 | 8 | 0 | 2 | 200657 | 200455 | 0 | 202 | 10 | 200657 | 0 | 8 L | Secure | 6042 | 200359.6497 | 24438.1323 | 8014.386 | 208374.0357 | 232812.1681 | VFF/Japan | ATC
26 | MBT Project-001 | Parwan Demining Project-01 | Complete | AP,AT | 1,2,3,4 | 1392 | CA | Parwan | Bagram, Charikar & Jabalussaraj | 31 | 29 | 2 | 0 | 1066119 | 995367 | 70752 | 0 | 31 | 1066119 | 0 | 28 Low, 11 Mod | Secure | 24422 | 1028664.075 | 129836.3743 | 41146.563 | 1069810.638 | 1199647.0124 | DOS RFP | OMAR
27 | MBT Project-062/A | Kabul Demining Project-14/A | Complete | AP | 4,5 | 1392 | CA | Kabul | Guldara | 3 | 3 |  | 0 | 109900 | 109900 | 0 | 0 | 3 | 109900 | 0 | 3 Min | Secure | 305 | 109836.0334 | 13398.2726 | 4393.4413 | 114229.4748 | 127627.7474 | CIDA | HALO Trust
28 | MBT Project-234 | Logar Demining Project-08 | Complete | AP | 3,5 | 1392 | CA | Loger | Mohammad Agha | 24 | 23 |  | 1 | 1586148 | 1538099 | 0 | 48049 | 24 | 1586148 | 0 | 23 Sub | Secure | 876 | 1542275.8413 | 187514.7384 | 61691.0337 | 1603966.8749 | 1791481.6134 | DOS | OMAR
29 | MBT Project-168 | Kandahar Demining Project-01 AT | Complete | AT | 1 | 1392 | SA | Kandahar | Zhari | 10 | 1 | 9 |  | 1432099 | 113755 | 1318344 | 0 | 10 | 1432099 | 0 | 2 H | Secure | 0 | 744918.6825 | 172025.7371 | 29796.7473 | 774715.4298 | 946741.1669 | DOS | DAFA
30 | MBT Project-256/A | Paktya Demining Project-07/A | Complete | AP,AT | 1,3,4 | 1392 | SE | Paktya | Ali Khail (Jaji), Laja Ahmad Khail | 13 | 9 | 4 |  | 768138 | 416338 | 351800 | 0 | 13 | 768138 | 0 | 23 Sub | Secure | 6736 | 584539.324 | 92961.4575 | 23381.573 | 607920.8969 | 700882.3544 | VTF/Aus | MCPA
31 | MBT Project-256 | Paktya Demining Project-07 | Complete | AP,AT | 1 | 1392 | SE | Paktya | Ali Khail (Jaji), Laja Ahmad Khail, Gardaiz | 8 | 4 | 4 |  | 344681 | 155284 | 189397 |  | 8 | 344681 | 0 | 13 Sub | Secure | 1153 | 245877.8764 | 41652.5351 | 9835.1151 | 255712.9915 | 297365.5265 | VTF/CIDA | ATC
32 | MBT Project-041/A | Samangan Demining Project-10/A | Complete | AP | 1 | 1392 | NA | Samangan | Khuram wa Sarbagh | 5 | 4 | 1 | 0 | 219427 | 169427 | 50000 | 0 | 5 | 219427 | 0 | 2 L | Secure | 17 | 193268.6435 | 26653.7453 | 7730.7457 | 200999.3892 | 227653.1346 | SIDA | DDG
33 | MBT Project-304 | EODT Kandahar West EMCPA Project | Complete | AP,AT | 1,2,3,4,5 | 1392 | SA | Kandahar | Arghandab,Arghestan, Panjwee, Kandahar, Zhari | 33 | 6 | 26 | 1 | 2954114 | 202676 | 2746057 | 5381 | 33 | 2954114 | 0 | 39 H | Secure | 2709 | 1517952.2811 | 354144.5263 | 60718.0912 | 1578670.3724 | 1932814.8986 | UAE | EMCPA
34 | MBT Project-053 | EODT Kandahar East EMCPA Project | Complete | AP,AT | 1,2,3,4,5 | 1392 | SA | Kandahar | Arghistan, Daman, Khakrez,Spin Boldak, Maruf | 32 | 11 | 21 |  | 4694050 | 1730426 | 2963624 | 0 | 32 | 4694050 | 0 | 52 H | Secure | 1195 | 3148417.2422 | 566498.397 | 125936.6897 | 3274353.9319 | 3840852.3289 | UAE | EMCPA
35 | MBT Project-202 | Khost Demining Project-01 | Complete | AP,AT | 1,2,4,5 | 1392 | SE | Khost | Tani | 18 | 16 | 2 |  | 634032 | 472677 | 161355 | 0 | 18 | 634032 | 0 | 14 H | Secure | 556 | 549659.486 | 76982.8574 | 21986.3794 | 571645.8654 | 648628.7228 | VTF/ Aus | MCPA
36 | MBT Project-106 | Hirat Demining Project-05 (AT) | Complete | AT | 1 | 1392 | WA | Hirat | Kohsan | 7 | 0 | 7 | 0 | 585200 | 0 | 585200 | 0 | 7 | 585200 | 0 | 26 Mod | Secure | 405 | 280196.7721 | 70204.5615 | 11207.8709 | 291404.6429 | 361609.2044 | DOS | HALO Trust
37 | MBT Project-125/B | Takhar Demining Project-02/B | Complete | AP,AT,ERW | 3,5 | 1392 | NE | Takhar | Chal, Taluqan, Farkhar | 13 | 11 | 1 | 1 | 501641 | 397663 | 91850 | 12128 | 13 | 501641 | 0 |  | Secure | 1987 | 442690.0347 | 59499.3612 | 17707.6014 | 460397.6361 | 519896.9972 | DOS | HALO Trust
38 | MBT Project-125/E | Takhar Demining Project-02/E | Complete | AP | 5 | 1392 | NE | Takhar | Namk Ab Taluqn | 2 | 2 |  |  | 53700 | 53700 |  |  | 2 | 53700 | 0 |  | Secure | 54 | 53668.7443 | 6546.7447 | 2146.7498 | 55815.494 | 62362.2387 | Germani | HALO Trust
39 | MBT Project-018 | Panjshir Demining Project-03 | Complete | AP | 1,4 | 1392 | CA | Panjshir | Khinj, Shutul, Bazark, Rukha and Unaba | 26 | 26 |  |  | 1132554 | 1132554 | 0 | 0 | 26 | 1132554 | 0 | 26 Min | Secure | 20273 | 1131894.8045 | 138073.4056 | 45275.7922 | 1177170.5967 | 1315244.0023 | DOS RFP | OMAR
40 | MBT Project-004 | Parwan Demining Project-04 | Complete | AP | 2,3,4 | 1392 | CA | Parwan | Shikh Ali, | 14 | 14 |  |  | 468270 | 468270 | 0 | 0 | 14 | 468270 | 0 | 9 Sub | Secure | 2366 | 467997.4466 | 57088.3451 | 18719.8979 | 486717.3444 | 543805.6896 | DOS RFP | OMAR
41 | MBT Project-004/A | Parwan Demining Project-04/A | Complete | AP | 4 | 1392 | CA | Parwan | Shikh Ali, Surepasa | 4 | 4 |  |  | 155825 | 155825 |  |  | 4 | 155825 | 0 | 1 Sub, 3 Low | Secure | 677 | 155734.3031 | 18997.1414 | 6229.3721 | 161963.6752 | 180960.8166 | VTF Aust | ATC
42 | MBT Project-013 | Logar Demining Project-26 (AT) | Complete | AT | 3 | 1392 | CA | Loger | Mohammad Agha | 8 | 0 | 8 |  | 760060 | 0 | 760060 | 0 | 8 | 760060 | 0 | 16 Sub | Secure | 2040 | 363920.6401 | 91181.9532 | 14556.8256 | 378477.4657 | 469659.4188 | DOS | MCPA
43 | MBT Project-181/A | Nangarhar Demining Project-02/A | Complete | AT | 1 | 1392 | EA | Nangarhar | Chaparhar, Mohmand Dara Pachir Wa Agam, Rodat | 1 |  | 1 |  | 59841 |  | 59841 |  | 1 | 59841 | 0 |  | Secure | 155 | 28652.1788 | 7178.9323 | 1146.0872 | 29798.266 | 36977.1982 | German | MDC
44 | MBT Project-181/D | Nangarhar Demining Project-02/D | Complete | AT | 4 | 1392 | EA | Nangarhar | ro | 6 | 0 | 6 |  | 809179 | 0 | 809179 |  | 6 | 809179 | 0 |  | Secure | 3869 | 387439.0701 | 97074.6016 | 15497.5628 | 402936.6329 | 500011.2345 | DOS | OMAR
45 | MBT Project-073/A | Logar Demining Project-08 (AT)/A | Complete | AT | 1 | 1392 | CA | Loger | Khoshi | 7 |  | 7 |  | 807094 |  | 807094 |  | 7 | 807094 | 0 | 7 Sub | Secure | 839 | 386440.7614 | 96824.4708 | 15457.6305 | 401898.3918 | 498722.8626 | OCHA | HALO Trust
46 | MBT Project-073/C | Logar Demining Project-08 (AT)/C | Complete | AT | 4,5 | 1392 | CA | Loger | Puli Alam | 3 |  | 3 |  | 315189 |  | 315189 |  | 3 | 315189 | 0 | 5 Sub | Secure | 458 | 150914.1155 | 37812.2104 | 6036.5646 | 156950.6801 | 194762.8905 | DOS | HALO Trust
47 | MBT Project-073/D | Logar Demining Project-08 (AT)/D | Complete | AT | 1,3,5 | 1392 | CA | Loger | Khushi, Puli Alam | 10 |  | 10 |  | 658831 |  | 658831 |  | 10 | 658831 | 0 | 6 Sub | Secure | 2398 | 315451.6738 | 79037.8357 | 12618.067 | 328069.7408 | 407107.5765 | B-Germany | HALO Trust
48 | MBT Project-120/B | Baghlan Demining Project-13/B | Complete | AP | 4,5 | 1392 | NE | Baghlan | Khinjan | 3 | 3 |  |  | 252160 | 252160 |  |  | 3 | 252160 | 0 | 9 L | Secure | 240 | 252013.232 | 30741.66 | 10080.5293 | 262093.7612 | 292835.4212 | B-Germany | HALO Trust
49 | MBT Project-002/B | Parwan Demining Project-02/B | Complete | AP | 1,2,5 | 1392 | CA | Parwan | Kohi Safi | 4 | 4 |  |  | 375828 | 375828 |  |  | 4 | 375828 | 0 | 2 Sub | Secure | 460 | 375609.2518 | 45818.435 | 15024.3701 | 390633.6219 | 436452.0569 | ODS | OMAR
50 | MBT Project-002/E | Parwan Demining Project-02/E | Complete | AP | 1 | 1392 | CA | Parwan | Kohi Safi | 3 | 3 |  |  | 135400 | 135400 | 0 | 0 | 3 | 135400 | 0 |  | Secure | 243 | 135321.1913 | 16507.062 | 5412.8477 | 140734.039 | 157241.101 | CIDA | HT
51 | MBT Project-150/A | Baghlan Demining Project-21/A | Complete | AP | 2 | 1392 | NE | Baghlan | Baghlan-i-Jadid, | 5 | 5 | 0 | 0 | 192200 | 192200 | 0 | 0 | 5 | 192200 | 0 | 5 Sub | Secure | 6 | 192088.1313 | 23431.738 | 7683.5253 | 199771.6565 | 223203.3945 | German | MDC
52 | MBT Project-100 | Khost Demining Project-05 | Complete | AP,AT | 1,2,4,5 | 1392 | SE | Khost | Tani, Mando Zayi | 15 | 6 | 9 | 0 | 216016 | 130476 | 85540 | 0 | 15 | 216016 | 0 |  | Secure | 457 | 171357.0496 | 26168.7195 | 6854.282 | 178211.3316 | 204380.0511 | VTF | MCPA
53 | MBT Project-067 | Panjshir Demining Project-02 | Complete | AP,AT | 1,3,5 | 1392 | CA | Panjshir | Khinj, Unaba | 8 | 8 | 0 |  | 379526 | 379526 | 0 | 0 | 8 | 379526 | 0 | 8 Min | Secure | 9058 | 379305.0994 | 46269.2705 | 15172.204 | 394477.3034 | 440746.5739 | DOS | DDG
54 | MBT Project-121/B | Baghlan Demining Project-15/B | Complete | AP | 4,5 | 1392 | NE | Baghlan | Dushi, | 2 | 2 |  |  | 93000 | 93000 |  |  | 2 | 93000 | 0 | 11 L | Secure | 143 | 92945.87 | 11337.9377 | 3717.8348 | 96663.7048 | 108001.6425 | B-AAR | HALO Trust
55 | MBT Project-008/A | Kabul Demining Project-05/A | Complete | AP | 4 | 1392 | CA | Kabul | Khaki Jabar | 2 | 2 |  | 0 | 144496 | 144496 | 0 | 0 | 2 | 144496 | 0 | 2 Mod | Secure | 79 | 144411.8971 | 17615.9855 | 5776.4759 | 150188.3729 | 167804.3584 | DOS | DDG
56 | MBT Project-269 | Zabul Demining Project-01 | Complete | AT | 2 | 1392 | SA | Zabul | Qalat | 1 |  |  | 1 | 1361022 | 0 | 0 | 1361022 | 1 | 1361022 | 0 | 3 H | Secure | 30 | 143670.3072 | 0 | 5746.8123 | 149417.1195 | 149417.1195 | VTF | DAFA
57 | MBT Project-109/A | Parwan Demining Project-09/A | Complete | AP, ERW | 1,5 | 1392 | CA | Bamyan | Bamyan | 11 | 9 | 1 | 1 | 663670 | 366548 | 100 | 297022 | 11 | 663670 | 0 | 7 Min, 1 Low | Secure | 2299 | 397736.356 | 44699.0762 | 15909.4542 | 413645.8103 | 458344.8865 | VTF No cost Extention | ATC
58 | MBT Project-017 | Panjshir Demining Project-01 | Complete | AP,AT,ERW | 1,2,3,5 | 1392 | CA | Panjshir | Bazarak, Unaba, Shutol | 8 | 5 |  | 3 | 317793 | 244127 |  | 73666 | 8 | 317793 | 0 | 11 Min | Secure | 2880 | 251761.1351 | 29762.3304 | 10070.4454 | 261831.5805 | 291593.9109 | DOS RFP | OMAR
59 | MBT Project-181/B | Nangarhar Demining Project-02/B | Complete | AP,AT | 1,5 | 1392 | EA | Nangarhar | Chaparhar | 9 | 7 | 2 |  | 731842 | 509878 | 221964 |  | 9 | 731842 | 0 |  | Secure | 1129 | 615858.7346 | 88789.2211 | 24634.3494 | 640493.0839 | 729282.3051 | DOS | MCPA
60 | MBT Project-006/A | Kabul Demining Project-02/A | Complete | AP, ERW | 2 | 1392 | CA | Kabul | Khaki Jabar | 4 | 4 |  |  | 303119 | 303119 |  |  | 4 | 303119 | 0 | 3 Mod | Secure | 76 | 302942.5716 | 36954.2403 | 12117.7029 | 315060.2745 | 352014.5147 | DOS | OMAR
61 | MBT Project-250/A | Laghman Demining Project-01/A | Complete | AP | 1 | 1392 | EA | Laghman | Qarghaye | 4 | 4 |  |  | 253145 | 253145 | 0 | 0 | 4 | 253145 | 0 | 3 H | Secure | 252 | 252997.6586 | 30861.7446 | 10119.9063 | 263117.565 | 293979.3096 | DOS | OMAR
62 | MBT Project-033 | Takhar Demining Project-01 | Complete | AP,AT | 1,2,3,5 | 1392 | NE | Takhar | Taluqan & Namak Abb | 22 | 21 | 1 |  | 556965 | 555075 | 1890 | 0 | 22 | 556965 | 0 | 4 L, 35 Min | Secure | 2282 | 555656.864 | 67897.7671 | 22226.2746 | 577883.1386 | 645780.9057 | DOS RFP | MDC
63 | MBT Project-097 | Takhar Demining Project-2 (AT) | Complete | AT,ERW | 2,3,5 | 1392 | NE | Takhar | Khwaja Ghar, Taluqan | 9 | 0 | 5 | 4 | 196004 |  | 31745 | 164259 | 9 | 196004 | 0 | 11 L | Secure | 4546 | 32538.949 | 3808.3455 | 1301.558 | 33840.5069 | 37648.8525 | DOS RFP | MDC
64 | MBT Project-058/A | Kabul Demining Project-07/A | Complete | AP | 1,4,5 | 1392 | CA | Kabul | Guldara, Shakardara & Mir bacha kot | 17 | 17 |  |  | 548027 | 548027 | 0 | 0 | 17 | 548027 | 0 | 17 Min | Secure | 1331 | 547708.0245 | 66811.7849 | 21908.321 | 569616.3455 | 636428.1304 | DOS | HALO Trust
65 | MBT Project-058 | Kabul Demining Project-07 | Closed | AP | 4 | 1392 | CA | Kabul | Qarabagh, | 0 |  |  |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 L, 8 Min | Secure | 149 | 0 | 0 | 0 | 0 | 0 |  |  | This Project All hazards cleared in sub projects
66 | MBT Project-007 | Kabul Demining Project-04 | Complete | AP | 2,3 | 1392 | CA | Kabul | Musyi & Khaki Jabar | 11 | 10 |  | 1 | 816189 | 780721 | 0 | 35468 | 11 | 816189 | 0 | 12 Mod | Secure | 542 | 784010.6101 | 95180.2804 | 31360.4244 | 815371.0345 | 910551.3149 | DOS RFP | ATC
67 | MBT Project-121/D | Baghlan Demining Project-15/D | Complete | AP | 5 | 1392 | NE | Baghlan | Khenlan | 4 | 4 |  |  | 295290 | 295290 |  |  | 4 | 295290 | 0 | 2 L | Secure | 36 | 295118.1284 | 35999.781 | 11804.7251 | 306922.8536 | 342922.6345 | CIDA | HALO Trust
68 | MBT Project-108/C | Parwan Demining Project-07/C | Complete | AP, ERW | 5 | 1392 | CA | Parwan | Bagram | 4 | 4 |  |  | 352201 | 352201 |  |  | 4 | 352201 | 0 | 4 Mod | Secure | 154 | 351996.0038 | 42937.9893 | 14079.8402 | 366075.8439 | 409013.8332 | DOS | ATC
69 | MBT Project-020 | Kabul Demining Project-02 (AT) | Complete | AP,AT,ERW | 2,3,4,5 | 1392 | CA | Kabul | Surobi, Khak-i-jabar, Kabul | 17 | 10 | 2 | 5 | 962851 | 769378 | 58443 | 135030 | 17 | 962851 | 0 | 9 Mod, 13 Sub | Secure | 225722 | 811166.8465 | 100808.6364 | 32446.6739 | 843613.5204 | 944422.1568 | DOS | ATC
70 | MBT Project-089 | Samangan Demining Project-3 | Complete | AP,AT | 2,3,4,5 | 1392 | NA | Balkh, Samangan | Darai Suf Bala,Hazat Sultan, Firoz Hakhshi,Darai Suf Paian, Charkent, Kaldar | 23 | 19 | 4 | 0 | 557718 | 486896 | 70822 | 0 | 23 | 557718 | 0 | 32 Mod | Secure | 2069 | 520522.5435 | 67855.3899 | 20820.9017 | 541343.4453 | 609198.8352 | Diffirent Donors | HALO Trust
71 | MBT Project-002/D | Parwan Demining Project-002/D | Complete | AP | 1 | 1392 | CA | Parwan | Kohi Safi | 2 | 2 | 0 | 0 | 127000 | 127000 | 0 | 0 | 2 | 127000 |  |  | Secure | 199 | 126926.0805 | 15482.9902 | 5077.0432 | 132003.1237 | 147486.1139 | B-Germany | HALO Trust
72 | MBT Project-221/A | Parwan Demining Project-06/A | Complete | AP | 1,5 | 1392-1393 | CA | Parwan | Kohi Safi | 2 | 1 | 1 |  | 81607 | 30507 | 51100 | 0 | 2 | 81607 |  |  | Secure | 154 | 54956.1866 | 9849.5119 | 2198.2475 | 57154.4341 | 67003.946 | GAGP | HALO Trust
73 | MBT Project-139 | Hirat Demining Project-10 (AT) | Complete | AP,AT,ERW | 1,2,3,4,5 | 1392-1393 | WA | Hirat | Gulran, Koshk, Shindand | 66 | 9 | 44 | 13 | 10731711 | 388015 | 4062196 | 6281500 | 66 | 10731711 | 0 | 1 H, 10 Mod & 19 Sub | Secure | 8908 | 2995868.4586 | 534632.7789 | 119834.7383 | 3115703.1969 | 3650335.9759 | DFID | HALO Trust
74 | MBT Project-002/F | Parwan Demining Project-02/F | Complete | AP | 2 | 1392-1393 | CA | Parwan | Kohi Safi | 2 | 2 |  |  | 127600 | 127600 |  |  | 2 | 127600 | 0 |  | Secure | 88 | 127525.7313 | 15556.1382 | 5101.0293 | 132626.7605 | 148182.8987 | German | HALO Trust
75 | MBT Project-037 | Balkh Demining Project-1 | Complete | AP, ERW | 3,5 | 1392-1393 | NA | Balkh | Khulm | 7 | 4 | 0 | 3 | 378401 | 233982 | 0 | 144419 | 7 | 378401 | 0 | 6 Mod | Secure | 39 | 249090.7695 | 28525.5198 | 9963.6308 | 259054.4003 | 287579.9201 | SIDA | DDG
76 | MBT Project-121/C | Baghlan Demining Project-15/C | Complete | AP | 5 | 1392-1393 | NE | Baghlan | Dushi | 5 | 5 |  |  | 211389 | 211389 |  |  | 5 | 211389 | 0 | 5 L | Secure | 42 | 211265.9624 | 25771.1324 | 8450.6385 | 219716.6009 | 245487.7334 |  | HALO Trust
77 | MBT Project-125/D | Takhar Demining Project-02/D | Complete | AP | 1,5 | 1392-1393 | NE | Takhar | Namk Ab Taluqn | 22 | 22 |  |  | 319070 | 319070 |  |  | 22 | 319070 | 0 |  | Secure | 339 | 318884.2874 | 38898.8795 | 12755.3715 | 331639.6589 | 370538.5384 | CIDA | HALO Trust
78 | MBT Project-125/C | Takhar Demining Project-02/C | Complete | AP | 4,5 | 1392-1393 | NE | Takhar | Chal | 7 | 7 |  |  | 304975 | 304975 |  |  | 7 | 304975 | 0 |  | Secure | 145 | 304797.4913 | 37180.5114 | 12191.8997 | 316989.391 | 354169.9024 | GAGP | HALO Trust
79 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Complete | AP,AT | 3,4,5 | 1392-1393 | CA | Loger | Khoshi, Mohmmad Agha, Pul-e-alam | 12 | 4 | 8 |  | 906617 | 286899 | 619718 |  | 12 | 906617 | 0 | 4 Sub | Secure | 1206 | 583456.1805 | 109322.3813 | 23338.2472 | 606794.4277 | 716116.809 | Bilateral | HALO Trust
Sub Total | [9 empty] | 902 | 594 | 271 | 37 | 60867757 | 27500569 | 24808842 | 8558346 | 902 | 60867757 | 0 | 0 | 0 | 406975 | 40266587.9097 | 6328922.3292 | 1610663.5164 | 41877251.4261 | 48206173.7552 | 0 | 0
80 | MBT Project-166 | Hilmand Demining Project-10 | Planned | AIF | 1,2 | 1392 | SA | Hilmand | Naw Zad | 5 | 5 |  |  | 274563 | 274563 | 0 | 0 | 5 | 274563 | 0 | 11 H | Secure | 20006 | 274403.1924 | 33472.8838 | 10976.1277 | 285379.3201 | 318852.2039 | DOS | MDC
81 | MBT Project-129 | Samangan Demining Project-4 | Planned | AP,AT | 5 | 1392 | NA | Samangan | Darai Suf Bala | 15 | 14 | 0 | 1 | 492553 | 449422 | 0 | 43131 | 15 | 492553 | 0 | 28 Mod | Secure | 791 | 453713.3514 | 54790.5231 | 18148.5341 | 471861.8855 | 526652.4086 | Diffirent Donors | HALO Trust
82 | MBT Project-092 | Samangan Demining Project-8 | Planned | AP | 1,3,4 | 1392 | NA | Samangan | Khuram Wa Sarbagh | 34 | 34 | 0 | 0 | 666187 | 666187 | 0 | 0 | 34 | 666187 | 0 | 34 L | Secure | 634 | 665799.2503 | 81217.0615 | 26631.97 | 692431.2203 | 773648.2818 | JaVTF/Japan | OMAR
83 | MBT Project-058/C | Kabul Demining Project-07/B | Planned | AP | 4 | 1392 | CA | Kabul | Guldara | 6 | 6 |  |  | 157650 | 157650 | 0 | 0 | 6 | 157650 | 0 | 8 Min | Secure | 865 | 157558.2409 | 19219.6331 | 6302.3296 | 163860.5705 | 183080.2036 | Germani | HALO Trust
84 | MBT Project-044 | Nangarhar Demining Project-01 | Planned | AP,AT,ERW | 1,3,4,5 | 1392 | EA | Nangarhar | Sorkhrod, Hesarak, Khogaynai, Achin | 23 | 6 | 16 | 1 | 2292072 | 347762 | 1866367 | 77943 | 23 | 2292072 | 0 | 10 H, 3 Sub | Secure | 6163 | 1249413.4237 | 266298.8612 | 49976.5369 | 1299389.9606 | 1565688.8218 | DOS | MDC
85 | MBT Project-015 | Logar Demining Project-06 | Planned | AP,AT,ERW | 2,3,4 | 1392 | CA | Logar | Mohammad Agha | 12 | 4 | 7 | 1 | 5382660 | 826572 | 4345665 | 210423 | 12 | 5382660 | 0 | 14 Sub | Secure | 1460 | 2929030.0481 | 622105.578 | 117161.2019 | 3046191.25 | 3668296.828 | GOV of Af | MDC | cooppermine project
86 | MBT Project-002/C | Parwan Demining Project-02/C | Planned | AP | 1,2 | 1392 | CA | Parwan | Kohi Safi | 3 | 3 |  |  | 302855 | 302855 |  |  | 3 | 302855 | 0 | 3 Sub | Secure | 423 | 302678.7253 | 36922.0552 | 12107.149 | 314785.8743 | 351707.9294 | DOS | HALO Trust
87 | MBT Project-062 | Kabul Demining Project-14 | Planned | AP | 2,3,4,5 | 1392-1393 | CA | Kabul | Guldara, Shakardara, Qarabagh, Farza, Kalakan | 40 | 35 |  | 5 | 1581986 | 1049706 | 0 | 532280 | 40 | 1581986 | 0 | 1 L, 31 Min | Secure | 12598 | 1104288.3667 | 98842.692 | 88343.0693 | 1192631.436 | 1291474.1281 | Diffirent Donors | HALO Trust
88 | MBT Project-057 | Kabul Demining Project-03 | Planned | AP,AT | 1,3,4 | 1392-1393 | CA | Kabul | Paghman, Kabul | 6 | 4 | 2 | 0 | 246876 | 212004 | 34872 | 0 | 6 | 246876 | 0 | 7 Mod, 1 Sub | Secure | 500 | 231467.9092 | 24529.1945 | 18517.4327 | 249985.3419 | 274514.5364 | DOS | DAFA
89 | MBT Project-107 | Hirat Demining Project-07 (AT) | Complete | AT | 5 | 1392-1393 | WA | Hirat | Kohsan | 7 | 0 | 7 | 0 | 751000 | 0 | 751000 | 0 | 7 | 751000 | 0 | 8 Mod | Secure | 75 | 426155.6863 | 98341.9371 | 34092.4549 | 460248.1412 | 558590.0783 | NVESD | HALO Trust
90 | MBT Project-120/A | Baghlan Demining Project-13/A | Planned | AP | 5 | 1392-1393 | NE | Baghlan | Khinjan,Andarab | 9 | 9 |  |  | 393487 | 393487 |  |  | 9 | 393487 | 0 | 9 L | Secure | 170 | 392885.1964 | 37051.6262 | 31430.8157 | 424316.0121 | 461367.6383 | GAGP | HALO Trust
91 | MBT Project-002/A | Parwan Demining Project-02/A | Planned | AP | 1,2 | 1392-1393 | CA | Parwan | Kohi Safi | 21 | 21 |  |  | 1085051 | 1085051 |  |  | 21 | 1085051 | 0 | 23 Sub | Secure | 2402 | 1083391.5102 | 102170.8572 | 86671.3208 | 1170062.8311 | 1272233.6883 | Diffirent Donors | HALO Trust
92 | MBT Project-121/A | Baghlan Demining Project-15/A | Planned | AP | 4,5 | 1392-1393 | NE | Baghlan | Dushi, Khenjan | 12 | 12 |  |  | 490211 | 490211 |  |  | 12 | 490211 | 0 | 10 L | Secure | 302 | 489461.2655 | 46159.3769 | 39156.9012 | 528618.1668 | 574777.5437 | AAR Japan | HALO Trust
93 | MBT Project-043 | Baghlan Demining Project-1 (AT) | Planned | AP,AT,ERW | 1,2,3,5 | 1392-1393 | NE | Baghlan | Dushi, Polekhumri,Khenjan | 15 | 8 | 2 | 5 | 604114 | 236544 | 6720 | 360850 | 15 | 604114 | 0 | 4 L, 7 Sub | Secure | 2725 | 278087.0421 | 23153.4887 | 22246.9634 | 300334.0055 | 323487.4942 | DOS | HALO Trust
94 | MBT Project-026 | Badakhshan Demining Project-01 | Planned | AP | 1,3,5 | 1392-1393 | NE | Badakhshan | Argo, Darayim | 10 | 10 |  |  | 104800 | 104800 | 0 | 0 | 10 | 104800 | 0 | 5 Mod,7 Min | Secure | 616 | 104639.7176 | 9868.2051 | 8371.1774 | 113010.8951 | 122879.1002 | Diffirent Donors | HALO Trust
95 | MBT Project-161 | Hilmand Demining Project-01 | Planned | AP,AT,ERW | 2 | 1392-1393 | SA | Hilmand | Kajaki | 14 | 10 | 1 | 3 | 1695806 | 1453030 | 61116 | 181660 | 14 | 1695806 | 0 | 6 H, 7 Ext | Secure | 480 | 1504664.1926 | 144823.6095 | 120373.1354 | 1625037.328 | 1769860.9376 | DOS | DAFA
96 | MBT Project-117 | Badakhshan Demining Project-03 | Planned | AP, ERW | 1,3,5 | 1392-1393 | NE | Badakhshan | Darwazbala,Darwaz, Khwahan | 6 | 5 |  | 1 | 744117 | 386720 | 0 | 357397 | 6 | 744117 | 0 | 36 Min | Secure | 1032 | 423855.5898 | 36414.4302 | 33908.4472 | 457764.037 | 494178.4672 | PATRIP | FSD
97 | MBT Project-034 | Takhar Demining Project-05 | Planned | AP,ERW | 2,3,4 | 1392-1393 | NE | Takhar | Hazar Sumuch, Farkhar | 7 | 6 | 0 | 1 | 80729.5 | 80714 | 0 | 15.5 | 7 | 80729.5 | 0 | 4 Min, 2L | Secure | 556 | 80592.1912 | 7600.2129 | 6447.3753 | 87039.5665 | 94639.7794 | DOS RFP | MDC
98 | MBT Project-216/A | Hilmand Demining Project-06/A | Planned | ERW | 2,3,5 | 1392-1393 | SA | Hilmand | Musa Qala | 12 |  | 0 | 12 | 1668533 | 0 | 0 | 1668533 | 12 | 1668533 | 0 | 4 Ext | Secure | 3807 | 176131.3547 | 0 | 14090.5084 | 190221.8631 | 190221.8631 | DOS | DAFA
99 | MBT Project-005 | Kabul Demining Project-01 | Planned | AP,ERW | 1,2,3,4,5 | 1392-1393 | CA | Kabul and Parwan | Paghman,Dahsabz, Khakejabar,Bagram | 12 | 11 |  | 1 | 507872 | 504487 | 0 | 3385 | 12 | 507872 | 0 | 10 Mod | Secure | 3382 | 504072.7543 | 47503.6374 | 40325.8203 | 544398.5746 | 591902.212 | DANIDA | DDG
100 | MBT Project-102 | Hilmand Demining Project-02 AT | Planned | AT | 2,3,4 | 1392-1393 | SA | Hilmand | Sangin | 6 |  | 6 |  | 594200 |  | 594200 | 0 | 6 | 594200 | 0 | 8 Ext | Secure | 5512 | 337179.3725 | 77809.293 | 26974.3498 | 364153.7224 | 441963.0153 | DOS | MDC
101 | MBT Project-125/A | Takhar Demining Project-02/A | Planned | AP,ERW | 1,2,5 | 1392-1393 | NE | Takhar | Namak Abb, Rustaq | 20 | 17 |  | 3 | 354599 | 354426 |  | 173 | 20 | 354599 | 0 |  | Secure | 1643 | 353902.1987 | 33373.5541 | 28312.1759 | 382214.3746 | 415587.9287 | Diffirent Donors | HALO Trust
102 | MBT Project-125/F | Takhar Demining Project-02/F | Planned | AP | 5 | 1393 | NE | Takhar | Taluqan | 7 | 7 | 0 | 0 | 239900 | 239900 | 0 | 0 | 7 | 239900 | 0 |  | Secure | 56 | 239533.0941 | 22589.5268 | 19162.6475 | 258695.7416 | 281285.2685 | B-Germany | HALO Trust
103 | MBT Project-102/A | Hilmand Demining Project-02 AT/A | Planned | AP,AT | 3,4,5 | 1393 | SA | Hilmand | Sangin | 5 | 1 | 4 | 0 | 484052 | 6479 | 477573 | 0 | 5 | 484052 | 0 |  | Secure | 765 | 277468.358 | 63147.2996 | 22197.4686 | 299665.8266 | 362813.1262 | DOS | MDC
104 | MBT Project-114/A | Logar Demining Project-19 (AT)/A | Planned | AT, AP | 4,5 | 1393 | CA | Logar | Khoshi,Mohammad Agha | 6 | 2 | 4 |  | 458833 | 134667 | 324166 |  | 6 | 458833 | 0 | 5 Sub | Secure | 254 | 318409.3532 | 55129.4341 | 25472.7483 | 343882.1015 | 399011.5356 | DOS | HALO Trust
105 | MBT Project-079 | Baghlan Demining Project-02 | Planned | AP | 1,5 | 1393 | NE | Baghlan | Tala Wa Barfak | 15 | 15 |  |  | 1060515 | 1060515 |  | 0 | 15 | 1060515 | 0 | 15 Sub | Secure | 155 | 1058893.0359 | 99860.4919 | 84711.4429 | 1143604.4788 | 1243464.9707 | VTF-Japan | HALO Trust
106 | MBT Project-169 | Kandahar Demining Project-02 AT | Planned | AT | 1 | 1393 | SA | Kandahar | Zhari | 5 |  | 5 |  | 1210332 |  | 1210332 |  | 5 | 1210332 | 0 | 11 H | Secure | 0 | 686804.08 | 158490.5372 | 54944.3264 | 741748.4064 | 900238.9436 | DOS | DAFA
107 | MBT Project-002 | Parwan Demining Project-02 | Planned | AP, ERW | 1,2,3,5 | 1393 | CA | Parwan | Kohi Safi | 32 | 23 | 0 | 9 | 1201960 | 958250 | 0 | 243710 | 32 | 1201960 | 0 | 64 Sub | Secure | 2824 | 982510.6165 | 90230.9882 | 78600.8493 | 1061111.4658 | 1151342.454 | VTF-Australia | MCPA
108 | MBT Project-125 | Takhar Demining Project-02 | Planned | AP,AT | 1,3,4,5 | 1393 | NE | Takhar | Namak Abb, Chal, Taluqan,Farkhar | 32 | 31 | 1 |  | 792365 | 785565 | 6800 |  | 32 | 792365 | 0 | 14 L, 59 Min | Secure | 1549 | 788222.2143 | 74861.0241 | 63057.7771 | 851279.9915 | 926141.0156 | Bilateral | HALO Trust
109 | MBT Project-103 | Hirat Demining Project-01 | Planned | AP,AT,ERW | 1,3,4,5 | 1393 | WA | Hirat | Guzarah, Hirat, Koshk,Ghoryan,Gulran,Pashtun Zarghun & Shindand | 83 | 18 | 57 | 8 | 9472754 | 913673 | 4082481 | 4476600 | 83 | 9472754 | 0 | 19 H, 2 Sub | Secure | 4955 | 3701436.0727 | 620626.1797 | 296114.8858 | 3997550.9586 | 4618177.1382 | DFID | HALO Trust
110 | MBT Project-101 | Nimroz Demining Project-01 | Planned | AP,AT | 1,3,5 | 1393 | SA | Nimroz | Chahar Burjak, Zranj | 7 | 4 | 3 |  | 1051587 | 1049987 | 1600 | 0 | 7 | 1051587 | 0 | 6 Sub | Secure | 807 | 1049289.0591 | 99078.6684 | 83943.1247 | 1133232.1838 | 1232310.8522 | VTF-Japan | DAFA
111 | MBT Project-018/A | Panjshir Demining Project-03/A | Planned | AP,AT | 1,3,5 | 1393 | CA | Panjshir | Khinj, Paryan | 13 | 11 | 2 |  | 522876 | 488876 | 34000 | 0 | 13 | 522876 | 0 | 27 Min | Secure | 719 | 507421.6406 | 50485.9018 | 40593.7313 | 548015.3719 | 598501.2737 | VTF-Australia | HALO Trust
112 | MBT Project-160 | Paktya Demining Project-09 | Planned | AP,AT | 1,2,3 | 1393 | SE | Paktya | Gardiz,Sayed Karam | 8 | 1 | 7 |  | 517559 | 51191 | 466368 | 0 | 8 | 517559 | 0 | 9 Sub | Secure | 492 | 315753.6867 | 65890.2105 | 25260.2949 | 341013.9816 | 406904.1921 | VTF-Japan | MCPA
113 | MBT Project-221 | Parwan Demining Project-06 | Planned | AP,AT | 1,2,3,4,5 | 1393 | CA | Parwan | Charikar, Bagram,Jabalussaraj,Kohi Safi,Salang,Shinwari | 90 | 88 | 2 | 0 | 3650320 | 3648613 | 1707 | 0 | 90 | 3650320 | 0 | 35 L | Secure | 7461 | 3644001.4072 | 343785.1837 | 291520.1126 | 3935521.5198 | 4279306.7035 | Bilateral | HALO Trust
114 | MBT Project-221/B | Parwan Demining Project-06 /B | Planned | AP | 4,5 | 1393 | CA | Parwan | Jabalussaraj | 4 | 4 |  |  | 206160 | 206160 | 0 | 0 | 4 | 206160 | 0 |  | Secure | 2242 | 205844.6965 | 19412.4921 | 16467.5757 | 222312.2722 | 241724.7643 | B-Germany | HALO Trust
115 | MBT Project-221/C | Parwan Demining Project-06 /C | Planned | AP | 5 | 1393 | CA | Parwan | Jabalussaraj | 5 | 5 | 0 | 0 | 187983 | 187983 |  |  | 5 | 187983 | 0 |  | Secure |  | 187695.4966 | 17700.9046 | 15015.6397 | 202711.1363 | 220412.0409 | GAGP | HALO Trust
116 | MBT Project-095 | Samangan Demining Project-2 (AT) | Planned | AP,AT | 1,2,3,4,5 | 1393 | NA | Samangan | Dara-I-Sufi Payin, Dara-I-Sufi Bala, Aibak, Khuram wa Sarbagh, Hazart Soltan | 33 | 27 | 6 |  | 787219 | 782282 | 4937 | 0 | 33 | 787219 | 0 | 19 Mod | Secure | 3182 | 783887.0742 | 74307.9333 | 62710.9659 | 846598.0401 | 920905.9735 | Bilateral | HALO Trust
117 | MBT Project-013/A | Logar Demining Project-26 (AT)/A | Planned | AT | 3,4.5 | 1393 | CA | Logar | Mohammad Agha | 9 | 0 | 9 |  | 610535 | 0 | 610535 | 0 | 9 | 610535 | 0 | 17 Sub | Secure | 1476 | 346448.6843 | 79948.3283 | 27715.8947 | 374164.5791 | 454112.9074 | DOS | MCPA
118 | MBT Project-073 | Logar Demining Project-08 (AT) | Planned | AT | 4,5 | 1393 | CA | Logar | Khoshi | 4 |  | 4 |  | 352237 | 0 | 352237 | 0 | 4 | 352237 | 0 | 8 Sub | Secure | 265 | 199877.231 | 46124.7256 | 15990.1785 | 215867.4095 | 261992.135 | DFATD | HALO Trust
119 | MBT Project-085 | Takhar Demining Project-03 | Planned | AP,AT | 1,2,3,5 | 1393 | NE | Takhar | Taluqan, Baharak, Namakab, Rustaq, Khwajaghar | 26 | 24 | 2 |  | 676168 | 643905 | 32263 |  | 26 | 676168 | 0 | 26 Mini & 19 L | Secure | 2254 | 661227.8751 | 64856.3266 | 52898.23 | 714126.1051 | 778982.4317 | DOS | MDC
120 | MBT Project-151 | Balkh Demining Project-2 (AT) | Planned | ERW | 1,3,5 | 1393 | NA | Balkh | Nahri Shahi | 11 | 0 | 0 | 11 | 1242503 | 0 | 0 | 1242503 | 11 | 1242503 | 0 | 6 Mod | Secure | 12 | 131159.3697 | 0 | 10492.7496 | 141652.1193 | 141652.1193 | SIDA | DDG
121 | MBT Project-059 | Kabul Demining Project-10 | Planned | AP | 1,2,3,5 | 1393 | CA | Kabul | Bagrami, Kabul , Khak Jabar, Paghman, Sorobi | 12 | 12 |  |  | 599181 | 599181 | 0 | 0 | 12 | 599181 | 0 | 6 L, 6 Mod | Secure | 590 | 598264.6055 | 56420.2387 | 47861.1684 | 646125.774 | 702546.0127 | DOS | ATC
122 | MBT Project-105 | Samangan Demining Project-15 | Planned | AP | 5 | 1393 | NA | Samangan | Dara-I-Sufi Bala | 7 | 7 | 0 | 0 | 262915 | 262915 |  | 0 | 7 | 262915 | 0 | 3 H, 8 Mod & 2 Sub | Secure | 167 | 262512.8947 | 24756.6713 | 21001.0316 | 283513.9263 | 308270.5976 | DOS | HALO Trust
123 | MBT Project-069 | Panjshir Demining Project-07 | Planned | AP | 4,5 | 1393 | CA | Panjshir | Shutul | 11 | 11 |  |  | 904116 | 904116 | 0 | 0 | 11 | 904116 | 0 | 10 Min | Secure | 1102 | 902733.2344 | 85133.6082 | 72218.6587 | 974951.8931 | 1060085.5013 | DOS | OMAR
124 | MBT Project-138 | Hirat Demining Project-08 (AT) | Planned | AT | 5 | 1393 | WA | Hirat | Kohsan | 4 | 0 | 4 | 0 | 786300 | 0 | 786300 | 0 | 4 | 786300 | 0 | 15 Mod | Secure | 0 | 446186.7059 | 102964.401 | 35694.9365 | 481881.6424 | 584846.0433 | NVESD | HALO Trust
125 | MBT Project-130 | Samangan Demining Project-11 | Planned | AP | 5,6 | 1393 | NA | Samangan | Ruyi Du Ab, Khuram Sarbagh | 21 | 21 |  | 0 | 491316 | 491316 |  | 0 | 21 | 491316 | 0 | 38 L | Secure | 57 | 490564.5755 | 46263.4262 | 39245.166 | 529809.7416 | 576073.1678 | SIDA | DDG
126 | MBT Project-142 | Maydan Wardak Demining Project-01 | Planned | AP | 2 | 1393 | CA | Maydan Wardak | Maydan Shahr, Nirkh | 6 | 6 |  |  | 273303 | 273303 |  | 0 | 6 | 273303 | 0 | 8 Mod, 12 H | Secure | 666 | 272885.0072 | 25734.8289 | 21830.8006 | 294715.8078 | 320450.6366 | B-Japan | MDC
127 | MBT Project-185 | Kabul new city Demining Project | Planned | AP,AT,ERW | 1,2,5 | 1393 | CA | Kabul and Parwan | Dahsabz, Koh-Safi, Bagram | 8 | 6 | 1 | 1 | 807409 | 393820 | 68402 | 345187 | 8 | 807409 | 0 |  | Secure | 328 | 468470.6179 | 46040.0864 | 37477.6494 | 505948.2674 | 551988.3537 | VTF-Japan | DDG
128 | MBT Project-074 | Logar Demining Project-09 (AT) | Planned | AP,AT,ERW | 2,3,4,5 | 1393 | CA | Logar | Khoshi, Mohmmad Agha | 37 | 22 | 14 | 1 | 5309593 | 2827579 | 2481873 | 141 | 37 | 5309593 | 0 | 7 H | Secure | 2389 | 4231610.6185 | 591247.5059 | 338528.8495 | 4570139.468 | 5161386.9739 | Bilateral | HALO Trust
129 | MBT Project-055/A | Parwan Demining Project-08/A | Planned | AP | 3 | 1393 | CA | Parwan | Bagram | 1 | 1 |  |  | 4649 | 4649 |  |  | 1 | 4649 | 0 | 23 Sub | Secure | 629 | 4641.8898 | 437.7604 | 371.3512 | 5013.2409 | 5451.0013 | B-Japan | ATC
130 | MBT Project-232 | Kabul Demining Project-21 | Planned | AP,ERW | 3,5 | 1393 | CA | Kabul | Kabul , Sorobi | 8 | 7 |  | 1 | 785023 | 748297 | 0 | 36726 | 7 | 748297 | 36726 |  | Secure | 526 | 751029.3646 | 70461.3386 | 60082.3492 | 811111.7137 | 881573.0524 | B-Japan | ATC
131 | MBT Project-008/B | Kabul Demining Project-05/B | Planned | AP | 4 | 1393 | CA | Kabul | Khake Jabar | 13 | 13 |  |  | 856444 | 856444 |  |  | 13 | 856444 | 0 |  | Secure | 1378 | 855134.1445 | 80644.7049 | 68410.7316 | 923544.876 | 1004189.5809 | DOS | OMAR
132 | MBT Project-015/A | Logar Demining Project-06/A | Planned | AT | 4 | 1393 | CA | Logar | M. Agha | 2 |  | 2 |  | 2916704 |  | 2916704 |  | 2 | 2916704 | 0 |  | Secure | 312 | 1655086.5443 | 381936.513 | 132406.9235 | 1787493.4679 | 2169429.9809 | GOV of Af | MDC
133 | MBT Project-044/A | Nangarhar Demining Project-01/A | Planned | AP,AT,ERW | 1,2,3,4,5 | 1393 | EA | Nangarhar | Acheen, Chaparhar, Kot, Rodat, Surkh Rod | 14 | 1 | 11 | 2 | 1372910 | 128802 | 1034306 | 209802 | 14 | 1372910 | 0 |  | Secure | 3522 | 737669.7887 | 147568.5748 | 59013.5831 | 796683.3718 | 944251.9466 | DOS | MDC
134 | MBT Project-026/A | Badakhshan Demining Project-01/A | Planned | AP,UXO | 3,4,5 | 1393 | NE | Badakhshan | Argo & Faiz Abad | 7 | 7 |  |  | 174976 | 174976 |  |  | 7 | 174976 | 0 |  | Secure | 264 | 174708.3896 | 16476.1361 | 13976.6712 | 188685.0608 | 205161.1969 | Bilateral | HALO Trust
135 | MBT Project-027/A | Baghlan Demining Project-01/A | Planned | AP | 1,2,3,5 | 1393 | NE | Baghlan | Dushi, Khenjan, Tala wa Barfak & Puli khumry | 12 | 12 |  |  | 717495 | 717495 |  |  | 12 | 717495 | 0 |  | Secure | 1236 | 716397.6547 | 67560.9526 | 57311.8124 | 773709.4671 | 841270.4197 | Bilateral | HALO Trust
136 | MBT Project-027/B | Baghlan Demining Project-01/B | Planned | AP | 2 | 1393 | NE | Baghlan | Tala Wa Barfak | 3 | 3 |  |  | 230800 | 230800 | 0 | 0 | 3 | 230800 | 0 |  | Secure | 18 | 230447.0118 | 21732.6502 | 18435.7609 | 248882.7727 | 270615.4229 | GAGP | HALO Trust
137 | MBT Project-059/A | Kabul Demining Project-10/A | Planned | AP,UXO | 3,4,5 | 1393 | CA | Kabul | Bagrami, Kabul | 3 | 1 |  | 2 | 1151674 | 294100 |  | 857574 | 3 | 1151674 | 0 |  | Secure | 300 | 384176.2312 | 27693.1214 | 30734.0985 | 414910.3297 | 442603.4511 | DOS | ATC
138 | MBT Project-112/A | Panjshir Demining Project-06/A | Planned | AP | 3,4 | 1393 | CA | Panjshir | Rukha | 8 | 8 |  |  | 558306 | 558306 |  |  | 8 | 558306 | 0 |  | Secure | 2911 | 557452.1202 | 52571.3562 | 44596.1696 | 602048.2899 | 654619.6461 | DOS | DDG
139 | MBT Project-114/B | Logar Demining Project-19 (AT)/B | Planned | AT | 1,5 | 1393 | CA | Logar | Khoshi | 5 |  | 5 |  | 496557 |  | 496557 |  | 5 | 496557 | 0 |  | Secure | 1825 | 281771.7565 | 65023.1388 | 22541.7405 | 304313.497 | 369336.6358 | DOS | DAFA
140 | MBT Project-075/A | Logar Demining Project-10 (AT)/A | Planned | AP | 2 | 1393 | CA | Logar | M. Agha | 7 | 7 |  |  | 1087602 | 1087602 |  |  | 7 | 1087602 | 0 |  | Secure | 457 | 1085938.6087 | 102411.0652 | 86875.0887 | 1172813.6974 | 1275224.7626 | DOS | OMAR
141 | MBT Project-121/E | Baghlan Demining Project-15/E | Planned | AP | 5 | 1393 | NE | Baghlan | Dushi and Nahrin | 3 | 3 |  |  | 36360 | 36360 |  |  | 3 | 36360 | 0 |  | Secure | 6 | 36304.3906 | 3423.7399 | 2904.3512 | 39208.7418 | 42632.4817 | AAR Japan | HALO Trust
142 | MBT Project-121/F | Baghlan Demining Project-15/F | Planned | AP,UXO | 3,4,5 | 1393 | NE | Baghlan | Dushi | 4 | 2 |  | 2 | 538500 | 36500 |  | 502000 | 4 | 538500 | 0 |  | Secure | 809 | 89435.6007 | 3436.9226 | 7154.8481 | 96590.4488 | 100027.3714 | DOS | HALO Trust
143 | MBT Project-062/B | Kabul Demining Project-14 /A | Planned | AP | 1,5 | 1393 | CA | Kabul | Guldara | 4 | 4 |  |  | 155705 | 155705 |  |  | 4 | 155705 | 0 |  | Secure | 63 | 155466.8629 | 14661.5351 | 12437.349 | 167904.212 | 182565.7471 | DOS | HALO Trust
144 | MBT Project-223/B | Kabul Demining Project-08/B | Planned | AP,AT,ERW | 1,2,3,4,5 | 1393 | CA | Kabul | Khaki Jabbar, Paghman | 13 | 10 | 1 | 2 | 571258 | 403953 | 10943 | 156362 | 13 | 571258 | 0 |  | Secure | 1984 | 426050.4731 | 39470.0923 | 34084.0378 | 460134.5109 | 499604.6032 | DANIDA | DDG
145 | MBT Project-181/E | Nangarhar Demining Project-02/E | Planned | AP,AT,ERW | 1,2,5 | 1393 | EA | Nangarhar | Chaparhar, Pachier Agam, Shinwar,Muhmand Dara | 18 | 3 | 14 | 1 | 1938808 | 237811 | 1700955 | 42 | 18 | 1938808 | 0 |  | Secure | 7663 | 1202660.305 | 245129.4525 | 96212.8244 | 1298873.1294 | 1544002.5818 | VTF-Australia | MCPA
146 | MBT Project-223/A | Kabul Demining Project-08 /A | Planned | AP | 4 | 1393 | CA | Kabul | Qarabagh,Shakardara | 3 | 3 |  |  | 112950 | 112950 |  |  | 3 | 112950 | 0 |  | Secure | 711 | 112777.2529 | 10635.6276 | 9022.1802 | 121799.4332 | 132435.0607 | Bilateral | HALO Trust
147 | MBT Project-127 | Balkh Demining Project-3 | Planned | AP,AT | 4,5 | 1393 | NA | Balkh | Chaharkent | 7 | 6 | 1 | 0 | 329334 | 179334 | 150000 | 0 | 7 | 329334 | 0 | 1 L, 27 Mod | Secure | 85 | 264177.3715 | 36528.693 | 21134.1897 | 285311.5613 | 321840.2543 | Bilateral | HALO Trust
148 | MBT Project-127/A | Balkh Demining Project-3/A | Planned | UXO | 3 | 1393 | NA | Balkh | Chahar Kint | 1 |  |  | 1 | 41522 |  |  | 41522 | 1 | 41522 | 0 |  | Secure | 13 | 4383.0875 | 0 | 350.647 | 4733.7345 | 4733.7345 | DOS | HALO Trust
149 | MBT Project-127/B | Balkh Demining Project-3/B | Planned | AP | 2,3,4,5 | 1393 | NA | Balkh | Chahar Kint | 23 | 23 | 0 | 0 | 338087 | 338087 | 0 | 0 | 23 | 338087 | 0 |  | Secure | 1034 | 337569.9258 | 31835.0369 | 27005.5941 | 364575.5198 | 396410.5567 | B-Germany | HALO Trust
150 | MBT Project-057/A | Kabul Demining Project-03 /A | Planned | AP | 1,4,5 | 1393 | CA | Kabul | Paghman, Surobi | 4 | 4 |  |  | 226812 | 226812 |  |  | 4 | 226812 | 0 |  | Secure | 245 | 226465.1111 | 21357.1311 | 18117.2089 | 244582.3199 | 265939.4511 | DOS | DAFA
151 | MBT Project-307/A | Bamyan Demining Project-01/A | Planned | AP | 5 | 1393 | CA | Bamyan | Sayghan | 2 | 2 |  |  | 32940 | 32940 |  |  | 2 | 32940 | 0 |  | Secure | 94 | 32889.6212 | 3101.7049 | 2631.1697 | 35520.7909 | 38622.4958 | Bilateral | HALO Trust
152 | MBT Project-045 | Paktya Demining Project-03 | Planned | AP,AT | 1,2,3 | 1393 | SE | Paktya | Gardiz | 7 | 3 | 4 |  | 395901 | 210677 | 185224 |  | 7 | 395901 | 0 | 20 Sub | Secure | 366 | 315460.3285 | 44092.5327 | 25236.8263 | 340697.1548 | 384789.6875 | B-Germany | HALO Trust
153 | MBT Project-126/A | Takhar Demining Project-07/A | Planned | AP | 5 | 1393 | NE | Takhar | Namak Ab | 16 | 16 | 0 | 0 | 339620 | 339620 |  | 0 | 16 | 339620 | 0 | 21 Sub | Secure | 460 | 339100.5812 | 31979.3876 | 27128.0465 | 366228.6277 | 398208.0153 | GAGP | HALO Trust
154 | MBT Project-203 | Khost Demining Project-02 | Planned | AP,AT | 1,5 | 1393 | SE | Khost | Gurbuz | 27 | 12 | 15 |  | 1851569 | 753697 | 1097872 | 0 | 27 | 1851569 | 0 | 1 H, 8 Sub | Secure | 4080 | 1375532.8297 | 214733.9416 | 110042.6264 | 1485575.4561 | 1700309.3976 | Bilateral | Halo Trust
155 | MBT Project-059/B | Kabul Demining Project-10/B | Planned | AP | 1,4,5 | 1393 | CA | Kabul | Guldara & Kalakan | 4 | 4 |  |  | 116863 | 116863 |  |  | 4 | 116863 | 0 |  | Secure | 534 | 116684.2684 | 11004.0845 | 9334.7415 | 126019.0098 | 137023.0943 | B-Germany | HALO Trust
156 | MBT Project-111 | Panjshir Demining Project-04 | Pledged | AP,AT, ERW | 1,3,5 | 1393 | CA | Panjshir | Khenj (Hese- Awal) | 25 | 16 | 8 | 1 | 1668720 | 1408466 | 260250 | 4 | 21 | 1576966 | 91754 | 21 Min | Secure | 502 | 1553991.4154 | 166703.5586 | 124319.3132 | 1678310.7287 | 1845014.2873 | DOS |  | Reserved for WRA (DOS) 1394 fund
157 | MBT Project-251 | Nangarhar Demining Project-04 | Pledged | AP,AT,ERW | 1,2,3,4,5,6 | 1393 | EA | Nangarhar | Achin, Bahsud, Chaprahar, Dahbala, Hesarak, Khugyani,Kot, Momadara, Nazian, Pachir Agam, Surkhroad,Dur Baba,Deh Bala,Kama | 90 | 21 | 58 | 11 | 11056374 | 1107062 | 5750242 | 4199070 | 79 | 8734834 | 2321540 | 49 H, 16 Sub | Secure | 25398 | 4811605.6808 | 857226.0687 | 384928.4545 | 5196534.1353 | 6053760.204 | DOS |  | Reserved for WRA (DOS) 1394 fund
158 | MBT Project-028 | Baghlan Demining Project-09 | Pledged | AP, ERW | 2,3 | 1393 | NE | Baghlan | Khinjan | 32 | 31 |  | 1 | 2924858 | 2881026 | 0 | 43832 | 28 | 2836134 | 88724 | 30 L | secure | 4174 | 2881246.6574 | 271283.9268 | 230499.7326 | 3111746.39 | 3383030.3169 | DOS |  | Reserved for WRA (DOS) 1394 fund
159 | MBT Project-003 | Parwan Demining Project-03 | Pledged | AP,AT,ERW | 1,2,3,4,5 | 1393 | CA | Parwan | Bagram, Charikar and Salang | 45 | 39 | 2 | 4 | 1720697 | 1577013 | 40115 | 103569 | 31 | 952402 | 768295 | 80 Min | Secure | 17636 | 1608297.2003 | 153748.0907 | 128663.776 | 1736960.9763 | 1890709.067 | DOS |  | Reserved for WRA (DOS) 1394 fund
160 | MBT Project-010 | Kapisa Demining Project-01 | Pledged | AP,AT | 1,2,3 | 1393 | CA | Kapisa | Hisa-i-Awali Kohistan, Mahmudi raqi | 17 | 13 | 4 |  | 1264809 | 1222193 | 42616 | 0 | 17 | 1264809 | 0 | 9 Min, 6 Mod | Secure | 4350 | 1244506.2546 | 120664.9376 | 99560.5004 | 1344066.755 | 1464731.6926 | DOS |  | Reserved for WRA (DOS) 1393 fund
161 | MBT Project-201 | Nangarhar Demining Project-03 | Open | AT | 1 | 1393 | EA | Nangarhar | Pachir Agam | 3 |  | 3 |  | 414146 | 0 | 414146 | 0 |  |  | 414146 | 4 H, 5 Sub | Secure | 742 | 235007.5537 | 54231.5844 | 18800.6043 | 253808.158 | 308039.7424
162 | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) | Open | AP.AT | 1,2 | 1393 | CA | Maydan Wardak | Chaki Wardak & Saydabad | 11 |  | 11 |  | 848106 | 93477 | 754629 | 0 |  |  | 848106 | 4 H, 7 Sub | Secure | 3606 | 521549.0011 | 107619.1532 | 41723.9201 | 563272.9211 | 670892.0743
163 | MBT Project-269/A | Zabul Demining Project-01/A | Open | AT,ERW | 1,2 | 1393 | SA | Zabul | Tarnak Wa Jaldak, Qalat | 5 |  | 3 | 2 | 2556111 | 0 | 1268736 | 1287375 |  |  | 2556111 | 3 H | secure | 825 | 855841.5723 | 166138.4233 | 68467.3258 | 924308.8981 | 1090447.3214
164 | MBT Project-181 | Nangarhar Demining Project-02 | Open | AP,AT,ERW | 1,2,3 | 1393 | EA | Nangarhar | Chaparhar, Pachir Wa Agam, Rodat | 14 | 6 | 6 | 2 | 987846 | 528658 | 458813 | 375 |  |  | 987846 | 2 S, 25 H | Secure | 6256 | 788242.9361 | 109860.2715 | 63059.4349 | 851302.371 | 961162.6425
165 | MBT Project-186 | Kandahar Demining Project-03 | Open | AP,AT,ERW | 1,2,3 | 1393 | SA | Kandahar | Daman, Kandhar | 10 | 4 | 1 | 5 | 2170813 | 108787 | 5141 | 2056885 |  |  | 2170813 | 15 H | secure | 283 | 328663.9126 | 10916.8337 | 26293.113 | 354957.0256 | 365873.8592
166 | MBT Project-309 | Good Neighbor project | Open | AP, ERW | 1,2,3 | 1393 | CA | Parwan | Bagram | 9 | 7 |  | 2 | 169557 | 125953 |  | 43604 |  |  | 169557 | 12 Mod | Secure | 5927 | 130363.2307 | 11860.0195 | 10429.0585 | 140792.2891 | 152652.3086
167 | MBT Project-305 | Kandahar Demining Project-06 AT | Open | AP,AT,ERW | 1,2,3 | 1394 | SA | Kandahar | Arghistan | 17 | 6 | 7 | 4 | 2322672 | 476854 | 1078418 | 767400 |  |  | 2322672 | 27 H | Secure | 893 | 1169081.2543 | 171923.4687 | 140289.7505 | 1309371.0049 | 1481294.4736
168 | MBT Project-027 | Baghlan Demining Project-01 | Open | AP | 1,2,3 | 1394 | NE | Baghlan | Tala Wa Barfak | 11 | 11 |  |  | 608922 | 608922 | 0 | 0 |  |  | 608922 | 14 Sub | secure | 1141 | 607990.7075 | 85347.9971 | 72958.8849 | 680949.5924 | 766297.5895
169 | MBT Project-088 | Saripul Demining Project-1 | Open | AP,AT,ERW | 1,2,3,4,5 | 1394 | NA | Saripul | Gosfandi, Saripul,Sangcharak,Balkhab & Sayyad | 53 | 47 | 3 | 3 | 1869606 | 1815933 | 40262 | 13411 |  |  | 1869606 | 32 L, 1 Mod, 6 Sub | Secure | 3580 | 1837418.0754 | 258448.9422 | 220490.169 | 2057908.2444 | 2316357.1866
170 | MBT Project-009 | Kabul Demining Project-06 | Open | AP,AT,ERW | 1,2,3,4,5 | 1394 | CA | Kabul | Surobi | 23 | 19 | 3 | 1 | 1519302 | 1453265 | 65592 | 445 |  |  | 1519302 | 8 Sub | Secure | 1212 | 1488309.5786 | 210084.7901 | 178597.1494 | 1666906.728 | 1876991.5181
171 | MBT Project-121 | Baghlan Demining Project-15 | Open | AP, ERW | 1,2,3,4,5 | 1394 | NE | Baghlan | Dushi, Khenjan, Pulikhumri | 56 | 52 |  | 4 | 3263426 | 2619426 | 0 | 644000 |  |  | 3263426 | 54 L | Secure | 4000 | 2683400.8494 | 367145.1559 | 322008.1019 | 3005408.9513 | 3372554.1072 |  |  | Reserved for WRA (DOS) 1394 fund
172 | MBT Project-039 | Jawzjan Demining Project-1 | Open | AP,AT,ERW | 1,2,3,4,5 | 1394 | NA | Jawzjan | Khvajeh Do Kuh Now, Sheberghan, Qustapa, Mardian | 15 | 4 | 4 | 7 | 722165 | 197153 | 124095 | 400917 |  |  | 722165 | 2 H, 3 L | Secure | 1579 | 309590.3428 | 39725.8845 | 37150.8411 | 346741.1839 | 386467.0684
173 | MBT Project-051 | Paktya Demining Project-02 AT | Open | AP,AT,ERW | 1,2,3,4,5 | 1394 | SE | Paktya | Gardiz, AhmadAbad | 14 | 1 | 11 | 2 | 793288 | 88182 | 704820 | 286 |  |  | 793288 | 4 Sub | Secure | 4066 | 488028.1237 | 81040.9921 | 58563.3748 | 546591.4986 | 627632.4907
174 | MBT Project-068 | Panjshir Demining Project-05 | Open | AP,AT,ERW | 1,2,3,5 | 1394 | CA | Panjshir | Paryan, Bazarak,Rukha | 102 | 97 | 1 | 4 | 5020184 | 4557265 | 10350 | 452569 |  |  | 5020184 | 60 Min | Secure | 1818 | 4603941.6409 | 639765.9664 | 552472.9969 | 5156414.6378 | 5796180.6041
175 | MBT Project-100/A | Khost Demining Project-05/A | Open | AP,AT | 1,2,3,5 | 1394 | SE | Khost | Tani, Matun | 17 | 12 | 1 | 4 | 2223985 | 447484 | 110317 | 1666184 |  |  | 2223985 | 4 H, 6 Ext | Secure | 1109 | 685282.4954 | 73470.2925 | 82233.8994 | 767516.3948 | 840986.6873
176 | MBT Project-001/A | Parwan Demining Project-01/A | Open | AP,AT | 1,2,3,5 | 1394 | CA | Parwan | Bagram,Salang, Shenwari and Charikar | 19 | 18 | 1 | 0 | 915528 | 915077 | 451 | 0 |  |  | 915528 |  | Secure | 1181 | 913933.3909 | 128303.3785 | 109672.0069 | 1023605.3978 | 1151908.7763
177 | MBT Project-037/B | Balkh Demining Project-1/B | Open | AP,AT,ERW | 1,2,3,5 | 1394 | NA | Balkh | Shortepa, Shahrak Hairatan, Nahreshahi & Khulm | 18 | 14 | 3 | 1 | 1026896 | 553755 | 391127 | 82014 |  |  | 1026896 | 10 Mod | secure | 478 | 783510.9277 | 115729.0272 | 94021.3113 | 877532.2391 | 993261.2663 |  |  | Reserved for Japan fund 1394
178 | MBT Project-184 | Kandahar Demining Project-04 AT | Open | AT | 1,2,3,5 | 1394 | SA | Kandahar | Arghandab | 16 |  | 16 |  | 1171662 | 0 | 1171662 | 0 |  |  | 1171662 | 7 H | Secure | 2182 | 664860.7506 | 114172.6075 | 79783.2901 | 744644.0407 | 858816.6482 |  |  | Reserved for Japan fund 1394
179 | MBT Project-271 | Hilmand Demining Project-05 AT | Open | AT | 1,2,4 | 1394 | SA | Hilmand | Nahri Sarraj, Nad Ali, Lashkar Gah | 12 | 0 | 12 |  | 2271567 | 0 | 2271567 | 0 |  |  | 2271567 | 14 H | Secure | 2932 | 1289002.9212 | 221352.8539 | 154680.3505 | 1443683.2717 | 1665036.1256
180 | MBT Project-136 | Kandahar Demining Project-01 | Open | AP,AT | 1,2,5 | 1394 | SA | Kandahar | Zhari | 22 | 1 | 21 |  | 5215955 | 80000 | 5135955 | 0 |  |  | 5215955 | 12 H | Secure | 279 | 2994280.3471 | 511686.1478 | 359313.6416 | 3353593.9887 | 3865280.1365
181 | MBT Project-099 | Paktya Demining Project-02 | Open | AP,AT | 1,2,5 | 1394 | SE | Paktya | Ali Khail (Jaji) | 9 | 7 | 2 |  | 381395 | 330594 | 50801 |  |  |  | 381395 | 7 Sub | Secure | 6809 | 358915.4629 | 51287.1674 | 43069.8555 | 401985.3185 | 453272.4858
182 | MBT Project-256/B | Paktya Demining Project-07/B | Open | AP,AT | 1,3,4,5 | 1394 | SE | Paktya | Ali Khail (Jaji), Laja Ahmad Khail,Chamkani,Jani Khail | 17 | 12 | 3 | 2 | 585887 | 551906 | 33781 | 200 |  |  | 585887 | 7 Sub | Secure | 22784 | 570252.0822 | 80648.2847 | 68430.2499 | 638682.332 | 719330.6167
183 | MBT Project-223 | Kabul Demining Project-08 | Open | AP,ERW | 1,3,4,5 | 1394 | CA | Kabul | Charasyab, Paghman | 8 | 6 | 0 | 2 | 390517 | 384683 | 0 | 5834 |  |  | 390517 | 10 Mod | Secure | 1169 | 384710.5019 | 53918.1103 | 46165.2602 | 430875.7621 | 484793.8724
184 | MBT Project-236 | Nimroz Demining Project-02 | Open | AP,AT | 1,3,4,5 | 1394 | SA | Nimroz | Chahar Burjak | 19 | 10 | 9 |  | 5299671 | 1833039 | 3466632 | 0 |  |  | 5299671 | 3 Sub | Secure | 2448 | 3797379.2556 | 594729.1971 | 455685.5107 | 4253064.7663 | 4847793.9634
185 | MBT Project-307 | Bamyan Demining Project-01 | Open | AP | 1,3,4,5 | 1394 | CA | Bamyan | Bamyan,Kahmard, Shibar | 20 | 20 |  |  | 410354 | 410354 |  | 0 |  |  | 410354 | 13 Lwo | Secure | 1763 | 409726.3998 | 57516.2205 | 49167.168 | 458893.5677 | 516409.7882 |  |  | Reserved for Japan fund 1394
186 | MBT Project-020/A | Kabul Demining Project-02 (AT)/A | Open | AP,AT,ERW | 1,3,5 | 1394 | CA | Kabul | Khak-i-jabar, Shakardara, Kabul | 9 | 3 |  | 6 | 958762 | 54580 |  | 904182 |  |  | 958762 | 10 Mod, 13 Sub | Secure | 167451 | 149942.5246 | 7650.0663 | 17993.103 | 167935.6276 | 175585.6939
187 | MBT Project-096 | Samangan Demining Project-14 | Open | AP,AT,ERW | 1,3,4,5,6 | 1394 | NA | Samangan | Feroz Nakhchir, Ruyi Du Ab, Darasuf Bala, Darasuf Payan | 41 | 36 | 4 | 1 | 1020550 | 997480 | 23070 |  |  |  | 1020550 | 18 Mod | Secure | 587 | 1009045.5365 | 142057.2931 | 121085.4644 | 1130131.0008 | 1272188.294
188 | MBT Project-181/C | Nangarhar Demining Project-02/C | Open | AP,AT | 1,3,4,5,6 | 1394 | EA | Nangarhar | Chaparhar, Rodat,Kot, Hesarak, Nazian | 18 | 7 | 11 |  | 1970169 | 636002 | 1334167 |  |  |  | 1970169 |  | Secure | 2464 | 1392103.6632 | 219151.5039 | 167052.4396 | 1559156.1028 | 1778307.6067
189 | MBT Project-280 | Khost Demining Project-03 | Open | AP | 1,4,5 | 1394 | SE | Khost | Nadir Shah Kot, Shamal, | 16 | 16 |  |  | 824226 | 824226 | 0 | 0 |  |  | 824226 | 14 Ext | Secure | 2494 | 822965.4191 | 115525.5324 | 98755.8503 | 921721.2693 | 1037246.8018 |  |  | Reserved for Japan fund 1394
190 | MBT Project-225 | NangaharDemining Project-05 | Open | AP,AT,ERW | 1,4,5,6 | 1394 | EA | Nangarhar | Khugyani, Kot, Nazyan,Hesarak | 32 | 7 | 12 | 13 | 4556224 | 643418 | 1658713 | 2254093 |  |  | 4556224 | 12 H, 5 Sub | secure | 9386 | 1821615.6902 | 251816.3347 | 218593.8828 | 2040209.573 | 2292025.9076
191 | MBT Project-006 | Kabul Demining Project-02 | Open | AP, ERW | 2 | 1394 | CA | Kabul | Khaki Jabar | 3 | 3 |  | 0 | 199680 | 199680 | 0 | 0 |  |  | 199680 | 7 Mod | Secure | 69 | 199374.6071 | 27987.6373 | 23924.9528 | 223299.5599 | 251287.1972 |  |  | Reserved for Japan fund 1394
192 | MBT Project-025 | Logar Demining Project-04 (AT) | Open | AT,ERW | 2 | 1394 | CA | Loger | Puli Alam | 5 | 0 | 5 | 0 | 351802 | 0 | 351802 |  |  |  | 351802 | 15 H | Secure | 743 | 199630.3898 | 34281.3471 | 23955.6468 | 223586.0366 | 257867.3836
193 | MBT Project-161/A | Hilmand Demining Project-01/A | Open | AP,AT,ERW | 2 | 1394 | SA | Hilmand | Kajaki, Musa Qala | 15 | 1 | 11 | 3 | 1693034 | 90000 | 1237500 | 365534 |  |  | 1693034 | 7 H, 7 Ext | Secure | 2279 | 830668.9318 | 133202.8118 | 99680.2718 | 930349.2036 | 1063552.0153
194 | MBT Project-135 | Kandahar Demining Project-10 | Open | AT | 2 | 1394 | SA | Kandahar | Zhari | 1 |  | 1 |  | 14622500 | 0 | 14622500 | 0 |  |  | 14622500 | 4 H | Secure | 97 | 8297551.9608 | 1424889.5612 | 995706.2353 | 9293258.1961 | 10718147.7573
195 | MBT Project-071 | Logar Demining Project-06 (AT) | Open | AP,AT,ERW | 2,3 | 1394 | CA | Loger | Mohammad Agha | 20 | 3 | 9 | 8 | 2164088 | 303400 | 1349798 | 510890 |  |  | 2164088 | 13 Sub | Secure | 4110 | 1122810.0329 | 174056.3568 | 134737.204 | 1257547.2369 | 1431603.5937
196 | MBT Project-032 | Kunduz Demining Project-01 | Open | AP,AT,ERW | 2,3 | 1394 | NE | Kunduz | Khanabad | 10 | 4 | 2 | 4 | 95211 | 11734 | 83477 | 0 |  |  | 95211 | 7 Sub | Secure | 3282 | 59085.1594 | 9779.0827 | 7090.2191 | 66175.3785 | 75954.4612 |  |  | Reserved for Japan fund 1394
197 | MBT Project-164 | Hilmand Demining Project-05 | Open | AP | 2,3 | 1394 | SA | Hilmand | Kajaki | 7 | 7 |  |  | 1480074 | 1480074 |  | 0 |  |  | 1480074 | 10 H | Secure | 239 | 1477810.3574 | 207450.7925 | 177337.2429 | 1655147.6003 | 1862598.3928
198 | MBT Project-041 | Samangan Demining Project-10 | Open | AP,ERW | 2,3,4 | 1394 | NA | Samangan | Ruyi Du Ab | 20 | 16 | 0 | 4 | 518046 | 518009 | 0 | 37 |  |  | 518046 | 14 L | Secure | 1476 | 517220.6567 | 72605.4086 | 62066.4788 | 579287.1355 | 651892.5441
199 | MBT Project-054 | Parwan Demining Project-05 | Open | AP | 2,3,4 | 1394 | CA | Parwan | Shinwari & Siagird | 42 | 42 |  |  | 1686973 | 1686973 | 0 | 0 |  |  | 1686973 | 35 Sub | Secure | 13113 | 1684392.9236 | 236450.2624 | 202127.1508 | 1886520.0745 | 2122970.3369
200 | MBT Project-019 | Kabul Demining Project-01 (AT) | Open | AP, AT | 2,3,4,5 | 1394 | CA | Kabul | Khaki jabar, Musayi | 11 | 9 | 2 |  | 1442674 | 1191479 | 251195 | 0 |  |  | 1442674 | 5 Mod | Secure | 1104 | 1332197.587 | 191478.3089 | 159863.7104 | 1492061.2975 | 1683539.6064
201 | MBT Project-165 | Kandahar Demining Project-09 | Open | AT | 2,3,4,5 | 1394 | SA | Kandahar | Panjwayi | 9 | 0 | 9 |  | 2911128 |  | 2911128 | 0 |  |  | 2911128 | 3 H | Secure | 5449 | 1651922.4376 | 283674.8777 | 198230.6925 | 1850153.1302 | 2133828.0078
202 | MBT Project-245 | Faryab Demining Project-2 | Open | AP, AT,ERW | 2,3,4,5 | 1394 | NA | Faryab | Shirin Tagab, Pashtun Kot, Dulatabad, Maimana, Qurghan & Almar | 12 | 1 | 8 | 3 | 289279 | 121566 | 162717 | 4996 |  |  | 289279 | 1 L, 7 Mod, 1 H | Secure | 3046 | 214241.3775 | 32894.9465 | 25708.9653 | 239950.3428 | 272845.2893 |  |  | Reserved for Japan fund 1394
203 | MBT Project-128 | Samangan Demining Project-2 | Open | AP,AT,ERW | 2,3,4,5 | 1394 | NA | Samangan | Aybak, Firoz Nakhchir & Hazrat Sultan, Khuram wa Sarbagh | 18 | 12 | 5 | 1 | 1224796 | 708755 | 514691 | 1350 |  |  | 1224796 | 24 L | Secure | 1194 | 999875.4411 | 149494.9008 | 119985.0529 | 1119860.4941 | 1269355.3949
204 | MBT Project-124 | Kunduz Demining Project-03 | Open | AP,AT,ERW | 2,3,4,5 | 1394 | NE | Kunduz | Chahar Dara, Ali Abad and Kunduz | 14 | 4 | 2 | 8 | 442030 | 105990 | 299614 | 36426 |  |  | 442030 | 7 Sub | Secure | 13483 | 279689.3063 | 44051.7049 | 33562.7168 | 313252.0231 | 357303.728 |  |  | Reserved for Japan fund 1394
205 | MBT Project-153 | Kunduz Demining Project-04 | Open | AP,AT | 2,3,5 | 1394 | NE | Kunduz | Dasht-i-Archi, Imam Sahib | 18 | 10 | 8 |  | 927092 | 695116 | 231976 | 0 |  |  | 927092 | 19 Sub | Secure | 341 | 825687.89 | 120034.0611 | 99082.5468 | 924770.4368 | 1044804.4979
206 | MBT Project-109 | Parwan Demining Project-09 | Open | AP | 2,3,5 | 1395 | CA | Parwan | Shikh Ali, | 36 | 36 |  |  | 2051747 | 2051747 | 0 | 0 |  |  | 2051747 | 1 L, 7 Min, 31 Sub | Secure | 1650 | 2048609.034 | 316269.4474 | 327777.4454 | 2376386.4794 | 2692655.9268
207 | MBT Project-171 | Kunar Demining Project-02 | Open | AP,ERW | 2,3,4,5 | 1395 | EA | Kunar | Khaskunar, Narang, Shaygal wa Shital | 6 | 4 |  | 2 | 1198751 | 364442 |  | 834309 | 6 |  | 1198751 | 4 Sub | Secure | 1347 | 451954.7818 | 56177.4283 | 72312.7651 | 524267.5469 | 580444.9752
208 | MBT Project-268 | Kandahar Demining Project-08 | Open | AP,AT,ERW | 2,3,5 | 1395 | SA | Kandahar | Ghorak, Khakrez | 13 | 2 | 10 | 1 | 2393164 | 243868 | 2088915 | 60381 |  |  | 2393164 | 3 S | Secure | 1509 | 1435225.7451 | 292944.3379 | 229636.1192 | 1664861.8643 | 1957806.2022
209 | MBT Project-094 | Balkh Demining Project-1 (AT) | Open | AP,AT,ERW | 2,3,5 | 1395 | NA | Balkh | Keshendai Balkh, khulm,Kaldar,Shulgara, Zari | 21 | 14 | 7 | 0 | 638632 | 423348 | 215284 |  |  |  | 638632 | 24 Mod | Secure | 4018 | 544863.6435 | 91574.3045 | 87178.183 | 632041.8264 | 723616.1309
210 | MBT Project-134 | Badakhshan Demining Project-04 | Open | AP,ERW | 2,3,5 | 1395 | NE | Badakhshan | Argo, Fiazabad,Kuran Wa Munjan | 15 | 14 |  | 1 | 680256 | 680254 | 0 | 2 |  |  | 680256 | 13 Min,5 Mod | Secure | 950 | 679213.8227 | 104858.7163 | 108674.2116 | 787888.0343 | 892746.7506
211 | MBT Project-126 | Takhar Demining Project-07 | Open | AP,ERW | 2,3,4,5,6 | 1395 | NE | Takhar | Farkhar,Ishkmesh, Namkab | 46 | 44 |  | 2 | 1160572 | 1160491 | 0 | 81 |  |  | 1160572 | 29 L | Secure | 684 | 1158724.6818 | 178885.5289 | 185395.9491 | 1344120.6309 | 1523006.1598 |  |  | Reserved for WRA (DOS) 1394 fund
212 | MBT Project-085/A | Takhar Demining Project-03/A | Open | AP,ERW | 2,4,5 | 1395 | NE | Takhar | Khwajaghar | 12 | 3 |  | 9 | 2797534 | 89386 |  | 2708148 |  |  | 2797534 | 26 Mini & 19 L | Secure | 1781 | 375123.0362 | 13778.5316 | 60019.6858 | 435142.722 | 448921.2535
213 | MBT Project-084 | Kunduz Demining Project-02 | Open | AP,AT,ERW | 2,4,5 | 1395 | NE | Kunduz | Khanabad | 72 | 63 | 5 | 4 | 1063174 | 1039594 | 23580 | 0 |  |  | 1063174 | 67 Sub | Secure | 3797 | 1051384.5268 | 163132.1538 | 168221.5243 | 1219606.0511 | 1382738.205
214 | MBT Project-072 | Logar Demining Project-07 (AT) | Open | AT,ERW | 3 | 1395 | CA | Loger | Mohammad Agha | 17 | 0 | 16 | 1 | 1625053 | 0 | 1623481 | 1572 |  |  | 1625053 | 18 Sub | Secure | 2338 | 921411.8264 | 198457.4184 | 147425.8922 | 1068837.7186 | 1267295.137
215 | MBT Project-014 | Logar Demining Project-27 (AT) | Open | AP,AT | 3 | 1395 | CA | Loger | Mohammad Agha, Pul-e-Alam | 12 | 1 | 11 |  | 1268469 | 441 | 1268028 | 0 |  |  | 1268469 | 1 High, 12 Sub | Secure | 1691 | 719984.0573 | 155074.1433 | 115197.4492 | 835181.5065 | 990255.6498
216 | MBT Project-178 | Logar Demining Project-02 | Open | AP,AT,ERW | 3 | 1395 | CA | Loger | Pulli Alam, Khoshi | 8 | 3 | 4 | 1 | 661363 | 211448 | 448265 | 1650 |  |  | 661363 | 2 H, 1 S | Secure | 3250 | 465667.1977 | 87390.7213 | 74506.7516 | 540173.9493 | 627564.6706
217 | MBT Project-162 | Hilmand Demining Project-03 | Open | AP,AT | 3,4 | 1395 | SA | Hilmand | Nahri Sarraj | 5 | 2 | 3 |  | 1035000 | 210000 | 825000 | 0 |  |  | 1035000 | 5 H | Secure | 2170 | 677825.8824 | 133220.3233 | 108452.1412 | 786278.0235 | 919498.3468
218 | MBT Project-016 | Maydan Wardak Demining Project-10 | Open | AP,ERW | 3,4 | 1395 | CA | Maydan Wardak | Day Mirdad & Hisai Awali Bihsud | 6 | 5 |  | 1 | 1305064 | 1302805 | 0 | 2259 |  |  | 1305064 | 3 Sub & 5 L | Secure | 1100 | 1301050.9361 | 200822.722 | 208168.1498 | 1509219.0859 | 1710041.8079
219 | MBT Project-077 | Logar Demining Project-12 (AT) | Open | AP,AT | 3,4 | 1395 | CA | Loger | Mohammad Agha | 4 | 1 | 3 |  | 1751186 | 384143 | 1367043 | 0 |  |  | 1751186 | 4 Sub | Secure | 462 | 1159285.3778 | 226324.2143 | 185485.6604 | 1344771.0382 | 1571095.2525
220 | MBT Project-060 | Kabul Demining Project-11 | Open | AP | 3,4,5 | 1395 | CA | Kabul | Sarobi | 20 | 20 |  |  | 873654 | 873654 | 0 | 0 |  |  | 873654 | 12 Sub | Secure | 762 | 872317.8233 | 134670.6333 | 139570.8517 | 1011888.675 | 1146559.3083
221 | MBT Project-217 | Zabul Demining Project-02 | Open | AP,AT | 3,4,5 | 1395 | SA | Zabul | Tarnak Wa Jaldak, Qalat | 14 | 6 | 8 |  | 1570220 | 752720 | 817500 | 0 |  |  | 1570220 | 12 H | Secure | 1035 | 1215459.9576 | 215961.852 | 194473.5932 | 1409933.5509 | 1625895.4029
222 | MBT Project-312 | Zabul Demining Project-03 AT | Open | AT | 3,4,5 | 1395 | SA | Zabul | Tarnak Wa Jaldak, Shamulzayi, Mizan, Atghar | 13 |  | 13 |  | 1587500 | 0 | 1587500 | 0 |  |  | 1587500 | 13 H | Secure | 812 | 900828.4314 | 194059.0323 | 144132.549 | 1044960.9804 | 1239020.0127
223 | MBT Project-112 | Panjshir Demining Project-06 | Open | AP,AT | 3,4,5 | 1395 | CA | Panjshir | Rukha & Unaba | 30 | 29 | 1 |  | 719166 | 716975 | 2191 | 0 |  |  | 719166 | 34 Min | Secure | 1713 | 717121.7351 | 110786.9589 | 114739.4776 | 831861.2127 | 942648.1716 |  |  | Reserved for WRA (DOS) 1394 fund
224 | MBT Project-272 | Nimroz Demining Project-01 AT | Open | AT | 3,4,5 | 1395 | SA | Nimroz | Khash Rod, Kang | 12 |  | 12 |  | 2122414 | 0 | 2122414 | 0 |  |  | 2122414 | 3 H, 1 S | Secure | 1080 | 1204365.9051 | 259447.9414 | 192698.5448 | 1397064.4499 | 1656512.3913
225 | MBT Project-113 | Logar Demining Project-14 (AT) | Open | AT, AP | 3,4,5 | 1395 | CA | Loger | Mohammad Agha | 3 | 1 | 2 |  | 6215339 | 784 | 6214555 | 0 |  |  | 6215339 | 1 Sub | Secure | 3248 | 3527238.1284 | 759799.9243 | 564358.1005 | 4091596.2289 | 4851396.1533
226 | MBT Project-050 | Paktya Demining Project-01 AT | Open | AP,AT | 3,4,5 | 1395 | SE | Paktya | Sayed Karam | 6 | 1 | 5 |  | 618504 | 181153 | 437351 | 0 |  |  | 618504 | 5 Sub | Secure | 6228 | 429051.1962 | 81386.7074 | 68648.1914 | 497699.3876 | 579086.095
227 | MBT Project-082 | Baghlan Demining Project-12 | Open | AP | 3,5 | 1395 | NE | Baghlan | Khinjan | 35 | 34 |  | 1 | 3308991 | 3028460 |  | 280531 |  |  | 3308991 | 26 L | Secure | 2191 | 3053441.26 | 466826.2562 | 488550.6016 | 3541991.8616 | 4008818.1178
228 | MBT Project-114 | Logar Demining Project-19 (AT) | Open | AT, AP | 3,5 | 1395 | CA | Loger | Azra, Khoshi | 5 | 1 | 4 |  | 148148 | 81510 | 66638 | 0 |  |  | 148148 | 13 Sub | Secure | 296 | 119199.1361 | 20710.4308 | 19071.8618 | 138270.9979 | 158981.4287
229 | MBT Project-235 | Logar Demining Project-09 | Open | AP, AT,ERW | 3,5 | 1395 | CA | Loger | Mohammad Agha | 6 | 3 | 2 | 1 | 193672 | 176927 | 13705 | 3040 |  |  | 193672 | 17 Sub | Secure | 574 | 184754.2257 | 28947.9884 | 29560.6761 | 214314.9018 | 243262.8902
230 | MBT Project-078 | Badakhshan Demining Project-02 | Open | AP | 3,5 | 1395 | NE | Badakhshan | Kuran Wa Munjan, Wakhan, Zebak | 24 | 24 |  |  | 1073701 | 1073701 | 0 |  |  |  | 1073701 | 12 Mod, 13 Min | Secure | 311 | 1072058.8691 | 165507.1614 | 171529.419 | 1243588.2881 | 1409095.4495
231 | MBT Project-110 | Parwan Demining Project-10 | Open | AP | 3,5 | 1395 | CA | Parwan | Shinwari | 33 | 33 |  |  | 1518675 | 1518675 | 0 | 0 |  |  | 1518675 | 34 Sub | Secure | 2137 | 1516352.3206 | 234098.3089 | 242616.3713 | 1758968.6919 | 1993067.0008
232 | MBT Project-308 | Kandahar Demining Project-08 AT | Open | AP,AT | 3,5 | 1395 | SA | Kandahar | Maruf | 15 | 13 | 2 |  | 1119057 | 954783 | 164274 | 0 |  |  | 1119057 | 9 H | Secure | 954 | 1046540.186 | 167257.5454 | 167446.4298 | 1213986.6158 | 1381244.1612
233 | MBT Project-076 | Logar Demining Project-11 (AT) | Open | AT | 4 | 1395 | CA | Loger | Mohammad Agha | 3 |  | 3 |  | 1378442 | 0 | 1378442 | 0 |  |  | 1378442 | 3 Sub | Secure | 387 | 782198.2643 | 168503.383 | 125151.7223 | 907349.9866 | 1075853.3696
234 | MBT Project-008 | Kabul Demining Project-05 | Open | AP | 4 | 1395 | CA | Kabul | Khaki Jabar | 4 | 4 |  | 0 | 230157 | 230157 | 0 | 0 |  |  | 230157 | 23 Mod | Secure | 383 | 229804.9952 | 35477.8768 | 36768.7992 | 266573.7944 | 302051.6712
235 | MBT Project-147 | Logar Demining Project-13 (AT) | Open | AT | 4 | 1395 | CA | Loger | Mohammad Agha | 3 |  | 3 |  | 1468000 | 0 | 1468000 | 0 |  |  | 1468000 | 3 Sub | Secure | 399 | 833018.0392 | 179451.124 | 133282.8863 | 966300.9255 | 1145752.0495
236 | MBT Project-075 | Logar Demining Project-10 (AT) | Open | AP,AT | 4 | 1395 | CA | Loger | Mohammad Agha | 8 | 4 | 4 |  | 2595617 | 814660 | 1780957 | 0 |  |  | 2595617 | 13 Sub | Secure | 902 | 1824019.8451 | 343284.505 | 291843.1752 | 2115863.0203 | 2459147.5254
237 | MBT Project-030 | Baghlan Demining Project-11 | Open | AP | 4,5 | 1395 | NE | Baghlan | Khinjan | 14 | 14 |  |  | 1497890 | 1497890 | 0 | 0 |  |  | 1497890 | 9 L | Secure | 1652 | 1495599.1094 | 230894.3756 | 239295.8575 | 1734894.9669 | 1965789.3426
238 | MBT Project-233 | Kapisa Demining Project-08 | Open | AP | 4,5 | 1395 | CA | Kapisa | Hisa-i-Awali Kohistan | 6 | 6 |  |  | 756547 | 756547 | 0 | 0 |  |  | 756547 | 6 Min | Secure | 427 | 755389.9281 | 116619.0089 | 120862.3885 | 876252.3166 | 992871.3255
239 | MBT Project-180 | Baghlan Demining Project-05 | Open | AP,AT | 4,5 | 1395 | NE | Baghlan | Burka | 39 | 35 | 4 |  | 1088822 | 1057196 | 31626 | 0 |  |  | 1088822 | 39 S | Secure | 633 | 1073525.3167 | 166828.9975 | 171764.0507 | 1245289.3674 | 1412118.3648
240 | MBT Project-242 | Baghlan Demining Project-03 | Open | AP | 4,5 | 1395 | NE | Baghlan | Tala Wa Barfak | 29 | 29 |  |  | 2157015 | 2157015 | 0 | 0 |  |  | 2157015 | 25 Sub | Secure | 1205 | 2153716.0359 | 332496.1323 | 344594.5657 | 2498310.6016 | 2830806.734
241 | MBT Project-252 | Khost Demining Project-04 | Open | AP | 4,5 | 1395 | SE | Khost | Jaji Maidan | 5 | 5 |  |  | 390743 | 390743 | 0 | 0 |  |  | 390743 | 10 Ext | Secure | 176 | 390145.3931 | 60231.6332 | 62423.2629 | 452568.6559 | 512800.2891
242 | MBT Project-294 | Logar Demining Project-22 (AT) | Open | AP,AT | 4,5 | 1395 | CA | Loger | Mohammad Agha | 4 | 1 | 3 |  | 1511716 | 52866 | 1458850 | 0 |  |  | 1511716 | 3 Sub | Secure | 381 | 880611.0089 | 186481.715 | 140897.7614 | 1021508.7703 | 1207990.4853
243 | MBT Project-104 | Hirat Demining Project-02 | Open | AP,AT | 4,5 | 1395 | WA | Hirat | Kohsan | 35 | 2 | 33 | 0 | 6924220 | 108500 | 6815720 | 0 |  |  | 6924220 | 2 H, 6 Mod, 19 Sub | Secure | 402 | 3975921.0549 | 849891.5176 | 636147.3688 | 4612068.4237 | 5461959.9413
244 | MBT Project-130/A | Samangan Demining Project-11/A | Open | AP,AT | 5 | 1395 | NA | Samangan | Khuram Wa Sarbagh, Aybak | 9 | 7 | 2 | 0 | 238180 | 223180 | 15000 | 0 |  |  | 238180 |  | Secure | 129 | 231350.4306 | 36236.0259 | 37016.0689 | 268366.4995 | 304602.5253 |  |  | Reserved by DDG for SIDA 1393 Contengecy
245 | MBT Project-093 | Samangan Demining Project-9 | Open | AP | 5 | 1395 | NA | Samangan | Khuram Wa Sarbagh, Hazrat Sultan | 20 | 20 | 0 | 0 | 752547 | 752547 | 0 | 0 |  |  | 752547 | 17 L | Secure | 193 | 751396.0458 | 116002.4232 | 120223.3673 | 871619.4131 | 987621.8363
246 | MBT Project-224 | Kabul Demining Project-09 | Open | AP | 5 | 1396 | CA | Kabul | Charasyab | 17 | 17 |  |  | 482398 | 482398 | 0 | 0 |  |  | 482398 | 17 Mod | Secure | 664 | 481660.2148 |  | 96332.043 | 577992.2578 | 577992.2578
247 | MBT Project-120 | Baghlan Demining Project-13 | Open | AP | 5 | 1396 | NE | Baghlan | Khinjan | 32 | 32 |  |  | 2516331 | 2516331 | 0 | 0 |  |  | 2516331 | 33 L | Secure | 285 | 2512482.4938 |  | 502496.4988 | 3014978.9925 | 3014978.9925
248 | MBT Project-055 | Parwan Demining Project-08 | Open | AP,AT,ERW | 5 | 1396 | CA | Parwan | Bagram, KoheSafi | 3 | 1 | 1 | 1 | 336680 | 66600 | 35080 | 235000 |  |  | 336680 | 24 Mod | Secure | 274 | 111211.064 |  | 22242.2128 | 133453.2768 | 133453.2768
249 | MBT Project-306 | Kandahar Demining Project-09 AT | Open | AP,AT | 4,5 | 1396 | SA | Kandahar | Arghistan | 30 | 13 | 17 |  | 9420536 | 2191880 | 7228656 | 0 |  |  | 9420536 | 20 H | Secure | 1114 | 6290435.6471 |  | 1258087.1294 | 7548522.7765 | 7548522.7765
250 | MBT Project-230 | Kabul Demining Project-19 | Open | AP,AT | 4,5 | 1396 | CA | Kabul | Khaki Jabar | 49 | 42 | 7 |  | 2930246 | 2740294 | 189952 | 0 |  |  | 2930246 | 27 Mod | Secure | 781 | 2843891.4107 |  | 568778.2821 | 3412669.6929 | 3412669.6929
251 | MBT Project-228 | Kabul Demining Project-17 | Open | AP | 5 | 1396 | CA | Kabul | Sarobi | 21 | 21 | 0 |  | 1385248 | 1385248 | 0 | 0 |  |  | 1385248 | 16, Sub | Secure | 316 | 1383129.3854 |  | 276625.8771 | 1659755.2625 | 1659755.2625
252 | MBT Project-189 | Farah Demining Project-01 | Open | AT | 5 | 1396 | WA | Farah | Anardara | 4 | 0 | 4 | 0 | 946544 | 0 | 946544 | 0 |  |  | 946544 | 6 Mod | Secure | 11 | 537117.3208 |  | 107423.4642 | 644540.7849 | 644540.7849
253 | MBT Project-273 | Farah Demining Project-06 | Open | AP,AT | 5 | 1396 | WA | Farah | Gulistan | 7 | 1 | 6 | 0 | 2207348 | 85848 | 2121500 | 0 |  |  | 2207348 | 7 H | Secure | 95 | 1289563.958 |  | 257912.7916 | 1547476.7496 | 1547476.7496
254 | MBT Project-313 | Farah Demining Project-05 | Open | AT | 5 | 1396 | WA | Farah | Bakwa | 1 | 0 | 1 | 0 | 6000000 | 0 | 6000000 | 0 |  |  | 6000000 | 1H | Secure | 15 | 3404705.8824 |  | 680941.1765 | 4085647.0588 | 4085647.0588
255 | MBT Project-311 | Zabul Demining Project-02 AT | Open | AT | 5 | 1396 | SA | Zabul | Tarnak Wa Jaldak | 2 |  | 2 |  | 1320000 | 0 | 1320000 | 0 |  |  | 1320000 | 2 H | Secure | 6 | 749035.2941 |  | 149807.0588 | 898842.3529 | 898842.3529
256 | MBT Project-152 | Baghlan Demining Project-2 (AT) | Open | AP | 5 | 1396 | NE | Baghlan | Tala Wa Barfak | 16 | 16 |  |  | 1559297 | 1559297 |  | 0 |  |  | 1559297 | 16 Sub | Secure | 313 | 1556912.1928 |  | 311382.4386 | 1868294.6314 | 1868294.6314
257 | MBT Project-310 | Zabul Demining Project-06 | Open | AP | 5 | 1396 | SA | Zabul | Tarnak Wa Jaldak | 1 | 1 |  |  | 1750000 | 1750000 | 0 | 0 |  |  | 1750000 | 1 H | Secure | 3 | 1747323.5294 |  | 349464.7059 | 2096788.2353 | 2096788.2353
258 | MBT Project-061 | Kabul Demining Project-13 | Open | AP | 5 | 1396 | CA | Kabul | Charasyab | 13 | 13 |  |  | 752845 | 752845 | 0 | 0 |  |  | 752845 | 13 Mod | Secure | 742 | 751693.59 |  | 150338.718 | 902032.308 | 902032.308
259 | MBT Project-042 | Samangan Demining Project-1 (AT) | Open | AP,AT | 5 | 1396 | NA | Samangan | Feroz Nakhchir | 6 | 2 | 4 | 0 | 89924 | 72660 | 17264 | 0 |  |  | 89924 | 10 L | Secure | 8 | 82345.3467 |  | 16469.0693 | 98814.416 | 98814.416
260 | MBT Project-145 | Kabul Demining Project-04 (AT) | Open | AT | 5 | 1396 | CA | Kabul | Charasyab | 2 |  | 2 |  | 298879 | 0 | 298879 | 0 |  |  | 298879 | 2 Mod | Secure | 19 | 169599.1816 |  | 33919.8363 | 203519.0179 | 203519.0179
261 | MBT Project-226 | Kabul Demining Project-15 | Open | AP | 5 | 1396 | CA | Kabul | Charasyab | 18 | 18 |  |  | 1788420 | 1788420 | 0 | 0 |  |  | 1788420 | 18 Mod | Secure | 259 | 1785684.7694 |  | 357136.9539 | 2142821.7233 | 2142821.7233
262 | MBT Project-229 | Kabul Demining Project-18 | Open | AP | 5 | 1396 | CA | Kabul | Charasyab | 5 | 5 |  |  | 763418 | 763418 | 0 | 0 |  |  | 763418 | 6 Mod | Secure | 85 | 762250.4195 |  | 152450.0839 | 914700.5034 | 914700.5034
263 | MBT Project-227 | Kabul Demining Project-16 | Open | AP | 5 | 1396 | CA | Kabul | Paghman | 5 | 5 | 0 | 0 | 334729 | 334729 |  | 0 |  |  | 334729 | 7 Mod | Secure | 73 | 334217.0615 |  | 66843.4123 | 401060.4738 | 401060.4738
264 | MBT Project-065 | Kapisa Demining Project-04 | Open | AP | 5 | 1396 | CA | Kapisa | Mamoodi Raqi | 5 | 5 |  |  | 274500 | 274500 | 0 | 0 |  |  | 274500 | 11 Mod | Secure | 179 | 274080.1765 |  | 54816.0353 | 328896.2118 | 328896.2118
265 | MBT Project-231 | Kabul Demining Project-20 | Open | AP,AT | 5 | 1396 | CA | Kabul | Khaki Jabar | 23 | 20 | 3 |  | 1684350 | 1550399 | 133951 | 0 |  |  | 1684350 | 24 Mod | Secure | 352 | 1624038.4278 |  | 324807.6856 | 1948846.1134 | 1948846.1134
266 | MBT Project-011 | Kapisa Demining Project-05 | Open | AP | 5 | 1396 | CA | Kapisa | Kohband | 11 | 11 |  |  | 271476 | 271476 | 0 | 0 |  |  | 271476 | 11 Mod | Secure | 277 | 271060.8014 |  | 54212.1603 | 325272.9617 | 325272.9617
267 | MBT Project-292 | Logar Demining Project-07 | Open | AP | 5 | 1396 | CA | Loger | Mohammad Agha | 10 | 10 | 0 |  | 914880 | 914880 | 0 | 0 |  |  | 914880 | 2 H & 5 Sub | Secure | 209 | 913480.7718 |  | 182696.1544 | 1096176.9261 | 1096176.9261
268 | MBT Project-246 | Samangan Demining Project-7 | Open | AP | 5 | 1396 | NA | Samangan | Feroz Nakhchir | 5 | 5 | 0 | 0 | 248159 | 248159 | 0 | 0 |  |  | 248159 | 8 L | Secure | 12 | 247779.4627 |  | 49555.8925 | 297335.3552 | 297335.3552
269 | MBT Project-247 | Samangan Demining Project-13 | Open | AP | 5,6 | 1396 | NA | Samangan | Ruyi Du Ab | 44 | 44 | 0 | 0 | 1649414 | 1649414 | 0 | 0 |  |  | 1649414 | 32 L | Secure | 576 | 1646891.3668 |  | 329378.2734 | 1976269.6402 | 1976269.6402
270 | MBT Project-131 | Samangan Demining Project-12 | Open | AP | 6 | 1396 | NA | Samangan | Ruyi Du Ab | 16 | 16 | 0 | 0 | 908120 | 908120 | 0 | 0 |  |  | 908120 | 16 L | Secure | 27 | 906731.1106 |  | 181346.2221 | 1088077.3327 | 1088077.3327
271 | MBT Project-098 | Ghazni Demining Project-01 | Open | AP,AT | 1,2 | 1396 | SE | Ghazni | Qarabagh, Waghaz | 5 | 4 | 1 |  | 576750 | 378750 | 198000 | 0 |  |  | 576750 | 4 H, 1 Sub | Insecure | 3283 | 490526.0294 |  | 98105.2059 | 588631.2353 | 588631.2353
272 | MBT Project-143 | Maydan Wardak Demining Project-02 | Open | AP,AT | 1,2 | 1396 | CA | Maydan Wardak | Galraez , Nerkh , Sayed Abad | 17 | 16 | 1 |  | 1413490 | 1344378 | 69112 | 0 |  |  | 1413490 | 3 Sub, 7 Mod | Insecure | 5178 | 1381539.5646 |  | 276307.9129 | 1657847.4776 | 1657847.4776
273 | MBT Project-190 | Maydan Wardak Demining Project-04 | Open | AP,AT | 1,2,3 | 1396 | CA | Maydan Wardak | Maydan Shahr & Chaki Wardak | 27 | 26 | 1 | 0 | 3530986 | 3449521 | 81465 |  |  |  | 3530986 | 16 Mod, 1 Sub | Insecure | 16235 | 3490472.6561 |  | 698094.5312 | 4188567.1873 | 4188567.1873
274 | MBT Project-174 | Farah Demining Project-07 | Open | AP,AT | 1,2,3 | 1396 | WA | Farah | Anardara, Khakisapid, Qalaka | 12 | 1 | 11 | 0 | 2723239 | 17784 | 2705455 | 0 |  |  | 2723239 | 1 H 11 Mod | Insecure | 2526 | 1552969.8931 |  | 310593.9786 | 1863563.8717 | 1863563.8717
275 | MBT Project-118 | Baghlan Demining Project-04 | Open | AP, ERW | 1,2,3,4 | 1396 | NE | Baghlan | Burka, Nahrin, Khowaja Hijran, | 24 | 22 |  | 2 | 589262 | 589237 | 0 | 25 |  |  | 589262 | 12 Mod, 11 Sub | Insecure | 2066 | 588338.453 |  | 117667.6906 | 706006.1436 | 706006.1436
276 | MBT Project-150 | Baghlan Demining Project-21 | Open | AP,AT,ERW | 1,2,3,4 | 1396 | NE | Baghlan | Baghlan-i-Jadid, Dahana-i-Ghori | 28 | 24 | 2 | 2 | 724168 | 713334 | 7942 | 2892 |  |  | 724168 | 27 Sub | Insecure | 5443 | 717054.9955 |  | 143410.9991 | 860465.9947 | 860465.9947
277 | MBT Project-154 | Kunar Demining Project-01 | Open | AP, ERW | 1,2,3,4,5 | 1396 | EA | Kunar | Khas Kunar, Marawara, Narang, Narai & Shagal | 30 | 28 |  | 2 | 2317063 | 1909816 | 0 | 407247 |  |  | 2317063 | 31 H & 3Sub | Insecure | 4123 | 1949884.3451 |  | 389976.869 | 2339861.2141 | 2339861.2141
278 | MBT Project-244 | Balkh Demining Project-3 (AT) | Open | AP,AT,ERW | 1,2,5 | 1396 | NA | Balkh | Dihdadi, Marmul | 11 | 1 | 8 | 2 | 794508 | 40000 | 452744 | 301764 |  |  | 794508 | 2 L, 12 Mod | secure | 424 | 328703.2409 |  | 65740.6482 | 394443.8891 | 394443.8891
279 | MBT Project-200 | Nuristan Demining Project-01 | Open | AP | 1,3 | 1396 | EA | Nuristan | Kamdish | 2 | 2 |  |  | 2000450 | 2000450 | 0 | 0 |  |  | 2000450 | 2H | Insecure | 4454 | 1997390.4882 |  | 399478.0976 | 2396868.5859 | 2396868.5859
280 | MBT Project-250 | Laghman Demining Project-01 | Open | AP,AT | 1,2,3,4,5 | 1397 | EA | Laghman | Qarghaye, Mehtarlam | 45 | 37 | 8 |  | 3205745 | 2409448 | 796297 | 0 |  |  | 3205745 | 28 H | Insecure | 2498 | 2857622.4752 |  | 685829.3941 | 3543451.8693 | 3543451.8693 |  |  | Reserved for WRA (DOS) 1394 fund
281 | MBT Project-119 | Baghlan Demining Project-07 | Open | AP, ERW | 1,2,3,4 | 1397 | NE | Baghlan | Andarab, Dih Salah | 29 | 27 |  | 2 | 497348 | 497348 | 0 | 0 |  |  | 497348 | 27 Mod | Insecure | 6104 | 496587.3501 |  | 119180.964 | 615768.3141 | 615768.3141
282 | MBT Project-191 | Maydan Wardak Demining Project-05 | Open | AP,AT | 1,3 | 1397 | CA | Maydan Wardak | Nirkh, Day Mirdad, Hesa Awal Bahsoud | 12 | 11 | 1 |  | 1242243.5 | 1144243.5 | 98000 | 0 |  |  | 1242243.5 | 8 H, 2 Sub & 2 L | Insecure | 1819 | 1198103.6766 |  | 287544.8824 | 1485648.559 | 1485648.559
283 | MBT Project-192 | Maydan Wardak Demining Project-07 | Open | AP | 1,3 | 1397 | CA | Maydan Wardak | Jalriz | 9 | 9 |  |  | 1059307 | 1059307 | 0 | 0 |  |  | 1059307 | 9 Mod | Insecure | 1041 | 1057686.8834 |  | 253844.852 | 1311531.7354 | 1311531.7354
284 | MBT Project-195 | Maydan Wardak Demining Project-11 | Open | AP | 1,3,4 | 1397 | CA | Maydan Wardak | Jalriz, Saydabad | 8 | 8 |  |  | 332193 | 332193 | 0 | 0 |  |  | 332193 | 1 L, 2 H, 7 Mod | Insecure | 2124 | 331684.9401 |  | 79604.3856 | 411289.3257 | 411289.3257
285 | MBT Project-173 | Farah Demining Project-04 | Open | AP,AT,ERW | 1,3,4 | 1397 | WA | Farah, Ghor | Bakwa, Bala Baluk, Farah , Golistan, Shahrak | 10 | 3 | 6 | 1 | 2511747 | 1276358 | 937514 | 297875 |  |  | 2511747 | 8 H, 3 S | Insecure | 3210 | 1837843.027 |  | 441082.3265 | 2278925.3535 | 2278925.3535
286 | MBT Project-080 | Baghlan Demining Project-19 | Open | AP,ERW | 1,3,4,5 | 1397 | NE | Baghlan | Dih Saleh, PoliHesar, Khost Wa Firing | 21 | 18 |  | 3 | 309026 | 244295 | 0 | 64731 |  |  | 309026 | 3 L, 8 Mod | Insecure | 5879 | 250754.4159 |  | 60181.0598 | 310935.4758 | 310935.4758
287 | MBT Project-199 | Faryab Demining Project-1 | Open | AP,AT, ERW | 1,3,4,5 | 1397 | NA | Faryab | Qaysar, Kuhistan,Ghurmach | 26 | 20 | 5 | 1 | 3848348 | 2781038 | 1067190 | 120 |  |  | 3848348 | 2 Mod, 8 Sub | Insecure | 4572 | 3382375.3268 |  | 811770.0784 | 4194145.4052 | 4194145.4052
288 | MBT Project-160/A | Paktya Demining Project-09/A | Open | AP,AT | 1,2,3,5 | 1397 | SE | Paktya | Gardiz | 13 | 12 | 1 |  | 1389349 | 1360748 | 28601 |  |  |  | 1389349 |  | Insecure | 567 | 1374896.5215 |  | 329975.1652 | 1704871.6866 | 1704871.6866
289 | MBT Project-243 | Baghlan Demining Project-06 | Open | AP | 1,5 | 1397 | NE | Baghlan | Khwaja Hejran & Nahrin | 37 | 37 |  |  | 1656708 | 1656708 | 0 | 0 |  |  | 1656708 | 41 Mod | Insecure | 10876 | 1654174.2113 |  | 397001.8107 | 2051176.022 | 2051176.022
290 | MBT Project-267 | Hilmand Demining Project-08 AT | Open | AT | 2 | 1397 | SA | Hilmand | Kajaki | 1 |  | 1 |  | 4000000 | 0 | 4000000 | 0 |  |  | 4000000 | 1 H | insecure | 582 | 2269803.9216 |  | 544752.9412 | 2814556.8627 | 2814556.8627
291 | MBT Project-049 | Paktika Demining Project-01 | Open | AP,AT | 2 | 1397 | SE | Paktika | Urgun | 6 | 4 | 2 |  | 1714498 | 1534498 | 180000 | 0 |  |  | 1714498 | 6 Sub | Insecure | 3390 | 1634292.2972 |  | 392230.1513 | 2026522.4485 | 2026522.4485
292 | MBT Project-158 | Ghazni Demining Project-01 AT | Open | AT | 2 | 1397 | SE | Ghazni | Dih Yak | 1 |  | 1 |  | 6000000 | 0 | 6000000 | 0 |  |  | 6000000 | 1 Sub | Insecure | 208 | 3404705.8824 |  | 817129.4118 | 4221835.2941 | 4221835.2941
293 | MBT Project-144 | Maydan Wardak Demining Project-03 | Open | AP | 2 | 1397 | CA | Maydan Wardak | Jalriz, Nirkh & Saydabad | 15 | 15 |  |  | 1153763 | 1153763 | 0 | 0 |  |  | 1153763 | 5 H, 10 Mod | Insecure | 4353 | 1151998.4213 |  | 276479.6211 | 1428478.0424 | 1428478.0424
294 | MBT Project-204 | Ghazni Demining Project-02 AT | Open | AT | 2 | 1397 | SE | Ghazni | Dih Yak | 1 |  | 1 |  | 4000000 | 0 | 4000000 | 0 |  |  | 4000000 | 1 S | Insecure | 1360 | 2269803.9216 |  | 544752.9412 | 2814556.8627 | 2814556.8627
295 | MBT Project-205 | Ghazni Demining Project-03 | Open | AP,AT,ERW | 2 | 1397 | SE | Ghazni | Bahrami Shahid (Jaghatu), Khowaja Omari, Waghaz, Wali mohammd Shahid, Zanakhan | 9 | 3 | 5 | 1 | 1074643 | 379600 | 694850 | 193 |  |  | 1074643 | 2 Mod, 6 Sub | Insecure | 1606 | 773333.1222 |  | 185599.9493 | 958933.0715 | 958933.0715
296 | MBT Project-206 | Ghazni Demining Project-03 AT | Open | AT | 2 | 1397 | SE | Ghazni | Andar | 9 |  | 9 |  | 625300 | 0 | 625300 | 0 |  |  | 625300 | 9 H | Insecure | 1961 | 354827.098 |  | 85158.5035 | 439985.6016 | 439985.6016
297 | MBT Project-208 | Ghazni Demining Project-04 AT | Open | AT | 2 | 1397 | SE | Ghazni | Ab Band, Giro, Qarabagh | 6 |  | 6 |  | 1226000 | 0 | 1226000 | 0 |  |  | 1226000 | 2 S, 4 H | Insecure | 2248 | 695694.902 |  | 166966.7765 | 862661.6784 | 862661.6784
298 | MBT Project-024 | Logar Demining Project-03 (AT) | Open | AT | 2 | 1397 | CA | Loger | Puli Alam | 26 |  | 26 |  | 1537883 | 0 | 1537883 | 0 |  |  | 1537883 | 15 H | Insecure | 2641 | 872673.2161 |  | 209441.5719 | 1082114.7879 | 1082114.7879
299 | MBT Project-167 | Hilmand Demining Project-11 | Open | AIF | 2,3 | 1397 | SA | Hilmand | Naw Zad | 14 | 14 |  |  | 4053985 | 4053985 | 0 | 0 |  |  | 4053985 | 9 H | insecure | 16585 | 4047784.7876 |  | 971468.349 | 5019253.1367 | 5019253.1367
300 | MBT Project-207 | Paktya Demining Project-01 | Open | AP,AT | 2,3 | 1397 | SE | Paktya | Sayed Karam | 15 | 1 | 14 | 0 | 418493 | 51741 | 366752 | 0 |  |  | 418493 | 13 S | Insecure | 7793 | 259775.6487 |  | 62346.1557 | 322121.8043 | 322121.8043
301 | MBT Project-159 | Ghazni Demining Project-02 | Open | AP,AT,ERW | 2,3 | 1397 | SE | Ghazni | Andar, Dih yak | 14 | 2 | 11 | 1 | 1713895 | 32500 | 1388895 | 292500 |  |  | 1713895 | 1 H, 13 S | Insecure | 3566 | 851456.6008 |  | 204349.5842 | 1055806.185 | 1055806.185
302 | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) | Open | AP,AT | 2,3 | 1397 | CA | Maydan Wardak | Chaki Wardak, Nirkh & Saydabad | 24 | 3 | 21 |  | 2376625 | 346800 | 2029825 |  |  |  | 2376625 | 11 H, 10 Sub | Insecure | 15555 | 1498095.7863 |  | 359542.9887 | 1857638.775 | 1857638.775
303 | MBT Project-156 | Paktika Demining Project-03 | Open | AP,AT | 2,3 | 1397 | SE | Paktika | Dila, Gomal, Waza Khwa | 8 | 2 | 6 |  | 1626704 | 160000 | 1466704 | 0 |  |  | 1626704 | 8 H | Insecure | 1030 | 992037.9169 |  | 238089.1 | 1230127.0169 | 1230127.0169
304 | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) | Open | AT, AP, ERW | 2,3 | 1397 | CA | Maydan Wardak | Nirkh, Chaki Wardak & Jalriz | 15 | 1 | 12 | 2 | 1472143 | 120000 | 423343 | 928800 |  |  | 1472143 | 3 H, 3 Mod & 9 Sub | Insecure | 2020 | 458087.5619 |  | 109941.0149 | 568028.5767 | 568028.5767
305 | MBT Project-183 | Kandahar Demining Project-02 | Open | AP,AT | 2,3,4,5 | 1397 | SA | Kandahar | Maywand | 34 | 11 | 23 |  | 4261183 | 465300 | 3795883 | 0 |  |  | 4261183 | 43 H | insecure | 1794 | 2618565.8945 |  | 628455.8147 | 3247021.7092 | 3247021.7092
306 | MBT Project-022 | Logar Demining Project-01 (AT) | Open | AT | 2,3 | 1397 | CA | Loger | Puli Alam, Charkh & Baraki Barak | 5 |  | 5 |  | 705202 | 0 | 705202 | 0 |  |  | 705202 | 6 H | InSecure | 1826 | 400167.5663 |  | 96040.2159 | 496207.7822 | 496207.7822
307 | MBT Project-188 | Badghis Demining Project-01 | Open | AP,AT | 2,3,4,5 | 1397 | WA | Badghis | Bala Murghab, Ab Khorma, Qadis | 15 | 10 | 5 | 0 | 658421 | 416421 | 242000 | 0 |  |  | 658421 | 1 Mod, 14 H | Insecure | 3740 | 553107.2581 |  | 132745.7419 | 685853 | 685853
308 | MBT Project-046 | Paktya Demining Project-04 | Open | AT,ERW | 2,3 | 1397 | SE | Paktya | Zurmat | 6 |  | 4 | 2 | 230199 | 0 | 90199 | 140000 |  |  | 230199 | 6 H | Insecure | 3128 | 65961.9958 |  | 15830.879 | 81792.8748 | 81792.8748
309 | MBT Project-302 | Ghazni Demining Project-15 AT | Open | AT,ERW | 2,3,4,5 | 1397 | SE | Ghazni | Ghazni | 5 |  | 4 | 1 | 208357 | 0 | 202534 | 5823 |  |  | 208357 | 9 Mod | Insecure | 1349 | 115542.7963 |  | 27730.2711 | 143273.0674 | 143273.0674
310 | MBT Project-163 | Hilmand Demining Project-04 | Open | AP | 3,4 | 1397 | SA | Hilmand | Nawzad | 5 |  | 5 |  | 148500 |  | 148500 | 0 |  |  | 148500 | 13 H | insecure | 821 | 84266.4706 |  | 20223.9529 | 104490.4235 | 104490.4235
311 | MBT Project-048 | Khost Demining Project-01 AT | Open | AP,AT | 2,3,4,5 | 1397 | SE | Khost | Sabari, Terezayi | 11 | 3 | 8 |  | 502200 | 185200 | 317000 | 0 |  |  | 502200 | 2 H, 8 Ext | Insecure | 1962 | 364798.7137 |  | 87551.6913 | 452350.405 | 452350.405
312 | MBT Project-220 | Hirat Demining Project-04 | Open | AP,AT | 2,3,4 | 1398 | WA | Hirat | Shandand | 5 | 1 | 4 |  | 4389780 | 97200 | 4292580 |  |  |  | 4389780 | 6 H | Insecure | 1414 | 2532880.0706 |  | 709206.4198 | 3242086.4904 | 3242086.4904
313 | MBT Project-155 | Paktika Demining Project-02 | Open | AP,AT | 2,3 | 1398 | SE | Paktika | Mata Khan, Sar Awza, Shren, Urgon | 14 | 7 | 7 |  | 1002205 | 105405 | 896800 | 0 |  |  | 1002205 | 8 Mod, 6 Sub | Insecure | 2141 | 614133.8316 |  | 171957.4728 | 786091.3044 | 786091.3044
314 | MBT Project-237 | Hilmand Demining Project-01 AT | Open | AT | 2 | 1398 | SA | Hilmand | Sangin | 1 |  | 1 |  | 25000000 | 0 | 25000000 | 0 |  |  | 25000000 | 1 Ext | Insecure | 11155 | 14186274.5098 |  | 3972156.8627 | 18158431.3725 | 18158431.3725
315 | MBT Project-285 | Hilmand Demining Project-08 | Open | AP,AT | 2,3,4,5 | 1398 | SA | Hilmand | Garmser, Reg(Khanshin), Nawa-I- Barak Zayi, | 10 | 4 | 6 |  | 1630750 | 746000 | 884750 | 0 |  |  | 1630750 | 3 H | Insecure | 2033 | 1246911.3137 |  | 349135.1678 | 1596046.4816 | 1596046.4816
316 | MBT Project-117/A | Badakhshan Demining Project-03/A | Open | AP, ERW | 2,3,4,5,6 | 1398 | NE | Badakhshan | Darwazbala,Darwaz,Sheki, Sheghnan, Kofab, Khwahan | 48 | 43 |  | 5 | 3407323 | 2386695 | 0 | 1020628 |  |  | 3407323 | 36 Min | secure | 4355 | 2490782.8708 |  | 697419.2038 | 3188202.0747 | 3188202.0747
317 | MBT Project-187 | Uruzgan Demining Project-01 ERW | Open | ERW | 2,3,5 | 1398 | SA | Uruzgan | Chora | 4 |  |  | 4 | 128100 | 0 | 0 | 128100 |  |  | 128100 | 4 H | Insecure | 404 | 13522.3136 |  | 3786.2478 | 17308.5615 | 17308.5615
318 | MBT Project-038 | Balkh Demining Project-2 | Open | AP,AT | 2,3,5 | 1398 | NA | Balkh | Chimtal & Charbolak | 16 | 13 | 3 | 0 | 529851 | 424501 | 105350 | 0 |  |  | 529851 | 4 Mod, 12 Sub | Insecure | 6277 | 483632.724 |  | 135417.1627 | 619049.8867 | 619049.8867
319 | MBT Project-255 | Paktya Demining Project-06 | Open | AP | 2,4,5 | 1398 | SE | Paktya | Shawak | 4 | 4 |  |  | 683200 | 683200 | 0 | 0 |  |  | 683200 | 4 H | Insecure | 320 | 682155.1059 |  | 191003.4296 | 873158.5355 | 873158.5355
320 | MBT Project-179 | Maydan Wardak Demining Project-06 | Open | AP | 3 | 1398 | CA | Maydan Wardak | Saydabad | 6 | 6 |  |  | 396600 | 396600 | 0 | 0 |  |  | 396600 | 7 H | Insecure | 1079 | 395993.4353 |  | 110878.1619 | 506871.5972 | 506871.5972
321 | MBT Project-209 | Ghazni Demining Project-04 | Open | AP,AT | 3 | 1398 | SE | Ghazni | Ab Band, Giro, Qarabagh, Jaghori | 11 | 5 | 6 |  | 1811190 | 1081065 | 730125 | 0 |  |  | 1811190 | 4 Min, 4 H, 2 S | Insecure | 8422 | 1493721.7535 |  | 418242.091 | 1911963.8445 | 1911963.8445
322 | MBT Project-210 | Ghazni Demining Project-05 | Open | AP,AT | 3 | 1398 | SE | Ghazni | Khwaja Umari, Waghaz | 11 | 3 | 8 |  | 1178638 | 249549 | 929089 | 0 |  |  | 1178638 | 3 Mod, 8 S | Insecure | 2801 | 776379.8007 |  | 217386.3442 | 993766.145 | 993766.145
323 | MBT Project-211 | Ghazni Demining Project-05 AT | Open | AT | 3 | 1398 | SE | Ghazni | Wali Muhammadi Shahid | 6 |  | 6 |  | 1035131 | 0 | 1035131 | 0 |  |  | 1035131 | 6 Sub | Insecure | 3274 | 587386.1008 |  | 164468.1082 | 751854.209 | 751854.209
324 | MBT Project-300 | Ghazni Demining Project-13 AT | Open | AT | 3 | 1398 | SE | Ghazni | Andar | 13 |  | 13 |  | 1704200 | 0 | 1704200 | 0 |  |  | 1704200 | 13 H | Insecure | 4687 | 967049.9608 |  | 270773.989 | 1237823.9498 | 1237823.9498
325 | MBT Project-212 | Ghazni Demining Project-06 | Open | AP,AT | 3 | 1398 | SE | Ghazni | Wali Muhammadi Shahid | 5 | 1 | 4 |  | 969750 | 180000 | 789750 | 0 |  |  | 969750 | 5 Sub | Insecure | 1156 | 627869.1176 |  | 175803.3529 | 803672.4706 | 803672.4706
326 | MBT Project-213 | Ghazni Demining Project-06 AT | Open | AT | 3 | 1398 | SE | Ghazni | Wali Muhammadi Shahid | 7 |  | 7 |  | 1056925 | 0 | 1056925 | 0 |  |  | 1056925 | 7 S | Insecure | 5619 | 599753.1275 |  | 167930.8757 | 767684.0031 | 767684.0031
327 | MBT Project-281 | Ghazni Demining Project-12 AT | Open | AT | 3 | 1398 | SE | Ghazni | Andar | 16 |  | 16 |  | 1413299 | 0 | 1413299 | 0 |  |  | 1413299 | 16 H | Insecure | 6088 | 801977.9031 |  | 224553.8129 | 1026531.716 | 1026531.716
328 | MBT Project-193 | Maydan Wardak Demining Project-08 | Open | AP | 3 | 1398 | CA | Maydan Wardak | Jalriz | 18 | 18 |  |  | 1798202 | 1798202 | 0 | 0 |  |  | 1798202 | 18 Mod | Insecure | 7755 | 1795451.8087 |  | 502726.5064 | 2298178.3151 | 2298178.3151
329 | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) | Open | AT | 3 | 1398 | CA | Maydan Wardak | Saydabad | 11 |  | 11 |  | 1954862 | 0 | 1954862 | 0 |  |  | 1954862 | 12 H | Insecure | 10021 | 1109288.3584 |  | 310600.7404 | 1419889.0988 | 1419889.0988
330 | MBT Project-214 | Ghazni Demining Project-07 | Open | AP,AT | 3,4 | 1398 | SE | Ghazni | Ab band, Giro, Jaghori, Nawar, Qarabagh | 9 | 4 | 5 |  | 1089315 | 418300 | 671015 | 0 |  |  | 1089315 | 5 H, 1 S, 4 Min | Insecure | 1591 | 798428.3667 |  | 223559.9427 | 1021988.3093 | 1021988.3093
331 | MBT Project-216 | Hilmand Demining Project-06 | Open | AT,ERW | 3,4,5 | 1398 | SA | Hilmand | Musa Qala | 4 |  | 3 | 1 | 361748 | 0 | 227194 | 134554 |  |  | 361748 | 5 Ext | Insecure | 38 | 143125.0598 |  | 40075.0168 | 183200.0766 | 183200.0766
332 | MBT Project-070 | Kapisa Demining Project-01 (AT) | Open | AT | 3,4 | 1398 | CA | Kapisa | Kohband, Tagab | 7 |  | 7 |  | 1275439 | 0 | 1275439 | 0 |  |  | 1275439 | 4 H, 3 Mod | Insecure | 2818 | 723749.111 |  | 202649.7511 | 926398.8621 | 926398.8621
333 | MBT Project-063 | Kapisa Demining Project-07 | Open | AP | 3,4 | 1398 | CA | Kapisa | Nijrab , Kohband, Alasay | 16 | 16 |  |  | 750061 | 750061 | 0 | 0 |  |  | 750061 | 20 H, 6 Mod | Insecure | 5797 | 748913.8479 |  | 209695.8774 | 958609.7253 | 958609.7253
334 | MBT Project-175 | Hirat Demining Project-09 (AT) | Open | AT,ERW | 3,4,5 | 1398 | WA | Hirat | Gulran | 32 | 0 | 29 | 3 | 2532260 | 0 | 2532110 | 150 |  |  | 2532260 | 47 Sub | Insecure | 2010 | 1436864.1361 |  | 402321.9581 | 1839186.0941 | 1839186.0941
335 | MBT Project-197 | Logar Demining Project-15 (AT) | Open | AT | 3,4 | 1398 | CA | Loger | Mohammad Agha, Pul-e-Alam | 14 | 0 | 14 |  | 1107349 |  | 1107349 | 0 |  |  | 1107349 | 13 Sub | Insecure | 1524 | 628366.2757 |  | 175942.5572 | 804308.8329 | 804308.8329
336 | MBT Project-194 | Maydan Wardak Demining Project-09 | Open | AP,AT | 3,4 | 1399 | CA | Maydan Wardak | Maydan Shahr, Chaki Wardak & Nirkh | 12 | 8 | 4 |  | 1092902 | 919612 | 173290 | 0 |  |  | 1092902 | 1 S, 4 Mod, 6 H | Insecure | 6169 | 1016539.115 |  | 325292.5168 | 1341831.6318 | 1341831.6318
337 | MBT Project-140 | Parwan Demining Project-13 | Open | AP | 3,4 | 1399 | CA | Parwan | Sia Gird (Ghorband) | 5 | 5 |  |  | 148950 | 148950 | 0 | 0 |  |  | 148950 | 12 Sub | Insecure | 878 | 148722.1941 |  | 47591.1021 | 196313.2962 | 196313.2962
338 | MBT Project-218 | Zabul Demining Project-03 | Open | AP,AT | 3,4,5 | 1399 | SA | Zabul | Shamulzayi | 5 | 2 | 3 |  | 492500 | 282500 | 210000 | 0 |  |  | 492500 | 5 H | Insecure | 118 | 401232.6471 |  | 128394.4471 | 529627.0941 | 529627.0941
339 | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) | Open | AP,AT,ERW | 3,4,5 | 1399 | CA | Maydan Wardak | Nirkh, Chaki Wardak, Jaghatu | 21 | 2 | 18 | 1 | 2132836 | 277700 | 1197483 | 657653 |  |  | 2132836 | 8 H, 12 Sub | Insecure | 5211 | 1026210.434 |  | 328387.3389 | 1354597.7728 | 1354597.7728
340 | MBT Project-064 | Kapisa Demining Project-02 | Open | AP | 3,4,5 | 1399 | CA | Kapisa | Tagab | 4 | 4 |  |  | 1203250 | 1203250 | 0 | 0 |  |  | 1203250 | 4 H | Insecure | 553 | 1201409.7353 |  | 384451.1153 | 1585860.8506 | 1585860.8506
341 | MBT Project-270 | Hilmand Demining Project-04 AT | Open | AT | 3,4 | 1399 | SA | Hilmand | Sangin | 3 |  | 3 |  | 20107397 | 0 | 20107397 | 0 |  |  | 20107397 | 3 Ext | Insecure | 9553 | 11409962.1408 |  | 3651187.8851 | 15061150.0258 | 15061150.0258
342 | MBT Project-314 | Farah Demining Project-08 (AT) | Open | AT | 3,5 | 1399 | WA | Farah | Shib Koh & Lash Wa Juwayn | 7 | 0 | 7 | 0 | 1524200 | 0 | 1524200 | 0 |  |  | 1524200 | 7 Mod | Insecure | 65 | 864908.7843 |  | 276770.811 | 1141679.5953 | 1141679.5953
343 | MBT Project-196 | Maydan Wardak Demining Project-12 | Open | AP | 3,5 | 1399 | CA | Maydan Wardak | Nirkh | 15 | 15 |  |  | 785759 | 785759 | 0 | 0 |  |  | 785759 | 15 H | Insecure | 3055 | 784557.2509 |  | 251058.3203 | 1035615.5712 | 1035615.5712
344 | MBT Project-123 | Baghlan Demining Project-18 | Open | AP,AT | 3,5 | 1399 | NE | Baghlan | PoliHesar | 53 | 52 | 1 |  | 9899265 | 9865645 | 33620 | 0 |  |  | 9899265 | 52 L | Insecure | 1356 | 9869634.0684 |  | 3158282.9019 | 13027916.9703 | 13027916.9703
345 | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) | Open | AT | 3,5 | 1399 | CA | Maydan Wardak | Saydabad | 22 |  | 22 |  | 649278 | 0 | 649278 | 0 |  |  | 649278 | 22 H | Insecure | 6507 | 368433.4376 |  | 117898.7 | 486332.1377 | 486332.1377
346 | MBT Project-278 | Maydan Wardak Demining Project-15 | Open | AP,AT | 3,5 | 1399 | CA | Maydan Wardak | Saydabad | 18 | 15 | 3 |  | 1028850 | 930850 | 98000 | 0 |  |  | 1028850 | 18 H | Insecure | 4888 | 985036.5431 |  | 315211.6938 | 1300248.2369 | 1300248.2369
347 | MBT Project-296 | Logar Demining Project-24 (AT) | Open | AP,AT | 3,5 | 1399 | CA | Loger | Mohammad Agha | 16 | 1 | 15 |  | 1640059 | 130212 | 1509847 | 0 |  |  | 1640059 | 15 Sub | Insecure | 2456 | 986777.0126 |  | 315768.644 | 1302545.6567 | 1302545.6567
348 | MBT Project-215 | Ghazni Demining Project-07 AT | Open | AT | 4 | 1399 | SE | Ghazni | Waghaz, Wali Muhammadi Shahid | 8 |  | 8 |  | 1183054 | 0 | 1183054 | 0 |  |  | 1183054 | 8 S | Insecure | 4064 | 671325.1522 |  | 214824.0487 | 886149.2008 | 886149.2008
349 | MBT Project-198 | Logar Demining Project-18 (AT) | Open | AP,AT | 4 | 1399 | CA | Loger | Mohammad Agha, Kushi | 8 |  | 8 |  | 1357756 | 0 | 1357756 | 0 |  |  | 1357756 | 6 Sub | Insecure | 2006 | 770459.9733 |  | 246547.1915 | 1017007.1648 | 1017007.1648
350 | MBT Project-239 | Logar Demining Project-17 (AT) | Open | AT | 4 | 1399 | CA | Loger | Mohammad Agha | 9 |  | 9 |  | 2671793 | 0 | 2671793 | 0 |  |  | 2671793 | 9 Sub | Insecure | 2355 | 1516111.5573 |  | 485155.6983 | 2001267.2556 | 2001267.2556
351 | MBT Project-149 | Baghlan Demining Project-08 | Open | AP | 3,5 | 1400 | NE | Baghlan | Andarab | 15 | 15 |  |  | 307827 | 307827 | 0 | 0 |  |  | 307827 | 1 L, 12 Mod | Insecure | 916 | 307356.2058 |  | 110648.2341 | 418004.4398 | 418004.4398
352 | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) | Open | AT | 4 | 1400 | CA | Maydan Wardak | SayedAbad, Jaghatu & Chaki Wardak | 19 | 0 | 19 |  | 1312673 | 0 | 1312673 | 0 |  |  | 1312673 | 7 Sub, 12 H | Insecure | 4944 | 744877.5808 |  | 268155.9291 | 1013033.5099 | 1013033.5099
353 | MBT Project-264 | Paktika Demining Project-05 | Open | AP,AT | 4 | 1400 | SE | Paktika | Urgon | 4 | 1 | 3 |  | 1003500 | 409500 | 594000 | 0 |  |  | 1003500 | 4 Sub | Insecure | 3231 | 745939.5882 |  | 268538.2518 | 1014477.84 | 1014477.84
354 | MBT Project-257 | Ghazni Demining Project-09 AT | Open | AT | 4 | 1400 | SE | Ghazni | Wali Muhammadi Shahid | 9 |  | 9 |  | 1187450 | 0 | 1187450 | 0 |  |  | 1187450 | 9 Sub | Insecure | 7926 | 673819.6667 |  | 242575.08 | 916394.7467 | 916394.7467
355 | MBT Project-254 | Paktika Demining Project-04 | Open | AP,AT | 4 | 1400 | SE | Paktika | Sar Hawza, Sarobi | 5 | 1 | 4 |  | 1052500 | 187500 | 865000 | 0 |  |  | 1052500 | 5 Sub | Insecure | 1219 | 678058.3333 |  | 244101 | 922159.3333 | 922159.3333
356 | MBT Project-263 | Paktika Demining Project-02 AT | Open | AT | 4 | 1400 | SE | Paktika | Dila | 2 |  | 2 |  | 858000 | 0 | 858000 | 0 |  |  | 858000 | 2 H | Insecure | 857 | 486872.9412 |  | 175274.2588 | 662147.2 | 662147.2
357 | MBT Project-253 | Ghazni Demining Project-08 AT | Open | AT | 4 | 1400 | SE | Ghazni | Wali Muhammadi Shahid | 6 |  | 6 |  | 1101937 | 0 | 1101937 | 0 |  |  | 1101937 | 6 Sub | Insecure | 2778 | 625295.231 |  | 225106.2832 | 850401.5141 | 850401.5141
358 | MBT Project-265 | Paktika Demining Project-03 AT | Open | AT | 4 | 1400 | SE | Paktika | Janikhil, Wazakhowa, Zarghon Shahar | 6 |  | 6 |  | 1555000 | 0 | 1555000 | 0 |  |  | 1555000 | 3 Sub, 3 H | Insecure | 2432 | 882386.2745 |  | 317659.0588 | 1200045.3333 | 1200045.3333
359 | MBT Project-238 | Logar Demining Project-16 (AT) | Open | AT | 4 | 1400 | CA | Loger | Mohammad Agha | 4 |  | 4 |  | 644600 | 0 | 644600 | 0 |  |  | 644600 | 4 Sub | Insecure | 855 | 365778.902 |  | 131680.4047 | 497459.3067 | 497459.3067
360 | MBT Project-262 | Paktika Demining Project-01 AT | Open | AT | 4 | 1400 | SE | Paktika | Sharan, Mata Khan | 3 |  | 3 |  | 1190000 | 0 | 1190000 | 0 |  |  | 1190000 | 1 Sub, 2 Mod | Insecure | 339 | 675266.6667 |  | 243096 | 918362.6667 | 918362.6667
361 | MBT Project-133 | Kandahar Demining Project-03 | Open | AP,AT | 4,5 | 1400 | SA | Kandahar | Arghistan | 13 | 2 | 11 |  | 6003874 | 369492 | 5634382 | 0 |  |  | 6003874 | 16 H | Insecure | 362 | 3566162.4844 |  | 1283818.4944 | 4849980.9788 | 4849980.9788
362 | MBT Project-249 | Kandahar Demining Project-05 | Open | AT | 4,5 | 1400 | SA | Kandahar | Arghistan | 5 | 0 | 5 |  | 2240994 |  | 2240994 | 0 |  |  | 2240994 | 4 H | Insecure | 125 | 1271654.2424 |  | 457795.5272 | 1729449.7696 | 1729449.7696
363 | MBT Project-081 | Baghlan Demining Project-20 | Open | AP | 4,5 | 1400 | NE | Baghlan | Dih Saleh | 12 | 12 |  |  | 108566 | 108566 | 0 | 0 |  |  | 108566 | 11 Mod | Insecure | 571 | 108399.9579 |  | 39023.9848 | 147423.9427 | 147423.9427
364 | MBT Project-301 | Ghazni Demining Project-14 AT | Open | AT | 4,5 | 1400 | SE | Ghazni | Andar, Deh Yak | 16 |  | 16 |  | 2035637 | 0 | 2035637 | 0 |  |  | 2035637 | 1 S, 15 H | Insecure | 5140 | 1155124.2114 |  | 415844.7161 | 1570968.9275 | 1570968.9275
365 | MBT Project-275 | Farah Demining Project-07 (AT) | Open | AT | 4,5 | 1400 | WA | Farah | Anardara | 3 | 0 | 3 | 0 | 373235 | 0 | 373235 | 0 |  |  | 373235 | 4 Mod | Insecure | 164 | 211792.5667 |  | 76245.324 | 288037.8907 | 288037.8907
366 | MBT Project-222 | Parwan Demining Project-11 | Open | AP | 4,5 | 1400 | CA | Parwan | Siagird | 29 | 29 |  |  | 385108 | 385108 | 0 | 0 |  |  | 385108 | 27 Sub | Insecure | 1741 | 384519.0113 |  | 138426.8441 | 522945.8554 | 522945.8554
367 | MBT Project-266 | Paktya Demining Project-03 AT | Open | AT,ERW | 4,5 | 1400 | SE | Paktya | Zurmat | 4 |  | 2 | 2 | 1300000 | 0 | 240000 | 1060000 |  |  | 1300000 | 4 H | Insecure | 548 | 248082.4777 |  | 89309.692 | 337392.1697 | 337392.1697
375 | MBT Project-176 | Farah Demining Project-09 (AT) | Open | AT | 4,5 | 1400 | WA | Farah | Bakwa, Bala Baluk, Gulestan & Khaki Safid | 17 | 0 | 17 | 0 | 1446694 | 0 | 1446694 | 0 |  |  | 1446694 | 17 H | Insecure | 784 | 820927.9286 |  | 295534.0543 | 1116461.9829 | 1116461.9829
368 | MBT Project-219 | Farah Demining Project-02 | Open | AP,AT | 5 | 1400 | WA | Farah | Farah, Lash Wa Juwayn, Shib Koh & Qala-i-Kah | 13 | 6 | 7 | 0 | 3492640 | 1744900 | 1747740 | 0 |  |  | 3492640 | 12Mod & 1Sub | Insecure | 30 | 2733988.1059 |  | 984235.7181 | 3718223.824 | 3718223.824
369 | MBT Project-146 | Logar Demining Project-05 (AT) | Open | AP,AT | 5 | 1400 | CA | Loger | Khoshi | 14 | 1 | 13 |  | 747535 | 166966 | 580569 |  |  |  | 747535 | 5 H, 7 Sub | Insecure | 2200 | 496155.0885 |  | 178615.8318 | 674770.9203 | 674770.9203
370 | MBT Project-276 | Maydan Wardak Demining Project-13 | Open | AP | 5 | 1400 | CA | Maydan Wardak | Day Mirdad, Markazi Bihsud & Hisai Awali Bihsud,Chaki Wardak | 7 | 7 |  |  | 976550 | 976550 | 0 | 0 |  |  | 976550 | 3 Sub & 11 L | Insecure | 953 | 975056.4529 |  | 351020.3231 | 1326076.776 | 1326076.776
371 | MBT Project-122 | Baghlan Demining Project-17 | Open | AP | 5 | 1400 | NE | Baghlan | Baghlan-i-Jadid, Dahana-i-Ghori | 39 | 39 |  |  | 1478779 | 1478779 | 0 | 0 |  |  | 1478779 | 38 Sub | Insecure | 389 | 1476517.338 |  | 531546.2417 | 2008063.5797 | 2008063.5797
372 | MBT Project-132 | Baghlan Demining Project-22 | Open | AP | 5 | 1400 | NE | Baghlan | Pol-e-Hesar | 1 | 1 |  |  | 2888862 | 2888862 | 0 | 0 |  |  | 2888862 | 1 L | Insecure | 0 | 2884443.7405 |  | 1038399.7466 | 3922843.487 | 3922843.487
373 | MBT Project-248 | Baghlan Demining Project-4 (AT) | Open | AP,AT,ERW | 5 | 1400 | NE | Baghlan | Baghlan-Jadid, Dahana-I- Ghory | 9 | 7 | 1 | 1 | 324368 | 294368 | 30000 | 0 |  |  | 324368 | 9 Sub | Insecure | 37 | 310941.3195 |  | 111938.875 | 422880.1946 | 422880.1946
374 | MBT Project-157 | Paktya Demining Project-08 | Open | AP | 5 | 1400 | SE | Paktya | Sayed Karam | 2 | 2 |  |  | 192641 | 192641 | 0 | 0 |  |  | 192641 | 4 Sub | Insecure | 432 | 192346.3726 |  | 69244.6941 | 261591.0667 | 261591.0667
376 | MBT Project-172 | Hirat Demining Project-03 | Open | AP,AT | 5 | 1400 | WA | Hirat | Shindand | 7 | 4 | 3 | 0 | 1822902 | 334402 | 1488500 | 0 |  |  | 1822902 | 9 H | Insecure | 191 | 1178541.346 |  | 424274.8845 | 1602816.2305 | 1602816.2305
377 | MBT Project-277 | Maydan Wardak Demining Project-14 | Open | AP | 5 | 1400 | CA | Maydan Wardak | Maydan Shahr & Jalriz | 12 | 12 |  |  | 743006 | 743006 | 0 | 0 |  |  | 743006 | 12 Mod | Insecure | 1122 | 741869.6379 |  | 267073.0696 | 1008942.7075 | 1008942.7075
378 | MBT Project-056 | Parwan Demining Project-12 | Open | AP | 5 | 1400 | CA | Parwan | Surkhi Parsa | 6 | 6 |  |  | 130100 | 130100 | 0 | 0 |  |  | 130100 | 6 L | Insecure | 59 | 129901.0235 |  | 46764.3685 | 176665.392 | 176665.392
379 | MBT Project-141 | Kapisa Demining Project-06 | Open | AP | 5 | 1400 | CA | Kapisa | Nijrab | 9 | 9 |  |  | 301591 | 301591 | 0 | 0 |  |  | 301591 | 22 H | Insecure | 188 | 301129.7432 |  | 108406.7075 | 409536.4507 | 409536.4507
380 | MBT Project-258 | Ghazni Demining Project-08 | Open | AP,AT | 5 | 1400 | SE | Ghazni | Ab Band, Giro, Jaghori, Qarabagh | 16 | 6 | 10 |  | 1607585 | 419348 | 1188237 | 0 |  |  | 1607585 | 1 Min, 7 H, 8 Sub | Insecure | 1253 | 1092972.8948 |  | 393470.2421 | 1486443.137 | 1486443.137
381 | MBT Project-259 | Ghazni Demining Project-09 | Open | AP,AT | 5 | 1400 | SE | Ghazni | Wali Muhammadi Shahid | 16 | 1 | 15 | 0 | 2410381 | 62400 | 2347981 | 0 |  |  | 2410381 | 16 Sub | Insecure | 3419 | 1394668.6851 |  | 502080.7266 | 1896749.4117 | 1896749.4117
382 | MBT Project-261 | Ghazni Demining Project-11 AT | Open | AT | 5 | 1400 | SE | Ghazni | Nawa | 3 |  | 3 |  | 353251 | 0 | 353251 | 0 |  |  | 353251 | 3 Ext | Insecure | 65 | 200452.6263 |  | 72162.9455 | 272615.5717 | 272615.5717
383 | MBT Project-282 | Paktika Demining Project-06 | Open | AP,AT | 5 | 1400 | SE | Paktika | Gayan, Sarobi, Sharan | 5 | 1 | 4 |  | 537950 | 145450 | 392500 | 0 |  |  | 537950 | 1 H, 1 Mod, 3 Sub | Insecure | 425 | 367952.0569 |  | 132462.7405 | 500414.7973 | 500414.7973
384 | MBT Project-303 | Paktika Demining Project-05 AT | Open | AT | 5 | 1401 | SE | Paktika | Dila | 2 |  | 2 |  | 720000 | 0 | 720000 | 0 |  |  | 720000 | 2 H | Insecure | 136 | 408564.7059 |  | 163425.8824 | 571990.5882 | 571990.5882
385 | MBT Project-283 | Paktika Demining Project-04 AT | Open | AT | 5 | 1401 | SE | Paktika | Sar Hawza, Waza Khowa, Zarghon Shahar | 5 |  | 5 |  | 1034520 | 0 | 1034520 | 0 |  |  | 1034520 | 2 Sub, 3 H | Insecure | 209 | 587039.3882 |  | 234815.7553 | 821855.1435 | 821855.1435
386 | MBT Project-284 | Hilmand Demining Project-07 | Open | AT | 5 | 1401 | SA | Hilmand | Kajaki, Musa Qala | 3 | 1 | 2 |  | 358476 | 242226 | 116250 |  |  |  | 358476 | 4 H, 2 Ext | Insecure | 157 | 307821.7132 |  | 123128.6853 | 430950.3984 | 430950.3984
387 | MBT Project-274 | Farah Demining Project-08 | Open | AP,AT | 5 | 1401 | WA | Farah | Bakua, Khak-e-safeed | 8 | 2 | 6 | 0 | 2456918 | 575118 | 1881800 | 0 |  |  | 2456918 | 8 H | Insecure | 535 | 1642067.6627 |  | 656827.0651 | 2298894.7277 | 2298894.7277
388 | MBT Project-287 | Zabul Demining Project-04 | Open | AP,AT | 5 | 1401 | SA | Zabul | Shinkay, Qalat, Mizan | 6 | 5 | 1 |  | 638375 | 542375 | 96000 | 0 |  |  | 638375 | 6 H | Insecure | 12 | 596020.7794 |  | 238408.3118 | 834429.0912 | 834429.0912
389 | MBT Project-288 | Zabul Demining Project-05 | Open | AP,AT | 5 | 1401 | SA | Zabul | Tarnak Wa Jaldak | 10 | 2 | 8 |  | 1737500 | 100000 | 1637500 | 0 |  |  | 1737500 | 10 H | Insecure | 324 | 1029048.0392 |  | 411619.2157 | 1440667.2549 | 1440667.2549
390 | MBT Project-293 | Logar Demining Project-20 (AT) | Open | AT | 5 | 1401 | CA | Loger | Mohammad Agha | 5 |  | 5 |  | 1994346 | 0 | 1994346 | 0 |  |  | 1994346 | 5 Sub | Insecure | 418 | 1131693.5929 |  | 452677.4372 | 1584371.0301 | 1584371.0301
391 | MBT Project-260 | Ghazni Demining Project-10 AT | Open | AT | 5 | 1401 | SE | Ghazni | Waghaz, Khowaja Umari | 12 |  | 12 |  | 1340736 | 0 | 1340736 | 0 |  |  | 1340736 | 3 Mod, 9 sub | Insecure | 742 | 760801.9576 |  | 304320.7831 | 1065122.7407 | 1065122.7407
392 | MBT Project-290 | Farah Demining Project-03 | Open | AT | 5 | 1401 | WA | Farah | Qala-i-Kah | 1 | 0 | 1 | 0 | 7000000 | 0 | 7000000 | 0 |  |  | 7000000 | 1Mod | Insecure | 46 | 3972156.8627 |  | 1588862.7451 | 5561019.6078 | 5561019.6078
393 | MBT Project-279 | Logar Demining Project-21 (AT) | Open | AT | 5 | 1401 | CA | Loger | Mohammad Agha | 4 |  | 4 |  | 2019045 | 0 | 2019045 | 0 |  |  | 2019045 | 4 Sub | Insecure | 94 | 1145709.0647 |  | 458283.6259 | 1603992.6906 | 1603992.6906
394 | MBT Project-295 | Logar Demining Project-23 (AT) | Open | AT | 5 | 1401 | CA | Loger | Mohammad Agha | 21 |  | 21 |  | 1731719 | 0 | 1731719 | 0 |  |  | 1731719 | 21 Sub | Insecure | 1288 | 982665.6443 |  | 393066.2577 | 1375731.902 | 1375731.902
395 | MBT Project-291 | Farah Demining Project-10 (AT) | Open | AT | 5 | 1401 | WA | Farah | Bakwa | 1 | 0 | 1 | 0 | 20250000 | 0 | 20250000 | 0 |  | 0 | 20250000 | 1H | Insecure | 33 | 11490882.3529 |  | 4596352.9412 | 16087235.2941 | 16087235.2941
396 | MBT Project-297 | Logar Demining Project-25 (AT) | Open | AT | 5 | 1401 | CA | Loger | Mohammad Agha | 8 |  | 8 |  | 1621001 | 0 | 1621001 | 0 |  | 0 | 1621001 | 11 Sub | Insecure | 525 | 919838.6067 |  | 367935.4427 | 1287774.0493 | 1287774.0493
Total | [9 empty] | 5503 | 3528 | 1686 | 289 | 595147363 | 215357446.5 | 334268101 | 45521815.5 | 2098 | 148207457.5 | 446939905.5 | 0 | 0 | 1319157 | 406793196.0912 | 30647436.75 | 78930120.4065 | 485723316.4977 | 516370753.2477
Legend:
Completed Projects
Fully Planned Projects
Projects which divided to sub projects
Year Separator
Projects reserved by Donors for year 1394 funding
Project reserved for SIDA 1392-1395 funding
Un-Planned Projects
Note on D19: alauddin.mateen: The project hazards canceled
Note on T44: alauddin.mateen: As per DAFA proposal
Note on W44: alauddin.mateen: Just For CBD
Note on K54: alauddin.mateen: 2 hazards are SHA and need for farther assessment
Note on A66: alauddin.mateen: Part of 189 Project which planned for 1396
Note on B79: Alauddin.Mateen: 1 hazards is worked on
Note on C79: Arif.Rahil: It is completed (HT statement)
Note on B80: Alauddin.Mateen: only one hazard of project is nopen at the end of 1392
Note on C80: Arif.Rahil: It is now empty
Note on B82: Alauddin.Mateen: 2 hazards are open and 2 other ar worked on
Note on C82: Arif.Rahil: All hazards are completed
Note on B83: Alauddin.Mateen: 3 hazards are worked on
Note on B85: Alauddin.Mateen: one hazard is worked on and 6 other are open
Note on C85: Arif.Rahil: Based on HALO Trust statement, all 4 open hazards are cancelled and one remained open hazard is linked with other project planned for 1393
Note on I85: arif.rahil: One hazard from Balkh province is included in thi s project
Note on B91: Alauddin.Mateen: 4 hazadsa are worked on and one is open
Note on C91: Arif.Rahil: All hazards are planned for 1392/93
Note on C92: Arif.Rahil: 2 worked on hazards with plan year 1392/93
Note on B97: Alauddin.Mateen: 2 hazards is worked on
Note on C97: Arif.Rahil: Based on inputs received from HT, these 2 hazards are completed
Note on F97: alauddin.mateen: HT Proirity
Note on B99: Alauddin.Mateen: 3 hazards are worked on
Note on C99: Arif.Rahil: All hazards are completed (HT Statement)
Note on B103: Alauddin.Mateen: 2 hazards is open and 3 are worked on
Note on C103: Arif.Rahil: 2 are cancelled and 3 are completed
Note on B104: Alauddin.Mateen: 1 hazard is worked on
Note on B105: Alauddin.Mateen: 2 hazards are worked on
Note on C105: Arif.Rahil: Planned years is changed to 1392/93
Note on B106: Alauddin.Mateen: 2 hazars are worked on
Note on C106: Arif.Rahil: 2 worked on hazards with plan year 1392/93
Note on C107: Arif.Rahil: 1 hazards planned for 1392 is worked on
Note on B108: Alauddin.Mateen: 9 hazaes are worked on
Note on C108: Arif.Rahil: All hazards are planned for 1392/93
Note on B109: Alauddin.Mateen: 3 open and 3 worked on hazards
Note on C109: Arif.Rahil: 3 open are cancelled, 2 worked on are completed and one is worked on planned for 1392/93
Note on B110: Alauddin.Mateen: 1 hazards are worked on
Note on C110: Arif.Rahil: 2 worked on hazards planned for 1392/93
Note on B116: Alauddin.Mateen: 2 hazards are worked on
Note on B117: 2lauddin.Mateen: 6 hazards are open and 4 are worked on
Note on C117: Arif.Rahil: 5 are worked on with plan year 1392/93 and 2 open are linked with other project
Note on W126: alauddin.mateen: Just For CBD
Note on C134: alauddin.mateen: CIDA 1392
Note on W173: rezwanullah.safi: As per OMAR feedback the security status change form Insecure to Secure ( Achin and Hesarak are suetable for CB)
Note on W178: alauddin.mateen: Just For CBD
Note on G179: Alauddin.Mateen: As per SA Recommadation
Note on W179: Alauddin.Mateen: As per SA Recommandation
Note on G183: Alauddin.Mateen: As per SA recommandation
Note on W183: alauddin.mateen: Just For CBD
Note on G184: Alauddin.Mateen: As per NE recommandation
Note on W184: Alauddin.Mateen: As per NE area office recommandation
Note on B185: Arif.Rahil: Comments received from RO Mazar: 1- BF-0002 and MF-0001(Sar-i-Pul, Sangcharak, Qalmaqi, Tebir) after clearance of these two hazards, the rest of district would be announced free of mine/ERW 2- MF-0001 (Sar-i-Pul, Balkhab, Jare Akhzara) after clearance of this MF, the rest of district would be announce free of mine/ERW
Note on U187: akbar.oriakhil: 4 hazards having rank 5 given to HT along with Takhar project 02
Note on B188: Arif.Rahil: Comments received from RO Mazar: 1- BF-0001(Jawzjan, Mardyan, Khan Aregh) after clearance of this task the rest of district would be announce free of mine/ERW 2- BF-0012 and 0013(Jawzjan, Seberghan, Shor jar) after clearance of these two BFs the rest of province center (Sheberghan) would be announce free of mine/ERW
Note on W191: rezwanullah.safi: As per MCPA feedback the security status change form Insecure to Secure
Note on W194: alauddin.mateen: Just For CBD
Note on W195: alauddin.mateen: Just For CBD
Note on W196: alauddin.mateen: Just For CBD
Note on W200: alauddin.mateen: Just For CBD
Note on R203: Alauddin.Mateen: hazard don’t have area
Note on W206: Alauddin.Mateen: As per MCPA comments some of vileges (Dago, Myagan, Dawlatzai, Dinarkhil) are insecure
Note on U207: akbar.oriakhil: It has been offered to ATC/MCPA in CIDA PIPS recently
Note on R212: alauddin.mateen: Spot UXO No Area
Note on W212: rezwanullah.safi: As per MDC feedback the security status change form Insecure to Secure
Note on W213: alauddin.mateen: Just For CBD
Note on N220: alauddin.mateen: 6 SPOT UXO
Note on W220: rezwanullah.safi: As per MDC feedback the security status change form Insecure to Secure
Note on W221: rezwanullah.safi: As per MDC feedback the security status change form Insecure to Secure
Note on W224: alauddin.mateen: Just For CBD
Note on B225: Arif.Rahil: Comments received from RO Mazar; 1- MF-0044 and 0045 (Balkh, Khulm, Sayghanchi village) after clearance of these two hazards the rest of community would announce free of mine/ERW 2- MF-0053 and 0054 (Balkh, Khulm, Ismail Khayl village)these two hazards located very close to the village and from other side after clearance of these two hazards the rest of community will be free of mine/ERW
Note on W226: alauddin.mateen: Just For CBD
Note on R229: Alauddin.Mateen: BF do not have area
Note on W229: rezwanullah.safi: As per MDC feedback the security status change form Insecure to Secure
Note on W233: alauddin.mateen: Just For CBD
Note on W237: alauddin.mateen: Just For CBD
Note on W238: alauddin.mateen: Just For CBD
Note on W240: alauddin.mateen: Just For SBD
Note on B244: Alauddin.Mateen: 4 hazards are open and one hazard cleared by DAFA in 1392
Note on W248: alauddin.mateen: Just For CBD
Note on W257: rezwanullah.safi: As per MCPA feedback the security status change form Insecure to Secure
Note on W265: alauddin.mateen: Just For CBD
Note on W268: alauddin.mateen: Just For CBD
Note on W269: alauddin.mateen: Just For SBD
Note on W270: alauddin.mateen: Just For CBD
Note on W271: alauddin.mateen: Just For CBD
Note on W273: alauddin.mateen: Just For CBD
Note on W294: Alauddin.Mateen: As per DDG comment
Note on G306: Alauddin.Mateen: As per SA recommandation
Note on W306: alauddin.mateen: Just For CBD
Note on G315: Alauddin.Mateen: As per SA recommandation
Note on G321: Alauddin.Mateen: As per SA recommanation
Note on G326: Alauddin.Mateen: As per SA Recommanation
Note on G332: Alauddin.Mateen: As per NE RO comments
Note on U332: Ajmal: uxo 1005108 ap remaining
Note on W354: alauddin.mateen: CBDT is implementable

## Hazard List
Region | Province | District | Village | City GUID | IMSMAGUID | IMSMAID | Survey Agency | HazardName | Area | Longitude | Latitude | Status | Device | Device Detail | HazardType | Plan Year | Project ID | Project Name | Project Donor | Project Funded | Plan Start Date | Plan End Date | Project Plan Year | Plan Agency | C_GUID | Additional Information | Impact Classification | Plan Intrest | SLS (Security Level) | Population | HazardClassification | OTTAWARanking | Hazard Requested | Hazard Requested Comment | Survey Date | Hazard Cancelled | Project Status
Central | Bamyan | Bamyan | Kakrak | {056593CF-6C12-4230-AA6D-869CB2827CDF} | c0a8-0009-1467f357853-1993cd8a-1eb1-e | Hz-ID-18782 | HT - HALO TRUST | H/8549 | 320 | 67.8552 | 34.8035 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {056593CF-6C12-4230-AA6D-869CB2827CDF} |  | High with Victim | High with Victims | Minimal | 46 | CHA | 1 |  |  | 2014-05-22 16:30 | No | Open
Central | Bamyan | Bamyan | Lala Kheyl | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} | c0a8-0009-13b3b183afd-9e2ebe6-48b5-f1 | Hz-ID-17302 | ATC - Afghan Technical Consultants | AF/2801/28760/MF0124 | 59560 | 67.8661 | 34.8071 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-109/A | Parwan Demining Project-09/A | VTF-Japan | Yes | 2013-05-05 | 2013-09-15 | 1392 | ATC | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} |  |  |  | Minimal | 14 | CHA | 1 | Yes |  | 2012-09-19 16:30 | No | Complete
Central | Bamyan | Bamyan | Lala Kheyl | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} | c0a8-0009-13b405350e3-b492b98e-4bc0-4 | Hz-ID-17385 | ATC - Afghan Technical Consultants | AF/2801/28760/MF0127 | 39904 | 67.8755 | 34.81 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-109/A | Parwan Demining Project-09/A | VTF-Japan | Yes | 2013-05-05 | 2013-07-05 | 1392 | ATC | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} |  |  |  | Minimal | 31 | CHA | 1 | Yes |  | 2012-09-04 16:30 | No | Complete
Central | Bamyan | Bamyan | Lala Kheyl | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} | c0a8-0009-13b405e805e-fd16f304-4c74-4 | Hz-ID-17386 | ATC - Afghan Technical Consultants | AF/2801/28760/MF0128 | 27690 | 67.8755 | 34.81 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-109/A | Parwan Demining Project-09/A | VTF-Japan | Yes |  |  | 1392 | ATC | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} |  |  |  | Minimal | 18 | CHA | 1 | Yes |  | 2012-09-19 16:30 | No | Complete
Central | Bamyan | Bamyan | Lala Kheyl | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} | c0a8-0009-13b406db4b3-c14550b7-4cb4-9 | Hz-ID-17387 | ATC - Afghan Technical Consultants | AF/2801/28760/MF0129 | 59575 | 67.8791 | 34.8093 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-109/A | Parwan Demining Project-09/A | VTF-Japan | Yes | 2013-07-06 | 2013-10-30 | 1392 | ATC | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} |  |  |  | Minimal | 18 | CHA | 1 | Yes |  | 2012-09-11 16:30 | No | Complete
Central | Bamyan | Bamyan | Lala Kheyl | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} | c0a8-0009-13b45e1d6b9-966a2420-595b-8 | Hz-ID-17384 | ATC - Afghan Technical Consultants | AF/2801/28760/MF0126 | 27265 | 67.8751 | 34.7995 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-109/A | Parwan Demining Project-09/A | VTF-Japan | Yes | 2013-05-19 | 2013-07-10 | 1392 | ATC | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} |  |  |  | Minimal | 24 | CHA | 1 | Yes |  | 2012-09-04 16:30 | No | Complete
Central | Bamyan | Bamyan | Lala Kheyl | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} | c0a8-0009-13b4a81c97d-419e661e-5a86-f | Hz-ID-17383 | ATC - Afghan Technical Consultants | AF/2801/28760/MF0125 | 24920 | 67.8751 | 34.7995 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-109/A | Parwan Demining Project-09/A | VTF-Japan | Yes | 2013-05-05 | 2013-07-05 | 1392 | ATC | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} |  |  |  | Minimal | 9 | CHA | 1 | Yes |  | 2012-09-02 16:30 | No | Complete
Central | Bamyan | Bamyan | Lala Kheyl | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} | c0a8-0009-1410638a0a1-73012380-6b7d-b | Hz-ID-18132 | MCPA - Mine Clearance Planning Agency | AF/2801/28760/MF0134 | 14323 | 67.8635 | 34.8071 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-109/A | Parwan Demining Project-09/A | VTF-Japan | Yes |  |  | 1392 | ATC | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} |  |  |  | Minimal | 18 | CHA | 2 |  |  | 2013-07-20 16:30 | No | Complete
Central | Bamyan | Bamyan | Lala Kheyl | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} | c0a8-0009-141063d82fd-1b4a904-6bae-5c | Hz-ID-18131 | MCPA - Mine Clearance Planning Agency | AF/2801/28760/MF0133 | 51981 | 67.8613 | 34.804 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-109/A | Parwan Demining Project-09/A | VTF-Japan | Yes |  |  | 1392 | ATC | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} |  |  |  | Minimal | 15 | CHA | 3 |  |  | 2013-07-25 16:30 | No | Complete
Central | Bamyan | Bamyan | Lala Kheyl | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} | c0a8-0009-14405c58984-4ae01dc2-4a7-69 | Hz-ID-18426 | ATC - Afghan Technical Consultants | AF/2801/28760/MF0138 | 47000 | 67.8624 | 34.8044 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} |  | High with Victim | High with Victims | Minimal | 33 | CHA | 1 |  |  | 2013-10-30 16:30 | No | Open
Central | Bamyan | Bamyan | Lala Kheyl | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} | c0a8-00f6-13a911f4a14-fcea411b-49b-18 | Hz-ID-17303 | ATC - Afghan Technical Consultants | AF/2801/28760/MF0130 | 61330 | 67.8791 | 34.8093 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-109/A | Parwan Demining Project-09/A | VTF-Japan | Yes | 2013-07-11 | 2013-10-31 | 1392 | ATC | {B1918BD2-DA25-44DC-8B39-E36255E8DA2F} |  |  |  | Minimal | 147 | CHA | 1 |  |  | 2012-09-19 16:30 | No | Complete
Central | Bamyan | Bamyan | Somaqoli | {6705D822-761E-4D5B-9100-F82C30AEE30F} | c0a8-0009-141062b146a-861af8da-6b01-7 | Hz-ID-18138 | MCPA - Mine Clearance Planning Agency | AF/2801/28761/MF0137 | 69265 | 67.8884 | 34.8147 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {6705D822-761E-4D5B-9100-F82C30AEE30F} |  | Medium | Critical Infrastracture | Minimal | 90 | CHA | 3 |  |  | 2013-07-24 16:30 | No | Open
Central | Bamyan | Bamyan | Somaqoli | {6705D822-761E-4D5B-9100-F82C30AEE30F} | c0a8-0009-141062fa50f-89d116dd-6b23-3 | Hz-ID-18137 | MCPA - Mine Clearance Planning Agency | AF/2801/28761/MF0136 | 33104 | 67.8884 | 34.8147 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {6705D822-761E-4D5B-9100-F82C30AEE30F} |  | Medium | Critical Infrastracture | Minimal | 90 | CHA | 3 |  |  | 2013-07-23 16:30 | No | Open
Central | Bamyan | Bamyan | Somaqoli | {6705D822-761E-4D5B-9100-F82C30AEE30F} | c0a8-0009-1410633105a-4d17821f-6b40-1 | Hz-ID-18135 | MCPA - Mine Clearance Planning Agency | AF/2801/28761/MF0135 | 4125 | 67.8884 | 34.8147 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {6705D822-761E-4D5B-9100-F82C30AEE30F} |  | Medium | Critical Infrastracture | Minimal | 71 | CHA | 3 |  |  | 2013-07-22 16:30 | No | Open
Central | Bamyan | Bamyan | Tayboti | {04044519-3446-4482-990A-81996D3BB6EE} | c0a8-0009-13f1806719f-78a04bfb-3fc1-a | Hz-ID-17953 | ATC - Afghan Technical Consultants | AF/2801/28742/BF0131 | 297022 | 67.8085 | 34.8608 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-109/A | Parwan Demining Project-09/A | VTF-Japan | Yes | 2013-05-18 | 2013-09-30 | 1392 | ATC | {04044519-3446-4482-990A-81996D3BB6EE} |  |  |  | Minimal | 1 | CHA | 5 |  |  | 2013-05-18 16:30 | No | Complete
Central | Bamyan | Bamyan | Tekar | {20734875-6E7C-4058-86C2-E2E4E00A80FB} | c0a8-0009-141064188c2-244d9b3c-6bde-1 | Hz-ID-18130 | MCPA - Mine Clearance Planning Agency | AF/2801/28702/MF0132 | 100 | 67.722 | 34.7681 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-109/A | Parwan Demining Project-09/A | VTF-Japan | Yes |  |  | 1392 | ATC | {20734875-6E7C-4058-86C2-E2E4E00A80FB} |  |  |  | Minimal | 2004 | CHA | 3 |  |  | 2013-07-13 16:30 | No | Complete
Central | Bamyan | Kahmard | Banaq | {81A86247-6BD7-40CB-92D8-2CD332DF0B2A} | c0a8-0009-13fdb714e92-6cb75698-a5-6ec | Hz-ID-18031 | MCPA - Mine Clearance Planning Agency | AF/1311/28882/MF0089 | 4382 | 67.5983 | 35.3242 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {81A86247-6BD7-40CB-92D8-2CD332DF0B2A} |  | Medium | Critical Infrastracture | Low | 135 | CHA | 3 |  |  | 2013-05-27 16:30 | No | Open
Central | Bamyan | Kahmard | Banaq | {81A86247-6BD7-40CB-92D8-2CD332DF0B2A} | c0a8-0009-13fdb73277f-d32f8ef4-132-e6 | Hz-ID-18033 | MCPA - Mine Clearance Planning Agency | AF/1311/28882/MF0090 | 9589 | 67.6426 | 35.3362 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {81A86247-6BD7-40CB-92D8-2CD332DF0B2A} |  | Low | Agriculture Blocked | Low | 135 | CHA | 4 |  |  | 2013-05-30 16:30 | No | Open
Central | Bamyan | Kahmard | Doabi | {28A2F38C-2C0B-40F8-B894-32CD35F1A9DB} | c0a8-0009-13fdb726e6f-e91bb871-102-a7 | Hz-ID-18026 | MCPA - Mine Clearance Planning Agency | AF/1311/28888/MF0086 | 27808 | 67.6608 | 35.3245 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {28A2F38C-2C0B-40F8-B894-32CD35F1A9DB} |  | Low | Agriculture Blocked | Low | 15 | CHA | 5 |  |  | 2013-05-23 16:30 | No | Open
Central | Bamyan | Kahmard | Laghaki | {F6D7F04D-A1CE-446E-A2A9-9530108FB4A8} | c0a8-0009-13fdb70bb2a-bf4d5916-71-72e | Hz-ID-18022 | MCPA - Mine Clearance Planning Agency | AF/1311/28883/MF0082 | 750 | 67.6175 | 35.2884 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {F6D7F04D-A1CE-446E-A2A9-9530108FB4A8} |  | Low | Agriculture Blocked | Low | 5 | CHA | 5 |  |  | 2013-05-19 16:30 | No | Open
Central | Bamyan | Kahmard | Pa'inbagh | {B6260BAA-282D-4FD6-81CE-54FA827026FB} | c0a8-0009-13fdb6fe69e-fce22cc8-34-315 | Hz-ID-18025 | MCPA - Mine Clearance Planning Agency | AF/1311/28887/MF0085 | 2967 | 67.7081 | 35.3297 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {B6260BAA-282D-4FD6-81CE-54FA827026FB} |  | Medium | Critical Infrastracture | Low | 6 | CHA | 3 |  |  | 2013-05-23 16:30 | No | Open
Central | Bamyan | Kahmard | Pa'inbagh | {B6260BAA-282D-4FD6-81CE-54FA827026FB} | c0a8-0009-13fdb705f17-2ee5f22d-4f-859 | Hz-ID-18024 | MCPA - Mine Clearance Planning Agency | AF/1311/28887/MF0084 | 31802 | 67.6899 | 35.3329 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {B6260BAA-282D-4FD6-81CE-54FA827026FB} |  | Medium | Critical Infrastracture | Low | 358 | CHA | 3 |  |  | 2013-05-19 16:30 | No | Open
Central | Bamyan | Kahmard | Pa'inbagh | {B6260BAA-282D-4FD6-81CE-54FA827026FB} | c0a8-0009-13fdb72c4b8-b3e510bf-11c-d4 | Hz-ID-18023 | MCPA - Mine Clearance Planning Agency | AF/1311/28887/MF0083 | 3381 | 67.6712 | 35.3323 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {B6260BAA-282D-4FD6-81CE-54FA827026FB} |  | Medium | Critical Infrastracture | Low | 298 | CHA | 3 |  |  | 2013-05-21 16:30 | No | Open
Central | Bamyan | Kahmard | Ru-ye Sang | {E11F7073-5096-400D-B074-8D526D4268B9} | c0a8-0009-13fdb71040b-c1771266-89-a62 | Hz-ID-18030 | MCPA - Mine Clearance Planning Agency | AF/1311/28886/MF0087 | 30191 | 67.6431 | 35.3076 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {E11F7073-5096-400D-B074-8D526D4268B9} |  | Low | Agriculture Blocked | Low | 15 | CHA | 5 |  |  | 2013-05-30 16:30 | No | Open
Central | Bamyan | Kahmard | Ru-ye Sang | {E11F7073-5096-400D-B074-8D526D4268B9} | c0a8-0009-14014603f21-f84f1ba4-651-17 | Hz-ID-18069 | MCPA - Mine Clearance Planning Agency | AF/1311/28886/MF0092 | 3900 | 67.6178 | 35.3271 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {E11F7073-5096-400D-B074-8D526D4268B9} |  | Low | Agriculture Blocked | Low | 67 | CHA | 5 |  |  | 2013-06-02 16:30 | No | Open
Central | Bamyan | Kahmard | Ru-ye Sang | {E11F7073-5096-400D-B074-8D526D4268B9} | c0a8-0009-1401494da43-9fdeba79-f7b-cf | Hz-ID-18068 | MCPA - Mine Clearance Planning Agency | AF/1311/28886/MF0091 | 20847 | 67.609 | 35.3377 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {E11F7073-5096-400D-B074-8D526D4268B9} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2013-06-01 16:30 | No | Open
Central | Bamyan | Kahmard | Ru-ye Sang | {E11F7073-5096-400D-B074-8D526D4268B9} | c0a8-0009-1422bb21156-812b6f60-4d66-5 | Hz-ID-18208 | MCPA - Mine Clearance Planning Agency | AF/2803/28886/MF0088 | 38781 | 67.6426 | 35.3362 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {E11F7073-5096-400D-B074-8D526D4268B9} |  | Medium | Agriculture Blocked | Low | 111 | CHA | 3 |  |  | 2013-09-03 16:30 | No | Open
Central | Bamyan | Kahmard | Yelgahe Ajar | {84712F2C-A8D1-43C6-A678-A4FA3A9E71BC} | c0a8-0009-13fdb719763-b0cd5afc-c0-fae | Hz-ID-18021 | MCPA - Mine Clearance Planning Agency | AF/1311/28876/MF0081 | 5367 | 67.4977 | 35.3671 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {84712F2C-A8D1-43C6-A678-A4FA3A9E71BC} |  | Low | Critical Infrastracture | Low | 145 | CHA | 4 |  |  | 2013-05-16 16:30 | No | Open
Central | Bamyan | Kahmard | Yelgahe Ajar | {84712F2C-A8D1-43C6-A678-A4FA3A9E71BC} | c0a8-0009-13fdb7406d4-678f7228-169-2b | Hz-ID-18020 | MCPA - Mine Clearance Planning Agency | AF/1311/28876/MF0080 | 34260 | 67.4943 | 35.3695 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {84712F2C-A8D1-43C6-A678-A4FA3A9E71BC} |  | Low | Critical Infrastracture | Low | 143 | CHA | 4 |  |  | 2013-05-16 16:30 | No | Open
Central | Bamyan | Sayghan | Khodaydadkhel | {0AA5A640-5C06-4D11-A82A-20345C3A93BE} | c0a8-0009-144067c09c9-e8ea37e3-9cb-e7 | Hz-ID-18483 | HT - HALO TRUST | H/8526 | 26480 | 67.677 | 35.1738 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-307/A | Bamyan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {0AA5A640-5C06-4D11-A82A-20345C3A93BE} |  | Low | Agriculture Blocked | Minimal | 11 | CHA | 5 |  |  | 2014-01-14 16:30 | No | Planned
Central | Bamyan | Sayghan | Sayghan | {4166A123-7D41-4958-93D0-85B7D2B49255} | c0a8-0009-144061f6caa-f5934bf5-84b-42 | Hz-ID-18484 | HT - HALO TRUST | H/8527 | 6460 | 67.6564 | 35.1824 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-307/A | Bamyan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {4166A123-7D41-4958-93D0-85B7D2B49255} |  | Low | Agriculture Blocked | Minimal | 83 | CHA | 5 |  |  | 2014-01-17 16:30 | No | Planned
Central | Bamyan | Shibar | Dara-I-Palang | {76D32E88-9984-4DE0-8DF1-CE31FD84DAAB} | c0a8-0009-13b45d83688-9497d7b1-5895-e | Hz-ID-17307 | MCPA - Mine Clearance Planning Agency | AF/2802/00362/MF0092 | 20265 | 68.0107 | 34.9497 | Open | AP Only | AP Only | MineField | Blank | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 | None | {76D32E88-9984-4DE0-8DF1-CE31FD84DAAB} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2011-10-04 16:30 | No | Open
Central | Bamyan | Shibar | Paymuri | {E25413D4-78C3-4680-819E-1B9136D88234} | c0a8-0009-13f18368473-3a5e6508-4302-6 | Hz-ID-17950 | HT - HALO TRUST | H/8509 | 22250 | 68.0207 | 34.7861 | Open | AP Only | AP Only | MineField |  | MBT Project-307 | Bamyan Demining Project-01 |  |  |  |  | 1394 |  | {E25413D4-78C3-4680-819E-1B9136D88234} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2013-05-19 16:30 | No | Open
Central | Kabul | Bagrami | Charkh-e-Aab | {900E4FCC-29A3-4E0A-9E69-DF37E391B72B} | c0a8-00f6-1380d66f68e-822ca7d7-17fa-9 | Hz-ID-17036 | DDG - Danish Demining Group | AF/0110/00433/MF0164 | 294100 | 69.1919 | 34.4479 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059/A | Kabul Demining Project-10/A | DOS | Yes | 2014-05-01 | 2014-09-30 | 1393 | ATC | {900E4FCC-29A3-4E0A-9E69-DF37E391B72B} |  | Low | Agriculture Blocked | Low | 4 | CHA | 4 |  |  | 2011-12-27 16:30 | No | Planned
Central | Kabul | Bagrami | Syahbini | {BCDC28F3-F5F9-4088-9FCB-DC3F124A46EF} | c0a8-0009-13c0eb23fb1-d2fdf118-d37-8d | Hz-ID-17533 | DDG - Danish Demining Group | AF/0110/00106/MF0166 | 68541 | 69.182 | 34.4549 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes |  |  | 1393 | ATC | {BCDC28F3-F5F9-4088-9FCB-DC3F124A46EF} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2012-12-20 16:30 | No | Planned
Central | Kabul | Bagrami | Syahbini | {BCDC28F3-F5F9-4088-9FCB-DC3F124A46EF} | c0a8-0009-13c0eb64ead-44ab6b5a-d53-e9 | Hz-ID-17535 | DDG - Danish Demining Group | AF/0110/00106/MF0168 | 66279 | 69.1858 | 34.4591 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes | 2014-05-01 | 2014-06-30 | 1393 | ATC | {BCDC28F3-F5F9-4088-9FCB-DC3F124A46EF} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2012-12-20 16:30 | No | Planned
Central | Kabul | Bagrami | Syahbini | {BCDC28F3-F5F9-4088-9FCB-DC3F124A46EF} | c0a8-0009-13c1eef3f39-84aa6984-4bc-d9 | Hz-ID-17534 | DDG - Danish Demining Group | AF/0110/00106/MF0167 | 55848 | 69.1858 | 34.4591 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes | 2014-05-01 | 2014-08-30 | 1393 | ATC | {BCDC28F3-F5F9-4088-9FCB-DC3F124A46EF} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2012-12-20 16:30 | No | Planned
Central | Kabul | Bagrami | Syahbini | {BCDC28F3-F5F9-4088-9FCB-DC3F124A46EF} | c0a8-0009-13c7f60b7b6-31e65b4e-6ebc-3 | Hz-ID-17603 | DDG - Danish Demining Group | AF/0110/00106/MF0165 | 77260 | 69.182 | 34.4599 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes |  |  | 1393 | ATC | {BCDC28F3-F5F9-4088-9FCB-DC3F124A46EF} |  | Low | Agriculture Blocked | Low | 12 | CHA | 5 |  |  | 2012-12-27 16:30 | No | Planned
Central | Kabul | Bagrami | Welayati | {BF6D415C-AFEB-416F-AA60-CA8C2C105AC5} | c0a8-00f6-137da6256ec-cc03cf99-1fed-a | Hz-ID-17033 | DDG - Danish Demining Group | AF/0110/00095/MF0163 | 30003 | 69.1813 | 34.4752 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes | 2014-05-01 | 2014-06-26 | 1393 | ATC | {BF6D415C-AFEB-416F-AA60-CA8C2C105AC5} |  |  |  | Low | 0 | CHA | 5 |  |  | 2011-12-26 16:30 | No | Planned
Central | Kabul | Chahar Asyab | Asmanqal'eh | {553C0179-8DD6-4D7A-AAC1-D5726D65F4B7} | c0a8-0057-12c3b76a9d1-6e70a62d-12c0b- | MF-HQ-15256 | MCPA - Mine Clearance Planning Agency | AF/0109/02173/MF7269 | 31180 | 69.0202 | 34.395 | Open | AP Only | AP Only | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {553C0179-8DD6-4D7A-AAC1-D5726D65F4B7} | a | Low | Agriculture Blocked | Moderate | 131 | CHA | 5 |  |  | 2010-09-21 | No | Open
Central | Kabul | Chahar Asyab | Chahar Suq | {9700D882-ED6E-43A5-86E4-60608A55FAF6} | c0a8-0009-14106d1411a-854c6da7-8db7-9 | Hz-ID-18116 | MCPA - Mine Clearance Planning Agency | AF/0109/32121/SpotERW0147 | 100 | 69.1663 | 34.411 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-223 | Kabul Demining Project-08 |  |  |  |  | 1394 |  | {9700D882-ED6E-43A5-86E4-60608A55FAF6} |  | High | Critical Infrastracture | Moderate | 943 | CHA | 3 |  |  | 2012-07-18 16:30 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b692b71-3de2bccd-8963-d | MF-HQ-15046 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7249 | 48066 | 69.0045 | 34.3889 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 58 | CHA | 5 |  |  | 2010-08-20 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b69f800-6ffa94cc-92cb-3 | MF-HQ-14805 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7015 | 30666 | 68.9979 | 34.3798 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 38 | CHA | 5 |  |  | 2010-07-06 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b6aab08-fa1ce30b-9b34-a | MF-HQ-14806 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7016 | 31723 | 68.9982 | 34.379 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 9 | CHA | 5 |  |  | 2010-07-09 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b6ab229-9de58794-9b89-4 | MF-HQ-14804 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7014 | 32654 | 68.9984 | 34.3794 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 9 | CHA | 5 |  |  | 2010-07-12 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b6acce9-9ecf6d9a-9cbd-9 | MF-HQ-14819 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7027 | 34370 | 68.99 | 34.3847 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 41 | CHA | 5 |  |  | 2010-07-16 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b6b19c0-ea275a37-a04c-9 | MF-HQ-15035 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7069 | 15409 | 69.0056 | 34.3817 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 113 | CHA | 5 |  |  | 2010-08-11 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b6b6984-d3c17cc7-a429-6 | MF-HQ-14808 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7018 | 31729 | 68.9966 | 34.3806 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 38 | CHA | 5 |  |  | 2010-07-08 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b6e3d20-e04653df-c6a5-6 | MF-HQ-14823 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7030 | 36253 | 68.99 | 34.3865 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 41 | CHA | 5 |  |  | 2010-07-22 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b6fe868-b6b81b9e-db01-d | MF-HQ-14807 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7017 | 30671 | 68.9964 | 34.3799 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 38 | CHA | 5 |  |  | 2010-07-05 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b71d56f-2b82364f-f27e-e | MF-HQ-14820 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7028 | 44985 | 68.9921 | 34.3856 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 29 | CHA | 5 |  |  | 2010-07-24 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b7464eb-160db2c7-11127- | MF-HQ-14812 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7021 | 8073 | 68.9982 | 34.379 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 9 | CHA | 5 |  |  | 2010-07-10 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b74f102-21831833-117b3- | MF-HQ-14822 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7029 | 35623 | 68.9921 | 34.3865 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 70 | CHA | 5 |  |  | 2010-07-21 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b778139-72920251-135c9- | MF-HQ-14809 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7019 | 30656 | 68.995 | 34.3822 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 29 | CHA | 5 |  |  | 2010-07-04 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b77f10a-c7f1cde8-13aec- | MF-HQ-15232 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7255 | 3650 | 69.007 | 34.3702 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 33 | CHA | 5 |  |  | 2010-08-31 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b78807c-a76d993a-14174- | MF-HQ-15234 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7256 | 6344 | 69.008 | 34.3689 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 33 | CHA | 5 |  |  | 2010-09-01 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b789949-150038b1-14289- | MF-HQ-14815 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7023 | 30878 | 68.9936 | 34.3826 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 38 | CHA | 5 |  |  | 2010-07-14 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-0057-12c3b7a48e4-ce3ddd86-1561c- | MF-HQ-14810 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7020 | 30648 | 68.9953 | 34.3826 | Open | AP Only | AP Only | MineField |  | MBT Project-224 | Kabul Demining Project-09 |  |  |  |  | 1396 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 38 | CHA | 5 |  |  | 2010-07-07 | No | Open
Central | Kabul | Chahar Asyab | Kariz | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} | c0a8-00f6-134c655244b-d606e4a9-291e-3 | MF-16459 | MCPA - Mine Clearance Planning Agency | AF/0109/02172/MF7823 | 30618 | 69.0108 | 34.3867 | Open | AP Only | AP Only | MineField |  | MBT Project-223 | Kabul Demining Project-08 |  |  |  |  | 1394 |  | {E589823F-E357-47DC-937D-ECAD4F2E9DDB} |  | Low | Agriculture Blocked | Moderate | 58 | CHA | 5 |  |  | 2011-04-01 16:30 | No | Open
Central | Kabul | Chahar Asyab | Khan Kala | {1C86FBAC-AC99-480B-B9DB-92A7C838A00E} | c0a8-0057-12c3b6e784b-cab9c05f-c96e-5 | MF-HQ-14447 | MCPA - Mine Clearance Planning Agency | AF/0109/02180/MF6855 | 28032 | 68.9973 | 34.39 | Open | AP Only | AP Only | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {1C86FBAC-AC99-480B-B9DB-92A7C838A00E} |  | Low | Agriculture Blocked | Moderate | 29 | CHA | 5 |  |  | 2010-04-15 | No | Open
Central | Kabul | Chahar Asyab | Qal'eh-yeShaghasi | {5B5FA4B2-B05A-4087-834B-51C75E5363A3} | c0a8-0057-12fd3187d81-e99ddd5a-268c-8 | MF-HQ-10340 | MCPA - Mine Clearance Planning Agency | AF/0109/00273/MF0005 | 54800 | 69.2018 | 34.3838 | Open | AP Only | AP Only | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {5B5FA4B2-B05A-4087-834B-51C75E5363A3} |  | Low | Agriculture Blocked | Moderate | 18 | CHA | 5 |  |  | 2009-04-21 | No | Open
Central | Kabul | Chahar Asyab | Qal'eh-yeShaghasi | {5B5FA4B2-B05A-4087-834B-51C75E5363A3} | c0a8-0057-12fd319eed3-579e2b46-26b8-9 | MF-HQ-10342 | MCPA - Mine Clearance Planning Agency | AF/0114/00273/MF0007 | 89353 | 69.2012 | 34.3814 | Open | AP Only | AP Only | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {5B5FA4B2-B05A-4087-834B-51C75E5363A3} |  | Low | Agriculture Blocked | Moderate | 32 | CHA | 5 |  |  | 2009-05-11 | No | Open
Central | Kabul | Chahar Asyab | Qal'eh-yeShaghasi | {5B5FA4B2-B05A-4087-834B-51C75E5363A3} | c0a8-0057-12fd31b861c-12ea64fe-26e1-b | MF-HQ-10341 | MCPA - Mine Clearance Planning Agency | AF/0109/00273/MF0006 | 52580 | 69.2018 | 34.3838 | Open | AP Only | AP Only | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {5B5FA4B2-B05A-4087-834B-51C75E5363A3} |  | Low | Agriculture Blocked | Moderate | 12 | CHA | 5 |  |  | 2009-04-23 | No | Open
Central | Kabul | Chahar Asyab | Qal'eh-yeShaghasi | {5B5FA4B2-B05A-4087-834B-51C75E5363A3} | c0a8-0057-12fd31cdee0-5144cc46-26f8-c | MF-HQ-10339 | MCPA - Mine Clearance Planning Agency | AF/0109/00273/MF0004 | 48290 | 69.2018 | 34.3838 | Open | AP Only | AP Only | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {5B5FA4B2-B05A-4087-834B-51C75E5363A3} |  | Low | Agriculture Blocked | Moderate | 18 | CHA | 5 |  |  | 2009-04-19 | No | Open
Central | Kabul | Chahar Asyab | Saydkhel | {BD7D8F6D-6308-429F-BF12-015A41FD4CB3} | c0a8-0057-12c3b6b215e-30a39142-a0a2-b | MF-HQ-14488 | MCPA - Mine Clearance Planning Agency | AF/0109/02171/MF6774 | 37851 | 69.0323 | 34.3863 | Open | AP Only | AP Only | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {BD7D8F6D-6308-429F-BF12-015A41FD4CB3} |  | Low | Agriculture Blocked | Moderate | 138 | CHA | 5 |  |  | 2010-02-21 | No | Open
Central | Kabul | Chahar Asyab | Saydkhel | {BD7D8F6D-6308-429F-BF12-015A41FD4CB3} | c0a8-0057-12c3b6b4ea4-92ac5816-a2e0-9 | MF-HQ-14489 | MCPA - Mine Clearance Planning Agency | AF/0109/02171/MF6775 | 32154 | 69.0331 | 34.384 | Open | AP Only | AP Only | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {BD7D8F6D-6308-429F-BF12-015A41FD4CB3} |  | Low | Agriculture Blocked | Moderate | 138 | CHA | 5 |  |  | 2010-02-22 | No | Open
Central | Kabul | Chahar Asyab | Saydkhel | {BD7D8F6D-6308-429F-BF12-015A41FD4CB3} | c0a8-00f6-135384e501a-d1690972-221-e0 | MF-16619 | MCPA - Mine Clearance Planning Agency | AF/0109/02171/MF6786 | 36879 | 69.0331 | 34.3839 | Open | AP Only | AP Only | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {BD7D8F6D-6308-429F-BF12-015A41FD4CB3} |  | Low | Agriculture Blocked | Moderate | 196 | CHA | 5 |  |  | 2010-02-23 16:30 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9deef7-47a000b3-2da97- | MF-CA-1742 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0111 | 58175 | 69.0785 | 34.4195 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9df0bc-43d945b6-2daab- | MF-CA-1741 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0110 | 54323 | 69.0785 | 34.4195 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9df290-63eaf843-2dabf- | MF-CA-1708 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0077 | 73742 | 69.0603 | 34.4252 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9df464-183ba1e1-2dad3- | MF-CA-1724 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0102 | 60583 | 69.0603 | 34.4252 | Open | AP Only | AP Only | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 17 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9df647-2c2fa24e-2dae6- | MF-CA-1755 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0120 | 238758 | 69.0591 | 34.427 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 17 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9df82b-2dbec6b5-2dafa- | MF-CA-1756 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0141 | 216233 | 69.0591 | 34.427 | Open | AP Only | AP Only | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 35 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9df9ff-56eb6cb5-2db0f- | MF-CA-1751 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0118 | 341526 | 69.0591 | 34.427 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 35 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9dfbc3-895bfd0b-2db23- | MF-CA-1722 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0083 | 36316 | 69.0628 | 34.4251 | Open | AP Only | AP Only | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9dfd88-fb086faa-2db36- | MF-CA-1739 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0108 | 52593 | 69.0808 | 34.4193 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 7 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9dff4c-1bcc7a29-2db4a- | MF-CA-1740 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0109 | 51081 | 69.0808 | 34.4193 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-145 | Kabul Demining Project-04 (AT) |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e0130-92dc0311-2db5e- | MF-CA-1702 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0074 | 87425 | 69.0648 | 34.419 | Open | AP Only | AP Only | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 23 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e04e7-3500de5e-2db87- | MF-CA-1733 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0106 | 51186 | 69.0825 | 34.4186 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e06cb-f8a5a8f6-2db9b- | MF-CA-1726 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0104 | 70230 | 69.0599 | 34.4254 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 7 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e08ae-2f37a1dc-2dbaf- | MF-CA-1738 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0107 | 65381 | 69.0823 | 34.4179 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 7 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e0ac1-224f9473-2dbc3- | MF-CA-1743 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0112 | 69675 | 69.0807 | 34.4193 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e0c95-eb557784-2dbd8- | MF-CA-1723 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0101 | 55404 | 69.0603 | 34.4252 | Open | AP Only | AP Only | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e0e69-fda57c03-2dbeb- | MF-CA-1753 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0119 | 247798 | 69.0591 | 34.427 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-145 | Kabul Demining Project-04 (AT) |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 17 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e103d-b9af65d7-2dbff- | MF-CA-1750 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0117 | 130036 | 69.0599 | 34.4254 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 18 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e1220-fbea90cc-2dc13- | MF-CA-1757 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0142 | 87987 | 69.0632 | 34.4134 | Open | AP Only | AP Only | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 16 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e13d5-61e33049-2dc28- | MF-CA-1732 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0105 | 38847 | 69.0825 | 34.4186 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-226 | Kabul Demining Project-15 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e178d-217580e7-2dc4e- | MF-CA-1749 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0116 | 284684 | 69.0736 | 34.4222 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-229 | Kabul Demining Project-18 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 17 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e219b-f5968dca-2dc9e- | MF-CA-1709 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0078 | 69512 | 69.0603 | 34.4252 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-229 | Kabul Demining Project-18 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e2736-1c084297-2dcd9- | MF-CA-1747 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0115 | 284759 | 69.0736 | 34.4222 | Open | AP Only | AP Only | MineField |  | MBT Project-229 | Kabul Demining Project-18 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 30 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e2929-18382f2a-2dcee- | MF-CA-1710 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0079 | 67570 | 69.0603 | 34.4252 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-229 | Kabul Demining Project-18 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Shahtut | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} | c0a8-0057-12c3b9e2b3b-f61e6a43-2dd02- | MF-CA-1746 | MCPA - Mine Clearance Planning Agency | AF/0109/00230/MF0114 | 56893 | 69.0771 | 34.4117 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-229 | Kabul Demining Project-18 |  |  |  |  | 1396 |  | {D6A649F5-5318-43D8-B80F-7C7E80AB9039} |  | Low | Agriculture Blocked | Moderate | 12 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Tangee Sayidan | {4711B7CD-53AA-40A5-AF95-EBDD97EF2C67} | c0a8-0057-12c3ba60435-5fc8c252-32950- | MF-CA-1622 | MCPA - Mine Clearance Planning Agency | AF/0109/00173/MF0143 | 1862 | 69.0941 | 34.4389 | Open | AP Only | AP Only | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {4711B7CD-53AA-40A5-AF95-EBDD97EF2C67} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Tangee Sayidan | {4711B7CD-53AA-40A5-AF95-EBDD97EF2C67} | c0a8-0057-12c3ba60e34-63fefcce-329bc- | MF-CA-1619 | MCPA - Mine Clearance Planning Agency | AF/0109/00173/MF0144 | 231677 | 69.0968 | 34.4377 | Open | AP Only | AP Only | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 | None | {4711B7CD-53AA-40A5-AF95-EBDD97EF2C67} |  | Low | Agriculture Blocked | Moderate | 7 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Ushturparida | {933EAA56-5E30-46F7-A9B4-693766F871F7} | c0a8-0057-12c3b6892fb-7b6b7b43-82b4-b | MF-HQ-14694 | MCPA - Mine Clearance Planning Agency | AF/0109/02181/MF6885 | 37129 | 69.0062 | 34.4021 | Open | AP Only | AP Only | MineField |  | MBT Project-223 | Kabul Demining Project-08 |  |  |  |  | 1394 |  | {933EAA56-5E30-46F7-A9B4-693766F871F7} |  | Low | Agriculture Blocked | Moderate | 38 | CHA | 4 |  |  | 2010-06-25 | No | Open
Central | Kabul | Chahar Asyab | Ushturparida | {933EAA56-5E30-46F7-A9B4-693766F871F7} | c0a8-0057-12c3b74ef6d-c97528f5-1179f- | MF-HQ-14692 | MCPA - Mine Clearance Planning Agency | AF/0109/02181/MF6883 | 43570 | 69.0068 | 34.4011 | Open | AP Only | AP Only | MineField |  | MBT Project-223 | Kabul Demining Project-08 |  |  |  |  | 1394 |  | {933EAA56-5E30-46F7-A9B4-693766F871F7} |  | Low | Agriculture Blocked | Moderate | 124 | CHA | 4 |  |  | 2010-06-23 | No | Open
Central | Kabul | Chahar Asyab | Ushturparida | {933EAA56-5E30-46F7-A9B4-693766F871F7} | c0a8-0057-12c3b9ed914-d9d89daf-2e38f- | MF-CA-1759 | MCPA - Mine Clearance Planning Agency | AF/0109/02181/MF0066 | 53900 | 68.9746 | 34.3959 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {933EAA56-5E30-46F7-A9B4-693766F871F7} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Chahar Asyab | Ushturparida | {933EAA56-5E30-46F7-A9B4-693766F871F7} | c0a8-0057-12c3b9edbd2-69b8adac-2e3a7- | MF-CA-1760 | MCPA - Mine Clearance Planning Agency | AF/0109/02181/MF0067 | 54287 | 68.9719 | 34.3949 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-061 | Kabul Demining Project-13 |  |  |  |  | 1396 |  | {933EAA56-5E30-46F7-A9B4-693766F871F7} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kabul | Dih Sabz | Baba Qashkhar | {AF75D9F0-4820-4619-B1FA-C61F4980FE45} | c0a8-008e-132c9280b86-cd27039f-2a7b-2 | MF-15014 | MCPA - Mine Clearance Planning Agency | AF/0102/00328/MF0141 | 67080 | 69.4036 | 34.6958 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-185 | Kabul new city Demining Project | VTF-Japan | Yes | 2014-06-02 | 2014-07-23 | 1393 | DDG | {AF75D9F0-4820-4619-B1FA-C61F4980FE45} | , |  |  | Moderate | 1 | CHA | 5 |  |  | 2010-11-22 16:30 | No | Planned
Central | Kabul | Dih Sabz | Baba Qashkhar | {AF75D9F0-4820-4619-B1FA-C61F4980FE45} | c0a8-008e-132c928ae0a-bff5d1b1-2ac4-b | MF-15015 | MCPA - Mine Clearance Planning Agency | AF/0102/00328/MF0142 | 21016 | 69.4036 | 34.6958 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-185 | Kabul new city Demining Project | VTF-Japan | No |  |  | 1393 | DDG | {AF75D9F0-4820-4619-B1FA-C61F4980FE45} | , |  |  | Moderate | 1 | CHA | 5 |  |  | 2010-11-24 16:30 | No | Planned
Central | Kabul | Dih Sabz | Deh-sabze Khas | {BC564D12-9B01-4746-BDA5-E9DBF270A97F} | c0a8-008e-13459d80b7d-896c4ba0-23b-88 | MF-16421 | MCPA - Mine Clearance Planning Agency | AF/0102/00345/MF0148 | 105375 | 69.4191 | 34.6412 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-185 | Kabul new city Demining Project | VTF-Japan | Yes | 2014-05-01 | 2014-06-22 | 1393 | DDG | {BC564D12-9B01-4746-BDA5-E9DBF270A97F} | Kabul New City |  |  | Moderate | 0 | CHA | 2 |  |  | 2011-11-29 16:30 | No | Planned
Central | Kabul | Dih Sabz | Deh-sabze Khas | {BC564D12-9B01-4746-BDA5-E9DBF270A97F} | c0a8-008e-1345f21e823-f677d860-1c24-6 | MF-16420 | MCPA - Mine Clearance Planning Agency | AF/0102/00345/MF0149 | 77550 | 69.4191 | 34.6412 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-007 | Kabul Demining Project-04 | DOS | Yes | 2013-11-07 | 2014-04-08 | 1392 | ATC | {BC564D12-9B01-4746-BDA5-E9DBF270A97F} |  |  |  | Moderate | 0 | CHA | 2 |  |  | 2011-11-30 16:30 | No | Complete
Central | Kabul | Dih Sabz | Deh-sabze Khas | {BC564D12-9B01-4746-BDA5-E9DBF270A97F} | c0a8-00f6-134e51f3f78-25a3aafe-668-ab | MF-16422 | MCPA - Mine Clearance Planning Agency | AF/0102/00345/MF0147 | 100177 | 69.4191 | 34.6412 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes | 2013-12-01 | 2014-04-15 | 1392-1393 | DDG | {BC564D12-9B01-4746-BDA5-E9DBF270A97F} |  |  |  | Moderate | 0 | CHA | 2 |  |  | 2011-11-27 16:30 | No | Planned
Central | Kabul | Dih Sabz | Qal'eh-ye Haji Mohammad Afzalkhan | {39631057-BFA0-4F09-9BA1-5C525BD4289A} | c0a8-0009-13c0f4d34d8-32214c86-1155-8 | Hz-ID-17548 | DAFA - Demining Agency for Afghanistan | AF/0102/00309/BF0152 | 4935 | 69.211 | 34.639 | Open | UXO Only | UXO Only | BF | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes |  |  | 1392-1393 | HT | {39631057-BFA0-4F09-9BA1-5C525BD4289A} |  | Medium | Critical Infrastracture | Moderate | 69 | CHA | 3 |  |  | 2012-12-13 16:30 | No | Planned
Central | Kabul | Dih Sabz | Sangaw | {093C5092-BFF2-4408-8392-7B410B49F3AA} | c0a8-0057-12c3b70c462-8b95ba06-e583-6 | MF-HQ-11370 | HT - HALO TRUST | H/5491 | 44800 | 69.2388 | 34.7841 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes | 2012-11-14 | 2013-04-14 | 1392-1393 | DDG | {093C5092-BFF2-4408-8392-7B410B49F3AA} |  |  |  | Moderate | 12 | CHA | 4 |  |  | 2009-03-18 | No | Planned
Central | Kabul | Dih Sabz | Shaykhu | {D4903B0B-54BC-4393-B9C6-220FD005E0A5} | c0a8-0009-13e3bae6fc6-6437999d-ce4-de | Hz-ID-17743 | DAFA - Demining Agency for Afghanistan | AF/0102/00322/MF0153 | 41780 | 69.2206 | 34.7766 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-185 | Kabul new city Demining Project | VTF-Japan | Yes | 2014-06-01 | 2014-07-23 | 1393 | DDG | {D4903B0B-54BC-4393-B9C6-220FD005E0A5} | Kabul New City | High with Victim | High with Victims | Moderate | 4 | CHA | 2 |  |  | 2013-03-03 16:30 | No | Planned
Central | Kabul | Farza | Qal'eh-ye Mirza | {C280CD00-6446-4351-9E8B-E76E8AA81922} | c0a8-0057-12c3b75ec8d-568ff611-12345- | MF-HQ-11397 | HT - HALO TRUST | H/4383 | 14000 | 69.0259 | 34.8038 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes |  |  | 1392-1393 | HT | {C280CD00-6446-4351-9E8B-E76E8AA81922} | , |  |  | Minimal | 235 | CHA | 5 |  |  | 2008-08-03 | No | Planned
Central | Kabul | Farza | Qal'eh-ye Salimkhan | {AE26C183-AE84-47EF-B710-491D2EA8736A} | c0a8-0009-14365bd1f18-a0270f3-795-2ae | Hz-ID-18309 | HT - HALO TRUST | H/8524 | 24 | 69.0348 | 34.7915 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2014-01-02 | 2014-01-14 | 1392-1393 | HT | {AE26C183-AE84-47EF-B710-491D2EA8736A} |  |  |  | Minimal | 1547 | CHA | 4 |  |  | 2013-12-09 16:30 | No | Planned
Central | Kabul | Farza | Qal'eh-ye Salimkhan | {AE26C183-AE84-47EF-B710-491D2EA8736A} | c0a8-0057-12c3b6c89ae-29c9dbed-b1e4-b | MF-HQ-11622 | HT - HALO TRUST | H/6220 | 35000 | 69.0172 | 34.7805 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/B | Kabul Demining Project-07/B | GAGP | Yes |  |  | 1392 | HT | {AE26C183-AE84-47EF-B710-491D2EA8736A} | planned year & Agency removed |  |  | Minimal | 347 | CHA | 4 |  |  | 2009-06-14 | No | Complete
Central | Kabul | Farza | Qal'eh-ye Salimkhan | {AE26C183-AE84-47EF-B710-491D2EA8736A} | c0a8-0057-12c3b793b50-e5f761de-149fa- | MF-HQ-11619 | HT - HALO TRUST | H/6218 | 45000 | 69.0156 | 34.7798 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/B | Kabul Demining Project-07/B | GAGP | Yes | 2013-11-01 | 2013-12-23 | 1392 | HT | {AE26C183-AE84-47EF-B710-491D2EA8736A} | , |  |  | Minimal | 149 | CHA | 4 |  |  | 2009-06-11 | No | Complete
Central | Kabul | Farza | Qal'eh-ye Salimkhan | {AE26C183-AE84-47EF-B710-491D2EA8736A} | c0a8-0057-12c3b798605-2f81971d-14d69- | MF-HQ-11620 | HT - HALO TRUST | H/6219 | 47500 | 69.0194 | 34.7807 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/B | Kabul Demining Project-07/B | GAGP | Yes | 2013-08-23 | 2013-10-23 | 1392 | HT | {AE26C183-AE84-47EF-B710-491D2EA8736A} | Planned Year and Agency removed |  |  | Minimal | 198 | CHA | 4 |  |  | 2009-06-13 | No | Complete
Central | Kabul | Farza | Qal'eh-ye Salimkhan | {AE26C183-AE84-47EF-B710-491D2EA8736A} | c0a8-0057-12c3ba6ca7e-724c42df-33135- | MF-CA-1889 | HT - HALO TRUST | H/1615 | 32500 | 69.0185 | 34.778 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/B | Kabul Demining Project-07/B | GAGP | Yes | 2013-08-13 | 2013-10-23 | 1392 | HT | {AE26C183-AE84-47EF-B710-491D2EA8736A} | , |  |  | Minimal | 198 | CHA | 4 |  |  | 2009-06-12 | No | Complete
Central | Kabul | Farza | Qal'eh-ye Salimkhan | {AE26C183-AE84-47EF-B710-491D2EA8736A} | c0a8-0057-12c3ba9cb32-cea561a1-34d9d- | MF-HT-1381 | HT - HALO TRUST | H/1617 | 19000 | 69.0175 | 34.7972 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/B | Kabul Demining Project-07/B | GAGP | Yes | 2013-12-01 | 2013-12-23 | 1392 | HT | {AE26C183-AE84-47EF-B710-491D2EA8736A} | , |  |  | Minimal | 179 | CHA | 4 |  |  | 2007-12-01 | No | Complete
Central | Kabul | Guldara | Arabha | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} | c0a8-0057-12c3b80b5b9-2e48511a-19f0d- | MF-HT-274 | HT - HALO TRUST | H/3865 | 33000 | 69.0279 | 34.747 | Worked on | AP Only | AP Only | MineField | 1392 | MBT Project-058/C | Kabul Demining Project-07/C | B-Germany | Yes | 2013-10-01 | 2013-11-23 | 1392 | HT | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} | Removed from HT plan | Low | Agriculture Blocked | Minimal | 257 | CHA | 4 |  |  | 2007-11-30 | No | Planned
Central | Kabul | Guldara | Arabha | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} | c0a8-0057-12edd2817f5-5834aa93-676-b1 | MF-HT-273 | HT - HALO TRUST | H/3864 | 29700 | 69.0264 | 34.738 | Worked on | AP Only | AP Only | MineField | 1392 | MBT Project-058/C | Kabul Demining Project-07/C | B-Germany | Yes | 2013-10-01 | 2013-11-23 | 1392 | HT | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} |  | Low | Agriculture Blocked | Minimal | 117 | CHA | 4 |  |  | 2007-11-30 | No | Planned
Central | Kabul | Guldara | Arabha | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} | c0a8-008e-1328fa1f0c5-408cd5ae-2057-5 | MF-15777 | HT - HALO TRUST | H/7675 | 17650 | 69.0281 | 34.746 | Worked on | AP Only | AP Only | MineField | 1392 | MBT Project-058/C | Kabul Demining Project-07/C | B-Germany | Yes | 2013-10-01 | 2013-10-23 | 1392 | HT | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} |  | Low | Agriculture Blocked | Minimal | 117 | CHA | 4 |  |  | 2011-01-13 16:30 | No | Planned
Central | Kabul | Guldara | Arabha | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} | c0a8-008e-1328fb33d82-76b574f3-22f4-4 | MF-15775 | HT - HALO TRUST | H/7673 | 32000 | 69.0281 | 34.746 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062/A | Kabul Demining Project-14/A | CIDA | Yes | 2013-11-01 | 2013-12-23 | 1392 | HT | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} |  |  |  | Minimal | 117 | CHA | 4 |  |  | 2011-01-11 16:30 | No | Complete
Central | Kabul | Guldara | Arabha | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} | c0a8-008e-1328fb36fe6-37310559-2318-6 | MF-15776 | HT - HALO TRUST | H/7674 | 25600 | 69.0281 | 34.746 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/C | Kabul Demining Project-07/C | B-Germany | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} |  |  |  | Minimal | 117 | CHA | 4 |  |  | 2011-01-12 16:30 | No | Planned
Central | Kabul | Guldara | Arabha | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} | c0a8-008e-1328fb39b78-dcc06b2f-232c-4 | MF-15863 | HT - HALO TRUST | H/7672 | 16700 | 69.0212 | 34.7456 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/C | Kabul Demining Project-07/C | B-Germany | Yes | 2013-12-01 | 2013-12-23 | 1392 | HT | {1668DD1C-CB34-40A7-93DB-F9BE2477AD5C} |  |  |  | Minimal | 0 | CHA | 4 |  |  | 2011-01-10 16:30 | No | Planned
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0009-141076ce519-38397c32-afb5-6 | Hz-ID-17951 | HT - HALO TRUST | H/8510 | 7650 | 68.9819 | 34.7424 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059/B | Kabul Demining Project-10/B | B-Germany | Yes |  |  | 1393 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} |  | Low | Agriculture Blocked | Minimal | 116 | CHA | 4 |  |  | 2013-05-06 16:30 | No | Planned
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0009-14227942cad-e68f1627-38f3-2 | Hz-ID-18203 | HT - HALO TRUST | H/8519 | 10425 | 68.9871 | 34.7351 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-059/B | Kabul Demining Project-10/B | B-Germany | Yes | 2014-07-01 | 2014-09-10 | 1393 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} |  |  |  | Minimal | 32 | CHA | 5 |  |  | 2013-10-08 16:30 | No | Planned
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0057-12c3b690146-84cf48aa-8799-3 | MF-HQ-13433 | HT - HALO TRUST | H/6703 | 27000 | 68.9677 | 34.7288 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/B | Kabul Demining Project-07/B | GAGP | Yes | 2013-07-01 |  | 1392 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} |  |  |  | Minimal | 93 | CHA | 4 |  |  | 2009-10-09 | No | Complete
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0057-12c3b6ad6b9-7617b473-9d37-5 | MF-HQ-13436 | HT - HALO TRUST | H/6705 | 34200 | 68.9726 | 34.7308 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-06-01 | 2013-08-22 | 1392-1393 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} |  |  |  | Minimal | 76 | CHA | 5 |  |  | 2009-10-11 | No | Planned
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0057-12c3b6cab70-1315d648-b382-c | MF-HQ-13443 | HT - HALO TRUST | H/6710 | 40000 | 68.9726 | 34.7308 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062/A | Kabul Demining Project-14/A | CIDA | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} |  |  |  | Minimal | 94 | CHA | 5 |  |  | 2009-10-16 | No | Complete
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0057-12c3b709325-89fa36c5-e31a-e | MF-HQ-13437 | HT - HALO TRUST | H/6706 | 27000 | 68.9726 | 34.7308 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-08-10 | 2013-12-23 | 1392-1393 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} |  |  |  | Minimal | 76 | CHA | 5 |  |  | 2009-10-12 | No | Planned
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0057-12c3b71503b-9cf74714-ec03-4 | MF-HQ-13441 | HT - HALO TRUST | H/6708 | 40500 | 68.9726 | 34.7308 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-06-01 | 2013-08-22 | 1392-1393 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} |  |  |  | Minimal | 94 | CHA | 5 |  |  | 2009-10-14 | No | Planned
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0057-12c3b742731-9c6c6fd6-10e5b- | MF-HQ-13434 | HT - HALO TRUST | H/6704 | 47550 | 68.9726 | 34.7308 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-09-10 | 2013-12-23 | 1392-1393 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} |  |  |  | Minimal | 18 | CHA | 5 |  |  | 2009-10-10 | No | Planned
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0057-12c3b7528d3-3cbe69f0-11a48- | MF-HQ-13586 | HT - HALO TRUST | H/6709 | 44900 | 68.9726 | 34.7308 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-07-01 | 2013-10-23 | 1392-1393 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} |  |  |  | Minimal | 94 | CHA | 5 |  |  | 2009-10-15 | No | Planned
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0057-12c3b79281e-402931f2-1491c- | MF-HQ-13429 | HT - HALO TRUST | H/6701 | 30000 | 68.9646 | 34.7319 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-07-01 | 2013-09-15 | 1392-1393 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} |  |  |  | Minimal | 17 | CHA | 5 |  |  | 2009-10-07 | No | Planned
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0057-12c3b797dea-60a21df5-14d09- | MF-HQ-13431 | HT - HALO TRUST | H/6702 | 30187 | 68.9677 | 34.7288 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-07-01 | 2013-09-23 | 1392-1393 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} | , |  |  | Minimal | 93 | CHA | 5 |  |  | 2009-10-08 | No | Planned
Central | Kabul | Guldara | Gerdbed | {081A02CF-846C-4832-B90E-BB3E01A949FE} | c0a8-0057-12c3b7a02ff-7cb20934-15304- | MF-HQ-13439 | HT - HALO TRUST | H/6707 | 51150 | 68.9726 | 34.7308 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-08-18 | 2013-12-23 | 1392-1393 | HT | {081A02CF-846C-4832-B90E-BB3E01A949FE} |  |  |  | Minimal | 94 | CHA | 5 |  |  | 2009-10-13 | No | Planned
Central | Kabul | Guldara | Jalwani | {6CF6AE56-BB0D-47EE-A370-D1C2F90CAE6A} | c0a8-0057-12c3b74d2c9-fb3b0ac3-1164d- | MF-HQ-15227 | HT - HALO TRUST | H/7076 | 33000 | 69.0327 | 34.7319 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes |  |  | 1392-1393 | HT | {6CF6AE56-BB0D-47EE-A370-D1C2F90CAE6A} | Removed from HT plan |  |  | Minimal | 234 | CHA | 5 |  |  | 2010-09-01 | No | Planned
Central | Kabul | Guldara | Jalwani | {6CF6AE56-BB0D-47EE-A370-D1C2F90CAE6A} | c0a8-008e-1328fa18bad-7e1de0e1-201f-2 | MF-15780 | HT - HALO TRUST | H/7614 | 30000 | 69.0327 | 34.7319 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/B | Kabul Demining Project-07/B | GAGP | Yes | 2013-11-01 | 2014-01-23 | 1392 | HT | {6CF6AE56-BB0D-47EE-A370-D1C2F90CAE6A} |  |  |  | Minimal | 234 | CHA | 4 |  |  | 2011-01-06 16:30 | No | Complete
Central | Kabul | Guldara | Jalwani | {6CF6AE56-BB0D-47EE-A370-D1C2F90CAE6A} | c0a8-008e-1328fa1bc8c-f854401-2031-dc | MF-15779 | HT - HALO TRUST | H/7615 | 32500 | 69.0327 | 34.7319 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/B | Kabul Demining Project-07/B | GAGP | Yes | 2013-11-21 | 2014-01-23 | 1392 | HT | {6CF6AE56-BB0D-47EE-A370-D1C2F90CAE6A} |  |  |  | Minimal | 351 | CHA | 4 |  |  | 2011-01-07 16:30 | No | Complete
Central | Kabul | Guldara | Kando Sang | {5C237E0B-CD76-42FB-BCC9-AA85B5FB0216} | c0a8-0057-12c3b6b7da0-af3f25b1-a51a-2 | MF-HQ-13970 | HT - HALO TRUST | H/6748 | 27750 | 68.9904 | 34.7594 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-05-21 | 2013-07-23 | 1392-1393 | HT | {5C237E0B-CD76-42FB-BCC9-AA85B5FB0216} |  |  |  | Minimal | 1 | CHA | 5 |  |  | 2010-01-13 | No | Planned
Central | Kabul | Guldara | Kando Sang | {5C237E0B-CD76-42FB-BCC9-AA85B5FB0216} | c0a8-0057-12c3b729958-d0c5d321-fb98-1 | MF-HQ-13969 | HT - HALO TRUST | H/6749 | 3101 | 68.9904 | 34.7594 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-06-01 | 2013-06-17 | 1392-1393 | HT | {5C237E0B-CD76-42FB-BCC9-AA85B5FB0216} |  |  |  | Minimal | 1 | CHA | 5 |  |  | 2010-01-13 | No | Planned
Central | Kabul | Guldara | Kando Sang | {5C237E0B-CD76-42FB-BCC9-AA85B5FB0216} | c0a8-0057-12c3b7f90ce-b4f13a16-1920f- | MF-HQ-11929 | HT - HALO TRUST | H/1608 | 52100 | 68.9728 | 34.7551 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-06-18 | 2013-10-12 | 1392-1393 | HT | {5C237E0B-CD76-42FB-BCC9-AA85B5FB0216} |  |  |  | Minimal | 28 | CHA | 5 |  |  | 2008-05-04 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-0009-13f2d298c95-37d50a4f-5df4-3 | Hz-ID-17910 | HT - HALO TRUST | H/8504 | 57600 | 68.9949 | 34.7343 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-062/B | Kabul Demining Project-14 /B | DOS | Yes | 2013-07-01 | 2014-04-23 | 1393 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  |  |  | Minimal | 55 | CHA | 1 |  |  | 2013-04-19 16:30 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-0009-142278c3c9f-8034bbf5-3432-3 | Hz-ID-18202 | HT - HALO TRUST | H/8518 | 30000 | 68.9927 | 34.7396 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059/B | Kabul Demining Project-10/B | B-Germany | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  | High with Victim | High with Victims | Minimal | 55 | CHA | 1 |  |  | 2013-10-05 16:30 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-0009-147330d10fe-f5f75639-177-1a | Hz-ID-18856 | HT - HALO TRUST | H/8800 | 16250 | 68.9924 | 34.7208 | Open | AP Only | AP Only | MineField |  | MBT Project-020/A | Kabul Demining Project-02 (AT)/A |  |  |  |  | 1394 |  | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  | High with Victim | High with Victims | Minimal | 0 | CHA | 1 |  |  | 2014-06-19 16:30 | No | Open
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-004c-13006adb407-deb1d893-b4b-85 | MF-HQ-13750 | HT - HALO TRUST | H/6723 | 65962 | 68.9926 | 34.7212 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-06-01 | 2013-10-23 | 1392-1393 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  |  |  | Minimal | 39 | CHA | 5 |  |  | 2009-12-05 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-0057-12c3b6967e4-e5966a9f-8bf5-2 | MF-HQ-13450 | HT - HALO TRUST | H/6280 | 37900 | 68.9726 | 34.7308 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062/A | Kabul Demining Project-14/A | CIDA | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  |  |  | Minimal | 94 | CHA | 5 |  |  | 2009-10-06 | No | Complete
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-0057-12c3b6e6bcd-d97e2498-c8e3-7 | MF-HQ-13447 | HT - HALO TRUST | H/6278 | 36000 | 68.9773 | 34.7249 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-062/B | Kabul Demining Project-14 /B | DOS | Yes | 2014-06-01 | 2014-08-23 | 1393 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  | High with Victim | High with Victims | Minimal | 2 | CHA | 5 |  |  | 2009-10-04 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-0057-12c3b6f53d8-3ce57f1d-d3dc-f | MF-HQ-13449 | HT - HALO TRUST | H/6279 | 43600 | 68.9726 | 34.7308 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-08-15 | 2013-10-23 | 1392-1393 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  |  |  | Minimal | 18 | CHA | 5 |  |  | 2009-10-05 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-0057-12c3b7226a9-983d73fb-f637-1 | MF-HQ-13712 | HT - HALO TRUST | H/6716 | 30000 | 68.9871 | 34.723 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-09-15 | 2014-01-23 | 1392-1393 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  |  |  | Minimal | 2 | CHA | 5 |  |  | 2009-12-02 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-0057-12c3b748823-c399bc1d-112b9- | MF-HQ-13715 | HT - HALO TRUST | H/6712 | 27980 | 68.9773 | 34.7249 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-062/B | Kabul Demining Project-14 /B | DOS | Yes | 2014-09-01 | 2014-09-23 | 1393 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  | High with Victim | High with Victims | Minimal | 4 | CHA | 5 |  |  | 2009-12-02 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-0057-12c3b752a69-b829b673-11a5a- | MF-HQ-13444 | HT - HALO TRUST | H/6275 | 34125 | 68.9782 | 34.724 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-062/B | Kabul Demining Project-14 /B | DOS | Yes | 2014-05-15 | 2014-08-23 | 1393 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  |  |  | Minimal | 2 | CHA | 5 |  |  | 2009-10-07 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-0057-12c3b80c9b6-3b544190-19fca- | MF-HT-981 | HT - HALO TRUST | H/1607 | 52500 | 68.9963 | 34.74 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-05-01 | 2013-07-12 | 1392-1393 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | a |  |  | Minimal | 55 | CHA | 5 |  |  | 2009-09-04 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-0057-12c3b9fa6eb-e7ea4358-2eb6c- | MF-CA-1891 | HT - HALO TRUST | H/1606 | 49400 | 68.9809 | 34.7319 | Open | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-11-01 | 2013-12-23 | 1392-1393 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  | High with Victim | High with Victims | Minimal | 18 | CHA | 5 |  |  | 2008-05-19 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-008e-132c348dac1-1bc799a6-393-bc | MF-15778 | HT - HALO TRUST | H/7671 | 35000 | 69.0281 | 34.746 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/C | Kabul Demining Project-07/C | B-Germany | Yes |  |  | 1392 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  |  |  | Minimal | 257 | CHA | 4 |  |  | 2011-01-09 16:30 | No | Planned
Central | Kabul | Guldara | Qole Ne'mat | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} | c0a8-00f6-1349d69b404-4ada5189-3af-ee | MF-16461 | HT - HALO TRUST | H/7612 | 24500 | 68.9958 | 34.7393 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-04-11 | 2013-06-23 | 1392-1393 | HT | {453E77B9-6719-48C3-A1D3-75175BCF9FDC} |  |  |  | Minimal | 23 | CHA | 5 |  |  | 2011-01-05 16:30 | No | Planned
Central | Kabul | Guldara | Sange Shanda | {EB369965-5278-4C88-8CA9-9C302D12D090} | c0a8-0057-12c3b87cacd-ae8edbe3-1ef60- | MF-CA-794 | HT - HALO TRUST | H/1605 | 74000 | 68.9889 | 34.7522 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-03-16 | 2013-06-14 | 1392 | MDC | {EB369965-5278-4C88-8CA9-9C302D12D090} |  |  |  | Minimal | 93 | CHA | 1 |  |  | 2008-03-01 | No | Complete
Central | Kabul | Kabul | Aliabad | {67EFB6D6-20D9-4C23-801A-F436B6508670} | c0a8-0009-13c0eb8d9bb-c2772036-d90-b6 | Hz-ID-17538 | MCPA - Mine Clearance Planning Agency | AF/0101/00087/BF0906 | 35146 | 69.1386 | 34.5164 | Open | UXO Only | UXO Only | BF |  | MBT Project-020/A | Kabul Demining Project-02 (AT)/A |  |  |  |  | 1394 |  | {67EFB6D6-20D9-4C23-801A-F436B6508670} |  | High | Critical Infrastracture | Substantial | 15952 | SHA | 3 |  |  | 2012-11-20 16:30 | No | Open
Central | Kabul | Kabul | Aliabad | {67EFB6D6-20D9-4C23-801A-F436B6508670} | c0a8-0009-13c0ec4ada8-3bb1c2a3-e23-db | Hz-ID-17539 | MCPA - Mine Clearance Planning Agency | AF/0101/00087/BF0907 | 48500 | 69.1363 | 34.5163 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-06-28 | 2013-10-10 | 1392 | ATC | {67EFB6D6-20D9-4C23-801A-F436B6508670} |  |  |  | Substantial | 15952 | SHA | 3 |  |  | 2012-11-21 16:30 | No | Complete
Central | Kabul | Kabul | Aliabad | {67EFB6D6-20D9-4C23-801A-F436B6508670} | c0a8-0009-13c0f2e7389-f4822e97-1051-4 | Hz-ID-17545 | MCPA - Mine Clearance Planning Agency | AF/0101/00087/BF0914 | 8442 | 69.1318 | 34.5166 | Open | UXO Only | UXO Only | BF |  | MBT Project-020/A | Kabul Demining Project-02 (AT)/A |  |  |  |  | 1394 |  | {67EFB6D6-20D9-4C23-801A-F436B6508670} | , | High | Critical Infrastracture | Substantial | 34015 | SHA | 3 |  |  | 2012-12-18 16:30 | No | Open
Central | Kabul | Kabul | Aliabad | {67EFB6D6-20D9-4C23-801A-F436B6508670} | c0a8-0009-13c1ef3c7ea-87f14e6-519-bb1 | Hz-ID-17537 | MCPA - Mine Clearance Planning Agency | AF/0101/00087/BF0905 | 21024 | 69.136 | 34.5179 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-10-11 | 2013-11-18 | 1392 | ATC | {67EFB6D6-20D9-4C23-801A-F436B6508670} |  |  |  | Substantial | 33951 | SHA | 3 |  |  | 2012-11-19 16:30 | No | Complete
Central | Kabul | Kabul | Aliabad | {67EFB6D6-20D9-4C23-801A-F436B6508670} | c0a8-0009-13c1f2878c8-d431c87f-6d7-72 | Hz-ID-17541 | MCPA - Mine Clearance Planning Agency | AF/0101/00087/BF0910 | 7467 | 69.1326 | 34.5134 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-05-18 | 2013-05-26 | 1392 | ATC | {67EFB6D6-20D9-4C23-801A-F436B6508670} |  |  |  | Substantial | 30309 | SHA | 3 |  |  | 2012-12-09 16:30 | No | Complete
Central | Kabul | Kabul | Aliabad | {67EFB6D6-20D9-4C23-801A-F436B6508670} | c0a8-0009-13c1f2ab29a-385956d0-6f1-d1 | Hz-ID-17542 | MCPA - Mine Clearance Planning Agency | AF/0101/00087/BF0911 | 66770 | 69.1326 | 34.5142 | Open | UXO Only | UXO Only | BF |  | MBT Project-020/A | Kabul Demining Project-02 (AT)/A |  |  |  |  | 1394 |  | {67EFB6D6-20D9-4C23-801A-F436B6508670} | , | Medium | Critical Infrastracture | Substantial | 30309 | SHA | 3 |  |  | 2012-12-10 16:30 | No | Open
Central | Kabul | Kabul | Aliabad | {67EFB6D6-20D9-4C23-801A-F436B6508670} | c0a8-0009-13c1f2d5156-f2801b16-719-8c | Hz-ID-17543 | MCPA - Mine Clearance Planning Agency | AF/0101/00087/BF0912 | 33092 | 69.1327 | 34.5148 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-04-14 | 2013-05-16 | 1392 | ATC | {67EFB6D6-20D9-4C23-801A-F436B6508670} |  |  |  | Substantial | 30309 | SHA | 3 |  |  | 2012-12-12 16:30 | No | Complete
Central | Kabul | Kabul | Aliabad | {67EFB6D6-20D9-4C23-801A-F436B6508670} | c0a8-0009-13c228a175c-79d5e145-c-73b9 | Hz-ID-17544 | MCPA - Mine Clearance Planning Agency | AF/0101/00087/BF0913 | 67984 | 69.1284 | 34.5182 | Open | UXO Only | UXO Only | BF |  | MBT Project-020/A | Kabul Demining Project-02 (AT)/A |  |  |  |  | 1394 |  | {67EFB6D6-20D9-4C23-801A-F436B6508670} | , | High | Critical Infrastracture | Substantial | 34015 | SHA | 3 |  |  | 2012-12-16 16:30 | No | Open
Central | Kabul | Kabul | Aliabad | {67EFB6D6-20D9-4C23-801A-F436B6508670} | c0a8-0009-1455e78be7b-77720807-1990-c | Hz-ID-18625 | MCPA - Mine Clearance Planning Agency | AF/0101/00087/BF0917 | 85840 | 69.1501 | 34.5105 | Open | UXO Only | UXO Only | BF |  | MBT Project-020/A | Kabul Demining Project-02 (AT)/A |  |  |  |  | 1394 |  | {67EFB6D6-20D9-4C23-801A-F436B6508670} |  | High | Critical Infrastracture | Substantial | 50452 | CHA | 3 |  |  | 2014-02-03 16:30 | No | Open
Central | Kabul | Kabul | Chihilsutoon | {6C4DFBED-C514-46CE-8DAF-2BBA12FFADFA} | c0a8-0009-13daf7af7db-58767738-19ff-6 | Hz-ID-17720 | MCPA - Mine Clearance Planning Agency | AF/0101/00197/MF0909 | 31588 | 69.1841 | 34.4555 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes |  |  | 1393 | ATC | {6C4DFBED-C514-46CE-8DAF-2BBA12FFADFA} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 1 |  |  | 2012-11-22 16:30 | No | Planned
Central | Kabul | Kabul | Chihilsutoon | {6C4DFBED-C514-46CE-8DAF-2BBA12FFADFA} | c0a8-0057-12c3b963b4a-3e9e0217-28b1a- | MF-CA-1659 | MCPA - Mine Clearance Planning Agency | AF/0101/00197/MF0864 | 40100 | 69.1692 | 34.4652 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes |  |  | 1392 | MDC | {6C4DFBED-C514-46CE-8DAF-2BBA12FFADFA} |  |  |  | Substantial | 153 | CHA | 1 |  |  | 2008-10-22 | No | Complete
Central | Kabul | Kabul | Qargha | {63F5E0B6-FAC7-441E-B921-D0AD57BE3E74} | c0a8-0009-1453fd75ca1-4c9ff860-e0f-11 | Hz-ID-18595 | ATC - Afghan Technical Consultants | AF/0108/00536/BF0918 | 683030 | 69.0353 | 34.561 | Worked on | UXO Only | UXO Only | BF | 1393 | MBT Project-059/A | Kabul Demining Project-10/A | DOS | Yes |  |  | 1393 | ATC | {63F5E0B6-FAC7-441E-B921-D0AD57BE3E74} |  | Medium | Critical Infrastracture | Substantial | 276 | CHA | 3 |  |  | 2014-03-08 16:30 | No | Planned
Central | Kabul | Kabul | Qargha | {63F5E0B6-FAC7-441E-B921-D0AD57BE3E74} | c0a8-0009-1467f542ab4-5cc12743-2048-7 | Hz-ID-18820 | ATC - Afghan Technical Consultants | AF/0101/00536/BF0919 | 36726 | 69.0307 | 34.5492 | Open | UXO Only | UXO Only | BF |  | MBT Project-232 | Kabul Demining Project-21 | B-Japan |  |  |  | 1393 |  | {63F5E0B6-FAC7-441E-B921-D0AD57BE3E74} |  | Medium | Critical Infrastracture | Substantial | 463 | CHA | 3 |  |  | 2014-06-04 16:30 | No | Planned
Central | Kabul | Kabul | Qargha | {63F5E0B6-FAC7-441E-B921-D0AD57BE3E74} | c0a8-008e-132ae4b8e64-ca80b64b-1165-f | BF-HQ-13351 | MCPA - Mine Clearance Planning Agency | AF/0101/00536/BF0885 | 174544 | 69.0653 | 34.5548 | Closed | UXO Only | UXO Only | BF | 1393 | MBT Project-059/A | Kabul Demining Project-10/A | DOS | Yes | 2014-05-01 | 2014-09-30 | 1393 | ATC | {63F5E0B6-FAC7-441E-B921-D0AD57BE3E74} | , |  |  | Substantial | 20 | CHA | 5 |  |  | 2009-11-03 | No | Planned
Central | Kabul | Kalakan | Chahartut | {DC05995C-D51D-42FA-9265-9C73870A624D} | c0a8-0009-1454517358f-7e480a70-1e3-5f | Hz-ID-18553 | HT - HALO TRUST | H/8534 | 68788 | 69.2086 | 34.7887 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059/B | Kabul Demining Project-10/B | B-Germany | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {DC05995C-D51D-42FA-9265-9C73870A624D} |  | Low | Agriculture Blocked | Minimal | 331 | CHA | 4 |  |  | 2014-03-05 16:30 | No | Planned
Central | Kabul | Kalakan | Chahartut | {DC05995C-D51D-42FA-9265-9C73870A624D} | c0a8-0057-12c3baf4294-5e01d690-38140- | MF-HT-1372 | HT - HALO TRUST | H/3876 | 29700 | 69.2014 | 34.7851 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-04-03 | 2013-06-18 | 1392 | HT | {DC05995C-D51D-42FA-9265-9C73870A624D} |  |  |  | Minimal | 3 | CHA | 4 |  |  | 2007-12-01 | No | Complete
Central | Kabul | Kalakan | Kalakan | {443833B4-4BE7-431A-A0F0-1FC36DD1D7BF} | c0a8-0009-13f184bef3d-4958012c-44fe-5 | Hz-ID-17952 | HT - HALO TRUST | H/8506 | 609 | 69.152 | 34.7923 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-06-18 | 2013-07-11 | 1392-1393 | HT | {443833B4-4BE7-431A-A0F0-1FC36DD1D7BF} |  |  |  | Minimal | 192 | CHA | 2 |  |  | 2013-05-08 16:30 | No | Planned
Central | Kabul | Kalakan | Zemma | {A3A7650F-D164-40AF-9EC1-7CE061494680} | c0a8-0009-144060ed98c-274f132-7f3-70c | Hz-ID-18486 | HT - HALO TRUST | H/8529 | 25800 | 69.1867 | 34.7216 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-020/A | Kabul Demining Project-02 (AT)/A |  | No |  |  | 1394 | ATC | {A3A7650F-D164-40AF-9EC1-7CE061494680} |  | Low | Agriculture Blocked | Minimal | 18 | CHA | 5 |  |  | 2014-01-19 16:30 | No | Open
Central | Kabul | Kalakan | Zemma | {A3A7650F-D164-40AF-9EC1-7CE061494680} | c0a8-008e-1328fa1cb89-27056a72-2043-7 | MF-16123 | MCPA - Mine Clearance Planning Agency | AF/0104/00318/MF0027 | 31205 | 69.1942 | 34.7243 | Closed | AP Only | AP Only | MineField | 1391/1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-01-01 | 2013-04-15 | 1392 | HT | {A3A7650F-D164-40AF-9EC1-7CE061494680} |  |  |  | Minimal | 229 |  | 4 |  |  | 2011-06-05 16:30 | No | Complete
Central | Kabul | Khaki Jabbar | Baghgay | {AAD9D967-2FA7-406B-808A-B50D470636E5} | c0a8-0009-13daf7bc44d-1e5250d0-1a51-7 | Hz-ID-17716 | MCPA - Mine Clearance Planning Agency | AF/0111/00138/MF0373 | 68973 | 69.332 | 34.3702 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {AAD9D967-2FA7-406B-808A-B50D470636E5} |  | Low | Agriculture Blocked | Moderate | 33 | CHA | 5 |  |  | 2013-01-31 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Baghgay | {AAD9D967-2FA7-406B-808A-B50D470636E5} | c0a8-0009-13daf88e0ad-d606f8bd-1d8c-4 | Hz-ID-17715 | MCPA - Mine Clearance Planning Agency | AF/0111/00138/MF0372 | 74108 | 69.332 | 34.3702 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {AAD9D967-2FA7-406B-808A-B50D470636E5} |  | Low | Agriculture Blocked | Moderate | 10 | CHA | 5 |  |  | 2013-01-27 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Baghgay | {AAD9D967-2FA7-406B-808A-B50D470636E5} | c0a8-0009-13daf892c7c-e0250010-1db9-9 | Hz-ID-17713 | MCPA - Mine Clearance Planning Agency | AF/0111/00138/MF0371 | 54118 | 69.3263 | 34.369 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {AAD9D967-2FA7-406B-808A-B50D470636E5} |  | Low | Agriculture Blocked | Moderate | 10 | CHA | 5 |  |  | 2013-01-27 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Bato Khel | {614A5224-EAC6-4D6D-9B71-419BD2FDAC65} | c0a8-0057-12c3b877906-bb9c77ae-1eba7- | MF-HQ-14107 | MCPA - Mine Clearance Planning Agency | AF/0111/00289/MF0322 | 72717 | 69.3588 | 34.2621 | Open | AP Only | AP Only | MineField |  | MBT Project-019 | Kabul Demining Project-01 (AT) |  |  |  |  | 1394 |  | {614A5224-EAC6-4D6D-9B71-419BD2FDAC65} |  | Low | Agriculture Blocked | Moderate | 70 | SHA | 3 |  |  | 2010-02-01 | No | Open
Central | Kabul | Khaki Jabbar | Bato Khel | {614A5224-EAC6-4D6D-9B71-419BD2FDAC65} | c0a8-0057-12c3b98624c-99c8bcf-2a14c-a | MF-HQ-14108 | MCPA - Mine Clearance Planning Agency | AF/0111/00289/MF0323 | 172757 | 69.3575 | 34.2619 | Open | AP Only | AP Only | MineField |  | MBT Project-019 | Kabul Demining Project-01 (AT) |  |  |  |  | 1394 |  | {614A5224-EAC6-4D6D-9B71-419BD2FDAC65} |  | Low | Agriculture Blocked | Moderate | 29 | CHA | 3 |  |  | 2010-02-01 | No | Open
Central | Kabul | Khaki Jabbar | Bato Khel | {614A5224-EAC6-4D6D-9B71-419BD2FDAC65} | c0a8-0057-12c3b9fbc4f-d63f1a01-2ec46- | MF-HQ-14105 | MCPA - Mine Clearance Planning Agency | AF/0111/00289/MF0320 | 50000 | 69.3708 | 34.262 | Open | AP Only | AP Only | MineField | Blank | MBT Project-008 | Kabul Demining Project-05 | DOS | No | 2012-03-01 | 2012-07-31 | 1395 | Blank | {614A5224-EAC6-4D6D-9B71-419BD2FDAC65} |  | Low | Agriculture Blocked | Moderate | 8 | CHA | 4 |  |  | 2010-02-01 | No | Open
Central | Kabul | Khaki Jabbar | Bato Khel | {614A5224-EAC6-4D6D-9B71-419BD2FDAC65} | c0a8-0057-12c3ba8446a-3ee3782c-33f89- | MF-HQ-14106 | MCPA - Mine Clearance Planning Agency | AF/0111/00289/MF0321 | 59075 | 69.3667 | 34.2606 | Open | AP Only | AP Only | MineField |  | MBT Project-008 | Kabul Demining Project-05 | DOS |  |  |  | 1395 |  | {614A5224-EAC6-4D6D-9B71-419BD2FDAC65} |  | Low | Agriculture Blocked | Moderate | 22 | CHA | 4 |  |  | 2010-02-01 | No | Open
Central | Kabul | Khaki Jabbar | Chakari | {39008FCF-F2AC-463C-94BC-582E4B9331F7} | c0a8-0009-13daf85d884-5ee01564-1c38-d | Hz-ID-17718 | MCPA - Mine Clearance Planning Agency | AF/0111/00145/MF0376 | 35128 | 69.458 | 34.3446 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {39008FCF-F2AC-463C-94BC-582E4B9331F7} |  | Low | Agriculture Blocked | Moderate | 6 | CHA | 5 |  |  | 2013-01-30 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Chakari | {39008FCF-F2AC-463C-94BC-582E4B9331F7} | c0a8-0057-12c3b81361d-dd7e6a91-1a4a4- | MF-HQ-14091 | MCPA - Mine Clearance Planning Agency | AF/0111/00145/MF0330 | 6980 | 69.4456 | 34.3562 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-03-16 | 2013-04-30 | 1392 | MDC | {39008FCF-F2AC-463C-94BC-582E4B9331F7} |  |  |  | Moderate | 96 | CHA | 4 | Yes |  | 2010-02-01 | No | Complete
Central | Kabul | Khaki Jabbar | Chakari | {39008FCF-F2AC-463C-94BC-582E4B9331F7} | c0a8-0057-12c3b844b1c-3420f713-1c7da- | MF-HQ-14090 | MCPA - Mine Clearance Planning Agency | AF/0111/00145/MF0329 | 10748 | 69.434 | 34.3529 | Open | AT Only | AT Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {39008FCF-F2AC-463C-94BC-582E4B9331F7} |  | Low | Comunity Centers | Moderate | 96 | CHA | 5 |  |  | 2010-02-01 | No | Open
Central | Kabul | Khaki Jabbar | Chakari | {39008FCF-F2AC-463C-94BC-582E4B9331F7} | c0a8-0057-12c3b8e37a2-ade56b0a-236f3- | MF-HQ-14087 | MCPA - Mine Clearance Planning Agency | AF/0111/00145/MF0326 | 28732 | 69.457 | 34.3422 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {39008FCF-F2AC-463C-94BC-582E4B9331F7} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2010-02-01 | No | Open
Central | Kabul | Khaki Jabbar | Chakari | {39008FCF-F2AC-463C-94BC-582E4B9331F7} | c0a8-0057-12c3b999ec8-2318efa8-2ae69- | MF-HQ-14086 | MCPA - Mine Clearance Planning Agency | AF/0111/00145/MF0325 | 5324 | 69.4528 | 34.3431 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {39008FCF-F2AC-463C-94BC-582E4B9331F7} |  | Low | Agriculture Blocked | Moderate | 17 | CHA | 5 |  |  | 2010-02-01 | No | Open
Central | Kabul | Khaki Jabbar | Chakari | {39008FCF-F2AC-463C-94BC-582E4B9331F7} | c0a8-0057-12c3ba0d9d9-7557f90b-2f74e- | MF-HQ-14085 | MCPA - Mine Clearance Planning Agency | AF/0111/00145/MF0324 | 24293 | 69.4578 | 34.3546 | Open | AT Only | AT Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {39008FCF-F2AC-463C-94BC-582E4B9331F7} |  | Low | Agriculture Blocked | Moderate | 35 | CHA | 5 |  |  | 2010-03-31 | No | Open
Central | Kabul | Khaki Jabbar | Chakari | {39008FCF-F2AC-463C-94BC-582E4B9331F7} | c0a8-0057-12c3ba30ac2-59bb9a9b-30c95- | MF-HQ-14092 | MCPA - Mine Clearance Planning Agency | AF/0111/00145/MF0331 | 26250 | 69.4521 | 34.3347 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {39008FCF-F2AC-463C-94BC-582E4B9331F7} |  | Low | Water Blocked | Moderate | 5 | CHA | 5 |  |  | 2010-03-29 | No | Open
Central | Kabul | Khaki Jabbar | Chalaw(Woli Khel) | {C1178817-CD87-41A2-BD44-72E28D8503EC} | c0a8-0057-12c3b85cce4-3c803ad5-1d927- | MF-HQ-13395 | MCPA - Mine Clearance Planning Agency | AF/0111/00137/MF0279 | 5900 | 69.459 | 34.3678 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes |  |  | 1392 | MDC | {C1178817-CD87-41A2-BD44-72E28D8503EC} |  |  |  | Moderate | 329 | CHA | 2 |  |  | 2009-09-12 | No | Complete
Central | Kabul | Khaki Jabbar | Chalaw(Woli Khel) | {C1178817-CD87-41A2-BD44-72E28D8503EC} | c0a8-0057-12c3b85d0ab-954f2aa9-1d94f- | MF-HQ-13394 | MCPA - Mine Clearance Planning Agency | AF/0111/00137/MF0276 | 102084 | 69.4621 | 34.3704 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-07-07 | 2013-08-31 | 1392 | MDC | {C1178817-CD87-41A2-BD44-72E28D8503EC} |  |  |  | Moderate | 344 | CHA | 2 | No |  | 2009-09-08 | No | Complete
Central | Kabul | Khaki Jabbar | Chalaw(Woli Khel) | {C1178817-CD87-41A2-BD44-72E28D8503EC} | c0a8-0057-12c3b85d2ae-41df5718-1d962- | MF-HQ-13393 | MCPA - Mine Clearance Planning Agency | AF/0111/00137/MF0265 | 45979 | 69.4595 | 34.373 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-09-08 | 2013-10-30 | 1392 | MDC | {C1178817-CD87-41A2-BD44-72E28D8503EC} |  |  |  | Moderate | 329 | CHA | 2 |  |  | 2009-09-06 | No | Complete
Central | Kabul | Khaki Jabbar | Chalaw(Woli Khel) | {C1178817-CD87-41A2-BD44-72E28D8503EC} | c0a8-0057-12c3b9005d4-f1345078-24a09- | MF-HQ-13392 | MCPA - Mine Clearance Planning Agency | AF/0111/00155/MF0264 | 4480 | 69.462 | 34.3551 | Open | AP Only | AP Only | MineField |  | MBT Project-006 | Kabul Demining Project-02 | DOS |  |  |  | 1394 |  | {C1178817-CD87-41A2-BD44-72E28D8503EC} |  | High with Victim | High with Victims | Moderate | 29 | CHA | 2 |  |  | 2009-09-03 | No | Open
Central | Kabul | Khaki Jabbar | Chalaw(Woli Khel) | {C1178817-CD87-41A2-BD44-72E28D8503EC} | c0a8-0057-12c3b90097b-a8a802ed-24a30- | MF-HQ-13390 | MCPA - Mine Clearance Planning Agency | AF/0111/00137/MF0251 | 28514 | 69.4639 | 34.3609 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-006/A | Kabul Demining Project-02/A | DOS | Yes | 2013-07-01 | 2013-09-30 | 1392 | OMAR | {C1178817-CD87-41A2-BD44-72E28D8503EC} |  |  |  | Moderate | 45 | CHA | 2 |  |  | 2009-08-30 | No | Complete
Central | Kabul | Khaki Jabbar | Chalaw(Woli Khel) | {C1178817-CD87-41A2-BD44-72E28D8503EC} | c0a8-0057-12c3b900da0-81fe6bf4-24a5c- | MF-HQ-13391 | MCPA - Mine Clearance Planning Agency | AF/0111/00137/MF0252 | 46755 | 69.4646 | 34.3586 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-006/A | Kabul Demining Project-02/A | DOS | Yes | 2013-06-08 | 2013-06-30 | 1392 | OMAR | {C1178817-CD87-41A2-BD44-72E28D8503EC} |  |  |  | Moderate | 29 | CHA | 2 |  |  | 2009-09-01 | No | Complete
Central | Kabul | Khaki Jabbar | Charwazi | {3B528833-205A-4204-89F4-54ADA2278044} | c0a8-0057-12fd32ba822-3e623c59-27e0-6 | MF-HQ-13411 | MCPA - Mine Clearance Planning Agency | AF/0111/00139/MF0289 | 116768 | 69.3308 | 34.3201 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {3B528833-205A-4204-89F4-54ADA2278044} |  | Low | Agriculture Blocked | Moderate | 11 | CHA | 5 |  |  | 2009-09-17 | No | Open
Central | Kabul | Khaki Jabbar | Charwazi | {3B528833-205A-4204-89F4-54ADA2278044} | c0a8-0057-12fd32cba58-e16b6c3c-27f5-5 | MF-HQ-13377 | MCPA - Mine Clearance Planning Agency | AF/0111/00139/MF0270 | 52724 | 69.345 | 34.3213 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {3B528833-205A-4204-89F4-54ADA2278044} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2009-09-16 | No | Open
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-1313704c6f1-f9164da0-286-7e | MF-HQ-13079 | MCPA - Mine Clearance Planning Agency | AF/0112/00162/MF0210 | 54779 | 69.5316 | 34.514 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  | Low | Agriculture Blocked | Moderate | 71 | CHA | 4 |  |  | 2009-07-30 | No | Planned
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-131a2684625-8f3bc2c5-1c5b-8 | MF-HQ-13047 | MCPA - Mine Clearance Planning Agency | AF/0112/00162/MF0226 | 49000 | 69.5295 | 34.5237 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes |  |  | 1392-1393 | DDG | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  |  |  | Moderate | 8 | CHA | 5 |  |  | 2009-08-16 | No | Planned
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-131a269b202-e1974cbe-1cd5-7 | MF-HQ-13042 | MCPA - Mine Clearance Planning Agency | AF/0112/00162/MF0223 | 50425 | 69.5349 | 34.5191 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-007 | Kabul Demining Project-04 | DOS | Yes | 2013-05-11 | 2013-08-30 | 1392 | ATC | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  |  |  | Moderate | 328 | CHA | 3 |  |  | 2009-08-02 | No | Complete
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-131a26b93da-2b343d3a-1d09-b | MF-HQ-13082 | MCPA - Mine Clearance Planning Agency | AF/0111/00162/MF0222 | 22408 | 69.5298 | 34.524 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  | Low | Agriculture Blocked | Moderate | 24 | CHA | 5 |  |  | 2009-08-11 | No | Open
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-131a26cbd84-4b5a2256-1d30-a | MF-HQ-13081 | MCPA - Mine Clearance Planning Agency | AF/0112/00162/MF0221 | 8903 | 69.5378 | 34.5179 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  | Low | Agriculture Blocked | Moderate | 377 | CHA | 4 |  |  | 2009-08-09 | No | Planned
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-131a26dbb7c-77c7c7ab-1d55-5 | MF-HQ-13044 | MCPA - Mine Clearance Planning Agency | AF/0112/00162/MF0224 | 110835 | 69.5371 | 34.5179 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes | 2014-07-02 | 2014-09-30 | 1393 | OMAR | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  | Low | Agriculture Blocked | Moderate | 377 | CHA | 4 |  |  | 2009-08-04 | No | Planned
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-131a26eaac6-fb005a4a-1d7b-5 | MF-HQ-13048 | MCPA - Mine Clearance Planning Agency | AF/0112/00162/MF0227 | 35705 | 69.5371 | 34.5179 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  | Low | Agriculture Blocked | Moderate | 377 | CHA | 4 |  |  | 2009-08-06 | No | Planned
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-131a26fa2d5-874dc238-1da5-5 | MF-HQ-13076 | MCPA - Mine Clearance Planning Agency | AF/0112/00162/MF0209 | 50071 | 69.5283 | 34.5171 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-008/A | Kabul Demining Project-05/A | DOS | Yes | 2013-12-01 | 2014-04-30 | 1392 | DDG | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  |  |  | Moderate | 71 | CHA | 4 |  |  | 2009-07-28 | No | Complete
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-131a2708aa2-3e135843-1dd4-6 | MF-HQ-13072 | MCPA - Mine Clearance Planning Agency | AF/0112/00162/MF0204 | 104333 | 69.5181 | 34.5115 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-007 | Kabul Demining Project-04 | DOS | Yes | 2013-11-16 | 2014-04-30 | 1392 | ATC | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  |  |  | Moderate | 68 | CHA | 4 |  |  | 2009-07-21 | No | Complete
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-131a2716c38-606e67a7-1e01-7 | MF-HQ-13073 | MCPA - Mine Clearance Planning Agency | AF/0111/00162/MF0205 | 40575 | 69.5181 | 34.5115 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes | 2014-06-09 | 2014-07-15 | 1393 | OMAR | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  | Low | Agriculture Blocked | Moderate | 58 | CHA | 4 |  |  | 2009-07-23 | No | Planned
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-131ad71e0f1-6ce4aead-210d-a | MF-HQ-13074 | MCPA - Mine Clearance Planning Agency | AF/0112/00162/MF0208 | 64060 | 69.5228 | 34.5151 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-007 | Kabul Demining Project-04 | DOS | Yes | 2013-05-11 | 2013-08-05 | 1392 | ATC | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  |  |  | Moderate | 14 | CHA | 3 |  |  | 2009-07-26 | No | Complete
Central | Kabul | Khaki Jabbar | Chawki | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} | c0a8-008e-131ad72bb77-992bdb50-2441-b | MF-HQ-13046 | MCPA - Mine Clearance Planning Agency | AF/0112/00162/MF0225 | 94425 | 69.5278 | 34.5179 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-008/A | Kabul Demining Project-05/A | DOS | Yes | 2013-11-03 | 2014-04-30 | 1392 | DDG | {673E52FB-9D48-4B2A-B9AB-0BA155EEDB24} |  |  |  | Moderate | 8 | CHA | 4 |  |  | 2009-08-13 | No | Complete
Central | Kabul | Khaki Jabbar | Chinari | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} | c0a8-0057-12c3bb1b148-adf955bb-3985e- | MF-CA-1729 | MCPA - Mine Clearance Planning Agency | AF/0110/00164/MF0124 | 167254 | 69.4903 | 34.4976 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-09-09 | No | Open
Central | Kabul | Khaki Jabbar | Chinari | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} | c0a8-0057-12c3bb1b35a-10e3ecd3-39873- | MF-CA-1731 | MCPA - Mine Clearance Planning Agency | AF/0110/00164/MF0129 | 28945 | 69.5004 | 34.5017 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-09-09 | No | Open
Central | Kabul | Khaki Jabbar | Chinari | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} | c0a8-0057-12fd330280f-819089ae-2861-2 | MF-CA-1633 | MCPA - Mine Clearance Planning Agency | AF/0110/00164/MF0142 | 55443 | 69.5085 | 34.4983 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2008-09-16 | No | Open
Central | Kabul | Khaki Jabbar | Chinari | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} | c0a8-0057-12fd331ebe5-86dd73f6-28cf-6 | MF-CA-1727 | MCPA - Mine Clearance Planning Agency | AF/0110/00164/MF0135 | 79067 | 69.4789 | 34.4591 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2008-09-11 | No | Open
Central | Kabul | Khaki Jabbar | Chinari | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} | c0a8-0057-12fd3331a0c-356ae3b6-28e3-6 | MF-CA-1871 | MCPA - Mine Clearance Planning Agency | AF/0110/00164/MF0134 | 48374 | 69.4812 | 34.4755 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-09-10 | No | Open
Central | Kabul | Khaki Jabbar | Chinari | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} | c0a8-008e-131a27260b7-e07e874b-1e52-d | MF-CA-1639 | MCPA - Mine Clearance Planning Agency | AF/0110/00164/MF0143 | 152442 | 69.5117 | 34.5069 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-007 | Kabul Demining Project-04 | DOS | Yes | 2013-07-22 | 2013-10-05 | 1392 | ATC | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} |  |  |  | Moderate | 15 | CHA | 3 |  |  | 2008-09-18 | No | Complete
Central | Kabul | Khaki Jabbar | Chinari | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} | c0a8-008e-131a273761c-bf983322-1e88-a | MF-CA-1629 | MCPA - Mine Clearance Planning Agency | AF/0110/00164/MF0125 | 85224 | 69.5085 | 34.4983 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2008-09-13 | No | Open
Central | Kabul | Khaki Jabbar | Chinari | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} | c0a8-008e-131a274741c-22af2256-1eb2-6 | MF-CA-1730 | MCPA - Mine Clearance Planning Agency | AF/0110/00164/MF0136 | 19852 | 69.478 | 34.4723 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {9C0A339E-12FC-49B1-BA78-8A20DC04F15C} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-09-11 | No | Open
Central | Kabul | Khaki Jabbar | Darband | {7023ED14-36C9-48F9-90E1-35BD2A56081E} | c0a8-0009-13daf7b5ddd-cc49de69-1a2b-a | Hz-ID-17717 | MCPA - Mine Clearance Planning Agency | AF/0111/00131/MF0375 | 14225 | 69.3933 | 34.2718 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-06-24 | 2013-07-24 | 1392 | MDC | {7023ED14-36C9-48F9-90E1-35BD2A56081E} |  |  |  | Moderate | 1 | CHA | 5 |  |  | 2013-01-30 16:30 | No | Complete
Central | Kabul | Khaki Jabbar | Darband | {7023ED14-36C9-48F9-90E1-35BD2A56081E} | c0a8-0009-13e7d4f754b-35d85b96-1e43-5 | Hz-ID-17857 | MCPA - Mine Clearance Planning Agency | AF/0111/00131/MF0377 | 100201 | 69.3845 | 34.2847 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-08-13 | 2013-10-03 | 1392 | MDC | {7023ED14-36C9-48F9-90E1-35BD2A56081E} |  |  |  | Moderate | 130 | CHA | 5 |  |  | 2013-03-11 16:30 | No | Complete
Central | Kabul | Khaki Jabbar | Darband | {7023ED14-36C9-48F9-90E1-35BD2A56081E} | c0a8-0009-13e7d50a0ea-6cdb9bf8-1e6f-d | Hz-ID-17855 | MCPA - Mine Clearance Planning Agency | AF/0111/00131/MF0374 | 106562 | 69.3738 | 34.2839 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-06-27 | 2013-10-16 | 1392 | MDC | {7023ED14-36C9-48F9-90E1-35BD2A56081E} |  |  |  | Moderate | 14 | CHA | 5 |  |  | 2013-03-12 16:30 | No | Complete
Central | Kabul | Khaki Jabbar | Darband | {7023ED14-36C9-48F9-90E1-35BD2A56081E} | c0a8-0057-12c3b84e19e-b990be8a-1cec2- | MF-HQ-14111 | MCPA - Mine Clearance Planning Agency | AF/0111/00131/MF0337 | 71840 | 69.3766 | 34.2803 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-06-11 | 2013-07-06 | 1392 | MDC | {7023ED14-36C9-48F9-90E1-35BD2A56081E} |  |  |  | Moderate | 74 | CHA | 3 |  |  | 2010-02-01 | No | Complete
Central | Kabul | Khaki Jabbar | Darband | {7023ED14-36C9-48F9-90E1-35BD2A56081E} | c0a8-0057-12c3b8dce56-b9698c91-231dc- | MF-HQ-14109 | MCPA - Mine Clearance Planning Agency | AF/0111/00131/MF0335 | 43394 | 69.3981 | 34.2788 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-07-25 | 2013-08-17 | 1392 | MDC | {7023ED14-36C9-48F9-90E1-35BD2A56081E} |  |  |  | Moderate | 13 | CHA | 5 |  |  | 2010-02-01 | No | Complete
Central | Kabul | Khaki Jabbar | Darband | {7023ED14-36C9-48F9-90E1-35BD2A56081E} | c0a8-0057-12c3b9fcd6e-c3bdf5a6-2ecea- | MF-HQ-14110 | MCPA - Mine Clearance Planning Agency | AF/0111/00131/MF0336 | 120883 | 69.3965 | 34.2908 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-05-18 | 2013-07-25 | 1392 | MDC | {7023ED14-36C9-48F9-90E1-35BD2A56081E} |  |  |  | Moderate | 62 | CHA | 4 |  |  | 2010-02-01 | No | Complete
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3b6d05ce-398f4684-b7da-b | MF-HQ-13407 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0305 | 40000 | 69.4579 | 34.4211 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2009-10-20 | No | Open
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3b74c66a-d08c8bde-115b5- | MF-HQ-13408 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0306 | 183036 | 69.4636 | 34.412 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2009-10-19 | No | Open
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3b786f0e-6fee016e-140ae- | MF-HQ-13409 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0307 | 133715 | 69.4636 | 34.412 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  | Low | Agriculture Blocked | Moderate | 4 | CHA | 5 |  |  | 2009-10-21 | No | Open
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3b7d6b4a-634548e5-17a58- | MF-HQ-13140 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0214 | 75472 | 69.4389 | 34.3903 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-230 | Kabul Demining Project-19 | DOS | Yes |  |  | 1396 | OMAR | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  | Low | Agriculture Blocked | Moderate | 22 | CHA | 5 |  |  | 2009-07-27 | No | Open
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3b7d703a-c6d70805-17a8a- | MF-HQ-13382 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0215 | 57801 | 69.4338 | 34.3881 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-007 | Kabul Demining Project-04 | DOS | Yes | 2013-09-28 | 2013-12-29 | 1392 | ATC | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  |  |  | Moderate | 7 | CHA | 3 |  |  | 2009-07-29 | No | Complete
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3b7d725c-632a214a-17aa2- | MF-HQ-13025 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0200 | 60292 | 69.4365 | 34.4041 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes |  |  | 1393 | OMAR | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  |  |  | Moderate | 56 | CHA | 4 |  |  | 2009-07-25 | No | Planned
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3b7d7b12-55ee4e3e-17b00- | MF-HQ-13092 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0199 | 32813 | 69.4365 | 34.4041 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes |  |  | 1393 | OMAR | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  |  |  | Moderate | 50 | CHA | 4 |  |  | 2009-07-23 | No | Planned
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3b7d7d34-79fb4748-17b16- | MF-HQ-13129 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0211 | 53980 | 69.4377 | 34.3986 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes |  |  | 1393 | OMAR | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  |  |  | Moderate | 71 | CHA | 4 |  |  | 2009-07-28 | No | Planned
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3b7d7f47-3c438291-17b2d- | MF-HQ-13130 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0212 | 68912 | 69.4389 | 34.3903 | Open | AP Only | AP Only | MineField | Blank | MBT Project-230 | Kabul Demining Project-19 |  | No |  |  | 1396 | None | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  | Low | Agriculture Blocked | Moderate | 22 | CHA | 5 |  |  | 2009-07-28 | No | Open
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3b8dae97-8185c4f1-23076- | MF-HQ-13097 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0185 | 21000 | 69.4303 | 34.3894 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-07-25 | 2013-09-15 | 1392 | MDC | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  |  |  | Moderate | 30 | CHA | 2 |  |  | 2009-07-13 | No | Complete
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3b8db70f-bfb4866-230d2-a | MF-HQ-13126 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0191 | 234675 | 69.4292 | 34.398 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes | 2014-04-01 | 2014-08-31 | 1393 | OMAR | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | Planned Year and Agency Name removed | Low | Agriculture Blocked | Moderate | 334 | CHA | 4 |  |  | 2009-07-19 | No | Planned
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3bb8aa15-5de72934-3d8a1- | MF-HQ-13010 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0178 | 136864 | 69.4136 | 34.4136 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-232 | Kabul Demining Project-21 | B-Japan | Yes |  |  | 1393 | ATC | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  | High Requested | Resettlment/Local Request | Moderate | 4 | CHA | 5 | Yes | Dear Matin Sahib! Please find attached ATC Japan De-mining project 1393 hazard list along with local people request for clearance of the selected area, in the query list the classification is low, the issue is already shared it with RO office as well. | 2009-07-06 | No | Planned
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3bb8ad02-2e44d054-3d8b8- | MF-HQ-13009 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0172 | 116688 | 69.4086 | 34.4047 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-232 | Kabul Demining Project-21 | B-Japan | Yes |  |  | 1393 | ATC | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  | High Requested | Resettlment/Local Request | Moderate | 5 | CHA | 5 | Yes | Dear Matin Sahib! Please find attached ATC Japan De-mining project 1393 hazard list along with local people request for clearance of the selected area, in the query list the classification is low, the issue is already shared it with RO office as well. | 2009-07-04 | No | Planned
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3bb8af33-72ba42a3-3d8cd- | MF-HQ-13008 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0177 | 162900 | 69.4136 | 34.4136 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-232 | Kabul Demining Project-21 | B-Japan | Yes |  |  | 1393 | ATC | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  | High Requested | Resettlment/Local Request | Moderate | 3 | CHA | 5 | Yes | Dear Matin Sahib! Please find attached ATC Japan De-mining project 1393 hazard list along with local people request for clearance of the selected area, in the query list the classification is low, the issue is already shared it with RO office as well. | 2009-07-07 | No | Planned
Central | Kabul | Khaki Jabbar | Dawran Khel | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} | c0a8-0057-12c3bb8b1b3-40a77d91-3d8e1- | MF-HQ-13007 | MCPA - Mine Clearance Planning Agency | AF/0111/00158/MF0171 | 78188 | 69.4086 | 34.4047 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-232 | Kabul Demining Project-21 | B-Japan | Yes |  |  | 1393 | ATC | {FCB5CEE2-3A5B-4B5E-98A7-A8E9F85A595E} |  | High Requested | Resettlment/Local Request | Moderate | 19 | CHA | 5 | Yes | Dear Matin Sahib! Please find attached ATC Japan De-mining project 1393 hazard list along with local people request for clearance of the selected area, in the query list the classification is low, the issue is already shared it with RO office as well. | 2009-07-05 | No | Planned
Central | Kabul | Khaki Jabbar | Ghozgay | {191F1415-A042-4ECB-AB9D-0A86C27409B4} | c0a8-0009-13daf7b1a2a-a3af8a35-1a16-9 | Hz-ID-17712 | MCPA - Mine Clearance Planning Agency | AF/0111/00142/MF0370 | 85082 | 69.3854 | 34.326 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {191F1415-A042-4ECB-AB9D-0A86C27409B4} |  | Low | Agriculture Blocked | Moderate | 17 | CHA | 5 |  |  | 2013-01-17 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Ghozgay | {191F1415-A042-4ECB-AB9D-0A86C27409B4} | c0a8-0009-13daf7d5fa1-f9aed5fa-1af3-3 | Hz-ID-17703 | MCPA - Mine Clearance Planning Agency | AF/0111/00142/MF0361 | 74804 | 69.3854 | 34.326 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {191F1415-A042-4ECB-AB9D-0A86C27409B4} |  | Low | Agriculture Blocked | Moderate | 20 | CHA | 5 |  |  | 2013-01-15 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Ghozgay | {191F1415-A042-4ECB-AB9D-0A86C27409B4} | c0a8-0009-13daf7dad82-749930fd-1b0a-f | Hz-ID-17704 | MCPA - Mine Clearance Planning Agency | AF/0111/00142/MF0362 | 72995 | 69.3817 | 34.3238 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {191F1415-A042-4ECB-AB9D-0A86C27409B4} |  | Low | Agriculture Blocked | Moderate | 18 | CHA | 5 |  |  | 2013-01-14 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Ghozgay | {191F1415-A042-4ECB-AB9D-0A86C27409B4} | c0a8-0009-13daf7df4ce-27a768d0-1b21-c | Hz-ID-17705 | MCPA - Mine Clearance Planning Agency | AF/0111/00142/MF0363 | 80595 | 69.373 | 34.321 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {191F1415-A042-4ECB-AB9D-0A86C27409B4} |  | Low | Agriculture Blocked | Moderate | 22 | CHA | 5 |  |  | 2013-01-16 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Ghozgay | {191F1415-A042-4ECB-AB9D-0A86C27409B4} | c0a8-0009-13daf84dc8a-60d80694-1bd4-d | Hz-ID-17707 | MCPA - Mine Clearance Planning Agency | AF/0111/00142/MF0365 | 227622 | 69.3622 | 34.3137 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {191F1415-A042-4ECB-AB9D-0A86C27409B4} |  | Low | Agriculture Blocked | Moderate | 16 | CHA | 5 |  |  | 2013-01-15 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Ghozgay | {191F1415-A042-4ECB-AB9D-0A86C27409B4} | c0a8-0009-13dc012e68a-17045fc5-681b-1 | Hz-ID-17708 | MCPA - Mine Clearance Planning Agency | AF/0111/00142/MF0366 | 134830 | 69.3568 | 34.3134 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {191F1415-A042-4ECB-AB9D-0A86C27409B4} |  | Low | Agriculture Blocked | Moderate | 6 | CHA | 5 |  |  | 2013-01-15 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Ghozgay | {191F1415-A042-4ECB-AB9D-0A86C27409B4} | c0a8-0009-13dc423ae4b-851c02e3-cfc-3e | Hz-ID-17706 | MCPA - Mine Clearance Planning Agency | AF/0111/00142/MF0364 | 56814 | 69.3722 | 34.3208 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {191F1415-A042-4ECB-AB9D-0A86C27409B4} |  | Low | Agriculture Blocked | Moderate | 7 | CHA | 5 |  |  | 2013-01-14 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Ghozgay | {191F1415-A042-4ECB-AB9D-0A86C27409B4} | c0a8-0009-13de85d2c53-5bf340c8-9371-1 | Hz-ID-17709 | MCPA - Mine Clearance Planning Agency | AF/0111/00142/MF0367 | 90021 | 69.3796 | 34.3213 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {191F1415-A042-4ECB-AB9D-0A86C27409B4} |  | Low | Agriculture Blocked | Moderate | 18 | CHA | 5 |  |  | 2013-01-15 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Ghozgay | {191F1415-A042-4ECB-AB9D-0A86C27409B4} | c0a8-0057-12c3b8a3414-8cb447ce-20a33- | MF-HQ-13867 | MCPA - Mine Clearance Planning Agency | AF/0111/00142/MF0312 | 43426 | 69.3894 | 34.3281 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-007 | Kabul Demining Project-04 | DOS | Yes | 2013-09-09 | 2013-11-15 | 1392 | ATC | {191F1415-A042-4ECB-AB9D-0A86C27409B4} |  |  |  | Moderate | 17 | CHA | 3 |  |  | 2009-12-01 | No | Complete
Central | Kabul | Khaki Jabbar | Ghozgay | {191F1415-A042-4ECB-AB9D-0A86C27409B4} | c0a8-0057-12c3b8e5bc4-5bf372f5-23877- | MF-HQ-13865 | MCPA - Mine Clearance Planning Agency | AF/0111/00142/MF0314 | 93901 | 69.383 | 34.324 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {191F1415-A042-4ECB-AB9D-0A86C27409B4} |  | Low | Agriculture Blocked | Moderate | 20 | CHA | 5 |  |  | 2009-12-01 | No | Open
Central | Kabul | Khaki Jabbar | Ghozgay | {191F1415-A042-4ECB-AB9D-0A86C27409B4} | c0a8-0057-12c3ba80d64-67e2c61a-33d6c- | MF-HQ-13864 | MCPA - Mine Clearance Planning Agency | AF/0111/00142/MF0317 | 167203 | 69.3674 | 34.3185 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {191F1415-A042-4ECB-AB9D-0A86C27409B4} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2009-12-01 | No | Open
Central | Kabul | Khaki Jabbar | Gurgemaydan | {593D597F-F354-466C-8267-E01121ABA1E2} | c0a8-0057-12c3baea82b-c46d1d1-37b8f-b | MF-HQ-14100 | MCPA - Mine Clearance Planning Agency | AF/0505/03921/MF0339 | 35586 | 69.3988 | 34.2428 | Open | AT Only | AT Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {593D597F-F354-466C-8267-E01121ABA1E2} |  | Low | Other | Moderate | 42 | CHA | 5 |  |  | 2010-02-01 | No | Open
Central | Kabul | Khaki Jabbar | Gurgemaydan | {593D597F-F354-466C-8267-E01121ABA1E2} | c0a8-0057-12c3bb53646-89e8b536-3b9ca- | MF-HQ-14095 | MCPA - Mine Clearance Planning Agency | AF/0505/03921/MF0338 | 82442 | 69.3907 | 34.2378 | Open | AT Only | AT Only | MineField |  | MBT Project-019 | Kabul Demining Project-01 (AT) |  |  |  |  | 1394 |  | {593D597F-F354-466C-8267-E01121ABA1E2} |  | Low | Agriculture Blocked | Moderate | 67 | CHA | 2 |  |  | 2010-02-01 | No | Open
Central | Kabul | Khaki Jabbar | Jango Zay | {FDE3B83E-8E4F-4AD1-9FB8-9BC8EB3BF69B} | c0a8-0009-13e7d51546e-b312340a-1e89-1 | Hz-ID-17851 | MCPA - Mine Clearance Planning Agency | AF/0111/00130/MF0380 | 37970 | 69.4061 | 34.2685 | Open | AT Only | AT Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {FDE3B83E-8E4F-4AD1-9FB8-9BC8EB3BF69B} |  | Low | Other | Moderate | 55 | CHA | 5 |  |  | 2013-03-14 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Jango Zay | {FDE3B83E-8E4F-4AD1-9FB8-9BC8EB3BF69B} | c0a8-0009-13e7d5c42d5-1e91e093-1eb0-8 | Hz-ID-17850 | MCPA - Mine Clearance Planning Agency | AF/0111/00130/MF0379 | 69150 | 69.4149 | 34.248 | Open | AT Only | AT Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {FDE3B83E-8E4F-4AD1-9FB8-9BC8EB3BF69B} |  | Low | Other | Moderate | 25 | CHA | 5 |  |  | 2013-03-13 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Jango Zay | {FDE3B83E-8E4F-4AD1-9FB8-9BC8EB3BF69B} | c0a8-0009-13e7d603a05-140f58f7-1fc8-6 | Hz-ID-17849 | MCPA - Mine Clearance Planning Agency | AF/0111/00130/MF0378 | 26831 | 69.4149 | 34.248 | Open | AT Only | AT Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {FDE3B83E-8E4F-4AD1-9FB8-9BC8EB3BF69B} |  | Low | Other | Moderate | 17 | CHA | 5 |  |  | 2013-03-12 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Jango Zay | {FDE3B83E-8E4F-4AD1-9FB8-9BC8EB3BF69B} | c0a8-0057-12c3b84ce4d-4935dcbf-1cdf4- | MF-HQ-14101 | MCPA - Mine Clearance Planning Agency | AF/0111/00130/MF0340 | 74784 | 69.4284 | 34.221 | Open | AT Only | AT Only | MineField | Blank | MBT Project-230 | Kabul Demining Project-19 |  | No |  |  | 1396 | None | {FDE3B83E-8E4F-4AD1-9FB8-9BC8EB3BF69B} |  | Low | Agriculture Blocked | Moderate | 77 | SHA | 4 |  |  | 2010-02-01 | No | Open
Central | Kabul | Khaki Jabbar | Khaki Jabbar | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} | c0a8-0009-13e737ce8e6-41b45bea-8f5-d5 | MF-HQ-13375 | MCPA - Mine Clearance Planning Agency | AF/0111/00160/MF0293 | 104179 | 69.4902 | 34.4049 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-007 | Kabul Demining Project-04 | DOS | Yes | 2013-09-21 | 2014-03-16 | 1392 | ATC | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} |  |  |  | Moderate | 106 | CHA | 2 |  |  | 2009-09-30 | No | Complete
Central | Kabul | Khaki Jabbar | Khaki Jabbar | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} | c0a8-0009-13e737ef2a0-5c81bc47-9a9-12 | MF-HQ-13376 | MCPA - Mine Clearance Planning Agency | AF/0111/00160/MF0297 | 98210 | 69.4883 | 34.4048 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-04-14 |  | 1392 | ATC | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} |  |  |  | Moderate | 95 | CHA | 2 |  |  | 2009-10-01 | No | Complete
Central | Kabul | Khaki Jabbar | Khaki Jabbar | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} | c0a8-0009-13e73844c15-ddf32505-c50-ec | MF-HQ-13384 | MCPA - Mine Clearance Planning Agency | AF/0111/00160/MF0296 | 138045 | 69.4853 | 34.4021 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-06-01 | 2013-10-31 | 1392 | ATC | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} |  |  |  | Moderate | 94 | CHA | 2 |  |  | 2009-10-01 | No | Complete
Central | Kabul | Khaki Jabbar | Khaki Jabbar | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} | c0a8-0009-13e738dd2f3-538958e0-d4b-32 | MF-HQ-13385 | MCPA - Mine Clearance Planning Agency | AF/0111/00160/MF0298 | 66592 | 69.4836 | 34.4145 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-04-14 | 2013-07-27 | 1392 | ATC | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} |  |  |  | Moderate | 14 | CHA | 2 |  |  | 2009-10-04 | No | Complete
Central | Kabul | Khaki Jabbar | Khaki Jabbar | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} | c0a8-0009-13e73905ee5-a9bffffd-df8-eb | MF-HQ-13389 | MCPA - Mine Clearance Planning Agency | AF/0111/00160/MF0302 | 84186 | 69.475 | 34.407 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-06-22 | 2013-10-31 | 1392 | ATC | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} |  |  |  | Moderate | 2 | CHA | 2 |  |  | 2009-10-13 | No | Complete
Central | Kabul | Khaki Jabbar | Khaki Jabbar | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} | c0a8-0009-13e73924815-83599226-ebe-8c | MF-HQ-13373 | MCPA - Mine Clearance Planning Agency | AF/0111/00160/MF0291 | 7447 | 69.5058 | 34.4003 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-06-22 | 2013-06-30 | 1392 | ATC | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} |  |  |  | Moderate | 39 | CHA | 2 |  |  | 2009-09-27 | No | Complete
Central | Kabul | Khaki Jabbar | Khaki Jabbar | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} | c0a8-0009-1453fe37516-3c83589a-e59-af | Hz-ID-18597 | ATC - Afghan Technical Consultants | AF/0111/00160/MF0383 | 66190 | 69.4863 | 34.4037 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-232 | Kabul Demining Project-21 | B-Japan | Yes |  |  | 1393 | ATC | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} |  | High Requested | Resettlment/Local Request | Moderate | 28 | CHA | 5 | Yes | Dear Matin Sahib! Please find attached ATC Japan De-mining project 1393 hazard list along with local people request for clearance of the selected area, in the query list the classification is low, the issue is already shared it with RO office as well. | 2014-03-12 16:30 | No | Planned
Central | Kabul | Khaki Jabbar | Khaki Jabbar | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} | c0a8-0057-12c3bab33ff-6dbb5e56-35a53- | MF-HQ-13388 | MCPA - Mine Clearance Planning Agency | AF/0111/00160/MF0301 | 84600 | 69.475 | 34.407 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-232 | Kabul Demining Project-21 | B-Japan | Yes |  |  | 1393 | ATC | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} |  | High Requested | Resettlment/Local Request | Moderate | 3 | CHA | 5 | Yes | Dear Matin Sahib! Please find attached ATC Japan De-mining project 1393 hazard list along with local people request for clearance of the selected area, in the query list the classification is low, the issue is already shared it with RO office as well. | 2009-10-11 | No | Planned
Central | Kabul | Khaki Jabbar | Khaki Jabbar | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} | c0a8-0057-12c3bab4472-f0f29680-35af1- | MF-HQ-13387 | MCPA - Mine Clearance Planning Agency | AF/0111/00160/MF0300 | 102867 | 69.4789 | 34.413 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-232 | Kabul Demining Project-21 | B-Japan | Yes |  |  | 1393 | ATC | {556C0A24-31A5-4424-9244-2D16FA0A4AAE} |  | High Requested | Resettlment/Local Request | Moderate | 1 | CHA | 5 | Yes | Dear Matin Sahib! Please find attached ATC Japan De-mining project 1393 hazard list along with local people request for clearance of the selected area, in the query list the classification is low, the issue is already shared it with RO office as well. | 2009-10-08 | No | Planned
Central | Kabul | Khaki Jabbar | Kharoti | {E68DB89F-9F9B-4DC4-8722-977116B31C62} | c0a8-0057-12c3b737dba-3a223d76-10653- | MF-HQ-13405 | MCPA - Mine Clearance Planning Agency | AF/0111/00148/MF0285 | 90308 | 69.3381 | 34.3703 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {E68DB89F-9F9B-4DC4-8722-977116B31C62} |  | Low | Agriculture Blocked | Moderate | 33 | CHA | 5 |  |  | 2009-09-17 | No | Open
Central | Kabul | Khaki Jabbar | Kharoti | {E68DB89F-9F9B-4DC4-8722-977116B31C62} | c0a8-0057-12c3b7407b0-5cf3eecf-10cd2- | MF-HQ-13448 | MCPA - Mine Clearance Planning Agency | AF/0111/00148/MF0284 | 35264 | 69.341 | 34.375 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {E68DB89F-9F9B-4DC4-8722-977116B31C62} |  | Low | Agriculture Blocked | Moderate | 40 | CHA | 5 |  |  | 2009-09-15 | No | Open
Central | Kabul | Khaki Jabbar | Kharoti | {E68DB89F-9F9B-4DC4-8722-977116B31C62} | c0a8-0057-12c3ba26cc1-ce201985-30686- | MF-HQ-13005 | MCPA - Mine Clearance Planning Agency | AF/0111/00148/MF0229 | 67477 | 69.3419 | 34.3679 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes | 2014-06-05 | 2014-07-31 | 1393 | OMAR | {E68DB89F-9F9B-4DC4-8722-977116B31C62} |  | Low | Agriculture Blocked | Moderate | 17 | CHA | 4 |  |  | 2009-08-13 | No | Planned
Central | Kabul | Khaki Jabbar | Kharoti | {E68DB89F-9F9B-4DC4-8722-977116B31C62} | c0a8-0057-12c3ba26f02-e0a87d32-3069c- | MF-HQ-13003 | MCPA - Mine Clearance Planning Agency | AF/0111/00148/MF0230 | 34872 | 69.3419 | 34.3679 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {E68DB89F-9F9B-4DC4-8722-977116B31C62} |  | Low | Agriculture Blocked | Moderate | 34 | CHA | 5 |  |  | 2009-08-16 | No | Open
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-0009-143850d697f-a70e3a65-42a8-3 | Hz-ID-18376 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0111/00150/MF0381 | 35348 | 69.3999 | 34.4108 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes | 2014-05-01 | 2014-07-02 | 1393 | ATC | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} |  |  |  | Moderate | 14 | CHA | 2 |  |  | 2013-12-24 16:30 | No | Planned
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-0057-12c3b862bd4-3317687e-1dd2f- | MF-HQ-13006 | MCPA - Mine Clearance Planning Agency | AF/0111/00150/MF0167 | 138090 | 69.3999 | 34.4108 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-006/A | Kabul Demining Project-02/A | DOS | Yes | 2013-07-20 | 2013-09-30 | 1392 | OMAR | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | OMAR Contingency Plan 1392 |  |  | Moderate | 1 | CHA | 2 |  |  | 2009-06-21 | No | Complete
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-0057-12c3b862d89-7f27080e-1dd47- | MF-HQ-12833 | MCPA - Mine Clearance Planning Agency | AF/0111/00150/MF0168 | 89760 | 69.3999 | 34.4108 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-006/A | Kabul Demining Project-02/A | DOS | Yes | 2013-10-01 | 2013-11-30 | 1392 | OMAR | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | OMAR Contingency Plan 1392 |  |  | Moderate | 5 | CHA | 2 |  |  | 2009-06-20 | No | Complete
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-0057-12c3b863102-ecf20840-1dd5a- | MF-HQ-13372 | MCPA - Mine Clearance Planning Agency | AF/0111/00150/MF0308 | 78354 | 69.4034 | 34.3965 | Open | AP Only | AP Only | MineField | Blank | MBT Project-006 | Kabul Demining Project-02 | DOS | No |  |  | 1394 | None | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | OMAR Contingency Plan 1392 | High with Victim | High with Victims | Moderate | 19 | CHA | 2 |  |  | 2009-07-30 | No | Open
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-0057-12c3b9f5ec5-bc76e45f-2e8b6- | MF-HQ-13116 | MCPA - Mine Clearance Planning Agency | AF/0111/00150/MF0162 | 37504 | 69.3838 | 34.419 | Open | AP Only | AP Only | MineField |  | MBT Project-019 | Kabul Demining Project-01 (AT) |  |  |  |  | 1394 |  | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | , | High with Victim | High with Victims | Moderate | 2 | CHA | 2 |  |  | 2009-06-14 | No | Open
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-0057-12c3b9f68e3-d6dbd958-2e90e- | MF-HQ-13088 | MCPA - Mine Clearance Planning Agency | AF/0111/00150/MF0158 | 19065 | 69.3864 | 34.4208 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-12-01 | 2013-12-17 | 1392 | ATC | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} |  |  |  | Moderate | 2 | CHA | 2 |  |  | 2009-06-16 | No | Complete
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-0057-12c3bb16432-4c079f74-3956e- | MF-HQ-12843 | MCPA - Mine Clearance Planning Agency | AF/0111/00150/MF0179 | 155224 | 69.3865 | 34.3704 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2014-03-14 | 2014-04-30 | 1392 | ATC | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} |  |  |  | Moderate | 104 | CHA | 2 |  |  | 2009-07-09 | No | Complete
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-0057-12c3bb16bd0-9aa25395-395bb- | MF-HQ-13061 | MCPA - Mine Clearance Planning Agency | AF/0111/00150/MF0180 | 116846 | 69.3815 | 34.3723 | Open | AP Only | AP Only | MineField | Blank | MBT Project-006 | Kabul Demining Project-02 | DOS | No |  |  | 1394 | None | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | OMAR Contingency Plan 1392 | High with Victim | High with Victims | Moderate | 19 | CHA | 2 |  |  | 2009-07-09 | No | Open
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-0057-12c3bb170df-a5597310-395e5- | MF-HQ-13063 | MCPA - Mine Clearance Planning Agency | AF/0111/00150/MF0189 | 161758 | 69.3752 | 34.3731 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-09-14 | 2013-11-28 | 1392 | MDC | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} |  |  |  | Moderate | 26 | CHA | 2 |  |  | 2009-07-14 | No | Complete
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-0057-12c3bb1736e-5f40ebc0-395fd- | MF-HQ-13058 | MCPA - Mine Clearance Planning Agency | AF/0111/00150/MF0174 | 175064 | 69.3791 | 34.3842 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-10-01 | 2014-04-30 | 1392 | ATC | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} |  |  |  | Moderate | 36 | CHA | 2 |  |  | 2009-07-05 | No | Complete
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-0057-12c3bb17abe-b2845152-39648- | MF-HQ-13060 | MCPA - Mine Clearance Planning Agency | AF/0111/00150/MF0175 | 168753 | 69.3741 | 34.382 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-019 | Kabul Demining Project-01 (AT) |  |  |  |  | 1394 |  | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} |  | High with Victim | High with Victims | Moderate | 5 | CHA | 2 |  |  | 2009-07-07 | No | Open
Central | Kabul | Khaki Jabbar | Khurd Kabul | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} | c0a8-00f6-135a86163ea-c357710a-e6-f2b | MF-16692 | MCPA - Mine Clearance Planning Agency | AF/0111/00150/MF0352 | 25545 | 69.3829 | 34.3779 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-10-25 | 2013-11-30 | 1392 | ATC | {9A1C472E-99E1-412F-A3FD-12D6AC9604CA} |  |  |  | Moderate | 6 | CHA | 2 |  |  | 2011-12-27 16:30 | No | Complete
Central | Kabul | Khaki Jabbar | Kooz Malang | {E5A471A1-1872-44B9-8968-ABA537E45E7C} | c0a8-0009-13d0ad76d0f-2887612d-3522-4 | Hz-ID-17653 | MCPA - Mine Clearance Planning Agency | AF/0111/00045/MF0353 | 46170 | 69.3659 | 34.3756 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {E5A471A1-1872-44B9-8968-ABA537E45E7C} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2012-12-08 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Kooz Malang | {E5A471A1-1872-44B9-8968-ABA537E45E7C} | c0a8-0009-13d0baf8750-9966e7fb-35a6-7 | Hz-ID-17658 | MCPA - Mine Clearance Planning Agency | AF/0111/00045/MF0358 | 32980 | 69.3623 | 34.3688 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {E5A471A1-1872-44B9-8968-ABA537E45E7C} |  | Low | Agriculture Blocked | Moderate | 18 | CHA | 5 |  |  | 2012-12-09 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Kooz Malang | {E5A471A1-1872-44B9-8968-ABA537E45E7C} | c0a8-0009-13d0bb6a6e5-5cd7039-35c1-a7 | Hz-ID-17659 | MCPA - Mine Clearance Planning Agency | AF/0111/00045/MF0359 | 74451 | 69.3618 | 34.3653 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {E5A471A1-1872-44B9-8968-ABA537E45E7C} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2012-12-10 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Kooz Malang | {E5A471A1-1872-44B9-8968-ABA537E45E7C} | c0a8-0009-13dab182069-72b50b3f-46e-a5 | Hz-ID-17655 | MCPA - Mine Clearance Planning Agency | AF/0111/00045/MF0355 | 60725 | 69.3647 | 34.3748 | Open | AP Only | AP Only | MineField |  | MBT Project-231 | Kabul Demining Project-20 |  |  |  |  | 1396 |  | {E5A471A1-1872-44B9-8968-ABA537E45E7C} |  | Low | Agriculture Blocked | Moderate | 9 | CHA | 5 |  |  | 2012-01-05 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Malang | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} | c0a8-0009-13d0b862677-2f235688-3557-b | Hz-ID-17654 | MCPA - Mine Clearance Planning Agency | AF/0111/00147/MF0354 | 44729 | 69.3659 | 34.3756 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} |  | Low | Agriculture Blocked | Moderate | 9 | CHA | 5 |  |  | 2012-12-06 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Malang | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} | c0a8-0009-13d0ba810a9-14299413-3570-6 | Hz-ID-17656 | MCPA - Mine Clearance Planning Agency | AF/0111/00147/MF0356 | 34000 | 69.359 | 34.3721 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} |  | Low | Agriculture Blocked | Moderate | 28 | CHA | 5 |  |  | 2012-12-08 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Malang | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} | c0a8-0009-13d0bab9cf8-3be7812c-358c-f | Hz-ID-17657 | MCPA - Mine Clearance Planning Agency | AF/0111/00147/MF0357 | 40005 | 69.359 | 34.3721 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} |  | Low | Agriculture Blocked | Moderate | 28 | CHA | 5 |  |  | 2012-12-09 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Malang | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} | c0a8-0009-13d0bbebc7d-dbff5254-3630-8 | Hz-ID-17660 | MCPA - Mine Clearance Planning Agency | AF/0111/00147/MF0360 | 20249 | 69.3534 | 34.3725 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} |  | Low | Agriculture Blocked | Moderate | 23 | CHA | 5 |  |  | 2012-12-10 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Malang | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} | c0a8-0057-12c3b749d29-a954087f-113b3- | MF-HQ-13435 | MCPA - Mine Clearance Planning Agency | AF/0111/00147/MF0273 | 50000 | 69.367 | 34.3266 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} |  | Low | Agriculture Blocked | Moderate | 3 | CHA | 5 |  |  | 2009-09-12 | No | Open
Central | Kabul | Khaki Jabbar | Malang | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} | c0a8-0057-12c3b7879b8-5c405076-14123- | MF-HQ-13442 | MCPA - Mine Clearance Planning Agency | AF/0111/00147/MF0271 | 110200 | 69.3726 | 34.3269 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} |  | Low | Agriculture Blocked | Moderate | 14 | CHA | 5 |  |  | 2009-09-06 | No | Open
Central | Kabul | Khaki Jabbar | Malang | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} | c0a8-0057-12c3ba278e1-6a8b0a3d-30701- | MF-HQ-13380 | MCPA - Mine Clearance Planning Agency | AF/0111/00147/MF0267 | 98050 | 69.3876 | 34.3368 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} |  | Low | Agriculture Blocked | Moderate | 19 | CHA | 5 |  |  | 2009-09-13 | No | Open
Central | Kabul | Khaki Jabbar | Malang | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} | c0a8-0057-12c3ba27af3-d03bc6ef-30714- | MF-HQ-13414 | MCPA - Mine Clearance Planning Agency | AF/0111/00147/MF0272 | 67100 | 69.3876 | 34.3368 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} |  | Low | Agriculture Blocked | Moderate | 19 | CHA | 5 |  |  | 2009-09-08 | No | Open
Central | Kabul | Khaki Jabbar | Malang | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} | c0a8-0057-12c3ba27d15-e7961e06-3072a- | MF-HQ-13379 | MCPA - Mine Clearance Planning Agency | AF/0111/00147/MF0268 | 65481 | 69.377 | 34.3294 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} |  | Low | Agriculture Blocked | Moderate | 18 | CHA | 5 |  |  | 2009-09-14 | No | Open
Central | Kabul | Khaki Jabbar | Malang | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} | c0a8-0057-12c3ba27fc4-1a1f41c0-30740- | MF-HQ-13381 | MCPA - Mine Clearance Planning Agency | AF/0111/00147/MF0266 | 133588 | 69.3802 | 34.3323 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {F49E1097-A40C-4EA7-8BDE-61B2550A3F76} |  | Low | Agriculture Blocked | Moderate | 20 | CHA | 5 |  |  | 2009-09-07 | No | Open
Central | Kabul | Khaki Jabbar | Mirza Khan Karez | {3B7EC4EA-A6A2-4468-830F-18A84E074F66} | c0a8-0057-12c3b7651d3-9be3efb-127ea-1 | MF-HQ-12841 | MCPA - Mine Clearance Planning Agency | AF/0111/00157/MF0243 | 9970 | 69.3179 | 34.4096 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {3B7EC4EA-A6A2-4468-830F-18A84E074F66} |  | Low | Agriculture Blocked | Moderate | 8 | CHA | 5 |  |  | 2009-08-18 | No | Open
Central | Kabul | Khaki Jabbar | Mula Umar Kalay | {27F5BDD5-359A-45B1-8731-3EFA8C891B6F} | c0a8-0057-12c3baa3fd3-cc6a8ad-3519b-4 | MF-HQ-14097 | MCPA - Mine Clearance Planning Agency | AF/0112/00163/BF0346 | 35468 | 69.5093 | 34.5148 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-007 | Kabul Demining Project-04 | DOS | Yes | 2013-12-08 | 2014-03-04 | 1392 | ATC | {27F5BDD5-359A-45B1-8731-3EFA8C891B6F} |  |  |  | Moderate | 21 | CHA | 2 |  |  | 2010-02-01 | No | Complete
Central | Kabul | Khaki Jabbar | Natookhel & Sewak | {3F5E6394-C6CD-47E7-AEC6-ECD603CC913B} | c0a8-0057-12c3b866c7b-636debb-1dffe-8 | MF-HQ-13413 | MCPA - Mine Clearance Planning Agency | AF/0111/00187/MF0274 | 84898 | 69.4834 | 34.3578 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {3F5E6394-C6CD-47E7-AEC6-ECD603CC913B} |  | Low | Agriculture Blocked | Moderate | 10 | CHA | 5 |  |  | 2009-09-13 | No | Open
Central | Kabul | Khaki Jabbar | Natookhel & Sewak | {3F5E6394-C6CD-47E7-AEC6-ECD603CC913B} | c0a8-0057-12c3b866edb-bc44805d-1e018- | MF-HQ-13378 | MCPA - Mine Clearance Planning Agency | AF/0111/00187/MF0269 | 70500 | 69.4834 | 34.3578 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {3F5E6394-C6CD-47E7-AEC6-ECD603CC913B} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2009-09-15 | No | Open
Central | Kabul | Khaki Jabbar | Qafas Kalay | {80BC330F-0A3B-4970-8573-5B29F255FA53} | c0a8-0057-12c3b6f41fd-81a1518b-d2fd-2 | MF-HQ-13139 | MCPA - Mine Clearance Planning Agency | AF/0112/00166/MF0262 | 7580 | 69.5423 | 34.5141 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes | 2014-08-02 | 2014-08-14 | 1393 | OMAR | {80BC330F-0A3B-4970-8573-5B29F255FA53} |  | Low | Agriculture Blocked | Moderate | 69 | CHA | 4 |  |  | 2009-08-09 | No | Planned
Central | Kabul | Khaki Jabbar | Qafas Kalay | {80BC330F-0A3B-4970-8573-5B29F255FA53} | c0a8-0057-12c3b85fa0b-73f98752-1db1e- | MF-HQ-13108 | MCPA - Mine Clearance Planning Agency | AF/0112/00166/MF0263 | 20792 | 69.5444 | 34.5132 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {80BC330F-0A3B-4970-8573-5B29F255FA53} |  | Low | Water Blocked | Moderate | 12 | CHA | 5 |  |  | 2009-08-11 | No | Open
Central | Kabul | Khaki Jabbar | Qafas Kalay | {80BC330F-0A3B-4970-8573-5B29F255FA53} | c0a8-0057-12c3b85fce8-87db49a1-1db35- | MF-HQ-13123 | MCPA - Mine Clearance Planning Agency | AF/0112/00166/MF0257 | 28129 | 69.5423 | 34.5115 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {80BC330F-0A3B-4970-8573-5B29F255FA53} |  | Low | Agriculture Blocked | Moderate | 12 | CHA | 5 |  |  | 2009-07-28 | No | Open
Central | Kabul | Khaki Jabbar | Qafas Kalay | {80BC330F-0A3B-4970-8573-5B29F255FA53} | c0a8-0057-12c3b85ff68-3416f783-1db4c- | MF-HQ-13125 | MCPA - Mine Clearance Planning Agency | AF/0112/00166/MF0258 | 18059 | 69.5421 | 34.5138 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes | 2014-09-01 | 2014-09-30 | 1393 | OMAR | {80BC330F-0A3B-4970-8573-5B29F255FA53} |  | Low | Agriculture Blocked | Moderate | 12 | CHA | 4 |  |  | 2009-07-30 | No | Planned
Central | Kabul | Khaki Jabbar | Qafas Kalay | {80BC330F-0A3B-4970-8573-5B29F255FA53} | c0a8-0057-12c3b8601e8-69661ffa-1db66- | MF-HQ-13106 | MCPA - Mine Clearance Planning Agency | AF/0112/00166/MF0260 | 41343 | 69.542 | 34.5159 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-007 | Kabul Demining Project-04 | DOS | Yes | 2013-05-11 | 2013-08-01 | 1392 | ATC | {80BC330F-0A3B-4970-8573-5B29F255FA53} |  |  |  | Moderate | 12 | CHA | 3 |  |  | 2009-08-04 | No | Complete
Central | Kabul | Khaki Jabbar | Qafas Kalay | {80BC330F-0A3B-4970-8573-5B29F255FA53} | c0a8-0057-12c3b878ded-ead501a4-1ec88- | MF-HQ-13105 | MCPA - Mine Clearance Planning Agency | AF/0112/00166/MF0259 | 85162 | 69.5428 | 34.5164 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-007 | Kabul Demining Project-04 | DOS | Yes |  | 2013-11-06 | 1392 | ATC | {80BC330F-0A3B-4970-8573-5B29F255FA53} |  |  |  | Moderate | 32 | CHA | 3 |  |  | 2009-08-02 | No | Complete
Central | Kabul | Khaki Jabbar | Qafas Kalay | {80BC330F-0A3B-4970-8573-5B29F255FA53} | c0a8-0057-12c3ba05e84-18862c-2f2b1-11 | MF-HQ-13102 | MCPA - Mine Clearance Planning Agency | AF/0112/00166/MF0261 | 22029 | 69.5433 | 34.5057 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {80BC330F-0A3B-4970-8573-5B29F255FA53} |  | Low | Water Blocked | Moderate | 3 | CHA | 5 |  |  | 2009-08-06 | No | Open
Central | Kabul | Khaki Jabbar | Sheman Zay | {7F3FEA00-4205-45B9-B255-8D9E9F73F948} | c0a8-0057-12c3b9ed4b1-62693aab-2e36d- | MF-HQ-13862 | MCPA - Mine Clearance Planning Agency | AF/0111/00146/MF0316 | 33685 | 69.4445 | 34.3118 | Open | AP Only | AP Only | MineField |  | MBT Project-008 | Kabul Demining Project-05 | DOS |  |  |  | 1395 |  | {7F3FEA00-4205-45B9-B255-8D9E9F73F948} |  | Low | Agriculture Blocked | Moderate | 51 | CHA | 4 |  |  | 2009-12-01 | No | Open
Central | Kabul | Khaki Jabbar | Sherullah | {8E5F84D6-F1CB-4792-95AF-645F4F4A470B} | c0a8-0009-13daf7c0b5b-79662e8b-1a7c-b | Hz-ID-17710 | MCPA - Mine Clearance Planning Agency | AF/0111/00133/MF0368 | 18449 | 69.3913 | 34.2993 | Open | AT Only | AT Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {8E5F84D6-F1CB-4792-95AF-645F4F4A470B} |  | Low | Agriculture Blocked | Moderate | 23 | CHA | 5 |  |  | 2013-01-21 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Sherullah | {8E5F84D6-F1CB-4792-95AF-645F4F4A470B} | c0a8-0009-13daf857224-2766aa47-1c0e-5 | Hz-ID-17711 | MCPA - Mine Clearance Planning Agency | AF/0111/00133/MF0369 | 16122 | 69.4034 | 34.2797 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {8E5F84D6-F1CB-4792-95AF-645F4F4A470B} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2013-01-20 16:30 | No | Open
Central | Kabul | Khaki Jabbar | Sherullah | {8E5F84D6-F1CB-4792-95AF-645F4F4A470B} | c0a8-0057-12c3b8b1eec-4d098464-2143b- | MF-HQ-13869 | MCPA - Mine Clearance Planning Agency | AF/0111/00133/MF0310 | 66458 | 69.4051 | 34.2975 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes |  |  | 1393 | OMAR | {8E5F84D6-F1CB-4792-95AF-645F4F4A470B} |  | Low | Agriculture Blocked | Moderate | 197 | CHA | 4 |  |  | 2009-12-01 | No | Planned
Central | Kabul | Khaki Jabbar | Sherullah | {8E5F84D6-F1CB-4792-95AF-645F4F4A470B} | c0a8-0057-12c3b9785d8-7f4209fa-29841- | MF-HQ-13870 | MCPA - Mine Clearance Planning Agency | AF/0111/00133/MF0318 | 77686 | 69.3913 | 34.2993 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes | 2014-05-02 | 2014-07-01 | 1393 | OMAR | {8E5F84D6-F1CB-4792-95AF-645F4F4A470B} |  | Low | Agriculture Blocked | Moderate | 30 | CHA | 4 |  |  | 2009-12-01 | No | Planned
Central | Kabul | Khaki Jabbar | Taghar | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} | c0a8-0057-12c3b82f42a-3969652f-1b863- | MF-HQ-13109 | MCPA - Mine Clearance Planning Agency | AF/0111/00161/MF0220 | 68148 | 69.3435 | 34.4397 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2009-08-03 | No | Open
Central | Kabul | Khaki Jabbar | Taghar | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} | c0a8-0057-12c3b82f820-a680a151-1b892- | MF-HQ-13034 | MCPA - Mine Clearance Planning Agency | AF/0111/00161/MF0217 | 66240 | 69.3444 | 34.4405 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} |  | Low | Agriculture Blocked | Moderate | 3 | CHA | 5 |  |  | 2009-08-03 | No | Open
Central | Kabul | Khaki Jabbar | Taghar | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} | c0a8-0057-12c3b9f0d6c-6789b477-2e58b- | MF-HQ-12837 | MCPA - Mine Clearance Planning Agency | AF/0111/00161/MF0232 | 56127 | 69.3379 | 34.4424 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2009-08-09 | No | Open
Central | Kabul | Khaki Jabbar | Taghar | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} | c0a8-0057-12c3b9f11a1-2abdd4aa-2e5b7- | MF-HQ-13037 | MCPA - Mine Clearance Planning Agency | AF/0111/00161/MF0218 | 98988 | 69.3435 | 34.4397 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} |  | Low | Agriculture Blocked | Moderate | 3 | CHA | 5 |  |  | 2009-08-05 | No | Open
Central | Kabul | Khaki Jabbar | Taghar | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} | c0a8-0057-12c3b9f1384-de32df52-2e5cc- | MF-HQ-12838 | MCPA - Mine Clearance Planning Agency | AF/0111/00161/MF0233 | 40729 | 69.3276 | 34.4426 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2009-08-11 | No | Open
Central | Kabul | Khaki Jabbar | Taghar | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} | c0a8-0057-12c3b9f1568-bc776629-2e5df- | MF-HQ-12839 | MCPA - Mine Clearance Planning Agency | AF/0111/00161/MF0234 | 56838 | 69.3276 | 34.4426 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} |  | Low | Agriculture Blocked | Moderate | 15 | CHA | 5 |  |  | 2009-08-13 | No | Open
Central | Kabul | Khaki Jabbar | Taghar | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} | c0a8-0057-12c3b9f1799-5a7ab701-2e5f4- | MF-HQ-12835 | MCPA - Mine Clearance Planning Agency | AF/0111/00161/MF0231 | 78954 | 69.3379 | 34.4424 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {B8E282FB-F5D6-4104-A3B0-EA331BAA42B8} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2009-08-06 | No | Open
Central | Kabul | Khaki Jabbar | Talokhel | {8754BF80-C221-4C2D-936B-899DA5E3EE26} | c0a8-0057-12c3b85cb20-350aeffd-1d914- | MF-HQ-13421 | MCPA - Mine Clearance Planning Agency | AF/0111/00155/MF0256 | 49280 | 69.4573 | 34.3751 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-09-30 | 2013-11-12 | 1392 | MDC | {8754BF80-C221-4C2D-936B-899DA5E3EE26} |  |  |  | Moderate | 29 | CHA | 5 |  |  | 2009-09-06 | No | Complete
Central | Kabul | Khaki Jabbar | Talokhel | {8754BF80-C221-4C2D-936B-899DA5E3EE26} | c0a8-0057-12c3b85cea8-b7fbae38-1d938- | MF-HQ-13423 | MCPA - Mine Clearance Planning Agency | AF/0111/00155/MF0278 | 35242 | 69.4621 | 34.367 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-10-20 | 2013-11-07 | 1392 | MDC | {8754BF80-C221-4C2D-936B-899DA5E3EE26} |  |  |  | Moderate | 374 | CHA | 3 |  |  | 2009-09-12 | No | Complete
Central | Kabul | Khaki Jabbar | Talokhel | {8754BF80-C221-4C2D-936B-899DA5E3EE26} | c0a8-0057-12c3b85d482-573e2b2c-1d979- | MF-HQ-13422 | MCPA - Mine Clearance Planning Agency | AF/0111/00155/MF0277 | 141932 | 69.4621 | 34.3704 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-09-12 | 2013-11-11 | 1392 | MDC | {8754BF80-C221-4C2D-936B-899DA5E3EE26} |  |  |  | Moderate | 336 | CHA | 5 |  |  | 2009-09-08 | No | Complete
Central | Kabul | Khaki Jabbar | Talokhel | {8754BF80-C221-4C2D-936B-899DA5E3EE26} | c0a8-0057-12c3b9007c7-88795b2d-24a1c- | MF-HQ-13418 | MCPA - Mine Clearance Planning Agency | AF/0111/00155/MF0255 | 6455 | 69.466 | 34.3528 | Open | AP Only | AP Only | MineField |  | MBT Project-230 | Kabul Demining Project-19 |  |  |  |  | 1396 |  | {8754BF80-C221-4C2D-936B-899DA5E3EE26} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2009-09-03 | No | Open
Central | Kabul | Khaki Jabbar | Talokhel | {8754BF80-C221-4C2D-936B-899DA5E3EE26} | c0a8-0057-12c3b900b9d-a1a25233-24a44- | MF-HQ-13417 | MCPA - Mine Clearance Planning Agency | AF/0111/00155/MF0254 | 31770 | 69.4675 | 34.3598 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes |  |  | 1392 | MDC | {8754BF80-C221-4C2D-936B-899DA5E3EE26} |  |  |  | Moderate | 7 | CHA | 5 |  |  | 2009-09-01 | No | Complete
Central | Kabul | Khaki Jabbar | Talokhel | {8754BF80-C221-4C2D-936B-899DA5E3EE26} | c0a8-0057-12c3b900fa3-f5303e0b-24a72- | MF-HQ-13416 | MCPA - Mine Clearance Planning Agency | AF/0111/00155/MF0253 | 43006 | 69.4639 | 34.3607 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes |  |  | 1392 | MDC | {8754BF80-C221-4C2D-936B-899DA5E3EE26} |  |  |  | Moderate | 45 | CHA | 4 |  |  | 2009-08-30 | No | Complete
Central | Kabul | Khaki Jabbar | Zendan | {0A3192F0-C37B-484C-B10D-4E0598D03866} | c0a8-0057-12c3b7547d7-b36e090f-11bb0- | MF-HQ-13134 | MCPA - Mine Clearance Planning Agency | AF/0111/00154/MF0201 | 63567 | 69.438 | 34.3707 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes |  |  | 1393 | OMAR | {0A3192F0-C37B-484C-B10D-4E0598D03866} |  |  |  | Moderate | 68 | CHA | 4 |  |  | 2009-07-19 | No | Planned
Central | Kabul | Khaki Jabbar | Zendan | {0A3192F0-C37B-484C-B10D-4E0598D03866} | c0a8-0057-12c3b90bebc-540a11aa-25131- | MF-HQ-13132 | MCPA - Mine Clearance Planning Agency | AF/0111/00154/MF0203 | 22447 | 69.4347 | 34.3623 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-008/B | Kabul Demining Project-05/B | DOS | Yes |  |  | 1393 | OMAR | {0A3192F0-C37B-484C-B10D-4E0598D03866} |  |  |  | Moderate | 39 | CHA | 4 | No |  | 2009-07-21 | No | Planned
Central | Kabul | Khaki Jabbar | Zendan | {0A3192F0-C37B-484C-B10D-4E0598D03866} | c0a8-0057-12c3b90c2c1-6440e600-25148- | MF-HQ-13131 | MCPA - Mine Clearance Planning Agency | AF/0111/00154/MF0193 | 9504 | 69.4231 | 34.3695 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-09-12 | 2013-09-29 | 1392 | MDC | {0A3192F0-C37B-484C-B10D-4E0598D03866} |  |  |  | Moderate | 313 | CHA | 4 | Yes |  | 2009-07-14 | No | Complete
Central | Kabul | Khaki Jabbar | Zendan | {0A3192F0-C37B-484C-B10D-4E0598D03866} | c0a8-0057-12c3baebd12-26062160-37c43- | MF-HQ-13067 | MCPA - Mine Clearance Planning Agency | AF/0111/00154/MF0195 | 87397 | 69.4257 | 34.3689 | Open | AP Only | AP Only | MineField |  | MBT Project-008 | Kabul Demining Project-05 | DOS |  |  |  | 1395 |  | {0A3192F0-C37B-484C-B10D-4E0598D03866} |  | Low | Agriculture Blocked | Moderate | 302 | CHA | 4 |  |  | 2009-07-16 | No | Open
Central | Kabul | Mir Bacha Kot | Aqsarai | {534ADD1E-4751-4096-9B65-190221F541B5} | c0a8-0057-12c3b9cfcf0-8ee742a-2d135-7 | MF-CA-1437 | HT - HALO TRUST | H/3875 | 48000 | 69.2039 | 34.786 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-03-04 | 2013-06-23 | 1392 | HT | {534ADD1E-4751-4096-9B65-190221F541B5} |  |  |  | Minimal | 3 | CHA | 4 |  |  | 2007-12-03 | No | Complete
Central | Kabul | Mir Bacha Kot | Lochakan | {89B94CCB-1522-466E-A1D0-3EA7586315C5} | c0a8-0009-13e73314a4a-ecccd13d-477-73 | Hz-ID-17829 | DAFA - Demining Agency for Afghanistan | AF/0103/00674/MF0047 | 78675 | 69.1591 | 34.7397 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-07-10 | 2014-04-10 | 1392 | HT | {89B94CCB-1522-466E-A1D0-3EA7586315C5} |  |  |  | Minimal | 37 | CHA | 5 |  |  | 2013-04-27 16:30 | No | Complete
Central | Kabul | Mir Bacha Kot | Lochakan | {89B94CCB-1522-466E-A1D0-3EA7586315C5} | c0a8-0057-12c3b8b6c11-a72e962e-21795- | MF-HQ-11901 | HT - HALO TRUST | H/3325 | 60450 | 69.1618 | 34.7398 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-11-06 | 2014-02-23 | 1392 | HT | {89B94CCB-1522-466E-A1D0-3EA7586315C5} |  |  |  | Minimal | 37 | CHA | 4 |  |  | 2008-09-21 | No | Complete
Central | Kabul | Mir Bacha Kot | Shekhan | {65325322-BDE0-4C49-AF19-5E975F7670E7} | c0a8-0057-12c3b9f7b2b-ba83b84-2e9ca-3 | MF-CA-1133 | HT - HALO TRUST | H/4338 | 45000 | 69.1633 | 34.7181 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-07-06 | 2014-01-23 | 1392 | HT | {65325322-BDE0-4C49-AF19-5E975F7670E7} |  |  |  | Minimal | 85 | CHA | 4 |  |  | 2008-06-11 | No | Complete
Central | Kabul | Musayi | Alukhel | {B17A4B8A-DD91-4B50-A9A0-0DC2BBAEC173} | c0a8-0057-12c3b83ec99-15ce8a88-1c390- | MF-HQ-10346 | MCPA - Mine Clearance Planning Agency | AF/0114/00219/MF0001 | 24097 | 69.1661 | 34.3184 | Open | AP Only | AP Only | MineField |  | MBT Project-019 | Kabul Demining Project-01 (AT) |  |  |  |  | 1394 | None | {B17A4B8A-DD91-4B50-A9A0-0DC2BBAEC173} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2009-04-21 | No | Open
Central | Kabul | Musayi | Alukhel | {B17A4B8A-DD91-4B50-A9A0-0DC2BBAEC173} | c0a8-0057-12c3ba97ac3-2d95e64c-34aad- | MF-HQ-10347 | MCPA - Mine Clearance Planning Agency | AF/0114/00219/MF0002 | 43525 | 69.1624 | 34.3182 | Open | AP Only | AP Only | MineField |  | MBT Project-019 | Kabul Demining Project-01 (AT) |  |  |  |  | 1394 | None | {B17A4B8A-DD91-4B50-A9A0-0DC2BBAEC173} |  | Low | Agriculture Blocked | Moderate | 24 | CHA | 4 |  |  | 2009-04-07 | No | Open
Central | Kabul | Musayi | Haji Malang | {9698FD2D-F310-41B7-9EB7-01D6BA5ACD81} | c0a8-0057-12c3b96d794-cdb9a786-29115- | MF-HQ-11485 | MCPA - Mine Clearance Planning Agency | AF/0114/00456/MF0008 | 58046 | 69.2188 | 34.3403 | Open | AP Only | AP Only | MineField |  | MBT Project-019 | Kabul Demining Project-01 (AT) |  |  |  |  | 1394 |  | {9698FD2D-F310-41B7-9EB7-01D6BA5ACD81} |  | Low | Agriculture Blocked | Moderate | 41 | CHA | 5 |  |  | 2009-07-29 | No | Open
Central | Kabul | Musayi | Qeshlaqe Sufla | {D6C41E50-B616-4015-8622-EC3EED0D9366} | c0a8-0009-13f09ac5351-e630ecc9-1eef-c | Hz-ID-17929 | MCPA - Mine Clearance Planning Agency | AF/0114/00274/MF0013 | 381367 | 69.2393 | 34.4171 | Open | AP Only | AP Only | MineField |  | MBT Project-019 | Kabul Demining Project-01 (AT) |  |  |  |  | 1394 |  | {D6C41E50-B616-4015-8622-EC3EED0D9366} |  | Low | Agriculture Blocked | Moderate | 33 | CHA | 5 |  |  | 2013-04-25 16:30 | No | Open
Central | Kabul | Musayi | Qeshlaqe Sufla | {D6C41E50-B616-4015-8622-EC3EED0D9366} | c0a8-0057-12c3b93f326-e09abb6d-272c3- | MF-HQ-11481 | MCPA - Mine Clearance Planning Agency | AF/0114/00274/MF0005 | 370350 | 69.228 | 34.4246 | Open | AP Only | AP Only | MineField |  | MBT Project-019 | Kabul Demining Project-01 (AT) |  |  |  |  | 1394 |  | {D6C41E50-B616-4015-8622-EC3EED0D9366} |  | Low | Agriculture Blocked | Moderate | 831 | CHA | 4 |  |  | 2009-07-29 | No | Open
Central | Kabul | Musayi | Shadkhana | {95824695-0AF3-4BCA-A838-7818F2C13409} | c0a8-0057-12c3b85764d-787571a5-1d584- | MF-HQ-11483 | MCPA - Mine Clearance Planning Agency | AF/0114/00243/MF0007 | 31116 | 69.1968 | 34.3133 | Open | AP Only | AP Only | MineField |  | MBT Project-019 | Kabul Demining Project-01 (AT) |  |  |  |  | 1394 |  | {95824695-0AF3-4BCA-A838-7818F2C13409} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2009-07-29 | No | Open
Central | Kabul | Paghman | Arghandehe Pa'in | {666F5FDD-F33D-40E8-AD1D-8E848048AFB5} | c0a8-0057-12c3b6a80ed-7f9c6603-9932-9 | MF-HT-1132 | MCPA - Mine Clearance Planning Agency | AF/0108/00501/MF1661 | 10851 | 68.8654 | 34.4931 | Open | AP Only | AP Only | MineField | Blank | MBT Project-227 | Kabul Demining Project-16 |  | No |  |  | 1396 | None | {666F5FDD-F33D-40E8-AD1D-8E848048AFB5} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 5 |  |  | 2007-06-01 | No | Open
Central | Kabul | Paghman | Badamqol | {0EB1B87D-A1B3-46BC-8BA9-022028CEEC77} | c0a8-0009-13dab18ce7e-11188fab-488-1e | Hz-ID-17620 | MCPA - Mine Clearance Planning Agency | AF/0108/00476/MF0262 | 10943 | 68.8976 | 34.4631 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {0EB1B87D-A1B3-46BC-8BA9-022028CEEC77} |  | High with Victim | High with Victims | Moderate | 68 | SHA | 1 |  |  | 2012-11-25 16:30 | No | Planned
Central | Kabul | Paghman | Badamqol | {0EB1B87D-A1B3-46BC-8BA9-022028CEEC77} | c0a8-008e-1342748bfe1-a09ca916-5cb-b1 | MF-16396 | MCPA - Mine Clearance Planning Agency | AF/0108/00476/MF8165 | 41875 | 68.8679 | 34.4817 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes |  |  | 1393 | ATC | {0EB1B87D-A1B3-46BC-8BA9-022028CEEC77} |  | High with Victim | High with Victims | Moderate | 36 | CHA | 1 |  |  | 2011-11-23 16:30 | No | Planned
Central | Kabul | Paghman | Badamqol | {0EB1B87D-A1B3-46BC-8BA9-022028CEEC77} | c0a8-008e-13427509425-381aa733-5e2-81 | MF-16395 | MCPA - Mine Clearance Planning Agency | AF/0108/00476/MF8164 | 41341 | 68.8679 | 34.4817 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes |  |  | 1393 | ATC | {0EB1B87D-A1B3-46BC-8BA9-022028CEEC77} |  | High with Victim | High with Victims | Moderate | 36 | CHA | 1 |  |  | 2011-11-22 16:30 | No | Planned
Central | Kabul | Paghman | Bar Arghandy | {47EED028-49DB-423A-BE91-697DC1296E5B} | c0a8-0009-13b7ea3f8c4-e380f34a-514c-4 | Hz-ID-17450 | MCPA - Mine Clearance Planning Agency | AF/0108/00478/BF0255 | 5734 | 68.8498 | 34.4992 | Open | UXO Only | UXO Only | BF |  | MBT Project-223 | Kabul Demining Project-08 |  |  |  |  | 1394 |  | {47EED028-49DB-423A-BE91-697DC1296E5B} |  | High with Victim | High with Victims | Moderate | 1 | CHA | 1 |  |  | 2012-09-30 16:30 | No | Open
Central | Kabul | Paghman | Bar Arghandy | {47EED028-49DB-423A-BE91-697DC1296E5B} | c0a8-0009-13b830ea186-f0656e75-91-f37 | Hz-ID-17459 | MCPA - Mine Clearance Planning Agency | AF/0108/00478/MF0258 | 37966 | 68.86 | 34.4921 | Open | AP Only | AP Only | MineField |  | MBT Project-223 | Kabul Demining Project-08 |  |  |  |  | 1394 |  | {47EED028-49DB-423A-BE91-697DC1296E5B} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 1 |  |  | 2012-10-08 16:30 | No | Open
Central | Kabul | Paghman | Bar Arghandy | {47EED028-49DB-423A-BE91-697DC1296E5B} | c0a8-0009-13b830f4d4e-e2bbc147-ab-f5d | Hz-ID-17457 | MCPA - Mine Clearance Planning Agency | AF/0108/00478/MF0257 | 127183 | 68.8455 | 34.4943 | Open | AP Only | AP Only | MineField |  | MBT Project-223 | Kabul Demining Project-08 |  |  |  |  | 1394 |  | {47EED028-49DB-423A-BE91-697DC1296E5B} |  | High with Victim | High with Victims | Moderate | 3 | CHA | 1 |  |  | 2012-10-04 16:30 | No | Open
Central | Kabul | Paghman | Bar Arghandy | {47EED028-49DB-423A-BE91-697DC1296E5B} | c0a8-0009-13b830fc5a8-949c5453-c9-f17 | Hz-ID-17456 | MCPA - Mine Clearance Planning Agency | AF/0108/00478/MF0256 | 108217 | 68.8455 | 34.4943 | Open | AP Only | AP Only | MineField |  | MBT Project-223 | Kabul Demining Project-08 |  |  |  |  | 1394 |  | {47EED028-49DB-423A-BE91-697DC1296E5B} |  | High with Victim | High with Victims | Moderate | 2 | CHA | 1 |  |  | 2012-10-02 16:30 | No | Open
Central | Kabul | Paghman | Bar Arghandy | {47EED028-49DB-423A-BE91-697DC1296E5B} | c0a8-00f6-135520c83c6-1dbbb214-175-6a | MF-16649 | MCPA - Mine Clearance Planning Agency | AF/0108/00478/MF0249 | 103008 | 68.9511 | 34.4642 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes | 2014-04-01 | 2014-07-23 | 1393 | DDG | {47EED028-49DB-423A-BE91-697DC1296E5B} |  | High with Victim | High with Victims | Moderate | 20 | CHA | 1 |  |  | 2011-12-01 16:30 | No | Planned
Central | Kabul | Paghman | Bazikhel | {531144AF-DD1B-4F5E-BA71-D4ECA95334DB} | c0a8-0057-12c3b856991-b4a82148-1d4f3- | MF-HT-947 | HT - HALO TRUST | H/1669 | 30000 | 68.9193 | 34.4933 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {531144AF-DD1B-4F5E-BA71-D4ECA95334DB} |  | Medium | Agriculture Blocked | Moderate | 632 | CHA | 5 |  |  | 2007-06-02 | No | Planned
Central | Kabul | Paghman | Chandal Baee | {030E0213-33BE-4A30-A5F1-8994AF22C118} | c0a8-0009-13b7e4e5385-5254d006-4dd7-d | Hz-ID-17298 | ATC - Afghan Technical Consultants | AF/0108/00557/MF0252 | 8827 | 68.9459 | 34.5818 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {030E0213-33BE-4A30-A5F1-8994AF22C118} |  | High with Victim | High with Victims | Moderate | 90 | CHA | 2 |  |  | 2012-09-13 16:30 | No | Planned
Central | Kabul | Paghman | Darrah-ye Keshta | {E1FC9225-FF77-41EB-9CD1-8A2F8ACA7ECD} | c0a8-0057-12c3bb35501-b6d42542-3a81b- | MF-CA-1321 | MCPA - Mine Clearance Planning Agency | AF/0108/00563/MF0194 | 28595 | 68.9511 | 34.6072 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-057/A | Kabul Demining Project-03 /A | DOS | Yes | 2014-04-20 | 2014-07-30 | 1393 | DAFA | {E1FC9225-FF77-41EB-9CD1-8A2F8ACA7ECD} |  | Low | Agriculture Blocked | Moderate | 95 | CHA | 4 |  |  | 2008-10-23 | No | Planned
Central | Kabul | Paghman | Darrah-ye Keshta | {E1FC9225-FF77-41EB-9CD1-8A2F8ACA7ECD} | c0a8-008e-133f9039131-477b3f1a-5cc-46 | MF-16371 | ATC - Afghan Technical Consultants | AF/0108/00563/MF0244 | 14950 | 68.9559 | 34.617 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-057 | Kabul Demining Project-03 | DOS | Yes | 2013-10-20 | 2013-11-27 | 1392-1393 | DAFA | {E1FC9225-FF77-41EB-9CD1-8A2F8ACA7ECD} |  |  |  | Moderate | 24 | CHA | 4 |  |  | 2011-10-17 16:30 | No | Planned
Central | Kabul | Paghman | Gele Surkh | {C3443D1F-AC0E-43C7-904A-3C9C5AC318AE} | c0a8-0057-12fd339387a-5a474a79-2927-2 | MF-CA-1401 | MCPA - Mine Clearance Planning Agency | AF/0108/00559/MF0179 | 24931 | 68.9433 | 34.6136 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes | 2013-04-15 | 2013-06-30 | 1392-1393 | DDG | {C3443D1F-AC0E-43C7-904A-3C9C5AC318AE} |  |  |  | Moderate | 23 | CHA | 3 |  |  | 2008-08-24 | No | Planned
Central | Kabul | Paghman | Gele Surkh | {C3443D1F-AC0E-43C7-904A-3C9C5AC318AE} | c0a8-00c9-12fd9974e88-eb2f76ad-fb0-f9 | MF-CA-1399 | MCPA - Mine Clearance Planning Agency | AF/0108/00559/MF0178 | 47465 | 68.9433 | 34.6136 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes | 2013-05-02 | 2013-08-22 | 1392-1393 | DDG | {C3443D1F-AC0E-43C7-904A-3C9C5AC318AE} |  |  |  | Moderate | 100 | CHA | 3 |  |  | 2008-08-21 | No | Planned
Central | Kabul | Paghman | Katakhel | {A6776B8B-69FD-44C4-A63C-0607FA68A1DE} | c0a8-0057-12c3b825628-13098c18-1b189- | MF-HT-980 | MCPA - Mine Clearance Planning Agency | AF/0108/00500/MF1674 | 64506 | 68.8675 | 34.491 | Open | AP Only | AP Only | MineField |  | MBT Project-227 | Kabul Demining Project-16 |  |  |  |  | 1396 |  | {A6776B8B-69FD-44C4-A63C-0607FA68A1DE} |  | Low | Agriculture Blocked | Moderate | 36 | CHA | 5 |  |  | 2007-06-01 | No | Open
Central | Kabul | Paghman | Katakhel | {A6776B8B-69FD-44C4-A63C-0607FA68A1DE} | c0a8-0057-12c3b8980ed-d554c586-2026c- | MF-CA-2120 | MCPA - Mine Clearance Planning Agency | AF/0108/00500/MF1664 | 24391 | 68.8478 | 34.5331 | Open | AP Only | AP Only | MineField |  | MBT Project-227 | Kabul Demining Project-16 |  |  |  |  | 1396 |  | {A6776B8B-69FD-44C4-A63C-0607FA68A1DE} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-09-14 | No | Open
Central | Kabul | Paghman | Katakhel | {A6776B8B-69FD-44C4-A63C-0607FA68A1DE} | c0a8-0057-12c3bb2080d-945cd4cc-39bd0- | MF-CA-2121 | HT - HALO TRUST | AF/0108/00500/MF1665 | 35643 | 68.8566 | 34.5199 | Open | AP Only | AP Only | MineField |  | MBT Project-227 | Kabul Demining Project-16 |  |  |  |  | 1396 |  | {A6776B8B-69FD-44C4-A63C-0607FA68A1DE} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2008-09-20 | No | Open
Central | Kabul | Paghman | Kuhbaki | {3A39974D-A13E-4C37-A256-71FA33C17C49} | c0a8-00f6-13550fcebc6-e2b58379-14-36a | MF-16666 | MCPA - Mine Clearance Planning Agency | AF/0108/00504/MF0247 | 17530 | 68.9203 | 34.527 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {3A39974D-A13E-4C37-A256-71FA33C17C49} |  | Low | Agriculture Blocked | Moderate | 71 | CHA | 5 |  |  | 2011-11-22 16:30 | No | Planned
Central | Kabul | Paghman | Magnsan <Parachi> | {8EEA7ED9-D7B8-4665-8900-DE0C70CCD556} | c0a8-0057-12c3b8b9aed-e9afd772-21984- | MF-CA-1439 | MCPA - Mine Clearance Planning Agency | AF/0108/00432/MF0133 | 52948 | 68.9373 | 34.6003 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes | 2013-05-14 | 2013-08-22 | 1392-1393 | DDG | {8EEA7ED9-D7B8-4665-8900-DE0C70CCD556} |  |  |  | Moderate | 177 | CHA | 1 | Yes | This hazard is located near to community,When we went to the other task completion the people requested verbaly. | 2008-08-24 | No | Planned
Central | Kabul | Paghman | Magnsan <Parachi> | {8EEA7ED9-D7B8-4665-8900-DE0C70CCD556} | c0a8-008e-134075f17f0-12168867-d0-2a3 | MF-16370 | MCPA - Mine Clearance Planning Agency | AF/0108/00432/MF0246 | 112332 | 68.9414 | 34.5982 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes | 2013-07-06 | 2014-05-23 | 1392-1393 | DDG | {8EEA7ED9-D7B8-4665-8900-DE0C70CCD556} |  |  |  | Moderate | 1161 | CHA | 1 | Yes | This hazard is located near to community,When we went to the other task completion the people requested verbaly. | 2011-11-14 16:30 | No | Planned
Central | Kabul | Paghman | Oryakhel | {EADC28B5-F912-4060-AB63-3D33E82F2E20} | c0a8-0009-13b7f0c1a05-193e2883-6109-3 | Hz-ID-17452 | MCPA - Mine Clearance Planning Agency | AF/0108/00507/MF0253 | 4723 | 68.9577 | 34.5309 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-057 | Kabul Demining Project-03 | DOS | Yes | 2013-04-10 | 2013-05-05 | 1392-1393 | DAFA | {EADC28B5-F912-4060-AB63-3D33E82F2E20} |  |  |  | Moderate | 161 | CHA | 3 |  |  | 2012-09-30 16:30 | No | Planned
Central | Kabul | Paghman | Oryakhel | {EADC28B5-F912-4060-AB63-3D33E82F2E20} | c0a8-0009-13b830d30fa-c9fff14b-47-83c | Hz-ID-17455 | MCPA - Mine Clearance Planning Agency | AF/0108/00507/MF0254 | 30149 | 68.9572 | 34.5293 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-057 | Kabul Demining Project-03 | DOS | Yes | 2013-04-10 | 2013-10-27 | 1392-1393 | DAFA | {EADC28B5-F912-4060-AB63-3D33E82F2E20} |  |  |  | Moderate | 180 | CHA | 3 |  |  | 2012-10-01 16:30 | No | Planned
Central | Kabul | Paghman | Pas Kalay | {4899AD8B-9D13-426B-B2C7-EF996C5BDCF2} | c0a8-0057-12c3b930109-8521d8f9-268a6- | MF-CA-1460 | MCPA - Mine Clearance Planning Agency | AF/0108/00487/MF0204 | 199338 | 68.9588 | 34.4524 | Open | AP Only | AP Only | MineField |  | MBT Project-227 | Kabul Demining Project-16 |  |  |  |  | 1396 |  | {4899AD8B-9D13-426B-B2C7-EF996C5BDCF2} |  | Low | Agriculture Blocked | Moderate | 36 | CHA | 5 |  |  | 2008-10-21 | No | Open
Central | Kabul | Paghman | Pasha'i | {796DA795-0D2D-4892-AB76-3D1E34912F6F} | c0a8-0009-143765f900e-820e730f-30b5-6 | Hz-ID-18363 | MCPA - Mine Clearance Planning Agency | AF/0108/00543/MF0265 | 18180 | 68.9234 | 34.5581 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {796DA795-0D2D-4892-AB76-3D1E34912F6F} |  | Low | Agriculture Blocked | Moderate | 49 | CHA | 5 |  |  | 2013-10-27 16:30 | No | Planned
Central | Kabul | Paghman | Pasha'i | {796DA795-0D2D-4892-AB76-3D1E34912F6F} | c0a8-008e-131178b0c4e-b06e5eec-29de-a | MF-CA-1011 | MCPA - Mine Clearance Planning Agency | AF/0108/00543/MF0131 | 50071 | 68.9248 | 34.5591 | Worked on | AP Only | AP Only | MineField | 1392/1393 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes | 2013-08-22 | 2014-05-15 | 1392-1393 | DDG | {796DA795-0D2D-4892-AB76-3D1E34912F6F} |  | Medium | Critical Infrastracture | Moderate | 269 | CHA | 3 |  |  | 2008-07-10 | No | Planned
Central | Kabul | Paghman | Qal'eh ye Janda | {DCDC1329-77F9-4897-B5DF-E3AB48F45240} | c0a8-0057-12c3b8cd184-e2fe12b3-22738- | MF-CA-1465 | MCPA - Mine Clearance Planning Agency | AF/0108/00499/MF0168 | 48555 | 68.9208 | 34.503 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-057 | Kabul Demining Project-03 | DOS | Yes | 2013-04-07 | 2013-11-23 | 1392-1393 | DAFA | {DCDC1329-77F9-4897-B5DF-E3AB48F45240} |  |  |  | Moderate | 31 | CHA | 1 | Yes |  | 2008-09-11 | No | Planned
Central | Kabul | Paghman | Qal'eh ye Janda | {DCDC1329-77F9-4897-B5DF-E3AB48F45240} | c0a8-0057-12c3b8cd683-404934ed-22774- | MF-CA-1463 | MCPA - Mine Clearance Planning Agency | AF/0108/00499/MF0166 | 104177 | 68.9189 | 34.4982 | Worked on | AP Only | AP Only | MineField | 1392 | MBT Project-057 | Kabul Demining Project-03 | DOS | Yes | 2013-04-10 | 2014-09-27 | 1392-1393 | DAFA | {DCDC1329-77F9-4897-B5DF-E3AB48F45240} |  | High with Victim | High with Victims | Moderate | 73 | CHA | 1 | Yes |  | 2008-08-21 | No | Planned
Central | Kabul | Paghman | Qal'eh ye Janda | {DCDC1329-77F9-4897-B5DF-E3AB48F45240} | c0a8-0057-12c3b8cd818-3126ff35-22786- | MF-CA-1464 | MCPA - Mine Clearance Planning Agency | AF/0108/00499/MF0167 | 125744 | 68.9189 | 34.4982 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-057/A | Kabul Demining Project-03 /A | DOS | Yes | 2014-04-20 | 2014-09-27 | 1393 | DAFA | {DCDC1329-77F9-4897-B5DF-E3AB48F45240} |  | High with Victim | High with Victims | Moderate | 56 | CHA | 1 | Yes |  | 2008-08-25 | No | Planned
Central | Kabul | Paghman | Qal'eh ye Janda | {DCDC1329-77F9-4897-B5DF-E3AB48F45240} | c0a8-008e-133f8ea4a8d-4f4b405f-5ab-4f | MF-16372 | MCPA - Mine Clearance Planning Agency | AF/0108/00499/MF0243 | 44322 | 68.9223 | 34.5051 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-057 | Kabul Demining Project-03 | DOS | Yes | 2013-04-07 | 2013-11-23 | 1392-1393 | DAFA | {DCDC1329-77F9-4897-B5DF-E3AB48F45240} |  |  |  | Moderate | 31 | CHA | 1 | Yes |  | 2011-09-08 16:30 | No | Planned
Central | Kabul | Paghman | Qal'eh-ye Badal | {FD96C773-90F2-4856-BAF2-896560FD9C9F} | c0a8-0057-12c3b94687e-37280911-27785- | MF-CA-1018 | MCPA - Mine Clearance Planning Agency | AF/0108/00560/MF0123 | 8600 | 68.9379 | 34.6063 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes | 2013-09-08 | 2013-11-23 | 1392-1393 | DDG | {FD96C773-90F2-4856-BAF2-896560FD9C9F} |  |  |  | Moderate | 147 | CHA | 3 | No |  | 2008-07-14 | No | Planned
Central | Kabul | Paghman | Qal'eh-ye Badal | {FD96C773-90F2-4856-BAF2-896560FD9C9F} | c0a8-00c9-12fd999e702-269e78d5-fce-11 | MF-HQ-10916 | MCPA - Mine Clearance Planning Agency | AF/0108/00560/MF0210 | 13797 | 68.9322 | 34.6048 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes | 2013-09-08 | 2013-11-23 | 1392-1393 | DDG | {FD96C773-90F2-4856-BAF2-896560FD9C9F} |  |  |  | Moderate | 173 | CHA | 3 | No |  | 2008-11-25 | No | Planned
Central | Kabul | Paghman | Qal'eh-ye Hakim | {5750D835-98C1-4698-AC8D-BD1F0AA1A9CC} | c0a8-0009-13df25b06d7-765dc7e8-605-c1 | Hz-ID-17789 | MCPA - Mine Clearance Planning Agency | AF/0108/00578/BF0263 | 3385 | 68.9785 | 34.6042 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes | 2013-04-15 | 2013-04-18 | 1392-1393 | DDG | {5750D835-98C1-4698-AC8D-BD1F0AA1A9CC} |  |  |  | Moderate | 755 | CHA | 2 |  |  | 2013-03-31 16:30 | No | Planned
Central | Kabul | Paghman | Qal'eh-ye Hakim | {5750D835-98C1-4698-AC8D-BD1F0AA1A9CC} | c0a8-00c9-12fd99c43bc-35c82fad-ff4-5b | MF-HQ-13688 | MCPA - Mine Clearance Planning Agency | AF/0108/00578/MF0231 | 48606 | 68.9682 | 34.6154 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {5750D835-98C1-4698-AC8D-BD1F0AA1A9CC} | Contingency Plan for DAFA Kabul VTF Project 1391 | High with Victim | High with Victims | Moderate | 97 | CHA | 2 |  |  | 2009-11-15 | No | Planned
Central | Kabul | Paghman | Qal'eh-ye-Naw | {EC435539-75C0-43A7-927B-43A227DC8516} | c0a8-0009-13cb36a6237-f005c49c-5c7-59 | Hz-ID-17613 | MCPA - Mine Clearance Planning Agency | AF/0108/00482/BF0260 | 59073 | 68.8979 | 34.488 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {EC435539-75C0-43A7-927B-43A227DC8516} |  | Medium | Agriculture Blocked | Moderate | 24 | SHA | 3 | No |  | 2012-11-12 16:30 | No | Planned
Central | Kabul | Paghman | Qal'eh-ye-Naw | {EC435539-75C0-43A7-927B-43A227DC8516} | c0a8-0009-13dcf3b8c58-df3efddf-3d9-a5 | Hz-ID-17774 | MCPA - Mine Clearance Planning Agency | AF/0108/00482/MF0261 | 78415 | 68.8905 | 34.4863 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {EC435539-75C0-43A7-927B-43A227DC8516} | , | Low | Agriculture Blocked | Moderate | 56 | CHA | 5 |  |  | 2012-11-14 16:30 | No | Planned
Central | Kabul | Paghman | Seiakoh | {EACFE2FC-A7D2-4F2F-9866-AEB717F223E7} | c0a8-0009-13e8258b7d2-36d63d88-7ff-c3 | Hz-ID-17879 | MCPA - Mine Clearance Planning Agency | AF/0108/00731/BF0264 | 97289 | 68.8985 | 34.5162 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-223/B | Kabul Demining Project-08/B | DANIDA | Yes |  |  | 1393 | DDG | {EACFE2FC-A7D2-4F2F-9866-AEB717F223E7} |  | Low | Agriculture Blocked | Moderate | 52 | CHA | 5 |  |  | 2013-03-31 16:30 | No | Planned
Central | Kabul | Paghman | Wodikhel | {95412868-7181-4C02-B82E-7CCB6F4735DE} | c0a8-0009-143cdf46c4b-deade4c7-2fb8-a | Hz-ID-18412 | DDG - Danish Demining Group | AF/0108/00544/MF0266 | 73358 | 68.9221 | 34.5725 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes |  |  | 1393 | ATC | {95412868-7181-4C02-B82E-7CCB6F4735DE} |  | Medium | Critical Infrastracture | Moderate | 443 | CHA | 3 |  |  | 2013-12-12 16:30 | No | Planned
Central | Kabul | Qarabagh | Cashmeh-ye Kharuti | {D17C2F80-1F15-42B7-AE53-EA63556630C8} | c0a8-0057-12c3b96bd22-ebdbc0f8-29006- | MF-HQ-11996 | HT - HALO TRUST | H/5907 | 40800 | 69.2467 | 34.7768 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-10-11 | 2014-02-23 | 1392-1393 | HT | {D17C2F80-1F15-42B7-AE53-EA63556630C8} |  |  |  | Low | 15 | CHA | 5 |  |  | 2009-03-13 | No | Planned
Central | Kabul | Qarabagh | Chawni | {5B7BB7F3-65E8-4A5F-8B80-4DF377F8D970} | c0a8-0009-13e2b866060-b43e193f-ac6-12 | MF-CA-562 | HT - HALO TRUST | H/1715 | 10250 | 69.2391 | 34.8863 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes |  |  | 1392 | MDC | {5B7BB7F3-65E8-4A5F-8B80-4DF377F8D970} |  |  |  | Low | 83 | CHA | 3 | Yes |  | 2007-05-31 | No | Complete
Central | Kabul | Qarabagh | Gudar | {56CC1E9B-9B9C-44D3-B6BA-DCCDA8491A53} | c0a8-0009-13dc3fef70c-bebd177d-b86-4c | Hz-ID-17745 | HT - HALO TRUST | H/8400 | 16000 | 69.2237 | 34.8331 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-03-30 | 2013-06-22 | 1392-1393 | HT | {56CC1E9B-9B9C-44D3-B6BA-DCCDA8491A53} |  |  |  | Low | 188 | CHA | 4 |  |  | 2013-03-15 16:30 | No | Planned
Central | Kabul | Qarabagh | Khwaja-shoab | {77B8F1CF-9F57-42DE-BF20-BB4BCA521529} | c0a8-0057-12c3b859300-4c4d0658-1d6be- | MF-HT-1060 | HT - HALO TRUST | H/1718 | 89000 | 69.0772 | 34.8862 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-223/A | Kabul Demining Project-08 /A | Bilateral | Yes |  |  | 1393 | HT | {77B8F1CF-9F57-42DE-BF20-BB4BCA521529} |  | Low | Agriculture Blocked | Low | 149 | CHA | 4 |  |  | 2007-04-01 | No | Planned
Central | Kabul | Qarabagh | Sawzsang | {84121583-A65B-46AD-82F6-FCE51888DAB5} | c0a8-0009-13fa326b40e-a4c7cb09-cb2-b6 | Hz-ID-17991 | HT - HALO TRUST | BLU/2751 | 2115 | 69.1427 | 34.8163 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-06-11 | 2013-06-19 | 1392-1393 | HT | {84121583-A65B-46AD-82F6-FCE51888DAB5} |  |  |  | Low | 647 | CHA | 2 |  |  | 2013-06-04 16:30 | No | Planned
Central | Kabul | Qarabagh | Sawzsang | {84121583-A65B-46AD-82F6-FCE51888DAB5} | c0a8-0009-13fa3285809-bd801ef5-ce9-d7 | Hz-ID-17992 | HT - HALO TRUST | BLU/2752 | 3790 | 69.142 | 34.8164 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-06-19 | 2013-07-10 | 1392-1393 | HT | {84121583-A65B-46AD-82F6-FCE51888DAB5} |  |  |  | Low | 647 | CHA | 3 |  |  | 2013-06-19 16:30 | No | Planned
Central | Kabul | Qarabagh | Starghach | {F19FC164-0B86-4FBF-AB38-579655855D02} | c0a8-0057-12c3b72a079-c4690771-fbf3-d | MF-HQ-14857 | HT - HALO TRUST | H/7052 | 20000 | 69.0901 | 34.8921 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes |  |  | 1392 | MDC | {F19FC164-0B86-4FBF-AB38-579655855D02} |  |  |  | Low | 102 | CHA | 3 | Yes |  | 2010-07-12 | No | Complete
Central | Kabul | Shakardara | Balakarez | {96D6AC1E-0758-4C6D-856E-E0983BE1D7A8} | c0a8-0057-12c3b96203c-6d0ffa85-289e6- | MF-CA-1914 | HT - HALO TRUST | H/4380 | 33300 | 69.0171 | 34.6167 | Closed | AP Only | AP Only | MineField | 1391/1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2012-12-22 | 2013-06-21 | 1392 | HT | {96D6AC1E-0758-4C6D-856E-E0983BE1D7A8} |  |  |  | Minimal | 50 | CHA | 5 |  |  | 2010-08-20 | No | Complete
Central | Kabul | Shakardara | Chanakhel | {16AAD33E-0CA3-4D8C-99E7-81DC6AB96AB2} | c0a8-0009-1404d275d93-a116bfc1-22b2-a | Hz-ID-18092 | HT - HALO TRUST | H/8512 | 52000 | 68.9652 | 34.692 | Worked on | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-08-13 | 2013-12-23 | 1392-1393 | HT | {16AAD33E-0CA3-4D8C-99E7-81DC6AB96AB2} |  | Low | Agriculture Blocked | Minimal | 1024 | CHA | 4 |  |  | 2013-07-10 16:30 | No | Planned
Central | Kabul | Shakardara | Chanakhel | {16AAD33E-0CA3-4D8C-99E7-81DC6AB96AB2} | c0a8-00f6-1353c76b522-e4bd6b9b-1395-7 | MF-16618 | HT - HALO TRUST | H/8346 | 31854 | 68.9812 | 34.6896 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-03-16 | 2013-04-24 | 1392 | MDC | {16AAD33E-0CA3-4D8C-99E7-81DC6AB96AB2} |  |  |  | Minimal | 222 | CHA | 3 | Yes |  | 2012-01-02 16:30 | No | Complete
Central | Kabul | Shakardara | Deh-e Solayman | {E8978975-DF2E-451E-8479-531401DC8ED1} | c0a8-0009-13fb7542f11-1bb49136-3d6e-c | Hz-ID-17994 | HT - HALO TRUST | B/3033 | 1440 | 69.0384 | 34.6819 | Worked on | UXO Only | UXO Only | BF | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes |  |  | 1392-1393 | HT | {E8978975-DF2E-451E-8479-531401DC8ED1} |  | High | Critical Infrastracture | Minimal | 1731 | CHA | 3 |  |  | 2013-06-23 16:30 | No | Planned
Central | Kabul | Shakardara | Deh-e Solayman | {E8978975-DF2E-451E-8479-531401DC8ED1} | c0a8-0009-13fb781d9fd-66a4b49a-4c27-3 | Hz-ID-18003 | HT - HALO TRUST | H/8508 | 1052 | 69.0384 | 34.6819 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes |  |  | 1392-1393 | HT | {E8978975-DF2E-451E-8479-531401DC8ED1} |  |  |  | Minimal | 1731 | CHA | 3 |  |  | 2013-06-23 16:30 | No | Planned
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-0057-12c3b6b486d-ada18c1d-a294-d | MF-HQ-13733 | HT - HALO TRUST | H/6300 | 14675 | 68.998 | 34.705 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-04-20 | 2013-05-23 | 1392 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 29 | CHA | 4 |  |  | 2011-07-13 16:30 | No | Complete
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-0057-12c3b6c0e58-e44634f3-ac01-f | MF-HQ-13738 | HT - HALO TRUST | H/6731 | 38164 | 68.998 | 34.705 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-04-05 | 2013-07-10 | 1392-1393 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 115 | CHA | 5 |  |  | 2009-12-02 | No | Planned
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-0057-12c3b6c2764-5deb49fe-ad35-d | MF-HQ-13204 | HT - HALO TRUST | H/6281 | 31263 | 68.998 | 34.705 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-05-07 | 2013-07-12 | 1392 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 86 | CHA | 4 |  |  | 2009-09-03 | No | Complete
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-0057-12c3b6c4caf-ddb287f8-aefa-9 | MF-HQ-13732 | HT - HALO TRUST | H/6299 | 18354 | 68.998 | 34.705 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-06-01 | 2013-07-09 | 1392 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 29 | CHA | 4 |  |  | 2009-12-02 | No | Complete
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-0057-12c3b782ba9-8620b668-13d9b- | MF-HQ-13157 | HT - HALO TRUST | H/6282 | 20300 | 68.9992 | 34.6954 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-05-18 | 2013-07-05 | 1392 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 241 | CHA | 4 |  |  | 2009-09-04 | No | Complete
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-0057-12c3b793805-63aa950b-149d2- | MF-HQ-13728 | HT - HALO TRUST | H/6726 | 25664 | 68.998 | 34.705 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes |  |  | 1392 | MDC | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 29 | CHA | 5 | Yes |  | 2009-12-02 | No | Complete
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-0057-12c3b7af8b0-19dc3a97-15dfc- | MF-HQ-13716 | HT - HALO TRUST | H/6729 | 23540 | 68.998 | 34.705 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-05-01 | 2013-06-23 | 1392 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 29 | CHA | 4 |  |  | 2009-12-05 | No | Complete
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-008e-13122008047-9024628a-3bd-f3 | MF-HQ-13740 | HT - HALO TRUST | H/6730 | 25143 | 68.998 | 34.705 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-05-14 | 2013-07-17 | 1392-1393 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 29 | CHA | 5 |  |  | 2009-11-14 | No | Planned
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-008e-1312202c7aa-5fe3cc05-3d5-50 | MF-HQ-13730 | HT - HALO TRUST | H/6297 | 19220 | 68.998 | 34.705 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-04-07 | 2013-06-17 | 1392 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 64 | CHA | 4 |  |  | 2009-12-02 | No | Complete
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-008e-131414f3b4a-c95cec6e-190b-a | MF-HQ-14984 | HT - HALO TRUST | H/7091 | 10111 | 69.0051 | 34.7006 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-09-01 | 2013-11-23 | 1392-1393 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 35 | CHA | 5 |  |  | 2010-08-08 | No | Planned
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-008e-13431b6802f-8a0b0ab0-5c4-23 | MF-16043 | HT - HALO TRUST | H/7865 | 33333 | 68.998 | 34.705 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-05-14 | 2013-07-06 | 1392 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 86 | CHA | 4 |  |  | 2011-05-08 16:30 | No | Complete
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-008e-13431c1846e-709fc2ea-5ee-6c | MF-16045 | HT - HALO TRUST | H/7866 | 23642 | 68.998 | 34.705 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-07-07 | 2013-09-23 | 1392 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 86 | CHA | 4 |  |  | 2011-05-09 16:30 | No | Complete
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-008e-134506b74b5-7157fc19-79-417 | MF-16042 | HT - HALO TRUST | H/7862 | 40000 | 69.0061 | 34.7137 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-07-01 | 2013-09-18 | 1392-1393 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 115 | CHA | 5 |  |  | 2011-05-03 16:30 | No | Planned
Central | Kabul | Shakardara | Qala-e-Hakim Dara Shakar Dara | {FCAD4F01-CC55-4A88-9494-743963251052} | c0a8-00f6-134c0bd7cf8-46f0ccaa-e62-b7 | MF-16041 | HT - HALO TRUST | H/7861 | 46013 | 68.998 | 34.705 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-05-14 | 2013-07-22 | 1392-1393 | HT | {FCAD4F01-CC55-4A88-9494-743963251052} |  |  |  | Minimal | 115 | CHA | 5 |  |  | 2011-05-06 16:30 | No | Planned
Central | Kabul | Shakardara | Qala-Khwaja | {DC86E4E4-0A58-4DA7-BD33-62B33874329C} | c0a8-00f6-13528b504a8-5e153b6d-8f9-a5 | BF-15162 | HT - HALO TRUST | B/2532 | 520000 | 68.9869 | 34.695 | Closed | UXO Only | UXO Only | BF | 1391/1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2012-01-01 | 2012-05-08 | 1392-1393 | HT | {DC86E4E4-0A58-4DA7-BD33-62B33874329C} |  |  |  | Minimal | 2459 | CHA | 3 |  |  | 2011-10-02 16:30 | No | Planned
Central | Kabul | Shakardara | Qala-ye-Shamshir | {B4C0EBCD-2B91-4C68-8A96-D0302F3D927E} | c0a8-00f6-13551ecc403-6b05df99-3cd-9c | MF-16682 | HT - HALO TRUST | H/8348 | 37370 | 69.0115 | 34.6241 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/A | Kabul Demining Project-07/A | DOS | Yes | 2013-01-01 | 2013-04-23 | 1392 | HT | {B4C0EBCD-2B91-4C68-8A96-D0302F3D927E} |  |  |  | Minimal | 182 | CHA | 4 |  |  | 2012-01-03 16:30 | No | Complete
Central | Kabul | Shakardara | Qal'eh ye Lalay | {D6315EA7-22EA-4D93-9964-6DFB7094064A} | c0a8-0009-13f185e65db-4184c3ca-477d-f | Hz-ID-17954 | HT - HALO TRUST | H/8507 | 17600 | 69.001 | 34.691 | Worked on | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-09-18 | 2013-12-23 | 1392-1393 | HT | {D6315EA7-22EA-4D93-9964-6DFB7094064A} |  | Low | Agriculture Blocked | Minimal | 26 | CHA | 5 |  |  | 2013-05-07 16:30 | No | Planned
Central | Kabul | Shakardara | Qal'eh ye Lalay | {D6315EA7-22EA-4D93-9964-6DFB7094064A} | c0a8-0009-142d1a9e0b5-a25c4b1f-10ac-1 | Hz-ID-18253 | HT - HALO TRUST | H/8522 | 6017 | 68.997 | 34.699 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-12-14 | 2014-01-23 | 1392-1393 | HT | {D6315EA7-22EA-4D93-9964-6DFB7094064A} |  |  |  | Minimal | 281 | CHA | 4 |  |  | 2013-11-22 16:30 | No | Planned
Central | Kabul | Shakardara | Qal'eh ye Lalay | {D6315EA7-22EA-4D93-9964-6DFB7094064A} | c0a8-0009-142d1b5b37a-4165ed83-1190-e | Hz-ID-18254 | HT - HALO TRUST | H/8523 | 5311 | 68.9977 | 34.6925 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-12-14 | 2014-01-23 | 1392-1393 | HT | {D6315EA7-22EA-4D93-9964-6DFB7094064A} |  |  |  | Minimal | 241 | CHA | 4 |  |  | 2013-11-22 16:30 | No | Planned
Central | Kabul | Shakardara | Qal'eh ye Lalay | {D6315EA7-22EA-4D93-9964-6DFB7094064A} | c0a8-0009-146608b5fbe-85e8471f-6cdc-e | Hz-ID-18748 | HT - HALO TRUST | H/8538 | 11700 | 68.9973 | 34.6969 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-223/A | Kabul Demining Project-08 /A | Bilateral | Yes |  |  | 1393 | HT | {D6315EA7-22EA-4D93-9964-6DFB7094064A} |  | Low | Agriculture Blocked | Minimal | 281 | CHA | 4 |  |  | 2014-04-15 16:30 | No | Planned
Central | Kabul | Shakardara | Qal'eh ye Lalay | {D6315EA7-22EA-4D93-9964-6DFB7094064A} | c0a8-0009-146608d8fa4-106ec359-6d09-7 | Hz-ID-18749 | HT - HALO TRUST | H/8539 | 12250 | 68.9973 | 34.6969 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-223/A | Kabul Demining Project-08 /A | Bilateral | Yes |  |  | 1393 | HT | {D6315EA7-22EA-4D93-9964-6DFB7094064A} |  | Low | Agriculture Blocked | Minimal | 281 | CHA | 4 |  |  | 2014-04-17 16:30 | No | Planned
Central | Kabul | Shakardara | Qal'eh ye Lalay | {D6315EA7-22EA-4D93-9964-6DFB7094064A} | c0a8-0057-12c3b7dc3e4-5b36b9c0-17e2a- | MF-CA-792 | HT - HALO TRUST | H/4208 | 18000 | 69.0048 | 34.7032 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/B | Kabul Demining Project-07/B | GAGP | Yes | 2013-07-01 | 2013-07-29 | 1392 | HT | {D6315EA7-22EA-4D93-9964-6DFB7094064A} |  |  |  | Minimal | 35 | CHA | 4 |  |  | 2008-03-01 | No | Complete
Central | Kabul | Shakardara | Qal'eh ye Lalay | {D6315EA7-22EA-4D93-9964-6DFB7094064A} | c0a8-0057-12c3bb6d83b-c4e2a27e-3c84c- | MF-HT-1004 | HT - HALO TRUST | H/3714 | 36500 | 68.9653 | 34.6916 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-058/B | Kabul Demining Project-07/B | GAGP | Yes | 2013-07-01 |  | 1392 | HT | {D6315EA7-22EA-4D93-9964-6DFB7094064A} |  |  |  | Minimal | 76 | CHA | 4 |  |  | 2007-07-09 | No | Complete
Central | Kabul | Shakardara | Qal'eh ye Lalay | {D6315EA7-22EA-4D93-9964-6DFB7094064A} | c0a8-00f6-135520b4b2b-c17c022c-12c-ea | MF-16553 | HT - HALO TRUST | H/8347 | 21462 | 68.9821 | 34.6994 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-07-01 | 2013-09-23 | 1392-1393 | HT | {D6315EA7-22EA-4D93-9964-6DFB7094064A} |  |  |  | Minimal | 180 | CHA | 5 |  |  | 2011-12-17 16:30 | No | Planned
Central | Kabul | Shakardara | Qal'eh-ye Entefat | {9EABF878-839A-4E23-A788-84F233715573} | c0a8-00f6-137c15daf79-20994f70-1fa7-3 | MF-16762 | ATC - Afghan Technical Consultants | AF/0102/00647/MF0147 | 36900 | 69.1364 | 34.6828 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-03-16 | 2013-06-30 | 1392 | MDC | {9EABF878-839A-4E23-A788-84F233715573} |  |  |  | Minimal | 9 | CHA | 2 |  |  | 2012-03-30 16:30 | No | Complete
Central | Kabul | Shakardara | Qal'eh-ye Yonus | {35C39A10-65D4-429F-85E8-B6E808D66904} | c0a8-0009-14734090345-e2ff61d5-65b-c0 | Hz-ID-18855 | HT - HALO TRUST | H/8799 | 12530 | 68.9952 | 34.7153 | Open | AP Only | AP Only | MineField |  | MBT Project-020/A | Kabul Demining Project-02 (AT)/A |  |  |  |  | 1394 |  | {35C39A10-65D4-429F-85E8-B6E808D66904} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-06-17 16:30 | No | Open
Central | Kabul | Shakardara | Shakar Darreh | {3DCDEFA2-EE74-4429-83C8-40BB5D769AB4} | c0a8-0009-142d1a77d57-7ab04f19-103f-e | Hz-ID-18261 | HT - HALO TRUST | H/8517 | 28000 | 68.9902 | 34.7041 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-062 | Kabul Demining Project-14 | Bilateral | Yes | 2013-10-12 | 2014-01-23 | 1392-1393 | HT | {3DCDEFA2-EE74-4429-83C8-40BB5D769AB4} |  |  |  | Minimal | 1534 | CHA | 2 |  |  | 2013-10-03 16:30 | No | Planned
Central | Kabul | Shakardara | Shakar Darreh | {3DCDEFA2-EE74-4429-83C8-40BB5D769AB4} | c0a8-0057-12c3b69a521-903ab5e7-8edc-8 | BF-HQ-12342 | HT - HALO TRUST | B/1689 | 640000 | 69.08 | 34.6684 | Worked on | UXO Only | UXO Only | BF | 1389/1390 | MBT Project-020/A | Kabul Demining Project-02 (AT)/A |  | Yes | 2010-06-28 |  | 1394 | ATC | {3DCDEFA2-EE74-4429-83C8-40BB5D769AB4} |  | High with Victim | High with Victims | Minimal | 2690 | CHA | 1 |  |  | 2005-11-11 | No | Open
Central | Kabul | Surobi | Dopay | {28C186EC-FF71-48B1-AA70-2A47CB002023} | c0a8-0009-13daf88ae67-301b8cf9-1d60-d | Hz-ID-17721 | MDC - Mine Detection and Dog Center | AF/0112/00401/MF0540 | 380126 | 69.7292 | 34.5844 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-021 | Kabul Demining Project-03 (AT) | B-Germany | Yes | 2013-03-16 | 2013-12-19 | 1392 | MDC | {28C186EC-FF71-48B1-AA70-2A47CB002023} |  |  |  | Substantial | 663 | CHA | 4 |  |  | 2013-03-05 16:30 | No | Complete
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-13dc976aa73-ad399161-2178-6 | Hz-ID-17749 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0532 | 30968 | 69.6017 | 34.4819 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2013-02-18 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-13e8256aeb3-22f76a13-77a-7c | Hz-ID-17870 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0536 | 15538 | 69.6153 | 34.4844 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2013-03-13 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-13e8256fb7a-77e32bdc-795-29 | Hz-ID-17872 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0537 | 53325 | 69.6063 | 34.4901 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 25 | CHA | 5 |  |  | 2013-03-04 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-13e82575961-588b4b68-7ad-e9 | Hz-ID-17874 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0538 | 4002 | 69.6073 | 34.4861 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 6 | CHA | 5 |  |  | 2013-03-04 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-13e825920b0-db5a030b-814-6c | Hz-ID-17880 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0542 | 125788 | 69.6165 | 34.4975 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-060 | Kabul Demining Project-11 |  | No |  |  | 1395 | DDG | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 14 | CHA | 5 |  |  | 2013-03-05 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-13e82598b92-60a16f1e-830-79 | Hz-ID-17884 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0544 | 9884 | 69.6415 | 34.5365 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 25 | CHA | 5 |  |  | 2013-03-06 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-13e825a145f-96f4f4fb-849-64 | Hz-ID-17882 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0543 | 71096 | 69.6132 | 34.5012 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-060 | Kabul Demining Project-11 |  | No |  |  | 1395 | DDG | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 31 | CHA | 5 |  |  | 2013-03-06 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-13e825a72b3-ea79721e-865-bc | Hz-ID-17887 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0545 | 37125 | 69.5945 | 34.563 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-060 | Kabul Demining Project-11 |  | No |  |  | 1395 | DDG | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 93 | CHA | 5 |  |  | 2013-03-07 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-13e825d5118-f79f5f16-8b5-c1 | Hz-ID-17888 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0546 | 78597 | 69.6139 | 34.4991 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-060 | Kabul Demining Project-11 |  | No |  |  | 1395 | DDG | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2013-03-07 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-13e8793ef37-cdf45fce-21e4-f | Hz-ID-17889 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0547 | 5620 | 69.6097 | 34.4973 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-060 | Kabul Demining Project-11 |  | No |  |  | 1395 | DDG | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 31 | CHA | 5 |  |  | 2013-03-07 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-13e87945327-b279be37-21fa-7 | Hz-ID-17890 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0548 | 22812 | 69.5932 | 34.5602 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-060 | Kabul Demining Project-11 |  | No |  |  | 1395 | DDG | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 88 | CHA | 5 |  |  | 2013-03-10 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-1454556c437-1b24a7f6-34b-fa | Hz-ID-18610 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0553 | 37259 | 69.6148 | 34.4832 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 16 | CHA | 5 |  |  | 2014-02-27 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-145cadc6c0c-37129392-188b-2 | Hz-ID-18659 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0558 | 6393 | 69.6068 | 34.5026 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Medium | Critical Infrastracture | Substantial | 43 | CHA | 3 |  |  | 2014-03-05 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-145d601ef92-36c39918-381e-c | Hz-ID-18660 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0559 | 62620 | 69.6224 | 34.5037 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Critical Infrastracture | Substantial | 13 | CHA | 5 |  |  | 2014-03-06 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-145d6042d2c-b7d2f57-384b-bd | Hz-ID-18657 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0555 | 94370 | 69.594 | 34.4904 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 39 | CHA | 5 |  |  | 2014-03-02 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0009-145d608785d-dfd9de61-3882-1 | Hz-ID-18656 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0554 | 9042 | 69.5994 | 34.4932 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2014-03-01 16:30 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0057-12c3b6a3b65-71a0cc76-95dd-5 | MF-HQ-14778 | DDG - Danish Demining Group | AF/0112/00364/MF0511 | 26640 | 69.6509 | 34.5288 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 61 | CHA | 4 |  |  | 2010-06-29 | No | Open
Central | Kabul | Surobi | Ganda-khasaray | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} | c0a8-0057-12c3b71bb99-91da0dfa-f141-3 | MF-HQ-14404 | MCPA - Mine Clearance Planning Agency | AF/0112/00364/MF0501 | 38892 | 69.6642 | 34.5416 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {DC33E938-C2D7-45C9-86CA-C51199FC23FB} |  | Low | Agriculture Blocked | Substantial | 174 | CHA | 4 |  |  | 2010-03-17 | No | Open
Central | Kabul | Surobi | Gwara Khwara | {BB983060-310F-451C-A2B7-5D174C9422BE} | c0a8-0009-13e825567f6-75314d84-74a-14 | Hz-ID-17866 | MCPA - Mine Clearance Planning Agency | AF/0112/00434/MF0534 | 72609 | 69.7472 | 34.6255 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {BB983060-310F-451C-A2B7-5D174C9422BE} |  | Low | Agriculture Blocked | Substantial | 70 | CHA | 5 |  |  | 2013-03-02 16:30 | No | Open
Central | Kabul | Surobi | Gwara Khwara | {BB983060-310F-451C-A2B7-5D174C9422BE} | c0a8-0009-13e8255e3d8-13a43a5d-762-16 | Hz-ID-17868 | MCPA - Mine Clearance Planning Agency | AF/0112/00434/MF0535 | 71074 | 69.7472 | 34.6255 | Open | AP Only | AP Only | MineField |  | MBT Project-060 | Kabul Demining Project-11 |  |  |  |  | 1395 |  | {BB983060-310F-451C-A2B7-5D174C9422BE} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2013-03-03 16:30 | No | Open
Central | Kabul | Surobi | Tizini Khas | {94A1EAF7-3E37-41DF-A266-17D43F415464} | c0a8-0057-12c3b6bb66a-92b77f6d-a7e4-c | MF-HQ-13541 | DDG - Danish Demining Group | AF/0112/00355/MF0467 | 28437 | 69.5827 | 34.3626 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-04-14 | 2013-04-30 | 1392 | ATC | {94A1EAF7-3E37-41DF-A266-17D43F415464} | , |  |  | Substantial | 56 | CHA | 4 |  |  | 2009-10-01 | No | Complete
Central | Kabul | Surobi | Tizini Khas | {94A1EAF7-3E37-41DF-A266-17D43F415464} | c0a8-0057-12c3b78d35b-a4f3d2ce-14542- | BF-HQ-14010 | MCPA - Mine Clearance Planning Agency | AF/0111/00355/BF0466 | 24947 | 69.5802 | 34.4004 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2014-01-02 | 2014-04-30 | 1392 | ATC | {94A1EAF7-3E37-41DF-A266-17D43F415464} |  |  |  | Substantial | 49 | CHA | 5 |  |  | 2009-10-01 | No | Complete
Central | Kabul | Surobi | Tizini Khas | {94A1EAF7-3E37-41DF-A266-17D43F415464} | c0a8-0057-12c3b994d50-7792a80b-2aaf4- | MF-HQ-13959 | DDG - Danish Demining Group | AF/0112/00355/MF0486 | 30006 | 69.5805 | 34.365 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-020 | Kabul Demining Project-02 (AT) | DOS | Yes | 2013-05-05 | 2013-05-15 | 1392 | ATC | {94A1EAF7-3E37-41DF-A266-17D43F415464} | , |  |  | Substantial | 147 | CHA | 5 |  |  | 2009-12-21 | No | Complete
Central | Kabul | Surobi | Zero Tanga | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} | c0a8-0009-13e3badd79d-f2da0a6e-c92-f1 | Hz-ID-17787 | DAFA - Demining Agency for Afghanistan | AF/0112/00363/MF0548 | 42660 | 69.6346 | 34.5233 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-057/A | Kabul Demining Project-03 /A | DOS | Yes | 2014-04-20 | 2014-07-27 | 1393 | DAFA | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} |  |  |  | Substantial | 70 | CHA | 5 |  |  | 2013-03-20 16:30 | No | Planned
Central | Kabul | Surobi | Zero Tanga | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} | c0a8-0057-12c3ba46b36-d6916d75-319fc- | MF-CA-2164 | MCPA - Mine Clearance Planning Agency | AF/0112/00363/MF0348 | 31835 | 69.5605 | 34.5264 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes | 2014-05-01 | 2014-06-30 | 1393 | ATC | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} |  |  |  | Substantial | 24 | CHA | 5 |  |  | 2008-12-18 | No | Planned
Central | Kabul | Surobi | Zero Tanga | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} | c0a8-0057-12c3ba46f7a-b0b72a47-31a23- | MF-CA-2206 | MCPA - Mine Clearance Planning Agency | AF/0112/00363/MF0352 | 45905 | 69.566 | 34.5305 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-059 | Kabul Demining Project-10 | DOS | Yes | 2014-05-01 | 2014-07-24 | 1393 | ATC | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} |  | Low | Agriculture Blocked | Substantial | 21 | CHA | 5 |  |  | 2008-12-16 | No | Planned
Central | Kabul | Surobi | Zero Tanga | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} | c0a8-0057-12c3ba4716d-ad65c8c0-31a39- | MF-CA-2207 | MCPA - Mine Clearance Planning Agency | AF/0112/00363/MF0353 | 29813 | 69.5608 | 34.5259 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-057/A | Kabul Demining Project-03 /A | DOS | Yes |  |  | 1393 | DAFA | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} |  | Low | Agriculture Blocked | Substantial | 24 | CHA | 5 |  |  | 2008-12-18 | No | Planned
Central | Kapisa | Alasay | Sarekdar | {AD7A1F6B-B14A-4242-B105-2A363F0CAB49} | c0a8-0057-12c3b8cf097-2dc0696c-22878- | MF-HQ-11489 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0206/00910/MF0001 | 57038 | 69.7996 | 34.8937 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {AD7A1F6B-B14A-4242-B105-2A363F0CAB49} |  | High Requested | Resettlment/Local Request | High | 97 | SHA | 4 |  |  | 2009-07-28 | No | Open
Central | Kapisa | Hisa-i-Awali Kohistan | Chashma-I-Mazullah | {F7855CA6-3EB9-4F30-8556-2F73F974FB03} | c0a8-004c-13026d37de5-f991ebe2-e56-48 | MF-CA-1500 | DDG - Danish Demining Group | AF/0202/00776/MF0012 | 130212 | 69.3232 | 35.1619 | Open | AP Only | AP Only | MineField |  | MBT Project-233 | Kapisa Demining Project-08 |  |  |  |  | 1395 |  | {F7855CA6-3EB9-4F30-8556-2F73F974FB03} |  | Low | Agriculture Blocked | Minimal | 27 | CHA | 5 |  |  | 2008-09-27 | No | Open
Central | Kapisa | Hisa-i-Awali Kohistan | Galwanan | {5E903D24-A3D9-489B-B630-28D6EAA36400} | c0a8-00f6-139a94f5b3c-74a86f1b-3328-f | Hz-ID-17245 | DDG - Danish Demining Group | AF/0202/01002/MF0045 | 47 | 69.3273 | 35.1021 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {5E903D24-A3D9-489B-B630-28D6EAA36400} |  | High Requested | Resettlment/Local Request | Minimal | 836 | CHA | 1 | Yes | Local People and Authority request during my visit of DDG teams. | 2012-08-02 16:30 | No | Pledged
Central | Kapisa | Hisa-i-Awali Kohistan | Khamba | {371AE1D6-801F-422A-BA95-DDD64F1D7663} | c0a8-0057-12c3b8aa1a3-196fe29-20ed0-a | MF-CA-1490 | DDG - Danish Demining Group | AF/0202/01187/MF0020 | 127350 | 69.351 | 35.174 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {371AE1D6-801F-422A-BA95-DDD64F1D7663} | Planned Year and Agency removed | High Requested | Resettlment/Local Request | Minimal | 9 | CHA | 1 | Yes | Local People and Authority request during my visit of DDG teams. | 2008-10-20 | No | Pledged
Central | Kapisa | Hisa-i-Awali Kohistan | Khamba | {371AE1D6-801F-422A-BA95-DDD64F1D7663} | c0a8-0057-12c3b8aa3a6-7b0f38a-20ee2-5 | MF-CA-1487 | MCPA - Mine Clearance Planning Agency | AF/0202/01187/MF019 | 188600 | 69.351 | 35.174 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {371AE1D6-801F-422A-BA95-DDD64F1D7663} | Planned Year and Agency removed | High Requested | Resettlment/Local Request | Minimal | 43 | CHA | 1 | Yes | Local People and Authority request during my visit of DDG teams. | 2008-10-19 | No | Pledged
Central | Kapisa | Hisa-i-Awali Kohistan | Kuhnadeh | {D22E3E9D-A5E0-42D8-8090-FB260E490116} | c0a8-0057-12c3bb2af90-870db8f6-3a1b1- | MF-CA-1497 | DDG - Danish Demining Group | AF/0202/00978/MF0009 | 189355 | 69.2965 | 35.1664 | Open | AP Only | AP Only | MineField |  | MBT Project-233 | Kapisa Demining Project-08 |  |  |  |  | 1395 |  | {D22E3E9D-A5E0-42D8-8090-FB260E490116} |  | Low | Agriculture Blocked | Minimal | 181 | CHA | 4 |  |  | 2008-09-20 | No | Open
Central | Kapisa | Hisa-i-Awali Kohistan | Kuhnadeh | {D22E3E9D-A5E0-42D8-8090-FB260E490116} | c0a8-0057-12c3bb2b1b2-ad835618-3a1c3- | MF-CA-1498 | DDG - Danish Demining Group | AF/0202/00978/MF0010 | 28856 | 69.2953 | 35.1649 | Open | AP Only | AP Only | MineField |  | MBT Project-233 | Kapisa Demining Project-08 |  |  |  |  | 1395 |  | {D22E3E9D-A5E0-42D8-8090-FB260E490116} |  | Low | Agriculture Blocked | Minimal | 92 | CHA | 4 |  |  | 2008-09-22 | No | Open
Central | Kapisa | Hisa-i-Awali Kohistan | Kuhnadeh | {D22E3E9D-A5E0-42D8-8090-FB260E490116} | c0a8-0057-12c3bb2b3a6-8a5228bc-3a1d6- | MF-CA-1499 | DDG - Danish Demining Group | AF/0202/00978/MF0011 | 15428 | 69.2953 | 35.1649 | Open | AP Only | AP Only | MineField |  | MBT Project-233 | Kapisa Demining Project-08 |  |  |  |  | 1395 |  | {D22E3E9D-A5E0-42D8-8090-FB260E490116} |  | Low | Agriculture Blocked | Minimal | 92 | CHA | 4 |  |  | 2008-09-24 | No | Open
Central | Kapisa | Hisa-i-Awali Kohistan | Muri | {D2770724-985B-49F7-84A0-DCC0E8479320} | c0a8-00f6-1380879a00a-b6fa154a-f0a-5e | Hz-ID-17002 | ATC - Afghan Technical Consultants | AF/0202/01013/MF0041 | 37706 | 69.3862 | 35.1165 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {D2770724-985B-49F7-84A0-DCC0E8479320} |  | High with Victim | High with Victims | Minimal | 26 | CHA | 1 | Yes | Local People and Authority request during my visit of DDG teams. | 2012-04-25 16:30 | No | Pledged
Central | Kapisa | Hisa-i-Awali Kohistan | Naserkhankhel | {6671D55F-DFD3-4CA4-B922-74BF09BA07DA} | c0a8-00f6-13923397f05-ddd54ebe-3036-4 | Hz-ID-17182 | DDG - Danish Demining Group | AF/0202/00979/MF0042 | 16956 | 69.3131 | 35.1283 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {6671D55F-DFD3-4CA4-B922-74BF09BA07DA} |  | High Requested | Resettlment/Local Request | Minimal | 220 | SHA | 1 | Yes | Local People and Authority request during my visit of DDG teams. | 2012-07-08 16:30 | No | Pledged
Central | Kapisa | Hisa-i-Awali Kohistan | Pufdom | {3A413682-91F5-470D-A609-7CC1E725FDDB} | c0a8-0057-12c3bb47a49-b994bf48-3b29b- | MF-CA-1494 | DDG - Danish Demining Group | AF/0202/01186/MF0018 | 174991 | 69.3611 | 35.1635 | Open | AP Only | AP Only | MineField |  | MBT Project-233 | Kapisa Demining Project-08 |  |  |  |  | 1395 |  | {3A413682-91F5-470D-A609-7CC1E725FDDB} | Planned year removed | Low | Agriculture Blocked | Minimal | 12 | CHA | 5 |  |  | 2008-10-16 | No | Open
Central | Kapisa | Hisa-i-Awali Kohistan | Pufdom | {3A413682-91F5-470D-A609-7CC1E725FDDB} | c0a8-0057-12c3bb47c5c-98aa0107-3b2ad- | MF-CA-1492 | DDG - Danish Demining Group | AF/0202/01186/MF0017 | 217705 | 69.3611 | 35.1635 | Open | AP Only | AP Only | MineField |  | MBT Project-233 | Kapisa Demining Project-08 |  |  |  |  | 1395 |  | {3A413682-91F5-470D-A609-7CC1E725FDDB} | Planned year removed | Low | Agriculture Blocked | Minimal | 23 | CHA | 5 |  |  | 2008-10-14 | No | Open
Central | Kapisa | Hisa-i-Awali Kohistan | Rabat | {67DC5225-2DEE-497D-8F57-B99F12988ECD} | c0a8-0057-12c3b8fac70-ae28b1bd-24641- | MF-CA-1522 | DDG - Danish Demining Group | AF/0202/01184/MF0026 | 311662 | 69.3187 | 35.1713 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {67DC5225-2DEE-497D-8F57-B99F12988ECD} |  | High Requested | Resettlment/Local Request | Minimal | 229 | CHA | 1 | Yes | Local People and Authority request during my visit of DDG teams. | 2008-10-21 | No | Pledged
Central | Kapisa | Hisa-i-Awali Kohistan | Sanjan | {2E55D974-2935-43A6-88B3-A871140663D5} | c0a8-00f6-134c0a22ed0-540c64ae-d25-4b | MF-15893 | DDG - Danish Demining Group | AF/0202/01017/MF7679 | 600 | 69.3765 | 35.139 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {2E55D974-2935-43A6-88B3-A871140663D5} |  | High Requested | Resettlment/Local Request | Minimal | 10 | CHA | 1 | Yes | Local People and Authority request during my visit of DDG teams. | 2011-03-10 16:30 | No | Pledged
Central | Kapisa | Hisa-i-Awali Kohistan | Sanjan | {2E55D974-2935-43A6-88B3-A871140663D5} | c0a8-00f6-139a948efb4-a9b09be-31c3-f4 | Hz-ID-17244 | DDG - Danish Demining Group | AF/0202/01017/MF0043 | 291960 | 69.3693 | 35.1703 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {2E55D974-2935-43A6-88B3-A871140663D5} |  | High Requested | Resettlment/Local Request | Minimal | 15 | CHA | 1 | Yes | Local People and Authority request during my visit of DDG teams. | 2012-08-05 16:30 | No | Pledged
Central | Kapisa | Hisa-i-Awali Kohistan | Sanjan | {2E55D974-2935-43A6-88B3-A871140663D5} | c0a8-00f6-13a3ac11b0b-fee34334-fec0-9 | Hz-ID-17246 | MDC - Mine Detection and Dog Center | AF/0202/01017/MF0044 | 29359 | 69.3883 | 35.1206 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {2E55D974-2935-43A6-88B3-A871140663D5} |  | High Requested | Resettlment/Local Request | Minimal | 26 | CHA | 1 | Yes | Local People and Authority request during my visit of DDG teams. | 2012-07-16 16:30 | No | Pledged
Central | Kapisa | Koh Band | Durnama (1) | {0C50FB10-C033-4F4F-9D01-0461BDCED01D} | c0a8-00f6-134e600e8d2-f01b3125-862-e2 | MF-15621 | DDG - Danish Demining Group | AF/0203/01043/MF7602 | 25500 | 69.4869 | 35.0724 | Open | AP Only | AP Only | MineField |  | MBT Project-011 | Kapisa Demining Project-05 |  |  |  |  | 1396 |  | {0C50FB10-C033-4F4F-9D01-0461BDCED01D} |  | Low | Agriculture Blocked | Moderate | 34 | CHA | 5 |  |  | 2010-11-29 16:30 | No | Open
Central | Kapisa | Koh Band | Durnama (2) | {26EE2F21-7DAE-428F-90E3-A355E4648950} | c0a8-008e-1328a41a85f-1ab128ba-51c-80 | MF-15622 | DDG - Danish Demining Group | AF/0203/01047/MF7607 | 22000 | 69.4869 | 35.0724 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {26EE2F21-7DAE-428F-90E3-A355E4648950} |  | Low | Agriculture Blocked | Moderate | 9 | CHA | 4 |  |  | 2010-12-04 16:30 | No | Open
Central | Kapisa | Koh Band | Durnama (2) | {26EE2F21-7DAE-428F-90E3-A355E4648950} | c0a8-008e-1328f9b6741-580f88df-1ce9-4 | MF-15608 | DDG - Danish Demining Group | AF/0203/01047/MF7604 | 28000 | 69.4869 | 35.0724 | Open | AP Only | AP Only | MineField |  | MBT Project-011 | Kapisa Demining Project-05 |  |  |  |  | 1396 |  | {26EE2F21-7DAE-428F-90E3-A355E4648950} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2010-12-01 16:30 | No | Open
Central | Kapisa | Koh Band | Durnama (2) | {26EE2F21-7DAE-428F-90E3-A355E4648950} | c0a8-008e-1328f9baa77-1b2193fc-1d11-1 | MF-15609 | DDG - Danish Demining Group | AF/0203/01047/MF7605 | 26700 | 69.4869 | 35.0724 | Open | AP Only | AP Only | MineField |  | MBT Project-011 | Kapisa Demining Project-05 |  |  |  |  | 1396 |  | {26EE2F21-7DAE-428F-90E3-A355E4648950} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2010-12-02 16:30 | No | Open
Central | Kapisa | Koh Band | Durnama (2) | {26EE2F21-7DAE-428F-90E3-A355E4648950} | c0a8-008e-1328ff94bb5-acfb046b-2fa2-c | MF-16108 | DDG - Danish Demining Group | AF/0203/01047/MF7827 | 15000 | 69.4993 | 35.042 | Open | AP Only | AP Only | MineField |  | MBT Project-011 | Kapisa Demining Project-05 |  |  |  |  | 1396 |  | {26EE2F21-7DAE-428F-90E3-A355E4648950} |  | Medium | Critical Infrastracture | Moderate | 12 | CHA | 5 |  |  | 2011-04-05 16:30 | No | Open
Central | Kapisa | Koh Band | Durnama (2) | {26EE2F21-7DAE-428F-90E3-A355E4648950} | c0a8-008e-132c95e7e21-e8a9c4d0-3277-5 | MF-15606 | DDG - Danish Demining Group | AF/0203/01047/MF7603 | 18000 | 69.4869 | 35.0724 | Open | AP Only | AP Only | MineField |  | MBT Project-011 | Kapisa Demining Project-05 |  |  |  |  | 1396 |  | {26EE2F21-7DAE-428F-90E3-A355E4648950} |  | Low | Agriculture Blocked | Moderate | 34 | CHA | 5 |  |  | 2010-11-30 16:30 | No | Open
Central | Kapisa | Koh Band | Durnama (2) | {26EE2F21-7DAE-428F-90E3-A355E4648950} | c0a8-00f6-134c656b08f-faf77ce8-2932-7 | MF-15610 | DDG - Danish Demining Group | AF/0203/01047/MF7606 | 22500 | 69.4869 | 35.0724 | Open | AP Only | AP Only | MineField |  | MBT Project-011 | Kapisa Demining Project-05 |  |  |  |  | 1396 |  | {26EE2F21-7DAE-428F-90E3-A355E4648950} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2010-12-03 16:30 | No | Open
Central | Kapisa | Koh Band | Durnama (2) | {26EE2F21-7DAE-428F-90E3-A355E4648950} | c0a8-00f6-13533c3ec75-779d60bb-31f-e7 | MF-15508 | DDG - Danish Demining Group | AF/0203/01047/MF7555 | 29594 | 69.499 | 35.0748 | Open | AP Only | AP Only | MineField |  | MBT Project-011 | Kapisa Demining Project-05 |  |  |  |  | 1396 |  | {26EE2F21-7DAE-428F-90E3-A355E4648950} |  | Low | Agriculture Blocked | Moderate | 13 | CHA | 5 |  |  | 2010-11-08 16:30 | No | Open
Central | Kapisa | Koh Band | Jan Khan Khail | {56BB693B-7188-4041-A246-48D0E080E7A0} | c0a8-0057-12c3bafd560-b68ab254-386cb- | MF-CA-1387 | DDG - Danish Demining Group | AF/0203/00260/MF0008 | 11236 | 69.4703 | 35.1006 | Open | AT Only | AT Only | MineField |  | MBT Project-070 | Kapisa Demining Project-01 (AT) |  |  |  |  | 1398 |  | {56BB693B-7188-4041-A246-48D0E080E7A0} | Planned Agency removed | Low | Agriculture Blocked | Moderate | 27 | CHA | 4 |  |  | 2008-09-21 | No | Open
Central | Kapisa | Koh Band | Jan Khan Khail | {56BB693B-7188-4041-A246-48D0E080E7A0} | c0a8-0057-12c3bafdcee-e68cbe4d-386df- | MF-CA-1386 | DDG - Danish Demining Group | AF/0203/00260/MF0005 | 2544 | 69.4767 | 35.102 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {56BB693B-7188-4041-A246-48D0E080E7A0} | Planned Agency removed | Low | Agriculture Blocked | Moderate | 12 | CHA | 4 |  |  | 2008-09-22 | No | Open
Central | Kapisa | Koh Band | Jan Khan Khail | {56BB693B-7188-4041-A246-48D0E080E7A0} | c0a8-0057-12c3bafdf20-2fb1a8be-386f3- | MF-CA-1381 | DDG - Danish Demining Group | AF/0203/00260/MF0002 | 71949 | 69.4505 | 35.1021 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {56BB693B-7188-4041-A246-48D0E080E7A0} | Planned Agency removed | Low | Agriculture Blocked | Moderate | 949 | CHA | 4 |  |  | 2008-09-22 | No | Open
Central | Kapisa | Koh Band | Jan Khan Khail | {56BB693B-7188-4041-A246-48D0E080E7A0} | c0a8-0057-12c3bafe122-ae8f973a-38709- | MF-CA-1384 | DDG - Danish Demining Group | AF/0203/00260/MF0004 | 2596 | 69.4595 | 35.0985 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {56BB693B-7188-4041-A246-48D0E080E7A0} | Planned Agency Removed | Medium | Agriculture Blocked | Moderate | 76 | CHA | 3 |  |  | 2008-09-25 | No | Open
Central | Kapisa | Koh Band | Jan Khan Khail | {56BB693B-7188-4041-A246-48D0E080E7A0} | c0a8-0057-12c3bafe354-e50c08b2-3871d- | MF-CA-1380 | DDG - Danish Demining Group | AF/0203/00260/MF0001 | 76610 | 69.4505 | 35.1021 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {56BB693B-7188-4041-A246-48D0E080E7A0} | Planned Agency removed | Low | Agriculture Blocked | Moderate | 174 | CHA | 4 |  |  | 2008-09-18 | No | Open
Central | Kapisa | Koh Band | Malekar | {5B23C4D4-638D-47F9-BAF9-7B50ABA91827} | c0a8-008e-1328a9e7552-f34d9b70-a4d-65 | MF-15625 | DDG - Danish Demining Group | AF/0203/01044/MF7611 | 32800 | 69.4886 | 35.1025 | Open | AP Only | AP Only | MineField |  | MBT Project-011 | Kapisa Demining Project-05 |  |  |  |  | 1396 |  | {5B23C4D4-638D-47F9-BAF9-7B50ABA91827} |  | Low | Agriculture Blocked | Moderate | 35 | CHA | 5 |  |  | 2010-12-07 16:30 | No | Open
Central | Kapisa | Koh Band | Malekar | {5B23C4D4-638D-47F9-BAF9-7B50ABA91827} | c0a8-008e-1328ab3af3d-10794c05-afc-71 | MF-15624 | DDG - Danish Demining Group | AF/0203/01044/MF7610 | 33000 | 69.4886 | 35.1026 | Open | AP Only | AP Only | MineField |  | MBT Project-011 | Kapisa Demining Project-05 |  |  |  |  | 1396 |  | {5B23C4D4-638D-47F9-BAF9-7B50ABA91827} |  | Low | Agriculture Blocked | Moderate | 35 | CHA | 5 |  |  | 2010-12-06 16:30 | No | Open
Central | Kapisa | Koh Band | Malekar | {5B23C4D4-638D-47F9-BAF9-7B50ABA91827} | c0a8-008e-1328ac65f4a-f93c3b74-c0f-b4 | MF-15623 | DDG - Danish Demining Group | AF/0203/01044/MF7609 | 31000 | 69.4886 | 35.1025 | Open | AP Only | AP Only | MineField |  | MBT Project-011 | Kapisa Demining Project-05 |  |  |  |  | 1396 |  | {5B23C4D4-638D-47F9-BAF9-7B50ABA91827} |  | Low | Agriculture Blocked | Moderate | 35 | CHA | 5 |  |  | 2010-12-05 16:30 | No | Open
Central | Kapisa | Koh Band | Qala I Mirza Mir | {DCC0129E-E3D4-4F48-8E2E-F78C647749A3} | c0a8-0057-12c3b7f42a0-5e1c54b4-18e5c- | MF-CA-1396 | DDG - Danish Demining Group | AF/0203/00683/MF0007 | 8505 | 69.4204 | 35.1065 | Open | AT Only | AT Only | MineField |  | MBT Project-070 | Kapisa Demining Project-01 (AT) |  |  |  |  | 1398 |  | {DCC0129E-E3D4-4F48-8E2E-F78C647749A3} |  | High Requested | Resettlment/Local Request | Moderate | 948 | CHA | 3 | Yes |  | 2008-09-18 | No | Open
Central | Kapisa | Koh Band | Shawani | {68BAF2F6-EC52-4E57-9B41-B9A5BE804AE4} | c0a8-0057-12c3b822dd1-9fe280ef-1afb7- | MF-CA-1388 | DDG - Danish Demining Group | AF/0203/01027/MF0003 | 2728 | 69.4393 | 35.0945 | Open | AT Only | AT Only | MineField |  | MBT Project-070 | Kapisa Demining Project-01 (AT) |  |  |  |  | 1398 |  | {68BAF2F6-EC52-4E57-9B41-B9A5BE804AE4} | Planned Agency Removed | Medium | Critical Infrastracture | Moderate | 194 | CHA | 3 |  |  | 2008-09-18 | No | Open
Central | Kapisa | Koh Band | Shawani | {68BAF2F6-EC52-4E57-9B41-B9A5BE804AE4} | c0a8-0057-12c3babfb9f-34475acb-36174- | MF-CA-1390 | DDG - Danish Demining Group | AF/0203/01027/MF0006 | 9382 | 69.4282 | 35.0852 | Open | AP Only | AP Only | MineField |  | MBT Project-011 | Kapisa Demining Project-05 |  |  |  |  | 1396 |  | {68BAF2F6-EC52-4E57-9B41-B9A5BE804AE4} |  | Low | Agriculture Blocked | Moderate | 73 | CHA | 5 |  |  | 2008-09-23 | No | Open
Central | Kapisa | Koh Band | Shawani | {68BAF2F6-EC52-4E57-9B41-B9A5BE804AE4} | c0a8-0057-12c3bad1237-184bdde2-36c50- | MF-CA-1392 | DDG - Danish Demining Group | AF/0203/01027/MF0009 | 104700 | 69.4343 | 35.0881 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {68BAF2F6-EC52-4E57-9B41-B9A5BE804AE4} | Planned Agency Removed | Low | Agriculture Blocked | Moderate | 186 | CHA | 4 |  |  | 2008-09-18 | No | Open
Central | Kapisa | Mahmudi Raqi | Badamali | {D9421EDD-609C-4F09-A9F9-5E3ABE3FD930} | c0a8-00f6-135511540be-5690312a-73-a75 | MF-16665 | DDG - Danish Demining Group | AF/0201/00789/MF0088 | 678 | 69.3891 | 34.9964 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {D9421EDD-609C-4F09-A9F9-5E3ABE3FD930} |  | Medium | Critical Infrastracture | Moderate | 162 | CHA | 3 |  |  | 2011-12-10 16:30 | No | Pledged
Central | Kapisa | Mahmudi Raqi | Kuhna Qala | {00118ECA-8BD9-4102-B9AB-05CCDE60E589} | c0a8-0009-13adec5a9cc-3c44711e-e26-ed | Hz-ID-17344 | DDG - Danish Demining Group | AF/0201/00797/MF0090 | 1825 | 69.3768 | 35.0072 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-108/A | Parwan Demining Project-07/A | VTF-Japan | Yes |  |  | 1392 | ATC | {00118ECA-8BD9-4102-B9AB-05CCDE60E589} |  |  |  | Moderate | 2010 | CHA | 3 |  |  | 2012-10-14 16:30 | No | Complete
Central | Kapisa | Mahmudi Raqi | Mula Faqir Khel | {13C7F86E-B8FC-4488-8E8C-6E9A086E0610} | c0a8-0009-13b60329662-3582e755-2d1e-d | Hz-ID-17433 | DDG - Danish Demining Group | AF/0201/00776/MF0089 | 59 | 69.3254 | 35.0216 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {13C7F86E-B8FC-4488-8E8C-6E9A086E0610} |  | High with Victim | High with Victims | Moderate | 945 | CHA | 2 |  |  | 2012-09-09 16:30 | No | Pledged
Central | Kapisa | Mahmudi Raqi | Qal'a Sarkari | {968E69AA-23A7-4188-9B18-FC8EF2B775A0} | c0a8-0057-12c3b6a6fbd-90e98342-985f-9 | MF-HQ-15039 | DDG - Danish Demining Group | H/7080 | 58500 | 69.4263 | 35.0825 | Open | AP Only | AP Only | MineField |  | MBT Project-065 | Kapisa Demining Project-04 |  |  |  |  | 1396 |  | {968E69AA-23A7-4188-9B18-FC8EF2B775A0} |  | Low | Agriculture Blocked | Moderate | 7 | CHA | 5 |  |  | 2010-08-03 | No | Open
Central | Kapisa | Mahmudi Raqi | Qal'a Sarkari | {968E69AA-23A7-4188-9B18-FC8EF2B775A0} | c0a8-0057-12c3b6df596-abcca0cb-c34a-8 | MF-HQ-15040 | DDG - Danish Demining Group | AF/0202/01000/MF7081 | 61000 | 69.4263 | 35.0825 | Open | AP Only | AP Only | MineField |  | MBT Project-065 | Kapisa Demining Project-04 |  |  |  |  | 1396 |  | {968E69AA-23A7-4188-9B18-FC8EF2B775A0} |  | Low | Agriculture Blocked | Moderate | 78 | CHA | 5 |  |  | 2010-08-14 | No | Open
Central | Kapisa | Mahmudi Raqi | Qal'a Sarkari | {968E69AA-23A7-4188-9B18-FC8EF2B775A0} | c0a8-0057-12c3b6eecbe-63165696-cf12-2 | MF-HQ-15049 | DDG - Danish Demining Group | AF/0202/01000/MF7084 | 42000 | 69.4263 | 35.0825 | Open | AP Only | AP Only | MineField |  | MBT Project-065 | Kapisa Demining Project-04 |  |  |  |  | 1396 |  | {968E69AA-23A7-4188-9B18-FC8EF2B775A0} |  | Low | Agriculture Blocked | Moderate | 73 | CHA | 5 |  |  | 2010-09-18 | No | Open
Central | Kapisa | Mahmudi Raqi | Qal'a Sarkari | {968E69AA-23A7-4188-9B18-FC8EF2B775A0} | c0a8-0057-12c3b778954-e001b853-13629- | MF-HQ-15038 | DDG - Danish Demining Group | AF/0202/01000/MF7079 | 63000 | 69.4241 | 35.081 | Open | AP Only | AP Only | MineField |  | MBT Project-065 | Kapisa Demining Project-04 |  |  |  |  | 1396 |  | {968E69AA-23A7-4188-9B18-FC8EF2B775A0} |  | Low | Agriculture Blocked | Moderate | 11 | CHA | 5 |  |  | 2010-08-02 | No | Open
Central | Kapisa | Mahmudi Raqi | Qal'a Sarkari | {968E69AA-23A7-4188-9B18-FC8EF2B775A0} | c0a8-0057-12c3b7805f1-eb600499-13bd9- | MF-HQ-15037 | DDG - Danish Demining Group | AF/0202/01000/MF7078 | 50000 | 69.4229 | 35.0791 | Open | AP Only | AP Only | MineField |  | MBT Project-065 | Kapisa Demining Project-04 |  |  |  |  | 1396 |  | {968E69AA-23A7-4188-9B18-FC8EF2B775A0} |  | Low | Agriculture Blocked | Moderate | 10 | CHA | 5 |  |  | 2010-08-01 | No | Open
Central | Kapisa | Mahmudi Raqi | Shokhi | {E9EC6129-9E78-420E-86DF-C0033728AB65} | c0a8-0009-13dc997f0be-57b9f469-223c-b | Hz-ID-17760 | HT - HALO TRUST | H/8397 | 6300 | 69.3974 | 34.9811 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {E9EC6129-9E78-420E-86DF-C0033728AB65} |  | High with Victim | High with Victims | Moderate | 116 | CHA | 2 |  |  | 2013-03-05 16:30 | No | Pledged
Central | Kapisa | Mahmudi Raqi | Shokhi | {E9EC6129-9E78-420E-86DF-C0033728AB65} | c0a8-0009-13dce9c37ca-b4c78f11-162-bd | Hz-ID-17765 | HT - HALO TRUST | H/8398 | 9700 | 69.3974 | 34.9811 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {E9EC6129-9E78-420E-86DF-C0033728AB65} |  | High with Victim | High with Victims | Moderate | 823 | CHA | 2 |  |  | 2013-03-05 16:30 | No | Pledged
Central | Kapisa | Mahmudi Raqi | Shokhi | {E9EC6129-9E78-420E-86DF-C0033728AB65} | c0a8-0009-13dce9ea92b-50be3b2b-1a8-c3 | Hz-ID-17770 | HT - HALO TRUST | H/8399 | 25938 | 69.4116 | 34.9711 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {E9EC6129-9E78-420E-86DF-C0033728AB65} |  | High with Victim | High with Victims | Moderate | 352 | CHA | 2 |  |  | 2013-03-05 16:30 | No | Pledged
Central | Kapisa | Mahmudi Raqi | Shokhi | {E9EC6129-9E78-420E-86DF-C0033728AB65} | c0a8-0057-12c3b959658-5453070d-28432- | MF-HQ-14012 | DDG - Danish Demining Group | AF/0201/00727/MF0083 | 50799 | 69.4096 | 34.9769 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {E9EC6129-9E78-420E-86DF-C0033728AB65} | , | High with Victim | High with Victims | Moderate | 191 | CHA | 2 |  |  | 2010-01-07 | No | Pledged
Central | Kapisa | Mahmudi Raqi | Shokhi | {E9EC6129-9E78-420E-86DF-C0033728AB65} | c0a8-00f6-13754639f63-6708f172-66b-ac | MF-16699 | DDG - Danish Demining Group | AF/0201/00727/MF0087 | 85766 | 69.4109 | 34.982 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {E9EC6129-9E78-420E-86DF-C0033728AB65} |  | High with Victim | High with Victims | Moderate | 146 | CHA | 2 |  |  | 2011-08-25 16:30 | No | Pledged
Central | Kapisa | Mahmudi Raqi | Shokhi | {E9EC6129-9E78-420E-86DF-C0033728AB65} | c0a8-00f6-138557b9b1a-8948baeb-3c0-f1 | MF-16698 | DDG - Danish Demining Group | AF/0201/00727/MF0086 | 81329 | 69.4142 | 34.9796 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-010 | Kapisa Demining Project-01 | DOS | No |  |  | 1393 | WRA | {E9EC6129-9E78-420E-86DF-C0033728AB65} |  | High with Victim | High with Victims | Moderate | 201 | CHA | 2 |  |  | 2011-09-27 16:30 | No | Pledged
Central | Kapisa | Nijrab | Babaykhel | {1BA1B36B-4032-4103-B41D-8CA2CEE4D7B7} | c0a8-008e-1328f4ed842-2f96b3a2-f62-a2 | MF-15788 | HT - HALO TRUST | H/7649 | 30756 | 69.5521 | 35.1012 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {1BA1B36B-4032-4103-B41D-8CA2CEE4D7B7} |  | Low | Agriculture Blocked | High | 11 | CHA | 4 |  |  | 2011-01-06 16:30 | No | Open
Central | Kapisa | Nijrab | Babaykhel | {1BA1B36B-4032-4103-B41D-8CA2CEE4D7B7} | c0a8-008e-1328f680b2e-89deb20b-10ed-6 | MF-15789 | HT - HALO TRUST | H/7650 | 32500 | 69.5521 | 35.1012 | Open | AP Only | AP Only | MineField |  | MBT Project-141 | Kapisa Demining Project-06 |  |  |  |  | 1400 |  | {1BA1B36B-4032-4103-B41D-8CA2CEE4D7B7} |  | Low | Agriculture Blocked | High | 11 | CHA | 5 |  |  | 2011-01-07 16:30 | No | Open
Central | Kapisa | Nijrab | Bagh Khana Bala | {138847BC-A7EA-49AE-89B3-309CB0C5D817} | c0a8-0057-12c3bb50e5c-1f09755b-3b853- | MF-HT-787 | HT - HALO TRUST | H/1779 | 43200 | 69.6231 | 35.0222 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {138847BC-A7EA-49AE-89B3-309CB0C5D817} |  | Medium | Critical Infrastracture | High | 1007 | CHA | 3 |  |  | 2006-08-01 | No | Open
Central | Kapisa | Nijrab | Bagh Khana Bala | {138847BC-A7EA-49AE-89B3-309CB0C5D817} | c0a8-008e-1328f9ec388-d9fac6df-1ee7-b | MF-16046 | HT - HALO TRUST | H/7863 | 3966 | 69.6394 | 35.0317 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {138847BC-A7EA-49AE-89B3-309CB0C5D817} |  | Medium | Critical Infrastracture | High | 20 | CHA | 3 |  |  | 2011-05-02 16:30 | No | Open
Central | Kapisa | Nijrab | Bagh Khana Bala | {138847BC-A7EA-49AE-89B3-309CB0C5D817} | c0a8-008e-132c992621c-2ae82116-37aa-8 | MF-16049 | HT - HALO TRUST | H/7892 | 7320 | 69.6394 | 35.0317 | Open | AP Only | AP Only | MineField |  | MBT Project-141 | Kapisa Demining Project-06 |  |  |  |  | 1400 |  | {138847BC-A7EA-49AE-89B3-309CB0C5D817} |  | Medium | Critical Infrastracture | High | 20 | CHA | 5 |  |  | 2011-05-03 16:30 | No | Open
Central | Kapisa | Nijrab | Bazare Badakhshi | {F4048EE8-B4C8-40F8-BEF1-6C4B5D447F64} | c0a8-008e-1342d1612ba-ee6f07b4-32-103 | MF-15637 | HT - HALO TRUST | H/7624 | 41850 | 69.6231 | 35.0822 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {F4048EE8-B4C8-40F8-BEF1-6C4B5D447F64} |  | Medium | Critical Infrastracture | High | 173 | CHA | 4 |  |  | 2010-12-02 16:30 | No | Open
Central | Kapisa | Nijrab | Bazare Badakhshi | {F4048EE8-B4C8-40F8-BEF1-6C4B5D447F64} | c0a8-00f6-134c6377d2a-2a71fb83-278c-2 | MF-15638 | HT - HALO TRUST | H/7625 | 33000 | 69.6282 | 35.0257 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {F4048EE8-B4C8-40F8-BEF1-6C4B5D447F64} |  | Low | Agriculture Blocked | High | 173 | CHA | 4 |  |  | 2010-12-03 16:30 | No | Open
Central | Kapisa | Nijrab | Dehe Ghawchak | {370ABE0C-4D49-45C2-BA75-FFEB7F264E4F} | c0a8-0009-13bb6cebc8b-ef960c4e-2a62-a | Hz-ID-17476 | HT - HALO TRUST | H/8387 | 13611 | 69.6234 | 35.0722 | Open | AP Only | AP Only | MineField |  | MBT Project-141 | Kapisa Demining Project-06 |  |  |  |  | 1400 |  | {370ABE0C-4D49-45C2-BA75-FFEB7F264E4F} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2012-11-10 16:30 | No | Open
Central | Kapisa | Nijrab | Eskenya | {2DEAF347-5964-4156-9C03-EBF0AB667478} | c0a8-008e-132909caa5e-9b49e2c2-311-3c | MF-16148 | HT - HALO TRUST | H/7691 | 20852 | 69.6096 | 35.0393 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {2DEAF347-5964-4156-9C03-EBF0AB667478} |  | Medium | Critical Infrastracture | High | 226 | CHA | 3 |  |  | 2011-05-01 16:30 | No | Open
Central | Kapisa | Nijrab | Feroza'i | {2584F0D7-16F4-48D0-BFAB-A916E76AA556} | c0a8-0057-12c3b9c8a80-c16d038c-2cd01- | MF-HT-798 | HT - HALO TRUST | H/1780 | 140000 | 69.6279 | 34.9714 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {2584F0D7-16F4-48D0-BFAB-A916E76AA556} |  | Medium | Critical Infrastracture | High | 1667 | CHA | 3 |  |  | 2006-08-01 | No | Open
Central | Kapisa | Nijrab | Ghazibikhel | {86389034-422C-4219-9312-4E314997D78A} | c0a8-008e-1328a3783b3-623d7669-343-6b | MF-15633 | HT - HALO TRUST | H/7623 | 34500 | 69.6231 | 35.0822 | Open | AP Only | AP Only | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {86389034-422C-4219-9312-4E314997D78A} |  | Medium | Critical Infrastracture | High | 1007 | CHA | 4 |  |  | 2010-12-01 16:30 | No | Open
Central | Kapisa | Nijrab | Gyawa-i-Payan | {8797A6F0-A619-4260-817D-B0C283F48791} | c0a8-008e-1328f4f1792-15e30ab6-f78-ca | MF-15787 | HT - HALO TRUST | H/7648 | 12800 | 69.5356 | 35.0005 | Open | AP Only | AP Only | MineField |  | MBT Project-141 | Kapisa Demining Project-06 |  |  |  |  | 1400 |  | {8797A6F0-A619-4260-817D-B0C283F48791} |  | Low | Agriculture Blocked | High | 19 | CHA | 5 |  |  | 2011-01-04 16:30 | No | Open
Central | Kapisa | Nijrab | Gyawa-i-Payan | {8797A6F0-A619-4260-817D-B0C283F48791} | c0a8-008e-1328f4f9038-67217f06-fa1-9f | MF-15786 | HT - HALO TRUST | H/7647 | 19920 | 69.5356 | 35.0005 | Open | AP Only | AP Only | MineField |  | MBT Project-141 | Kapisa Demining Project-06 |  |  |  |  | 1400 |  | {8797A6F0-A619-4260-817D-B0C283F48791} |  | Low | Agriculture Blocked | High | 62 | CHA | 5 |  |  | 2011-01-02 16:30 | No | Open
Central | Kapisa | Nijrab | Gyawa-i-Payan | {8797A6F0-A619-4260-817D-B0C283F48791} | c0a8-008e-1328f6978aa-7d9fd801-1150-9 | MF-15785 | HT - HALO TRUST | H/7646 | 17240 | 69.5356 | 35.0005 | Open | AP Only | AP Only | MineField |  | MBT Project-141 | Kapisa Demining Project-06 |  |  |  |  | 1400 |  | {8797A6F0-A619-4260-817D-B0C283F48791} |  | Low | Agriculture Blocked | High | 62 | CHA | 5 |  |  | 2011-01-01 16:30 | No | Open
Central | Kapisa | Nijrab | Salakhel | {825FC1C6-F2CF-415A-85C2-3D6CA75CF371} | c0a8-0057-12c3b862417-d65d5291-1dcd7- | MF-CA-1328 | MCPA - Mine Clearance Planning Agency | AF/0204/01088//MF014 | 64500 | 69.5615 | 35.0635 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-063 | Kapisa Demining Project-07 |  |  |  |  | 1398 |  | {825FC1C6-F2CF-415A-85C2-3D6CA75CF371} |  | Medium | Agriculture Blocked | High | 10 | CHA | 3 |  |  | 2008-09-28 | No | Open
Central | Kapisa | Nijrab | Sherwani Bala | {CE19777B-B31E-48B3-9A6C-DDDEE7DCC7AF} | c0a8-0057-12c3b9110dc-9824f57b-2549e- | MF-CA-1367 | MCPA - Mine Clearance Planning Agency | AF/0204/01050/MF005 | 144200 | 69.5937 | 35.0199 | Open | AP Only | AP Only | MineField |  | MBT Project-141 | Kapisa Demining Project-06 |  |  |  |  | 1400 |  | {CE19777B-B31E-48B3-9A6C-DDDEE7DCC7AF} |  | Low | Agriculture Blocked | High | 7 | CHA | 5 |  |  | 2008-09-24 | No | Open
Central | Kapisa | Nijrab | Sherwani Bala | {CE19777B-B31E-48B3-9A6C-DDDEE7DCC7AF} | c0a8-008e-1328f9c0b1c-6cd4e9e4-1d70-e | MF-15627 | HT - HALO TRUST | H/7617 | 22000 | 69.5939 | 35.0273 | Open | AP Only | AP Only | MineField |  | MBT Project-141 | Kapisa Demining Project-06 |  |  |  |  | 1400 |  | {CE19777B-B31E-48B3-9A6C-DDDEE7DCC7AF} |  | Low | Agriculture Blocked | High | 7 | CHA | 5 |  |  | 2010-11-27 16:30 | No | Open
Central | Kapisa | Nijrab | Sherwani Bala | {CE19777B-B31E-48B3-9A6C-DDDEE7DCC7AF} | c0a8-008e-1328f9c4213-f7f4d2ad-1d86-c | MF-15626 | HT - HALO TRUST | H/7616 | 32000 | 69.5885 | 35.0254 | Open | AP Only | AP Only | MineField |  | MBT Project-141 | Kapisa Demining Project-06 |  |  |  |  | 1400 |  | {CE19777B-B31E-48B3-9A6C-DDDEE7DCC7AF} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2010-11-26 16:30 | No | Open
Central | Kapisa | Tagab | Gwan | {1DE8A0A3-1B5F-4EEB-8806-7A7D764A253B} | c0a8-0057-12c3bb5e567-e739ab6-3bff9-b | MF-HQ-11488 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0205/00855/MF0008 | 263250 | 69.7048 | 34.7242 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-064 | Kapisa Demining Project-02 |  |  |  |  | 1399 |  | {1DE8A0A3-1B5F-4EEB-8806-7A7D764A253B} |  | Low | Agriculture Blocked | High | 27 | SHA | 5 |  |  | 2009-07-28 | No | Open
Central | Kapisa | Tagab | Karezuna | {1C4AADC3-64FF-471B-A390-A60FAB980CCF} | c0a8-0057-12c3bb7b2ce-7d2b164a-3d01a- | MF-HQ-10276 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0205/01068/MF0010 | 616495 | 69.6129 | 34.9359 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-070 | Kapisa Demining Project-01 (AT) |  |  |  |  | 1398 |  | {1C4AADC3-64FF-471B-A390-A60FAB980CCF} |  | Low | Agriculture Blocked | High | 1007 | SHA | 4 |  |  | 2009-11-03 16:30 | No | Open
Central | Kapisa | Tagab | Kora | {D787CE8B-D7D7-4F7D-9CA3-8A838922FB86} | c0a8-0057-12c3b7f6961-c5e4ed34-19052- | MF-HQ-11493 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0205/01069/MF0005 | 370575 | 69.6218 | 34.9321 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-070 | Kapisa Demining Project-01 (AT) |  |  |  |  | 1398 |  | {D787CE8B-D7D7-4F7D-9CA3-8A838922FB86} |  | Low | Agriculture Blocked | High | 406 | SHA | 4 |  |  | 2009-07-28 | No | Open
Central | Kapisa | Tagab | Kora | {D787CE8B-D7D7-4F7D-9CA3-8A838922FB86} | c0a8-0057-12c3b81f822-6dae339c-1ad46- | MF-HQ-11490 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0205/01069/MF0006 | 200000 | 69.5933 | 34.9193 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-064 | Kapisa Demining Project-02 |  |  |  |  | 1399 |  | {D787CE8B-D7D7-4F7D-9CA3-8A838922FB86} |  | Low | Agriculture Blocked | High | 26 | SHA | 5 |  |  | 2009-07-28 | No | Open
Central | Kapisa | Tagab | Kora | {D787CE8B-D7D7-4F7D-9CA3-8A838922FB86} | c0a8-0057-12c3b988cb4-21b42342-2a329- | MF-HQ-11491 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0205/01069/MF0007 | 24000 | 69.6233 | 34.9104 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-070 | Kapisa Demining Project-01 (AT) |  |  |  |  | 1398 |  | {D787CE8B-D7D7-4F7D-9CA3-8A838922FB86} |  | Medium | Critical Infrastracture | High | 134 | SHA | 3 |  |  | 2009-07-28 | No | Open
Central | Kapisa | Tagab | Kora | {D787CE8B-D7D7-4F7D-9CA3-8A838922FB86} | c0a8-0057-12c3ba7edd3-79f1dec5-33c37- | MF-HQ-11492 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0205/01069/MF0004 | 241900 | 69.6116 | 34.9319 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-070 | Kapisa Demining Project-01 (AT) |  |  |  |  | 1398 |  | {D787CE8B-D7D7-4F7D-9CA3-8A838922FB86} |  | Medium | Critical Infrastracture | High | 102 | SHA | 3 |  |  | 2009-07-28 | No | Open
Central | Kapisa | Tagab | Nawrozkhel | {2D21B1F1-80BE-444C-B9FD-97B9F736D996} | c0a8-0057-12c3ba9c401-3c202cad-34d55- | MF-HQ-11496 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0205/00816/MF0009 | 308000 | 69.654 | 34.7974 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-064 | Kapisa Demining Project-02 |  |  |  |  | 1399 |  | {2D21B1F1-80BE-444C-B9FD-97B9F736D996} |  | Low | Critical Infrastracture | High | 171 | SHA | 4 |  |  | 2009-07-28 | No | Open
Central | Kapisa | Tagab | Shatoray | {A2E56BDD-7934-4E3F-B835-28E144EFA797} | c0a8-0057-12c3bb63ad5-e01fd0e8-3c2ce- | MF-HQ-11494 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0205/00804/MF0003 | 432000 | 69.6504 | 34.8114 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-064 | Kapisa Demining Project-02 |  |  |  |  | 1399 |  | {A2E56BDD-7934-4E3F-B835-28E144EFA797} |  | Medium | Critical Infrastracture | High | 329 | SHA | 3 |  |  | 2009-07-28 | No | Open
Central | Logar | Azra | Qasemkhel (1) | {AE42DFC8-656A-492C-90D6-EAFC73A74AF2} | c0a8-0057-12c3b804156-7286e039-199e1- | MF-HQ-14126 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/5724/03928/MF0008 | 11880 | 69.441 | 33.9555 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-114 | Logar Demining Project-19 (AT) | DOS |  |  |  | 1395 |  | {AE42DFC8-656A-492C-90D6-EAFC73A74AF2} |  | Medium | Critical Infrastracture | Substantial | 86 | SHA | 3 |  |  | 2010-02-01 | No | Open
Central | Logar | Azra | Speen Jumat | {4BA9BBF1-1BA1-49B0-9932-8607FF66F947} | c0a8-0057-12c3baa86f0-e6ec4b58-3542d- | MF-HQ-14162 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/5724/00226/MF0009 | 24650 | 69.738 | 34.0497 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-114 | Logar Demining Project-19 (AT) | DOS |  |  |  | 1395 |  | {4BA9BBF1-1BA1-49B0-9932-8607FF66F947} |  | Low | Agriculture Blocked | Substantial | 9 | SHA | 5 |  |  | 2010-02-01 | No | Open
Central | Logar | Baraki Barak | Baraki | {79EA060A-5402-43DA-93C4-938A47418610} | c0a8-0057-12c3bb4a10b-ba691997-3b442- | MF-HQ-11504 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0503/31856/MF0003 | 162000 | 68.9076 | 33.9716 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-022 | Logar Demining Project-01 (AT) |  |  |  |  | 1397 |  | {79EA060A-5402-43DA-93C4-938A47418610} |  | High with Victim | High with Victims | High | 1 | SHA | 2 |  |  | 2009-07-28 | No | Open
Central | Logar | Charkh | Bandoka | {DD7CA801-F29E-422B-A97E-AC2741011AA7} | c0a8-0057-12c3ba30269-2fbfe108-30c47- | MF-HQ-11503 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0502/03805/MF0002 | 52002 | 68.954 | 33.8159 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-022 | Logar Demining Project-01 (AT) |  |  |  |  | 1397 |  | {DD7CA801-F29E-422B-A97E-AC2741011AA7} |  | High with Victim | High with Victims | High | 818 | SHA | 2 |  |  | 2009-07-28 | No | Open
Central | Logar | Charkh | Bandoka | {DD7CA801-F29E-422B-A97E-AC2741011AA7} | c0a8-0057-12c3bb76433-c06c3eb1-3cd12- | MF-HQ-11502 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0502/03805/MF0003 | 211200 | 68.9596 | 33.816 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-022 | Logar Demining Project-01 (AT) |  |  |  |  | 1397 |  | {DD7CA801-F29E-422B-A97E-AC2741011AA7} |  | High with Victim | High with Victims | High | 647 | SHA | 2 |  |  | 2009-07-28 | No | Open
Central | Logar | Charkh | Garmaba (Fazal Haq's village) | {6332FE29-8236-43F5-8E67-9FF7C2EEB1CF} | c0a8-0057-12c3b8a303d-a948d272-20a00- | MF-CA-419 | MCPA - Mine Clearance Planning Agency | AF/0502/00000/MF 001 | 123745 | 68.9751 | 33.8419 | Open | AT Only | AT Only | MineField | Blank | MBT Project-022 | Logar Demining Project-01 (AT) |  | No |  |  | 1397 | None | {6332FE29-8236-43F5-8E67-9FF7C2EEB1CF} |  | Medium | Critical Infrastracture | High | 19 | CHA | 3 |  |  | 2006-11-01 | No | Open
Central | Logar | Charkh | Garmaba (Fazal Haq's village) | {6332FE29-8236-43F5-8E67-9FF7C2EEB1CF} | c0a8-0057-12c3b8a3211-d095b135-20a20- | MF-CA-2117 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0502/00299/MF002 | 156255 | 68.9751 | 33.8419 | Open | AT Only | AT Only | MineField |  | MBT Project-022 | Logar Demining Project-01 (AT) |  |  |  |  | 1397 |  | {6332FE29-8236-43F5-8E67-9FF7C2EEB1CF} |  | High | Critical Infrastracture | High | 341 | CHA | 3 |  |  | 2009-03-15 | No | Open
Central | Logar | Khoshi | Arat | {6EF49838-2CDD-4E49-89BB-3133272B9287} | c0a8-0009-13e783173e6-99f28ff6-131a-c | Hz-ID-17836 | MCPA - Mine Clearance Planning Agency | AF/0504/03715/MF0051 | 166966 | 69.2618 | 33.9613 | Open | AP Only | AP Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {6EF49838-2CDD-4E49-89BB-3133272B9287} |  | Low | Agriculture Blocked | Substantial | 245 | CHA | 5 |  |  | 2013-03-25 16:30 | No | Open
Central | Logar | Khoshi | Arat | {6EF49838-2CDD-4E49-89BB-3133272B9287} | c0a8-0057-12c3bb6a03b-ff29261c-3c65e- | MF-HQ-12882 | MCPA - Mine Clearance Planning Agency | AF/0504/03715/MF0017 | 81510 | 69.2428 | 33.9684 | Open | AP Only | AP Only | MineField |  | MBT Project-114 | Logar Demining Project-19 (AT) | DOS |  |  |  | 1395 |  | {6EF49838-2CDD-4E49-89BB-3133272B9287} |  | Low | Agriculture Blocked | Substantial | 31 | CHA | 5 |  |  | 2009-10-05 | No | Open
Central | Logar | Khoshi | Chenari | {E9187D9B-20F1-4DA9-94D4-A9EC9C9E8AC8} | c0a8-0009-13f09aa3759-84f2923e-1e46-c | Hz-ID-17930 | MCPA - Mine Clearance Planning Agency | AF/0504/03697/MF0055 | 18002 | 69.2798 | 33.9847 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {E9187D9B-20F1-4DA9-94D4-A9EC9C9E8AC8} |  | Low | Agriculture Blocked | Substantial | 31 | CHA | 5 |  |  | 2013-04-17 16:30 | No | Open
Central | Logar | Khoshi | Chenari | {E9187D9B-20F1-4DA9-94D4-A9EC9C9E8AC8} | c0a8-0057-12c3bae34b2-b6418a40-37716- | MF-HQ-11501 | MCPA - Mine Clearance Planning Agency | AF/0504/03697/MF0013 | 42776 | 69.2807 | 33.9874 | Open | AT Only | AT Only | MineField |  | MBT Project-198 | Logar Demining Project-18 (AT) |  |  |  |  | 1399 |  | {E9187D9B-20F1-4DA9-94D4-A9EC9C9E8AC8} |  | Low | Agriculture Blocked | Substantial | 106 | CHA | 4 |  |  | 2009-07-28 | No | Open
Central | Logar | Khoshi | Darkh | {AD7E168F-BDAD-445C-B3D4-3E17C8C0099A} | c0a8-0009-14490d3ecf8-945b2711-583-a5 | Hz-ID-18507 | MCPA - Mine Clearance Planning Agency | AF/0504/03725/MF0069 | 2190 | 69.2917 | 34.0607 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {AD7E168F-BDAD-445C-B3D4-3E17C8C0099A} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2014-01-22 16:30 | No | Open
Central | Logar | Khoshi | Darkh | {AD7E168F-BDAD-445C-B3D4-3E17C8C0099A} | c0a8-0009-14495deecff-d3dd6868-e07-f2 | Hz-ID-18508 | MCPA - Mine Clearance Planning Agency | AF/0504/03725/MF0070 | 12191 | 69.2934 | 34.0597 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {AD7E168F-BDAD-445C-B3D4-3E17C8C0099A} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2014-01-23 16:30 | No | Open
Central | Logar | Khoshi | Daryakhan | {3D431BD7-F311-4DA8-AEC8-A3CD8BBCA966} | c0a8-0009-13f095e2b29-3bc9a15b-17c8-6 | Hz-ID-17934 | MCPA - Mine Clearance Planning Agency | AF/0504/03724/MF0059 | 26699 | 69.2272 | 34.0416 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/D | Logar Demining Project-08 (AT)/D | B-Germany | Yes | 2013-12-01 | 2013-12-10 | 1392 | HT | {3D431BD7-F311-4DA8-AEC8-A3CD8BBCA966} |  |  |  | Substantial | 50 | CHA | 5 |  |  | 2013-04-23 16:30 | No | Complete
Central | Logar | Khoshi | Daryakhan | {3D431BD7-F311-4DA8-AEC8-A3CD8BBCA966} | c0a8-0009-13f097003f3-e9451f28-193a-9 | Hz-ID-17933 | MCPA - Mine Clearance Planning Agency | AF/0504/03724/MF0058 | 15077 | 69.2451 | 34.0376 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/D | Logar Demining Project-08 (AT)/D | B-Germany | Yes | 2013-12-15 | 2013-12-23 | 1392 | HT | {3D431BD7-F311-4DA8-AEC8-A3CD8BBCA966} |  |  |  | Substantial | 159 | CHA | 3 |  |  | 2013-04-21 16:30 | No | Complete
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-0009-13e732961b7-e86bc53c-420-ef | Hz-ID-17826 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0052 | 120232 | 69.1586 | 34.0116 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-114/B | Logar Demining Project-19 (AT)/B | DOS | Yes | 2013-12-06 | 2013-12-30 | 1393 | DAFA | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 285 | CHA | 5 |  |  | 2013-03-26 16:30 | No | Planned
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-0009-13e732cba19-ae2027c0-44b-4c | Hz-ID-17827 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0053 | 29073 | 69.201 | 34.0153 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-114/B | Logar Demining Project-19 (AT)/B | DOS | Yes | 2014-08-07 | 2014-08-13 | 1393 | DAFA | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  | Low | Agriculture Blocked | Substantial | 417 | CHA | 5 |  |  | 2013-03-25 16:30 | No | Planned
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-0009-13e73a566a4-a0e4c8eb-10bf-2 | Hz-ID-17828 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0054 | 82559 | 69.1717 | 34.01 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-114/B | Logar Demining Project-19 (AT)/B | DOS | Yes | 2014-08-14 | 2014-08-30 | 1393 | DAFA | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  | Medium | Critical Infrastracture | Substantial | 420 | CHA | 5 |  |  | 2013-03-28 16:30 | No | Planned
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-0009-13e78304f68-e376cae-1300-e8 | Hz-ID-17835 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0050 | 66265 | 69.1195 | 34.0078 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/D | Logar Demining Project-08 (AT)/D | B-Germany | Yes | 2013-08-13 | 2013-12-23 | 1392 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 108 | CHA | 5 |  |  | 2013-03-18 16:30 | No | Complete
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-0009-14490977361-9c070c60-43a-67 | Hz-ID-18505 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0067 | 4793 | 69.1785 | 33.996 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  | Medium | Agriculture Blocked | Substantial | 23 | CHA | 5 |  |  | 2014-01-29 16:30 | No | Planned
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-0009-144909910b5-310cdf8f-450-16 | Hz-ID-18506 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0068 | 67620 | 69.1731 | 33.9949 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes | 2014-06-02 | 2014-06-21 | 1393 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 14 | CHA | 5 |  |  | 2014-01-25 16:30 | No | Planned
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-0057-12c3ba3ee0c-31adf918-31518- | MF-HQ-13621 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0026 | 24724 | 69.1685 | 34.0101 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/D | Logar Demining Project-08 (AT)/D | B-Germany | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 875 | CHA | 1 | Yes |  | 2009-11-05 | No | Complete
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-00f6-135133be8d2-5d76d7d2-36c-50 | MF-16130 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0040 | 126357 | 69.1316 | 34.0099 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/A | Logar Demining Project-08 (AT)/A | OCHA | Yes | 2013-04-01 | 2013-09-23 | 1392 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 9 | CHA | 1 | Yes |  | 2011-06-14 16:30 | No | Complete
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-00f6-13514494f1f-a9fd305f-21-bf2 | MF-16136 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0045 | 85064 | 69.132 | 34.0101 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/A | Logar Demining Project-08 (AT)/A | OCHA | Yes | 2013-04-01 | 2013-09-23 | 1392 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 8 | CHA | 1 | Yes |  | 2011-06-20 16:30 | No | Complete
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-00f6-13514523865-78cee9fd-59-77c | MF-16133 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0043 | 109265 | 69.1389 | 34.0113 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/A | Logar Demining Project-08 (AT)/A | OCHA | Yes | 2013-05-10 | 2013-08-23 | 1392 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 127 | CHA | 1 | Yes |  | 2011-06-18 16:30 | No | Complete
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-00f6-13514547dd6-92107a5-71-9793 | MF-16131 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0041 | 140454 | 69.132 | 34.0101 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/A | Logar Demining Project-08 (AT)/A | OCHA | Yes | 2013-04-01 | 2013-09-23 | 1392 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 221 | CHA | 1 | Yes |  | 2011-06-15 16:30 | No | Complete
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-00f6-135145716c1-836e25ad-ab-13e | MF-16135 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0044 | 139824 | 69.1389 | 34.0113 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/A | Logar Demining Project-08 (AT)/A | OCHA | Yes | 2013-05-06 | 2013-09-23 | 1392 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 243 | CHA | 1 | Yes |  | 2011-06-19 16:30 | No | Complete
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-00f6-13514595be5-d72b6d6c-db-ef8 | MF-16132 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0042 | 82638 | 69.1389 | 34.0111 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/A | Logar Demining Project-08 (AT)/A | OCHA | Yes | 2013-05-10 | 2013-07-23 | 1392 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 137 | CHA | 1 | Yes |  | 2011-06-16 16:30 | No | Complete
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-00f6-1353d56a279-13b79ecf-16c9-e | MF-16638 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0048 | 153154 | 69.1474 | 34.0122 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-114/B | Logar Demining Project-19 (AT)/B | DOS | Yes | 2014-04-20 | 2014-08-06 | 1393 | DAFA | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  | High Requested | Resettlment/Local Request | Substantial | 438 | CHA | 1 | Yes |  | 2011-07-12 16:30 | No | Planned
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-00f6-135513c4c74-4eda581c-ea-439 | MF-16660 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0046 | 123492 | 69.132 | 34.0101 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/A | Logar Demining Project-08 (AT)/A | OCHA | Yes | 2013-04-01 | 2013-09-23 | 1392 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 94 | CHA | 1 | Yes |  | 2011-07-09 16:30 | No | Complete
Central | Logar | Khoshi | Deh-e Payan | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} | c0a8-00f6-1355186cdde-67736805-294-56 | MF-16663 | MCPA - Mine Clearance Planning Agency | AF/0504/03712/MF0047 | 65316 | 69.153 | 34.0124 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/D | Logar Demining Project-08 (AT)/D | B-Germany | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {EA8208D3-EB5B-4AA9-987C-6CEF8AE4E725} |  |  |  | Substantial | 306 | CHA | 1 | Yes |  | 2011-07-11 16:30 | No | Complete
Central | Logar | Khoshi | Dokanha-i-Dobandi | {95FAE501-0D68-4980-BD82-DA590F1A779A} | c0a8-0009-14401963edc-43814861-85-32e | Hz-ID-18442 | MCPA - Mine Clearance Planning Agency | AF/0504/03696/MF0063 | 23903 | 69.3162 | 33.9588 | Open | AT Only | AT Only | MineField |  | MBT Project-178 | Logar Demining Project-02 |  |  |  |  | 1395 |  | {95FAE501-0D68-4980-BD82-DA590F1A779A} |  | Medium | Critical Infrastracture | Substantial | 631 | CHA | 3 |  |  | 2013-12-25 16:30 | No | Open
Central | Logar | Khoshi | Dokanha-i-Dobandi | {95FAE501-0D68-4980-BD82-DA590F1A779A} | c0a8-0009-144019799ef-b2dfab80-f4-515 | Hz-ID-18441 | MCPA - Mine Clearance Planning Agency | AF/0504/03696/MF0062 | 9016 | 69.3162 | 33.9588 | Open | AT Only | AT Only | MineField |  | MBT Project-178 | Logar Demining Project-02 |  |  |  |  | 1395 |  | {95FAE501-0D68-4980-BD82-DA590F1A779A} |  | Medium | Critical Infrastracture | Substantial | 584 | CHA | 3 |  |  | 2013-12-24 16:30 | No | Open
Central | Logar | Khoshi | Dokanha-i-Dobandi | {95FAE501-0D68-4980-BD82-DA590F1A779A} | c0a8-0009-14401b22b74-9896ab57-41a-de | Hz-ID-18440 | MCPA - Mine Clearance Planning Agency | AF/0504/03696/MF0061 | 18877 | 69.3159 | 33.9628 | Open | AP Only | AP Only | MineField |  | MBT Project-198 | Logar Demining Project-18 (AT) |  |  |  |  | 1399 |  | {95FAE501-0D68-4980-BD82-DA590F1A779A} |  | Low | Agriculture Blocked | Substantial | 136 | CHA | 4 |  |  | 2013-12-23 16:30 | No | Open
Central | Logar | Khoshi | Dokanha-i-Dobandi | {95FAE501-0D68-4980-BD82-DA590F1A779A} | c0a8-0009-144908c5572-b861abb0-3f2-c7 | Hz-ID-18502 | MCPA - Mine Clearance Planning Agency | AF/0504/03696/MF0064 | 5635 | 69.3162 | 33.9588 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {95FAE501-0D68-4980-BD82-DA590F1A779A} |  | Medium | Critical Infrastracture | Substantial | 448 | CHA | 5 |  |  | 2014-01-01 16:30 | No | Open
Central | Logar | Khoshi | Ghozarkhel | {25B5F0C2-520D-4AE8-9D9C-4534615F0C98} | c0a8-0009-1449090dd2c-9aa90045-409-d3 | Hz-ID-18503 | MCPA - Mine Clearance Planning Agency | AF/0504/03707/MF0065 | 27280 | 69.3342 | 33.9641 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {25B5F0C2-520D-4AE8-9D9C-4534615F0C98} |  | Low | Agriculture Blocked | Substantial | 1070 | CHA | 5 |  |  | 2014-01-02 16:30 | No | Open
Central | Logar | Khoshi | Gulmohammad khel | {282A5266-CC18-4004-BB86-68C912436277} | c0a8-0057-12c3ba1165c-9c13c6bc-2f9a6- | MF-HQ-12883 | HT - HALO TRUST | AF/0504/03717/MF0018 | 4820 | 69.2385 | 34.0328 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes | 2014-03-07 | 2014-04-01 | 1393 | HT | {282A5266-CC18-4004-BB86-68C912436277} |  |  |  | Substantial | 160 | CHA | 3 |  |  | 2009-10-05 | No | Planned
Central | Logar | Khoshi | Hotak | {65092C28-510E-4A58-AB59-B7AD8EE1264A} | c0a8-0057-12c3ba89db0-c4d27bde-3428e- | MF-HQ-13620 | MCPA - Mine Clearance Planning Agency | AF/0504/31970/MF0027 | 111539 | 69.2503 | 33.9934 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-114/B | Logar Demining Project-19 (AT)/B | DOS | Yes | 2014-09-01 | 2014-09-28 | 1393 | DAFA | {65092C28-510E-4A58-AB59-B7AD8EE1264A} |  | High Requested | Resettlment/Local Request | Substantial | 265 | CHA | 1 | Yes |  | 2009-11-05 | No | Planned
Central | Logar | Khoshi | Kandaw (1) | {67B07205-5C08-41F5-A691-831A293FCB4A} | c0a8-0057-12c3b927d50-b0874f89-26342- | MF-HQ-12886 | MCPA - Mine Clearance Planning Agency | AF/0504/03686/MF0020 | 15244 | 69.3023 | 33.9545 | Open | AT Only | AT Only | MineField |  | MBT Project-198 | Logar Demining Project-18 (AT) |  |  |  |  | 1399 |  | {67B07205-5C08-41F5-A691-831A293FCB4A} |  | Low | Critical Infrastracture | Substantial | 241 | CHA | 4 |  |  | 2009-10-05 | No | Open
Central | Logar | Khoshi | Kandaw (1) | {67B07205-5C08-41F5-A691-831A293FCB4A} | c0a8-0057-12c3b974255-b7ef3e1c-2957f- | MF-HQ-12884 | MCPA - Mine Clearance Planning Agency | AF/0504/03686/MF0019 | 40659 | 69.3136 | 33.9583 | Open | AT Only | AT Only | MineField |  | MBT Project-198 | Logar Demining Project-18 (AT) |  |  |  |  | 1399 |  | {67B07205-5C08-41F5-A691-831A293FCB4A} |  | Low | Critical Infrastracture | Substantial | 651 | CHA | 4 |  |  | 2009-10-05 | No | Open
Central | Logar | Khoshi | Kandaw (1) | {67B07205-5C08-41F5-A691-831A293FCB4A} | c0a8-0057-12c3b99d496-988a2d00-2b0ac- | MF-HQ-12887 | MCPA - Mine Clearance Planning Agency | AF/0504/03686/MF0021 | 6146 | 69.2836 | 33.9594 | Open | AT Only | AT Only | MineField |  | MBT Project-178 | Logar Demining Project-02 |  |  |  |  | 1395 |  | {67B07205-5C08-41F5-A691-831A293FCB4A} |  | Low | Critical Infrastracture | Substantial | 41 | CHA | 3 |  |  | 2009-10-05 | No | Open
Central | Logar | Khoshi | Kandaw (1) | {67B07205-5C08-41F5-A691-831A293FCB4A} | c0a8-0057-12c3b9a85b8-50f6e98d-2b812- | MF-HQ-12888 | MCPA - Mine Clearance Planning Agency | AF/0504/03686/MF0022 | 22990 | 69.2826 | 33.9248 | Open | AT Only | AT Only | MineField |  | MBT Project-114 | Logar Demining Project-19 (AT) | DOS |  |  |  | 1395 |  | {67B07205-5C08-41F5-A691-831A293FCB4A} |  | Low | Other | Substantial | 18 | CHA | 5 |  |  | 2009-10-05 | No | Open
Central | Logar | Khoshi | Kandaw (1) | {67B07205-5C08-41F5-A691-831A293FCB4A} | c0a8-0057-12c3ba372f5-70c672e4-3105d- | MF-HQ-12889 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0504/03686/MF0023 | 7118 | 69.3027 | 33.9553 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-114 | Logar Demining Project-19 (AT) | DOS |  |  |  | 1395 |  | {67B07205-5C08-41F5-A691-831A293FCB4A} |  | Low | Critical Infrastracture | Substantial | 152 | SHA | 5 |  |  | 2009-10-05 | No | Open
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-0009-145d6482074-a850f472-3cdd-7 | Hz-ID-18652 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0076 | 111171 | 69.2122 | 34.0494 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2014-03-17 16:30 | No | Open
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-0009-145d64f72d4-fd64d1f-3d94-a8 | Hz-ID-18651 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0075 | 74545 | 69.2122 | 34.0494 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2014-03-16 16:30 | No | Open
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-0009-145da8c35c4-abab1d9-1b90-14 | Hz-ID-18647 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0071 | 55946 | 69.172 | 34.0563 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  | Low | Agriculture Blocked | Substantial | 70 | CHA | 5 |  |  | 2014-03-03 16:30 | No | Open
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-0009-145da8da190-4c79bd14-1bb5-2 | Hz-ID-18648 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0072 | 57727 | 69.172 | 34.0563 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  | Low | Agriculture Blocked | Substantial | 70 | CHA | 5 |  |  | 2014-03-04 16:30 | No | Open
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-0009-145da8ef9bd-1aa4bd54-1bdb-8 | Hz-ID-18649 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0073 | 79082 | 69.172 | 34.0563 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  | Low | Agriculture Blocked | Substantial | 42 | CHA | 5 |  |  | 2014-03-05 16:30 | No | Open
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-008e-1311c82dd7e-6665d198-103d-5 | MF-HQ-12885 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0029 | 101235 | 69.1721 | 34.0563 | Closed | AT Only | AT Only | MineField | 1392/1393 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes | 2014-02-02 | 2014-06-23 | 1392-1393 | HT | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  |  |  | Substantial | 46 | CHA | 5 |  |  | 2009-10-05 | No | Complete
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-008e-1328f6b92f7-b988c51d-116f-a | MF-16008 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0034 | 96416 | 69.1908 | 34.0579 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-073 | Logar Demining Project-08 (AT) | DFATD | Yes | 2014-03-11 | 2014-07-23 | 1393 | HT | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  |  |  | Substantial | 53 | CHA | 4 |  |  | 2011-04-27 16:30 | No | Planned
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-008e-1328f748764-471d5f51-123e-b | MF-16011 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0036 | 102694 | 69.1956 | 34.0519 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-073 | Logar Demining Project-08 (AT) | DFATD | Yes | 2014-03-08 | 2014-07-23 | 1393 | HT | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  |  |  | Substantial | 106 | CHA | 4 |  |  | 2011-05-01 16:30 | No | Planned
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-008e-1328f810639-a6b4398d-1373-9 | MF-16002 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0030 | 78375 | 69.1721 | 34.0563 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-114/A | Logar Demining Project-19 (AT)/A | DOS | Yes | 2014-03-09 | 2014-09-23 | 1393 | HT | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  | Low | Agriculture Blocked | Substantial | 46 | CHA | 5 |  |  | 2011-03-31 16:30 | No | Planned
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-008e-13290b6596e-eece1bc7-540-be | MF-16004 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0032 | 78000 | 69.1809 | 34.0523 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-114/A | Logar Demining Project-19 (AT)/A | DOS | Yes | 2014-05-11 | 2014-08-23 | 1393 | HT | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  | Low | Agriculture Blocked | Substantial | 98 | CHA | 5 |  |  | 2011-04-13 16:30 | No | Planned
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-008e-13290b823b7-31986aad-566-10 | MF-16005 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0031 | 74025 | 69.1809 | 34.0523 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-114/A | Logar Demining Project-19 (AT)/A | DOS | Yes | 2014-03-09 | 2014-06-23 | 1393 | HT | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  |  |  | Substantial | 46 | CHA | 5 |  |  | 2011-04-10 16:30 | No | Planned
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-008e-13290c4adbc-14dd5801-648-41 | MF-16007 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0033 | 96230 | 69.1899 | 34.0518 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-073 | Logar Demining Project-08 (AT) | DFATD | Yes | 2014-03-10 | 2014-08-23 | 1393 | HT | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  | Low | Agriculture Blocked | Substantial | 53 | CHA | 4 |  |  | 2011-04-14 16:30 | No | Planned
Central | Logar | Khoshi | Kariz-I-Fatehkhel | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} | c0a8-00f6-13551e6a649-88029c24-382-a0 | MF-16676 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0049 | 56897 | 69.1907 | 34.0588 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-073 | Logar Demining Project-08 (AT) | DFATD | Yes | 2014-03-30 | 2014-08-23 | 1393 | HT | {7E28C670-99E4-443F-A921-2E8A1A3F8CEE} |  | Low | Agriculture Blocked | Substantial | 53 | CHA | 5 |  |  | 2011-12-25 16:30 | No | Planned
Central | Logar | Khoshi | Kariz-I-Sultan Khel | {FF95B147-68B6-46F5-AFEB-7F27089D891B} | c0a8-0009-13f09a9b281-6b4019de-1e11-7 | Hz-ID-17932 | MCPA - Mine Clearance Planning Agency | AF/0504/00810/MF0057 | 41731 | 69.2225 | 34.0299 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes | 2014-01-01 | 2014-03-23 | 1392-1393 | HT | {FF95B147-68B6-46F5-AFEB-7F27089D891B} |  |  |  | Substantial | 126 | CHA | 4 |  |  | 2013-04-22 16:30 | No | Complete
Central | Logar | Khoshi | Kariz-I-Sultan Khel | {FF95B147-68B6-46F5-AFEB-7F27089D891B} | c0a8-0009-145d65180c8-2f9d6a0b-3dc7-8 | Hz-ID-18650 | MCPA - Mine Clearance Planning Agency | AF/0504/00810/MF0074 | 81946 | 69.2216 | 34.032 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {FF95B147-68B6-46F5-AFEB-7F27089D891B} |  | Low | Agriculture Blocked | Substantial | 28 | CHA | 5 |  |  | 2014-03-06 16:30 | No | Open
Central | Logar | Khoshi | Kariz-I-Sultan Khel | {FF95B147-68B6-46F5-AFEB-7F27089D891B} | c0a8-0057-12c3b95214b-655d82e0-27f4d- | MF-HQ-13631 | MCPA - Mine Clearance Planning Agency | AF/0504/00624/MF0024 | 2090 | 69.2484 | 34.0269 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes | 2014-01-01 | 2014-03-23 | 1392-1393 | HT | {FF95B147-68B6-46F5-AFEB-7F27089D891B} |  |  |  | Substantial | 285 | CHA | 3 |  |  | 2009-11-05 | No | Complete
Central | Logar | Khoshi | Kariz-I-Sultan Khel | {FF95B147-68B6-46F5-AFEB-7F27089D891B} | c0a8-008e-1328f6c4810-adbc795c-118a-3 | MF-16012 | MCPA - Mine Clearance Planning Agency | AF/0504/00383/MF0037 | 93766 | 69.1721 | 34.059 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-114/A | Logar Demining Project-19 (AT)/A | DOS | Yes | 2014-03-02 | 2014-06-02 | 1393 | HT | {FF95B147-68B6-46F5-AFEB-7F27089D891B} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2011-03-24 16:30 | No | Planned
Central | Logar | Khoshi | Khoshi | {E64105A1-EA3A-4CEE-B60B-B2C01283E685} | c0a8-0057-12c3b8122dc-20fa61eb-1a3c4- | MF-HQ-13619 | MCPA - Mine Clearance Planning Agency | AF/0504/03713/MF0028 | 2753 | 69.2226 | 34.0053 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/D | Logar Demining Project-08 (AT)/D | B-Germany | Yes | 2013-03-12 | 2013-10-18 | 1392 | HT | {E64105A1-EA3A-4CEE-B60B-B2C01283E685} |  |  |  | Substantial | 214 | CHA | 1 | Yes |  | 2009-11-05 | No | Complete
Central | Logar | Khoshi | Qarya-I-Dubandi | {6C74B397-BF4B-43B5-9A14-C08BB1990CCD} | c0a8-0057-12c3ba9fd87-8cb1a7e1-34f14- | MF-HQ-1948 | MCPA - Mine Clearance Planning Agency | AF/0502/004/MF0005 | 14000 | 69.2998 | 33.9554 | Open | AP Only | AP Only | MineField |  | MBT Project-178 | Logar Demining Project-02 |  |  |  |  | 1395 |  | {6C74B397-BF4B-43B5-9A14-C08BB1990CCD} |  | Medium | Critical Infrastracture | Substantial | 456 | CHA | 3 |  |  | 1995-09-03 | No | Open
Central | Logar | Khoshi | Sultankhel | {5BDB4038-9D5E-4D19-855A-D19E457CB81D} | c0a8-0057-12c3bb52c48-6b81366c-3b974- | MF-HQ-11499 | MCPA - Mine Clearance Planning Agency | AF/0504/03716/MF0010 | 52798 | 69.2291 | 34.0326 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes | 2014-01-01 | 2014-03-23 | 1392-1393 | HT | {5BDB4038-9D5E-4D19-855A-D19E457CB81D} |  |  |  | Substantial | 126 | CHA | 4 |  |  | 2009-07-28 | No | Complete
Central | Logar | Khoshi | Tangay | {01122E16-192B-45AA-AC06-5B7B9B797FD5} | c0a8-0009-14401a6dc7a-7bf6c238-2ac-39 | Hz-ID-18435 | MCPA - Mine Clearance Planning Agency | AF/0504/03687/MF0056 | 5663 | 69.2487 | 33.9453 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {01122E16-192B-45AA-AC06-5B7B9B797FD5} |  | Low | Agriculture Blocked | Substantial | 96 | CHA | 5 |  |  | 2013-12-19 16:30 | No | Open
Central | Logar | Khoshi | Tangay | {01122E16-192B-45AA-AC06-5B7B9B797FD5} | c0a8-0009-14401b09454-d304fbc8-3ef-a8 | Hz-ID-18437 | MCPA - Mine Clearance Planning Agency | AF/0504/03687/MF0060 | 29768 | 69.2605 | 33.9494 | Open | AT Only | AT Only | MineField |  | MBT Project-198 | Logar Demining Project-18 (AT) |  |  |  |  | 1399 |  | {01122E16-192B-45AA-AC06-5B7B9B797FD5} |  | Low | Agriculture Blocked | Substantial | 122 | CHA | 4 |  |  | 2013-12-18 16:30 | No | Open
Central | Logar | Khoshi | Zinak (1) | {1F29D55A-1703-474F-9622-F19542693C63} | c0a8-0009-144909399ee-df7cb5ad-423-d1 | Hz-ID-18504 | MCPA - Mine Clearance Planning Agency | AF/0504/03699/MF0066 | 49191 | 69.3735 | 33.9292 | Open | AT Only | AT Only | MineField |  | MBT Project-146 | Logar Demining Project-05 (AT) |  |  |  |  | 1400 |  | {1F29D55A-1703-474F-9622-F19542693C63} |  | Low | Critical Infrastracture | Substantial | 96 | CHA | 5 |  |  | 2014-01-19 16:30 | No | Open
Central | Logar | Mohammad Agha | Abparan | {A3EE2D83-5F26-47EA-8B44-E10050240681} | c0a8-00f6-137da667888-763656dc-2001-2 | Hz-ID-17034 | MDC - Mine Detection and Dog Center | AF/0505/03863/MF0657 | 220580 | 69.2758 | 34.195 | Worked on | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes | 2013-06-07 | 2014-04-30 | 1392 | MDC | {A3EE2D83-5F26-47EA-8B44-E10050240681} |  | High with Victim | High with Victims | Substantial | 10 | CHA | 2 |  |  | 2012-06-03 16:30 | No | Planned
Central | Logar | Mohammad Agha | Abparan | {A3EE2D83-5F26-47EA-8B44-E10050240681} | c0a8-00f6-137da69e078-9e32b5-2065-b50 | Hz-ID-17037 | MDC - Mine Detection and Dog Center | AF/0505/03863/MF0656 | 326631 | 69.2753 | 34.1978 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes | 2013-07-07 | 2013-12-31 | 1392 | MDC | {A3EE2D83-5F26-47EA-8B44-E10050240681} |  |  |  | Substantial | 7 | SHA | 2 |  |  | 2012-06-03 16:30 | No | Planned
Central | Logar | Mohammad Agha | Aynak | {527E4A8C-E2E6-45C5-9D08-EE81E4D34C54} | c0a8-0009-13b830e31d3-8c556e4-77-b604 | Hz-ID-17465 | MDC - Mine Detection and Dog Center | AF/0505/03922/MF0669 | 21495 | 69.296 | 34.281 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes |  |  | 1392 | MDC | {527E4A8C-E2E6-45C5-9D08-EE81E4D34C54} |  |  |  | Substantial | 34 | CHA | 2 |  |  | 2012-11-15 16:30 | No | Planned
Central | Logar | Mohammad Agha | Baghe Sultan | {A8AAE142-C9CD-4FC1-9AB8-1878929C3748} | c0a8-0009-142414f51ec-76e818cd-38cb-f | Hz-ID-18210 | MCPA - Mine Clearance Planning Agency | AF/0505/03821/MF0074 | 784 | 69.0753 | 34.1642 | Open | AP Only | AP Only | MineField |  | MBT Project-113 | Logar Demining Project-14 (AT) |  |  |  |  | 1395 |  | {A8AAE142-C9CD-4FC1-9AB8-1878929C3748} |  | High | Critical Infrastracture | Substantial | 1332 | CHA | 3 |  |  | 2013-09-02 16:30 | No | Open
Central | Logar | Mohammad Agha | Bawokhel | {8508F8D5-844E-423D-B876-385FBFFDF006} | c0a8-00f6-137da6b5ddf-98684a07-20bf-5 | Hz-ID-17038 | MDC - Mine Detection and Dog Center | AF/0505/03919/MF0655 | 398137 | 69.2923 | 34.2141 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes | 2013-07-06 | 2013-10-31 | 1392 | MDC | {8508F8D5-844E-423D-B876-385FBFFDF006} |  |  |  | Substantial | 116 | SHA | 4 |  |  | 2012-06-03 16:30 | No | Planned
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0009-14385021e60-8aa3bc2e-41a5-d | Hz-ID-18372 | MDC - Mine Detection and Dog Center | AF/0504/03831/MF0691 | 196555 | 69.2141 | 34.1112 | Open | AT Only | AT Only | MineField |  | MBT Project-113 | Logar Demining Project-14 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 37 | CHA | 5 |  |  | 2013-12-22 16:30 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b8c323b-dfbb7aa5-22060- | MF-HQ-14125 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0504/03831/MF0583 | 6018000 | 69.2232 | 34.0969 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-113 | Logar Demining Project-14 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Comunity Centers | Substantial | 1879 | SHA | 4 |  |  | 2010-02-01 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b930868-7b9da942-268fe- | MF-HQ-12991 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0517 | 464500 | 69.2589 | 34.1159 | Open | AT Only | AT Only | MineField |  | MBT Project-075 | Logar Demining Project-10 (AT) | DOS |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 189 | CHA | 4 |  |  | 2009-08-29 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b930a3c-c62b0d1-2690f-c | MF-HQ-12997 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0523 | 459371 | 69.2298 | 34.1104 | Open | AT Only | AT Only | MineField |  | MBT Project-076 | Logar Demining Project-11 (AT) |  | No |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 124 | CHA | 4 |  |  | 2009-08-30 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b930c3e-65c6f8a4-26921- | MF-HQ-12993 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0519 | 499500 | 69.2467 | 34.111 | Open | AT Only | AT Only | MineField |  | MBT Project-075 | Logar Demining Project-10 (AT) | DOS |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 207 | CHA | 4 |  |  | 2009-09-01 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b930e70-8c3108e3-26935- | MF-HQ-13011 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0524 | 451071 | 69.2298 | 34.1104 | Open | AT Only | AT Only | MineField |  | MBT Project-076 | Logar Demining Project-11 (AT) |  | No |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 139 | CHA | 4 |  |  | 2009-09-01 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b931073-2caf57fa-26949- | MF-HQ-12994 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0520 | 452000 | 69.2467 | 34.111 | Open | AT Only | AT Only | MineField |  | MBT Project-293 | Logar Demining Project-20 (AT) |  |  |  |  | 1401 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 178 | CHA | 5 |  |  | 2009-09-03 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b931256-ee5ca8f-2695d-e | MF-HQ-12995 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0521 | 468000 | 69.2467 | 34.111 | Open | AT Only | AT Only | MineField |  | MBT Project-076 | Logar Demining Project-11 (AT) |  | No |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 124 | CHA | 4 |  |  | 2009-09-05 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b93143a-3023cfc0-2696f- | MF-HQ-13250 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0550 | 367000 | 69.181 | 34.1214 | Open | AT Only | AT Only | MineField |  | MBT Project-147 | Logar Demining Project-13 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 213 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b9315fe-4af98423-26981- | MF-HQ-13256 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0535 | 482490 | 69.1994 | 34.105 | Open | AT Only | AT Only | MineField |  | MBT Project-294 | Logar Demining Project-22 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 79 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b931801-91dda550-26992- | MF-HQ-12996 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0522 | 465883 | 69.2298 | 34.1104 | Open | AT Only | AT Only | MineField |  | MBT Project-293 | Logar Demining Project-20 (AT) |  |  |  |  | 1401 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 178 | CHA | 5 |  |  | 2009-08-28 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b931b0c-32158bcc-269a5- | MF-HQ-13248 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0552 | 398254 | 69.1759 | 34.1218 | Open | AT Only | AT Only | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Medium | Critical Infrastracture | Substantial | 166 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b931d0f-e809df4c-269c1- | MF-HQ-13000 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0533 | 515000 | 69.2055 | 34.1042 | Open | AT Only | AT Only | MineField |  | MBT Project-279 | Logar Demining Project-21 (AT) |  |  |  |  | 1401 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 30 | CHA | 5 |  |  | 2009-09-10 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b931ee3-be35dca3-269d3- | MF-HQ-12999 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0532 | 489000 | 69.2055 | 34.1042 | Open | AT Only | AT Only | MineField |  | MBT Project-279 | Logar Demining Project-21 (AT) |  |  |  |  | 1401 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2009-09-08 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b9320d6-18dea93f-269e4- | MF-HQ-13255 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0536 | 651000 | 69.1994 | 34.105 | Open | AT Only | AT Only | MineField |  | MBT Project-147 | Logar Demining Project-13 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 93 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b9322aa-456b7ed2-269f6- | MF-HQ-12992 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0518 | 481000 | 69.2589 | 34.1159 | Open | AT Only | AT Only | MineField |  | MBT Project-075 | Logar Demining Project-10 (AT) | DOS |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 123 | CHA | 4 |  |  | 2009-08-30 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b9324bc-65a01c45-26a08- | MF-HQ-13013 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0526 | 484043 | 69.2148 | 34.1072 | Open | AT Only | AT Only | MineField |  | MBT Project-077 | Logar Demining Project-12 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 215 | CHA | 4 |  |  | 2009-09-05 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b932671-d5f2054-26a1c-c | MF-HQ-13015 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0527 | 424386 | 69.2148 | 34.1072 | Open | AT Only | AT Only | MineField |  | MBT Project-077 | Logar Demining Project-12 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 77 | CHA | 4 |  |  | 2009-09-06 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b932855-4186bc10-26a2d- | MF-HQ-13254 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0537 | 463000 | 69.1926 | 34.1055 | Open | AT Only | AT Only | MineField |  | MBT Project-294 | Logar Demining Project-22 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 17 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b932ad4-69437848-26a3f- | MF-HQ-13252 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0548 | 450000 | 69.1889 | 34.1306 | Open | AT Only | AT Only | MineField |  | MBT Project-147 | Logar Demining Project-13 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 93 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b932d15-e9bd491c-26a57- | MF-HQ-13242 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0554 | 207008 | 69.1812 | 34.1214 | Open | AP Only | AP Only | MineField |  | MBT Project-075 | Logar Demining Project-10 (AT) | DOS |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 213 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b93305f-be0ac585-26a6c- | MF-HQ-13246 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0553 | 384143 | 69.1629 | 34.1143 | Open | AP Only | AP Only | MineField |  | MBT Project-077 | Logar Demining Project-12 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Medium | Critical Infrastracture | Substantial | 31 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b933233-30b170d7-26a8a- | MF-HQ-13251 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0549 | 513360 | 69.1864 | 34.1062 | Open | AT Only | AT Only | MineField |  | MBT Project-294 | Logar Demining Project-22 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 32 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b933494-50def605-26a9b- | MF-HQ-13017 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03831/MF0528 | 535721 | 69.2148 | 34.1072 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-066 | Logar Demining Project-03 | CIDA | Yes | 2013-10-30 | 2013-12-31 | 1392 | MDC | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  |  |  | Substantial | 140 | CHA | 4 |  |  | 2009-09-07 | No | Complete
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b933696-a45dff83-26aae- | MF-HQ-12998 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0531 | 477000 | 69.2055 | 34.1042 | Open | AT Only | AT Only | MineField |  | MBT Project-279 | Logar Demining Project-21 (AT) |  |  |  |  | 1401 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2009-09-06 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b9338a9-4c7d88ad-26ac1- | MF-HQ-13249 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0551 | 411000 | 69.1799 | 34.1084 | Open | AP Only | AP Only | MineField |  | MBT Project-292 | Logar Demining Project-07 |  |  |  |  | 1396 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 30 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b933a7c-9aab0e02-26ad3- | MF-HQ-13018 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0529 | 538045 | 69.2148 | 34.1072 | Open | AT Only | AT Only | MineField |  | MBT Project-279 | Logar Demining Project-21 (AT) |  |  |  |  | 1401 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 56 | CHA | 5 |  |  | 2009-09-14 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b933c70-67a2378e-26ae4- | MF-HQ-12850 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0530 | 557812 | 69.2148 | 34.1072 | Open | AT Only | AT Only | MineField |  | MBT Project-293 | Logar Demining Project-20 (AT) |  |  |  |  | 1401 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 41 | CHA | 5 |  |  | 2009-09-15 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b933e63-3481ef66-26af5- | MF-HQ-13012 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0525 | 458614 | 69.2298 | 34.1104 | Open | AT Only | AT Only | MineField |  | MBT Project-077 | Logar Demining Project-12 (AT) |  |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 139 | CHA | 4 |  |  | 2009-09-03 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b934056-f3218507-26b07- | MF-HQ-12849 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0534 | 452952 | 69.1994 | 34.105 | Open | AT Only | AT Only | MineField |  | MBT Project-293 | Logar Demining Project-20 (AT) |  |  |  |  | 1401 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 18 | CHA | 5 |  |  | 2009-09-16 | No | Open
Central | Logar | Mohammad Agha | Burg | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} | c0a8-0057-12c3b934239-bf46e9c-26b19-2 | MF-HQ-13253 | MCPA - Mine Clearance Planning Agency | AF/0505/03831/MF0547 | 483150 | 69.1926 | 34.1055 | Open | AP Only | AP Only | MineField |  | MBT Project-075 | Logar Demining Project-10 (AT) | DOS |  |  |  | 1395 |  | {F8A877B1-48F5-4B50-8845-DD32D3CC9BC7} |  | Low | Agriculture Blocked | Substantial | 79 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Chinaray | {A47F018E-2752-4728-82F0-A9116081B8F1} | c0a8-00f6-13a6333e6cc-4921c6f0-465-4c | Hz-ID-17296 | MDC - Mine Detection and Dog Center | AF/0505/03886/BF0663 | 210423 | 69.2965 | 34.2913 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes | 2013-03-27 | 2013-05-12 | 1392 | MDC | {A47F018E-2752-4728-82F0-A9116081B8F1} |  |  |  | Substantial | 128 | CHA | 3 |  |  | 2012-07-25 16:30 | No | Planned
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-0057-12c3b688564-710f8080-8212-6 | MF-HQ-13315 | MCPA - Mine Clearance Planning Agency | AF/0505/03826/MF0468 | 17550 | 69.3315 | 34.1688 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Other | Substantial | 42 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-0057-12c3b6de4e4-e1ce3792-c27c-e | MF-HQ-13313 | MCPA - Mine Clearance Planning Agency | AF/0505/03826/MF0466 | 34012 | 69.3421 | 34.1733 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Agriculture Blocked | Substantial | 45 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-0057-12c3b6e5d2d-5e11b907-c82d-1 | MF-HQ-13314 | MCPA - Mine Clearance Planning Agency | AF/0505/03826/MF0467 | 69459 | 69.3421 | 34.1733 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Agriculture Blocked | Substantial | 81 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-0057-12c3b6fe1e2-2a327fbc-dab4-2 | MF-HQ-13311 | MCPA - Mine Clearance Planning Agency | AF/0505/03826/MF0461 | 69518 | 69.3302 | 34.1701 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Agriculture Blocked | Substantial | 74 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-0057-12c3b7631d6-f56a02b3-12671- | MF-HQ-13316 | MCPA - Mine Clearance Planning Agency | AF/0505/03826/MF0470 | 5600 | 69.336 | 34.1794 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Other | Substantial | 46 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-0057-12c3b792003-1ff03d8-148bf-5 | MF-HQ-13312 | MCPA - Mine Clearance Planning Agency | AF/0505/03826/MF0462 | 64893 | 69.3315 | 34.1688 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Agriculture Blocked | Substantial | 74 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-0057-12c3bae509b-dcd69e46-37815- | MF-HQ-13309 | MCPA - Mine Clearance Planning Agency | AF/0505/03826/MF0464 | 82052 | 69.3339 | 34.1753 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Agriculture Blocked | Substantial | 57 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-0057-12c3bae52cc-935f1bbc-37826- | MF-HQ-13308 | MCPA - Mine Clearance Planning Agency | AF/0505/03826/MF0463 | 73154 | 69.3339 | 34.1753 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Agriculture Blocked | Substantial | 74 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-0057-12c3bae558a-11a0c209-37838- | MF-HQ-13310 | MCPA - Mine Clearance Planning Agency | AF/0505/03826/MF0465 | 84963 | 69.3421 | 34.1733 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Agriculture Blocked | Substantial | 57 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-0057-12c3bae579d-ce31e70e-3784d- | MF-HQ-13307 | MCPA - Mine Clearance Planning Agency | AF/0505/03826/MF0353 | 73112 | 69.3297 | 34.1753 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Agriculture Blocked | Substantial | 55 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-00f6-13a4f21e6a0-26320ca1-8d59-a | Hz-ID-17292 | MDC - Mine Detection and Dog Center | AF/0505/03826/MF0666 | 1618029 | 69.2994 | 34.2089 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-015/A | Logar Demining Project-06/A | B-Govt Afghanistan | Yes | 2014-06-01 | 2014-11-30 | 1393 | MDC | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Agriculture Blocked | Substantial | 85 | SHA | 4 |  |  | 2012-09-11 16:30 | No | Planned
Central | Logar | Mohammad Agha | Chino Sar | {55835005-C661-41BD-9351-C8A4E4223AAA} | c0a8-00f6-13a630f3a85-7897ccbe-443-24 | Hz-ID-17295 | MDC - Mine Detection and Dog Center | AF/0505/03826/MF0664 | 1298675 | 69.3102 | 34.2089 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-015/A | Logar Demining Project-06/A | B-Govt Afghanistan | Yes | 2014-06-01 | 2014-11-30 | 1393 | MDC | {55835005-C661-41BD-9351-C8A4E4223AAA} |  | Low | Agriculture Blocked | Substantial | 227 | SHA | 4 |  |  | 2012-09-11 16:30 | No | Planned
Central | Logar | Mohammad Agha | Dag Kala | {E20A4B23-4585-4A51-990D-3A985FD2D595} | c0a8-0009-14636efcf4b-e7a99288-a16-ce | Hz-ID-18703 | HT - HALO TRUST | H/8541 | 840 | 69.0757 | 34.2854 | Open | Mixed | Mixed AT UXO | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {E20A4B23-4585-4A51-990D-3A985FD2D595} |  | High | Water Blocked | Substantial | 151 | CHA | 3 |  |  | 2014-05-05 16:30 | No | Planned
Central | Logar | Mohammad Agha | Dara | {B95D8AD1-4696-497E-94FF-7106AF0110B9} | c0a8-0057-12c3ba21c32-dcd5e9d7-3039b- | BF-HQ-13138 | MCPA - Mine Clearance Planning Agency | AF/0505/03858/BF0327 | 228998 | 69.291 | 34.1377 | Open | UXO Only | UXO Only | BF |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {B95D8AD1-4696-497E-94FF-7106AF0110B9} |  | Medium | Critical Infrastracture | Substantial | 101 | CHA | 3 |  |  | 2009-05-07 | No | Open
Central | Logar | Mohammad Agha | Dashtak(Loy Kalay) | {EF9523AE-4130-43B6-9A33-9896C596F3BE} | c0a8-0009-14384e62ae9-148b0dbc-3f80-c | Hz-ID-18365 | MCPA - Mine Clearance Planning Agency | AF/0505/03869/MF0685 | 36817 | 69.3056 | 34.3221 | Open | AP Only | AP Only | MineField |  | MBT Project-292 | Logar Demining Project-07 |  |  |  |  | 1396 |  | {EF9523AE-4130-43B6-9A33-9896C596F3BE} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2013-11-12 16:30 | No | Open
Central | Logar | Mohammad Agha | Dashtak(Loy Kalay) | {EF9523AE-4130-43B6-9A33-9896C596F3BE} | c0a8-0009-14384fb1501-85f0e11c-40fa-9 | Hz-ID-18367 | MCPA - Mine Clearance Planning Agency | AF/0505/03869/MF0686 | 32314 | 69.3037 | 34.3236 | Open | AP Only | AP Only | MineField |  | MBT Project-292 | Logar Demining Project-07 |  |  |  |  | 1396 |  | {EF9523AE-4130-43B6-9A33-9896C596F3BE} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2013-11-14 16:30 | No | Open
Central | Logar | Mohammad Agha | Dashtak(Loy Kalay) | {EF9523AE-4130-43B6-9A33-9896C596F3BE} | c0a8-0009-14384fdb67c-80e278ae-4157-d | Hz-ID-18370 | MCPA - Mine Clearance Planning Agency | AF/0505/03869/MF0687 | 38218 | 69.1926 | 34.2976 | Open | AP Only | AP Only | MineField |  | MBT Project-292 | Logar Demining Project-07 |  |  |  |  | 1396 |  | {EF9523AE-4130-43B6-9A33-9896C596F3BE} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2013-11-18 16:30 | No | Open
Central | Logar | Mohammad Agha | Dashtak(Loy Kalay) | {EF9523AE-4130-43B6-9A33-9896C596F3BE} | c0a8-0009-14400f43332-bdd70bdb-8ddd-5 | Hz-ID-18451 | MCPA - Mine Clearance Planning Agency | AF/0505/03869/MF0688 | 59359 | 69.2964 | 34.3371 | Open | AP Only | AP Only | MineField |  | MBT Project-292 | Logar Demining Project-07 |  |  |  |  | 1396 |  | {EF9523AE-4130-43B6-9A33-9896C596F3BE} |  | Low | Agriculture Blocked | Substantial | 6 | CHA | 5 |  |  | 2013-12-03 16:30 | No | Open
Central | Logar | Mohammad Agha | Dashtak(Loy Kalay) | {EF9523AE-4130-43B6-9A33-9896C596F3BE} | c0a8-0009-14401ac4fca-b6cd6c20-36a-a7 | Hz-ID-18452 | MCPA - Mine Clearance Planning Agency | AF/0505/03869/MF0689 | 95095 | 69.3009 | 34.3133 | Open | AP Only | AP Only | MineField |  | MBT Project-292 | Logar Demining Project-07 |  |  |  |  | 1396 |  | {EF9523AE-4130-43B6-9A33-9896C596F3BE} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2013-12-04 16:30 | No | Open
Central | Logar | Mohammad Agha | Dashtak(Loy Kalay) | {EF9523AE-4130-43B6-9A33-9896C596F3BE} | c0a8-0057-12c3b9518f2-545503bb-27eff- | MF-HQ-13772 | ATC - Afghan Technical Consultants | AF/0505/03869/MF0591 | 194063 | 69.2956 | 34.3355 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-012 | Logar Demining Project-01 | DOS | Yes | 2013-04-16 | 2013-05-07 | 1392 | ATC | {EF9523AE-4130-43B6-9A33-9896C596F3BE} |  |  |  | Substantial | 40 | CHA | 2 |  |  | 2009-12-05 | No | Complete
Central | Logar | Mohammad Agha | Dashtak(Loy Kalay) | {EF9523AE-4130-43B6-9A33-9896C596F3BE} | c0a8-0057-12c3ba2e104-37469f31-30b01- | MF-HQ-13771 | ATC - Afghan Technical Consultants | AF/0505/03869/MF0592 | 200000 | 69.2864 | 34.3096 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-012 | Logar Demining Project-01 | DOS | Yes | 2013-04-16 | 2013-05-07 | 1392 | ATC | {EF9523AE-4130-43B6-9A33-9896C596F3BE} |  |  |  | Substantial | 20 | CHA | 2 |  |  | 2009-12-05 | No | Complete
Central | Logar | Mohammad Agha | Dashtak(Loy Kalay) | {EF9523AE-4130-43B6-9A33-9896C596F3BE} | c0a8-00f6-13a62e95832-e44a6754-3cc-be | Hz-ID-17289 | MDC - Mine Detection and Dog Center | AF/0505/03869/MF0668 | 276342 | 69.1974 | 34.2855 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes | 2013-03-16 | 2013-05-13 | 1392 | MDC | {EF9523AE-4130-43B6-9A33-9896C596F3BE} |  |  |  | Substantial | 45 | CHA | 2 |  |  | 2012-08-17 16:30 | No | Planned
Central | Logar | Mohammad Agha | Dashtak(Loy Kalay) | {EF9523AE-4130-43B6-9A33-9896C596F3BE} | c0a8-00f6-13a62f3f5f2-17190b0a-3eb-d3 | Hz-ID-17290 | MDC - Mine Detection and Dog Center | AF/0505/03869/MF0667 | 662920 | 69.2026 | 34.2878 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes | 2013-06-16 | 2013-10-31 | 1392 | MDC | {EF9523AE-4130-43B6-9A33-9896C596F3BE} |  |  |  | Substantial | 32 | CHA | 2 |  |  | 2012-08-29 16:30 | No | Planned
Central | Logar | Mohammad Agha | Deh-e Manaka | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} | c0a8-0057-12c3b7ee4aa-4aa40f05-18a27- | MF-HQ-13111 | MCPA - Mine Clearance Planning Agency | AF/0505/03835/MF0331 | 62939 | 69.1172 | 34.1206 | Open | AP Only | AP Only | MineField |  | MBT Project-292 | Logar Demining Project-07 |  |  |  |  | 1396 |  | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2009-05-06 | No | Open
Central | Logar | Mohammad Agha | Deh-e Manaka | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} | c0a8-0057-12c3b7ee65e-dea66acc-18a3c- | MF-HQ-13114 | MCPA - Mine Clearance Planning Agency | AF/0505/03835/MF0333 | 39606 | 69.1172 | 34.1206 | Open | AP Only | AP Only | MineField |  | MBT Project-292 | Logar Demining Project-07 |  |  |  |  | 1396 |  | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2009-05-11 | No | Open
Central | Logar | Mohammad Agha | Deh-e Manaka | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} | c0a8-0057-12c3b7ee842-23777586-18a4f- | MF-HQ-13113 | MCPA - Mine Clearance Planning Agency | AF/0505/03835/MF0332 | 65432 | 69.1172 | 34.1206 | Open | AP Only | AP Only | MineField |  | MBT Project-292 | Logar Demining Project-07 |  |  |  |  | 1396 |  | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2009-05-09 | No | Open
Central | Logar | Mohammad Agha | Deh-e Manaka | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} | c0a8-0057-12c3b911eb1-23b75d15-25522- | MF-HQ-13120 | MCPA - Mine Clearance Planning Agency | AF/0505/03835/MF0347 | 74100 | 69.102 | 34.1486 | Open | AP Only | AP Only | MineField |  | MBT Project-292 | Logar Demining Project-07 |  |  |  |  | 1396 |  | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} |  | High Requested | Resettlment/Local Request | Substantial | 131 | CHA | 5 | Yes | Local Requested Confirmed by district authurity and assessde by MCPA. | 2009-05-16 | No | Open
Central | Logar | Mohammad Agha | Deh-e Manaka | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} | c0a8-0057-12c3b912094-ac6e4b5d-25535- | MF-HQ-13117 | MCPA - Mine Clearance Planning Agency | AF/0505/03835/MF0346 | 63182 | 69.1071 | 34.1499 | Open | AP Only | AP Only | MineField |  | MBT Project-075 | Logar Demining Project-10 (AT) | DOS |  |  |  | 1395 |  | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} |  | High Requested | Resettlment/Local Request | Substantial | 55 | CHA | 4 | Yes | Local Requested Confirmed by district authurity and assessde by MCPA. | 2009-05-13 | No | Open
Central | Logar | Mohammad Agha | Deh-e Manaka | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} | c0a8-0057-12c3b912268-1faeed04-25549- | MF-HQ-13121 | MCPA - Mine Clearance Planning Agency | AF/0505/03835/MF0348 | 61320 | 69.1071 | 34.1499 | Open | AP Only | AP Only | MineField |  | MBT Project-075 | Logar Demining Project-10 (AT) | DOS |  |  |  | 1395 |  | {BCB0A7DA-0280-4227-BD9B-1A995921FACA} |  | High Requested | Resettlment/Local Request | Substantial | 0 | CHA | 4 | Yes | Local Requested Confirmed by district authurity and assessde by MCPA. | 2009-05-18 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0009-13c2298dfe9-e561680b-a9-7fd | Hz-ID-17574 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0670 | 28674 | 69.2696 | 34.2137 | Open | AT Only | AT Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2012-12-17 16:30 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba6423e-f2b874bd-32be3- | MF-HQ-13323 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0459 | 70920 | 69.1707 | 34.1343 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 15 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba64653-303fb35e-32c0c- | MF-HQ-13322 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0460 | 69434 | 69.1707 | 34.1343 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 16 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba64894-fdbda025-32c1d- | MF-HQ-13321 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0471 | 163704 | 69.1708 | 34.1343 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 48 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba64a78-7dc491e2-32c32- | MF-HQ-13325 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0457 | 71800 | 69.1791 | 34.1286 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 30 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba64c7a-6fa0ce42-32c44- | MF-HQ-13326 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0456 | 66600 | 69.1694 | 34.1248 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 15 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba64e4e-a4becbd8-32c55- | MF-HQ-13318 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0474 | 214697 | 69.1529 | 34.1231 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | Planned Year Removed | Low | Agriculture Blocked | Substantial | 95 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba65273-634c43fb-32c77- | MF-HQ-13331 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0451 | 58280 | 69.1693 | 34.1205 | Open | AT Only | AT Only | MineField | Blank | MBT Project-295 | Logar Demining Project-23 (AT) |  | No |  |  | 1401 | None | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | Contingency Plan | Low | Agriculture Blocked | Substantial | 62 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba6563a-963148de-32c9d- | MF-CA-871 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0360 | 59400 | 69.1529 | 34.1231 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 32 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba6585c-c473f4a3-32cae- | MF-HQ-13320 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0472 | 174297 | 69.1708 | 34.1343 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 48 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba65a30-c6b71672-32cc0- | MF-HQ-13319 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0473 | 222872 | 69.1529 | 34.1231 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | Planned Year Removed | Low | Agriculture Blocked | Substantial | 95 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba6640f-c5db23d1-32d16- | MF-HQ-13328 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0454 | 65180 | 69.1781 | 34.1247 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 30 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba66844-30723e8a-32d3b- | MF-HQ-13329 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0453 | 67367 | 69.1781 | 34.1247 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 151 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba66bec-1a6badef-32d5c- | MF-HQ-13324 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0458 | 64313 | 69.1791 | 34.1286 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 30 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Dehmena | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} | c0a8-0057-12c3ba66fd2-275f9728-32d80- | MF-HQ-13330 | MCPA - Mine Clearance Planning Agency | AF/0505/03837/MF0452 | 88070 | 69.1781 | 34.1247 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {4F200B1C-7072-4C0A-890B-CC7DE3F08AD1} |  | Low | Agriculture Blocked | Substantial | 151 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Durwo | {A2F5817D-D848-4276-AADB-FBA91E82D262} | c0a8-0057-12c3b7114f0-3de93605-e933-4 | MF-HQ-13133 | MCPA - Mine Clearance Planning Agency | AF/0505/03860/MF0342 | 46500 | 69.2988 | 34.1336 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {A2F5817D-D848-4276-AADB-FBA91E82D262} |  | Low | Comunity Centers | Substantial | 110 | CHA | 5 |  |  | 2009-05-12 | No | Open
Central | Logar | Mohammad Agha | Durwo | {A2F5817D-D848-4276-AADB-FBA91E82D262} | c0a8-0057-12c3b72743b-2700bf99-f9d6-c | MF-HQ-13135 | MCPA - Mine Clearance Planning Agency | AF/0505/03860/MF0343 | 42920 | 69.2931 | 34.1295 | Open | AT Only | AT Only | MineField |  | MBT Project-295 | Logar Demining Project-23 (AT) |  |  |  |  | 1401 |  | {A2F5817D-D848-4276-AADB-FBA91E82D262} |  | Low | Comunity Centers | Substantial | 52 | CHA | 5 |  |  | 2009-05-14 | No | Open
Central | Logar | Mohammad Agha | Durwo | {A2F5817D-D848-4276-AADB-FBA91E82D262} | c0a8-0057-12c3b8c98b9-7e4fecac-224c9- | BF-HQ-13124 | MCPA - Mine Clearance Planning Agency | AF/0505/03860/BF0330 | 45730 | 69.3 | 34.1389 | Open | UXO Only | UXO Only | BF |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {A2F5817D-D848-4276-AADB-FBA91E82D262} |  | Medium | Agriculture Blocked | Substantial | 254 | CHA | 3 |  |  | 2009-05-09 | No | Open
Central | Logar | Mohammad Agha | Durwo | {A2F5817D-D848-4276-AADB-FBA91E82D262} | c0a8-0057-12c3b8c9a8d-233051c5-224dc- | BF-HQ-13128 | MCPA - Mine Clearance Planning Agency | AF/0505/03860/BF0339 | 84760 | 69.3 | 34.1389 | Open | UXO Only | UXO Only | BF |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {A2F5817D-D848-4276-AADB-FBA91E82D262} |  | Medium | Agriculture Blocked | Substantial | 114 | CHA | 3 |  |  | 2009-05-10 | No | Open
Central | Logar | Mohammad Agha | Durwo | {A2F5817D-D848-4276-AADB-FBA91E82D262} | c0a8-0057-12c3bab2bc5-52d78fef-359ff- | BF-HQ-13122 | MCPA - Mine Clearance Planning Agency | AF/0505/03860/BF0329 | 148860 | 69.3 | 34.1389 | Open | UXO Only | UXO Only | BF |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {A2F5817D-D848-4276-AADB-FBA91E82D262} |  | Medium | Agriculture Blocked | Substantial | 330 | CHA | 3 |  |  | 2009-05-06 | No | Open
Central | Logar | Mohammad Agha | Esare Tangi | {5A655E5B-0B0E-4164-921F-650A891FF3DB} | c0a8-0057-12f91913c55-e141a3e8-1d2b-5 | MF-CA-2031 | MCPA - Mine Clearance Planning Agency | AF/0505/03913/MF0306 | 56693 | 69.2861 | 34.2876 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes | 2012-11-03 | 2013-03-31 | 1392 | MDC | {5A655E5B-0B0E-4164-921F-650A891FF3DB} |  |  |  | Substantial | 17 | CHA | 5 |  |  | 2009-02-09 | No | Planned
Central | Logar | Mohammad Agha | Ghal Darrah | {7F40C2B3-0941-4E7E-9302-03B5282DF3B4} | c0a8-0057-12c3ba051f7-65a0d9b2-2f237- | MF-CA-1631 | MCPA - Mine Clearance Planning Agency | AF/0505/03898/MF0224 | 24965 | 69.161 | 34.2229 | Open | AT Only | AT Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {7F40C2B3-0941-4E7E-9302-03B5282DF3B4} |  | Low | Comunity Centers | Substantial | 13 | CHA | 5 |  |  | 2008-07-31 | No | Open
Central | Logar | Mohammad Agha | Gomaran | {5BC21E5B-826A-44CB-A595-97869A670269} | c0a8-0009-13b7e4a8c62-842e49ba-4d1d-1 | Hz-ID-17293 | MDC - Mine Detection and Dog Center | AF/0505/03908/MF0661 | 1160530 | 69.1974 | 34.2855 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes | 2013-04-20 | 2013-10-31 | 1392 | MDC | {5BC21E5B-826A-44CB-A595-97869A670269} |  |  |  | Substantial | 84 | SHA | 3 |  |  | 2012-07-11 16:30 | No | Planned
Central | Logar | Mohammad Agha | Gomaran | {5BC21E5B-826A-44CB-A595-97869A670269} | c0a8-0009-1404d3fe633-632672d3-2be4-5 | Hz-ID-18091 | MDC - Mine Detection and Dog Center | AF/0505/03908/MF0675 | 130212 | 69.1749 | 34.2814 | Open | AP Only | AP Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {5BC21E5B-826A-44CB-A595-97869A670269} |  | Low | Agriculture Blocked | Substantial | 34 | CHA | 5 |  |  | 2013-06-01 16:30 | No | Open
Central | Logar | Mohammad Agha | Gomaran | {5BC21E5B-826A-44CB-A595-97869A670269} | c0a8-00f6-135b9181c9a-32fd2ac8-114c-1 | MF-16700 | MCPA - Mine Clearance Planning Agency | AF/0505/03908/MF0647 | 95400 | 69.1641 | 34.2894 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes | 2013-03-14 | 2013-06-18 | 1392 | MDC | {5BC21E5B-826A-44CB-A595-97869A670269} |  |  |  | Substantial | 120 | CHA | 4 |  |  | 2011-12-11 16:30 | No | Planned
Central | Logar | Mohammad Agha | Gomaran | {5BC21E5B-826A-44CB-A595-97869A670269} | c0a8-00f6-13a63588f1c-3e9ecfc1-5ee-97 | Hz-ID-17288 | MDC - Mine Detection and Dog Center | AF/0505/03908/MF0659 | 1561782 | 69.1586 | 34.2822 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes | 2012-11-07 | 2013-05-09 | 1392 | MDC | {5BC21E5B-826A-44CB-A595-97869A670269} |  |  |  | Substantial | 303 | CHA | 4 |  |  | 2012-07-12 16:30 | No | Planned
Central | Logar | Mohammad Agha | Gulhamid | {F4C93CDC-C7AC-4843-9B3A-8BB1301B362C} | c0a8-0057-12c3b99f021-86fbcd83-2b1db- | MF-HQ-9915 | MCPA - Mine Clearance Planning Agency | AF/0505/03923/MF0326 | 1350 | 69.2916 | 34.2613 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-066 | Logar Demining Project-03 | CIDA | Yes | 2013-12-01 | 2013-12-02 | 1392 | MDC | {F4C93CDC-C7AC-4843-9B3A-8BB1301B362C} |  |  |  | Substantial | 52 | CHA | 3 |  |  | 2009-03-11 | No | Complete
Central | Logar | Mohammad Agha | Hosaynkhel | {216FC16E-EA77-4487-8D4D-559077E861AE} | c0a8-0057-12c3b899631-24f7f9a7-202d1- | MF-HQ-15150 | MCPA - Mine Clearance Planning Agency | AF/0505/03864/MF0624 | 475605 | 69.3406 | 34.2216 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {216FC16E-EA77-4487-8D4D-559077E861AE} | , | Medium | Agriculture Blocked | Substantial | 872 | CHA | 5 |  |  | 2010-09-26 | No | Open
Central | Logar | Mohammad Agha | Hosaynkhel | {216FC16E-EA77-4487-8D4D-559077E861AE} | c0a8-0057-12c3b8998e0-4ac98b09-202fd- | MF-HQ-13773 | MCPA - Mine Clearance Planning Agency | AF/0505/03864/MF0590 | 335957 | 69.3523 | 34.2399 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-075 | Logar Demining Project-10 (AT) | DOS |  |  |  | 1395 |  | {216FC16E-EA77-4487-8D4D-559077E861AE} | , | Low | Agriculture Blocked | Substantial | 36 | CHA | 4 |  |  | 2010-09-30 | No | Open
Central | Logar | Mohammad Agha | Hosaynkhel | {216FC16E-EA77-4487-8D4D-559077E861AE} | c0a8-00f6-13a6305ef18-27ebd84a-424-91 | Hz-ID-17294 | MDC - Mine Detection and Dog Center | AF/0505/03864/MF0665 | 391727 | 69.2994 | 34.2089 | Worked on | AT Only | AT Only | MineField | 1392 | MBT Project-015 | Logar Demining Project-06 | B-Govt Afghanistan | Yes | 2014-11-27 | 2014-05-30 | 1392 | MDC | {216FC16E-EA77-4487-8D4D-559077E861AE} |  | Low | Agriculture Blocked | Substantial | 252 | SHA | 4 |  |  | 2012-09-11 16:30 | No | Planned
Central | Logar | Mohammad Agha | Kariz-e Goli | {84ADEAD4-BE18-47A8-9C79-A7E6F9DBAA78} | c0a8-0057-12c3ba295d3-a0aee019-30816- | MF-HQ-13141 | MCPA - Mine Clearance Planning Agency | AF/0505/03897/MF0354 | 17610 | 69.1879 | 34.2378 | Open | AT Only | AT Only | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {84ADEAD4-BE18-47A8-9C79-A7E6F9DBAA78} |  | High with Victim | High with Victims | Substantial | 105 | CHA | 2 |  |  | 2009-05-16 | No | Open
Central | Logar | Mohammad Agha | Kochano Kalay | {AC3DF1AE-8981-4C91-907F-5835DF19C339} | c0a8-0009-1410663af1b-78bbb634-6e24-c | Hz-ID-18127 | MCPA - Mine Clearance Planning Agency | AF/0505/03883/BF0677 | 1907 | 69.0563 | 34.2731 | Open | UXO Only | UXO Only | BF |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {AC3DF1AE-8981-4C91-907F-5835DF19C339} |  | High | Critical Infrastracture | Substantial | 152 | CHA | 3 |  |  | 2013-07-01 16:30 | No | Open
Central | Logar | Mohammad Agha | Kopak | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} | c0a8-0057-12c3b6fb70c-7fb25cee-d89e-3 | MF-HQ-13280 | MCPA - Mine Clearance Planning Agency | AF/0505/03857/MF0435 | 115403 | 69.2696 | 34.1363 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} |  | Medium | Critical Infrastracture | Substantial | 211 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Kopak | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} | c0a8-0057-12c3b718770-d9a94dd3-eeaf-c | MF-HQ-13222 | MCPA - Mine Clearance Planning Agency | AF/0505/03857/MF0438 | 228520 | 69.2696 | 34.1363 | Open | AT Only | AT Only | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} |  | Medium | Critical Infrastracture | Substantial | 160 | CHA | 3 |  |  | 2009-07-26 | No | Open
Central | Logar | Mohammad Agha | Kopak | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} | c0a8-0057-12c3b74d46e-153b7411-11661- | MF-HQ-13281 | MCPA - Mine Clearance Planning Agency | AF/0505/03857/MF0491 | 98313 | 69.2696 | 34.1363 | Open | AT Only | AT Only | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} |  | Medium | Critical Infrastracture | Substantial | 211 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Kopak | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} | c0a8-0057-12c3b7524ed-76211673-11a19- | MF-HQ-13221 | MCPA - Mine Clearance Planning Agency | AF/0505/03857/MF0437 | 216400 | 69.2696 | 34.1363 | Open | AT Only | AT Only | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} |  | Medium | Critical Infrastracture | Substantial | 371 | CHA | 3 |  |  | 2009-07-28 | No | Open
Central | Logar | Mohammad Agha | Kopak | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} | c0a8-0057-12c3b78762f-be1d5e79-140fe- | MF-HQ-13282 | MCPA - Mine Clearance Planning Agency | AF/0505/03857/MF0490 | 163524 | 69.2696 | 34.1363 | Open | AT Only | AT Only | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} |  | Medium | Critical Infrastracture | Substantial | 121 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Kopak | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} | c0a8-0057-12c3b7a32e4-d0fcb409-15526- | MF-HQ-13220 | MCPA - Mine Clearance Planning Agency | AF/0505/03857/MF0436 | 106700 | 69.2696 | 34.1363 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {C66EC7FC-AB99-48A9-BD22-13DB170B7F91} |  | Medium | Critical Infrastracture | Substantial | 121 | CHA | 3 |  |  | 2009-07-27 | No | Open
Central | Logar | Mohammad Agha | Lande Kalay | {86E613BF-9FD5-449C-8B1A-614279E10950} | c0a8-0009-14636f4da41-551a621f-a40-bb | Hz-ID-18704 | HT - HALO TRUST | H/8542 | 825 | 69.0544 | 34.2911 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {86E613BF-9FD5-449C-8B1A-614279E10950} |  | High | Water Blocked | Substantial | 152 | CHA | 3 |  |  | 2014-05-05 16:30 | No | Planned
Central | Logar | Mohammad Agha | Lashkarikhel | {5667FB47-479F-4204-B7A8-E7E527CFB6F7} | c0a8-0009-141065898db-6aae9786-6d81-1 | Hz-ID-18129 | MCPA - Mine Clearance Planning Agency | AF/0505/03836/BF0683 | 224 | 69.0912 | 34.1559 | Open | UXO Only | UXO Only | BF |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {5667FB47-479F-4204-B7A8-E7E527CFB6F7} |  | High with Victim | High with Victims | Substantial | 153 | CHA | 2 |  |  | 2013-07-27 16:30 | No | Open
Central | Logar | Mohammad Agha | Lashkarikhel | {5667FB47-479F-4204-B7A8-E7E527CFB6F7} | c0a8-0009-141d53dc971-f25cbd75-25d-e3 | Hz-ID-18128 | MCPA - Mine Clearance Planning Agency | AF/0505/03836/BF0682 | 384 | 69.0851 | 34.1503 | Open | UXO Only | UXO Only | BF |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {5667FB47-479F-4204-B7A8-E7E527CFB6F7} |  | High with Victim | High with Victims | Substantial | 15 | CHA | 2 |  |  | 2013-07-25 16:30 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b69758a-3b69384e-8ca0-7 | MF-HQ-13301 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0378 | 83390 | 69.2048 | 34.1298 | Open | AT Only | AT Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 116 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b69acfd-7b127332-8f3b-c | MF-HQ-13273 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0428 | 64240 | 69.216 | 34.1383 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Critical Infrastracture | Substantial | 63 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b6a04cc-17c107cc-936d-f | MF-HQ-13272 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0371 | 68530 | 69.2082 | 34.1378 | Open | AT Only | AT Only | MineField | Blank | MBT Project-296 | Logar Demining Project-24 (AT) |  | No |  |  | 1399 | None | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 258 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b6a82b1-102e4c3d-9946-d | MF-HQ-13296 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0424 | 64120 | 69.2082 | 34.1378 | Open | AT Only | AT Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 125 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b6c25de-db59ca84-ad24-6 | MF-HQ-13276 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0431 | 96000 | 69.2138 | 34.1397 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Critical Infrastracture | Substantial | 125 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b6c4ec1-c7f39e0e-af10-c | MF-HQ-13283 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0427 | 72348 | 69.211 | 34.1401 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Critical Infrastracture | Substantial | 63 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b6cdaf8-6ac4c58c-b5c6-a | MF-HQ-13298 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0422 | 82799 | 69.2041 | 34.1303 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 120 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b6dc1ab-d3b0d0e8-c0c8-d | MF-HQ-13279 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0434 | 170390 | 69.216 | 34.1383 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Critical Infrastracture | Substantial | 151 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b6e1353-966134f9-c4a4-b | MF-HQ-13274 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0429 | 64225 | 69.216 | 34.1383 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Critical Infrastracture | Substantial | 126 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b6ecb0b-2bc75681-cd85-2 | MF-HQ-13275 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0430 | 100490 | 69.2138 | 34.1397 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Critical Infrastracture | Substantial | 125 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b745f6f-196b87f-110ea-2 | MF-HQ-13302 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0376 | 95760 | 69.2048 | 34.1298 | Open | AT Only | AT Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 62 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b746133-d4334c1e-110fb- | MF-HQ-13300 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0379 | 80295 | 69.2041 | 34.1303 | Open | AT Only | AT Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 13 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b74dcc7-154d1b7b-116c2- | MF-HQ-13277 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0432 | 98034 | 69.216 | 34.1383 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Critical Infrastracture | Substantial | 187 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b74e012-bf8171d2-116e7- | MF-HQ-13295 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0425 | 58872 | 69.2082 | 34.1378 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 63 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b74f2c7-1381f61-117c7-f | MF-HQ-13299 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0421 | 80080 | 69.2041 | 34.1303 | Open | AT Only | AT Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 133 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b752348-44922032-11a08- | MF-HQ-13290 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0375 | 92838 | 69.2048 | 34.1298 | Open | AT Only | AT Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 75 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b7694fa-57445e71-12b17- | MF-HQ-13294 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0380 | 93570 | 69.2041 | 34.1303 | Open | AT Only | AT Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 75 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b7a0659-8177152c-1532b- | MF-HQ-13297 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0423 | 64640 | 69.2082 | 34.1378 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 183 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b7a1bdc-1befd2d4-1541c- | MF-HQ-13278 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0433 | 175670 | 69.2138 | 34.1397 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Critical Infrastracture | Substantial | 89 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3b7a7a4f-5ed52af8-15876- | MF-HQ-13284 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0426 | 49086 | 69.2101 | 34.1397 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Critical Infrastracture | Substantial | 183 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3baf6512-f5c27ca9-3827d- | MF-HQ-13285 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0374 | 66761 | 69.2048 | 34.1298 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Water Blocked | Substantial | 75 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3baf687b-4fad1fb2-38293- | MF-CA-905 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0163 | 54966 | 69.2041 | 34.1304 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-013/A | Logar Demining Project-26 (AT) /A | DOS | Yes | 2014-04-12 | 2014-10-12 | 1393 | MCPA | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Agriculture Blocked | Substantial | 13 | CHA | 5 |  |  | 2008-05-12 | No | Planned
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3baf6d1d-50affe0b-382c0- | MF-HQ-13287 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0377 | 87370 | 69.2048 | 34.1298 | Open | AT Only | AT Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 89 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3baf7538-afcd0d52-382ff- | MF-HQ-13289 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0320 | 34550 | 69.1961 | 34.131 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-013/A | Logar Demining Project-26 (AT) /A | DOS | Yes | 2014-04-01 | 2014-09-30 | 1393 | MCPA | {8BDB2639-26C9-4503-8545-75843192A681} |  | Low | Agriculture Blocked | Substantial | 15 | CHA | 4 |  |  | 2009-10-22 | No | Planned
Central | Logar | Mohammad Agha | Mazgin | {8BDB2639-26C9-4503-8545-75843192A681} | c0a8-0057-12c3baf790e-fb47e400-38312- | MF-CA-702 | MCPA - Mine Clearance Planning Agency | AF/0505/03853/MF0153 | 54889 | 69.1959 | 34.131 | Open | Mixed | Mixed AT UXO | MineField | 1393 | MBT Project-013/A | Logar Demining Project-26 (AT) /A | DOS | Yes | 2014-07-01 | 2014-09-30 | 1393 | MCPA | {8BDB2639-26C9-4503-8545-75843192A681} |  | Medium | Agriculture Blocked | Substantial | 28 | CHA | 5 |  |  | 2007-09-01 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-144019b70d4-41e19b9e-152-69 | Hz-ID-18453 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0690 | 110565 | 69.0324 | 34.327 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-075/A | Logar Demining Project-10 (AT) /A | DOS | Yes | 2014-06-21 | 2014-09-30 | 1393 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 53 | CHA | 2 |  |  | 2013-12-23 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-144019d1559-d8c25a32-178-d2 | Hz-ID-18456 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0694 | 182469 | 69.0408 | 34.3263 | Worked on | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-075/A | Logar Demining Project-10 (AT) /A | DOS | Yes | 2014-06-21 | 2014-09-30 | 1393 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 74 | CHA | 2 |  |  | 2013-12-26 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-14401a010c5-c7aa8acd-1ec-7d | Hz-ID-18454 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0692 | 131681 | 69.0324 | 34.327 | Closed | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-075/A | Logar Demining Project-10 (AT) /A | DOS | Yes |  |  | 1393 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 21 | CHA | 2 |  |  | 2013-12-24 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-14401a4dcd0-e244795e-266-52 | Hz-ID-18455 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0693 | 197879 | 69.0408 | 34.3263 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-075/A | Logar Demining Project-10 (AT) /A | DOS | Yes | 2014-06-21 | 2014-09-30 | 1393 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 95 | CHA | 2 |  |  | 2013-12-25 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-14401a92372-5380502a-2ef-6d | Hz-ID-18457 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0695 | 137867 | 69.0448 | 34.3263 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-075/A | Logar Demining Project-10 (AT) /A | DOS | Yes |  |  | 1393 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 27 | CHA | 2 |  |  | 2013-12-28 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-14401b37cca-ce16e81-431-598 | Hz-ID-18458 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0696 | 182672 | 69.0168 | 34.3309 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-075/A | Logar Demining Project-10 (AT) /A | DOS | Yes |  |  | 1393 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 107 | CHA | 2 |  |  | 2013-12-29 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-14401b4cd83-150422b6-44c-64 | Hz-ID-18459 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0697 | 144469 | 69.0168 | 34.3309 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-075/A | Logar Demining Project-10 (AT) /A | DOS | Yes |  |  | 1393 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 80 | CHA | 2 |  |  | 2013-12-30 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-1449623f31f-43a62354-feb-1f | Hz-ID-18533 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/SERW0706 | 141 | 69.0119 | 34.3275 | Open | UXO Only | UXO Only | Spot ERW | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 2 |  |  | 2014-01-19 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-144a642b03d-28e0eb83-23b-a0 | Hz-ID-18511 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0698 | 195085 | 69.0477 | 34.3201 | Closed | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes | 2014-04-01 | 2014-07-20 | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 48 | CHA | 2 |  |  | 2014-01-04 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-144a64a5af0-d986688-27a-5e8 | Hz-ID-18514 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0699 | 144770 | 69.0477 | 34.3201 | Worked on | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes | 2014-06-01 | 2014-09-23 | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 122 | CHA | 2 |  |  | 2014-01-05 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-144a64c4c4d-45b08001-2be-4a | Hz-ID-18515 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0700 | 127118 | 69.0528 | 34.3159 | Closed | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes | 2014-03-30 | 2014-08-23 | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 106 | CHA | 2 |  |  | 2014-01-07 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-144a64ed121-1a55489b-2d5-d3 | Hz-ID-18516 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0701 | 124848 | 69.0528 | 34.3159 | Worked on | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes | 2014-04-01 | 2014-07-22 | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 106 | CHA | 2 |  |  | 2014-01-09 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-144a651fe53-ba959296-30b-5a | Hz-ID-18517 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0702 | 109013 | 69.0099 | 34.3336 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes | 2014-08-01 | 2014-11-23 | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 86 | CHA | 2 |  |  | 2014-01-11 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-144a653d849-72d48574-324-d5 | Hz-ID-18519 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0703 | 131867 | 69.0099 | 34.3336 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 62 | CHA | 2 |  |  | 2014-01-14 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-144a655d642-92d4b511-33c-6f | Hz-ID-18521 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0704 | 236101 | 69.0004 | 34.3329 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 26 | CHA | 2 |  |  | 2014-01-15 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-144a65667d5-b7679ecc-357-6f | Hz-ID-18522 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0705 | 238731 | 69.0004 | 34.3329 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 16 | CHA | 2 |  |  | 2014-01-18 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-1467f280df2-8350bca-1d37-f5 | Hz-ID-18771 | HT - HALO TRUST | H/8543 | 83500 | 69.0567 | 34.315 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 90 | CHA | 2 |  |  | 2014-05-07 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-1467f2f1723-16a5f350-1e26-b | Hz-ID-18774 | HT - HALO TRUST | H/8544 | 114200 | 69.0463 | 34.323 | Open | AP Only | AP Only | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 59 | CHA | 2 |  |  | 2014-05-09 16:30 | No | Open
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-1467f31887a-12b80841-1e4e-a | Hz-ID-18776 | HT - HALO TRUST | H/8545 | 103200 | 69.0463 | 34.323 | Open | AP Only | AP Only | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 59 | CHA | 2 |  |  | 2014-05-10 16:30 | No | Open
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0009-1467f37e72a-dda472ac-1ed8-9 | Hz-ID-18781 | HT - HALO TRUST | H/8548 | 86000 | 69.0463 | 34.3229 | Open | AP Only | AP Only | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 75 | CHA | 2 |  |  | 2014-05-13 16:30 | No | Open
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5e7b8-3356919c-3c00e- | MF-CA-1530 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0260 | 65720 | 69.0213 | 34.3277 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-07-01 | 2013-07-31 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 60 | CHA | 5 | Yes |  | 2008-08-21 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5e99b-29491aeb-3c020- | MF-CA-1505 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0242 | 43175 | 69.0463 | 34.3228 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes |  |  | 1392-1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 45 | CHA | 4 |  |  | 2008-07-20 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5eb60-72fa3fb6-3c031- | MF-CA-1536 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0265 | 70884 | 69.0213 | 34.3277 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes |  |  | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 39 | CHA | 5 | Yes |  | 2008-08-25 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5ed82-84249c7c-3c042- | MF-CA-1514 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0248 | 71457 | 69.0375 | 34.3217 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-114/A | Logar Demining Project-19 (AT)/A | DOS | Yes | 2014-06-01 | 2014-09-05 | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 55 | CHA | 4 |  |  | 2008-07-27 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5ef65-b19e2cad-3c054- | MF-CA-1534 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0263 | 72838 | 69.0213 | 34.3277 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-09-01 | 2013-09-30 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 85 | CHA | 5 | Yes |  | 2008-08-24 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5f178-59c29b0e-3c065- | MF-CA-1502 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0240 | 61439 | 69.0466 | 34.3235 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes | 2014-02-02 | 2014-05-10 | 1392-1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 45 | CHA | 4 |  |  | 2008-07-17 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5f35b-4f9d-3c077-e009 | MF-CA-1533 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0262 | 68902 | 69.0213 | 34.3277 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-08-01 | 2013-08-31 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 14 | CHA | 5 | Yes |  | 2008-08-23 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5f54e-29d8746f-3c089- | MF-CA-1535 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0264 | 69580 | 69.0213 | 34.3277 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-09-01 | 2013-09-30 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 39 | CHA | 5 | Yes |  | 2008-08-24 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5f732-3b16f41f-3c09a- | MF-CA-1511 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0246 | 68756 | 69.0375 | 34.3217 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-04-13 | 2013-04-30 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 55 | CHA | 5 | Yes |  | 2008-07-24 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5f8f6-aef97baf-3c0ab- | MF-CA-1520 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0253 | 65687 | 69.028 | 34.321 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-06-08 | 2013-06-29 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 23 | CHA | 5 | Yes |  | 2008-08-14 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5faea-d3f9dac9-3c0bc- | MF-CA-1517 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0251 | 70008 | 69.0375 | 34.3217 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-07-01 | 2013-07-31 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 9 | CHA | 5 | Yes |  | 2008-08-12 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5fcbd-ae59d085-3c0cd- | MF-CA-1521 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0254 | 64055 | 69.028 | 34.321 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-06-08 | 2013-06-30 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 60 | CHA | 5 | Yes |  | 2008-08-16 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb5fea1-47fe8f52-3c0de- | MF-CA-1504 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0241 | 70051 | 69.0463 | 34.3228 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes | 2014-04-01 | 2014-07-23 | 1392-1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 7 | CHA | 4 |  |  | 2008-07-19 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb600b3-8d9137c0-3c0ef- | MF-CA-1507 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0243 | 69907 | 69.0463 | 34.3228 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-05-27 | 2013-06-06 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 7 | CHA | 5 | Yes |  | 2008-07-21 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb602a7-54634d8d-3c100- | MF-CA-1523 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0255 | 68171 | 69.028 | 34.321 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-06-08 | 2013-06-30 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 14 | CHA | 5 | Yes |  | 2008-08-17 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb6046b-dd864103-3c111- | MF-CA-1510 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0245 | 71435 | 69.0375 | 34.3217 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-05-01 | 2013-05-15 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 16 | CHA | 5 | Yes |  | 2008-07-23 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb6067d-b13faa99-3c122- | MF-CA-1524 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0256 | 70560 | 69.028 | 34.321 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-08-01 | 2013-08-31 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 60 | CHA | 5 | Yes |  | 2008-08-19 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb6089f-12bf6d36-3c133- | MF-CA-1537 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0266 | 80035 | 69.0213 | 34.3277 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes |  |  | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 25 | CHA | 5 | Yes |  | 2008-08-25 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb60a93-7d74dd05-3c145- | MF-CA-1538 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0267 | 77949 | 69.0213 | 34.3277 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes |  |  | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 25 | CHA | 5 | Yes |  | 2008-09-06 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb60c86-37ac27b5-3c156- | MF-CA-1529 | MCPA - Mine Clearance Planning Agency | AF/0505/03885/MF0259 | 32600 | 69.028 | 34.321 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes | 2014-04-14 | 2014-05-18 | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 14 | CHA | 4 |  |  | 2008-08-21 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb60e98-3bea0fec-3c167- | MF-CA-1515 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0249 | 63210 | 69.0375 | 34.3217 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-114/A | Logar Demining Project-19 (AT)/A | DOS | Yes | 2014-09-01 | 2014-09-23 | 1393 | HT | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  | High with Victim | High with Victims | Substantial | 9 | CHA | 4 |  |  | 2008-07-28 | No | Planned
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb6109b-dab05223-3c178- | MF-CA-1519 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0252 | 49162 | 69.0342 | 34.3231 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-04-13 | 2013-04-30 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 69 | CHA | 5 | Yes |  | 2008-08-13 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb612cd-ad973983-3c18a- | MF-CA-1516 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0250 | 39723 | 69.0351 | 34.3232 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-05-01 | 2013-05-15 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 55 | CHA | 5 | Yes |  | 2008-08-11 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb614df-62333aee-3c19b- | MF-CA-1512 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0247 | 70021 | 69.0375 | 34.3217 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-05-01 | 2013-05-15 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 9 | CHA | 5 | Yes |  | 2008-07-26 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb616c2-dc6eff97-3c1ad- | MF-CA-1528 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0258 | 70384 | 69.028 | 34.321 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-09-01 | 2013-09-30 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 60 | CHA | 5 | Yes |  | 2008-08-20 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb618c5-7a135606-3c1be- | MF-CA-1539 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0268 | 73187 | 69.0213 | 34.3277 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes |  |  | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 51 | CHA | 5 | Yes |  | 2008-09-07 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb61ac8-4703defa-3c1cf- | MF-CA-1526 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0257 | 65640 | 69.028 | 34.321 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-08-01 | 2013-08-31 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 14 | CHA | 5 | Yes |  | 2008-08-20 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb61cac-5398b84f-3c1e0- | MF-CA-1508 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0244 | 49020 | 69.0424 | 34.3232 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-04-13 | 2013-05-15 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 55 | CHA | 5 | Yes |  | 2008-07-22 | No | Complete
Central | Logar | Mohammad Agha | Mirajan Kalay | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} | c0a8-0057-12c3bb61ebe-37ae6925-3c1f1- | MF-CA-1531 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0505/03885/MF0261 | 66475 | 69.0213 | 34.3277 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-07-01 | 2013-07-31 | 1392 | OMAR | {3FD43F4C-8C18-4133-AE2F-8DA570217BDA} |  |  |  | Substantial | 14 | CHA | 5 | Yes |  | 2008-08-23 | No | Complete
Central | Logar | Mohammad Agha | Mirzakhel | {1ABE6E2F-51A3-499D-B5BD-E6A123823F61} | c0a8-0009-14549f2ab0a-b0beb79e-714-42 | Hz-ID-18615 | MCPA - Mine Clearance Planning Agency | AF/0505/03813/MF0714 | 1494 | 69.1258 | 34.2125 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-235 | Logar Demining Project-09 |  |  |  |  | 1395 |  | {1ABE6E2F-51A3-499D-B5BD-E6A123823F61} |  | High | Critical Infrastracture | Substantial | 394 | CHA | 3 |  |  | 2014-02-16 16:30 | No | Open
Central | Logar | Mohammad Agha | Mirzakhel | {1ABE6E2F-51A3-499D-B5BD-E6A123823F61} | c0a8-0057-12c3b9d57e9-26562ab0-2d49d- | MF-CA-1642 | MCPA - Mine Clearance Planning Agency | AF/0505/03813/MF0179 | 63346 | 69.1758 | 34.2099 | Open | AP Only | AP Only | MineField |  | MBT Project-235 | Logar Demining Project-09 |  |  |  |  | 1395 |  | {1ABE6E2F-51A3-499D-B5BD-E6A123823F61} |  | Low | Agriculture Blocked | Substantial | 60 | CHA | 5 |  |  | 2008-07-21 | No | Open
Central | Logar | Mohammad Agha | Mirzakhel | {1ABE6E2F-51A3-499D-B5BD-E6A123823F61} | c0a8-0057-12c3b9d5d17-6058dd0c-2d4c9- | MF-CA-1641 | MCPA - Mine Clearance Planning Agency | AF/0505/03813/MF0178 | 53554 | 69.1731 | 34.2082 | Open | AP Only | AP Only | MineField |  | MBT Project-235 | Logar Demining Project-09 |  |  |  |  | 1395 |  | {1ABE6E2F-51A3-499D-B5BD-E6A123823F61} |  | Low | Agriculture Blocked | Substantial | 60 | CHA | 5 |  |  | 2008-07-19 | No | Open
Central | Logar | Mohammad Agha | Mirzakhel | {1ABE6E2F-51A3-499D-B5BD-E6A123823F61} | c0a8-0057-12c3ba7bd33-9cacf58a-33a67- | MF-CA-1616 | MCPA - Mine Clearance Planning Agency | AF/0505/03813/MF0222 | 60027 | 69.1767 | 34.2091 | Open | AP Only | AP Only | MineField |  | MBT Project-235 | Logar Demining Project-09 |  |  |  |  | 1395 |  | {1ABE6E2F-51A3-499D-B5BD-E6A123823F61} |  | Low | Agriculture Blocked | Substantial | 15 | CHA | 5 |  |  | 2008-07-27 | No | Open
Central | Logar | Mohammad Agha | Mola Bahadur | {E819E3A2-2D06-4217-B857-5160AED966CF} | c0a8-0009-1400018e998-89b7a3c0-239e-7 | Hz-ID-18061 | MCPA - Mine Clearance Planning Agency | AF/0505/03818/MF0678 | 10439 | 69.0489 | 34.2411 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {E819E3A2-2D06-4217-B857-5160AED966CF} |  | Low | Other | Substantial | 16 | CHA | 5 |  |  | 2013-07-03 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mola Bahadur | {E819E3A2-2D06-4217-B857-5160AED966CF} | c0a8-0009-141d53ddd4f-1f3ea2c6-275-1b | Hz-ID-18139 | MCPA - Mine Clearance Planning Agency | AF/0505/03818/MF0681 | 7715 | 69.0111 | 34.2212 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {E819E3A2-2D06-4217-B857-5160AED966CF} |  | Low | Other | Substantial | 46 | CHA | 5 |  |  | 2013-07-13 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mola Bahadur | {E819E3A2-2D06-4217-B857-5160AED966CF} | c0a8-0009-141d53dfa02-bd698b98-28e-84 | Hz-ID-18146 | MCPA - Mine Clearance Planning Agency | AF/0505/03818/MF0679 | 47715 | 69.0092 | 34.2433 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {E819E3A2-2D06-4217-B857-5160AED966CF} |  | Low | Other | Substantial | 16 | CHA | 5 |  |  | 2013-07-08 16:30 | No | Planned
Central | Logar | Mohammad Agha | Mola Bahadur | {E819E3A2-2D06-4217-B857-5160AED966CF} | c0a8-0009-1448b9ad56b-43da916e-1d1-6b | Hz-ID-18501 | MCPA - Mine Clearance Planning Agency | AF/0505/03818/BF0710 | 3040 | 69.012 | 34.2189 | Open | UXO Only | UXO Only | BF |  | MBT Project-235 | Logar Demining Project-09 |  |  |  |  | 1395 |  | {E819E3A2-2D06-4217-B857-5160AED966CF} |  | Medium | Small Hazards | Substantial | 0 | CHA | 5 |  |  | 2014-01-25 16:30 | No | Open
Central | Logar | Mohammad Agha | Mola Bahadur | {E819E3A2-2D06-4217-B857-5160AED966CF} | c0a8-0009-14549f5c99f-1bddf071-74c-54 | Hz-ID-18613 | MCPA - Mine Clearance Planning Agency | AF/0505/03818/MF0713 | 12211 | 69.0121 | 34.2371 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-235 | Logar Demining Project-09 |  |  |  |  | 1395 |  | {E819E3A2-2D06-4217-B857-5160AED966CF} |  | Low | Other | Substantial | 45 | CHA | 5 |  |  | 2014-02-04 16:30 | No | Open
Central | Logar | Mohammad Agha | Nyazgul | {76227ED8-AE80-4E36-B78A-B7577ABBCFC0} | c0a8-0057-12c3b977075-d9f114dc-2976a- | MF-HQ-14130 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0504/03896/MF0589 | 177536 | 69.2124 | 34.243 | Open | Mixed | Mixed AP AT UXO | Converted From SHA | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {76227ED8-AE80-4E36-B78A-B7577ABBCFC0} |  | Medium | Agriculture Blocked | Substantial | 115 | SHA | 3 |  |  | 2010-02-01 | No | Planned
Central | Logar | Mohammad Agha | Panamay | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} | c0a8-0009-14496264631-c7926d7e-1001-6 | Hz-ID-18531 | MCPA - Mine Clearance Planning Agency | AF/0505/03867/MF0712 | 179970 | 68.9845 | 34.3301 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2014-01-28 16:30 | No | Planned
Central | Logar | Mohammad Agha | Panamay | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} | c0a8-0009-14496353e54-ac56078e-101b-b | Hz-ID-18528 | MCPA - Mine Clearance Planning Agency | AF/0505/03867/MF0711 | 135780 | 68.9845 | 34.3301 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2014-01-26 16:30 | No | Planned
Central | Logar | Mohammad Agha | Panamay | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} | c0a8-0009-144963fd943-6d5bb3c2-103b-d | Hz-ID-18527 | MCPA - Mine Clearance Planning Agency | AF/0505/03867/MF0709 | 211541 | 68.9738 | 34.3289 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} |  | Low | Agriculture Blocked | Substantial | 17 | CHA | 5 |  |  | 2014-01-23 16:30 | No | Planned
Central | Logar | Mohammad Agha | Panamay | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} | c0a8-0009-1449643d4f0-5881f344-107d-4 | Hz-ID-18525 | MCPA - Mine Clearance Planning Agency | AF/0505/03867/MF0708 | 208760 | 68.9738 | 34.3289 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} |  | Low | Agriculture Blocked | Substantial | 45 | CHA | 5 |  |  | 2014-01-22 16:30 | No | Planned
Central | Logar | Mohammad Agha | Panamay | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} | c0a8-0009-144a657a37b-6862fc6a-371-b0 | Hz-ID-18523 | MCPA - Mine Clearance Planning Agency | AF/0505/03867/MF0707 | 227808 | 68.9738 | 34.3289 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} |  | Low | Agriculture Blocked | Substantial | 28 | CHA | 5 |  |  | 2014-01-20 16:30 | No | Planned
Central | Logar | Mohammad Agha | Panamay | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} | c0a8-0057-12c3b696268-a086c3b1-8bb9-c | MF-HQ-13085 | MCPA - Mine Clearance Planning Agency | AF/0505/03867/MF0341 | 64662 | 68.9668 | 34.3334 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2009-05-14 | No | Planned
Central | Logar | Mohammad Agha | Panamay | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} | c0a8-0057-12c3b70e182-6046e0e9-e6cd-e | MF-HQ-13084 | MCPA - Mine Clearance Planning Agency | AF/0505/03867/MF0340 | 61643 | 68.9668 | 34.3334 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} |  | Low | Agriculture Blocked | Substantial | 12 | CHA | 5 |  |  | 2009-05-13 | No | Planned
Central | Logar | Mohammad Agha | Panamay | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} | c0a8-0057-12c3b7ac6a9-9f91b24d-15bdc- | MF-HQ-13083 | MCPA - Mine Clearance Planning Agency | AF/0505/03867/MF0337 | 75998 | 68.9604 | 34.3325 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2009-05-12 | No | Planned
Central | Logar | Mohammad Agha | Panamay | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} | c0a8-0057-12c3b8cb57c-f907a97c-22607- | MF-HQ-13104 | MCPA - Mine Clearance Planning Agency | AF/0505/03867/MF0336 | 65798 | 68.9604 | 34.3325 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2009-05-11 | No | Planned
Central | Logar | Mohammad Agha | Panamay | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} | c0a8-0057-12c3b8cb7ad-a3d2391f-2261b- | MF-HQ-13107 | MCPA - Mine Clearance Planning Agency | AF/0505/03867/MF0334 | 80097 | 68.9604 | 34.3325 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2009-05-06 | No | Planned
Central | Logar | Mohammad Agha | Panamay | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} | c0a8-0057-12c3b8cb991-99dc7cb4-22631- | MF-HQ-13103 | MCPA - Mine Clearance Planning Agency | AF/0505/03867/MF0335 | 84174 | 68.9604 | 34.3326 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {D9B6F7B5-FCB7-4763-9DA1-315E185848D7} |  | Low | Agriculture Blocked | Substantial | 12 | CHA | 5 |  |  | 2009-05-09 | No | Planned
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3b951f48-4ed5b684-27f3c- | MF-CA-881 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0504/03831/0024 | 5750 | 69.2484 | 34.0265 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Critical Infrastracture | Substantial | 90 | SHA | 3 |  |  | 2009-11-05 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba9294a-83c68271-347b4- | MF-HQ-13068 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0405 | 66718 | 69.2318 | 34.1366 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-014 | Logar Demining Project-27 (AT) |  |  |  |  | 1395 |  | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 167 | CHA | 3 |  |  | 2009-06-18 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba92b5c-59a02ab9-347c6- | MF-HQ-13045 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0392 | 57000 | 69.2415 | 34.1341 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-013 | Logar Demining Project-26 (AT) | DOS | Yes | 2013-04-21 | 2013-11-30 | 1392 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  |  |  | Substantial | 214 | CHA | 3 |  |  | 2009-05-30 | No | Complete
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba92d40-1a970cbc-347d8- | MF-HQ-13065 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0407 | 119990 | 69.2318 | 34.1366 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-014 | Logar Demining Project-27 (AT) |  |  |  |  | 1395 |  | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 43 | CHA | 3 |  |  | 2009-06-21 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba92f43-839d90dd-347ea- | MF-HQ-13051 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0394 | 65300 | 69.2415 | 34.1341 | Open | Mixed | Mixed AT UXO | MineField | Blank | MBT Project-296 | Logar Demining Project-24 (AT) |  | No |  |  | 1399 | None | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 245 | CHA | 3 |  |  | 2009-06-01 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba93107-f233d40d-347fd- | MF-HQ-13059 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0399 | 53500 | 69.2364 | 34.1349 | Worked on | Mixed | Mixed AT UXO | MineField | 1393 | MBT Project-013/A | Logar Demining Project-26 (AT) /A | DOS | Yes | 2014-04-12 | 2014-10-21 | 1393 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 661 | CHA | 3 |  |  | 2009-06-08 | No | Planned
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba9374e-e8b4a040-34840- | MF-HQ-13066 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0406 | 118100 | 69.2318 | 34.1366 | Worked on | Mixed | Mixed AT UXO | MineField | 1393 | MBT Project-013/A | Logar Demining Project-26 (AT) /A | DOS | Yes | 2014-04-12 | 2014-11-30 | 1393 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 43 | CHA | 3 |  |  | 2009-06-20 | No | Planned
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba93922-37807c52-34853- | MF-HQ-13038 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0390 | 70250 | 69.2419 | 34.1342 | Open | Mixed | Mixed AT UXO | MineField | Blank | MBT Project-296 | Logar Demining Project-24 (AT) |  | No |  |  | 1399 | None | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 155 | CHA | 3 |  |  | 2009-05-24 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba93ae6-321d26c8-34865- | MF-HQ-13056 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0397 | 57300 | 69.2364 | 34.1349 | Open | AT Only | AT Only | MineField |  | MBT Project-238 | Logar Demining Project-16 (AT) |  |  |  |  | 1400 |  | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Low | Agriculture Blocked | Substantial | 121 | CHA | 4 |  |  | 2009-06-06 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba93cd9-fcbb7f35-34876- | MF-HQ-13075 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0404 | 67500 | 69.2318 | 34.1366 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-014 | Logar Demining Project-27 (AT) |  |  |  |  | 1395 |  | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 164 | CHA | 3 |  |  | 2009-06-16 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba93edc-4665c903-34888- | MF-HQ-13077 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0410 | 288250 | 69.2294 | 34.1365 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-014 | Logar Demining Project-27 (AT) |  |  |  |  | 1395 |  | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 132 | CHA | 3 |  |  | 2009-06-06 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba940b0-7041d088-3489a- | MF-HQ-13054 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0396 | 71700 | 69.2364 | 34.1349 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-013 | Logar Demining Project-26 (AT) | DOS | Yes | 2013-04-09 | 2013-09-25 | 1392 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  |  |  | Substantial | 121 | CHA | 3 |  |  | 2009-06-04 | No | Complete
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba94468-2b72587d-348be- | MF-HQ-13062 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0400 | 75000 | 69.2364 | 34.1349 | Worked on | Mixed | Mixed AT UXO | MineField | 1393 | MBT Project-013/A | Logar Demining Project-26 (AT) /A | DOS | Yes | 2014-04-12 | 2014-10-21 | 1393 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 121 | CHA | 3 |  |  | 2009-06-09 | No | Planned
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba9465b-11331d70-348d0- | MF-HQ-13029 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0384 | 82130 | 69.2495 | 34.1337 | Open | Mixed | Mixed AT UXO | MineField | 1393 | MBT Project-013/A | Logar Demining Project-26 (AT) /A | DOS | Yes | 2014-04-01 | 2014-09-30 | 1393 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} | Contingency Plan | Medium | Agriculture Blocked | Substantial | 338 | CHA | 3 |  |  | 2009-05-17 | No | Planned
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba9484e-7a71da8d-348e2- | MF-HQ-13036 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0389 | 73300 | 69.2419 | 34.1342 | Open | Mixed | Mixed AT UXO | MineField | 1393 | MBT Project-013/A | Logar Demining Project-26 (AT) /A | DOS | Yes | 2014-04-01 | 2014-07-30 | 1393 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 93 | CHA | 3 |  |  | 2009-05-21 | No | Planned
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba94add-ea5303df-348f4- | MF-HQ-13069 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0402 | 62800 | 69.2364 | 34.1349 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-014 | Logar Demining Project-27 (AT) |  |  |  |  | 1395 |  | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 183 | CHA | 3 |  |  | 2009-06-13 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba94f7f-d9cd9327-3491e- | MF-HQ-13078 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0411 | 238650 | 69.2294 | 34.1365 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-014 | Logar Demining Project-27 (AT) |  |  |  |  | 1395 |  | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 151 | CHA | 3 |  |  | 2009-07-08 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba95163-57a3453f-34931- | MF-HQ-13030 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0385 | 71915 | 69.2415 | 34.1341 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-013 | Logar Demining Project-26 (AT) | DOS | Yes | 2013-04-21 | 2013-11-30 | 1392 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  |  |  | Substantial | 214 | CHA | 3 |  |  | 2009-05-26 | No | Complete
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba95346-d7b8d2a6-34943- | MF-HQ-13057 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0398 | 62200 | 69.2364 | 34.1349 | Open | Mixed | Mixed AT UXO | MineField | Blank | MBT Project-014 | Logar Demining Project-27 (AT) |  | No |  |  | 1395 | Blank | {08E6CDF3-E7FE-457B-AB51-16358588E039} | , | Medium | Agriculture Blocked | Substantial | 183 | CHA | 3 |  |  | 2009-06-06 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba9552a-f4fc59a4-34955- | MF-HQ-13050 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0393 | 57000 | 69.2415 | 34.1341 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-013 | Logar Demining Project-26 (AT) | DOS | Yes | 2013-04-21 | 2013-11-30 | 1392 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  |  |  | Substantial | 121 | CHA | 3 |  |  | 2009-05-31 | No | Complete
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba9570d-bd0af207-34967- | MF-HQ-13033 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0387 | 84100 | 69.2419 | 34.1342 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-013 | Logar Demining Project-26 (AT) | DOS | Yes | 2013-04-21 | 2013-11-30 | 1392 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  |  |  | Substantial | 93 | CHA | 3 |  |  | 2009-05-19 | No | Complete
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba9595e-77ec01bb-34979- | MF-HQ-13031 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0386 | 72340 | 69.2415 | 34.1341 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-013 | Logar Demining Project-26 (AT) | DOS | Yes | 2013-08-25 | 2013-11-20 | 1392 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  |  |  | Substantial | 121 | CHA | 3 |  |  | 2009-09-27 | No | Complete
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba95b51-16655cd2-3498b- | MF-HQ-13064 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0401 | 60000 | 69.2364 | 34.1349 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-014 | Logar Demining Project-27 (AT) |  |  |  |  | 1395 |  | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 121 | CHA | 3 |  |  | 2009-06-11 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba95d35-474cadf9-3499d- | MF-HQ-13043 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0391 | 67550 | 69.2419 | 34.1342 | Open | Mixed | Mixed AT UXO | MineField | Blank | MBT Project-197 | Logar Demining Project-15 (AT) |  | No |  |  | 1398 | None | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 155 | CHA | 3 |  |  | 2009-05-25 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba95f66-15ecc0fc-349af- | MF-HQ-12970 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0409 | 276805 | 69.2294 | 34.1365 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-013 | Logar Demining Project-26 (AT) | DOS | Yes | 2013-04-09 | 2013-11-20 | 1392 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  |  |  | Substantial | 105 | CHA | 3 |  |  | 2009-07-04 | No | Complete
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba96179-a77bbfd1-349c3- | MF-HQ-13052 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0395 | 65460 | 69.2415 | 34.1341 | Open | Mixed | Mixed AT UXO | MineField | Blank | MBT Project-014 | Logar Demining Project-27 (AT) |  | No |  |  | 1395 | Blank | {08E6CDF3-E7FE-457B-AB51-16358588E039} | , | Medium | Agriculture Blocked | Substantial | 183 | CHA | 3 |  |  | 2009-06-02 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba9639b-20005575-349d5- | MF-HQ-12845 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0408 | 143310 | 69.2318 | 34.1366 | Open | Mixed | Mixed AT UXO | MineField | Blank | MBT Project-014 | Logar Demining Project-27 (AT) |  | No |  |  | 1395 | Blank | {08E6CDF3-E7FE-457B-AB51-16358588E039} | , | Medium | Agriculture Blocked | Substantial | 105 | CHA | 3 |  |  | 2009-06-22 | No | Open
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba9658e-e39156cc-349e8- | MF-HQ-13035 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0388 | 69200 | 69.2419 | 34.1342 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-013 | Logar Demining Project-26 (AT) | DOS | Yes | 2013-04-21 | 2013-11-30 | 1392 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  |  |  | Substantial | 93 | CHA | 3 |  |  | 2009-05-20 | No | Complete
Central | Logar | Mohammad Agha | Qaleh-ye Padshah | {08E6CDF3-E7FE-457B-AB51-16358588E039} | c0a8-0057-12c3ba967c0-509341bb-349fa- | MF-HQ-13071 | MCPA - Mine Clearance Planning Agency | AF/0505/03851/MF0403 | 64100 | 69.2318 | 34.1366 | Open | Mixed | Mixed AT UXO | MineField | 1393 | MBT Project-013/A | Logar Demining Project-26 (AT) /A | DOS | Yes |  |  | 1393 | MCPA | {08E6CDF3-E7FE-457B-AB51-16358588E039} |  | Medium | Agriculture Blocked | Substantial | 164 | CHA | 3 |  |  | 2009-06-15 | No | Planned
Central | Logar | Mohammad Agha | Qal'eh-ye Shahi(Qal'eh-ye Wazir) | {1F5DA112-9D34-452F-8AD0-8DADB79E8870} | c0a8-008e-1328f9fca49-feb37c85-1f4b-e | MF-15421 | MCPA - Mine Clearance Planning Agency | AF/0505/03844/MF0628 | 133 | 69.1046 | 34.2069 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-066 | Logar Demining Project-03 | CIDA | Yes | 2013-12-01 | 2013-12-02 | 1392 | MDC | {1F5DA112-9D34-452F-8AD0-8DADB79E8870} |  |  |  | Substantial | 474 | CHA | 3 |  |  | 2010-11-24 16:30 | No | Complete
Central | Logar | Mohammad Agha | Qal'eh-ye Shahi(Qal'eh-ye Wazir) | {1F5DA112-9D34-452F-8AD0-8DADB79E8870} | c0a8-008e-1328fc0f4c0-88f26abc-271a-8 | BF-15004 | MCPA - Mine Clearance Planning Agency | AF/0505/03844/BF0627 | 1572 | 69.105 | 34.2069 | Open | UXO Only | UXO Only | BF |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {1F5DA112-9D34-452F-8AD0-8DADB79E8870} |  | High | Critical Infrastracture | Substantial | 474 | CHA | 3 |  |  | 2010-11-23 16:30 | No | Open
Central | Logar | Mohammad Agha | Safedsang | {F0F0E48E-1952-46D4-8AAB-A3520892E066} | c0a8-0009-13fdc30332c-f3754cec-242d-a | Hz-ID-18037 | MCPA - Mine Clearance Planning Agency | AF/0505/03910/MF0672 | 52866 | 69.1587 | 34.3135 | Open | AP Only | AP Only | MineField |  | MBT Project-294 | Logar Demining Project-22 (AT) |  |  |  |  | 1395 |  | {F0F0E48E-1952-46D4-8AAB-A3520892E066} |  | Low | Agriculture Blocked | Substantial | 253 | CHA | 4 |  |  | 2013-05-01 16:30 | No | Open
Central | Logar | Mohammad Agha | Shahtut | {E59DC2F7-1053-4C34-8D6D-ECC5A82C8268} | c0a8-0057-12c3bb5a28e-27e857db-3bd72- | MF-HQ-13143 | MCPA - Mine Clearance Planning Agency | AF/0505/03859/MF0351 | 55951 | 69.2686 | 34.1383 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {E59DC2F7-1053-4C34-8D6D-ECC5A82C8268} |  | Medium | Critical Infrastracture | Substantial | 90 | CHA | 3 |  |  | 2009-05-27 | No | Open
Central | Logar | Mohammad Agha | Surkhabad | {4A3DFC1D-A7B3-4DDE-9512-35543F0D1173} | c0a8-0009-14227dc9094-40fc6983-47e4-d | Hz-ID-18207 | MCPA - Mine Clearance Planning Agency | AF/0505/03822/BF0684 | 27 | 69.0747 | 34.1796 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {4A3DFC1D-A7B3-4DDE-9512-35543F0D1173} |  | High | Critical Infrastracture | Substantial | 0 | CHA | 3 |  |  | 2013-09-15 16:30 | No | Open
Central | Logar | Mohammad Agha | Tor Wersek | {BB39E132-B7FC-4755-B570-E2EC1A370B75} | c0a8-0057-12c3b70a36a-c6a79721-e3e9-5 | MF-HQ-13094 | MCPA - Mine Clearance Planning Agency | AF/0505/03888/MF0368 | 112234 | 69.058 | 34.3126 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes | 2014-02-02 | 2014-07-10 | 1392-1393 | HT | {BB39E132-B7FC-4755-B570-E2EC1A370B75} |  |  |  | Substantial | 40 | CHA | 5 |  |  | 2009-05-26 | No | Complete
Central | Logar | Mohammad Agha | Waghjan | {00748D57-A1DD-4B44-B083-BE023951478E} | c0a8-004c-13006c9d965-4c30cade-bf0-c6 | MF-CA-398 | MCPA - Mine Clearance Planning Agency | AF/0505/03815/MF0150 | 2450 | 69.0721 | 34.1618 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-066 | Logar Demining Project-03 | CIDA | Yes | 2013-11-20 | 2013-11-30 | 1392 | MDC | {00748D57-A1DD-4B44-B083-BE023951478E} |  |  |  | Substantial | 1332 | CHA | 3 |  |  | 2006-09-01 | No | Complete
Central | Logar | Mohammad Agha | Waghjan | {00748D57-A1DD-4B44-B083-BE023951478E} | c0a8-0057-12c3b73aaf1-3019ebbe-10871- | MF-HQ-5523 | MCPA - Mine Clearance Planning Agency | AF/0505/005/MF 74 | 5074 | 69.0742 | 34.1625 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-071 | Logar Demining Project-06 (AT) |  |  |  |  | 1394 |  | {00748D57-A1DD-4B44-B083-BE023951478E} |  | Medium | Critical Infrastracture | Substantial | 1332 | CHA | 3 |  |  | 1998-10-21 | No | Open
Central | Logar | Mohammad Agha | Zara Kala | {04156B00-4092-4464-B6E4-BF3D6FC88DEA} | c0a8-0057-12c3b688989-1a34f4f9-8250-9 | MF-HQ-13262 | MCPA - Mine Clearance Planning Agency | AF/0505/03856/MF0417 | 249428 | 69.2594 | 34.1341 | Open | AT Only | AT Only | MineField |  | MBT Project-238 | Logar Demining Project-16 (AT) |  |  |  |  | 1400 |  | {04156B00-4092-4464-B6E4-BF3D6FC88DEA} |  | Low | Agriculture Blocked | Substantial | 247 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zara Kala | {04156B00-4092-4464-B6E4-BF3D6FC88DEA} | c0a8-0057-12c3b6c74d7-78bc57c6-b0f3-2 | MF-HQ-13258 | MCPA - Mine Clearance Planning Agency | AF/0505/03856/MF0413 | 93150 | 69.2544 | 34.1336 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-014 | Logar Demining Project-27 (AT) |  |  |  |  | 1395 |  | {04156B00-4092-4464-B6E4-BF3D6FC88DEA} |  | Medium | Agriculture Blocked | Substantial | 183 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zara Kala | {04156B00-4092-4464-B6E4-BF3D6FC88DEA} | c0a8-0057-12c3b6dc4c7-da53b957-c0eb-5 | MF-HQ-13261 | MCPA - Mine Clearance Planning Agency | AF/0505/03856/MF0416 | 236849 | 69.2594 | 34.1341 | Open | AT Only | AT Only | MineField |  | MBT Project-238 | Logar Demining Project-16 (AT) |  |  |  |  | 1400 |  | {04156B00-4092-4464-B6E4-BF3D6FC88DEA} |  | Low | Agriculture Blocked | Substantial | 246 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zara Kala | {04156B00-4092-4464-B6E4-BF3D6FC88DEA} | c0a8-0057-12c3b714958-182cc8bf-ebb8-5 | MF-HQ-13259 | MCPA - Mine Clearance Planning Agency | AF/0505/03856/MF0414 | 101023 | 69.2544 | 34.1336 | Open | AT Only | AT Only | MineField |  | MBT Project-238 | Logar Demining Project-16 (AT) |  |  |  |  | 1400 |  | {04156B00-4092-4464-B6E4-BF3D6FC88DEA} |  | Low | Agriculture Blocked | Substantial | 241 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zara Kala | {04156B00-4092-4464-B6E4-BF3D6FC88DEA} | c0a8-0057-12c3b79acd5-e5b08e75-14f1d- | MF-HQ-13260 | MCPA - Mine Clearance Planning Agency | AF/0505/03856/MF0415 | 99100 | 69.2544 | 34.1336 | Open | AT Only | AT Only | MineField |  | MBT Project-296 | Logar Demining Project-24 (AT) |  |  |  |  | 1399 |  | {04156B00-4092-4464-B6E4-BF3D6FC88DEA} |  | Low | Agriculture Blocked | Substantial | 183 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b7c3f2e-d9f6da6b-16cc1- | MF-HQ-13347 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0487 | 389614 | 69.1537 | 34.0975 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 62 | CHA | 4 |  |  | 2009-10-22 | No | Planned
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b7c40d4-f1f5ca75-16cd2- | MF-HQ-13349 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0489 | 350400 | 69.1537 | 34.0975 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 69 | CHA | 4 |  |  | 2009-10-22 | No | Planned
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b7c4269-7f7d0062-16ce3- | MF-HQ-13263 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0439 | 362200 | 69.1537 | 34.0975 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 192 | CHA | 5 |  |  | 2009-10-22 | No | Planned
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b7c441e-339305d8-16cf4- | MF-HQ-13341 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0481 | 409953 | 69.1537 | 34.0975 | Open | AT Only | AT Only | MineField |  | MBT Project-239 | Logar Demining Project-17 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 201 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b7c45f2-965f09bd-16d06- | MF-HQ-13342 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0482 | 392949 | 69.1537 | 34.0975 | Open | AT Only | AT Only | MineField |  | MBT Project-239 | Logar Demining Project-17 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 397 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b7c4797-af4f8e06-16d19- | MF-HQ-13345 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0485 | 383727 | 69.1537 | 34.0975 | Open | AT Only | AT Only | MineField |  | MBT Project-198 | Logar Demining Project-18 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 244 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b7c493c-b08c744-16d2a-b | MF-HQ-13344 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0484 | 414036 | 69.1537 | 34.0975 | Open | AT Only | AT Only | MineField |  | MBT Project-198 | Logar Demining Project-18 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 122 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b7c4ae2-b2f4a6f7-16d3b- | MF-HQ-13343 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0483 | 412669 | 69.1537 | 34.0975 | Open | AT Only | AT Only | MineField |  | MBT Project-198 | Logar Demining Project-18 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 384 | CHA | 4 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b7c4c87-c2b9e1e-16d4c-3 | MF-HQ-13346 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0486 | 394561 | 69.1537 | 34.0975 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 236 | CHA | 4 |  |  | 2009-10-22 | No | Planned
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b7c4e2c-ee62be1a-16d5d- | MF-HQ-13264 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0440 | 351750 | 69.1537 | 34.0975 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes |  |  | 1393 | HT | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 183 | CHA | 5 |  |  | 2009-10-22 | No | Planned
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b7c4fd1-7c0f1be3-16d6e- | MF-HQ-13348 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0488 | 318760 | 69.1537 | 34.0975 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-074 | Logar Demining Project-09 (AT) | Bilateral | Yes | 2014-05-01 | 2014-09-23 | 1393 | HT | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 130 | CHA | 5 |  |  | 2009-10-22 | No | Planned
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e47df-70b43285-2de04- | MF-HQ-12980 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0512 | 239200 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-239 | Logar Demining Project-17 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 90 | CHA | 4 |  |  | 2009-09-12 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e49c3-966b1cdf-2de19- | MF-HQ-12990 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0496 | 274900 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-239 | Logar Demining Project-17 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 281 | CHA | 4 |  |  | 2009-08-12 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e4ba6-f820c33-2de2a-2 | MF-HQ-12971 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0497 | 259850 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-297 | Logar Demining Project-25 (AT) |  |  |  |  | 1401 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 249 | CHA | 5 |  |  | 2009-07-04 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e4d6b-71fb4d76-2de3b- | MF-HQ-12984 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0515 | 251100 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-297 | Logar Demining Project-25 (AT) |  |  |  |  | 1401 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2009-09-16 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e4f3f-7e999806-2de4c- | MF-HQ-12988 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0494 | 279090 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-239 | Logar Demining Project-17 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 365 | CHA | 4 |  |  | 2009-08-15 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e5170-6752ca6d-2de5d- | MF-HQ-12979 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0511 | 279720 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-239 | Logar Demining Project-17 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 168 | CHA | 4 |  |  | 2009-09-07 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e5363-aac7d9d0-2de70- | MF-HQ-12989 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0495 | 260728 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-239 | Logar Demining Project-17 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 333 | CHA | 4 |  |  | 2009-08-16 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e5528-616a7b83-2de81- | MF-HQ-12985 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0516 | 250685 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-297 | Logar Demining Project-25 (AT) |  |  |  |  | 1401 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 84 | CHA | 5 |  |  | 2009-09-17 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e572a-1f031eda-2de92- | MF-HQ-12982 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0513 | 232170 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-297 | Logar Demining Project-25 (AT) |  |  |  |  | 1401 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 90 | CHA | 5 |  |  | 2009-09-13 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e597b-c9ec78fe-2dea5- | MF-HQ-12986 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0492 | 278810 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-239 | Logar Demining Project-17 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 215 | CHA | 4 |  |  | 2009-08-10 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e5bad-d81b0bf5-2deb9- | MF-HQ-12987 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0493 | 256443 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-239 | Logar Demining Project-17 (AT) |  |  |  |  | 1399 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 305 | CHA | 4 |  |  | 2009-08-12 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9e5d81-564b30a2-2decc- | MF-HQ-12983 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0514 | 292500 | 69.1419 | 34.1002 | Open | AT Only | AT Only | MineField |  | MBT Project-297 | Logar Demining Project-25 (AT) |  |  |  |  | 1401 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 53 | CHA | 5 |  |  | 2009-09-14 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3b9ef7ab-add0cf47-2e4b5- | MF-CA-1559 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0201 | 32469 | 69.165 | 34.1183 | Open | AT Only | AT Only | MineField |  | MBT Project-297 | Logar Demining Project-25 (AT) |  |  |  |  | 1401 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 17 | CHA | 5 |  |  | 2008-07-08 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3bb239a7-26f8b2ce-39da9- | MF-HQ-13266 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0448 | 163600 | 69.1552 | 34.1059 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Medium | Critical Infrastracture | Substantial | 74 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3bb23c56-187907b4-39dbb- | MF-HQ-13271 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0443 | 142344 | 69.1629 | 34.1143 | Open | AT Only | AT Only | MineField |  | MBT Project-297 | Logar Demining Project-25 (AT) |  |  |  |  | 1401 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Critical Infrastracture | Substantial | 16 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3bb23e78-34b26951-39dd1- | MF-HQ-13267 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0447 | 153993 | 69.1552 | 34.1059 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Medium | Critical Infrastracture | Substantial | 74 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3bb2405b-d70c3d0e-39de3- | MF-HQ-13268 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0446 | 153627 | 69.1577 | 34.108 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Medium | Critical Infrastracture | Substantial | 74 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3bb2427d-10a81f7c-39df4- | MF-HQ-13265 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0449 | 133316 | 69.1548 | 34.1005 | Open | AT Only | AT Only | MineField |  | MBT Project-072 | Logar Demining Project-07 (AT) |  |  |  |  | 1395 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Medium | Critical Infrastracture | Substantial | 275 | CHA | 3 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-0057-12c3bb24480-b3efd416-39e05- | MF-HQ-13270 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0444 | 159883 | 69.1629 | 34.1143 | Open | AT Only | AT Only | MineField |  | MBT Project-297 | Logar Demining Project-25 (AT) |  |  |  |  | 1401 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Critical Infrastracture | Substantial | 16 | CHA | 5 |  |  | 2009-10-22 | No | Open
Central | Logar | Mohammad Agha | Zarghun Shahr | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} | c0a8-00f6-135520427e9-6de3d74b-59-38f | MF-16671 | MCPA - Mine Clearance Planning Agency | AF/0505/03839/MF0645 | 65699 | 69.1577 | 34.108 | Open | AT Only | AT Only | MineField |  | MBT Project-293 | Logar Demining Project-20 (AT) |  |  |  |  | 1401 |  | {BB8900A9-DFE3-4AE7-B6B1-449ECE0D9D09} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2011-10-30 16:30 | No | Open
Central | Logar | Mohammad Agha | Zaydabad | {9A4F282B-8397-40FE-B050-85CE2525447B} | c0a8-0009-13fec164e61-7216cbaa-a01-37 | Hz-ID-18062 | MCPA - Mine Clearance Planning Agency | AF/0505/03905/BF0680 | 48049 | 69.1281 | 34.2687 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-234 | Logar Demining Project-08 | DOS | Yes | 2013-07-13 | 2013-09-29 | 1392 | OMAR | {9A4F282B-8397-40FE-B050-85CE2525447B} |  |  |  | Substantial | 18 | CHA | 3 |  |  | 2013-07-11 16:30 | No | Complete
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0009-14544fca73c-7333c87-e3-648f | Hz-ID-18603 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0198 | 8980 | 69.2043 | 33.908 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 96 | CHA | 2 |  |  | 2014-02-19 16:30 | No | Open
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0009-145450ee8de-ba4db318-16b-32 | Hz-ID-18604 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0199 | 8160 | 69.2066 | 33.9032 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 88 | CHA | 2 |  |  | 2014-02-20 16:30 | No | Open
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0009-145451435ef-bb7e45bc-1b2-1e | Hz-ID-18605 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0200 | 13895 | 69.2317 | 33.8915 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 78 | CHA | 2 |  |  | 2014-02-26 16:30 | No | Open
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0057-12c3b7be81b-582da552-168c7- | MF-HQ-13614 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0141 | 8994 | 69.229 | 33.8919 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 107 | CHA | 2 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0057-12c3b85e286-9367a2ec-1da0f- | MF-HQ-13603 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0133 | 7496 | 69.2043 | 33.908 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 76 | CHA | 2 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0057-12c3b928a1c-be8af2af-263c0- | MF-HQ-13617 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0137 | 10123 | 69.2238 | 33.8869 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 67 | CHA | 2 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0057-12c3b93f0c6-aa4a072b-272ae- | MF-HQ-13598 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0129 | 72694 | 69.2494 | 33.8962 | Open | AT Only | AT Only | MineField | Blank | MBT Project-024 | Logar Demining Project-03 (AT) |  | No |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 46 | CHA | 2 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0057-12c3b98e27f-45efe875-2a6b5- | MF-HQ-13601 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0134 | 26359 | 69.2183 | 33.8983 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 4 | CHA | 2 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0057-12c3b9c1727-6a77290d-2c7fd- | MF-HQ-13607 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0130 | 7950 | 69.228 | 33.8919 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 320 | CHA | 2 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0057-12c3ba97e7a-4472d5c2-34ad4- | MF-HQ-13613 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0136 | 9554 | 69.1996 | 33.8966 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 6 | CHA | 2 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0057-12c3bb57dc0-23c38807-3bc27- | MF-HQ-13600 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0131 | 23807 | 69.2265 | 33.8959 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 427 | CHA | 2 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Abchakan | {043233D8-437E-4F7A-A8F2-45B89C040ED9} | c0a8-0057-12c3bb805bd-1f83957c-3d319- | MF-HQ-13604 | MCPA - Mine Clearance Planning Agency | AF/0501/04034/MF0135 | 5789 | 69.1989 | 33.9017 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {043233D8-437E-4F7A-A8F2-45B89C040ED9} |  | High with Victim | High with Victims | High | 7 | CHA | 2 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Akhundkhel | {103F4647-1470-4C78-B60E-0643F09BAED5} | c0a8-0057-12c3b7d09ea-9804b2df-175f4- | MF-HQ-13632 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0501/03688/MF0142 | 50000 | 69.185 | 33.9451 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {103F4647-1470-4C78-B60E-0643F09BAED5} |  | Low | Other | High | 74 | CHA | 4 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Altamur | {1694A785-EC5A-4628-8601-19D4331A9E3B} | c0a8-0057-12c3bb24e02-45aa9246-39e53- | MF-HQ-13622 | MCPA - Mine Clearance Planning Agency | AF/0501/04037/MF0145 | 166173 | 69.1377 | 33.7907 | Open | AP Only | AP Only | MineField | Blank | MBT Project-178 | Logar Demining Project-02 |  | No |  |  | 1395 | None | {1694A785-EC5A-4628-8601-19D4331A9E3B} |  | Medium | Critical Infrastracture | High | 82 | CHA | 3 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Altamur | {1694A785-EC5A-4628-8601-19D4331A9E3B} | c0a8-0057-12c3bb4d5ff-e5d84e8d-3b661- | MF-HQ-13626 | MCPA - Mine Clearance Planning Agency | AF/0501/04037/MF0147 | 39866 | 69.1391 | 33.8076 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {1694A785-EC5A-4628-8601-19D4331A9E3B} |  | Low | Agriculture Blocked | High | 134 | CHA | 4 |  |  | 2009-11-05 | No | Open
Central | Logar | Puli Alam | Babus (1) | {B31B2A13-2B77-434A-AB21-FBCD7163CD6B} | c0a8-0009-14375cd81ac-b4d9dbe9-27c2-e | Hz-ID-18355 | MCPA - Mine Clearance Planning Agency | AF/0501/04005/MF0194 | 72849 | 68.97 | 34.1032 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {B31B2A13-2B77-434A-AB21-FBCD7163CD6B} |  | High with Victim | High with Victims | High | 1 | CHA | 2 |  |  | 2013-11-19 16:30 | No | Open
Central | Logar | Puli Alam | Babus (1) | {B31B2A13-2B77-434A-AB21-FBCD7163CD6B} | c0a8-0009-14375cf2337-4d2c828a-27db-6 | Hz-ID-18357 | MCPA - Mine Clearance Planning Agency | AF/0501/04005/MF0195 | 78807 | 68.9752 | 34.1053 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {B31B2A13-2B77-434A-AB21-FBCD7163CD6B} |  | High with Victim | High with Victims | High | 2 | CHA | 2 |  |  | 2013-11-20 16:30 | No | Open
Central | Logar | Puli Alam | Babus (1) | {B31B2A13-2B77-434A-AB21-FBCD7163CD6B} | c0a8-0009-14375d1f572-88065b16-281c-d | Hz-ID-18359 | MCPA - Mine Clearance Planning Agency | AF/0501/04005/MF0196 | 81593 | 68.9791 | 34.1102 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {B31B2A13-2B77-434A-AB21-FBCD7163CD6B} |  | High with Victim | High with Victims | High | 2 | CHA | 2 |  |  | 2013-11-26 16:30 | No | Open
Central | Logar | Puli Alam | Babus (1) | {B31B2A13-2B77-434A-AB21-FBCD7163CD6B} | c0a8-0009-14375eec39d-d3fd026f-2a6c-6 | Hz-ID-18360 | MCPA - Mine Clearance Planning Agency | AF/0501/04005/MF0197 | 86421 | 68.9808 | 34.115 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {B31B2A13-2B77-434A-AB21-FBCD7163CD6B} |  | High with Victim | High with Victims | High | 1 | CHA | 2 |  |  | 2013-11-27 16:30 | No | Open
Central | Logar | Puli Alam | Bala Qal'eh-ye Wazir | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} | c0a8-0009-13da11c2657-59262085-3e20-7 | Hz-ID-17737 | MCPA - Mine Clearance Planning Agency | AF/0501/04012/MF0187 | 64718 | 69.0961 | 34.0044 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/C | Logar Demining Project-08 (AT)/C | DOS | Yes | 2013-08-13 | 2014-01-23 | 1392 | HT | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} |  |  |  | High | 146 | CHA | 4 |  |  | 2013-03-20 16:30 | No | Complete
Central | Logar | Puli Alam | Bala Qal'eh-ye Wazir | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} | c0a8-0009-13da11f9127-ff146e38-3e53-9 | Hz-ID-17738 | MCPA - Mine Clearance Planning Agency | AF/0501/04012/MF0188 | 89218 | 69.0961 | 34.0044 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes | 2013-09-03 | 2013-11-23 | 1392-1393 | HT | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} |  |  |  | High | 16 | CHA | 5 |  |  | 2013-03-20 16:30 | No | Complete
Central | Logar | Puli Alam | Bala Qal'eh-ye Wazir | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} | c0a8-0009-13da1225d3a-97b678aa-3e6d-8 | Hz-ID-17739 | MCPA - Mine Clearance Planning Agency | AF/0501/04012/MF0192 | 127478 | 69.1 | 34.0047 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes | 2013-06-05 | 2013-07-23 | 1392-1393 | HT | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} |  |  |  | High | 220 | CHA | 4 |  |  | 2013-03-20 16:30 | No | Complete
Central | Logar | Puli Alam | Bala Qal'eh-ye Wazir | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} | c0a8-0009-13da124723e-5602ab9a-3e84-2 | Hz-ID-17740 | MCPA - Mine Clearance Planning Agency | AF/0501/04012/MF0193 | 143046 | 69.1 | 34.0047 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes | 2013-08-13 | 2013-12-23 | 1392-1393 | HT | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} |  |  |  | High | 146 | CHA | 4 |  |  | 2013-03-17 16:30 | No | Complete
Central | Logar | Puli Alam | Bala Qal'eh-ye Wazir | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} | c0a8-0009-13e7831aee2-e16287b5-1334-d | Hz-ID-17837 | MCPA - Mine Clearance Planning Agency | AF/0501/04012/MF0183 | 62122 | 69.1162 | 34.0074 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/B | Logar Demining Project-08 (AT)/B | Bilateral | Yes | 2013-08-13 | 2013-12-23 | 1392-1393 | HT | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} |  |  |  | High | 104 | CHA | 5 |  |  | 2013-03-17 16:30 | No | Complete
Central | Logar | Puli Alam | Bala Qal'eh-ye Wazir | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} | c0a8-0009-13e7832f58f-95f2848-135b-13 | Hz-ID-17838 | MCPA - Mine Clearance Planning Agency | AF/0501/04012/MF0184 | 107270 | 69.1162 | 34.0074 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/D | Logar Demining Project-08 (AT)/D | B-Germany | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} |  |  |  | High | 208 | CHA | 5 |  |  | 2013-03-18 16:30 | No | Complete
Central | Logar | Puli Alam | Bala Qal'eh-ye Wazir | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} | c0a8-0009-13e7842406d-c472e20a-1482-6 | Hz-ID-17839 | MCPA - Mine Clearance Planning Agency | AF/0501/04012/MF0185 | 99988 | 69.1072 | 34.0061 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/D | Logar Demining Project-08 (AT)/D | B-Germany | Yes | 2013-11-01 | 2013-12-23 | 1392 | HT | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} |  |  |  | High | 234 | CHA | 5 |  |  | 2013-03-18 16:30 | No | Complete
Central | Logar | Puli Alam | Bala Qal'eh-ye Wazir | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} | c0a8-0009-13e7d5ca78f-d0f0a7-1edc-537 | Hz-ID-17841 | MCPA - Mine Clearance Planning Agency | AF/0501/04012/MF0186 | 100825 | 69.1072 | 34.0061 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/D | Logar Demining Project-08 (AT)/D | B-Germany | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} |  |  |  | High | 130 | CHA | 5 |  |  | 2013-03-19 16:30 | No | Complete
Central | Logar | Puli Alam | Bala Qal'eh-ye Wazir | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} | c0a8-0009-13e7d5d1eb0-a9fa64d2-1ef4-9 | Hz-ID-17842 | MCPA - Mine Clearance Planning Agency | AF/0501/04012/MF0189 | 149914 | 69.1195 | 34.0078 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/D | Logar Demining Project-08 (AT)/D | B-Germany | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} |  |  |  | High | 114 | CHA | 5 |  |  | 2013-03-19 16:30 | No | Complete
Central | Logar | Puli Alam | Bala Qal'eh-ye Wazir | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} | c0a8-0009-13e7d5d6f9c-35d61621-1f0f-9 | Hz-ID-17843 | MCPA - Mine Clearance Planning Agency | AF/0501/04012/MF0190 | 106598 | 69.1125 | 34.007 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/C | Logar Demining Project-08 (AT)/C | DOS | Yes | 2013-09-01 | 2014-03-23 | 1392 | HT | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} |  |  |  | High | 110 | CHA | 5 |  |  | 2013-03-18 16:30 | No | Complete
Central | Logar | Puli Alam | Bala Qal'eh-ye Wazir | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} | c0a8-0009-13e7d5da9fd-eb9748a4-1f2b-1 | Hz-ID-17844 | MCPA - Mine Clearance Planning Agency | AF/0501/04012/MF0191 | 143873 | 69.1125 | 34.007 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-073/C | Logar Demining Project-08 (AT)/C | DOS | Yes | 2013-09-01 | 2014-03-23 | 1392 | HT | {450A22D9-77B1-4899-B6F1-AD31A4D77E71} |  |  |  | High | 330 | CHA | 5 |  |  | 2013-03-19 16:30 | No | Complete
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-0057-12c3b922c87-79a6acb0-2601e- | MF-HQ-13788 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0163 | 64506 | 69.1129 | 34.0763 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 1 | CHA | 2 |  |  | 2009-12-05 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f6d2274-d6a77c51-119e-9 | MF-16015 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0168 | 116025 | 69.1081 | 34.0922 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 230 | CHA | 2 |  |  | 2011-03-10 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f6dd127-1a9e7d7b-11b1-a | MF-16018 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0171 | 82975 | 69.1081 | 34.0838 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 230 | CHA | 2 |  |  | 2011-03-14 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f6f6bf9-2bf6205f-11d9-f | MF-16022 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0175 | 95183 | 69.1031 | 34.0838 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-025 | Logar Demining Project-04 (AT) | B-Germany | Yes |  |  | 1394 | HT | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 177 | CHA | 2 |  |  | 2011-03-20 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f70796d-5134b8b0-11ec-4 | MF-16024 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0177 | 101160 | 69.114 | 34.0799 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 27 | CHA | 2 |  |  | 2011-03-22 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f71d915-3a6aacca-1202-4 | MF-16029 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0182 | 166507 | 69.0908 | 34.0793 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 193 | CHA | 2 |  |  | 2011-05-16 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f72b30c-d8df8f78-1218-3 | MF-16026 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0179 | 114895 | 69.111 | 34.0805 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 8 | CHA | 2 |  |  | 2011-05-12 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f73aabf-1046ebda-122d-6 | MF-16017 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0170 | 72885 | 69.1037 | 34.0869 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-025 | Logar Demining Project-04 (AT) | B-Germany | Yes |  |  | 1394 | HT | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 170 | CHA | 2 |  |  | 2011-03-13 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f79182e-a42dc994-12be-f | MF-16027 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0180 | 92913 | 69.1145 | 34.1028 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-025 | Logar Demining Project-04 (AT) | B-Germany | Yes |  |  | 1394 | HT | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 275 | CHA | 2 |  |  | 2011-05-14 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f7af128-9e6c5ea3-12f6-8 | MF-16028 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0181 | 107759 | 69.1127 | 34.1101 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 200 | CHA | 2 |  |  | 2011-05-15 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f7ba650-7318bdc4-1307-9 | MF-16023 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0176 | 143360 | 69.114 | 34.0799 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 61 | CHA | 2 |  |  | 2011-03-21 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f7e098d-fe957209-133e-4 | MF-16019 | MCPA - Mine Clearance Planning Agency | AF/0501/03890/MF0172 | 62850 | 69.1081 | 34.0838 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-025 | Logar Demining Project-04 (AT) | B-Germany | Yes |  |  | 1394 | HT | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 60 | CHA | 2 |  |  | 2011-03-15 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-008e-1328f7f9449-ec981981-1350-1 | MF-16016 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0169 | 76475 | 69.1037 | 34.0869 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 170 | CHA | 2 |  |  | 2011-03-12 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-00f6-13551e382a4-edd1107c-35c-a0 | MF-16020 | MCPA - Mine Clearance Planning Agency | AF/0105/03980/MF0173 | 27971 | 69.1081 | 34.0838 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-025 | Logar Demining Project-04 (AT) | B-Germany | Yes |  |  | 1394 | HT | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 61 | CHA | 2 |  |  | 2011-07-11 16:30 | No | Open
Central | Logar | Puli Alam | Dadokhel | {D805E250-049D-4F06-9C80-A5A3A8B3513A} | c0a8-00f6-1355261c525-6e6ffc7e-4-6413 | MF-16025 | MCPA - Mine Clearance Planning Agency | AF/0501/03980/MF0178 | 40750 | 69.0991 | 34.0794 | Open | AT Only | AT Only | MineField |  | MBT Project-024 | Logar Demining Project-03 (AT) |  |  |  |  | 1397 |  | {D805E250-049D-4F06-9C80-A5A3A8B3513A} |  | High with Victim | High with Victims | High | 193 | CHA | 2 |  |  | 2011-07-11 16:30 | No | Open
Central | Logar | Puli Alam | Joyak | {5B0891DA-E2D4-4758-B805-506620DC55C1} | c0a8-0057-12c3b8de687-5afc8b0e-232ce- | MF-CA-1768 | MCPA - Mine Clearance Planning Agency | AF/0501/03997/MF0118 | 441 | 69.0297 | 34.014 | Open | AP Only | AP Only | MineField | Blank | MBT Project-014 | Logar Demining Project-27 (AT) |  | No |  |  | 1395 |  | {5B0891DA-E2D4-4758-B805-506620DC55C1} |  | High | Critical Infrastracture | High | 76 | CHA | 3 |  |  | 2008-11-27 | No | Open
Central | Logar | Puli Alam | Kuz Nurkhel | {A8DBB7F1-5329-4934-ABF9-4707A48D192B} | c0a8-0057-12c3ba325a1-9368e79b-30da9- | MF-HQ-13782 | MCPA - Mine Clearance Planning Agency | AF/0501/04038/MF0153 | 31275 | 69.0773 | 33.8036 | Open | AP Only | AP Only | MineField |  | MBT Project-178 | Logar Demining Project-02 |  |  |  |  | 1395 |  | {A8DBB7F1-5329-4934-ABF9-4707A48D192B} |  | Medium | Critical Infrastracture | High | 315 | CHA | 3 |  |  | 2009-12-05 | No | Open
Central | Logar | Puli Alam | Sepest(Sepec) | {A8FC861A-D38B-4555-B3FB-37C520C53309} | c0a8-0057-12c3b83fb87-7256f499-1c457- | MF-HQ-13780 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0501/04044/MF0156 | 253200 | 69.2077 | 33.8565 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {A8FC861A-D38B-4555-B3FB-37C520C53309} |  | Low | Agriculture Blocked | High | 114 | SHA | 4 |  |  | 2009-12-05 | No | Open
Central | Logar | Puli Alam | Sepest(Sepec) | {A8FC861A-D38B-4555-B3FB-37C520C53309} | c0a8-0057-12c3bb33699-b0b3f365-3a6f7- | MF-HQ-13781 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0501/04044/MF0157 | 409200 | 69.2136 | 33.8449 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-178 | Logar Demining Project-02 |  |  |  |  | 1395 |  | {A8FC861A-D38B-4555-B3FB-37C520C53309} |  | Medium | Critical Infrastracture | High | 932 | SHA | 3 |  |  | 2009-12-05 | No | Open
Central | Logar | Puli Alam | Shaghasi Kala | {5759410B-6DF5-4306-801C-2BA12A8A7B70} | c0a8-0057-12c3b867abd-db573300-1e09c- | MF-CA-1771 | MCPA - Mine Clearance Planning Agency | AF/0501/04033/MF0122 | 49845 | 69.0659 | 34.1116 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {5759410B-6DF5-4306-801C-2BA12A8A7B70} |  | Low | Comunity Centers | High | 192 | CHA | 4 |  |  | 2008-11-27 | No | Open
Central | Logar | Puli Alam | Shaghasi Kala | {5759410B-6DF5-4306-801C-2BA12A8A7B70} | c0a8-0057-12c3b88ff41-1a8bb56f-1fcfb- | MF-CA-1772 | MCPA - Mine Clearance Planning Agency | AF/0501/04033/MF0127 | 51629 | 69.0659 | 34.1116 | Open | AT Only | AT Only | MineField |  | MBT Project-197 | Logar Demining Project-15 (AT) |  |  |  |  | 1398 |  | {5759410B-6DF5-4306-801C-2BA12A8A7B70} |  | Medium | Agriculture Blocked | High | 192 | CHA | 4 |  |  | 2008-11-27 | No | Open
Central | Logar | Puli Alam | Woni Sufla | {65F15FE7-7150-4F16-9F0E-C0DE81C47221} | c0a8-0057-12c3b6ec16a-e04d9ec2-cd0d-e | BF-HQ-12846 | MCPA - Mine Clearance Planning Agency | AF/0505/03995/BF0128 | 1650 | 69.005 | 34.0265 | Open | UXO Only | UXO Only | BF |  | MBT Project-178 | Logar Demining Project-02 |  |  |  |  | 1395 |  | {65F15FE7-7150-4F16-9F0E-C0DE81C47221} |  | High | Critical Infrastracture | High | 209 | CHA | 3 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Chaki Wardak | Ambokhak | {3EB5C295-7262-4928-93A1-2391F80600E5} | c0a8-0057-12c3b9b9dc6-902c468-2c342-c | MF-HQ-11509 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02559/MF0026 | 1050 | 68.7525 | 34.1687 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {3EB5C295-7262-4928-93A1-2391F80600E5} |  | Medium | Critical Infrastracture | Substantial | 85 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Ambokhak | {3EB5C295-7262-4928-93A1-2391F80600E5} | c0a8-0057-12c3bab01f7-78bd9c66-35876- | MF-HQ-11508 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02559/MF0027 | 151700 | 68.7615 | 34.1694 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {3EB5C295-7262-4928-93A1-2391F80600E5} |  | Low | Agriculture Blocked | Substantial | 90 | SHA | 5 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Ambokhak | {3EB5C295-7262-4928-93A1-2391F80600E5} | c0a8-008e-132a00794b2-12d294b0-52-6e4 | MF-HQ-14000 | HT - HALO TRUST | H/2027 | 157000 | 68.7323 | 34.1518 | Open | AP Only | AP Only | MineField |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {3EB5C295-7262-4928-93A1-2391F80600E5} |  | Medium | Critical Infrastracture | Substantial | 285 | CHA | 3 |  |  | 2000-06-11 | No | Open
Central | Maydan Wardak | Chaki Wardak | Badqol | {5B1CA8C1-46C8-4D47-92EC-DA8AF5571C59} | c0a8-0057-12c3baf3fe6-10849f9f-3812e- | MF-HQ-12231 | HT - HALO TRUST | H/2028 | 40000 | 68.6105 | 34.1809 | Open | AT Only | AT Only | MineField |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {5B1CA8C1-46C8-4D47-92EC-DA8AF5571C59} |  | Low | Other | Substantial | 30 | CHA | 5 |  |  | 2000-06-13 16:30 | No | Open
Central | Maydan Wardak | Chaki Wardak | Bahadur Koday | {E51FDC29-6074-48B6-AF49-05DD03DC6085} | c0a8-0057-12c3bb6482e-7952f880-3c353- | MF-HQ-12497 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02528/MF0017 | 5250 | 68.602 | 34.1278 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {E51FDC29-6074-48B6-AF49-05DD03DC6085} |  | Low | Critical Infrastracture | Substantial | 147 | SHA | 4 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Bambay(Khawat) | {2DFC3EA5-18EB-4D8C-B861-C4E2AE5E47A7} | c0a8-0057-12c3b8635c3-58c90df2-1dd8a- | MF-HQ-12221 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02530/MF003 | 31288 | 68.6273 | 34.1352 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) |  |  |  |  | 1393 |  | {2DFC3EA5-18EB-4D8C-B861-C4E2AE5E47A7} |  | High with Victim | High with Victims | Substantial | 191 | SHA | 2 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Bum | {AEF45ECF-9BE2-4579-A92F-F74463E856D5} | c0a8-0057-12c3b817925-44c0d3e6-1a798- | MF-CA-174 | MCPA - Mine Clearance Planning Agency | AF/0406/02444/002 | 155350 | 68.5072 | 34.0589 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) |  |  |  |  | 1393 |  | {AEF45ECF-9BE2-4579-A92F-F74463E856D5} |  | High with Victim | High with Victims | Substantial | 98 | CHA | 2 |  |  | 2005-04-30 | No | Open
Central | Maydan Wardak | Chaki Wardak | Bum | {AEF45ECF-9BE2-4579-A92F-F74463E856D5} | c0a8-0057-12c3bb5d792-8adbda66-3bf70- | MF-CA-171 | MCPA - Mine Clearance Planning Agency | AF/0406/02444/MF 001 | 93477 | 68.5047 | 34.0592 | Open | AP Only | AP Only | MineField |  | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) |  |  |  |  | 1393 |  | {AEF45ECF-9BE2-4579-A92F-F74463E856D5} |  | High with Victim | High with Victims | Substantial | 129 | CHA | 2 |  |  | 2005-04-05 | No | Open
Central | Maydan Wardak | Chaki Wardak | Chaki Wardak | {060E3C9F-EC6F-43AE-8F10-702246AA6A2C} | c0a8-0057-12c3b890347-1369b383-1fd25- | MF-HQ-12222 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/31854/MF0028 | 127251 | 68.5781 | 34.1007 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) |  |  |  |  | 1393 |  | {060E3C9F-EC6F-43AE-8F10-702246AA6A2C} |  | High with Victim | High with Victims | Substantial | 717 | SHA | 1 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Chaki Wardak | {060E3C9F-EC6F-43AE-8F10-702246AA6A2C} | c0a8-0057-12c3b8dda09-726175a3-23256- | MF-HQ-12360 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/31854/MF0030 | 61416 | 68.5768 | 34.1035 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) |  |  |  |  | 1393 |  | {060E3C9F-EC6F-43AE-8F10-702246AA6A2C} |  | High with Victim | High with Victims | Substantial | 737 | SHA | 1 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Chaki Wardak | {060E3C9F-EC6F-43AE-8F10-702246AA6A2C} | c0a8-0057-12c3b99c04b-9768db2b-2afdd- | MF-HQ-12560 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/31854/MF0029 | 20000 | 68.5768 | 34.1035 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) |  |  |  |  | 1393 |  | {060E3C9F-EC6F-43AE-8F10-702246AA6A2C} |  | High with Victim | High with Victims | Substantial | 711 | SHA | 1 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Dawrankhel | {F023952D-2BC2-4804-88C2-D320DE280C77} | c0a8-0057-12c3b8f8c62-94e0ac11-244e6- | MF-HQ-12533 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02519/MF0042 | 58487 | 68.5738 | 34.0974 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {F023952D-2BC2-4804-88C2-D320DE280C77} |  | Medium | Critical Infrastracture | Substantial | 143 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Dawrankhel | {F023952D-2BC2-4804-88C2-D320DE280C77} | c0a8-0057-12c3b955998-7db4c797-2814f- | MF-HQ-12529 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02519/MF0041 | 29600 | 68.5725 | 34.0973 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {F023952D-2BC2-4804-88C2-D320DE280C77} |  | Medium | Critical Infrastracture | Substantial | 365 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Dawrankhel | {F023952D-2BC2-4804-88C2-D320DE280C77} | c0a8-0057-12c3b976eb1-8468fa2a-29755- | MF-HQ-12527 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02519/MF0040 | 1756 | 68.5687 | 34.0884 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {F023952D-2BC2-4804-88C2-D320DE280C77} |  | Low | Critical Infrastracture | Substantial | 151 | SHA | 5 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Fadzelkhel | {75E4BA77-A4C3-4A8C-A749-6D8651062FCC} | c0a8-0057-12c3b8397d6-4f8e61fb-1bfbb- | MF-HQ-12467 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02502/MF0038 | 100548 | 68.5175 | 34.0597 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {75E4BA77-A4C3-4A8C-A749-6D8651062FCC} |  | Medium | Critical Infrastracture | Substantial | 147 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Fadzelkhel | {75E4BA77-A4C3-4A8C-A749-6D8651062FCC} | c0a8-0057-12c3baf6263-a1f8c6db-3826c- | MF-HQ-12471 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02502/0039 | 78725 | 68.5175 | 34.0597 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {75E4BA77-A4C3-4A8C-A749-6D8651062FCC} |  | Medium | Critical Infrastracture | Substantial | 162 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Gerdab | {CA700DAB-36EE-4492-9A08-421252CEE729} | c0a8-0057-12c3bb68701-1af40a39-3c58f- | MF-HQ-11506 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02556/MF0016 | 131200 | 68.7029 | 34.1557 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {CA700DAB-36EE-4492-9A08-421252CEE729} |  | Low | Agriculture Blocked | Substantial | 196 | SHA | 4 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Goda | {286F4100-6276-421A-BA2B-06291A209ABA} | c0a8-0057-12c3b91fd40-e6555992-25e2c- | MF-HQ-12486 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02484/MF031 | 126000 | 68.519 | 34.2156 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {286F4100-6276-421A-BA2B-06291A209ABA} |  | Low | Agriculture Blocked | Substantial | 22 | SHA | 5 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Godan | {D5078590-428F-424E-8E19-55011F070B39} | c0a8-0057-12c3b8579e5-bbe40a72-1d5ac- | MF-HQ-11507 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02561/MF0025 | 64826 | 68.7102 | 34.1553 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) |  |  |  |  | 1393 |  | {D5078590-428F-424E-8E19-55011F070B39} |  | High with Victim | High with Victims | Substantial | 391 | SHA | 2 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Gulmori | {DBF4C068-F00D-4469-9424-B63DCBA85605} | c0a8-0057-12c3b8d8160-f260c99-22e8c-5 | MF-HQ-12473 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02499/0011 | 5750 | 68.5198 | 34.0156 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {DBF4C068-F00D-4469-9424-B63DCBA85605} |  | Medium | Critical Infrastracture | Substantial | 76 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Jalil | {A0B4B9AF-8C24-450C-ADFC-3095EA93E975} | c0a8-0057-12c3baa8193-6794d42-353f8-c | MF-HQ-12460 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02540/MF0022 | 1512 | 68.647 | 34.1593 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {A0B4B9AF-8C24-450C-ADFC-3095EA93E975} |  | Low | Agriculture Blocked | Substantial | 1 | SHA | 4 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Jalil | {A0B4B9AF-8C24-450C-ADFC-3095EA93E975} | c0a8-0057-12c3babc3ae-b619f601-35f7a- | MF-HQ-12455 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02540/MF0020 | 225225 | 68.64 | 34.1463 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {A0B4B9AF-8C24-450C-ADFC-3095EA93E975} |  | Medium | Critical Infrastracture | Substantial | 123 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Jalil | {A0B4B9AF-8C24-450C-ADFC-3095EA93E975} | c0a8-0057-12c3bb6a366-8e4f15fc-3c67d- | MF-HQ-12456 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02540/MF0021 | 92300 | 68.64 | 34.1463 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {A0B4B9AF-8C24-450C-ADFC-3095EA93E975} |  | Medium | Critical Infrastracture | Substantial | 123 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Koday (1) | {DED0AA11-6816-45CD-8DA7-E29C1F8EE38C} | c0a8-008e-1323d34d6a1-54ec22b8-1802-b | MF-HQ-12358 | HT - HALO TRUST | H/2035 | 12000 | 68.4471 | 33.9502 | Open | AT Only | AT Only | MineField |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {DED0AA11-6816-45CD-8DA7-E29C1F8EE38C} |  | High with Victim | High with Victims | Substantial | 493 | CHA | 2 |  |  | 2000-06-14 | No | Open
Central | Maydan Wardak | Chaki Wardak | Langar | {7E91A931-7CEE-4EE3-AB61-7859FAD901C7} | c0a8-0057-12c3b7d0835-4bbd8ea-175e3-9 | MF-HQ-12550 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02558/MF0037 | 210600 | 68.6844 | 34.1598 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {7E91A931-7CEE-4EE3-AB61-7859FAD901C7} |  | High with Victim | High with Victims | Substantial | 145 | SHA | 2 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Langar | {7E91A931-7CEE-4EE3-AB61-7859FAD901C7} | c0a8-0057-12c3b8137c2-70ff4b93-1a4b5- | MF-HQ-12545 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02558/MF0036 | 150000 | 68.6851 | 34.1583 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {7E91A931-7CEE-4EE3-AB61-7859FAD901C7} |  | High with Victim | High with Victims | Substantial | 1030 | SHA | 2 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Langar | {7E91A931-7CEE-4EE3-AB61-7859FAD901C7} | c0a8-0057-12c3b8f4601-f060dde6-24212- | MF-HQ-12351 | HT - HALO TRUST | H/2038 | 90000 | 68.6929 | 34.155 | Open | AT Only | AT Only | MineField |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {7E91A931-7CEE-4EE3-AB61-7859FAD901C7} |  | High with Victim | High with Victims | Substantial | 63 | CHA | 2 |  |  | 2009-09-13 16:30 | No | Open
Central | Maydan Wardak | Chaki Wardak | Langar | {7E91A931-7CEE-4EE3-AB61-7859FAD901C7} | c0a8-0057-12c3b9be752-c371211d-2c614- | MF-HQ-12552 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02558/MF0035 | 100800 | 68.6911 | 34.1634 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {7E91A931-7CEE-4EE3-AB61-7859FAD901C7} |  | High with Victim | High with Victims | Substantial | 394 | SHA | 2 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Langar | {7E91A931-7CEE-4EE3-AB61-7859FAD901C7} | c0a8-0057-12c3bae8b49-d0ac1cb-37a74-e | MF-HQ-12354 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02558/MF0034 | 96000 | 68.6688 | 34.1546 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {7E91A931-7CEE-4EE3-AB61-7859FAD901C7} |  | High with Victim | High with Victims | Substantial | 453 | SHA | 2 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Lwar | {C6F1F6D4-89FB-4E3E-904A-7639E70C7313} | c0a8-0057-12c3b998a8d-8eb7a643-2adb2- | MF-HQ-12519 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02495/MF0033 | 148500 | 68.6463 | 34.137 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {C6F1F6D4-89FB-4E3E-904A-7639E70C7313} |  | Medium | Critical Infrastracture | Substantial | 2277 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Lwar | {C6F1F6D4-89FB-4E3E-904A-7639E70C7313} | c0a8-0057-12c3b9cf4f4-402c4534-2d0e0- | MF-HQ-12240 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02495/MF0032 | 146000 | 68.6384 | 34.1336 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {C6F1F6D4-89FB-4E3E-904A-7639E70C7313} |  | Medium | Critical Infrastracture | Substantial | 238 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Modo | {1C427690-160A-4D42-847B-A84BBF09D0B4} | c0a8-0057-12c3b89922c-55ff6d2d-202be- | MF-HQ-12235 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02524/MF 0013 | 28496 | 68.6334 | 34.1341 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {1C427690-160A-4D42-847B-A84BBF09D0B4} |  | Medium | Critical Infrastracture | Substantial | 343 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Modo | {1C427690-160A-4D42-847B-A84BBF09D0B4} | c0a8-0057-12c3b8dd642-ab2c0597-23233- | MF-HQ-12480 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02524/0012 | 1387 | 68.6011 | 34.1086 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {1C427690-160A-4D42-847B-A84BBF09D0B4} |  | Medium | Agriculture Blocked | Substantial | 0 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Pana | {93FB30A2-5BD8-41F7-9C20-AD74AAB7938A} | c0a8-0057-12c3baa71ac-230e0ac3-35365- | MF-HQ-12491 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02526/0019 | 26784 | 68.5756 | 34.1314 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {93FB30A2-5BD8-41F7-9C20-AD74AAB7938A} |  | Low | Agriculture Blocked | Substantial | 21 | SHA | 5 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Sapedar | {FD2E09E0-1084-4FBC-9D10-BB9ABC79D793} | c0a8-0057-12c3bb3ca9c-aa5c899d-3ac65- | MF-HQ-12446 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02503/MF009 | 71200 | 68.5222 | 34.051 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {FD2E09E0-1084-4FBC-9D10-BB9ABC79D793} |  | Low | Agriculture Blocked | Substantial | 290 | SHA | 4 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Sewaka | {CE64B703-5AAE-47A2-9F48-CD18860DAC7E} | c0a8-0057-12c3b875e84-8bfdf6b6-1ea70- | MF-HQ-12504 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02506/MF0023 | 79520 | 68.551 | 34.06 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {CE64B703-5AAE-47A2-9F48-CD18860DAC7E} |  | Low | Critical Infrastracture | Substantial | 99 | SHA | 5 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Sewaka | {CE64B703-5AAE-47A2-9F48-CD18860DAC7E} | c0a8-0057-12c3ba17903-33a0e1f4-2fd63- | MF-HQ-12500 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02506/MF0024 | 236236 | 68.551 | 34.06 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {CE64B703-5AAE-47A2-9F48-CD18860DAC7E} |  | Low | Critical Infrastracture | Substantial | 164 | SHA | 4 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Spin Kalay | {A5E02E47-68AF-4296-8F97-B7362FBAF85D} | c0a8-0057-12c3b93acf7-8166fc5e-26fdb- | MF-HQ-12475 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02521/0014 | 29184 | 68.5681 | 34.0864 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {A5E02E47-68AF-4296-8F97-B7362FBAF85D} |  | Low | Critical Infrastracture | Substantial | 151 | SHA | 4 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Tatang | {94BC85AC-1101-4BF9-9CA0-7114849FEEC9} | c0a8-0057-12c3bb83110-b379e1ff-3d478- | MF-HQ-12511 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02529/MF0015 | 1200 | 68.6406 | 34.1582 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {94BC85AC-1101-4BF9-9CA0-7114849FEEC9} |  | Low | Comunity Centers | Substantial | 0 | SHA | 5 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Zaman Khail | {AB149E0E-00C9-4452-B3F0-AFC890A4E8F6} | c0a8-0057-12c3b7cf783-b09f9866-1751a- | MF-HQ-12355 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/00512/MF006 | 34250 | 68.6645 | 34.1504 | Open | Mixed | Mixed AT UXO | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {AB149E0E-00C9-4452-B3F0-AFC890A4E8F6} |  | High with Victim | High with Victims | Substantial | 333 | SHA | 2 |  |  | 2000-06-12 | No | Open
Central | Maydan Wardak | Chaki Wardak | Zaman Khail | {AB149E0E-00C9-4452-B3F0-AFC890A4E8F6} | c0a8-0057-12c3b822385-dbdd2289-1af3e- | MF-HQ-12566 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/00512/MF007 | 27300 | 68.6483 | 34.1578 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {AB149E0E-00C9-4452-B3F0-AFC890A4E8F6} |  | High with Victim | High with Victims | Substantial | 1 | SHA | 2 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Zaman Khail | {AB149E0E-00C9-4452-B3F0-AFC890A4E8F6} | c0a8-0057-12c3b8ca160-2c88bdc-2252f-2 | MF-HQ-12571 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/00512/MF005 | 20400 | 68.666 | 34.144 | Open | Mixed | Mixed AT UXO | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {AB149E0E-00C9-4452-B3F0-AFC890A4E8F6} |  | High with Victim | High with Victims | Substantial | 1475 | SHA | 2 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Zaman Khail | {AB149E0E-00C9-4452-B3F0-AFC890A4E8F6} | c0a8-0057-12c3b9a8348-12285221-2b7fe- | MF-HQ-12576 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/00512/MF008 | 18900 | 68.666 | 34.144 | Open | Mixed | Mixed AT UXO | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {AB149E0E-00C9-4452-B3F0-AFC890A4E8F6} |  | High with Victim | High with Victims | Substantial | 1475 | SHA | 2 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Zaman Khail | {AB149E0E-00C9-4452-B3F0-AFC890A4E8F6} | c0a8-0057-12c3baddd12-9d57f687-373e6- | MF-HQ-12289 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/00512/MF004 | 414675 | 68.6525 | 34.139 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {AB149E0E-00C9-4452-B3F0-AFC890A4E8F6} |  | High with Victim | High with Victims | Substantial | 1807 | SHA | 2 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Chaki Wardak | Zawara | {0B210330-776D-4057-88CD-C563687CEED1} | c0a8-0057-12c3bace4e1-b0bab361-36aa6- | MF-HQ-12483 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0406/02529/0010 | 24300 | 68.6227 | 34.1188 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {0B210330-776D-4057-88CD-C563687CEED1} |  | Low | Agriculture Blocked | Substantial | 136 | SHA | 5 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Day Mirdad | Bariqul | {D51A5924-A55A-487D-A428-FE5943B3F7D1} | c0a8-0057-12c3b86eb2a-2c57e948-1e54d- | MF-HQ-12293 | HT - HALO TRUST | H/2046 | 400000 | 68.2873 | 34.3199 | Open | AP Only | AP Only | MineField |  | MBT Project-016 | Maydan Wardak Demining Project-10 |  |  |  |  | 1395 |  | {D51A5924-A55A-487D-A428-FE5943B3F7D1} |  | Low | Agriculture Blocked | Substantial | 204 | CHA | 4 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Day Mirdad | Bariqul | {D51A5924-A55A-487D-A428-FE5943B3F7D1} | c0a8-0057-12c3b894fd0-ce88f531-2005e- | MF-HQ-12209 | HT - HALO TRUST | H/2041 | 300000 | 68.2998 | 34.3957 | Open | AP Only | AP Only | MineField |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {D51A5924-A55A-487D-A428-FE5943B3F7D1} |  | Medium | Critical Infrastracture | Substantial | 324 | CHA | 3 |  |  | 2000-06-16 16:30 | No | Open
Central | Maydan Wardak | Day Mirdad | Changd | {627CCCEA-4974-45FD-A742-92B568A75B4F} | c0a8-0057-12c3b8ac7e8-fc60a9fa-2107f- | MF-HQ-12212 | HT - HALO TRUST | H/2045 | 400000 | 68.4057 | 34.266 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-276 | Maydan Wardak Demining Project-13 |  |  |  |  | 1400 |  | {627CCCEA-4974-45FD-A742-92B568A75B4F} |  | Low | Agriculture Blocked | Substantial | 682 | CHA | 5 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Day Mirdad | Garmab | {8510F7CF-D1E6-433C-B651-62C31B1C258A} | c0a8-0057-12c3b9b7e55-659731db-2c1ee- | MF-HQ-12206 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0405/02686/MF0004 | 36600 | 68.3174 | 34.2602 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-276 | Maydan Wardak Demining Project-13 |  |  |  |  | 1400 |  | {8510F7CF-D1E6-433C-B651-62C31B1C258A} |  | Low | Critical Infrastracture | Substantial | 4 | SHA | 5 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Day Mirdad | Qotubkhel | {0CC8ADCE-78E7-474A-A11E-9867712C6926} | c0a8-008e-132a00500a7-6091bf13-30-6c5 | MF-HQ-12333 | HT - HALO TRUST | H/2044 | 800000 | 68.2882 | 34.2253 | Open | AP Only | AP Only | MineField |  | MBT Project-016 | Maydan Wardak Demining Project-10 |  |  |  |  | 1395 |  | {0CC8ADCE-78E7-474A-A11E-9867712C6926} |  | Medium | Critical Infrastracture | Substantial | 445 | CHA | 3 |  |  | 2009-06-16 16:30 | No | Open
Central | Maydan Wardak | Day Mirdad | Sare KotaleSufla | {081A5567-9379-4DDF-9646-4C0801A59FC3} | c0a8-0057-12c3b9b649e-73b030f6-2c0e4- | MF-HQ-12217 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0405/02763/MF0001 | 8437 | 68.3683 | 34.3842 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-016 | Maydan Wardak Demining Project-10 |  |  |  |  | 1395 |  | {081A5567-9379-4DDF-9646-4C0801A59FC3} |  | Low | Agriculture Blocked | Substantial | 166 | SHA | 4 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Day Mirdad | Surkhi | {2FB67980-8D43-463A-BD73-A25E8ACA3A1A} | c0a8-0057-12c3b835606-b59d991d-1bcb1- | MF-HQ-12450 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0405/13851/MF006 | 90000 | 68.309 | 34.4011 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {2FB67980-8D43-463A-BD73-A25E8ACA3A1A} |  | Medium | Critical Infrastracture | Substantial | 242 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Day Mirdad | Surkhi | {2FB67980-8D43-463A-BD73-A25E8ACA3A1A} | c0a8-0057-12c3b845384-55e06d1-1c831-9 | MF-HQ-12447 | UNMACA - United Nation Mine Action Center for Afghanistan | Af/0405/13851/MF005 | 75000 | 68.309 | 34.4011 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {2FB67980-8D43-463A-BD73-A25E8ACA3A1A} |  | Medium | Critical Infrastracture | Substantial | 112 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Day Mirdad | Wulyatak | {91D4264F-B1E1-44CE-B902-1ACB51E828D3} | c0a8-0057-12c3b8d6587-b08197be-22d58- | MF-HQ-12444 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0405/02756/MF008 | 159000 | 68.3061 | 34.3807 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {91D4264F-B1E1-44CE-B902-1ACB51E828D3} |  | Medium | Critical Infrastracture | Substantial | 297 | SHA | 3 |  |  | 2009-07-21 | No | Open
Central | Maydan Wardak | Hisa-I- Awali Bihsud | Barikak | {453B0603-4D1E-4220-8134-A7EA8C7CFC37} | c0a8-0009-1402398a702-9e7215bd-43c-d5 | Hz-ID-18067 | MCPA - Mine Clearance Planning Agency | AF/0403/03282/MF0014 | 178553 | 68.2987 | 34.4672 | Open | AP Only | AP Only | MineField |  | MBT Project-276 | Maydan Wardak Demining Project-13 |  |  |  |  | 1400 |  | {453B0603-4D1E-4220-8134-A7EA8C7CFC37} |  | Low | Agriculture Blocked | Low | 143 | CHA | 5 |  |  | 2013-06-11 16:30 | No | Open
Central | Maydan Wardak | Hisa-I- Awali Bihsud | Barikak | {453B0603-4D1E-4220-8134-A7EA8C7CFC37} | c0a8-0057-12c3bb63cd8-57ab4f4c-3c2e3- | MF-HQ-12628 | MCPA - Mine Clearance Planning Agency | AF/0403/3282/MF0003 | 29846 | 68.2988 | 34.4764 | Open | AP Only | AP Only | MineField |  | MBT Project-016 | Maydan Wardak Demining Project-10 |  |  |  |  | 1395 |  | {453B0603-4D1E-4220-8134-A7EA8C7CFC37} |  | Medium | Critical Infrastracture | Low | 219 | CHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Hisa-I- Awali Bihsud | Bursanak | {370C54B3-38B6-4125-A58D-913C2B0A1E66} | c0a8-00f6-1355b526116-5060e849-d5c-4a | MF-16685 | MCPA - Mine Clearance Planning Agency | AF/2802/03202/MF2054 | 30304 | 68.2061 | 34.4841 | Open | AP Only | AP Only | MineField |  | MBT Project-276 | Maydan Wardak Demining Project-13 |  |  |  |  | 1400 |  | {370C54B3-38B6-4125-A58D-913C2B0A1E66} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2000-07-13 16:30 | No | Open
Central | Maydan Wardak | Hisa-I- Awali Bihsud | Chelemjay | {A40D3BDE-071B-43EE-A73B-E499C990B5AC} | c0a8-0009-13fb7abeb88-b650c972-5853-b | Hz-ID-18006 | MCPA - Mine Clearance Planning Agency | AF/0403/03292/MF0013 | 14536 | 68.3158 | 34.4742 | Open | AP Only | AP Only | MineField |  | MBT Project-276 | Maydan Wardak Demining Project-13 |  |  |  |  | 1400 |  | {A40D3BDE-071B-43EE-A73B-E499C990B5AC} |  | Low | Agriculture Blocked | Low | 34 | CHA | 5 |  |  | 2013-05-25 16:30 | No | Open
Central | Maydan Wardak | Hisa-I- Awali Bihsud | Chelemjay | {A40D3BDE-071B-43EE-A73B-E499C990B5AC} | c0a8-0057-12c3b8b2dca-ba1c4a42-214db- | MF-HQ-12302 | MCPA - Mine Clearance Planning Agency | AF/0403/03292/MF0011 | 212158 | 68.3063 | 34.4731 | Open | AP Only | AP Only | MineField |  | MBT Project-276 | Maydan Wardak Demining Project-13 |  |  |  |  | 1400 |  | {A40D3BDE-071B-43EE-A73B-E499C990B5AC} |  | Low | Agriculture Blocked | Low | 67 | CHA | 5 |  |  | 2009-07-23 | No | Open
Central | Maydan Wardak | Hisa-I- Awali Bihsud | Jawqol | {A35381BD-AB09-4842-B34D-CCA2C7D9A688} | c0a8-008e-132a002c257-5a545dd1-1e-b15 | MF-HQ-12214 | HT - HALO TRUST | H/2053 | 150000 | 68.3008 | 34.4789 | Open | AP Only | AP Only | MineField |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {A35381BD-AB09-4842-B34D-CCA2C7D9A688} |  | Medium | Critical Infrastracture | Low | 61 | CHA | 3 |  |  | 2000-07-09 | No | Open
Central | Maydan Wardak | Hisa-I- Awali Bihsud | Qash | {11C9C33E-52BB-435B-B086-C6E9AC122A76} | c0a8-0009-13fe134fb26-501d455-34e1-8a | Hz-ID-18004 | MCPA - Mine Clearance Planning Agency | AF/0403/03283/BF0012 | 2259 | 68.27 | 34.4845 | Open | UXO Only | UXO Only | BF |  | MBT Project-016 | Maydan Wardak Demining Project-10 |  |  |  |  | 1395 |  | {11C9C33E-52BB-435B-B086-C6E9AC122A76} |  | Medium | Agriculture Blocked | Low | 30 | CHA | 3 |  |  | 2013-05-13 16:30 | No | Open
Central | Maydan Wardak | Hisa-I- Awali Bihsud | Qash | {11C9C33E-52BB-435B-B086-C6E9AC122A76} | c0a8-0057-12c3baa4781-23dfebce-351d2- | MF-HQ-12313 | MCPA - Mine Clearance Planning Agency | AF/0403/03284/MF2049 | 64522 | 68.2648 | 34.4847 | Open | AP Only | AP Only | MineField |  | MBT Project-016 | Maydan Wardak Demining Project-10 |  |  |  |  | 1395 |  | {11C9C33E-52BB-435B-B086-C6E9AC122A76} |  | Medium | Critical Infrastracture | Low | 36 | CHA | 3 |  |  | 2000-07-09 16:30 | No | Open
Central | Maydan Wardak | Hisa-I- Awali Bihsud | Qash | {11C9C33E-52BB-435B-B086-C6E9AC122A76} | c0a8-008e-132a008273f-1b42cd38-63-8d1 | MF-HQ-14002 | MCPA - Mine Clearance Planning Agency | AF/0403/03283/MF2051 | 104399 | 68.2701 | 34.4846 | Open | AP Only | AP Only | MineField |  | MBT Project-276 | Maydan Wardak Demining Project-13 |  |  |  |  | 1400 |  | {11C9C33E-52BB-435B-B086-C6E9AC122A76} |  | Low | Critical Infrastracture | Low | 23 | CHA | 5 |  |  | 2000-07-09 | No | Open
Central | Maydan Wardak | Jaghatu | Mola | {88CEBC70-9D3A-47DB-A29F-1535791DCFBE} | c0a8-0057-12c3b87254c-f33cf4a0-1e7fb- | MF-HQ-11471 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0603/03604/MF0001 | 80000 | 68.4362 | 33.9373 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {88CEBC70-9D3A-47DB-A29F-1535791DCFBE} |  | Low | Critical Infrastracture | Substantial | 277 | SHA | 4 |  |  | 2009-07-27 | No | Open
Central | Maydan Wardak | Jaghatu | Mola | {88CEBC70-9D3A-47DB-A29F-1535791DCFBE} | c0a8-0057-12c3b8a9a34-1186ece9-20e84- | MF-HQ-12359 | HT - HALO TRUST | H/2060 | 90000 | 68.4257 | 33.9297 | Open | AT Only | AT Only | MineField |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {88CEBC70-9D3A-47DB-A29F-1535791DCFBE} |  | Medium | Critical Infrastracture | Substantial | 209 | CHA | 3 |  |  | 2000-08-12 16:30 | No | Open
Central | Maydan Wardak | Jaghatu | Moradkhan | {580991A1-A14F-4A67-9E23-F49CE6ABFEE3} | c0a8-0057-12c3b717ec9-245d6074-ee45-e | MF-HQ-12312 | HT - HALO TRUST | H/2061 | 250000 | 68.2458 | 33.809 | Open | AT Only | AT Only | MineField |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {580991A1-A14F-4A67-9E23-F49CE6ABFEE3} |  | Low | Agriculture Blocked | Substantial | 81 | CHA | 5 |  |  | 2000-08-16 16:30 | No | Open
Central | Maydan Wardak | Jaghatu | Moradkhan | {580991A1-A14F-4A67-9E23-F49CE6ABFEE3} | c0a8-008e-132a00993b2-1377215b-75-d5e | MF-HQ-12356 | HT - HALO TRUST | H/2059 | 50000 | 68.4454 | 33.7982 | Open | AT Only | AT Only | MineField |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {580991A1-A14F-4A67-9E23-F49CE6ABFEE3} |  | Low | Critical Infrastracture | Substantial | 20 | CHA | 5 |  |  | 2000-08-13 16:30 | No | Open
Central | Maydan Wardak | Jaghatu | Pyadarah | {FC7FCC7B-89D8-420F-9723-6ADA5583DACD} | c0a8-0057-12c3b8a6051-ad5a0f92-20c0c- | MF-HQ-11469 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0603/03515/MF0002 | 120450 | 68.345 | 33.6889 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {FC7FCC7B-89D8-420F-9723-6ADA5583DACD} |  | Low | Agriculture Blocked | Substantial | 27 | SHA | 5 |  |  | 2009-07-27 | No | Open
Central | Maydan Wardak | Jaghatu | Pyadarah | {FC7FCC7B-89D8-420F-9723-6ADA5583DACD} | c0a8-0057-12c3ba40c84-e52bd5f3-3164b- | MF-HQ-11470 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0603/03515/MF0003 | 98000 | 68.3447 | 33.6856 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {FC7FCC7B-89D8-420F-9723-6ADA5583DACD} |  | Low | Agriculture Blocked | Substantial | 558 | SHA | 4 |  |  | 2009-07-27 | No | Open
Central | Maydan Wardak | Jalrez | Ahangaran | {97054003-A356-4A7E-97C4-2C915BECDE05} | c0a8-0057-12c3b890144-dcef531e-1fd11- | MF-HQ-11545 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02243/MF0007 | 53970 | 68.6397 | 34.5035 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-192 | Maydan Wardak Demining Project-07 |  |  |  |  | 1397 |  | {97054003-A356-4A7E-97C4-2C915BECDE05} |  | Medium | Critical Infrastracture | Moderate | 47 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Alakhel | {F32B0B82-A0F4-4E5F-A702-958AAC27DCD5} | c0a8-0057-12c3baa16e0-5c731044-35063- | MF-HQ-11546 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02250/MF0003 | 19053 | 68.6958 | 34.4687 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-195 | Maydan Wardak Demining Project-11 |  |  |  |  | 1397 |  | {F32B0B82-A0F4-4E5F-A702-958AAC27DCD5} |  | Low | Agriculture Blocked | Moderate | 304 | SHA | 4 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Alakhel | {F32B0B82-A0F4-4E5F-A702-958AAC27DCD5} | c0a8-0057-12c3bb30943-95524e4c-3a537- | MF-HQ-11547 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02250/MF0004 | 114050 | 68.6897 | 34.4567 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-192 | Maydan Wardak Demining Project-07 |  |  |  |  | 1397 |  | {F32B0B82-A0F4-4E5F-A702-958AAC27DCD5} |  | Medium | Agriculture Blocked | Moderate | 226 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Baghalak | {B6519254-351F-410A-917A-910A409B3BC9} | c0a8-0057-12c3b863777-cb844d00-1dda2- | MF-HQ-11569 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02265/MF0012 | 73475 | 68.6428 | 34.5196 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-192 | Maydan Wardak Demining Project-07 |  |  |  |  | 1397 |  | {B6519254-351F-410A-917A-910A409B3BC9} |  | Medium | Critical Infrastracture | Moderate | 82 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Dara | {711565E1-956B-4D3B-819D-A50F1B7FCE83} | c0a8-0057-12c3b881218-1e6b4b7a-1f26e- | MF-HQ-11534 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02260/MF0006 | 249275 | 68.7329 | 34.5084 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {711565E1-956B-4D3B-819D-A50F1B7FCE83} |  | Low | Agriculture Blocked | Moderate | 3 | SHA | 5 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Dara | {711565E1-956B-4D3B-819D-A50F1B7FCE83} | c0a8-0057-12c3b913cf8-51197d2c-25656- | MF-HQ-11533 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02260/MF0005 | 310000 | 68.7566 | 34.4846 | Open | UXO Only | UXO Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {711565E1-956B-4D3B-819D-A50F1B7FCE83} |  | Medium | Agriculture Blocked | Moderate | 7 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Dara-I-Zyarat | {4ECFC727-3DB5-4733-B450-17BEBF3E8E87} | c0a8-0057-12c3b7d8cbe-3bd48638-17bbd- | MF-HQ-11527 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/32039/MF0014 | 110000 | 68.6815 | 34.489 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-192 | Maydan Wardak Demining Project-07 |  |  |  |  | 1397 |  | {4ECFC727-3DB5-4733-B450-17BEBF3E8E87} |  | Medium | Critical Infrastracture | Moderate | 0 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Dara-I-Zyarat | {4ECFC727-3DB5-4733-B450-17BEBF3E8E87} | c0a8-0057-12c3b856398-8d15d7c8-1d4ac- | MF-HQ-11528 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/32039/MF0015 | 36000 | 68.6813 | 34.4862 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-192 | Maydan Wardak Demining Project-07 |  |  |  |  | 1397 |  | {4ECFC727-3DB5-4733-B450-17BEBF3E8E87} |  | Medium | Critical Infrastracture | Moderate | 35 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Dara-I-Zyarat | {4ECFC727-3DB5-4733-B450-17BEBF3E8E87} | c0a8-0057-12c3b929918-e109d76b-2645c- | MF-HQ-11525 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/32039/MF0016 | 385312 | 68.6814 | 34.489 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-192 | Maydan Wardak Demining Project-07 |  |  |  |  | 1397 |  | {4ECFC727-3DB5-4733-B450-17BEBF3E8E87} |  | Medium | Critical Infrastracture | Moderate | 0 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Dara-I-Zyarat | {4ECFC727-3DB5-4733-B450-17BEBF3E8E87} | c0a8-0057-12c3b9421f1-56b20a40-274b8- | MF-HQ-11526 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/32039/MF0013 | 18000 | 68.6711 | 34.4761 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-192 | Maydan Wardak Demining Project-07 |  |  |  |  | 1397 |  | {4ECFC727-3DB5-4733-B450-17BEBF3E8E87} |  | Medium | Agriculture Blocked | Moderate | 28 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Dewgan | {DD210EE5-FF3E-489E-A3AF-0809074BDAC5} | c0a8-0057-12c3b834296-8dd099c3-1bbd5- | MF-HQ-11561 | HT - HALO TRUST | H/2064 | 80000 | 68.6137 | 34.4132 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-192 | Maydan Wardak Demining Project-07 |  |  |  |  | 1397 |  | {DD210EE5-FF3E-489E-A3AF-0809074BDAC5} |  | Medium | Critical Infrastracture | Moderate | 0 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Diwlan (2) | {037DC539-E53E-40EE-A656-307AA80E16AF} | c0a8-0009-13b83956cc1-ddf3ad93-481-f5 | MF-HQ-11550 | UNMACA - United Nation Mine Action Center for Afghanistan | H/2077 | 120000 | 68.6055 | 34.4679 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {037DC539-E53E-40EE-A656-307AA80E16AF} |  | High with Victim | High with Victims | Moderate | 141 | CHA | 2 |  |  | 2004-09-16 16:30 | No | Open
Central | Maydan Wardak | Jalrez | Diwlan (2) | {037DC539-E53E-40EE-A656-307AA80E16AF} | c0a8-0057-12c3b9c0897-78062315-2c75e- | MF-HQ-11549 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02224/MF0001 | 174647 | 68.5875 | 34.4846 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {037DC539-E53E-40EE-A656-307AA80E16AF} |  | High with Victim | High with Victims | Moderate | 117 | SHA | 2 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Esma'elkhel | {81CBA415-DF3A-4A55-BEC1-CB2AE6D2181E} | c0a8-0057-12c3b9f7744-52c09a0f-2e9a2- | MF-HQ-11543 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02255/MF0030 | 28500 | 68.7038 | 34.4671 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-195 | Maydan Wardak Demining Project-11 |  |  |  |  | 1397 |  | {81CBA415-DF3A-4A55-BEC1-CB2AE6D2181E} |  | Low | Agriculture Blocked | Moderate | 84 | SHA | 4 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Esma'elkhel | {81CBA415-DF3A-4A55-BEC1-CB2AE6D2181E} | c0a8-0057-12c3babd98e-ff77ec1d-36034- | MF-HQ-11540 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02255/MF0031 | 248738 | 68.7287 | 34.4793 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {81CBA415-DF3A-4A55-BEC1-CB2AE6D2181E} |  | Medium | Critical Infrastracture | Moderate | 70 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Esma'elkhel | {81CBA415-DF3A-4A55-BEC1-CB2AE6D2181E} | c0a8-0057-12c3bb0b205-ffce1b69-38edd- | MF-HQ-11541 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02255/MF0032 | 127100 | 68.7108 | 34.4681 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-195 | Maydan Wardak Demining Project-11 |  |  |  |  | 1397 |  | {81CBA415-DF3A-4A55-BEC1-CB2AE6D2181E} |  | Low | Agriculture Blocked | Moderate | 345 | SHA | 4 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Esma'elkhel | {81CBA415-DF3A-4A55-BEC1-CB2AE6D2181E} | c0a8-0057-12c3bb145f9-86e4656c-39469- | MF-HQ-11542 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02255/MF0029 | 46200 | 68.7155 | 34.4685 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-195 | Maydan Wardak Demining Project-11 |  |  |  |  | 1397 |  | {81CBA415-DF3A-4A55-BEC1-CB2AE6D2181E} |  | Medium | Agriculture Blocked | Moderate | 413 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Esma'elkhel | {81CBA415-DF3A-4A55-BEC1-CB2AE6D2181E} | c0a8-0057-12e66aef5b6-5bee2a13-2a0-4e | MF-HQ-11544 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02255/MF0050 | 173250 | 68.7007 | 34.4529 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {81CBA415-DF3A-4A55-BEC1-CB2AE6D2181E} |  | Medium | Critical Infrastracture | Moderate | 264 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Ghundi Kalay | {B8102BCD-42B4-4419-997F-045070D76BFC} | c0a8-0057-12c3b87c39c-5d2c87dc-1ef11- | MF-HQ-11535 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02149/MF0049 | 188500 | 68.7478 | 34.4538 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-192 | Maydan Wardak Demining Project-07 |  |  |  |  | 1397 |  | {B8102BCD-42B4-4419-997F-045070D76BFC} |  | High with Victim | High with Victims | Moderate | 623 | SHA | 1 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Ghundi Kalay | {B8102BCD-42B4-4419-997F-045070D76BFC} | c0a8-0057-12c3bb6b31f-dfad2bd1-3c710- | MF-HQ-11536 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02149/MF0048 | 40000 | 68.7469 | 34.4608 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-195 | Maydan Wardak Demining Project-11 |  |  |  |  | 1397 |  | {B8102BCD-42B4-4419-997F-045070D76BFC} |  | High with Victim | High with Victims | Moderate | 301 | SHA | 1 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Honi | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} | c0a8-0057-12c3b7e0a16-9f1c72a5-1815c- | MF-HQ-11523 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/00764/MF0024 | 69861 | 68.4013 | 34.4511 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} |  | Medium | Critical Infrastracture | Moderate | 281 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Honi | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} | c0a8-0057-12c3b90d1be-4c106ed8-251f9- | MF-HQ-11521 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/00764/MF0025 | 5000 | 68.4318 | 34.454 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} |  | Medium | Agriculture Blocked | Moderate | 209 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Honi | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} | c0a8-0057-12c3b951ac6-4b436b63-27f10- | MF-HQ-11518 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/00764/MF0026 | 112725 | 68.469 | 34.4258 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} |  | Medium | Critical Infrastracture | Moderate | 28 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Honi | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} | c0a8-0057-12c3b993261-b1cb833d-2aa00- | MF-HQ-11517 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/00764/MF0021 | 100547 | 68.4339 | 34.4518 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} |  | Medium | Critical Infrastracture | Moderate | 105 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Honi | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} | c0a8-0057-12c3b9de68f-e2d967e8-2da44- | MF-HQ-11520 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/00764/MF0023 | 20508 | 68.4246 | 34.4525 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} |  | Medium | Critical Infrastracture | Moderate | 209 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Honi | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} | c0a8-0057-12c3bae0d93-6e7b68b5-37581- | MF-HQ-11519 | HT - HALO TRUST | H/2067 | 2500 | 68.4237 | 34.4349 | Open | AP Only | AP Only | MineField |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} |  | Medium | Critical Infrastracture | Moderate | 420 | CHA | 3 |  |  | 2004-09-18 16:30 | No | Open
Central | Maydan Wardak | Jalrez | Honi | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} | c0a8-0057-12c3bb673ee-3bd566ed-3c4dc- | MF-HQ-11522 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/00764/MF0022 | 165297 | 68.4709 | 34.4408 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {F3E340ED-0751-4685-B9E0-E471D5B5AD66} |  | Medium | Critical Infrastracture | Moderate | 1195 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Jagha'in | {91EADE71-A565-404A-A781-E55707F3B869} | c0a8-0057-12c3b6a272a-76200269-94ef-4 | MF-HQ-12141 | HT - HALO TRUST | H/2071 | 50000 | 68.5799 | 34.4244 | Open | AP Only | AP Only | MineField |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {91EADE71-A565-404A-A781-E55707F3B869} |  | High with Victim | High with Victims | Moderate | 33 | CHA | 2 |  |  | 2004-09-20 16:30 | No | Open
Central | Maydan Wardak | Jalrez | Jagha'in | {91EADE71-A565-404A-A781-E55707F3B869} | c0a8-0057-12c3b79398b-2b6315e9-149e8- | MF-HQ-12198 | HT - HALO TRUST | H/2069 | 42500 | 68.5805 | 34.441 | Open | AP Only | AP Only | MineField |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {91EADE71-A565-404A-A781-E55707F3B869} |  | High with Victim | High with Victims | Moderate | 603 | CHA | 2 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Jalrez | Jagha'in | {91EADE71-A565-404A-A781-E55707F3B869} | c0a8-0057-12c3b857821-456ba46c-1d599- | MF-HQ-11554 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02201/MF0034 | 21184 | 68.5839 | 34.4373 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {91EADE71-A565-404A-A781-E55707F3B869} |  | High with Victim | High with Victims | Moderate | 96 | SHA | 2 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Jagha'in | {91EADE71-A565-404A-A781-E55707F3B869} | c0a8-0057-12c3b98364e-6dd359a4-29f98- | MF-HQ-11555 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02201/MF0035 | 64400 | 68.5839 | 34.4373 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {91EADE71-A565-404A-A781-E55707F3B869} |  | High with Victim | High with Victims | Moderate | 616 | SHA | 2 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Jagha'in | {91EADE71-A565-404A-A781-E55707F3B869} | c0a8-0057-12c3b986e2d-39e7ea62-2a1bd- | MF-HQ-11556 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02201/MF0036 | 16800 | 68.5839 | 34.4374 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {91EADE71-A565-404A-A781-E55707F3B869} |  | High with Victim | High with Victims | Moderate | 603 | SHA | 2 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Jalrez | {03285883-7523-4112-A89C-35D4A9535AFD} | c0a8-0057-12c3b7193de-db5d4682-ef49-1 | MF-HQ-12155 | HT - HALO TRUST | H/2084 | 30000 | 68.6321 | 34.4592 | Open | AP Only | AP Only | MineField |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {03285883-7523-4112-A89C-35D4A9535AFD} |  | High with Victim | High with Victims | Moderate | 104 | CHA | 1 |  |  | 2004-09-16 16:30 | No | Open
Central | Maydan Wardak | Jalrez | Jalrez | {03285883-7523-4112-A89C-35D4A9535AFD} | c0a8-0057-12c3b74b26d-ffb7c21b-114c9- | MF-HQ-12154 | HT - HALO TRUST | H/2086 | 30000 | 68.6538 | 34.4519 | Open | AP Only | AP Only | MineField |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {03285883-7523-4112-A89C-35D4A9535AFD} |  | High with Victim | High with Victims | Moderate | 118 | CHA | 1 |  |  | 2004-09-15 16:30 | No | Open
Central | Maydan Wardak | Jalrez | Jalrez | {03285883-7523-4112-A89C-35D4A9535AFD} | c0a8-0057-12c3b7741e9-82eaf563-132f3- | MF-HQ-12153 | HT - HALO TRUST | H/2083 | 7500 | 68.6341 | 34.4545 | Open | AP Only | AP Only | MineField |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {03285883-7523-4112-A89C-35D4A9535AFD} |  | High with Victim | High with Victims | Moderate | 9 | CHA | 1 |  |  | 2004-09-16 16:30 | No | Open
Central | Maydan Wardak | Jalrez | Jalrez | {03285883-7523-4112-A89C-35D4A9535AFD} | c0a8-0057-12c3b8a7853-e5b90100-20d34- | MF-HQ-11563 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02231/MF0010 | 8400 | 68.6492 | 34.4811 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {03285883-7523-4112-A89C-35D4A9535AFD} |  | High with Victim | High with Victims | Moderate | 247 | SHA | 1 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Jalrez | {03285883-7523-4112-A89C-35D4A9535AFD} | c0a8-0057-12c3b8b7d40-4f546555-2184e- | MF-HQ-11564 | HT - HALO TRUST | H/2081 | 150000 | 68.6583 | 34.4756 | Open | AP Only | AP Only | MineField |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {03285883-7523-4112-A89C-35D4A9535AFD} |  | High with Victim | High with Victims | Moderate | 1020 | CHA | 1 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Kalacha | {6B61CCC3-D387-4EE5-AF5E-E7960318B486} | c0a8-0057-12c3bb2fed7-b85a335f-3a4d1- | MF-HQ-11572 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02234/MF0047 | 122496 | 68.647 | 34.4695 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {6B61CCC3-D387-4EE5-AF5E-E7960318B486} |  | Medium | Critical Infrastracture | Moderate | 3104 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Kharoti | {5628AB97-30F6-45B4-BD81-0C3711E8FC46} | c0a8-0057-12c3b7fe42a-8a9b7532-195db- | MF-HQ-11529 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02240/MF0019 | 20000 | 68.6329 | 34.4858 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-195 | Maydan Wardak Demining Project-11 |  |  |  |  | 1397 |  | {5628AB97-30F6-45B4-BD81-0C3711E8FC46} |  | High with Victim | High with Victims | Moderate | 339 | SHA | 4 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Kharoti | {5628AB97-30F6-45B4-BD81-0C3711E8FC46} | c0a8-0057-12c3b92e521-df9277fa-2677a- | MF-HQ-11530 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02240/MF0017 | 42900 | 68.633 | 34.4859 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {5628AB97-30F6-45B4-BD81-0C3711E8FC46} |  | High with Victim | High with Victims | Moderate | 75 | SHA | 5 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Kharoti | {5628AB97-30F6-45B4-BD81-0C3711E8FC46} | c0a8-0057-12c3bb3226d-9e280745-3a62d- | MF-HQ-11531 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02240/MF0018 | 102375 | 68.6396 | 34.4885 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {5628AB97-30F6-45B4-BD81-0C3711E8FC46} |  | High with Victim | High with Victims | Moderate | 92 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Qal'eh-ye-Malek | {2F2F10C1-00C4-4678-80AD-AD613EEBF59E} | c0a8-0057-12c3bae6bd8-bb7d23c4-3792b- | MF-HQ-11560 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02220/MF 0039 | 3058 | 68.584 | 34.4508 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {2F2F10C1-00C4-4678-80AD-AD613EEBF59E} |  | Medium | Critical Infrastracture | Moderate | 0 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Qal'eh-ye-Malek | {2F2F10C1-00C4-4678-80AD-AD613EEBF59E} | c0a8-0057-12c3bb15110-9c85c189-394c5- | MF-HQ-11559 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02220/MF0038 | 740 | 68.5831 | 34.4629 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-195 | Maydan Wardak Demining Project-11 |  |  |  |  | 1397 |  | {2F2F10C1-00C4-4678-80AD-AD613EEBF59E} |  | Medium | Comunity Centers | Moderate | 231 | SHA | 4 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Qole Baba | {BF1297AA-E558-411A-BF1F-1CD6D1415F88} | c0a8-0057-12c3b82cf7b-28617dac-1b6d4- | MF-HQ-11575 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02223/MF0009 | 151200 | 68.5577 | 34.4649 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {BF1297AA-E558-411A-BF1F-1CD6D1415F88} |  | High with Victim | High with Victims | Moderate | 78 | SHA | 2 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Qol-e Dosti | {48E7C3C1-7D49-4F73-A969-9CF7B4DF772B} | c0a8-0057-12c3bb42d34-3528e505-3b01a- | MF-HQ-11467 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02239/MF0037 | 10500 | 68.6416 | 34.4865 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {48E7C3C1-7D49-4F73-A969-9CF7B4DF772B} |  | Medium | Critical Infrastracture | Moderate | 65 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Rahimkhel | {9A3A0E3E-4366-45A8-8DAA-5B51141EBFD9} | c0a8-0057-12c3badd46b-2d13cc8f-37396- | MF-HQ-11532 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02150/MF0027 | 264000 | 68.7545 | 34.4667 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {9A3A0E3E-4366-45A8-8DAA-5B51141EBFD9} |  | Medium | Critical Infrastracture | Moderate | 701 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Sange Polak | {6D1FE222-C1C7-4942-90F2-B329A740B3E0} | c0a8-0057-12c3b8f3ea1-bb5ee3d3-241c0- | MF-HQ-11552 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02228/MF0044 | 78155 | 68.6408 | 34.5084 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {6D1FE222-C1C7-4942-90F2-B329A740B3E0} |  | Medium | Critical Infrastracture | Moderate | 308 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Sange Polak | {6D1FE222-C1C7-4942-90F2-B329A740B3E0} | c0a8-0057-12c3bb76896-86aea78c-3cd37- | MF-HQ-11551 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02228/MF0045 | 43316 | 68.6392 | 34.5079 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {6D1FE222-C1C7-4942-90F2-B329A740B3E0} |  | Medium | Critical Infrastracture | Moderate | 409 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Sanglakh | {1909115A-3324-4898-9FE0-4460027E5F96} | c0a8-0057-12c3b70bc37-92767d42-e51c-6 | MF-HQ-12181 | HT - HALO TRUST | H/2087 | 40000 | 68.8006 | 34.5986 | Open | AP Only | AP Only | MineField |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {1909115A-3324-4898-9FE0-4460027E5F96} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2004-09-14 16:30 | No | Open
Central | Maydan Wardak | Jalrez | Sanglakh | {1909115A-3324-4898-9FE0-4460027E5F96} | c0a8-0057-12c3bb40145-8df39e77-3ae7a- | MF-HQ-11553 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02268/MF0046 | 90336 | 68.674 | 34.5561 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {1909115A-3324-4898-9FE0-4460027E5F96} |  | Medium | Critical Infrastracture | Moderate | 72 | SHA | 3 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Sehqala | {C39BDF76-88A9-49C7-80D9-EFD49CD55ED1} | c0a8-0057-12c3b6beff0-d28291f7-aaa3-a | MF-HQ-12151 | HT - HALO TRUST | H/2085 | 22500 | 68.6635 | 34.451 | Open | AP Only | AP Only | MineField |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {C39BDF76-88A9-49C7-80D9-EFD49CD55ED1} |  | Low | Agriculture Blocked | Moderate | 58 | CHA | 5 |  |  | 2004-09-15 16:30 | No | Open
Central | Maydan Wardak | Jalrez | Takana | {36F43E0D-63D0-460F-8EE4-4B3FEEC674A2} | c0a8-0057-12c3b6c9764-214e942-b29b-9d | MF-HQ-12142 | HT - HALO TRUST | H/2089 | 116640 | 68.5684 | 34.457 | Open | AP Only | AP Only | MineField |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {36F43E0D-63D0-460F-8EE4-4B3FEEC674A2} |  | High with Victim | High with Victims | Moderate | 349 | CHA | 2 |  |  | 2004-09-20 | No | Open
Central | Maydan Wardak | Jalrez | Takana | {36F43E0D-63D0-460F-8EE4-4B3FEEC674A2} | c0a8-0057-12c3ba26081-2a4f3d36-30603- | MF-HQ-11558 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/00160/MF0041 | 42750 | 68.5845 | 34.4402 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {36F43E0D-63D0-460F-8EE4-4B3FEEC674A2} |  | High with Victim | High with Victims | Moderate | 129 | SHA | 2 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Takana | {36F43E0D-63D0-460F-8EE4-4B3FEEC674A2} | c0a8-0057-12c3ba56116-ba360b7e-32357- | MF-HQ-11557 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/00160/MF0040 | 90500 | 68.5741 | 34.4535 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {36F43E0D-63D0-460F-8EE4-4B3FEEC674A2} |  | High with Victim | High with Victims | Moderate | 102 | SHA | 2 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Jalrez | Tazagul Kala | {3193D98E-EB5E-43A8-93C3-FF016EE8D687} | c0a8-0057-12c3b80601c-24e06c91-19b21- | MF-HQ-11566 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02235/MF0043 | 48204 | 68.6472 | 34.4601 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {3193D98E-EB5E-43A8-93C3-FF016EE8D687} |  | Medium | Critical Infrastracture | Moderate | 306 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Tazagul Kala | {3193D98E-EB5E-43A8-93C3-FF016EE8D687} | c0a8-0057-12c3ba176f1-4887dff2-2fd4d- | MF-HQ-11565 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02235/MF0042 | 142336 | 68.644 | 34.4621 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-193 | Maydan Wardak Demining Project-08 |  |  |  |  | 1398 |  | {3193D98E-EB5E-43A8-93C3-FF016EE8D687} |  | Medium | Agriculture Blocked | Moderate | 126 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Jalrez | Tesha | {F0C5E9B6-BA63-47EC-90FA-40C1B581EC46} | c0a8-0057-12c3ba217ee-4aabfaef-30385- | MF-HQ-11537 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0402/02155/MF0008 | 463000 | 68.7504 | 34.4724 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {F0C5E9B6-BA63-47EC-90FA-40C1B581EC46} |  | High with Victim | High with Victims | Moderate | 308 | SHA | 2 |  |  | 2009-07-16 | No | Open
Central | Maydan Wardak | Maydan Shahr | Ahmadza'i | {F8BC4E02-1672-436F-B09B-8CF9A52F8F8A} | c0a8-008e-131180e2d3a-3f54fb3f-309-c4 | MF-HQ-12470 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02164/MF0190 | 400 | 68.8132 | 34.4431 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {F8BC4E02-1672-436F-B09B-8CF9A52F8F8A} |  | High | Critical Infrastracture | Moderate | 172 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Amar Khail | {0995308A-E612-40FF-93BE-729585245206} | c0a8-008e-131135424c7-7cfc24a6-1d05-1 | MF-HQ-12451 | MDC - Mine Detection and Dog Center | AF/0401/00022/MF0077 | 21484 | 68.8525 | 34.3739 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-142 | Maydan Wardak Demining Project-01 | B-Japan | Yes |  |  | 1393 | MDC | {0995308A-E612-40FF-93BE-729585245206} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 2 |  |  | 2009-07-15 | No | Planned
Central | Maydan Wardak | Maydan Shahr | Amar Khail | {0995308A-E612-40FF-93BE-729585245206} | c0a8-008e-1311783d794-2b73f5b9-28e4-e | MF-HQ-12449 | MDC - Mine Detection and Dog Center | AF/0401/00022/MF0078 | 50000 | 68.8552 | 34.3687 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-142 | Maydan Wardak Demining Project-01 | B-Japan | Yes |  |  | 1393 | MDC | {0995308A-E612-40FF-93BE-729585245206} |  | High with Victim | High with Victims | Moderate | 99 | CHA | 2 |  |  | 2009-07-15 | No | Planned
Central | Maydan Wardak | Maydan Shahr | Amar Khail | {0995308A-E612-40FF-93BE-729585245206} | c0a8-008e-131178eb9fc-53c12574-2a98-7 | MF-HQ-12452 | MDC - Mine Detection and Dog Center | AF/0401/00022/MF0076 | 18903 | 68.8498 | 34.3738 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-142 | Maydan Wardak Demining Project-01 | B-Japan | Yes |  |  | 1393 | MDC | {0995308A-E612-40FF-93BE-729585245206} |  | High with Victim | High with Victims | Moderate | 181 | CHA | 2 |  |  | 2009-07-15 | No | Planned
Central | Maydan Wardak | Maydan Shahr | Awulkhel | {59DBA0B7-30CD-497A-924B-D362DF1B0BFF} | c0a8-008e-131177d6f68-751e8e2d-2855-a | MF-HQ-12604 | MDC - Mine Detection and Dog Center | AF/0401/02138/MF0083 | 44454 | 68.8857 | 34.3578 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-142 | Maydan Wardak Demining Project-01 | B-Japan | Yes |  |  | 1393 | MDC | {59DBA0B7-30CD-497A-924B-D362DF1B0BFF} |  | High with Victim | High with Victims | Moderate | 145 | CHA | 2 |  |  | 2009-07-05 | No | Planned
Central | Maydan Wardak | Maydan Shahr | Awulkhel | {59DBA0B7-30CD-497A-924B-D362DF1B0BFF} | c0a8-008e-1311801ee4e-d59ac7c4-130-a2 | MF-HQ-12603 | MDC - Mine Detection and Dog Center | AF/0401/02138/MF0082 | 114522 | 68.8528 | 34.3572 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-142 | Maydan Wardak Demining Project-01 | B-Japan | Yes |  |  | 1393 | MDC | {59DBA0B7-30CD-497A-924B-D362DF1B0BFF} |  | High with Victim | High with Victims | Moderate | 125 | CHA | 2 |  |  | 2009-07-05 | No | Planned
Central | Maydan Wardak | Maydan Shahr | Baladeh | {BBAE031E-8C5C-4024-8935-D50A46DE9DF2} | c0a8-008e-13117880651-fc03d5e3-2975-a | MF-HQ-11548 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02160/MF0066 | 98208 | 68.7896 | 34.4851 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {BBAE031E-8C5C-4024-8935-D50A46DE9DF2} |  | Medium | Critical Infrastracture | Moderate | 91 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Burj | {6A4DFD65-D21C-49E1-9398-3DBC900B42D0} | c0a8-008e-13117926173-17d20f49-2b1e-1 | MF-HQ-12448 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02164/MF0061 | 53975 | 68.8142 | 34.5105 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {6A4DFD65-D21C-49E1-9398-3DBC900B42D0} |  | Medium | Critical Infrastracture | Moderate | 71 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Busraq | {EAA6F51E-E939-4082-89C2-72E71FFD85AA} | c0a8-0009-14400e6bd54-b133f13b-8d90-1 | Hz-ID-18445 | MCPA - Mine Clearance Planning Agency | AF/0401/02139/MF0194 | 50000 | 68.8087 | 34.4498 | Open | AP Only | AP Only | MineField |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {EAA6F51E-E939-4082-89C2-72E71FFD85AA} |  | Low | Agriculture Blocked | Moderate | 574 | CHA | 4 |  |  | 2013-12-29 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Busraq | {EAA6F51E-E939-4082-89C2-72E71FFD85AA} | c0a8-0009-1440193e39f-c0efe293-9-1a8d | Hz-ID-18443 | MCPA - Mine Clearance Planning Agency | AF/0401/02139/MF0192 | 86633 | 68.8189 | 34.4543 | Open | AP Only | AP Only | MineField |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {EAA6F51E-E939-4082-89C2-72E71FFD85AA} |  | Medium | Critical Infrastracture | Moderate | 262 | CHA | 3 |  |  | 2013-12-28 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Busraq | {EAA6F51E-E939-4082-89C2-72E71FFD85AA} | c0a8-0009-1440199a3e8-52bf12de-11b-38 | Hz-ID-18444 | MCPA - Mine Clearance Planning Agency | AF/0401/02139/MF0193 | 100000 | 68.8189 | 34.4543 | Open | AP Only | AP Only | MineField |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {EAA6F51E-E939-4082-89C2-72E71FFD85AA} |  | Medium | Critical Infrastracture | Moderate | 227 | CHA | 3 |  |  | 2013-12-28 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Ghundakhel | {D46D5258-5753-4AA9-888D-6AAD3702A6A8} | c0a8-008e-13112f4a27e-2b08932c-1a70-b | MF-HQ-11465 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02397/MF0071 | 157675 | 68.83 | 34.3837 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {D46D5258-5753-4AA9-888D-6AAD3702A6A8} |  | Medium | Critical Infrastracture | Moderate | 2261 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Ghundakhel | {D46D5258-5753-4AA9-888D-6AAD3702A6A8} | c0a8-008e-1311782bfe4-62c8085-28d4-10 | MF-HQ-11464 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02397/MF0072 | 246 | 68.8305 | 34.3786 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {D46D5258-5753-4AA9-888D-6AAD3702A6A8} |  | High | Critical Infrastracture | Moderate | 1731 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Ibrahim Khel | {FC19196F-1088-42F3-9419-E0A9A7770012} | c0a8-0009-147c9bcbcd4-c4c62b08-17b6-7 | Hz-ID-18893 | MCPA - Mine Clearance Planning Agency | AF/0401/32023/MF0202 | 58848 | 68.8617 | 34.3431 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {FC19196F-1088-42F3-9419-E0A9A7770012} |  | Low | Agriculture Blocked | Moderate | 9 | CHA | 5 |  |  | 2014-06-01 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Ibrahim Khel | {FC19196F-1088-42F3-9419-E0A9A7770012} | c0a8-0009-147c9c0bdf6-3819b9a5-1bcf-f | Hz-ID-18895 | MCPA - Mine Clearance Planning Agency | AF/0401/32023/MF0203 | 39915 | 68.8617 | 34.3431 | Open | AP Only | AP Only | MineField |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {FC19196F-1088-42F3-9419-E0A9A7770012} |  | Low | Agriculture Blocked | Moderate | 9 | CHA | 5 |  |  | 2014-06-03 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Ibrahim Khel | {FC19196F-1088-42F3-9419-E0A9A7770012} | c0a8-004c-13006cad3a7-882c992d-c04-18 | MF-HQ-12469 | MCPA - Mine Clearance Planning Agency | AF/0401/32023/MF0080 | 68884 | 68.8613 | 34.3437 | Open | AP Only | AP Only | MineField |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {FC19196F-1088-42F3-9419-E0A9A7770012} |  | Medium | Agriculture Blocked | Moderate | 15 | CHA | 5 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Jendekhel | {8F1CF570-27D2-4756-8F8E-4D7C97BFD24B} | c0a8-0057-12c3b743083-63c488d7-10eca- | MF-HQ-12201 | HT - HALO TRUST | H/2095 | 20000 | 68.7707 | 34.4678 | Open | AP Only | AP Only | MineField |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {8F1CF570-27D2-4756-8F8E-4D7C97BFD24B} |  | Low | Agriculture Blocked | Moderate | 802 | CHA | 5 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Maydan Shahr | Kharuti | {4654A346-952B-4143-BC1E-CC290622CCF0} | c0a8-008e-1311785d1f2-4d6295b9-2946-5 | MF-HQ-12476 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02130/MF 0062 | 375925 | 68.8081 | 34.4292 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {4654A346-952B-4143-BC1E-CC290622CCF0} |  | Medium | Agriculture Blocked | Moderate | 1159 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Kowt-e Ashrow | {12B8D3A9-D17B-4EAD-9A2E-65582B24AED8} | c0a8-008e-13112f79bde-2f7e6781-1b4a-3 | MF-HQ-12454 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02134/MF0058 | 186405 | 68.8005 | 34.4499 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {12B8D3A9-D17B-4EAD-9A2E-65582B24AED8} |  | High with Victim | High with Victims | Moderate | 204 | SHA | 2 |  |  | 2009-07-15 | No | Open
Central | Maydan Wardak | Maydan Shahr | Kowt-e Ashrow | {12B8D3A9-D17B-4EAD-9A2E-65582B24AED8} | c0a8-008e-13113df91a1-e65c8bb1-2559-1 | MF-HQ-12457 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02134/MF0060 | 312945 | 68.8044 | 34.4439 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {12B8D3A9-D17B-4EAD-9A2E-65582B24AED8} |  | High with Victim | High with Victims | Moderate | 1564 | SHA | 2 |  |  | 2009-07-15 | No | Open
Central | Maydan Wardak | Maydan Shahr | Kowt-e Ashrow | {12B8D3A9-D17B-4EAD-9A2E-65582B24AED8} | c0a8-008e-13117852c34-ccb1e8e0-2925-6 | MF-HQ-12459 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02134/MF0059 | 34300 | 68.7713 | 34.4536 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {12B8D3A9-D17B-4EAD-9A2E-65582B24AED8} |  | High with Victim | High with Victims | Moderate | 885 | SHA | 2 |  |  | 2009-07-15 | No | Open
Central | Maydan Wardak | Maydan Shahr | Kunda | {2BD785E4-168E-48DB-B520-594C23CABE2A} | c0a8-008e-13112f3293f-f295102a-1a05-5 | MF-HQ-11524 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02165/MF0068 | 62900 | 68.8193 | 34.5228 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {2BD785E4-168E-48DB-B520-594C23CABE2A} |  | Medium | Critical Infrastracture | Moderate | 66 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Kunda | {2BD785E4-168E-48DB-B520-594C23CABE2A} | c0a8-008e-13112f5520b-db61b3e0-1b0e-f | MF-HQ-11538 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02165/MF0069 | 68400 | 68.8193 | 34.5228 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {2BD785E4-168E-48DB-B520-594C23CABE2A} |  | Medium | Critical Infrastracture | Moderate | 73 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Kunda | {2BD785E4-168E-48DB-B520-594C23CABE2A} | c0a8-008e-1311808fb1a-914e9327-223-c4 | MF-HQ-11539 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02165/MF0067 | 52762 | 68.8193 | 34.5228 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {2BD785E4-168E-48DB-B520-594C23CABE2A} |  | Medium | Critical Infrastracture | Moderate | 139 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Lewan | {B7D9CC30-AD97-41D8-AB11-13B7124B33D1} | c0a8-0009-147c9c481fa-e81cdc74-204f-d | Hz-ID-18896 | MCPA - Mine Clearance Planning Agency | AF/0401/02161/MF0206 | 24748 | 68.8487 | 34.4501 | Open | AP Only | AP Only | MineField |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {B7D9CC30-AD97-41D8-AB11-13B7124B33D1} |  | Low | Agriculture Blocked | Moderate | 23 | CHA | 5 |  |  | 2014-06-01 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Lewan | {B7D9CC30-AD97-41D8-AB11-13B7124B33D1} | c0a8-0057-12c3b8548b9-5c4f545b-1d373- | MF-HQ-12442 | MCPA - Mine Clearance Planning Agency | AF/0401/02186/MF0075 | 81465 | 68.8321 | 34.4575 | Open | AT Only | AT Only | MineField |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {B7D9CC30-AD97-41D8-AB11-13B7124B33D1} |  | Medium | Critical Infrastracture | Moderate | 216 | CHA | 3 |  |  | 2009-07-15 | No | Open
Central | Maydan Wardak | Maydan Shahr | Lewan | {B7D9CC30-AD97-41D8-AB11-13B7124B33D1} | c0a8-008e-1311806c01f-f3f423b8-1e1-97 | MF-HQ-12441 | MCPA - Mine Clearance Planning Agency | AF/0401/02186/MF0074 | 348722 | 68.8522 | 34.4542 | Open | AP Only | AP Only | MineField |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {B7D9CC30-AD97-41D8-AB11-13B7124B33D1} |  | Medium | Critical Infrastracture | Moderate | 205 | CHA | 3 |  |  | 2009-07-15 | No | Open
Central | Maydan Wardak | Maydan Shahr | Mamaki | {0332A52D-6937-4F40-BA69-3E1499D6000E} | c0a8-008e-13117a06fa0-a5e143-2c41-72f | MF-HQ-11466 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02254/MF0081 | 190400 | 68.7468 | 34.4519 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {0332A52D-6937-4F40-BA69-3E1499D6000E} |  | Medium | Critical Infrastracture | Moderate | 245 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Mamikhel | {77141773-4F19-4025-8E72-B4A196EE2B58} | c0a8-0009-14400e952b9-5f127654-8dae-3 | Hz-ID-18447 | MCPA - Mine Clearance Planning Agency | AF/0408/02394/MF0196 | 40000 | 68.8246 | 34.394 | Open | AP Only | AP Only | MineField |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {77141773-4F19-4025-8E72-B4A196EE2B58} |  | High with Victim | High with Victims | Moderate | 643 | CHA | 1 |  |  | 2013-12-29 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Mamikhel | {77141773-4F19-4025-8E72-B4A196EE2B58} | c0a8-0009-14401aec15e-b0c5bed9-3a6-3e | Hz-ID-18446 | MCPA - Mine Clearance Planning Agency | AF/0408/02394/MF0195 | 90000 | 68.8136 | 34.394 | Open | AP Only | AP Only | MineField |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {77141773-4F19-4025-8E72-B4A196EE2B58} |  | High with Victim | High with Victims | Moderate | 59 | CHA | 1 |  |  | 2013-12-30 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Mamikhel | {77141773-4F19-4025-8E72-B4A196EE2B58} | c0a8-0009-144056c67f1-43833c55-17e5-7 | Hz-ID-18448 | MCPA - Mine Clearance Planning Agency | AF/0408/02394/MF0197 | 9997 | 68.8232 | 34.3983 | Open | AP Only | AP Only | MineField |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {77141773-4F19-4025-8E72-B4A196EE2B58} |  | High with Victim | High with Victims | Moderate | 610 | CHA | 1 |  |  | 2013-12-29 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Molakhel | {42E3AB18-0BDA-4B6C-A0BD-8AA4A51DEC20} | c0a8-0009-144019eb139-60e121eb-1b9-10 | Hz-ID-18449 | MCPA - Mine Clearance Planning Agency | AF/0401/02127/MF0198 | 90000 | 68.7672 | 34.451 | Open | AP Only | AP Only | MineField |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {42E3AB18-0BDA-4B6C-A0BD-8AA4A51DEC20} |  | High with Victim | High with Victims | Moderate | 1769 | CHA | 2 |  |  | 2013-12-30 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Molakhel | {42E3AB18-0BDA-4B6C-A0BD-8AA4A51DEC20} | c0a8-0009-14401aabe67-c9c39cfb-348-6b | Hz-ID-18450 | MCPA - Mine Clearance Planning Agency | AF/0401/02127/MF0199 | 90000 | 68.7728 | 34.4513 | Open | AP Only | AP Only | MineField |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {42E3AB18-0BDA-4B6C-A0BD-8AA4A51DEC20} |  | High with Victim | High with Victims | Moderate | 2201 | CHA | 2 |  |  | 2013-12-30 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Qal'eh-ye-Jabar | {21B5368C-73E6-4BC9-81F8-C9D24621D50D} | c0a8-008e-1311796db91-b7f4f3c4-2b81-d | MF-HQ-12462 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02162/MF0054 | 523710 | 68.814 | 34.5015 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {21B5368C-73E6-4BC9-81F8-C9D24621D50D} |  | High with Victim | High with Victims | Moderate | 78 | SHA | 2 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Qol | {FB8BD9B2-3216-45D7-9CAA-018DB32A0361} | c0a8-008e-131178ba9c3-70a9e0bd-29f8-6 | MF-HQ-12598 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02158/MF0073 | 69090 | 68.7843 | 34.5051 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {FB8BD9B2-3216-45D7-9CAA-018DB32A0361} |  | High with Victim | High with Victims | Moderate | 13 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Rustamkhel | {9B7163D2-0384-407D-A4BB-6E63ED736CF3} | c0a8-008e-13118098baf-2086f5c2-235-64 | MF-HQ-12040 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02133/MF0063 | 98424 | 68.8254 | 34.4593 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {9B7163D2-0384-407D-A4BB-6E63ED736CF3} |  | Medium | Critical Infrastracture | Moderate | 107 | SHA | 3 |  |  | 2009-07-15 | No | Open
Central | Maydan Wardak | Maydan Shahr | Shahqadam | {6056E746-D9B2-4F19-BF52-1F42FAF531D6} | c0a8-0009-144961650fd-68c9dacd-f3e-3c | Hz-ID-18510 | MCPA - Mine Clearance Planning Agency | AF/0401/02178/MF0201 | 19803 | 68.8735 | 34.4429 | Open | AT Only | AT Only | MineField |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {6056E746-D9B2-4F19-BF52-1F42FAF531D6} |  | Low | Comunity Centers | Moderate | 128 | CHA | 4 |  |  | 2014-01-06 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Shahqadam | {6056E746-D9B2-4F19-BF52-1F42FAF531D6} | c0a8-0009-1449616ed19-44299976-f70-8b | Hz-ID-18509 | MCPA - Mine Clearance Planning Agency | AF/0401/02178/MF0200 | 25787 | 68.8735 | 34.4429 | Open | AT Only | AT Only | MineField |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {6056E746-D9B2-4F19-BF52-1F42FAF531D6} |  | Low | Comunity Centers | Moderate | 184 | CHA | 4 |  |  | 2014-01-01 16:30 | No | Open
Central | Maydan Wardak | Maydan Shahr | Shahqadam | {6056E746-D9B2-4F19-BF52-1F42FAF531D6} | c0a8-0057-12c3b75c9b2-f4becada-121a2- | MF-HT-1242 | MCPA - Mine Clearance Planning Agency | AF/0401/02178/MF1711 | 99530 | 68.8716 | 34.4256 | Open | AP Only | AP Only | MineField |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {6056E746-D9B2-4F19-BF52-1F42FAF531D6} |  | Low | Agriculture Blocked | Moderate | 23 | CHA | 5 |  |  | 2006-11-01 | No | Open
Central | Maydan Wardak | Maydan Shahr | Shahqadam | {6056E746-D9B2-4F19-BF52-1F42FAF531D6} | c0a8-008e-131180288e6-4836fc14-142-c2 | MF-HQ-12445 | MCPA - Mine Clearance Planning Agency | AF/0401/02178/MF0055 | 31124 | 68.868 | 34.437 | Open | AP Only | AP Only | MineField |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {6056E746-D9B2-4F19-BF52-1F42FAF531D6} |  | Low | Agriculture Blocked | Moderate | 27 | CHA | 5 |  |  | 2009-07-15 | No | Open
Central | Maydan Wardak | Maydan Shahr | Soorqul | {10C55ACF-59C4-4778-99B9-9B699FB1C246} | c0a8-008e-1311358a450-759f68e1-1daa-7 | MF-CA-1451 | MCPA - Mine Clearance Planning Agency | AF/0108/00041/MF0148 | 45282 | 68.8946 | 34.4467 | Open | AP Only | AP Only | MineField |  | MBT Project-277 | Maydan Wardak Demining Project-14 |  |  |  |  | 1400 |  | {10C55ACF-59C4-4778-99B9-9B699FB1C246} |  | Low | Agriculture Blocked | Moderate | 78 | CHA | 5 |  |  | 2008-08-19 | No | Open
Central | Maydan Wardak | Maydan Shahr | Syahpetaw | {B02E6700-F063-4AF3-A7E8-196C57A74D37} | c0a8-008e-13118031635-b8c32d8b-154-45 | MF-HQ-12464 | MCPA - Mine Clearance Planning Agency | AF/0401/02145/MF0079 | 83179 | 68.8359 | 34.4222 | Open | AP Only | AP Only | MineField |  | MBT Project-190 | Maydan Wardak Demining Project-04 |  |  |  |  | 1396 |  | {B02E6700-F063-4AF3-A7E8-196C57A74D37} |  | Medium | Critical Infrastracture | Moderate | 1061 | CHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Maydan Shahr | Torkhel | {31BEFE31-4ACE-4933-9F02-3D1514702D5B} | c0a8-008e-13117807f06-bb2255fc-28ac-8 | MF-HQ-12042 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02133/MF0065 | 15000 | 68.8339 | 34.4038 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {31BEFE31-4ACE-4933-9F02-3D1514702D5B} |  | Low | Comunity Centers | Moderate | 1992 | SHA | 4 |  |  | 2009-07-15 | No | Open
Central | Maydan Wardak | Maydan Shahr | Torkhel | {31BEFE31-4ACE-4933-9F02-3D1514702D5B} | c0a8-008e-131179d042e-ba870cd5-2bdf-a | MF-HQ-12041 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0401/02133/MF0064 | 112700 | 68.8113 | 34.4069 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {31BEFE31-4ACE-4933-9F02-3D1514702D5B} |  | Low | Agriculture Blocked | Moderate | 1941 | SHA | 4 |  |  | 2009-07-15 | No | Open
Central | Maydan Wardak | Nirkh | Akhundzadakhel | {8F1336E4-08ED-4086-A06E-ACB4945339C0} | c0a8-0057-12c3b9ad7fb-b4357027-2bb92- | MF-HQ-12523 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02298/MF0028 | 64800 | 68.5841 | 34.353 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {8F1336E4-08ED-4086-A06E-ACB4945339C0} |  | Medium | Critical Infrastracture | High | 176 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Nirkh | Alaqadari Nerkh | {216194EE-2012-4B6D-AE15-9A6B251EB573} | c0a8-0057-12c3bb6f607-49dfa272-3c959- | MF-HQ-12525 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02382/MF0027 | 1100.5 | 68.8203 | 34.372 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {216194EE-2012-4B6D-AE15-9A6B251EB573} |  | Medium | Critical Infrastracture | High | 22 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Nirkh | Andar | {FC0A6234-C1BD-4FD6-8806-20A486BA3C43} | c0a8-0057-12c3b84e324-524fdba1-1ced5- | MF-HQ-12157 | HT - HALO TRUST | H/975 | 21150 | 68.8384 | 34.279 | Open | AP Only | AP Only | MineField |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {FC0A6234-C1BD-4FD6-8806-20A486BA3C43} |  | High with Victim | High with Victims | High | 235 | CHA | 2 |  |  | 2004-06-19 | No | Open
Central | Maydan Wardak | Nirkh | Andar | {FC0A6234-C1BD-4FD6-8806-20A486BA3C43} | c0a8-0057-12c3badcd98-9752b8f0-37351- | MF-HQ-12516 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02357/MF0022 | 45000 | 68.8313 | 34.2508 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {FC0A6234-C1BD-4FD6-8806-20A486BA3C43} |  | High with Victim | High with Victims | High | 471 | SHA | 2 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Nirkh | Andar | {FC0A6234-C1BD-4FD6-8806-20A486BA3C43} | c0a8-00c9-12fdd786474-70445424-4d9-4b | MF-HQ-10277 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0403/067/MF009A | 90292 | 68.8199 | 34.231 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {FC0A6234-C1BD-4FD6-8806-20A486BA3C43} |  | High with Victim | High with Victims | High | 186 | SHA | 2 |  |  | 2009-05-17 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Andar | {FC0A6234-C1BD-4FD6-8806-20A486BA3C43} | c0a8-00c9-12fdd7aac72-9d8c3726-4f9-41 | MF-HQ-12513 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02357/MF0021 | 45000 | 68.8308 | 34.2512 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {FC0A6234-C1BD-4FD6-8806-20A486BA3C43} |  | High with Victim | High with Victims | High | 471 | SHA | 2 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Nirkh | Ate Tangay | {31EFF9E3-5B55-4999-BB89-A338677DDBF2} | c0a8-0057-12c3b7ca282-58385891-1714d- | MF-HQ-11511 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02170/MF0030 | 74578 | 68.9351 | 34.3689 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {31EFF9E3-5B55-4999-BB89-A338677DDBF2} |  | Low | Agriculture Blocked | High | 17 | SHA | 5 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Ate Tangay | {31EFF9E3-5B55-4999-BB89-A338677DDBF2} | c0a8-0057-12c3b8a9fb0-e8c3be7b-20ebd- | MF-HQ-11512 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02170/MF0029 | 88000 | 68.9351 | 34.3689 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {31EFF9E3-5B55-4999-BB89-A338677DDBF2} |  | Low | Agriculture Blocked | High | 33 | SHA | 5 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Ate Tangay | {31EFF9E3-5B55-4999-BB89-A338677DDBF2} | c0a8-0057-12c3baa4e54-115e4d71-3520a- | MF-HQ-11510 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02170/MF0031 | 45037 | 68.933 | 34.3706 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {31EFF9E3-5B55-4999-BB89-A338677DDBF2} |  | Low | Agriculture Blocked | High | 315 | SHA | 4 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Awalkhel | {E99D1D43-0C4B-4BAD-8B37-25DC9A56DD63} | c0a8-0057-12c3b9b5e76-bc78ba1b-2c0bd- | MF-HQ-12156 | HT - HALO TRUST | H/2098 | 47850 | 68.8509 | 34.253 | Open | AP Only | AP Only | MineField |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {E99D1D43-0C4B-4BAD-8B37-25DC9A56DD63} |  | Low | Agriculture Blocked | High | 23 | CHA | 5 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Nirkh | Chaghara | {A4F9DED9-08F1-4201-A064-5EBC7435DD6C} | c0a8-00c9-12fdd7df3d2-875db378-516-7b | MF-HQ-12453 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02368/MF0024 | 78430 | 68.8733 | 34.293 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {A4F9DED9-08F1-4201-A064-5EBC7435DD6C} |  | High with Victim | High with Victims | High | 662 | SHA | 2 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Nirkh | Dehayat(Mara) | {A180B78D-4154-4153-B59F-9629DE66A3A5} | c0a8-0057-12c3ba592ee-ba8027a3-32512- | MF-HQ-12215 | HT - HALO TRUST | H/2104 | 73000 | 68.7725 | 34.3731 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {A180B78D-4154-4153-B59F-9629DE66A3A5} |  | Low | Agriculture Blocked | High | 253 | CHA | 5 |  |  | 2004-06-05 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Dehayat(Mara) | {A180B78D-4154-4153-B59F-9629DE66A3A5} | c0a8-0057-12c3ba593e8-ce6bc283-32524- | BF-HQ-8318 | HT - HALO TRUST | BLU/394 | 618800 | 68.7934 | 34.3592 | Open | UXO Only | UXO Only | BF |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {A180B78D-4154-4153-B59F-9629DE66A3A5} |  | Medium | Critical Infrastracture | High | 0 | CHA | 3 |  |  | 2001-08-11 | No | Open
Central | Maydan Wardak | Nirkh | Depak | {3E6795C0-E5A4-49C5-BABE-B93CE6FD2AFF} | c0a8-0057-12c3b71664a-4f1d5d3f-ed11-d | MF-HQ-12230 | HT - HALO TRUST | H/3088 | 10000 | 68.9394 | 34.3852 | Open | AP Only | AP Only | MineField |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {3E6795C0-E5A4-49C5-BABE-B93CE6FD2AFF} |  | Low | Agriculture Blocked | High | 313 | CHA | 5 |  |  | 2004-06-16 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Depak | {3E6795C0-E5A4-49C5-BABE-B93CE6FD2AFF} | c0a8-0057-12c3b8aa79c-79bc75d7-20f11- | MF-HQ-12608 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02167/MF0036 | 28700 | 68.9505 | 34.3881 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {3E6795C0-E5A4-49C5-BABE-B93CE6FD2AFF} |  | Low | Agriculture Blocked | High | 13 | SHA | 5 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Nirkh | Depak | {3E6795C0-E5A4-49C5-BABE-B93CE6FD2AFF} | c0a8-0057-12c3b94f148-83231979-27d4e- | MF-HQ-12601 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02167/MF0033 | 29106 | 68.9226 | 34.384 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {3E6795C0-E5A4-49C5-BABE-B93CE6FD2AFF} |  | Low | Agriculture Blocked | High | 9 | SHA | 5 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Nirkh | Depak | {3E6795C0-E5A4-49C5-BABE-B93CE6FD2AFF} | c0a8-0057-12c3ba1eaf6-462580c5-301e2- | MF-HQ-12606 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02167/MF0034 | 37100 | 68.9226 | 34.384 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {3E6795C0-E5A4-49C5-BABE-B93CE6FD2AFF} |  | Low | Agriculture Blocked | High | 42 | SHA | 4 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Nirkh | Depak | {3E6795C0-E5A4-49C5-BABE-B93CE6FD2AFF} | c0a8-0057-12c3ba28e64-2d4e7814-307d8- | MF-HQ-12596 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02167/MF0035 | 47025 | 68.9392 | 34.3869 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {3E6795C0-E5A4-49C5-BABE-B93CE6FD2AFF} |  | Low | Agriculture Blocked | High | 22 | SHA | 5 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Nirkh | Hajian (1) | {3B534B14-EFA4-4658-8A14-5D8FF613A7F7} | c0a8-0057-12c3b868f46-5b421038-1e17a- | MF-HQ-12478 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02375/MF010 | 79950 | 68.8979 | 34.3317 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {3B534B14-EFA4-4658-8A14-5D8FF613A7F7} |  | Low | Agriculture Blocked | High | 501 | SHA | 4 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Jawqol | {91351083-37C1-44C5-B568-5B1A5EC19B38} | c0a8-0057-12c3b87511c-955aa171-1e9f0- | MF-HQ-12229 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02289/MF0046 | 24237 | 68.7226 | 34.3819 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {91351083-37C1-44C5-B568-5B1A5EC19B38} |  | Low | Agriculture Blocked | High | 110 | SHA | 5 |  |  | 2006-04-13 | No | Open
Central | Maydan Wardak | Nirkh | Jawqol | {91351083-37C1-44C5-B568-5B1A5EC19B38} | c0a8-0057-12c3b8ac9cb-fc6a6239-21096- | MF-HQ-12174 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02289/MF0047 | 93712 | 68.7396 | 34.3996 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {91351083-37C1-44C5-B568-5B1A5EC19B38} |  | Medium | Agriculture Blocked | High | 60 | SHA | 3 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Nirkh | Kane Ezzat | {C39D342B-8432-4B79-8F9E-78B0E30D944F} | c0a8-0057-12e55f56283-6d87b107-a0-37d | BF-HQ-7435 | HT - HALO TRUST | B/290 | 657653 | 68.7825 | 34.3682 | Open | UXO Only | UXO Only | BF |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {C39D342B-8432-4B79-8F9E-78B0E30D944F} |  | Medium | Critical Infrastracture | High | 0 | CHA | 3 |  |  | 2000-07-15 | No | Open
Central | Maydan Wardak | Nirkh | Kane Ezzat | {C39D342B-8432-4B79-8F9E-78B0E30D944F} | c0a8-00c9-12fdd802c0b-a2b1659d-52e-d6 | MF-HQ-12210 | HT - HALO TRUST | H/2118 | 20000 | 68.8027 | 34.3591 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {C39D342B-8432-4B79-8F9E-78B0E30D944F} |  | Medium | Critical Infrastracture | High | 1096 | CHA | 3 |  |  | 2004-06-02 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Kane Ezzat | {C39D342B-8432-4B79-8F9E-78B0E30D944F} | c0a8-00c9-12fdd821e02-c34654ba-541-87 | MF-HQ-12213 | HT - HALO TRUST | H/2105 | 3500 | 68.8027 | 34.3591 | Open | AT Only | AT Only | MineField |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {C39D342B-8432-4B79-8F9E-78B0E30D944F} |  | Medium | Critical Infrastracture | High | 121 | CHA | 3 |  |  | 2004-06-03 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Karimdad | {04AE30A8-DBCB-4E4F-9EC5-9F0ABA98BB7B} | c0a8-0057-12c3b8a9bf9-91d36cec-20e95- | MF-HQ-12484 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02379/MF018 | 65000 | 68.7698 | 34.3773 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {04AE30A8-DBCB-4E4F-9EC5-9F0ABA98BB7B} |  | High with Victim | High with Victims | High | 108 | SHA | 2 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Karimdad | {04AE30A8-DBCB-4E4F-9EC5-9F0ABA98BB7B} | c0a8-0057-12c3b974cfe-237fd278-295f4- | MF-HQ-12481 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02379/MF017 | 69112 | 68.7698 | 34.3773 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {04AE30A8-DBCB-4E4F-9EC5-9F0ABA98BB7B} |  | High with Victim | High with Victims | High | 108 | SHA | 2 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Karimdad | {04AE30A8-DBCB-4E4F-9EC5-9F0ABA98BB7B} | c0a8-00c9-12fdd84e045-1061f527-588-93 | MF-HQ-12173 | HT - HALO TRUST | H/2108 | 52898 | 68.7747 | 34.3608 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {04AE30A8-DBCB-4E4F-9EC5-9F0ABA98BB7B} |  | High with Victim | High with Victims | High | 108 | CHA | 2 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Nirkh | Khurdka | {4385A1EE-31B0-48E3-B98A-4488A65A25EE} | c0a8-0057-12c3b8b593d-57fe36e9-216ad- | MF-HQ-12223 | HT - HALO TRUST | H/2102 | 80000 | 68.4293 | 34.2051 | Open | AT Only | AT Only | MineField |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {4385A1EE-31B0-48E3-B98A-4488A65A25EE} |  | Low | Agriculture Blocked | High | 20 | CHA | 5 |  |  | 2006-05-08 | No | Open
Central | Maydan Wardak | Nirkh | Khwaja Beland Omer Khail | {5386230F-ABFB-4745-AEEC-C98A4C969A00} | c0a8-0057-12c3b93ab71-ac397b65-26fc7- | MF-HQ-12216 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/00248/MF0032 | 59081 | 68.7073 | 34.3532 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {5386230F-ABFB-4745-AEEC-C98A4C969A00} |  | High with Victim | High with Victims | High | 299 | SHA | 1 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Nirkh | Khwaja Beland Omer Khail | {5386230F-ABFB-4745-AEEC-C98A4C969A00} | c0a8-0057-12c3ba483f3-12c0bcf5-31af0- | MF-HQ-12172 | HT - HALO TRUST | H/2109 | 98000 | 68.7239 | 34.3466 | Open | AT Only | AT Only | MineField |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {5386230F-ABFB-4745-AEEC-C98A4C969A00} |  | High with Victim | High with Victims | High | 156 | CHA | 1 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Nirkh | Mashikhel | {E343846C-B830-456D-8DED-EC8AC33D5386} | c0a8-0057-12c3b9a7583-bcacdc64-2b765- | MF-HQ-12826 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02390/MF0048 | 103025 | 68.9148 | 34.3529 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {E343846C-B830-456D-8DED-EC8AC33D5386} |  | Low | Agriculture Blocked | High | 122 | SHA | 4 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Nirkh | Nyazi | {D3B3533D-A540-4E91-B35F-CC4410F8C6DC} | c0a8-00f6-1355b4eb4ed-7308a7f-d3f-16e | MF-16686 | HT - HALO TRUST | H/2099 | 12000 | 68.7349 | 34.3743 | Open | AT Only | AT Only | MineField |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {D3B3533D-A540-4E91-B35F-CC4410F8C6DC} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2004-06-15 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Padshakhel | {AF9DD08E-E7EB-4B6E-B7D7-6C871DCFFB12} | c0a8-0057-12c3b71242c-be664acc-e9ee-a | MF-HQ-12233 | HT - HALO TRUST | H/2111 | 7500 | 68.9202 | 34.3558 | Open | AP Only | AP Only | MineField |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {AF9DD08E-E7EB-4B6E-B7D7-6C871DCFFB12} |  | Low | Agriculture Blocked | High | 108 | CHA | 5 |  |  | 2004-06-17 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Padshakhel | {AF9DD08E-E7EB-4B6E-B7D7-6C871DCFFB12} | c0a8-0057-12c3b757415-f3dd1a9c-11dc6- | MF-HQ-12224 | HT - HALO TRUST | H/2112 | 45000 | 68.7314 | 34.3167 | Open | AP Only | AP Only | MineField |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {AF9DD08E-E7EB-4B6E-B7D7-6C871DCFFB12} |  | Medium | Critical Infrastracture | High | 332 | CHA | 3 |  |  | 2004-06-16 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Padshakhel | {AF9DD08E-E7EB-4B6E-B7D7-6C871DCFFB12} | c0a8-0057-12c3b7ad7c9-727d3d33-15ca8- | MF-HQ-12220 | HT - HALO TRUST | H/3089 | 90000 | 68.7314 | 34.3167 | Open | AP Only | AP Only | MineField |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {AF9DD08E-E7EB-4B6E-B7D7-6C871DCFFB12} |  | Medium | Critical Infrastracture | High | 332 | CHA | 3 |  |  | 2004-06-16 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Qala-I-Bocha-I-Dadel | {263057E1-624A-4C9C-AEB8-485E382B7992} | c0a8-0057-12c3b6ba3d5-98577cef-a705-2 | MF-HQ-12237 | HT - HALO TRUST | H/2101 | 15000 | 68.6781 | 34.4079 | Open | AP Only | AP Only | MineField |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {263057E1-624A-4C9C-AEB8-485E382B7992} |  | Medium | Critical Infrastracture | High | 626 | CHA | 3 |  |  | 2003-08-04 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Qala-I-Bocha-I-Dadel | {263057E1-624A-4C9C-AEB8-485E382B7992} | c0a8-0057-12c3b71300e-2187c7dc-ea89-6 | MF-HQ-12238 | HT - HALO TRUST | H/2100 | 17000 | 68.6781 | 34.4079 | Open | AP Only | AP Only | MineField |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {263057E1-624A-4C9C-AEB8-485E382B7992} |  | Medium | Critical Infrastracture | High | 626 | CHA | 3 |  |  | 2004-06-07 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Qala-I-Bocha-I-Dadel | {263057E1-624A-4C9C-AEB8-485E382B7992} | c0a8-0057-12c3ba3917d-5105c6f9-3119b- | MF-HQ-13955 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/00110/MF0049 | 48000 | 68.678 | 34.4076 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {263057E1-624A-4C9C-AEB8-485E382B7992} |  | Medium | Critical Infrastracture | High | 1707 | SHA | 4 |  |  | 2009-12-21 | No | Open
Central | Maydan Wardak | Nirkh | Qala-I-Zeyarat Dadel | {293487B9-59E2-4EFA-8CAF-45252142F2D7} | c0a8-0057-12c3b96275d-2456db24-28a35- | MF-HQ-12458 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/00115/MF0045 | 102950 | 68.653 | 34.403 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {293487B9-59E2-4EFA-8CAF-45252142F2D7} |  | Medium | Critical Infrastracture | High | 52 | SHA | 3 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Qal'eh-ye-Snagi | {CB14A80D-69EC-436A-A6D1-759A5F5359B1} | c0a8-0057-12c3b896abf-f516857f-20184- | MF-HQ-11514 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02374/MF0012 | 110000 | 68.9194 | 34.3794 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {CB14A80D-69EC-436A-A6D1-759A5F5359B1} |  | Low | Agriculture Blocked | High | 31 | SHA | 5 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Qal'eh-ye-Snagi | {CB14A80D-69EC-436A-A6D1-759A5F5359B1} | c0a8-0057-12c3b8f2873-c3564a71-240b9- | MF-HQ-11515 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02374/MF0013 | 110000 | 68.9191 | 34.379 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {CB14A80D-69EC-436A-A6D1-759A5F5359B1} |  | Low | Agriculture Blocked | High | 31 | SHA | 4 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Qal'eh-ye-Snagi | {CB14A80D-69EC-436A-A6D1-759A5F5359B1} | c0a8-0057-12c3b98a459-71c4f0c1-2a41f- | MF-HQ-11513 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02374/MF0014 | 48600 | 68.8958 | 34.3327 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-191 | Maydan Wardak Demining Project-05 |  |  |  |  | 1397 |  | {CB14A80D-69EC-436A-A6D1-759A5F5359B1} |  | Medium | Critical Infrastracture | High | 18 | SHA | 3 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Qal'eh-ye-Snagi | {CB14A80D-69EC-436A-A6D1-759A5F5359B1} | c0a8-00c9-12fdd86bf12-70a7cda5-5b0-c0 | MF-HQ-11516 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02374/MF0015 | 337500 | 68.8851 | 34.3402 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-194 | Maydan Wardak Demining Project-09 |  |  |  |  | 1399 |  | {CB14A80D-69EC-436A-A6D1-759A5F5359B1} |  | Low | Agriculture Blocked | High | 54 | SHA | 4 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Qol-e Aka | {A5378384-A6D5-4D2C-863C-2595FFAF15FE} | c0a8-0057-12c3b811ca5-3127ebe5-1a37b- | MF-HQ-12219 | HT - HALO TRUST | H/2110 | 155000 | 68.6359 | 34.368 | Open | AP Only | AP Only | MineField |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {A5378384-A6D5-4D2C-863C-2595FFAF15FE} |  | Medium | Critical Infrastracture | High | 548 | CHA | 3 |  |  | 2004-06-16 16:30 | No | Open
Central | Maydan Wardak | Nirkh | R-Nirkh | {AA8D9D66-2998-4825-AD92-236EE5C5573C} | c0a8-0057-12c3b75cf6c-eebf416b-121e7- | MF-HQ-12345 | HT - HALO TRUST | H/2114 | 20000 | 68.8042 | 34.3578 | Open | AT Only | AT Only | MineField |  | MBT Project-241 | Maydan Wardak Demining Project-06 (AT) |  |  |  |  | 1399 |  | {AA8D9D66-2998-4825-AD92-236EE5C5573C} |  | Medium | Critical Infrastracture | High | 975 | CHA | 3 |  |  | 2004-06-08 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Sarferazkhel | {DE911FCA-E9DE-45ED-9792-0B0365B6B3A2} | c0a8-0057-12c3b82a36c-e60f3fb8-1b4c7- | MF-HQ-12461 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/02319/MF0011 | 18500 | 68.7183 | 34.3347 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-116 | Maydan Wardak Demining Project-03 (AT) |  |  |  |  | 1397 |  | {DE911FCA-E9DE-45ED-9792-0B0365B6B3A2} |  | Medium | Critical Infrastracture | High | 98 | SHA | 3 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Shah Kabul | {F4C5C36A-E702-4C8E-A2B6-0E14AF9BE8FF} | c0a8-0057-12c3bb237b4-826d7bcf-39d98- | MF-HQ-12218 | HT - HALO TRUST | H/2115 | 21000 | 68.8339 | 34.2989 | Open | AP Only | AP Only | MineField |  | MBT Project-196 | Maydan Wardak Demining Project-12 |  |  |  |  | 1399 |  | {F4C5C36A-E702-4C8E-A2B6-0E14AF9BE8FF} |  | Low | Critical Infrastracture | High | 22 | CHA | 5 |  |  | 2004-06-13 16:30 | No | Open
Central | Maydan Wardak | Nirkh | Shahabuddin | {C8ABB365-5261-4AED-BEBA-B6EB10947F44} | c0a8-0057-12c3b7f822e-377ff36c-1916c- | MF-HQ-12463 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/00619/MF043 | 9872 | 68.8794 | 34.3117 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {C8ABB365-5261-4AED-BEBA-B6EB10947F44} |  | High with Victim | High with Victims | High | 626 | SHA | 2 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Shahabuddin | {C8ABB365-5261-4AED-BEBA-B6EB10947F44} | c0a8-0057-12c3b850238-7195cee0-1d045- | MF-HQ-12472 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/00619/MF040 | 72100 | 68.8656 | 34.3212 | Open | AP Only | AP Only | Converted From SHA | Blank | MBT Project-143 | Maydan Wardak Demining Project-02 |  | No |  |  | 1396 | Blank | {C8ABB365-5261-4AED-BEBA-B6EB10947F44} |  | High with Victim | High with Victims | High | 263 | SHA | 2 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Shahabuddin | {C8ABB365-5261-4AED-BEBA-B6EB10947F44} | c0a8-0057-12c3b8c5380-d9f8b317-221bf- | MF-HQ-12474 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/00619/MF041 | 23940 | 68.8562 | 34.3261 | Open | AP Only | AP Only | Converted From SHA | 1393 | MBT Project-142 | Maydan Wardak Demining Project-01 | B-Japan | Yes |  |  | 1393 | MDC | {C8ABB365-5261-4AED-BEBA-B6EB10947F44} |  | High with Victim | High with Victims | High | 116 | SHA | 2 |  |  | 2009-07-13 | No | Planned
Central | Maydan Wardak | Nirkh | Shahabuddin | {C8ABB365-5261-4AED-BEBA-B6EB10947F44} | c0a8-0057-12c3b8dc0bf-3b78902c-2313c- | MF-HQ-12468 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/00619/MF044 | 150817 | 68.8767 | 34.313 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {C8ABB365-5261-4AED-BEBA-B6EB10947F44} |  | High with Victim | High with Victims | High | 825 | SHA | 2 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Nirkh | Shahabuddin | {C8ABB365-5261-4AED-BEBA-B6EB10947F44} | c0a8-0057-12c3b941fee-3bc351c4-274a1- | MF-HQ-12465 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/00619/MF042 | 136061 | 68.881 | 34.3113 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {C8ABB365-5261-4AED-BEBA-B6EB10947F44} |  | High with Victim | High with Victims | High | 646 | SHA | 2 |  |  | 2009-07-13 | No | Open
Central | Maydan Wardak | Saydabad | Abdulmohayedin | {41FE7086-5EE4-4EC1-B06A-615071038CF0} | c0a8-0057-12c3b9fa92c-30136cda-2eb81- | MF-HQ-12207 | HT - HALO TRUST | H/2150 | 6600 | 68.5408 | 33.7623 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {41FE7086-5EE4-4EC1-B06A-615071038CF0} |  | Low | Critical Infrastracture | High | 536 | CHA | 5 |  |  | 2004-12-14 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Alah Sang | {F215E145-851E-4094-BDBE-4E9E7445852E} | c0a8-0009-147c995b8dd-a86f7440-7a6-67 | Hz-ID-18887 | MCPA - Mine Clearance Planning Agency | AF/0407/00753/MF0073 | 20241 | 68.781 | 34.1784 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {F215E145-851E-4094-BDBE-4E9E7445852E} |  | Low | Critical Infrastracture | High | 112 | CHA | 4 |  |  | 2014-06-24 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Alah Sang | {F215E145-851E-4094-BDBE-4E9E7445852E} | c0a8-0009-147c9990848-bb281edd-b3f-b6 | Hz-ID-18889 | MCPA - Mine Clearance Planning Agency | AF/0407/00753/MF0074 | 35571 | 68.7887 | 34.1703 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {F215E145-851E-4094-BDBE-4E9E7445852E} |  | Low | Critical Infrastracture | High | 954 | CHA | 4 |  |  | 2014-06-16 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Alah Sang | {F215E145-851E-4094-BDBE-4E9E7445852E} | c0a8-0057-12c3b884b21-faa82218-1f4e5- | MF-HQ-12178 | MCPA - Mine Clearance Planning Agency | AF/0407/00753/MF0018 | 64557 | 68.7739 | 34.1699 | Open | AT Only | AT Only | MineField |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {F215E145-851E-4094-BDBE-4E9E7445852E} |  | Low | Critical Infrastracture | High | 178 | CHA | 4 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Alayarkhel | {EF1B0CBD-FA08-4823-B608-A0D2A7B612E5} | c0a8-0057-12c3b98ffde-b672b6e2-2a7ec- | MF-HQ-12658 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03454/MF0036 | 146400 | 68.7292 | 34.0301 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {EF1B0CBD-FA08-4823-B608-A0D2A7B612E5} |  | Low | Agriculture Blocked | High | 240 | SHA | 4 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Baghak | {87CB589D-1E17-4235-A9C8-E00260D3275C} | c0a8-0057-12c3bad3409-ed2931f6-36db3- | MF-HQ-12580 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03393/MF0063 | 266000 | 68.6152 | 33.8908 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) |  |  |  |  | 1398 |  | {87CB589D-1E17-4235-A9C8-E00260D3275C} |  | Medium | Critical Infrastracture | High | 195 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Bar Jang Joy | {173433D4-4416-498D-B045-ED76A1183BFB} | c0a8-0057-12c3b973e40-7a34f997-2955b- | MF-HQ-12672 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/32026/MF0042 | 111250 | 68.632 | 33.7662 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) |  |  |  |  | 1398 |  | {173433D4-4416-498D-B045-ED76A1183BFB} |  | Medium | Critical Infrastracture | High | 757 | SHA | 3 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Bar Mamel | {AE2DFC60-B162-444A-B0F8-DB14764A0205} | c0a8-0057-12c3b6dda2a-6f822802-c1f7-a | MF-HQ-12158 | HT - HALO TRUST | H/2120 | 49000 | 68.6925 | 33.9542 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {AE2DFC60-B162-444A-B0F8-DB14764A0205} |  | Medium | Critical Infrastracture | High | 319 | CHA | 3 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Bar Mamel | {AE2DFC60-B162-444A-B0F8-DB14764A0205} | c0a8-0057-12c3b7b07fc-40c329cf-15eaf- | MF-HQ-12165 | HT - HALO TRUST | H/2119 | 49200 | 68.6882 | 33.9454 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {AE2DFC60-B162-444A-B0F8-DB14764A0205} |  | Medium | Critical Infrastracture | High | 223 | CHA | 3 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Bar Mamel | {AE2DFC60-B162-444A-B0F8-DB14764A0205} | c0a8-0057-12c3ba8d3cc-9431463-34482-d | MF-HQ-12653 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03439/MF0053 | 48600 | 68.6921 | 33.9447 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) |  |  |  |  | 1398 |  | {AE2DFC60-B162-444A-B0F8-DB14764A0205} |  | Medium | Critical Infrastracture | High | 283 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Bergi | {B10F1BCD-F2E1-423E-BA8C-0A7F620B5CA6} | c0a8-0057-12c3bb8867f-4f0d2b91-3d75c- | MF-HQ-12553 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03421/MF0072 | 86400 | 68.6344 | 34.0218 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {B10F1BCD-F2E1-423E-BA8C-0A7F620B5CA6} |  | Low | Agriculture Blocked | High | 536 | SHA | 4 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Dundokay | {520EDACF-EA9E-4C4A-85DD-E38485A5221B} | c0a8-0057-12c3b6ee86a-bea21a68-cedc-6 | MF-HQ-12247 | HT - HALO TRUST | H/2127 | 300 | 68.6173 | 33.8845 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {520EDACF-EA9E-4C4A-85DD-E38485A5221B} |  | High with Victim | High with Victims | High | 0 | CHA | 3 |  |  | 2004-12-07 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Dundokay | {520EDACF-EA9E-4C4A-85DD-E38485A5221B} | c0a8-0057-12c3b770538-f54260f2-1303f- | MF-HQ-12148 | HT - HALO TRUST | H/2126 | 2000 | 68.6102 | 33.8765 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {520EDACF-EA9E-4C4A-85DD-E38485A5221B} |  | High with Victim | High with Victims | High | 138 | CHA | 3 |  |  | 2004-12-07 | No | Open
Central | Maydan Wardak | Saydabad | Dundokay | {520EDACF-EA9E-4C4A-85DD-E38485A5221B} | c0a8-0057-12c3b9c3fcc-6e5ad36b-2c9c1- | MF-HQ-12149 | HT - HALO TRUST | H/2125 | 21000 | 68.6036 | 33.8503 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {520EDACF-EA9E-4C4A-85DD-E38485A5221B} |  | High with Victim | High with Victims | High | 225 | CHA | 5 |  |  | 2004-12-07 | No | Open
Central | Maydan Wardak | Saydabad | Dundokay | {520EDACF-EA9E-4C4A-85DD-E38485A5221B} | c0a8-0057-12c3bb29f99-22d069f1-3a122- | MF-HQ-12572 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03397/MF0046 | 126000 | 68.6173 | 33.8845 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {520EDACF-EA9E-4C4A-85DD-E38485A5221B} |  | High with Victim | High with Victims | High | 201 | SHA | 4 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Gada'i | {5E7FF10E-9085-4D94-BFF6-6233B44BCBD4} | c0a8-0057-12c3b732df7-9b9cb5fb-1029f- | MF-HQ-12150 | HT - HALO TRUST | H/2143 | 33000 | 68.7647 | 34.0644 | Open | AP Only | AP Only | MineField |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {5E7FF10E-9085-4D94-BFF6-6233B44BCBD4} |  | Low | Agriculture Blocked | High | 265 | CHA | 5 |  |  | 2004-12-17 | No | Open
Central | Maydan Wardak | Saydabad | Gada'i | {5E7FF10E-9085-4D94-BFF6-6233B44BCBD4} | c0a8-0057-12c3b733cd5-e4f794c5-10355- | MF-HQ-12147 | HT - HALO TRUST | H/2145 | 24000 | 68.736 | 34.0247 | Open | AP Only | AP Only | MineField |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {5E7FF10E-9085-4D94-BFF6-6233B44BCBD4} |  | Low | Agriculture Blocked | High | 170 | CHA | 5 |  |  | 2004-12-16 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Haftasya | {A2EC8473-0E01-4403-8E21-61F52751E217} | c0a8-0057-12c3b8d30d1-6470df67-22b26- | MF-HQ-12670 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03392/MF0034 | 101150 | 68.6034 | 33.8301 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) |  |  |  |  | 1398 |  | {A2EC8473-0E01-4403-8E21-61F52751E217} |  | Medium | Critical Infrastracture | High | 1806 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Haftasya | {A2EC8473-0E01-4403-8E21-61F52751E217} | c0a8-0057-12c3ba2502c-b95deb48-30588- | MF-HQ-12675 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03392/MF0033 | 16387 | 68.6035 | 33.8319 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) |  |  |  |  | 1398 |  | {A2EC8473-0E01-4403-8E21-61F52751E217} |  | Medium | Critical Infrastracture | High | 951 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Haftasya | {A2EC8473-0E01-4403-8E21-61F52751E217} | c0a8-0057-12c3ba3fdc5-dfb09b89-315ba- | MF-HQ-12666 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03392/MF0032 | 43000 | 68.6342 | 33.7967 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {A2EC8473-0E01-4403-8E21-61F52751E217} |  | Low | Agriculture Blocked | High | 52 | SHA | 5 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Haftasya | {A2EC8473-0E01-4403-8E21-61F52751E217} | c0a8-0057-12c3bb7d08b-106c5728-3d117- | MF-HQ-12679 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03392/MF0031 | 10000 | 68.5987 | 33.8009 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {A2EC8473-0E01-4403-8E21-61F52751E217} |  | Low | Agriculture Blocked | High | 108 | SHA | 5 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Hamzakhel | {FD06A4A8-B797-4FB2-87F6-D30BA238CCD2} | c0a8-0057-12c3bb459a0-53bcc885-3b1a5- | MF-HQ-12610 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03455/MF0037 | 10000 | 68.6978 | 34.0062 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {FD06A4A8-B797-4FB2-87F6-D30BA238CCD2} |  | Low | Agriculture Blocked | High | 183 | SHA | 4 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Hasanbeg | {AB3F8C02-54A1-4930-AC3E-8CB46D3EAD16} | c0a8-0057-12c3bb356f4-a0155673-3a82f- | MF-HQ-12531 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03416/MF0043 | 831000 | 68.6056 | 34.0257 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) |  |  |  |  | 1398 |  | {AB3F8C02-54A1-4930-AC3E-8CB46D3EAD16} |  | Medium | Critical Infrastracture | High | 47 | SHA | 3 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Hasankhel (1) | {A2464829-0A62-42DA-8A71-CAFB194CA5AC} | c0a8-0057-12c3b984692-6811145f-2a035- | MF-HQ-12616 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03425/MF0041 | 60000 | 68.6822 | 33.9337 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {A2464829-0A62-42DA-8A71-CAFB194CA5AC} |  | High with Victim | High with Victims | High | 1055 | SHA | 2 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Hasankhel (1) | {A2464829-0A62-42DA-8A71-CAFB194CA5AC} | c0a8-0057-12c3b9faab2-a186546b-2eb92- | MF-HQ-12248 | HT - HALO TRUST | H/2133 | 100000 | 68.6386 | 34.0177 | Open | AT Only | AT Only | MineField |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {A2464829-0A62-42DA-8A71-CAFB194CA5AC} |  | High with Victim | High with Victims | High | 93 | CHA | 2 |  |  | 2004-12-08 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Hasankhel (1) | {A2464829-0A62-42DA-8A71-CAFB194CA5AC} | c0a8-0057-12c3baf068f-a7368fd0-37f1c- | MF-HQ-12620 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03425/MF0040 | 210000 | 68.6796 | 33.9285 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {A2464829-0A62-42DA-8A71-CAFB194CA5AC} |  | High with Victim | High with Victims | High | 1787 | SHA | 2 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Hasankhel (2) | {38470D4F-51FB-43E4-9A69-C94B80CA50D6} | c0a8-0057-12c3b690b35-a65c253c-8803-4 | MF-HQ-12245 | HT - HALO TRUST | H/2135 | 25000 | 68.6793 | 33.9289 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {38470D4F-51FB-43E4-9A69-C94B80CA50D6} |  | Medium | Critical Infrastracture | High | 281 | CHA | 3 |  |  | 2004-12-19 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Hasankhel (2) | {38470D4F-51FB-43E4-9A69-C94B80CA50D6} | c0a8-0057-12c3b714ec4-b3f064d9-ebf2-c | MF-HQ-12244 | HT - HALO TRUST | H/2136 | 3500 | 68.6816 | 33.9329 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {38470D4F-51FB-43E4-9A69-C94B80CA50D6} |  | Medium | Critical Infrastracture | High | 281 | CHA | 3 |  |  | 2009-09-12 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Haydarkhel | {82E2B557-8F0A-4926-9D80-9570C1C3D9C6} | c0a8-0057-12c3b6a6294-3eef258-97b9-a8 | MF-HQ-12166 | HT - HALO TRUST | H/2130 | 203350 | 68.702 | 33.9721 | Open | AP Only | AP Only | MineField |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {82E2B557-8F0A-4926-9D80-9570C1C3D9C6} |  | Low | Critical Infrastracture | High | 149 | CHA | 5 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Haydarkhel | {82E2B557-8F0A-4926-9D80-9570C1C3D9C6} | c0a8-0057-12c3b783c7a-386663d-13e62-a | MF-HQ-12203 | HT - HALO TRUST | H/2131 | 160000 | 68.7066 | 33.9801 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {82E2B557-8F0A-4926-9D80-9570C1C3D9C6} |  | Medium | Critical Infrastracture | High | 506 | CHA | 3 |  |  | 2004-12-13 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Haydarkhel | {82E2B557-8F0A-4926-9D80-9570C1C3D9C6} | c0a8-0057-12c3b7fbe82-a95ada36-1942a- | MF-HQ-12538 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03437/MF0038 | 64000 | 68.7045 | 33.9782 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) |  |  |  |  | 1398 |  | {82E2B557-8F0A-4926-9D80-9570C1C3D9C6} |  | Medium | Critical Infrastracture | High | 382 | SHA | 3 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Haydarkhel | {82E2B557-8F0A-4926-9D80-9570C1C3D9C6} | c0a8-0057-12c3baeb48a-1ad1bf3a-37bfb- | MF-HQ-12536 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03437/MF0039 | 107700 | 68.7049 | 33.9773 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) |  |  |  |  | 1398 |  | {82E2B557-8F0A-4926-9D80-9570C1C3D9C6} |  | Medium | Critical Infrastracture | High | 387 | SHA | 3 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Kashmur | {B18D6372-6E68-469F-B2FC-AC227B143725} | c0a8-0057-12c3baa5cf4-f692a94e-35285- | MF-HQ-12605 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03457/MF0059 | 102000 | 68.6911 | 34.0076 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) |  |  |  |  | 1398 |  | {B18D6372-6E68-469F-B2FC-AC227B143725} |  | Medium | Critical Infrastracture | High | 80 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Kodalak | {8A91ECFD-D599-4A37-8106-F1E41F145AC1} | c0a8-0057-12c3b9ad9fe-4136075e-2bba6- | MF-HQ-12562 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03472/MF0069 | 151800 | 68.7358 | 34.0255 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-179 | Maydan Wardak Demining Project-06 |  |  |  |  | 1398 |  | {8A91ECFD-D599-4A37-8106-F1E41F145AC1} |  | Medium | Agriculture Blocked | High | 26 | SHA | 3 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Kodali | {26CE6B70-A539-4EFF-828D-0A612F07F64E} | c0a8-0057-12c3b6a63eb-7c0d4f6c-97ca-3 | MF-HQ-12193 | HT - HALO TRUST | H/2142 | 20000 | 68.6412 | 33.7902 | Open | AP Only | AP Only | MineField |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {26CE6B70-A539-4EFF-828D-0A612F07F64E} |  | Low | Agriculture Blocked | High | 27 | CHA | 5 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Kodali | {26CE6B70-A539-4EFF-828D-0A612F07F64E} | c0a8-0057-12c3b6c4b38-2e3ae6c2-aee8-e | MF-HQ-12180 | HT - HALO TRUST | H/2144 | 25875 | 68.603 | 33.831 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {26CE6B70-A539-4EFF-828D-0A612F07F64E} |  | Medium | Critical Infrastracture | High | 951 | CHA | 3 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Kodali | {26CE6B70-A539-4EFF-828D-0A612F07F64E} | c0a8-0057-12c3b7500bb-ebfe23d8-11868- | MF-HQ-12197 | HT - HALO TRUST | H/2146 | 5000 | 68.6412 | 33.7902 | Open | AP Only | AP Only | MineField |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {26CE6B70-A539-4EFF-828D-0A612F07F64E} |  | Low | Agriculture Blocked | High | 27 | CHA | 5 |  |  | 2004-12-11 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Kuz Jangjay | {07400294-C178-4124-88B4-34467935B39A} | c0a8-0057-12c3ba74c3a-9c861be7-33647- | MF-HQ-12741 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03384/MF0057 | 246000 | 68.6148 | 33.7777 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {07400294-C178-4124-88B4-34467935B39A} |  | Low | Agriculture Blocked | High | 55 | SHA | 5 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Kuz Jangjay | {07400294-C178-4124-88B4-34467935B39A} | c0a8-0057-12c3bab5d01-561d2751-35bda- | MF-HQ-12737 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03384/MF0056 | 38400 | 68.6068 | 33.7907 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {07400294-C178-4124-88B4-34467935B39A} |  | Low | Agriculture Blocked | High | 24 | SHA | 5 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Lwar | {9141CA95-4E70-44F5-BF8B-5E47F15D4FC9} | c0a8-0057-12c3b8301a1-b8e262ae-1b900- | MF-HQ-12584 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03460/MF0065 | 120000 | 68.7139 | 34.0041 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) |  |  |  |  | 1398 |  | {9141CA95-4E70-44F5-BF8B-5E47F15D4FC9} |  | Medium | Critical Infrastracture | High | 2277 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Mashin Kala | {AB212A8E-2686-4C43-96C8-E543A956ACDA} | c0a8-0057-12c3b741382-9a4ab9fc-10d69- | MF-HQ-12194 | HT - HALO TRUST | H/2149 | 10000 | 68.6562 | 33.8863 | Open | AP Only | AP Only | MineField |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {AB212A8E-2686-4C43-96C8-E543A956ACDA} |  | Medium | Critical Infrastracture | High | 281 | CHA | 3 |  |  | 2004-12-20 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Mashin Kala | {AB212A8E-2686-4C43-96C8-E543A956ACDA} | c0a8-0057-12c3b792688-f6a431b2-1490a- | MF-HQ-12176 | HT - HALO TRUST | H/2148 | 16000 | 68.6621 | 33.8948 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {AB212A8E-2686-4C43-96C8-E543A956ACDA} |  | Medium | Critical Infrastracture | High | 994 | CHA | 3 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Musakhel | {708B4129-936F-40E0-8061-D8E6DB470C77} | c0a8-0057-12c3b72cd52-95e1cb2d-fe18-a | MF-HQ-12187 | HT - HALO TRUST | H/2151 | 4800 | 68.6054 | 33.8455 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {708B4129-936F-40E0-8061-D8E6DB470C77} |  | Medium | Agriculture Blocked | High | 85 | CHA | 3 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Musakhel | {708B4129-936F-40E0-8061-D8E6DB470C77} | c0a8-0057-12c3b8f1bf5-4101125f-2402a- | MF-HQ-12690 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03414/MF0049 | 47250 | 68.6322 | 33.9942 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {708B4129-936F-40E0-8061-D8E6DB470C77} |  | Low | Agriculture Blocked | High | 204 | SHA | 4 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Musakhel | {708B4129-936F-40E0-8061-D8E6DB470C77} | c0a8-0057-12c3ba9d1b7-c4ad4831-34de4- | MF-HQ-12685 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03414/MF0050 | 20000 | 68.6238 | 33.9924 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {708B4129-936F-40E0-8061-D8E6DB470C77} |  | Low | Agriculture Blocked | High | 90 | SHA | 5 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Musakhel | {708B4129-936F-40E0-8061-D8E6DB470C77} | c0a8-008e-13237d3d21e-5a61dbfd-371-fe | MF-HQ-12195 | HT - HALO TRUST | H/2147 | 5500 | 68.6363 | 33.9965 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {708B4129-936F-40E0-8061-D8E6DB470C77} |  | Low | Agriculture Blocked | High | 144 | CHA | 5 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Nasirkhel | {C56BCB7A-877B-41D9-862C-0F0A4619317C} | c0a8-0057-12c3b95064d-9d8440c-27e2f-f | MF-HQ-12667 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03418/MF0068 | 129500 | 68.6408 | 33.9958 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {C56BCB7A-877B-41D9-862C-0F0A4619317C} |  | Low | Agriculture Blocked | High | 240 | SHA | 4 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Payendakhel | {FB677F28-812B-4FB9-8266-B40550A56851} | c0a8-0057-12c3b73e39d-e10dad3c-10b29- | MF-HQ-12177 | HT - HALO TRUST | H/2152 | 12500 | 68.7219 | 33.9857 | Open | AP Only | AP Only | MineField |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {FB677F28-812B-4FB9-8266-B40550A56851} |  | Low | Agriculture Blocked | High | 158 | CHA | 5 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Payendakhel | {FB677F28-812B-4FB9-8266-B40550A56851} | c0a8-0057-12c3ba75020-ed0ead37-33669- | MF-HQ-12645 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03445/MF0019 | 50600 | 68.717 | 33.9909 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-195 | Maydan Wardak Demining Project-11 |  |  |  |  | 1397 |  | {FB677F28-812B-4FB9-8266-B40550A56851} |  | Low | Agriculture Blocked | High | 107 | SHA | 4 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Qarya-i Amir | {13EB2FF0-5E24-41B2-9F87-B875AA622857} | c0a8-0057-12c3b8f9ef8-70ba59cd-245b0- | MF-HQ-12205 | HT - HALO TRUST | H/2141 | 80000 | 68.8435 | 34.0375 | Open | AP Only | AP Only | MineField |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {13EB2FF0-5E24-41B2-9F87-B875AA622857} |  | High with Victim | High with Victims | High | 0 | CHA | 2 |  |  | 2004-12-05 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Salar | {CF010178-D736-4236-B97A-0B4F78C007E1} | c0a8-0057-12c3b8221a1-6f25f9b1-1af28- | MF-HQ-12555 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03426/MF0017 | 186775 | 68.6641 | 33.8987 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-298 | Maydan Wardak Demining Project-04 (AT) |  |  |  |  | 1398 |  | {CF010178-D736-4236-B97A-0B4F78C007E1} |  | High with Victim | High with Victims | High | 2856 | SHA | 3 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Salehkhel | {F814611B-AFA7-40CE-B67C-ECB4B9E879FC} | c0a8-0057-12c3b8610e5-187d5c8a-1dc0a- | MF-HQ-12767 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03469/MF0021 | 36000 | 68.7396 | 34.1308 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-179 | Maydan Wardak Demining Project-06 |  |  |  |  | 1398 |  | {F814611B-AFA7-40CE-B67C-ECB4B9E879FC} |  | Medium | Critical Infrastracture | High | 19 | SHA | 3 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Salehkhel | {F814611B-AFA7-40CE-B67C-ECB4B9E879FC} | c0a8-0057-12c3baa6167-3414a7c6-352ad- | MF-HQ-12765 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03469/MF0020 | 37500 | 68.7391 | 34.1307 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-179 | Maydan Wardak Demining Project-06 |  |  |  |  | 1398 |  | {F814611B-AFA7-40CE-B67C-ECB4B9E879FC} |  | Medium | Critical Infrastracture | High | 163 | SHA | 3 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Saydabad | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} | c0a8-0057-12c3b731fe3-4891f4fd-101f5- | MF-HQ-12189 | HT - HALO TRUST | H/2123 | 49500 | 68.7505 | 34.0601 | Open | AT Only | AT Only | MineField |  | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) |  |  |  |  | 1393 |  | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} |  | High with Victim | High with Victims | High | 242 | CHA | 1 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Saydabad | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} | c0a8-0057-12c3b75e952-54c2b5d1-12321- | MF-HQ-12160 | HT - HALO TRUST | H/2121 | 159998 | 68.7502 | 34.0594 | Open | AT Only | AT Only | MineField |  | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) |  |  |  |  | 1393 |  | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} |  | High with Victim | High with Victims | High | 242 | CHA | 1 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Saydabad | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} | c0a8-0057-12c3b79877b-4833299e-14d7d- | MF-HQ-12164 | HT - HALO TRUST | H/2140 | 10000 | 68.5914 | 33.7714 | Open | AP Only | AP Only | MineField |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} |  | High with Victim | High with Victims | High | 26 | CHA | 1 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Saydabad | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} | c0a8-0057-12c3b81c724-f329af5e-1ab2b- | MF-HQ-12159 | HT - HALO TRUST | H/2139 | 15000 | 68.5914 | 33.7714 | Open | AT Only | AT Only | MineField |  | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) |  |  |  |  | 1393 |  | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} |  | High with Victim | High with Victims | High | 86 | CHA | 1 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Saydabad | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} | c0a8-0057-12c3bb80179-ac6df886-3d2f5- | MF-HQ-12161 | HT - HALO TRUST | H/2137 | 70000 | 68.6067 | 33.7923 | Open | AT Only | AT Only | MineField |  | MBT Project-115 | Maydan Wardak Demining Project-01 (AT) |  |  |  |  | 1393 |  | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} |  | High with Victim | High with Victims | High | 62 | CHA | 1 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Saydabad | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} | c0a8-00f6-1356ffea8ba-b33ab167-12b-f8 | MF-16687 | HT - HALO TRUST | H/2124 | 300 | 68.6173 | 33.8846 | Open | AP Only | AP Only | MineField |  | MBT Project-143 | Maydan Wardak Demining Project-02 |  |  |  |  | 1396 |  | {FE123B6D-5C29-4F32-B6B7-823EE9DCB91F} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2002-07-09 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Shekhabad | {6AF87D38-592C-4B05-A2F7-FB7343E8EE96} | c0a8-0057-12c3b823669-e46b8195-1b01c- | MF-HQ-12717 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03483/MF0026 | 64400 | 68.7481 | 34.0804 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {6AF87D38-592C-4B05-A2F7-FB7343E8EE96} |  | Low | Agriculture Blocked | High | 797 | SHA | 5 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Shekhabad | {6AF87D38-592C-4B05-A2F7-FB7343E8EE96} | c0a8-0057-12c3b8b55a4-bf0afce1-21687- | MF-HQ-12725 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03483/MF0027 | 30000 | 68.7656 | 34.0855 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {6AF87D38-592C-4B05-A2F7-FB7343E8EE96} |  | Low | Agriculture Blocked | High | 141 | SHA | 4 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Shekhabad | {6AF87D38-592C-4B05-A2F7-FB7343E8EE96} | c0a8-0057-12c3b8e5455-d409cc8a-23827- | MF-HQ-12709 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03483/MF0023 | 72800 | 68.7544 | 34.0688 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-179 | Maydan Wardak Demining Project-06 |  |  |  |  | 1398 |  | {6AF87D38-592C-4B05-A2F7-FB7343E8EE96} |  | Medium | Critical Infrastracture | High | 194 | SHA | 3 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Shekhabad | {6AF87D38-592C-4B05-A2F7-FB7343E8EE96} | c0a8-0057-12c3bb26162-63613575-39f0a- | MF-HQ-12732 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03483/MF0022 | 58500 | 68.7423 | 34.1061 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-179 | Maydan Wardak Demining Project-06 |  |  |  |  | 1398 |  | {6AF87D38-592C-4B05-A2F7-FB7343E8EE96} |  | Medium | Agriculture Blocked | High | 61 | SHA | 3 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Shekha'zam Baba | {34FAB745-DBB5-4926-952D-F9B12DB75064} | c0a8-0057-12c3ba9b19a-9d287102-34c8d- | MF-HQ-12647 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03466/MF0035 | 115500 | 68.7499 | 34.0586 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {34FAB745-DBB5-4926-952D-F9B12DB75064} |  | Low | Critical Infrastracture | High | 110 | SHA | 4 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Sherdadkhel | {8DBC7650-4ECE-4DA3-8937-B7401D4E37F1} | c0a8-0057-12c3b777b7f-6b6ffe64-1358c- | MF-HQ-12183 | HT - HALO TRUST | H/2122 | 63000 | 68.7502 | 34.0594 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {8DBC7650-4ECE-4DA3-8937-B7401D4E37F1} |  | Low | Critical Infrastracture | High | 110 | CHA | 5 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Sherdadkhel | {8DBC7650-4ECE-4DA3-8937-B7401D4E37F1} | c0a8-0057-12c3b8561a5-a17e1086-1d498- | MF-HQ-12641 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03470/MF0070 | 127500 | 68.7716 | 34.0665 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {8DBC7650-4ECE-4DA3-8937-B7401D4E37F1} |  | Low | Agriculture Blocked | High | 38 | SHA | 5 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Sisay | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} | c0a8-0057-12c3b6bb4d5-e8f08b0c-a7d2-e | MF-HQ-12143 | HT - HALO TRUST | H/2155 | 170000 | 68.7463 | 34.0511 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} |  | High with Victim | High with Victims | High | 348 | CHA | 2 |  |  | 2004-12-04 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Sisay | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} | c0a8-0057-12c3b6d844f-133256d2-bdea-e | MF-HQ-12162 | HT - HALO TRUST | H/2154 | 24000 | 68.7463 | 34.0511 | Open | AT Only | AT Only | MineField |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} |  | High with Victim | High with Victims | High | 157 | CHA | 2 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Sisay | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} | c0a8-0057-12c3b6fef4a-a480787a-db59-6 | MF-HQ-12199 | HT - HALO TRUST | H/2158 | 25000 | 68.7411 | 34.0395 | Open | AT Only | AT Only | MineField |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} |  | High with Victim | High with Victims | High | 368 | CHA | 2 |  |  | 2004-12-05 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Sisay | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} | c0a8-0057-12c3b72e831-a5cbd326-ff51-8 | MF-HQ-12186 | HT - HALO TRUST | H/2157 | 89000 | 68.7463 | 34.0511 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} |  | High with Victim | High with Victims | High | 157 | CHA | 2 |  |  | 2004-12-04 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Sisay | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} | c0a8-0057-12c3b7341c5-16b5fede-1038e- | MF-HQ-12182 | HT - HALO TRUST | H/2156 | 110000 | 68.7496 | 34.0396 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} |  | High with Victim | High with Victims | High | 200 | CHA | 2 |  |  | 2004-12-04 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Sisay | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} | c0a8-0057-12c3b7787de-8f970c9c-13618- | MF-HQ-12243 | HT - HALO TRUST | H/2159 | 160000 | 68.7411 | 34.0395 | Open | AP Only | AP Only | MineField |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} |  | High with Victim | High with Victims | High | 368 | CHA | 2 |  |  | 2004-12-15 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Sisay | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} | c0a8-0057-12c3b81fbca-c55b32ab-1ad6e- | MF-HQ-12686 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03473/MF0029 | 40000 | 68.7426 | 34.0406 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} |  | High with Victim | High with Victims | High | 368 | SHA | 2 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Sisay | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} | c0a8-0057-12c3bb22463-b6f0f7ac-39ce5- | MF-HQ-12699 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03473/MF0030 | 66700 | 68.7371 | 34.0322 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-144 | Maydan Wardak Demining Project-03 |  |  |  |  | 1397 |  | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} |  | High with Victim | High with Victims | High | 367 | SHA | 2 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Sisay | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} | c0a8-0057-12c3bb378a7-3ac74849-3a963- | MF-HQ-12691 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03473/MF0028 | 34200 | 68.7371 | 34.0322 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-148 | Maydan Wardak Demining Project-02 (AT) |  |  |  |  | 1397 |  | {1ECC8CB5-FDCB-4058-B1D5-78F22D8749AE} |  | High with Victim | High with Victims | High | 367 | SHA | 2 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Sra Kala (3) | {F99EC8B8-09F1-4152-8EE9-F33D290D8911} | c0a8-0057-12c3b89c50d-ac14b95a-20529- | MF-HQ-12152 | HT - HALO TRUST | H/2132 | 11400 | 68.6868 | 34.0131 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {F99EC8B8-09F1-4152-8EE9-F33D290D8911} |  | Low | Agriculture Blocked | High | 42 | CHA | 5 |  |  | 2004-12-06 | No | Open
Central | Maydan Wardak | Saydabad | Sultankhel | {B330FD1A-1ABB-4ACC-B38E-65B7E87CE159} | c0a8-0057-12c3b80b0ba-9bc1fa2a-19ed7- | MF-HQ-10278 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0408/019/MF012A | 11420 | 68.6452 | 33.8783 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {B330FD1A-1ABB-4ACC-B38E-65B7E87CE159} |  | Low | Critical Infrastracture | High | 563 | SHA | 4 |  |  | 2009-05-17 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Sultankhel | {B330FD1A-1ABB-4ACC-B38E-65B7E87CE159} | c0a8-0057-12c3ba29a55-3eedaed-30846-5 | MF-HQ-12704 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03410/MF0061 | 88800 | 68.64 | 33.8751 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {B330FD1A-1ABB-4ACC-B38E-65B7E87CE159} |  | Low | Comunity Centers | High | 563 | SHA | 4 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Syahchob | {6F5CF487-F11E-4302-90CA-C6DE5770AC0D} | c0a8-0057-12c3b72fa1c-2765417-10029-c | MF-HQ-12202 | HT - HALO TRUST | H/2160 | 1500 | 68.7127 | 34.0041 | Open | AP Only | AP Only | MineField |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {6F5CF487-F11E-4302-90CA-C6DE5770AC0D} |  | Medium | Agriculture Blocked | High | 2277 | CHA | 3 |  |  | 2004-12-05 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Syahchob | {6F5CF487-F11E-4302-90CA-C6DE5770AC0D} | c0a8-0057-12c3bb7600e-7f2a7c8-3cced-b | MF-HQ-12599 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03465/MF0067 | 75000 | 68.7135 | 34.04 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {6F5CF487-F11E-4302-90CA-C6DE5770AC0D} |  | Low | Agriculture Blocked | High | 35 | SHA | 5 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Tagaw | {74A3D5AF-A23A-45E7-8858-7C594AED0C28} | c0a8-0057-12c3b84c73c-4997371e-1cda4- | MF-HQ-12659 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03618/MF0044 | 40000 | 68.8515 | 33.978 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-179 | Maydan Wardak Demining Project-06 |  |  |  |  | 1398 |  | {74A3D5AF-A23A-45E7-8858-7C594AED0C28} |  | Medium | Water Blocked | High | 616 | SHA | 3 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Towp Kalay | {8A101F54-CA19-48E3-B1EC-AC0C3BE252E2} | c0a8-0009-147c99b6342-906c6382-b6d-2d | Hz-ID-18891 | MCPA - Mine Clearance Planning Agency | AF/0407/03485/MF0075 | 25891 | 68.7811 | 34.1785 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {8A101F54-CA19-48E3-B1EC-AC0C3BE252E2} |  | Low | Critical Infrastracture | High | 383 | CHA | 4 |  |  | 2014-06-18 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Yawez | {D3C5EE04-CD64-404F-B51C-886348614FD2} | c0a8-0057-12c3b895db4-c2ca381e-200f7- | MF-HQ-12678 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03422/MF0060 | 40500 | 68.6393 | 34.0066 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-240 | Maydan Wardak Demining Project-05 (AT) |  |  |  |  | 1400 |  | {D3C5EE04-CD64-404F-B51C-886348614FD2} |  | Low | Agriculture Blocked | High | 165 | SHA | 4 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Zarnay | {B077AF90-4F60-4AFD-9B16-1E6B9BD23F50} | c0a8-0057-12c3bb22878-497c2ebb-39d0a- | MF-HQ-12651 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03480/MF0052 | 50000 | 68.7617 | 34.1122 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {B077AF90-4F60-4AFD-9B16-1E6B9BD23F50} |  | Low | Agriculture Blocked | High | 174 | SHA | 5 |  |  | 2009-07-06 | No | Open
Central | Maydan Wardak | Saydabad | Zarsang | {8F00FBB1-80B8-4580-9002-2F904D11D452} | c0a8-0057-12c3b6bee4b-33628d1c-aa92-f | MF-HQ-12242 | HT - HALO TRUST | H/2166 | 12000 | 68.7128 | 34.0748 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {8F00FBB1-80B8-4580-9002-2F904D11D452} |  | Low | Agriculture Blocked | High | 281 | CHA | 5 |  |  | 2008-04-04 16:30 | No | Open
Central | Maydan Wardak | Saydabad | Zarsang | {8F00FBB1-80B8-4580-9002-2F904D11D452} | c0a8-0057-12c3b6f8717-824d3a5b-d660-f | MF-HQ-12185 | HT - HALO TRUST | H/2167 | 75000 | 68.7322 | 34.0731 | Open | AP Only | AP Only | MineField |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {8F00FBB1-80B8-4580-9002-2F904D11D452} |  | Low | Agriculture Blocked | High | 20 | CHA | 5 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Zarsang | {8F00FBB1-80B8-4580-9002-2F904D11D452} | c0a8-0057-12c3b740955-98b2eee5-10ce7- | MF-HQ-12191 | HT - HALO TRUST | H/2165 | 46000 | 68.7512 | 34.0662 | Open | AT Only | AT Only | MineField |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {8F00FBB1-80B8-4580-9002-2F904D11D452} |  | Low | Critical Infrastracture | High | 83 | CHA | 5 |  |  | 2009-09-12 | No | Open
Central | Maydan Wardak | Saydabad | Zarsang | {8F00FBB1-80B8-4580-9002-2F904D11D452} | c0a8-0057-12c3b83d793-22ec8c30-1c296- | MF-HQ-12590 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03464/MF0048 | 21000 | 68.728 | 34.0741 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-299 | Maydan Wardak Demining Project-07 (AT) |  |  |  |  | 1399 |  | {8F00FBB1-80B8-4580-9002-2F904D11D452} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-07-05 | No | Open
Central | Maydan Wardak | Saydabad | Zarsang | {8F00FBB1-80B8-4580-9002-2F904D11D452} | c0a8-0057-12c3ba52011-e70d33ad-320b8- | MF-HQ-12594 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0407/03464/MF0047 | 15600 | 68.728 | 34.0741 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-278 | Maydan Wardak Demining Project-15 |  |  |  |  | 1399 |  | {8F00FBB1-80B8-4580-9002-2F904D11D452} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-07-05 | No | Open
Central | Panjsher | Bazarak | Astana | {C2FCD74D-A975-4BA4-AACD-521BC74F1408} | c0a8-0057-12c3b8e6d41-f621689f-2392f- | MF-CA-1789 | MCPA - Mine Clearance Planning Agency | AF/0310/01266/MF025 | 52900 | 69.5608 | 35.3876 | Open | AP Only | AP Only | MineField | Blank | MBT Project-068 | Panjshir Demining Project-05 |  | No |  |  | 1394 | None | {C2FCD74D-A975-4BA4-AACD-521BC74F1408} |  | High with Victim | High with Victims | Minimal | 3 | CHA | 2 |  |  | 2008-11-10 | No | Open
Central | Panjsher | Bazarak | Astana | {C2FCD74D-A975-4BA4-AACD-521BC74F1408} | c0a8-0057-12c3b95dda3-64b6c6fb-28725- | MF-CA-1791 | MCPA - Mine Clearance Planning Agency | AF/0310/01266/MF0018 | 75448 | 69.5488 | 35.357 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-017 | Panjshir Demining Project-01 | DOS | Yes |  |  | 1392 | OMAR | {C2FCD74D-A975-4BA4-AACD-521BC74F1408} |  |  |  | Minimal | 1 | CHA | 2 |  |  | 2008-11-10 | No | Complete
Central | Panjsher | Bazarak | Astana | {C2FCD74D-A975-4BA4-AACD-521BC74F1408} | c0a8-0057-12c3ba087f4-4d6aa8a-2f442-7 | MF-CA-1792 | MCPA - Mine Clearance Planning Agency | AF/0310/01266/MF010 | 66198 | 69.5742 | 35.3502 | Open | Mixed | Mixed AP UXO | MineField | Blank | MBT Project-068 | Panjshir Demining Project-05 |  | No |  |  | 1394 | None | {C2FCD74D-A975-4BA4-AACD-521BC74F1408} | , | High with Victim | High with Victims | Minimal | 7 | CHA | 2 |  |  | 2008-11-10 | No | Open
Central | Panjsher | Bazarak | Barak | {3CF6D48F-A159-4423-8208-49D7D06F3527} | c0a8-0057-12c3bab5f52-ae7aae0-35beb-6 | MF-CA-1801 | MCPA - Mine Clearance Planning Agency | AF/0310/01270/MF007 | 209500 | 69.5976 | 35.3781 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 | None | {3CF6D48F-A159-4423-8208-49D7D06F3527} | Planned year removed | Medium | Agriculture Blocked | Minimal | 10 | CHA | 3 |  |  | 2008-10-12 | No | Open
Central | Panjsher | Bazarak | Nolawa | {6D93762E-0614-4041-9A1F-8710F0EE1CEE} | c0a8-0057-12c3b8184d8-83b8cfa7-1a82f- | MF-CA-1779 | MCPA - Mine Clearance Planning Agency | AF/0310/01240/MF0016 | 121220 | 69.4884 | 35.2739 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {6D93762E-0614-4041-9A1F-8710F0EE1CEE} | Will be extended to 3rd quarter |  |  | Minimal | 139 | CHA | 4 |  |  | 2008-10-19 | No | Complete
Central | Panjsher | Bazarak | Parakh | {BBB57EA2-4D5E-452F-856D-8C69E998598B} | c0a8-0057-12c3bb7016c-5597344e-3c9b8- | MF-CA-1793 | MCPA - Mine Clearance Planning Agency | AF/0310/01237/MF0012 | 58132 | 69.4799 | 35.3049 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-017 | Panjshir Demining Project-01 | DOS | Yes |  |  | 1392 | OMAR | {BBB57EA2-4D5E-452F-856D-8C69E998598B} |  |  |  | Minimal | 10 | CHA | 2 |  |  | 2008-11-10 | No | Complete
Central | Panjsher | Bazarak | Sanguna | {D0E65A26-CDEA-4937-9D79-D03217511102} | c0a8-0057-12c3b838b48-a67bc76b-1bf26- | MF-CA-1784 | MCPA - Mine Clearance Planning Agency | AF/0310/01264/MF015 | 10350 | 69.5802 | 35.3749 | Open | AT Only | AT Only | MineField | Blank | MBT Project-068 | Panjshir Demining Project-05 |  | No |  |  | 1394 | None | {D0E65A26-CDEA-4937-9D79-D03217511102} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2008-10-19 | No | Open
Central | Panjsher | Khenj (Hese- Awal) | Anjoman | {E7F9EEE2-7559-41C6-AFFE-C7B3124661B0} | c0a8-0009-141a0fd7e84-9b9c2170-3a73-b | Hz-ID-18185 | HT - HALO TRUST | H/8516 | 22600 | 69.7126 | 35.4339 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes | 2014-06-01 | 2014-07-15 | 1393 | HT | {E7F9EEE2-7559-41C6-AFFE-C7B3124661B0} |  |  |  | Minimal | 95 | CHA | 5 |  |  | 2013-09-08 16:30 | No | Planned
Central | Panjsher | Khenj (Hese- Awal) | Anjoman | {E7F9EEE2-7559-41C6-AFFE-C7B3124661B0} | c0a8-0009-14227aa07d3-ae0bba29-412a-c | Hz-ID-18204 | HT - HALO TRUST | H/8520 | 3300 | 69.7123 | 35.4355 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes | 2014-06-01 | 2014-06-16 | 1393 | HT | {E7F9EEE2-7559-41C6-AFFE-C7B3124661B0} |  |  |  | Minimal | 80 | CHA | 3 |  |  | 2013-10-08 16:30 | No | Planned
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-0057-12c3ba13d7a-e399b8ae-2fb27- | MF-HQ-14119 | HT - HALO TRUST | AF/0311/01307/MF0025 | 147000 | 69.8677 | 35.5023 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes | 2014-06-17 | 2014-11-23 | 1393 | HT | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Medium | Critical Infrastracture | Minimal | 3 | CHA | 3 |  |  | 2010-02-01 | No | Planned
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-0057-12c3ba76c56-f73942b0-3376c- | MF-HQ-13504 | HT - HALO TRUST | H/8095 | 28800 | 69.8605 | 35.5018 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Low | Agriculture Blocked | Minimal | 2 | CHA | 5 |  |  | 2011-07-22 16:30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-0057-12c3ba76e69-79c625d7-33782- | MF-HQ-13506 | MCPA - Mine Clearance Planning Agency | AF/0311/01306/MF003 | 278450 | 69.8653 | 35.5022 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2008-11-13 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-0057-12dc627cdb5-8a913750-5b6-93 | MF-HQ-14117 | HT - HALO TRUST | H/8090 | 31000 | 69.847 | 35.5011 | Open | Mixed Mine | Mixed Mine | MineField | Blank | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | None | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Medium | Critical Infrastracture | Minimal | 21 | CHA | 3 |  |  | 2011-07-13 16:30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-00f6-1353dccb681-27e8e7c1-19c7-c | MF-16669 | HT - HALO TRUST | H/8091 | 37000 | 69.847 | 35.5011 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Low | Agriculture Blocked | Minimal | 21 | CHA | 5 |  |  | 2011-07-15 16:30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-00f6-1353dce02f7-ce3f8acd-19dc-b | MF-16668 | HT - HALO TRUST | H/8088 | 33000 | 69.847 | 35.5011 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Medium | Critical Infrastracture | Minimal | 19 | CHA | 3 |  |  | 2011-07-09 16:30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-00f6-1353dcfbe53-40b384df-19f4-3 | MF-16667 | HT - HALO TRUST | H/8087 | 37500 | 69.847 | 35.5011 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Medium | Critical Infrastracture | Minimal | 87 | CHA | 3 |  |  | 2011-07-07 16:30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-00f6-1353dd1fd00-3cb83140-1a0b-b | MF-16670 | HT - HALO TRUST | H/8086 | 32500 | 69.847 | 35.5011 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Medium | Critical Infrastracture | Minimal | 87 | CHA | 3 |  |  | 2011-07-05 16:30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-00f6-1353ddd9080-88f4833a-1a56-5 | MF-16662 | HT - HALO TRUST | H/8092 | 28000 | 69.847 | 35.5011 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Low | Agriculture Blocked | Minimal | 19 | CHA | 5 |  |  | 2011-07-18 16:30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-00f6-1353ddfb651-9186256c-1a6c-2 | MF-16661 | HT - HALO TRUST | H/8093 | 27500 | 69.847 | 35.5011 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Low | Agriculture Blocked | Minimal | 19 | CHA | 5 |  |  | 2011-07-20 16:30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-00f6-1353dec1f17-a8b4a266-1aaa-7 | MF-16659 | HT - HALO TRUST | H/8089 | 33750 | 69.847 | 35.5011 | Open | Mixed Mine | Mixed Mine | MineField | Blank | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | None | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Medium | Critical Infrastracture | Minimal | 19 | CHA | 3 |  |  | 2011-07-11 16:30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dahane Rewat | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} | c0a8-00f6-135515d3848-34317a07-20d-e3 | MF-16558 | HT - HALO TRUST | H/8094 | 27000 | 69.8605 | 35.5018 | Open | AP Only | AP Only | MineField | Blank | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | None | {03F7C535-BA40-437E-ABAB-BD3EFE4B9430} |  | Low | Agriculture Blocked | Minimal | 2 | CHA | 5 |  |  | 2011-07-21 16:30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dashti Rewat | {150C91E9-179B-497F-9668-E50CBF926ECE} | c0a8-0057-12c3b7ef2dc-cbe24e47-18ac5- | MF-HQ-13481 | MCPA - Mine Clearance Planning Agency | AF/0311/01307/MF022 | 81174 | 69.8201 | 35.4905 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes | 2014-09-01 | 2014-11-23 | 1393 | HT | {150C91E9-179B-497F-9668-E50CBF926ECE} |  | Medium | Critical Infrastracture | Minimal | 0 | CHA | 3 |  |  | 2009-08-08 | No | Planned
Central | Panjsher | Khenj (Hese- Awal) | Dashti Rewat | {150C91E9-179B-497F-9668-E50CBF926ECE} | c0a8-0057-12c3b7ef4c0-28cd69dd-18adc- | MF-HQ-13483 | MCPA - Mine Clearance Planning Agency | AF/0311/01307/MF0023 | 95232 | 69.8201 | 35.4905 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes |  |  | 1393 | HT | {150C91E9-179B-497F-9668-E50CBF926ECE} |  | Medium | Critical Infrastracture | Minimal | 0 | CHA | 3 |  |  | 2009-11-10 | No | Planned
Central | Panjsher | Khenj (Hese- Awal) | Dashti Rewat | {150C91E9-179B-497F-9668-E50CBF926ECE} | c0a8-0057-12c3b80c7d2-57138df-19fb5-9 | MF-HQ-13486 | MCPA - Mine Clearance Planning Agency | AF/0311/01307/MF0001 | 164412 | 69.8351 | 35.4848 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {150C91E9-179B-497F-9668-E50CBF926ECE} |  | Low | Agriculture Blocked | Minimal | 21 | CHA | 5 |  |  | 2008-11-11 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Dornama | {3FBE404C-FA97-4545-BB97-66527A69AC90} | c0a8-008e-13426b14ad0-45f9bb8b-88-464 | MF-16402 | HT - HALO TRUST | H/8341 | 35800 | 69.8376 | 35.506 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {3FBE404C-FA97-4545-BB97-66527A69AC90} |  |  |  | Minimal | 4622 | CHA | 4 |  |  | 2011-11-18 16:30 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Dornama | {3FBE404C-FA97-4545-BB97-66527A69AC90} | c0a8-008e-13426f3bd38-1eb560fb-567-a6 | MF-16401 | HT - HALO TRUST | H/8345 | 46800 | 69.8339 | 35.5031 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-067 | Panjshir Demining Project-02 | DOS | Yes | 2013-10-01 | 2013-11-24 | 1392 | DDG | {3FBE404C-FA97-4545-BB97-66527A69AC90} |  |  |  | Minimal | 4738 | CHA | 3 |  |  | 2011-11-20 16:30 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Dornama | {3FBE404C-FA97-4545-BB97-66527A69AC90} | c0a8-008e-1342cc2d7dc-b2f37802-49c-cb | MF-16413 | HT - HALO TRUST | H/8342 | 35400 | 69.8376 | 35.506 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {3FBE404C-FA97-4545-BB97-66527A69AC90} |  |  |  | Minimal | 4690 | CHA | 4 |  |  | 2011-11-21 16:30 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Kharu | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} | c0a8-0009-141a0fb037f-1c8147dd-3a4e-1 | Hz-ID-18184 | HT - HALO TRUST | H/8515 | 60000 | 69.6851 | 35.431 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes | 2014-06-01 | 2014-07-23 | 1393 | HT | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} |  |  |  | Minimal | 12 | CHA | 5 |  |  | 2013-09-07 16:30 | No | Planned
Central | Panjsher | Khenj (Hese- Awal) | Kharu | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} | c0a8-0009-147c8a9b601-80ef37b7-b31-3a | Hz-ID-18882 | HT - HALO TRUST | B/3204 | 4 | 69.6979 | 35.4197 | Open | UXO Only | UXO Only | BF |  | MBT Project-111 | Panjshir Demining Project-04 | DOS |  |  |  | 1393 |  | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} |  | High | Critical Infrastracture | Minimal | 85 | CHA | 2 |  |  | 2014-07-20 16:30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Kharu | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} | c0a8-008e-132c7d1b7ec-fef03364-150f-5 | MF-16282 | HT - HALO TRUST | H/8158 | 42500 | 69.6916 | 35.4135 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-067 | Panjshir Demining Project-02 | DOS | Yes | 2013-07-11 | 2013-11-24 | 1392 | DDG | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} |  |  |  | Minimal | 10 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2011-08-20 16:30 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Kharu | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} | c0a8-008e-132c7d402d7-46249ddd-1527-7 | MF-16280 | HT - HALO TRUST | H/8156 | 42500 | 69.6916 | 35.4135 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-067 | Panjshir Demining Project-02 | DOS | Yes | 2013-09-18 | 2013-11-24 | 1392 | DDG | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} |  |  |  | Minimal | 1294 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2011-08-16 16:30 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Kharu | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} | c0a8-008e-132c7db02bd-be567166-156a-2 | MF-16277 | HT - HALO TRUST | H/8110 | 28210 | 69.695 | 35.4096 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} |  |  |  | Minimal | 2737 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2011-08-13 16:30 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Kharu | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} | c0a8-008e-132c7dd67eb-e1523f19-157e-6 | MF-16276 | HT - HALO TRUST | H/8109 | 26242 | 69.695 | 35.4066 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-067 | Panjshir Demining Project-02 | DOS | Yes | 2013-10-01 | 2013-11-24 | 1392 | DDG | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} |  |  |  | Minimal | 1470 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2011-08-10 16:30 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Kharu | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} | c0a8-008e-132c8792273-4997873c-2326-6 | MF-16275 | HT - HALO TRUST | H/8107 | 2683 | 69.6962 | 35.4043 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-067 | Panjshir Demining Project-02 | DOS | Yes | 2013-10-01 | 2013-11-24 | 1392 | DDG | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} |  |  |  | Minimal | 1470 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2011-08-06 16:30 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Kharu | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} | c0a8-008e-132c8819c33-ec7ffad7-2489-7 | MF-16274 | HT - HALO TRUST | H/8108 | 20860 | 69.695 | 35.4096 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} |  |  |  | Minimal | 2737 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2011-08-08 16:30 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Kharu | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} | c0a8-008e-132e8320b74-8249efc4-c62-17 | MF-16281 | HT - HALO TRUST | H/8157 | 32500 | 69.6916 | 35.4135 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-067 | Panjshir Demining Project-02 | DOS | Yes | 2013-10-01 | 2013-11-24 | 1392 | DDG | {5E0B3256-D176-4B58-B367-6B2A769FEA8C} |  |  |  | Minimal | 10 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2011-08-18 16:30 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Mata | {F0340E0C-F4BD-4800-B828-82B233193BED} | c0a8-0009-14490780a25-93668da0-35a-10 | Hz-ID-18543 | HT - HALO TRUST | H/8532 | 29000 | 69.7332 | 35.4476 | Closed | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes | 2014-06-01 | 2014-07-15 | 1393 | HT | {F0340E0C-F4BD-4800-B828-82B233193BED} |  |  |  | Minimal | 140 | CHA | 5 |  |  | 2014-02-11 16:30 | No | Planned
Central | Panjsher | Khenj (Hese- Awal) | Mata | {F0340E0C-F4BD-4800-B828-82B233193BED} | c0a8-0009-1449088510a-b6ffe6d3-3d6-d2 | Hz-ID-18542 | HT - HALO TRUST | H/8531 | 5000 | 69.7355 | 35.435 | Closed | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes | 2014-06-01 | 2014-07-09 | 1393 | HT | {F0340E0C-F4BD-4800-B828-82B233193BED} |  |  |  | Minimal | 366 | CHA | 5 |  |  | 2014-02-09 16:30 | No | Planned
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3b92ad72-fa746bda-2652e- | MF-HQ-13458 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0016 | 52000 | 69.7093 | 35.3877 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 18 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2009-07-28 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3b92af55-2b0e843e-26543- | MF-HQ-13454 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0014 | 52000 | 69.7093 | 35.3877 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 18 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2009-07-25 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3b92b139-93672d04-26558- | MF-HQ-13453 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0013 | 63290 | 69.7134 | 35.3863 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2009-07-22 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3b92b2fd-89135407-2656c- | MF-HQ-13455 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0015 | 52000 | 69.7093 | 35.3877 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 18 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2009-07-27 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3b92b4f0-749471d6-2657f- | MF-HQ-13452 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0012 | 64606 | 69.7134 | 35.3863 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2009-07-20 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3b92b6f3-2465394b-26596- | MF-HQ-13460 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0021 | 81073 | 69.7337 | 35.3835 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2009-07-30 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3b92b8f6-f69fa775-265af- | MF-HQ-13451 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0011 | 65205 | 69.7134 | 35.3863 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2009-07-18 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3b9e2f9e-9159fbb4-2dd28- | MF-HQ-13463 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF017 | 79932 | 69.7272 | 35.3907 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2009-08-01 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3b9e31a1-27490f51-2dd3b- | MF-HQ-13465 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0018 | 113906 | 69.7272 | 35.3907 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2009-08-02 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3b9e3394-735214a0-2dd4e- | MF-HQ-13467 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0019 | 77780 | 69.7272 | 35.3907 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2009-08-04 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3b9e35c6-39fce112-2dd61- | MF-HQ-13469 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0020 | 58012 | 69.7272 | 35.3907 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2009-08-05 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3ba22279-ed8e9ca4-303de- | MF-HQ-13478 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0009 | 150000 | 69.6838 | 35.4054 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-111 | Panjshir Demining Project-04 | DOS | No |  |  | 1393 | WRA | {E2961033-93E4-476B-8534-071BF406937E} |  | High Requested | Resettlment/Local Request | Minimal | 45 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2008-11-13 | No | Pledged
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3ba2247c-930780a0-303ef- | MF-HQ-13476 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0008 | 150000 | 69.6838 | 35.4054 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {E2961033-93E4-476B-8534-071BF406937E} |  |  |  | Minimal | 177 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2008-11-11 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Peshghor | {E2961033-93E4-476B-8534-071BF406937E} | c0a8-0057-12c3bb51a2f-da0b4577-3b8c6- | MF-HQ-13472 | MCPA - Mine Clearance Planning Agency | AF/0311/01286/MF0010 | 75000 | 69.6921 | 35.4095 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {E2961033-93E4-476B-8534-071BF406937E} |  |  |  | Minimal | 1294 | CHA | 1 | Yes | Confirmed have animals accident Repeatedly | 2008-11-15 | No | Complete
Central | Panjsher | Khenj (Hese- Awal) | Rakh | {14473BD8-AA7B-4EED-A71E-5A7162E5595F} | c0a8-0009-144961f58a2-d66581fd-fce-a4 | Hz-ID-18540 | HT - HALO TRUST | H/8530 | 5500 | 69.7264 | 35.437 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes | 2014-06-01 | 2014-06-17 | 1393 | HT | {14473BD8-AA7B-4EED-A71E-5A7162E5595F} |  |  |  | Minimal | 16 | CHA | 5 |  |  | 2014-02-07 16:30 | No | Planned
Central | Panjsher | Khenj (Hese- Awal) | Safaid Chahr | {74FE24C3-EF42-4D9E-BC41-7099826DF66C} | c0a8-0057-12c3b8b90ef-5a1b1987-2191f- | MF-HQ-13517 | MCPA - Mine Clearance Planning Agency | AF/0311/00354/MF0005 | 14360 | 69.7718 | 35.4599 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes | 2014-08-01 | 2014-08-23 | 1393 | HT | {74FE24C3-EF42-4D9E-BC41-7099826DF66C} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 3 |  |  | 2008-11-11 | No | Planned
Central | Panjsher | Khenj (Hese- Awal) | Safaid Chahr | {74FE24C3-EF42-4D9E-BC41-7099826DF66C} | c0a8-0057-12c3b921d8a-9d5a4224-25f83- | MF-HQ-13514 | MCPA - Mine Clearance Planning Agency | AF/0311/00354/MF0004 | 19910 | 69.7718 | 35.4599 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes | 2014-08-01 | 2014-09-23 | 1393 | HT | {74FE24C3-EF42-4D9E-BC41-7099826DF66C} |  | Medium | Critical Infrastracture | Minimal | 0 | CHA | 3 |  |  | 2008-11-10 | No | Planned
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c075b25-ac0a3bc1-a8a-bd | Hz-ID-18706 | HT - HALO TRUST | H/8777 | 57510 | 69.8766 | 35.6197 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-24 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c0a7b70-12fe203c-aad-63 | Hz-ID-18707 | HT - HALO TRUST | H/8776 | 77650 | 69.8848 | 35.6206 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-23 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c0bf262-ff46a299-acf-c0 | Hz-ID-18708 | HT - HALO TRUST | H/8775 | 56250 | 69.8848 | 35.6206 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 13 | CHA | 5 |  |  | 2014-04-22 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c0fd263-3b3498d6-af0-d4 | Hz-ID-18709 | HT - HALO TRUST | H/8774 | 60012 | 69.8766 | 35.6197 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-21 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c12373c-8cd92abc-b12-2b | Hz-ID-18710 | HT - HALO TRUST | H/8773 | 58525 | 69.8766 | 35.6197 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-20 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c166fe6-22117bd9-b35-5b | Hz-ID-18711 | HT - HALO TRUST | H/8772 | 33751 | 69.8806 | 35.6114 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-20 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c18db16-9074cab8-b58-58 | Hz-ID-18712 | HT - HALO TRUST | H/8771 | 52100 | 69.8766 | 35.6197 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 11 | CHA | 5 |  |  | 2014-04-19 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c3556bf-d07480bb-bf9-46 | Hz-ID-18713 | HT - HALO TRUST | H/8770 | 82500 | 69.8766 | 35.6197 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 11 | CHA | 5 |  |  | 2014-04-18 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c48ca60-20b3f82d-c7c-3b | Hz-ID-18714 | HT - HALO TRUST | H/8769 | 60110 | 69.8766 | 35.6197 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-17 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c4ba7b2-b067028a-ca1-83 | Hz-ID-18715 | HT - HALO TRUST | H/8768 | 36253 | 69.8806 | 35.6114 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-16 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c581982-b5b2999e-cd0-1d | Hz-ID-18716 | HT - HALO TRUST | H/8767 | 42305 | 69.8806 | 35.6114 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 11 | CHA | 5 |  |  | 2014-04-15 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c598af9-2073041f-cf2-4c | Hz-ID-18717 | HT - HALO TRUST | H/8766 | 43150 | 69.8843 | 35.6111 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 11 | CHA | 5 |  |  | 2014-04-15 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c5bc53a-450f8f39-d14-7c | Hz-ID-18718 | HT - HALO TRUST | H/8765 | 65250 | 69.8843 | 35.6111 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 11 | CHA | 5 |  |  | 2014-04-14 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c5d3116-2aca11b9-d38-32 | Hz-ID-18719 | HT - HALO TRUST | H/8764 | 56100 | 69.8843 | 35.6111 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 11 | CHA | 5 |  |  | 2014-04-13 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c92e9b4-f802882a-de6-68 | Hz-ID-18720 | HT - HALO TRUST | H/8763 | 50100 | 69.8843 | 35.6111 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 11 | CHA | 5 |  |  | 2014-04-12 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c93bc5d-f54c723e-e2c-35 | Hz-ID-18724 | HT - HALO TRUST | H/8761 | 52750 | 69.8843 | 35.6111 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 11 | CHA | 5 |  |  | 2014-04-10 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c940158-ed0d4665-eaa-97 | Hz-ID-18725 | HT - HALO TRUST | H/8760 | 36250 | 69.8895 | 35.609 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-09 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c9445b8-88455c2f-ecf-60 | Hz-ID-18726 | HT - HALO TRUST | H/8759 | 50176 | 69.8895 | 35.609 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-09 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c948eb8-27e0b24a-ef2-b8 | Hz-ID-18727 | HT - HALO TRUST | H/8758 | 69518 | 69.8895 | 35.609 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-08 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c94d662-f9808f99-f16-33 | Hz-ID-18728 | HT - HALO TRUST | H/8757 | 66333 | 69.8895 | 35.609 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-07 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c951ec7-54072589-f39-91 | Hz-ID-18729 | HT - HALO TRUST | H/8756 | 57560 | 69.8895 | 35.609 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-07 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c95730e-9343de00-f5c-48 | Hz-ID-18730 | HT - HALO TRUST | H/8755 | 50135 | 69.8895 | 35.609 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-06 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c95c207-85dec3cb-f7f-7f | Hz-ID-18731 | HT - HALO TRUST | H/8754 | 57521 | 69.8895 | 35.609 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-05 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c960ad9-2ecdfcca-fa3-30 | Hz-ID-18732 | HT - HALO TRUST | H/8753 | 52506 | 69.8843 | 35.6111 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 11 | CHA | 5 |  |  | 2014-04-04 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1463c964bee-8624714b-fc8-e7 | Hz-ID-18733 | HT - HALO TRUST | H/8752 | 35111 | 69.8895 | 35.609 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-03 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-1468984183c-10f56ba1-221c-f | Hz-ID-18721 | HT - HALO TRUST | H/8762 | 55220 | 69.8843 | 35.6117 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-04-11 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0009-147c986f29d-897ddb5b-6e9-92 | Hz-ID-18903 | HT - HALO TRUST | H/8812 | 37503 | 69.8892 | 35.6093 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-07-19 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-0057-12dc626d018-eaf1194d-582-c5 | MF-HQ-13487 | MCPA - Mine Clearance Planning Agency | AF/0311/01276/MF0024 | 256349 | 69.8894 | 35.6344 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 260 | CHA | 5 |  |  | 2009-08-13 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-1328f83dc13-55081332-13d6-e | MF-16166 | HT - HALO TRUST | H/8029 | 40260 | 69.7824 | 35.6638 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 3 | CHA | 5 |  |  | 2011-06-12 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-1328f84768c-1a94823e-1400-5 | MF-16167 | HT - HALO TRUST | H/8030 | 42775 | 69.7824 | 35.6638 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-06-12 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-1328f92db45-da7733fa-1aa9-9 | MF-16162 | HT - HALO TRUST | H/8025 | 48600 | 69.7824 | 35.6638 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 3 | CHA | 5 |  |  | 2011-06-14 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-1328f9690d1-4ac8f362-1af5-8 | MF-16163 | HT - HALO TRUST | H/8026 | 37770 | 69.7824 | 35.6638 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-06-17 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-1328ffaa506-3bb32513-3057-e | MF-16165 | HT - HALO TRUST | H/8028 | 47700 | 69.7824 | 35.6638 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-06-18 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-1329071f7e5-b6adf4bb-2-19c0 | MF-16164 | HT - HALO TRUST | H/8027 | 57610 | 69.7824 | 35.6638 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 3 | CHA | 5 |  |  | 2011-06-15 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132908d91cc-f9fc7d17-109-39 | MF-16158 | HT - HALO TRUST | H/8022 | 25323 | 69.7824 | 35.6638 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} | Removed from HALO Trust plan based on e-mail received on 16th August 2012 | Low | Agriculture Blocked | Minimal | 3 | CHA | 5 |  |  | 2011-06-08 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-13290a6a664-db489e4a-3c7-f2 | MF-16160 | HT - HALO TRUST | H/8023 | 55640 | 69.7824 | 35.6638 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} | Removed from HALO Trust plan based on e-mail received on 16th August 2012 | Low | Agriculture Blocked | Minimal | 3 | CHA | 5 |  |  | 2011-06-19 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132ae90917d-626167f0-12d7-3 | MF-16271 | HT - HALO TRUST | H/8127 | 30600 | 69.7791 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-08-10 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132ae93842a-20d18a5d-12eb-4 | MF-16272 | HT - HALO TRUST | H/8128 | 34750 | 69.7791 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-08-13 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132ae95cbbd-936f2a47-133f-6 | MF-16267 | HT - HALO TRUST | H/8098 | 33600 | 69.7791 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-08-06 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132c9251b4a-fc996252-2a00-a | BF-15010 | HT - HALO TRUST | B/2908 | 60 | 69.8353 | 35.6522 | Open | UXO Only | UXO Only | BF |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} | Based on HALO Trust confirmation, the hazard removed from their plan | Medium | Agriculture Blocked | Minimal | 174 | CHA | 3 |  |  | 2010-11-04 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132c958ff88-8ea6d980-3149-8 | MF-15525 | HT - HALO TRUST | H/7592 | 35490 | 69.7739 | 35.6647 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 62 | CHA | 5 |  |  | 2010-11-08 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132c9591ef4-a302f26-3163-97 | MF-15527 | HT - HALO TRUST | H/7601 | 50000 | 69.7395 | 35.6647 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 25 | CHA | 5 |  |  | 2010-11-13 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132cd2d41b8-3d5ee28c-9b-130 | MF-16273 | HT - HALO TRUST | H/8129 | 33920 | 69.7791 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-08-14 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132cd2ea412-47938033-f6-967 | MF-16270 | HT - HALO TRUST | H/8100 | 33800 | 69.7791 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-08-09 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132f62b4797-73ac34e8-4dc-69 | MF-16263 | HT - HALO TRUST | H/8130 | 26400 | 69.7791 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-08-16 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132f62c9ac8-1eae16a9-51e-85 | MF-16258 | HT - HALO TRUST | H/8133 | 35520 | 69.7791 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-08-19 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132f62d186c-a03f60b5-535-d2 | MF-16257 | HT - HALO TRUST | H/8132 | 24480 | 69.7791 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-08-18 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-008e-132f62d8f6c-e1dea4-552-61d9 | MF-16256 | HT - HALO TRUST | H/8131 | 33120 | 69.7791 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-08-17 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-13518a38c1c-82858b4-637-f16 | MF-16545 | HT - HALO TRUST | H/8185 | 37500 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2011-09-24 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1352e72bfc4-e3c69486-18a-36 | MF-16561 | HT - HALO TRUST | H/8035 | 27732 | 69.7627 | 35.6667 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 62 | CHA | 5 |  |  | 2011-07-07 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-13531fda9b7-374e9275-249-7b | MF-16577 | HT - HALO TRUST | H/8102 | 20456 | 69.7739 | 35.6647 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 25 | CHA | 5 |  |  | 2011-07-11 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-135325d027e-d681b42c-4a9-f6 | BF-15181 | HT - HALO TRUST | B/2511 | 450000 | 69.8091 | 35.6665 | Open | UXO Only | UXO Only | BF |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} | Based on HALO Trust confirmation, the hazard is removed from their plan | Low | Agriculture Blocked | Minimal | 74 | CHA | 5 |  |  | 2011-08-21 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-13533a905e8-87848c5b-1ee-44 | MF-16603 | HT - HALO TRUST | H/8166 | 90000 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 87 | CHA | 5 |  |  | 2011-09-09 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-13533aaaf0a-9b85f18e-203-4a | MF-16602 | HT - HALO TRUST | H/8167 | 38100 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 26 | CHA | 5 |  |  | 2011-09-10 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-13533ad634f-2a243cdd-21d-ce | MF-16601 | HT - HALO TRUST | H/8169 | 39000 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 26 | CHA | 5 |  |  | 2011-09-12 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-13533b06833-d1588652-234-d8 | MF-16598 | HT - HALO TRUST | H/8173 | 25400 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2011-09-15 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-13538624028-de2afb0a-313-91 | MF-16612 | HT - HALO TRUST | H/8136 | 40000 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 62 | CHA | 5 |  |  | 2011-09-06 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-135386e8b99-d3d93916-32e-b7 | MF-16610 | HT - HALO TRUST | H/8181 | 32000 | 69.786 | 35.6633 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2011-09-21 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1353c621429-107f5054-11c7-5 | MF-16628 | HT - HALO TRUST | H/8177 | 35000 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2011-09-18 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1353c703c32-7f3aa9e-137c-6c | MF-16620 | HT - HALO TRUST | H/8174 | 169200 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 26 | CHA | 5 |  |  | 2011-09-16 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1353c9100b6-42a362d6-140c-e | MF-16625 | HT - HALO TRUST | H/8176 | 37500 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2011-09-17 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1353d45add8-12405125-1597-d | MF-16623 | HT - HALO TRUST | H/8175 | 33000 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2011-09-17 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1353d4672d9-2a787f88-15ad-b | MF-16611 | HT - HALO TRUST | H/8182 | 35200 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2011-09-21 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1353d473ba1-4d63359d-15c3-3 | MF-16632 | HT - HALO TRUST | H/8178 | 37000 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2011-09-19 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1353d6393ae-64a1f4ac-1766-4 | MF-16600 | HT - HALO TRUST | H/8171 | 35600 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2011-09-14 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1353d6d53c0-d82d1abc-17cd-c | MF-16569 | HT - HALO TRUST | H/8034 | 16448 | 69.7788 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} | Removed from HALO Trust plan based on e-mail received on 16th August 2012 | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-07-06 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1353d78ba86-5f4ca8cd-17f2-2 | MF-16574 | HT - HALO TRUST | H/8101 | 20469 | 69.7788 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} | Removed from HALO Trust plan based on e-mail received on 16th August 2012 | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2011-07-09 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1353db5da64-851402be-18e7-f | MF-16635 | HT - HALO TRUST | H/8179 | 38000 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2011-09-19 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1353db9f8be-b7cb205b-1901-4 | MF-16640 | HT - HALO TRUST | H/8184 | 37400 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 2 | CHA | 5 |  |  | 2011-09-23 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-135514c5154-72a696b8-18c-34 | MF-16637 | HT - HALO TRUST | H/8180 | 40000 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2011-09-20 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-135b90fb3d9-23bf93b5-1103-1 | MF-16697 | HT - HALO TRUST | H/8183 | 30000 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 2 | CHA | 5 |  |  | 2011-09-22 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-1392955557c-cdbc1132-33c-32 | Hz-ID-17234 | HT - HALO TRUST | H/8359 | 32532 | 69.8795 | 35.6325 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 8 | CHA | 5 |  |  | 2012-06-21 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-139aab67a91-3cbfb4b4-1d46-3 | Hz-ID-17235 | HT - HALO TRUST | H/8360 | 35500 | 69.8795 | 35.6325 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 8 | CHA | 5 |  |  | 2012-06-21 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-139aabc278f-c3e5d692-1d98-4 | Hz-ID-17232 | HT - HALO TRUST | H/8357 | 45103 | 69.8795 | 35.6325 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 8 | CHA | 5 |  |  | 2012-06-19 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-139aac7cf4d-b318138a-1e84-c | Hz-ID-17236 | HT - HALO TRUST | H/8361 | 32506 | 69.8798 | 35.6325 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 8 | CHA | 5 |  |  | 2012-06-22 16:30 | No | Open
Central | Panjsher | Paryan | Chawni Khawak | {C72EBBCF-6382-4119-ABBC-C296A9857810} | c0a8-00f6-13a3f2d32e6-255fab08-16e36- | Hz-ID-17233 | HT - HALO TRUST | H/8358 | 20113 | 69.8795 | 35.6325 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {C72EBBCF-6382-4119-ABBC-C296A9857810} |  | Low | Agriculture Blocked | Minimal | 28 | CHA | 5 |  |  | 2012-06-20 16:30 | No | Open
Central | Panjsher | Paryan | Dehe Khawak | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} | c0a8-0009-147c8b4c2c4-70113e34-ea4-ba | Hz-ID-18883 | HT - HALO TRUST | H/8802 | 51246 | 69.9236 | 35.6261 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2014-07-03 16:30 | No | Open
Central | Panjsher | Paryan | Dehe Khawak | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} | c0a8-0009-147c8b7c5bc-7967d5e-f5a-908 | Hz-ID-18884 | HT - HALO TRUST | H/8803 | 37550 | 69.9236 | 35.6261 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2014-07-05 16:30 | No | Open
Central | Panjsher | Paryan | Dehe Khawak | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} | c0a8-0009-147c8c046d7-12e46737-1400-1 | Hz-ID-18885 | HT - HALO TRUST | H/8804 | 32522 | 69.9236 | 35.6261 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2014-07-07 16:30 | No | Open
Central | Panjsher | Paryan | Dehe Khawak | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} | c0a8-0009-147c8cd6144-d0110d52-17d3-c | Hz-ID-18888 | HT - HALO TRUST | H/8806 | 41232 | 69.9236 | 35.6261 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-07-10 16:30 | No | Open
Central | Panjsher | Paryan | Dehe Khawak | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} | c0a8-0009-147c8cfcff6-e5e9baf3-1845-e | Hz-ID-18890 | HT - HALO TRUST | H/8807 | 33752 | 69.9236 | 35.6261 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-07-12 16:30 | No | Open
Central | Panjsher | Paryan | Dehe Khawak | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} | c0a8-0009-147c91fce08-49161f4e-22d-3b | Hz-ID-18892 | HT - HALO TRUST | H/8808 | 33748 | 69.9236 | 35.6261 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2014-07-14 16:30 | No | Open
Central | Panjsher | Paryan | Dehe Khawak | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} | c0a8-0009-147c9217200-1d9c1600-2c4-a8 | Hz-ID-18894 | HT - HALO TRUST | H/8809 | 37497 | 69.9236 | 35.6261 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2014-07-16 16:30 | No | Open
Central | Panjsher | Paryan | Dehe Khawak | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} | c0a8-0009-147c935f4b5-db896ace-586-a7 | Hz-ID-18897 | HT - HALO TRUST | H/8810 | 33750 | 69.9236 | 35.6261 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-07-17 16:30 | No | Open
Central | Panjsher | Paryan | Dehe Khawak | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} | c0a8-0009-147c9858b3b-e652a117-6c3-14 | Hz-ID-18900 | HT - HALO TRUST | H/8811 | 32488 | 69.9236 | 35.6261 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-07-18 16:30 | No | Open
Central | Panjsher | Paryan | Dehe Khawak | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} | c0a8-0009-147c9936a4a-a2c200b2-716-9f | Hz-ID-18886 | HT - HALO TRUST | H/8805 | 37542 | 69.9236 | 35.6261 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {D2839C96-A16D-4A5D-8B22-9ADEFC7C9174} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2014-07-09 16:30 | No | Open
Central | Panjsher | Paryan | Kamangar | {562C5830-B17F-4494-9636-1AC0AF44EAFF} | c0a8-0009-14375c0ab11-bde9b5ff-26a8-f | Hz-ID-18353 | HT - HALO TRUST | H/8525 | 39000 | 69.9067 | 35.5527 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes |  |  | 1393 | HT | {562C5830-B17F-4494-9636-1AC0AF44EAFF} |  | Low | Agriculture Blocked | Minimal | 2 | CHA | 5 |  |  | 2013-12-20 16:30 | No | Planned
Central | Panjsher | Paryan | Kure Mirzabeg | {A228DE70-2C64-452E-8D70-A7B12B0426D7} | c0a8-008e-132c947c587-a2ca9640-2d3b-5 | MF-15512 | HT - HALO TRUST | H/7579 | 29325 | 69.9163 | 35.5966 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {A228DE70-2C64-452E-8D70-A7B12B0426D7} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 1 | Yes | Confirmed have accident | 2010-10-31 16:30 | No | Open
Central | Panjsher | Paryan | Kure Mirzabeg | {A228DE70-2C64-452E-8D70-A7B12B0426D7} | c0a8-008e-132c947e96b-c3a1958d-2d4e-4 | MF-15511 | HT - HALO TRUST | H/7578 | 26000 | 69.9163 | 35.5966 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {A228DE70-2C64-452E-8D70-A7B12B0426D7} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 1 | Yes | Confirmed have accident | 2010-10-31 16:30 | No | Open
Central | Panjsher | Paryan | Kure Mirzabeg | {A228DE70-2C64-452E-8D70-A7B12B0426D7} | c0a8-008e-132c9480a34-e931ae65-2d61-9 | MF-15510 | HT - HALO TRUST | H/7577 | 29000 | 69.9163 | 35.5966 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {A228DE70-2C64-452E-8D70-A7B12B0426D7} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 1 | Yes | Confirmed have accident | 2010-10-30 16:30 | No | Open
Central | Panjsher | Paryan | Kure Mirzabeg | {A228DE70-2C64-452E-8D70-A7B12B0426D7} | c0a8-008e-132c957a3fe-e36b4224-308c-d | MF-15518 | HT - HALO TRUST | H/7585 | 37000 | 69.9161 | 35.5967 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {A228DE70-2C64-452E-8D70-A7B12B0426D7} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 1 | Yes | Confirmed have accident | 2010-11-03 16:30 | No | Open
Central | Panjsher | Paryan | Kure Mirzabeg | {A228DE70-2C64-452E-8D70-A7B12B0426D7} | c0a8-008e-132c957c57c-4d06006b-30a0-e | MF-15519 | HT - HALO TRUST | H/7586 | 56500 | 69.9163 | 35.5966 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {A228DE70-2C64-452E-8D70-A7B12B0426D7} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 1 | Yes | Confirmed have accident | 2010-11-03 16:30 | No | Open
Central | Panjsher | Paryan | Kure Mirzabeg | {A228DE70-2C64-452E-8D70-A7B12B0426D7} | c0a8-008e-132c957e3a1-820a1ec8-30b6-5 | MF-15516 | HT - HALO TRUST | H/7583 | 27500 | 69.9163 | 35.5966 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {A228DE70-2C64-452E-8D70-A7B12B0426D7} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 1 | Yes | Confirmed have accident | 2010-11-02 16:30 | No | Open
Central | Panjsher | Paryan | Kure Mirzabeg | {A228DE70-2C64-452E-8D70-A7B12B0426D7} | c0a8-008e-132c9580af8-7e0c0287-30cb-c | MF-15517 | HT - HALO TRUST | H/7584 | 35400 | 69.9163 | 35.5966 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {A228DE70-2C64-452E-8D70-A7B12B0426D7} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 1 | Yes | Confirmed have accident | 2010-11-02 16:30 | No | Open
Central | Panjsher | Paryan | Kure Mirzabeg | {A228DE70-2C64-452E-8D70-A7B12B0426D7} | c0a8-008e-132c9585a9f-ef17c677-30f3-5 | MF-15515 | HT - HALO TRUST | H/7582 | 29000 | 69.9163 | 35.5966 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {A228DE70-2C64-452E-8D70-A7B12B0426D7} |  | High Requested | Resettlment/Local Request | Minimal | 7 | CHA | 1 | Yes | Confirmed have accident | 2010-11-01 16:30 | No | Open
Central | Panjsher | Paryan | Kure Mirzabeg | {A228DE70-2C64-452E-8D70-A7B12B0426D7} | c0a8-008e-132c958bd46-65d6cd1f-311e-1 | MF-15513 | HT - HALO TRUST | H/7580 | 30500 | 69.9163 | 35.5966 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {A228DE70-2C64-452E-8D70-A7B12B0426D7} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 1 | Yes | Confirmed have accident | 2010-10-31 16:30 | No | Open
Central | Panjsher | Paryan | Kure Mirzabeg | {A228DE70-2C64-452E-8D70-A7B12B0426D7} | c0a8-008e-132c958def3-e5468e4c-3133-6 | MF-15514 | HT - HALO TRUST | H/7581 | 40500 | 69.9163 | 35.5966 | Open | AP Only | AP Only | MineField |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {A228DE70-2C64-452E-8D70-A7B12B0426D7} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 1 | Yes | Confirmed have accident | 2010-11-01 16:30 | No | Open
Central | Panjsher | Paryan | Kur-Petab | {E103AADF-A1F0-4B6C-AA6C-F0BE399A200A} | c0a8-0009-14636f7cb71-5c137fda-a62-af | Hz-ID-18705 | HT - HALO TRUST | B/3202 | 9 | 70.1047 | 35.7016 | Open | UXO Only | UXO Only | BF |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {E103AADF-A1F0-4B6C-AA6C-F0BE399A200A} |  | High | Critical Infrastracture | Minimal | 498 | CHA | 3 |  |  | 2014-04-02 16:30 | No | Open
Central | Panjsher | Paryan | Shaniz | {9E9697A0-3366-40C8-909B-F4E0AD2B1813} | c0a8-0057-12c3b81c0ce-e8494b86-1aae0- | MF-HQ-14115 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0310/01276/MF0026 | 800 | 69.9137 | 35.5828 | Open | Mixed | Mixed AP UXO | Converted From SHA | 1393 | MBT Project-018/A | Panjshir Demining Project-03/A | VTF-Australia | Yes |  |  | 1393 | HT | {9E9697A0-3366-40C8-909B-F4E0AD2B1813} |  | High Requested | Resettlment/Local Request | Minimal | 5 | SHA | 1 | Yes | Confirmed have accident | 2010-02-01 | No | Planned
Central | Panjsher | Rukha | Olok | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} | c0a8-0009-13fa8485b6f-98c2e55e-3296-3 | Hz-ID-17984 | DDG - Danish Demining Group | AF/0310/01214/MF0010 | 75132 | 69.439 | 35.2448 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-112/A | Panjshir Demining Project-06/A | DOS | Yes | 2014-04-05 | 2014-06-22 | 1393 | DDG | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} |  |  |  | Minimal | 439 | CHA | 3 | Yes |  | 2013-06-18 16:30 | No | Planned
Central | Panjsher | Rukha | Olok | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} | c0a8-0009-13fa86d2fbe-95ba89c4-3300-2 | Hz-ID-17985 | DDG - Danish Demining Group | AF/0310/01214/MF0011 | 73777 | 69.439 | 35.2448 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-112/A | Panjshir Demining Project-06/A | DOS | Yes | 2014-04-05 | 2014-06-22 | 1393 | DDG | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} |  |  |  | Minimal | 461 | CHA | 3 | Yes |  | 2013-06-18 16:30 | No | Planned
Central | Panjsher | Rukha | Olok | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} | c0a8-0009-13fa870197f-57a99e27-331c-1 | Hz-ID-17986 | DDG - Danish Demining Group | AF/0310/01214/MF0012 | 76136 | 69.439 | 35.2448 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-112/A | Panjshir Demining Project-06/A | DOS | Yes |  |  | 1393 | DDG | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} |  | High Requested | Resettlment/Local Request | Minimal | 461 | CHA | 3 | Yes |  | 2013-06-18 16:30 | No | Planned
Central | Panjsher | Rukha | Olok | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} | c0a8-0009-13fa873a690-17bfc2f7-3334-5 | Hz-ID-17987 | DDG - Danish Demining Group | AF/0310/01214/MF0013 | 76024 | 69.439 | 35.2448 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-112/A | Panjshir Demining Project-06/A | DOS | Yes |  |  | 1393 | DDG | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} |  | High Requested | Resettlment/Local Request | Minimal | 461 | CHA | 3 | Yes |  | 2013-06-18 16:30 | No | Planned
Central | Panjsher | Rukha | Olok | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} | c0a8-0009-13fa8779f1f-3cf3c2f3-334f-6 | Hz-ID-17988 | DDG - Danish Demining Group | AF/0310/01214/MF0014 | 75031 | 69.439 | 35.2448 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-112/A | Panjshir Demining Project-06/A | DOS | Yes |  |  | 1393 | DDG | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} |  | High Requested | Resettlment/Local Request | Minimal | 242 | CHA | 4 | Yes |  | 2013-06-18 16:30 | No | Planned
Central | Panjsher | Rukha | Olok | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} | c0a8-0009-13fa8964502-2ff0ea28-3435-c | Hz-ID-17989 | DDG - Danish Demining Group | AF/0310/01214/MF0015 | 58732 | 69.439 | 35.2448 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-112/A | Panjshir Demining Project-06/A | DOS | Yes |  |  | 1393 | DDG | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} |  | High Requested | Resettlment/Local Request | Minimal | 297 | CHA | 4 | Yes |  | 2013-06-18 16:30 | No | Planned
Central | Panjsher | Rukha | Olok | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} | c0a8-0009-13fa89974f6-5fad9bf9-3468-f | Hz-ID-17990 | DDG - Danish Demining Group | AF/0310/01214/MF0016 | 65615 | 69.439 | 35.2448 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-112/A | Panjshir Demining Project-06/A | DOS | Yes |  |  | 1393 | DDG | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} |  | High Requested | Resettlment/Local Request | Minimal | 275 | CHA | 4 | Yes |  | 2013-06-18 16:30 | No | Planned
Central | Panjsher | Rukha | Olok | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} | c0a8-0009-13fb74fabb1-86fa5fe6-3b44-a | Hz-ID-17993 | DDG - Danish Demining Group | AF/0310/01214/MF0017 | 57859 | 69.439 | 35.2448 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-112/A | Panjshir Demining Project-06/A | DOS | Yes |  |  | 1393 | DDG | {8A3D0881-CB83-4C5C-A8ED-824F410315C3} |  | High Requested | Resettlment/Local Request | Minimal | 275 | CHA | 4 | Yes |  | 2013-06-18 16:30 | No | Planned
Central | Panjsher | Rukha | Pyawusht | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} | c0a8-0009-14490bb2a07-ae2a7acf-537-9a | Hz-ID-18500 | HT - HALO TRUST | B/3201 | 2500 | 69.4535 | 35.2726 | Open | UXO Only | UXO Only | BF |  | MBT Project-068 | Panjshir Demining Project-05 |  |  |  |  | 1394 |  | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} |  | High with Victim | High with Victims | Minimal | 172 | CHA | 1 |  |  | 2014-02-04 16:30 | No | Open
Central | Panjsher | Rukha | Pyawusht | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} | c0a8-008e-1328ff9e7e2-1930c73d-3014-7 | MF-16038 | HT - HALO TRUST | H/7818 | 26000 | 69.4304 | 35.2794 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} |  | High with Victim | High with Victims | Minimal | 0 | CHA | 5 |  |  | 2011-05-09 16:30 | No | Open
Central | Panjsher | Rukha | Pyawusht | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} | c0a8-008e-132908e792a-ca73d7-140-707f | MF-16114 | HT - HALO TRUST | H/7874 | 24000 | 69.4247 | 35.2801 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} |  | High with Victim | High with Victims | Minimal | 1 | CHA | 5 |  |  | 2011-05-13 16:30 | No | Open
Central | Panjsher | Rukha | Pyawusht | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} | c0a8-008e-132908f0254-d75e33c8-150-6b | MF-16113 | HT - HALO TRUST | H/7875 | 23000 | 69.4238 | 35.281 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} |  | High with Victim | High with Victims | Minimal | 1 | CHA | 5 |  |  | 2011-05-14 16:30 | No | Open
Central | Panjsher | Rukha | Pyawusht | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} | c0a8-008e-132909198cf-3c9316c8-15f-8f | MF-16118 | HT - HALO TRUST | H/7860 | 27000 | 69.43 | 35.2795 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} |  | High with Victim | High with Victims | Minimal | 0 | CHA | 5 |  |  | 2011-05-08 16:30 | No | Open
Central | Panjsher | Rukha | Pyawusht | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} | c0a8-008e-132909367f4-24590b6e-19c-fb | MF-16117 | HT - HALO TRUST | H/7871 | 25000 | 69.4292 | 35.2814 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} |  | High with Victim | High with Victims | Minimal | 0 | CHA | 5 |  |  | 2011-05-04 16:30 | No | Open
Central | Panjsher | Rukha | Pyawusht | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} | c0a8-008e-1329099ee7a-5c5a9944-2ad-ac | MF-16112 | HT - HALO TRUST | H/7876 | 27850 | 69.4216 | 35.2828 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} |  | High with Victim | High with Victims | Minimal | 15 | CHA | 5 |  |  | 2011-05-15 16:30 | No | Open
Central | Panjsher | Rukha | Pyawusht | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} | c0a8-008e-1329e9ad0e1-be539882-39-f95 | MF-16036 | HT - HALO TRUST | H/7819 | 26000 | 69.4304 | 35.2794 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} |  | High with Victim | High with Victims | Minimal | 0 | CHA | 5 |  |  | 2011-05-10 16:30 | No | Open
Central | Panjsher | Rukha | Pyawusht | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} | c0a8-008e-1329e9bd3cd-33ae38e4-62-5f7 | MF-16115 | HT - HALO TRUST | H/7873 | 26000 | 69.4255 | 35.2795 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} |  | High with Victim | High with Victims | Minimal | 1 | CHA | 5 |  |  | 2011-05-12 16:30 | No | Open
Central | Panjsher | Rukha | Pyawusht | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} | c0a8-008e-132d3bcb06a-ba2495fb-c3d6-e | MF-16111 | HT - HALO TRUST | H/7877 | 28000 | 69.4238 | 35.2832 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} |  | High with Victim | High with Victims | Minimal | 15 | CHA | 5 |  |  | 2011-05-16 16:30 | No | Open
Central | Panjsher | Rukha | Pyawusht | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} | c0a8-00f6-134ac46f3db-7aca6997-f54-38 | MF-16116 | HT - HALO TRUST | H/7872 | 21000 | 69.4297 | 35.2801 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {45E6ED63-5A8D-4BFE-AF22-EA1023BA9ABE} |  | High with Victim | High with Victims | Minimal | 0 | CHA | 5 |  |  | 2011-05-11 16:30 | No | Open
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352d94b4ef-141eb70a-1a5-c7 | MF-16588 | HT - HALO TRUST | H/8062 | 27000 | 69.4617 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes | 2013-06-18 | 2013-07-20 | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 111 | CHA | 4 |  |  | 2011-08-06 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352d960599-84ee4bb3-1ba-f6 | MF-16586 | HT - HALO TRUST | H/8075 | 26300 | 69.4617 | 35.2711 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  | Low | Agriculture Blocked | Minimal | 111 | CHA | 5 |  |  | 2011-07-19 16:30 | No | Open
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352d96d073-b4b4d095-1cf-db | MF-16584 | HT - HALO TRUST | H/8074 | 27500 | 69.4617 | 35.2711 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  | Low | Agriculture Blocked | Minimal | 111 | CHA | 5 |  |  | 2011-07-18 16:30 | No | Open
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352d98018d-e1eb83f9-1e4-76 | MF-16583 | HT - HALO TRUST | H/8073 | 24000 | 69.4617 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 111 | CHA | 4 |  |  | 2011-07-17 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352d98c130-48ae0fcf-1fb-cf | MF-16582 | HT - HALO TRUST | H/8072 | 24500 | 69.4617 | 35.2711 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  | Low | Agriculture Blocked | Minimal | 111 | CHA | 5 |  |  | 2011-07-16 16:30 | No | Open
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352d9b0e5e-13128d2-225-ad0 | MF-16595 | HT - HALO TRUST | H/8019 | 25000 | 69.4616 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes | 2013-05-08 | 2013-05-30 | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 238 | CHA | 4 |  |  | 2011-07-02 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352d9c29d6-62218af2-23e-7c | MF-16593 | HT - HALO TRUST | H/8018 | 34265 | 69.4616 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes | 2013-05-08 | 2013-05-30 | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 238 | CHA | 4 |  |  | 2011-07-03 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352d9cf904-ff7ab083-254-ec | MF-16592 | HT - HALO TRUST | H/8017 | 25000 | 69.4617 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes | 2013-05-08 | 2013-05-30 | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 238 | CHA | 4 |  |  | 2011-07-01 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352d9e72df-26e69f3d-28e-eb | MF-16590 | HT - HALO TRUST | H/8020 | 27000 | 69.4617 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes | 2013-06-01 | 2013-06-20 | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 349 | CHA | 4 |  |  | 2011-07-04 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352db20ae6-6c90f48a-2a9-cf | MF-16580 | HT - HALO TRUST | H/8071 | 27267 | 69.4617 | 35.2711 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  | Low | Agriculture Blocked | Minimal | 111 | CHA | 5 |  |  | 2011-07-15 16:30 | No | Open
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352db3d6c6-eac347d7-2be-b3 | MF-16579 | HT - HALO TRUST | H/8070 | 27500 | 69.4617 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes | 2013-07-21 | 2013-08-25 | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 111 | CHA | 4 |  |  | 2011-07-14 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352db594b2-27ed6bc6-2d4-47 | MF-16576 | HT - HALO TRUST | H/8122 | 28000 | 69.4617 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes | 2013-06-01 | 2013-06-17 | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 111 | CHA | 4 |  |  | 2011-07-05 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1352e0f7951-f8d8b0e8-2-8493 | MF-16589 | HT - HALO TRUST | H/8066 | 32130 | 69.4617 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes | 2013-07-20 | 2013-08-31 | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 111 | CHA | 4 |  |  | 2011-07-10 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-135320ec25b-6bcaf2f0-296-8a | MF-16587 | HT - HALO TRUST | H/8067 | 27000 | 69.4617 | 35.2711 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  | Low | Agriculture Blocked | Minimal | 111 | CHA | 5 |  |  | 2011-07-11 16:30 | No | Open
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-135322a514d-a706ae83-3af-b9 | MF-16594 | HT - HALO TRUST | H/8064 | 27000 | 69.4617 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes | 2013-06-18 | 2013-07-20 | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 349 | CHA | 4 |  |  | 2011-07-08 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-135324578c1-a98b3f4c-3fd-e7 | MF-16591 | HT - HALO TRUST | H/8065 | 27000 | 69.4617 | 35.2411 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes | 2013-06-01 | 2013-06-17 | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 349 | CHA | 4 |  |  | 2011-08-09 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-1353247cfec-cbfee9-414-3a50 | MF-16585 | HT - HALO TRUST | H/8063 | 27000 | 69.4617 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes | 2013-06-22 | 2013-07-30 | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 349 | CHA | 4 |  |  | 2011-07-07 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-135324b2a10-c5fcec2a-429-52 | MF-16581 | HT - HALO TRUST | H/8068 | 27000 | 69.4617 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 111 | CHA | 4 |  |  | 2011-07-12 16:30 | No | Complete
Central | Panjsher | Rukha | Qarya Shast | {4052F14F-B63D-49AF-AE85-ECD1729BA869} | c0a8-00f6-135324e62a0-348bb389-440-b4 | MF-16578 | HT - HALO TRUST | H/8069 | 27000 | 69.4617 | 35.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {4052F14F-B63D-49AF-AE85-ECD1729BA869} |  |  |  | Minimal | 111 | CHA | 4 |  |  | 2011-07-13 16:30 | No | Complete
Central | Panjsher | Shutul | Arzawa | {B860EDE1-AD6D-4630-B02C-08E436A2E879} | c0a8-00f6-13923317d15-7ef5a947-2fcd-c | Hz-ID-17180 | DDG - Danish Demining Group | AF/0303/01807/MF0013 | 47667 | 69.2767 | 35.2553 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-017 | Panjshir Demining Project-01 | DOS | Yes |  |  | 1392 | OMAR | {B860EDE1-AD6D-4630-B02C-08E436A2E879} |  |  |  | Minimal | 146 | SHA | 5 |  |  | 2012-07-11 16:30 | No | Complete
Central | Panjsher | Shutul | Arzawa | {B860EDE1-AD6D-4630-B02C-08E436A2E879} | c0a8-00f6-139a941d393-d378d241-30b1-9 | Hz-ID-17243 | DDG - Danish Demining Group | AF/0303/01807/BF0015 | 28996 | 69.2731 | 35.2558 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-017 | Panjshir Demining Project-01 | DOS | Yes |  |  | 1392 | OMAR | {B860EDE1-AD6D-4630-B02C-08E436A2E879} |  |  |  | Minimal | 26 | CHA | 5 |  |  | 2012-08-08 16:30 | No | Complete
Central | Panjsher | Shutul | Arzawa | {B860EDE1-AD6D-4630-B02C-08E436A2E879} | c0a8-00f6-139aecb6967-8da6aade-44df-3 | Hz-ID-17178 | DDG - Danish Demining Group | AF/0303/01807/BF0014 | 28670 | 69.2835 | 35.2487 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-017 | Panjshir Demining Project-01 | DOS | Yes |  |  | 1392 | OMAR | {B860EDE1-AD6D-4630-B02C-08E436A2E879} |  |  |  | Minimal | 120 | SHA | 3 |  |  | 2012-07-11 16:30 | No | Complete
Central | Panjsher | Shutul | Chelana | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} | c0a8-0057-12c3b8c146e-d9219dbc-21f4d- | MF-HQ-13493 | DDG - Danish Demining Group | AF/0302/01801/MF0006 | 66528 | 69.279 | 35.1804 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} | Planned Year and Agency removed |  |  | Minimal | 139 | CHA | 4 |  |  | 2009-10-07 | No | Complete
Central | Panjsher | Shutul | Chelana | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} | c0a8-0057-12c3b8c28b9-ba78ed3f-22011- | MF-HQ-13495 | DDG - Danish Demining Group | AF/0302/01801/MF0007 | 70716 | 69.279 | 35.1804 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} | Planned year and Agency removed |  |  | Minimal | 640 | CHA | 4 |  |  | 2009-10-10 | No | Complete
Central | Panjsher | Shutul | Chelana | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} | c0a8-0057-12c3ba75213-fca60ecd-3367c- | MF-HQ-13499 | DDG - Danish Demining Group | AF/0302/01801/MF0009 | 347877 | 69.278 | 35.1808 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-069 | Panjshir Demining Project-07 | DOS | Yes | 2014-04-01 | 2014-09-30 | 1393 | OMAR | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} |  | Low | Agriculture Blocked | Minimal | 28 | CHA | 5 |  |  | 2009-10-13 | No | Planned
Central | Panjsher | Shutul | Chelana | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} | c0a8-0057-12c3ba75483-9b6ac0fb-33691- | MF-HQ-13497 | DDG - Danish Demining Group | AF/0302/01801/MF0008 | 265197 | 69.278 | 35.1808 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-069 | Panjshir Demining Project-07 | DOS | Yes | 2014-04-01 | 2014-09-30 | 1393 | OMAR | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} |  | Low | Agriculture Blocked | Minimal | 21 | CHA | 5 |  |  | 2009-10-12 | No | Planned
Central | Panjsher | Shutul | Chelana | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} | c0a8-00f6-135515a1618-b93e4a21-1f7-db | MF-16675 | DDG - Danish Demining Group | AF/0302/01801/MF0012 | 21032 | 69.2602 | 35.1583 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-069 | Panjshir Demining Project-07 | DOS | Yes |  |  | 1393 | OMAR | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} |  | Low | Agriculture Blocked | Minimal | 167 | CHA | 5 |  |  | 2011-12-05 16:30 | No | Planned
Central | Panjsher | Shutul | Jananjoy | {BFF7AAB0-EEFD-403A-9587-CDF3F69FE486} | c0a8-008e-132c9490a5f-6aac978d-2dbd-a | MF-15493 | DDG - Danish Demining Group | AF/0303/01800/MF7223 | 49000 | 69.2492 | 35.1733 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-069 | Panjshir Demining Project-07 | DOS | Yes | 2014-06-21 | 2014-07-31 | 1393 | OMAR | {BFF7AAB0-EEFD-403A-9587-CDF3F69FE486} |  | Low | Agriculture Blocked | Minimal | 6 | CHA | 5 |  |  | 2010-11-04 16:30 | No | Planned
Central | Panjsher | Shutul | Korawa | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} | c0a8-008e-1328f9358eb-47abd439-1abe-e | MF-16172 | DDG - Danish Demining Group | AF/0310/01189/MF8002 | 25760 | 69.33 | 35.2074 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-069 | Panjshir Demining Project-07 | DOS | Yes |  |  | 1393 | OMAR | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} |  |  |  | Minimal | 218 | CHA | 5 |  |  | 2011-06-07 16:30 | No | Planned
Central | Panjsher | Shutul | Korawa | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} | c0a8-008e-1328f971bc0-412a6a72-1b0b-9 | MF-16179 | DDG - Danish Demining Group | AF/0310/01189/MF8005 | 24000 | 69.33 | 35.2074 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} |  |  |  | Minimal | 44 | CHA | 4 |  |  | 2011-06-10 16:30 | No | Complete
Central | Panjsher | Shutul | Korawa | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} | c0a8-008e-1328f9a2f74-cacdf2fe-1c5d-2 | MF-16176 | DDG - Danish Demining Group | AF/0310/01189/MF8003 | 25500 | 69.33 | 35.2074 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-069 | Panjshir Demining Project-07 | DOS | Yes |  |  | 1393 | OMAR | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} |  |  |  | Minimal | 218 | CHA | 5 |  |  | 2011-06-08 16:30 | No | Planned
Central | Panjsher | Shutul | Korawa | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} | c0a8-008e-1328fe83340-99cdc95-2ca6-40 | MF-16178 | DDG - Danish Demining Group | AF/0310/01189/MF8004 | 25000 | 69.33 | 35.2074 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} |  |  |  | Minimal | 44 | CHA | 4 |  |  | 2011-06-09 16:30 | No | Complete
Central | Panjsher | Shutul | Korawa | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} | c0a8-008e-1328feba2f7-2e88089f-2d84-a | MF-16170 | DDG - Danish Demining Group | AF/0301/01189/MF8001 | 31600 | 69.33 | 35.2074 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-069 | Panjshir Demining Project-07 | DOS | Yes |  |  | 1393 | OMAR | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} |  |  |  | Minimal | 174 | CHA | 5 |  |  | 2011-06-06 16:30 | No | Planned
Central | Panjsher | Shutul | Korawa | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} | c0a8-00f6-135385bd550-25286d0-2aa-211 | MF-16614 | DDG - Danish Demining Group | AF/0310/01189/MF7878 | 23000 | 69.3224 | 35.2011 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-069 | Panjshir Demining Project-07 | DOS | Yes |  |  | 1393 | OMAR | {6AB3FD0B-329C-48A7-A109-7D277B6457FF} |  | Low | Agriculture Blocked | Minimal | 9 | CHA | 5 |  |  | 2011-05-07 16:30 | No | Planned
Central | Panjsher | Shutul | Sange Lakhshan | {05CDAB2B-E06F-44AA-B9E3-F8D2E57BE26B} | c0a8-008e-132c7ceb799-2d1dd812-14f4-2 | MF-16266 | DDG - Danish Demining Group | AF/0310/01808/MF8076 | 34500 | 69.293 | 35.2152 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-069 | Panjshir Demining Project-07 | DOS | Yes |  |  | 1393 | OMAR | {05CDAB2B-E06F-44AA-B9E3-F8D2E57BE26B} |  | Low | Agriculture Blocked | Minimal | 87 | CHA | 4 |  |  | 2011-08-01 16:30 | No | Planned
Central | Panjsher | Shutul | Sange Lakhshan | {05CDAB2B-E06F-44AA-B9E3-F8D2E57BE26B} | c0a8-008e-132c98e2d66-25ea64f9-3675-b | MF-16264 | DDG - Danish Demining Group | AF/0310/01808/MF8139 | 32650 | 69.2916 | 35.2137 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-069 | Panjshir Demining Project-07 | DOS | Yes | 2014-08-16 | 2014-09-30 | 1393 | OMAR | {05CDAB2B-E06F-44AA-B9E3-F8D2E57BE26B} |  | Low | Agriculture Blocked | Minimal | 87 | CHA | 5 |  |  | 2011-08-02 16:30 | No | Planned
Central | Panjsher | Shutul | Sange Lakhshan | {05CDAB2B-E06F-44AA-B9E3-F8D2E57BE26B} | c0a8-00f6-1350e955840-433276fe-4-667b | MF-16265 | DDG - Danish Demining Group | AF/0310/01808/MF8140 | 48000 | 69.293 | 35.2152 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-069 | Panjshir Demining Project-07 | DOS | Yes | 2014-08-16 | 2014-09-30 | 1393 | OMAR | {05CDAB2B-E06F-44AA-B9E3-F8D2E57BE26B} |  | Low | Agriculture Blocked | Minimal | 87 | CHA | 5 |  |  | 2011-08-03 16:30 | No | Planned
Central | Panjsher | Unaba | Anawa | {F49FBDF5-3798-4AFA-A5FA-247573F5C43E} | c0a8-0057-12c3b86d940-f4e0c952-1e495- | MF-CA-1774 | DDG - Danish Demining Group | AF/0310/01210/MF0005 | 37955 | 69.3619 | 35.2488 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-017 | Panjshir Demining Project-01 | DOS | Yes |  |  | 1392 | OMAR | {F49FBDF5-3798-4AFA-A5FA-247573F5C43E} |  |  |  | Minimal | 1 | CHA | 1 |  |  | 2008-11-19 | No | Complete
Central | Panjsher | Unaba | Anawa | {F49FBDF5-3798-4AFA-A5FA-247573F5C43E} | c0a8-0057-12c3ba24c65-603f1a3f-30562- | MF-CA-1775 | DDG - Danish Demining Group | AF/0310/01210/MF0006 | 24925 | 69.377 | 35.2505 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-017 | Panjshir Demining Project-01 | DOS | Yes |  |  | 1392 | OMAR | {F49FBDF5-3798-4AFA-A5FA-247573F5C43E} |  |  |  | Minimal | 0 | CHA | 1 |  |  | 2008-11-19 | No | Complete
Central | Panjsher | Unaba | Gholbak | {08B4A6F8-E642-43BE-96BB-0CABD0C4AC04} | c0a8-008e-133a5707186-59206841-406-c8 | MF-16346 | DDG - Danish Demining Group | AF/3407/01215/MF0028 | 87349 | 69.4262 | 35.2362 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-067 | Panjshir Demining Project-02 | DOS | Yes | 2013-07-01 | 2013-08-30 | 1392 | DDG | {08B4A6F8-E642-43BE-96BB-0CABD0C4AC04} |  |  |  | Minimal | 38 | CHA | 5 |  |  | 2011-09-14 16:30 | No | Complete
Central | Panjsher | Unaba | Gholbak | {08B4A6F8-E642-43BE-96BB-0CABD0C4AC04} | c0a8-008e-133a57f169f-8c45506d-427-f6 | MF-16347 | DDG - Danish Demining Group | AF/3407/01215/MF0027 | 98952 | 69.429 | 35.2353 | Closed | Mixed | Mixed AP UXO | MineField | 1391/1392 | MBT Project-067 | Panjshir Demining Project-02 | DOS | Yes | 2012-11-17 | 2013-07-30 | 1392 | DDG | {08B4A6F8-E642-43BE-96BB-0CABD0C4AC04} |  |  |  | Minimal | 28 | CHA | 5 |  |  | 2011-09-10 16:30 | No | Complete
Central | Panjsher | Unaba | Gholbak | {08B4A6F8-E642-43BE-96BB-0CABD0C4AC04} | c0a8-008e-134506acbb6-ec7fdb5d-63-3f4 | MF-16348 | DDG - Danish Demining Group | AF/0310/01215/MF0026 | 94925 | 69.429 | 35.2353 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-018 | Panjshir Demining Project-03 | DOS | Yes |  |  | 1392 | OMAR | {08B4A6F8-E642-43BE-96BB-0CABD0C4AC04} |  |  |  | Minimal | 28 | CHA | 4 |  |  | 2011-09-12 16:30 | No | Complete
Central | Panjsher | Unaba | Kar | {A7336522-26FB-490C-B723-C64622038D74} | c0a8-008e-132c43744c5-d4333bb9-b13-78 | MF-16289 | DDG - Danish Demining Group | H/8143 | 27500 | 69.4034 | 35.2224 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-112 | Panjshir Demining Project-06 |  | No |  |  | 1395 | DDG | {A7336522-26FB-490C-B723-C64622038D74} |  | Low | Agriculture Blocked | Minimal | 54 | CHA | 5 |  |  | 2011-08-08 16:30 | No | Open
Central | Panjsher | Unaba | Kar | {A7336522-26FB-490C-B723-C64622038D74} | c0a8-008e-132c8942d43-a8200f91-2604-2 | MF-16286 | DDG - Danish Demining Group | H/8146 | 26000 | 69.4034 | 35.2224 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-112 | Panjshir Demining Project-06 |  | No |  |  | 1395 | DDG | {A7336522-26FB-490C-B723-C64622038D74} |  | Low | Agriculture Blocked | Minimal | 54 | CHA | 5 |  |  | 2011-08-14 16:30 | No | Open
Central | Panjsher | Unaba | Kar | {A7336522-26FB-490C-B723-C64622038D74} | c0a8-008e-132c896326a-cc4eaf57-2617-d | MF-16285 | DDG - Danish Demining Group | H/8147 | 26000 | 69.4034 | 35.2224 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  | No |  |  | 1395 | DDG | {A7336522-26FB-490C-B723-C64622038D74} |  | Low | Agriculture Blocked | Minimal | 54 | CHA | 5 |  |  | 2011-08-15 16:30 | No | Open
Central | Panjsher | Unaba | Kar | {A7336522-26FB-490C-B723-C64622038D74} | c0a8-008e-132c89a9292-8302c621-262c-9 | MF-16284 | DDG - Danish Demining Group | H/8148 | 26000 | 69.4034 | 35.2224 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {A7336522-26FB-490C-B723-C64622038D74} |  | Low | Agriculture Blocked | Minimal | 6 | CHA | 5 |  |  | 2011-08-17 16:30 | No | Open
Central | Panjsher | Unaba | Kar | {A7336522-26FB-490C-B723-C64622038D74} | c0a8-008e-132c8a27ddb-96089ef2-26ad-9 | MF-16283 | DDG - Danish Demining Group | H/8149 | 25500 | 69.4034 | 35.2224 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {A7336522-26FB-490C-B723-C64622038D74} |  | Low | Agriculture Blocked | Minimal | 10 | CHA | 5 |  |  | 2011-08-19 16:30 | No | Open
Central | Panjsher | Unaba | Kar | {A7336522-26FB-490C-B723-C64622038D74} | c0a8-008e-132cd8e89e1-fb6cc7c1-7dc-e2 | MF-16287 | DDG - Danish Demining Group | H/8145 | 26000 | 69.4034 | 35.2224 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {A7336522-26FB-490C-B723-C64622038D74} |  | Low | Agriculture Blocked | Minimal | 48 | CHA | 5 |  |  | 2011-08-13 16:30 | No | Open
Central | Panjsher | Unaba | Kar | {A7336522-26FB-490C-B723-C64622038D74} | c0a8-008e-132cd910980-c8b98a8a-7f0-66 | MF-16288 | DDG - Danish Demining Group | H/8144 | 26000 | 69.4034 | 35.2224 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {A7336522-26FB-490C-B723-C64622038D74} |  | Low | Agriculture Blocked | Minimal | 62 | CHA | 5 |  |  | 2011-08-10 16:30 | No | Open
Central | Panjsher | Unaba | Kar | {A7336522-26FB-490C-B723-C64622038D74} | c0a8-008e-132cdae06ca-303aa8a6-856-e3 | MF-16290 | DDG - Danish Demining Group | H/8142 | 33126 | 69.4034 | 35.2224 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {A7336522-26FB-490C-B723-C64622038D74} |  | Low | Agriculture Blocked | Minimal | 62 | CHA | 5 |  |  | 2011-08-07 16:30 | No | Open
Central | Panjsher | Unaba | Kar | {A7336522-26FB-490C-B723-C64622038D74} | c0a8-008e-132cdae1e20-ff5c2e63-86a-8f | MF-16291 | DDG - Danish Demining Group | H/8141 | 26312 | 69.4034 | 35.2224 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {A7336522-26FB-490C-B723-C64622038D74} |  | Low | Agriculture Blocked | Minimal | 48 | CHA | 5 |  |  | 2011-08-06 16:30 | No | Open
Central | Panjsher | Unaba | Kar | {A7336522-26FB-490C-B723-C64622038D74} | c0a8-00f6-1353855005f-6ce4e2c7-24c-59 | MF-16616 | DDG - Danish Demining Group | H/8150 | 29600 | 69.4034 | 35.2224 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {A7336522-26FB-490C-B723-C64622038D74} |  | Low | Agriculture Blocked | Minimal | 10 | CHA | 5 |  |  | 2011-08-19 16:30 | No | Open
Central | Panjsher | Unaba | Kar | {A7336522-26FB-490C-B723-C64622038D74} | c0a8-00f6-1353859a3c9-5a16b521-27a-32 | MF-16615 | DDG - Danish Demining Group | H/8151 | 33700 | 69.4034 | 35.2224 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {A7336522-26FB-490C-B723-C64622038D74} |  | Low | Agriculture Blocked | Minimal | 18 | CHA | 5 |  |  | 2011-08-18 16:30 | No | Open
Central | Panjsher | Unaba | Malekan | {50F00ABF-60A7-4810-B53D-71FAE0D2D23B} | c0a8-00f6-13a9144aea1-205f4669-4dd-8b | Hz-ID-17304 | DDG - Danish Demining Group | AF/0310/01206/BF0029 | 16000 | 69.3651 | 35.2314 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-017 | Panjshir Demining Project-01 | DOS | Yes | 2013-06-08 | 2013-06-13 | 1392 | OMAR | {50F00ABF-60A7-4810-B53D-71FAE0D2D23B} |  |  |  | Minimal | 2255 | CHA | 3 |  |  | 2012-09-06 16:30 | No | Complete
Central | Panjsher | Unaba | Qala Miramshah | {2DE25E80-3740-4557-968C-9132B630994E} | c0a8-008e-1328a63271d-11700cc2-81a-31 | MF-15494 | DDG - Danish Demining Group | H/7224 | 1650 | 69.3514 | 35.247 | Open | AP Only | AP Only | MineField | Blank | MBT Project-112 | Panjshir Demining Project-06 |  | No |  |  | 1395 | None | {2DE25E80-3740-4557-968C-9132B630994E} |  | Low | Small Hazards | Minimal | 10 | CHA | 5 |  |  | 2010-11-08 16:30 | No | Open
Central | Panjsher | Unaba | Tawakh | {70C00506-3ED5-44C8-AF79-9DC189FF6277} | c0a8-0009-13adec20f17-afc8ed6d-da7-fb | Hz-ID-17341 | DDG - Danish Demining Group | AF/0310/01211/MF0030 | 2191 | 69.4055 | 35.2428 | Open | AT Only | AT Only | MineField | Blank | MBT Project-112 | Panjshir Demining Project-06 |  | No |  |  | 1395 | None | {70C00506-3ED5-44C8-AF79-9DC189FF6277} |  | High with Victim | High with Victims | Minimal | 259 | CHA | 3 |  |  | 2012-10-31 16:30 | No | Open
Central | Panjsher | Unaba | Tawakh | {70C00506-3ED5-44C8-AF79-9DC189FF6277} | c0a8-0009-14540bfeebb-7747b967-1453-c | Hz-ID-18601 | HT - HALO TRUST | H/8536 | 9600 | 69.3888 | 35.2424 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {70C00506-3ED5-44C8-AF79-9DC189FF6277} |  | High with Victim | High with Victims | Minimal | 215 | CHA | 4 |  |  | 2014-03-20 16:30 | No | Open
Central | Panjsher | Unaba | Tawakh | {70C00506-3ED5-44C8-AF79-9DC189FF6277} | c0a8-0009-1467b360136-cbba80d5-1b7b-5 | Hz-ID-18819 | HT - HALO TRUST | H/8751 | 13570 | 69.3888 | 35.2424 | Open | AP Only | AP Only | MineField |  | MBT Project-112 | Panjshir Demining Project-06 |  |  |  |  | 1395 |  | {70C00506-3ED5-44C8-AF79-9DC189FF6277} |  | High with Victim | High with Victims | Minimal | 215 | CHA | 4 |  |  | 2014-01-01 16:30 | No | Open
Central | Parwan | Bagram | Akakhel | {05A2B5A1-6947-4A16-8A99-D507792AD8B7} | c0a8-00c9-12fd98cf4f1-ab3673cb-e65-5b | MF-HQ-13899 | MCPA - Mine Clearance Planning Agency | AF/0308/01655/MF0322 | 42252 | 69.3001 | 34.9457 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-04-13 | 2013-05-06 | 1392 | OMAR | {05A2B5A1-6947-4A16-8A99-D507792AD8B7} |  |  |  | Moderate | 24 | CHA | 2 |  |  | 2009-11-30 | No | Complete
Central | Parwan | Bagram | Bakhshikhel Sayghani | {5F8BCB08-D41E-4883-8B8C-37E71174085F} | c0a8-0009-13e7d5fde9e-58592b50-1faf-7 | Hz-ID-17859 | MCPA - Mine Clearance Planning Agency | AF/0308/00005/MF0428 | 117254 | 69.3391 | 34.9392 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108/C | Parwan Demining Project-07/C | DOS | Yes | 2013-06-22 | 2013-12-26 | 1392 | ATC | {5F8BCB08-D41E-4883-8B8C-37E71174085F} |  |  |  | Moderate | 13 | CHA | 5 |  |  | 2013-03-13 16:30 | No | Complete
Central | Parwan | Bagram | Bakhshikhel Sayghani | {5F8BCB08-D41E-4883-8B8C-37E71174085F} | c0a8-0009-13e82525558-65c270e5-6f9-25 | Hz-ID-17861 | MCPA - Mine Clearance Planning Agency | AF/0308/00005/MF0429 | 76971 | 69.3391 | 34.9392 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108/C | Parwan Demining Project-07/C | DOS | Yes | 2013-12-01 | 2014-04-30 | 1392 | ATC | {5F8BCB08-D41E-4883-8B8C-37E71174085F} |  |  |  | Moderate | 34 | CHA | 5 |  |  | 2013-03-14 16:30 | No | Complete
Central | Parwan | Bagram | Bakhshikhel Sayghani | {5F8BCB08-D41E-4883-8B8C-37E71174085F} | c0a8-0009-13e8253742b-ec94663d-716-84 | Hz-ID-17863 | MCPA - Mine Clearance Planning Agency | AF/0308/00005/MF0430 | 96415 | 69.3391 | 34.9392 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108/C | Parwan Demining Project-07/C | DOS | Yes | 2014-01-01 | 2014-04-30 | 1392 | ATC | {5F8BCB08-D41E-4883-8B8C-37E71174085F} |  |  |  | Moderate | 94 | CHA | 5 |  |  | 2013-03-16 16:30 | No | Complete
Central | Parwan | Bagram | Bakhshikhel Sayghani | {5F8BCB08-D41E-4883-8B8C-37E71174085F} | c0a8-0009-13e8254fe3d-70eef083-730-1e | Hz-ID-17865 | MCPA - Mine Clearance Planning Agency | AF/0308/00005/MF0431 | 61561 | 69.33 | 34.9395 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108/C | Parwan Demining Project-07/C | DOS | Yes | 2014-01-12 | 2014-04-30 | 1392 | ATC | {5F8BCB08-D41E-4883-8B8C-37E71174085F} |  |  |  | Moderate | 13 | CHA | 5 |  |  | 2013-03-17 16:30 | No | Complete
Central | Parwan | Bagram | Barfikhel | {27438F0E-CF91-4B0D-A32A-EBC6440F9841} | c0a8-0009-13dc92bc081-6cc0c081-1f8d-c | Hz-ID-17744 | DDG - Danish Demining Group | AF/0308/01639/MF0427 | 366 | 69.2401 | 34.953 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-005 | Kabul Demining Project-01 | DANIDA | Yes | 2013-04-02 | 2013-04-07 | 1392-1393 | DDG | {27438F0E-CF91-4B0D-A32A-EBC6440F9841} |  |  |  | Moderate | 557 | CHA | 2 |  |  | 2013-03-17 16:30 | No | Planned
Central | Parwan | Bagram | Barfikhel | {27438F0E-CF91-4B0D-A32A-EBC6440F9841} | c0a8-008e-1328f9ca391-eacc39a2-1dca-7 | MF-15420 | ATC - Afghan Technical Consultants | AF/0308/01639/MF0362 | 930 | 69.2404 | 34.9586 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108/A | Parwan Demining Project-07/A | VTF-Japan | Yes | 2013-05-08 | 2013-07-09 | 1392 | ATC | {27438F0E-CF91-4B0D-A32A-EBC6440F9841} |  |  |  | Moderate | 0 | CHA | 3 |  |  | 2010-11-11 16:30 | No | Complete
Central | Parwan | Bagram | Gojurkhel | {5476BDB9-30F5-4347-82DF-8C42CEB09533} | c0a8-0009-1437076e758-980a1441-10ea5- | Hz-ID-18307 | ATC - Afghan Technical Consultants | AF/0308/01637/MF0434 | 4649 | 69.2631 | 34.9763 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-055/A | Parwan Demining Project-08 /A | B-Japan | Yes |  |  | 1393 | ATC | {5476BDB9-30F5-4347-82DF-8C42CEB09533} |  | High | Critical Infrastracture | Moderate | 629 | CHA | 3 |  |  | 2013-12-09 16:30 | No | Planned
Central | Parwan | Bagram | Gojurkhel | {5476BDB9-30F5-4347-82DF-8C42CEB09533} | c0a8-0057-12c3b6f5e82-b25d2a4c-d465-1 | MF-HQ-15111 | DDG - Danish Demining Group | AF/0308/01637/MF0355-HR | 20000 | 69.2768 | 34.9679 | Open | AP Only | AP Only | MineField | Blank | MBT Project-309 | Good Neighbor project |  | No |  |  | 1393 | None | {5476BDB9-30F5-4347-82DF-8C42CEB09533} |  | Medium | Critical Infrastracture | Moderate | 367 | CHA | 3 |  |  | 2010-07-12 | No | Open
Central | Parwan | Bagram | Jafarkhel | {7C98468F-9D41-4980-AEA2-D2D1E7AB1449} | c0a8-008e-132c95597f9-597c4357-2fc5-e | BF-15013 | MCPA - Mine Clearance Planning Agency | AF/0308/01650/BF0369 | 73 | 69.2573 | 34.9672 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-108/A | Parwan Demining Project-07/A | VTF-Japan | Yes |  |  | 1392 | ATC | {7C98468F-9D41-4980-AEA2-D2D1E7AB1449} | , |  |  | Moderate | 0 | CHA | 3 |  |  | 2010-12-13 16:30 | No | Complete
Central | Parwan | Bagram | Jala | {AB898C38-5D27-4E21-BAD7-A5DFF4AB712A} | c0a8-0057-12c3b8b7303-55c556d5-217d6- | MF-HT-847 | HT - HALO TRUST | H/1879 | 22950 | 69.475 | 34.9264 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | ATC | {AB898C38-5D27-4E21-BAD7-A5DFF4AB712A} | , | High with Victim | High with Victims | Moderate | 83 | CHA | 2 |  |  | 2006-08-01 | No | Pledged
Central | Parwan | Bagram | Jala | {AB898C38-5D27-4E21-BAD7-A5DFF4AB712A} | c0a8-0057-12c3b8d75fb-d96f21ec-22e0b- | MF-HT-882 | HT - HALO TRUST | H/1880 | 2250 | 69.4894 | 34.9273 | Open | AP Only | AP Only | MineField |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {AB898C38-5D27-4E21-BAD7-A5DFF4AB712A} | , | High with Victim | High with Victims | Moderate | 243 | CHA | 2 |  |  | 2006-08-01 | No | Pledged
Central | Parwan | Bagram | Jala | {AB898C38-5D27-4E21-BAD7-A5DFF4AB712A} | c0a8-0057-12c3ba5e8e9-aa8dd7a3-3287c- | MF-HT-897 | HT - HALO TRUST | H/1882 | 34000 | 69.4848 | 34.9257 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-04-30 | 2013-05-12 | 1392 | OMAR | {AB898C38-5D27-4E21-BAD7-A5DFF4AB712A} |  |  |  | Moderate | 243 | CHA | 2 |  |  | 2006-08-01 | No | Complete
Central | Parwan | Bagram | Jala | {AB898C38-5D27-4E21-BAD7-A5DFF4AB712A} | c0a8-0057-12c3bad6f63-7f4adbb5-36f7a- | MF-HT-852 | HT - HALO TRUST | H/1878 | 25425 | 69.478 | 34.933 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | ATC | {AB898C38-5D27-4E21-BAD7-A5DFF4AB712A} | , | High with Victim | High with Victims | Moderate | 130 | CHA | 2 |  |  | 2006-08-01 | No | Pledged
Central | Parwan | Bagram | Jala | {AB898C38-5D27-4E21-BAD7-A5DFF4AB712A} | c0a8-008e-13068b0f1b4-bc2f37a5-243-7a | MF-HT-894 | HT - HALO TRUST | H/1881 | 3600 | 69.4848 | 34.9257 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-05-13 | 2013-05-13 | 1392 | OMAR | {AB898C38-5D27-4E21-BAD7-A5DFF4AB712A} | Planned year and agency removed |  |  | Moderate | 0 | CHA | 2 |  |  | 2006-08-01 | No | Complete
Central | Parwan | Bagram | Janquadam | {E5964B2F-DC97-413B-B51B-E01F6520584F} | c0a8-0009-145da7778c5-289062b8-19db-1 | Hz-ID-18696 | SDA - Sterling Demining Afghanistan | AF/0308/01643/BF0356.A | 46785.05 | 69.246 | 34.9404 | Open | UXO Only | UXO Only | BF |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {E5964B2F-DC97-413B-B51B-E01F6520584F} |  | High with Victim | High with Victims | Moderate | 2100 | CHA | 2 |  |  | 2014-03-24 16:30 | No | Pledged
Central | Parwan | Bagram | Janquadam | {E5964B2F-DC97-413B-B51B-E01F6520584F} | c0a8-0009-145da7a2393-aab24e74-1a1a-3 | Hz-ID-18697 | SDA - Sterling Demining Afghanistan | AF/0308/01643/BF0358.A | 56678.99 | 69.2459 | 34.9437 | Open | UXO Only | UXO Only | BF |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {E5964B2F-DC97-413B-B51B-E01F6520584F} |  | High with Victim | High with Victims | Moderate | 1737 | CHA | 2 |  |  | 2014-03-25 16:30 | No | Pledged
Central | Parwan | Bagram | Kharoti | {163C089B-B26E-40D4-992A-078FCA24BAB1} | c0a8-0057-12c3b698dda-10330cd4-8dba-7 | MF-HQ-14599 | MCPA - Mine Clearance Planning Agency | AF/0308/01663/MF6862 | 27700 | 69.3603 | 34.88 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-04-13 | 2013-04-29 | 1392 | OMAR | {163C089B-B26E-40D4-992A-078FCA24BAB1} |  |  |  | Moderate | 66 | CHA | 2 |  |  | 2010-05-07 | No | Complete
Central | Parwan | Bagram | Kharoti | {163C089B-B26E-40D4-992A-078FCA24BAB1} | c0a8-0057-12c3b6a9b20-974789df-9a6d-5 | MF-HQ-14607 | MCPA - Mine Clearance Planning Agency | AF/0308/01663/MF6868 | 32227 | 69.357 | 34.8753 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-04-13 | 2013-04-29 | 1392 | OMAR | {163C089B-B26E-40D4-992A-078FCA24BAB1} |  |  |  | Moderate | 3 | CHA | 2 |  |  | 2010-05-13 | No | Complete
Central | Parwan | Bagram | Kharoti | {163C089B-B26E-40D4-992A-078FCA24BAB1} | c0a8-0057-12c3b9c9ff3-fc9efdd5-2cdbd- | MF-CA-2114 | MCPA - Mine Clearance Planning Agency | AF/0308/01663/MF244 | 35080 | 69.3612 | 34.9764 | Open | Mixed Mine | Mixed Mine | MineField | Blank | MBT Project-055 | Parwan Demining Project-08 |  | Yes |  |  | 1396 | Blank | {163C089B-B26E-40D4-992A-078FCA24BAB1} | , | High with Victim | High with Victims | Moderate | 29 | CHA | 5 |  |  | 2009-03-12 | No | Open
Central | Parwan | Bagram | Kharoti | {163C089B-B26E-40D4-992A-078FCA24BAB1} | c0a8-0057-12c3b9ca263-f7c409ca-2cdd3- | MF-CA-2081 | MCPA - Mine Clearance Planning Agency | AF/0308/01663/MF0236 | 37915 | 69.3566 | 34.9816 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {163C089B-B26E-40D4-992A-078FCA24BAB1} |  | High with Victim | High with Victims | Moderate | 1086 |  | 1 |  |  | 2009-02-23 | No | Pledged
Central | Parwan | Bagram | Nas Dara | {7125433E-0614-476E-A052-D026C51E8C0A} | c0a8-0057-12c3b7de74b-724a3385-17fc8- | MF-CA-2104 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0308/00008/MF0240 | 320000 | 69.48 | 34.9107 | Open | AP Only | AP Only | MineField | Blank | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | None | {7125433E-0614-476E-A052-D026C51E8C0A} | , | Low | Agriculture Blocked | Moderate | 98 | CHA | 4 |  |  | 2009-03-01 | No | Pledged
Central | Parwan | Bagram | Nika Khel | {80E6543F-226A-4CA7-92E4-680174514EC7} | c0a8-0057-12c3b801ca7-9ef006ae-19840- | MF-CA-1829 | MCPA - Mine Clearance Planning Agency | AF/0308/00780/MF5481 | 894 | 69.4114 | 34.9425 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-06-08 | 2013-06-09 | 1392 | OMAR | {80E6543F-226A-4CA7-92E4-680174514EC7} | , |  |  | Moderate | 285 | CHA | 3 |  |  | 2008-11-30 | No | Complete
Central | Parwan | Bagram | Nika Khel | {80E6543F-226A-4CA7-92E4-680174514EC7} | c0a8-0057-12c3bb2b828-b59aa56a-3a1fb- | MF-CA-1819 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0308/00780/MF5482 | 2459 | 69.4063 | 34.9479 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-06-18 | 2013-06-30 | 1392 | OMAR | {80E6543F-226A-4CA7-92E4-680174514EC7} |  |  |  | Moderate | 126 | CHA | 4 |  |  | 2008-12-01 | No | Complete
Central | Parwan | Bagram | Qal'eh-ye Ahmadkhan | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} | c0a8-008e-13136642e0c-113c88a2-7c-550 | MF-CA-2109 | HDI-Hemayatbrothers Demining International | AF/0308/01635/MF026-HR | 5365 | 69.2471 | 34.9311 | Open | AP Only | AP Only | MineField | Blank | MBT Project-309 | Good Neighbor project |  | No |  |  | 1393 | None | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} |  | High with Victim | High with Victims | Moderate | 3075 | CHA | 1 |  |  | 2009-03-12 | No | Open
Central | Parwan | Bagram | Qal'eh-ye Ahmadkhan | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} | c0a8-008e-13136652a4d-3206879a-a4-c93 | MF-CA-1735 | HDI-Hemayatbrothers Demining International | AF/0308/01635/MF019-HR | 2220 | 69.2643 | 34.957 | Open | Mixed | Mixed AP UXO | MineField | Blank | MBT Project-309 | Good Neighbor project |  | No |  |  | 1393 | None | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} |  | High with Victim | High with Victims | Moderate | 1950 | CHA | 1 |  |  | 2008-12-04 | No | Open
Central | Parwan | Bagram | Qal'eh-ye Ahmadkhan | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} | c0a8-008e-1313667a5bd-a5dc5d5e-e7-4fb | MF-CA-2201 | MCPA - Mine Clearance Planning Agency | AF/0308/01635/MF0249-HR | 69940 | 69.292 | 34.9346 | Open | AP Only | AP Only | MineField | Blank | MBT Project-309 | Good Neighbor project |  | No |  |  | 1393 | None | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} |  | High with Victim | High with Victims | Moderate | 125 | CHA | 2 |  |  | 2009-03-19 | No | Open
Central | Parwan | Bagram | Qal'eh-ye Ahmadkhan | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} | c0a8-008e-1328fcb03ea-fce16a7-287e-86 | BF-15090 | MCPA - Mine Clearance Planning Agency | AF/0308/01635/BF0388 | 345187 | 69.3333 | 34.9261 | Worked on | UXO Only | UXO Only | BF | 1393 | MBT Project-185 | Kabul new city Demining Project | VTF-Japan | Yes |  |  | 1393 | DDG | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} | Kabul New City | High with Victim | High with Victims | Moderate | 52 | CHA | 1 |  |  | 2011-05-01 16:30 | No | Planned
Central | Parwan | Bagram | Qal'eh-ye Ahmadkhan | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} | c0a8-008e-132c46ed16d-53249b2b-1234-c | BF-15113 | AGD-Afghan Greenfield Demining | AF/0308/01635/BF0013-HR | 25064 | 69.3019 | 34.9349 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-309 | Good Neighbor project |  | No |  |  | 1393 | None | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} |  | High with Victim | High with Victims | Moderate | 83 | CHA | 1 |  |  | 2011-07-30 16:30 | No | Open
Central | Parwan | Bagram | Qal'eh-ye Ahmadkhan | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} | c0a8-00f6-135522d1487-197bcd53-420-50 | BF-15166 | AGD-Afghan Greenfield Demining | AF/0308/01635/BF0020-HR | 18540 | 69.2901 | 34.9265 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-309 | Good Neighbor project |  | No |  |  | 1393 | None | {3C27ABBA-46A7-45BB-99E2-CE3535838C88} |  | High with Victim | High with Victims | Moderate | 59 | CHA | 1 |  |  | 2011-12-26 16:30 | No | Open
Central | Parwan | Bagram | Qal'eh-ye Malek | {C14A4EF3-7AFA-4786-8968-24BDC8E51792} | c0a8-008e-1328f9f75d4-633ab018-1f38-9 | MF-15477 | DDG - Danish Demining Group | AF/0308/01646/MF0366 | 195 | 69.2103 | 34.9707 | Open | AP Only | AP Only | MineField |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {C14A4EF3-7AFA-4786-8968-24BDC8E51792} | , | High | Critical Infrastracture | Moderate | 557 | CHA | 3 |  |  | 2010-12-02 16:30 | No | Pledged
Central | Parwan | Bagram | Qal'eh-ye Nasro | {519FBE7B-C7AB-4B83-B8D6-856041C65595} | c0a8-0009-13b4075be41-256eec4f-4cd1-e | Hz-ID-17389 | DDG - Danish Demining Group | AF/0301/01603/MF8373 | 2200 | 69.179 | 34.8867 | Open | AT Only | AT Only | MineField |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {519FBE7B-C7AB-4B83-B8D6-856041C65595} |  | High with Victim | High with Victims | Moderate | 73 | CHA | 2 |  |  | 2012-10-02 16:30 | No | Pledged
Central | Parwan | Bagram | Qal'eh-ye Safarkhel | {03B6C50B-4DB3-494F-B094-FB27CF681111} | c0a8-0009-13df3848db4-bc242f31-12ae-3 | Hz-ID-17788 | DDG - Danish Demining Group | AF/0308/01619/MF0432 | 68402 | 69.3083 | 34.9473 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-185 | Kabul new city Demining Project | VTF-Japan | Yes |  |  | 1393 | DDG | {03B6C50B-4DB3-494F-B094-FB27CF681111} |  | Low | Agriculture Blocked | Moderate | 73 | CHA | 5 |  |  | 2013-03-08 16:30 | No | Planned
Central | Parwan | Bagram | Qal'eh-ye Yozbashi | {5523275B-3B7B-4F21-9A1B-3428598860A4} | c0a8-00f6-135520489da-1afd6591-6c-8d6 | MF-16513 | AGD-Afghan Greenfield Demining | AF/0308/1635/MF0021-HR | 1500 | 69.2652 | 34.9311 | Open | Mixed | Mixed AP UXO | MineField | Blank | MBT Project-309 | Good Neighbor project |  | No |  |  | 1393 | None | {5523275B-3B7B-4F21-9A1B-3428598860A4} |  | Medium | Comunity Centers | Moderate | 134 | CHA | 3 |  |  | 2012-01-01 16:30 | No | Open
Central | Parwan | Bagram | Qaracha | {F89B1BAA-5F09-4F3B-AC8B-A94CA13F5BE1} | c0a8-0009-145da7eea78-8a922e7-1a8e-ae | Hz-ID-18698 | SDA - Sterling Demining Afghanistan | AF/0308/00767/MF0357.A | 99037.96 | 69.2853 | 34.925 | Open | AP Only | AP Only | MineField |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {F89B1BAA-5F09-4F3B-AC8B-A94CA13F5BE1} |  | High with Victim | High with Victims | Moderate | 698 | CHA | 2 |  |  | 2014-03-24 16:30 | No | Pledged
Central | Parwan | Bagram | Qaracha | {F89B1BAA-5F09-4F3B-AC8B-A94CA13F5BE1} | c0a8-0009-1472e149843-694d727f-24d-9c | Hz-ID-18765 | DDG - Danish Demining Group | AF/0308/00767/MF0426 | 87243 | 69.3398 | 34.9953 | Open | AP Only | AP Only | MineField |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {F89B1BAA-5F09-4F3B-AC8B-A94CA13F5BE1} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 2 |  |  | 2014-04-21 16:30 | No | Pledged
Central | Parwan | Bagram | Qaracha | {F89B1BAA-5F09-4F3B-AC8B-A94CA13F5BE1} | c0a8-0009-147330b1ae2-b0ca2d4-142-eb5 | Hz-ID-18766 | DDG - Danish Demining Group | AF/0308/00767/MF0427 | 55571 | 69.341 | 34.9979 | Open | AP Only | AP Only | MineField |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {F89B1BAA-5F09-4F3B-AC8B-A94CA13F5BE1} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 2 |  |  | 2014-04-21 16:30 | No | Pledged
Central | Parwan | Bagram | Robat | {727F4411-413A-4CE6-8688-5661DFB4C7DB} | c0a8-0009-1463c97c679-6e2eb60d-1064-c | Hz-ID-18737 | HT - HALO TRUST | H/8537 | 1537 | 69.1652 | 34.9241 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {727F4411-413A-4CE6-8688-5661DFB4C7DB} |  | Medium | Critical Infrastracture | Moderate | 699 | CHA | 3 |  |  | 2014-04-03 16:30 | No | Planned
Central | Parwan | Bagram | Sabikhel | {E05F9A93-327D-4539-AA89-E0E1D81A8E84} | c0a8-008e-1328f804a8b-40e54a96-1360-5 | MF-16037 | MCPA - Mine Clearance Planning Agency | AF/0308/01652/MF0389-HR | 328 | 69.3006 | 34.9506 | Open | AP Only | AP Only | MineField | Blank | MBT Project-309 | Good Neighbor project |  | No |  |  | 1393 | None | {E05F9A93-327D-4539-AA89-E0E1D81A8E84} |  | High | Water Blocked | Moderate | 0 | CHA | 3 |  |  | 2011-05-09 16:30 | No | Open
Central | Parwan | Bagram | Takhcha | {3AFA5A65-1FB9-4730-90A2-25579D7EEE22} | c0a8-0057-12c3b6d4a7b-3c4b96e4-bb1d-d | MF-HQ-15114 | DDG - Danish Demining Group | AF/0308/00004/MF0353 | 1339 | 69.3109 | 34.9986 | Open | AP Only | AP Only | MineField |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {3AFA5A65-1FB9-4730-90A2-25579D7EEE22} | , | High | Critical Infrastracture | Moderate | 121 | CHA | 3 |  |  | 2010-09-14 | No | Pledged
Central | Parwan | Bagram | Takhcha | {3AFA5A65-1FB9-4730-90A2-25579D7EEE22} | c0a8-0057-12c3bb56782-b84e77c0-3bb6f- | MF-HQ-11943 | HT - HALO TRUST | H/5906 | 29100 | 69.3101 | 34.9983 | Open | AP Only | AP Only | MineField | Blank | MBT Project-001/A | Parwan Demining Project-01/A |  | No |  |  | 1394 | None | {3AFA5A65-1FB9-4730-90A2-25579D7EEE22} |  | Medium | Critical Infrastracture | Moderate | 774 | CHA | 3 |  |  | 2009-03-02 | No | Open
Central | Parwan | Bagram | Yosbashi Ulia | {D10473C1-1420-4F44-8068-46650A0FF7CF} | c0a8-0009-141a15cc4dd-ab89f630-3e38-d | Hz-ID-18118 | ATC - Afghan Technical Consultants | AF/0308/00015/MF0433 | 10600 | 69.2686 | 34.9324 | Open | AP Only | AP Only | MineField |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {D10473C1-1420-4F44-8068-46650A0FF7CF} |  | High with Victim | High with Victims | Moderate | 432 | CHA | 2 |  |  | 2013-06-18 16:30 | No | Pledged
Central | Parwan | Bagram | Yosbashi Ulia | {D10473C1-1420-4F44-8068-46650A0FF7CF} | c0a8-0057-12c3b8096d4-15cecc36-19dae- | MF-CA-1822 | HT - HALO TRUST | H/5473-HR | 26600 | 69.265 | 34.9331 | Open | AP Only | AP Only | MineField | Blank | MBT Project-309 | Good Neighbor project |  | No |  |  | 1393 | None | {D10473C1-1420-4F44-8068-46650A0FF7CF} | Removed from HT plan | High with Victim | High with Victims | Moderate | 134 | CHA | 2 |  |  | 2008-12-04 | No | Open
Central | Parwan | Bagram | Yosbashi Ulia | {D10473C1-1420-4F44-8068-46650A0FF7CF} | c0a8-008e-132e7270aa5-db6502bd-2b7-8a | MF-CA-1823 | MCPA - Mine Clearance Planning Agency | AF/0308/00015/MF5474-HR | 12700 | 69.2686 | 34.9324 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108/A | Parwan Demining Project-07/A | VTF-Japan | Yes | 2013-06-10 | 2013-07-17 | 1392 | ATC | {D10473C1-1420-4F44-8068-46650A0FF7CF} |  |  |  | Moderate | 432 | CHA | 2 |  |  | 2008-12-05 | No | Complete
Central | Parwan | Chaharikar | Bayani Bala | {18F31C92-E753-4011-BA6E-8C31F25F1EF1} | c0a8-0057-12c3b981650-8ff2c6dc-29e42- | MF-CA-1432 | HT - HALO TRUST | H/4336 | 1617 | 69.1887 | 35.0425 | Open | AP Only | AP Only | MineField | Blank | MBT Project-001/A | Parwan Demining Project-01/A |  | No |  |  | 1394 | None | {18F31C92-E753-4011-BA6E-8C31F25F1EF1} |  | High | Critical Infrastracture | Low | 141 | CHA | 3 |  |  | 2008-06-16 | No | Open
Central | Parwan | Chaharikar | Bayani Bala | {18F31C92-E753-4011-BA6E-8C31F25F1EF1} | c0a8-008e-13146bfa196-158695f6-2f3e-d | MF-CA-1363 | HT - HALO TRUST | H/4232 | 160 | 69.2202 | 35.0406 | Open | AP Only | AP Only | MineField | Blank | MBT Project-001/A | Parwan Demining Project-01/A |  | No |  |  | 1394 | None | {18F31C92-E753-4011-BA6E-8C31F25F1EF1} |  | High | Critical Infrastracture | Low | 155 | CHA | 3 |  |  | 2008-04-14 | No | Open
Central | Parwan | Chaharikar | Belandi | {340AB1FA-5777-4228-9CE3-87CA3840642C} | c0a8-008e-1328f98a4e6-1502b78-1b8c-aa | MF-15498 | HT - HALO TRUST | H/7533 | 1500 | 69.1399 | 35.0804 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-07-13 | 2013-07-17 | 1392 | OMAR | {340AB1FA-5777-4228-9CE3-87CA3840642C} |  |  |  | Low | 140 | CHA | 3 |  |  | 2010-11-08 16:30 | No | Complete
Central | Parwan | Chaharikar | Chaykal | {33B01D76-CDA9-4D97-B3EE-C064A4C5039E} | c0a8-00f6-1355c8e165c-ca89b227-120d-4 | BF-15201 | MCPA - Mine Clearance Planning Agency | AF/0301/01612/BF0158 | 105 | 69.1671 | 34.942 | Open | UXO Only | UXO Only | BF |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {33B01D76-CDA9-4D97-B3EE-C064A4C5039E} | , | High | Water Blocked | Low | 0 | CHA | 3 |  |  | 2011-12-14 16:30 | No | Pledged
Central | Parwan | Chaharikar | Deh gholaman | {1A8543D1-6F82-4C09-A733-18FB25E692B6} | c0a8-0057-12c3b79f5a7-17d3af05-15262- | MF-HQ-14657 | MCPA - Mine Clearance Planning Agency | AF/0301/01371/MF0147 | 70000 | 69.0987 | 34.9395 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {1A8543D1-6F82-4C09-A733-18FB25E692B6} |  | Low | Agriculture Blocked | Low | 12 | CHA | 5 |  |  | 2010-03-25 | No | Planned
Central | Parwan | Chaharikar | Deh-e Neshar | {27955E18-7AA8-4C48-A652-E77437B153A7} | c0a8-00f6-134c657b5a1-6d5eaf8d-294b-7 | MF-15596 | MCPA - Mine Clearance Planning Agency | AF/0308/01610/MF7226 | 30943 | 69.1047 | 34.9431 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-05-07 | 2013-05-30 | 1392 | OMAR | {27955E18-7AA8-4C48-A652-E77437B153A7} |  |  |  | Low | 35 | CHA | 3 |  |  | 2010-11-28 16:30 | No | Complete
Central | Parwan | Chaharikar | Ghurband Dara | {635DFF68-B864-4101-A8B9-EDCF6AC65485} | c0a8-0057-12c3b78827e-62581277-14188- | MF-HT-1384 | MCPA - Mine Clearance Planning Agency | AF/0301/00006/MF3883 | 24800 | 69.0962 | 34.9504 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-05-14 | 2013-06-13 | 1392 | OMAR | {635DFF68-B864-4101-A8B9-EDCF6AC65485} |  |  |  | Low | 13 | CHA | 4 |  |  | 2007-12-01 | No | Complete
Central | Parwan | Chaharikar | Ghurband Dara | {635DFF68-B864-4101-A8B9-EDCF6AC65485} | c0a8-008e-1328a491876-574ab43e-67a-d7 | MF-15572 | MCPA - Mine Clearance Planning Agency | AF/0301/00006/MF7228 | 23400 | 69.0895 | 34.9516 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {635DFF68-B864-4101-A8B9-EDCF6AC65485} |  | Medium | Critical Infrastracture | Low | 21 | CHA | 5 |  |  | 2010-12-01 16:30 | No | Planned
Central | Parwan | Chaharikar | Ghurband Dara | {635DFF68-B864-4101-A8B9-EDCF6AC65485} | c0a8-00f6-1352e8f3061-28ba281c-1e6-75 | MF-16554 | MCPA - Mine Clearance Planning Agency | AF/0301/00006/MF8352 | 24800 | 69.0941 | 34.9536 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {635DFF68-B864-4101-A8B9-EDCF6AC65485} |  | Low | Agriculture Blocked | Low | 13 | CHA | 5 |  |  | 2011-12-13 16:30 | No | Planned
Central | Parwan | Chaharikar | Khalazai | {FC88B8D3-01AD-4F26-8D86-9A26589BAB91} | c0a8-0009-141d53ba2b0-2d352e90-20b-8a | Hz-ID-18115 | MCPA - Mine Clearance Planning Agency | AF/0301/00003/spotUXO0001 |  | 69.1672 | 34.9192 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-003 | Parwan Demining Project-03 | DOS |  |  |  | 1393 |  | {FC88B8D3-01AD-4F26-8D86-9A26589BAB91} |  | Medium | Comunity Centers | Low | 120 | CHA | 4 |  |  | 2013-01-27 16:30 | No | Pledged
Central | Parwan | Chaharikar | Khwaja Syarane Ulya | {EA3FFDAE-E89E-4B44-A1E1-9DE26D9FEEEE} | c0a8-0057-12c3b7c8eb4-7f43d5a8-1705a- | MF-CA-1373 | HT - HALO TRUST | H/5327 | 44400 | 69.1121 | 35.0175 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {EA3FFDAE-E89E-4B44-A1E1-9DE26D9FEEEE} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2008-09-03 | No | Planned
Central | Parwan | Chaharikar | Khwaja Syarane Ulya | {EA3FFDAE-E89E-4B44-A1E1-9DE26D9FEEEE} | c0a8-0057-12c3b7c9069-34de9e95-1706e- | MF-HQ-11913 | HT - HALO TRUST | H/4399 | 43000 | 69.1121 | 35.0175 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {EA3FFDAE-E89E-4B44-A1E1-9DE26D9FEEEE} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2008-09-02 | No | Planned
Central | Parwan | Chaharikar | Khwaja Syarane Ulya | {EA3FFDAE-E89E-4B44-A1E1-9DE26D9FEEEE} | c0a8-0057-12c3bb4a54f-3c9dc7ff-3b468- | MF-CA-1369 | HT - HALO TRUST | H/4374 | 42000 | 69.1121 | 35.0175 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {EA3FFDAE-E89E-4B44-A1E1-9DE26D9FEEEE} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2008-10-09 | No | Planned
Central | Parwan | Chaharikar | Khwaja Syarane Ulya | {EA3FFDAE-E89E-4B44-A1E1-9DE26D9FEEEE} | c0a8-0057-12c3bb4a742-28577da4-3b47d- | MF-CA-1370 | MCPA - Mine Clearance Planning Agency | AF/0301/01384/MF4375 | 40000 | 69.115 | 35.0195 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {EA3FFDAE-E89E-4B44-A1E1-9DE26D9FEEEE} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2008-08-09 | No | Planned
Central | Parwan | Chaharikar | Khwaja Syarane Ulya | {EA3FFDAE-E89E-4B44-A1E1-9DE26D9FEEEE} | c0a8-0057-12c3bb4a935-890136f3-3b490- | MF-CA-1371 | HT - HALO TRUST | H/4372 | 45000 | 69.1121 | 35.0175 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {EA3FFDAE-E89E-4B44-A1E1-9DE26D9FEEEE} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2008-08-10 | No | Planned
Central | Parwan | Chaharikar | Laghmani | {94F9F4F3-444A-4DD9-B5A9-D0D2AB7D6E2B} | c0a8-0009-13fcd1a68b3-2c120d95-131-a7 | Hz-ID-18027 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0301/00450/MF0160 | 119 | 69.1633 | 34.9777 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-06-15 | 2013-06-18 | 1392 | OMAR | {94F9F4F3-444A-4DD9-B5A9-D0D2AB7D6E2B} |  |  |  | Low | 0 | CHA | 3 |  |  | 2013-06-05 16:30 | No | Complete
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b7cacce-7dd53bfc-171c1- | MF-CA-2168 | HT - HALO TRUST | H/4331 | 40000 | 69.1149 | 35.0359 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | , | Medium | Critical Infrastracture | Low | 12 | CHA | 3 |  |  | 2008-06-15 | No | Planned
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b7cb009-2b750caf-171e7- | MF-CA-2182 | HT - HALO TRUST | H/4325 | 40000 | 69.1245 | 35.032 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | , | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2008-06-13 | No | Planned
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b7cb363-ec0c6673-1720b- | MF-CA-2174 | HT - HALO TRUST | H/4321 | 42000 | 69.1365 | 35.0464 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221/C | Parwan Demining Project-06 /C | GAGP | Yes |  |  | 1393 | HT | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2008-06-11 | No | Planned
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b7cb508-807f773f-1721d- | MF-CA-2186 | MCPA - Mine Clearance Planning Agency | AF/0301/01393/MF4315 | 40000 | 69.1444 | 35.0532 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221/C | Parwan Demining Project-06 /C | GAGP | Yes | 2014-04-11 | 2014-06-22 | 1393 | HT | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} |  | Low | Agriculture Blocked | Low | 3 | CHA | 5 |  |  | 2008-06-08 | No | Planned
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b7cc5ca-a4eb0e2d-172d4- | MF-CA-2187 | HT - HALO TRUST | H/4332 | 40000 | 69.113 | 35.0364 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | , | Medium | Critical Infrastracture | Low | 12 | CHA | 3 |  |  | 2008-06-16 | No | Planned
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b800235-f632a51d-19731- | MF-HQ-11817 | MCPA - Mine Clearance Planning Agency | AF/0301/01393/MF4306 | 31000 | 69.1554 | 35.0664 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108/A | Parwan Demining Project-07/A | VTF-Japan | Yes |  |  | 1392 | ATC | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} |  |  |  | Low | 1 | CHA | 5 |  |  | 2008-06-04 | No | Complete
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b8003ea-3c188eb3-19743- | MF-HQ-11925 | MCPA - Mine Clearance Planning Agency | AF/0301/01393/MF4311 | 47000 | 69.1497 | 35.0594 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-06-10 | 2013-07-20 | 1392 | OMAR | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} |  |  |  | Low | 4 | CHA | 3 |  |  | 2008-06-06 | No | Complete
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b8005be-178615d3-19755- | MF-HQ-11807 | MCPA - Mine Clearance Planning Agency | AF/0301/01393/MF4303 | 34000 | 69.1612 | 35.0717 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108/A | Parwan Demining Project-07/A | VTF-Japan | Yes |  |  | 1392 | ATC | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} |  |  |  | Low | 3 | CHA | 5 |  |  | 2008-06-02 | No | Complete
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b800772-a3cb56a5-19769- | MF-HQ-11918 | MCPA - Mine Clearance Planning Agency | AF/0301/01393/MF4308 | 40000 | 69.1535 | 35.0642 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-04-01 | 2014-06-23 | 1393 | HT | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} |  |  |  | Low | 0 | CHA | 5 |  |  | 2008-06-05 | No | Planned
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b800937-aa75bd58-1977b- | MF-HQ-11916 | MCPA - Mine Clearance Planning Agency | AF/0301/01393/MF4307 | 40000 | 69.1556 | 35.0652 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-03-30 | 2014-06-16 | 1393 | HT | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} |  |  |  | Low | 1 | CHA | 5 |  |  | 2008-06-04 | No | Planned
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b800b0b-b2a2200e-1978d- | MF-HQ-11805 | MCPA - Mine Clearance Planning Agency | AF/0301/01393/MF4305 | 40000 | 69.1574 | 35.0685 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108/A | Parwan Demining Project-07/A | VTF-Japan | Yes |  |  | 1392 | ATC | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} |  |  |  | Low | 1 | CHA | 5 |  |  | 2008-06-03 | No | Complete
Central | Parwan | Chaharikar | Mir'ala | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} | c0a8-0057-12c3b801048-e76a5800-197c3- | MF-HQ-11804 | MCPA - Mine Clearance Planning Agency | AF/0301/01393/MF4304 | 40000 | 69.1587 | 35.0699 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-04-01 | 2014-07-23 | 1393 | HT | {10DA70D2-7F2D-4539-8734-7BD5C14DA3CA} |  |  |  | Low | 3 | CHA | 5 |  |  | 2008-06-02 | No | Planned
Central | Parwan | Chaharikar | Myanshakh | {03B03E09-3B86-4871-AFC3-ADB827CADF7C} | c0a8-0009-14401b95ab8-58ebc83-47b-e6f | Hz-ID-18428 | MCPA - Mine Clearance Planning Agency | AF/0301/01400/BF0157 | 451 | 69.1951 | 34.9687 | Open | Mixed | Mixed AT UXO | BF |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {03B03E09-3B86-4871-AFC3-ADB827CADF7C} |  | High | Critical Infrastracture | Low | 0 | CHA | 3 |  |  | 2011-10-16 16:30 | No | Open
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467b3be06a-aa49fb01-1bda-7 | Hz-ID-18810 | HT - HALO TRUST | H/8789 | 95000 | 69.1314 | 35.053 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 10 | CHA | 5 |  |  | 2014-05-12 16:30 | No | Open
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f40827c-6941f70e-1f18-9 | Hz-ID-18788 | HT - HALO TRUST | H/8778 | 49500 | 69.15 | 35.0633 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 7 | CHA | 5 |  |  | 2014-05-01 16:30 | No | Planned
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f42a804-b0f804a1-1f4e-f | Hz-ID-18793 | HT - HALO TRUST | H/8779 | 74500 | 69.1454 | 35.0616 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 7 | CHA | 5 |  |  | 2014-05-02 16:30 | No | Planned
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f44ba2c-64a72fbe-1f82-8 | Hz-ID-18795 | HT - HALO TRUST | H/8780 | 80000 | 69.1428 | 35.0606 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 3 | CHA | 5 |  |  | 2014-05-03 16:30 | No | Planned
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f4ed141-8ab824e5-1fee-5 | Hz-ID-18818 | HT - HALO TRUST | H/8797 | 47900 | 69.1245 | 35.0428 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 10 | CHA | 5 |  |  | 2014-05-20 16:30 | No | Open
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f51ebe1-9e86f111-2018-9 | Hz-ID-18796 | HT - HALO TRUST | H/8781 | 61000 | 69.1403 | 35.0579 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 3 | CHA | 5 |  |  | 2014-05-04 16:30 | No | Planned
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f59b776-deab382e-206c-d | Hz-ID-18817 | HT - HALO TRUST | H/8796 | 75000 | 69.1245 | 35.0428 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 10 | CHA | 5 |  |  | 2014-05-19 16:30 | No | Open
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f5c2026-a707fb41-2096-3 | Hz-ID-18816 | HT - HALO TRUST | H/8795 | 47000 | 69.1245 | 35.0428 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2014-06-08 16:30 | No | Open
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f607a44-19396684-20c3-f | Hz-ID-18815 | HT - HALO TRUST | H/8794 | 67900 | 69.1245 | 35.0428 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2014-05-17 16:30 | No | Open
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f65c112-55cf04b3-20f0-f | Hz-ID-18814 | HT - HALO TRUST | H/8793 | 69850 | 69.1273 | 35.0474 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2014-05-16 16:30 | No | Open
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f6e8fc2-c7a744f1-21bd-3 | Hz-ID-18798 | HT - HALO TRUST | H/8782 | 65300 | 69.1392 | 35.0569 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 3 | CHA | 5 |  |  | 2014-05-05 16:30 | No | Planned
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f725984-86231e52-21ee-6 | Hz-ID-18801 | HT - HALO TRUST | H/8784 | 91500 | 69.1358 | 35.0554 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 17 | CHA | 5 |  |  | 2014-05-07 16:30 | No | Planned
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f7da010-badc8d34-2288-f | Hz-ID-18803 | HT - HALO TRUST | H/8785 | 65500 | 69.1392 | 35.0575 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 19 | CHA | 5 |  |  | 2014-05-08 16:30 | No | Planned
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f8a4aac-a69573f8-2310-1 | Hz-ID-18808 | HT - HALO TRUST | H/8787 | 108900 | 69.1358 | 35.0554 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 17 | CHA | 5 |  |  | 2014-05-10 16:30 | No | Planned
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467f9b2883-7d58360-2395-47 | Hz-ID-18813 | HT - HALO TRUST | H/8792 | 83500 | 69.1273 | 35.0474 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2014-05-15 16:30 | No | Open
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467fe4791d-da78d067-23d1-9 | Hz-ID-18812 | HT - HALO TRUST | H/8791 | 98000 | 69.1321 | 35.0486 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 10 | CHA | 5 |  |  | 2014-05-14 16:30 | No | Open
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467fe8bcee-4643012d-23fd-5 | Hz-ID-18811 | HT - HALO TRUST | H/8790 | 66000 | 69.1321 | 35.0486 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 10 | CHA | 5 |  |  | 2014-05-13 16:30 | No | Open
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-1467feb674f-aced301e-2428-8 | Hz-ID-18809 | HT - HALO TRUST | H/8788 | 108500 | 69.1314 | 35.053 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2014-05-11 16:30 | No | Planned
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0009-146a33f65e5-17e829e4-2-488c | Hz-ID-18799 | HT - HALO TRUST | H/8783 | 55000 | 69.138 | 35.0555 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 68 | CHA | 5 |  |  | 2014-05-06 16:30 | No | Planned
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0057-12c3b7ca5fb-c466269c-17171- | MF-HQ-10016 | MCPA - Mine Clearance Planning Agency | AF/0301/01388/MF4328 | 40000 | 69.1189 | 35.0347 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108/A | Parwan Demining Project-07/A | VTF-Japan | Yes | 2013-05-05 | 2013-08-31 | 1392 | ATC | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | RFP Project |  |  | Low | 1 | CHA | 3 |  |  | 2009-04-27 | No | Complete
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0057-12c3b7cae64-49298b10-171d5- | MF-HQ-10015 | HT - HALO TRUST | H/4327 | 40000 | 69.1209 | 35.0341 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108/A | Parwan Demining Project-07/A | VTF-Japan | Yes | 2013-05-05 | 2013-08-05 | 1392 | ATC | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  |  |  | Low | 1 | CHA | 5 |  |  | 2009-04-27 | No | Complete
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0057-12c3b7cb6ad-d66ec8c9-1722f- | MF-HQ-14255 | MCPA - Mine Clearance Planning Agency | AF/0301/01388/MF4300 | 38500 | 69.1355 | 35.0402 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221/C | Parwan Demining Project-06 /C | GAGP | Yes |  |  | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} |  | Low | Agriculture Blocked | Low | 17 | CHA | 5 |  |  | 2008-06-17 | No | Planned
Central | Parwan | Chaharikar | Ofyane Sharif | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | c0a8-0057-12c3b7cc09c-28efb426-1729b- | MF-HQ-11814 | HT - HALO TRUST | H/4320 | 38000 | 69.1373 | 35.0477 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-05-01 | 2014-06-23 | 1393 | HT | {856E74D7-ABD3-47EE-A545-76EBCC07A0C0} | , | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2008-06-10 | No | Planned
Central | Parwan | Chaharikar | Panjpadar | {61A9198C-FB3E-4F0B-9274-02D8CB281AF6} | c0a8-008e-1329eeced20-e73875ef-a17-40 | MF-16101 | HT - HALO TRUST | H/7812 | 200 | 69.1581 | 34.9426 | Open | AP Only | AP Only | MineField | Blank | MBT Project-001/A | Parwan Demining Project-01/A |  | No |  |  | 1394 | None | {61A9198C-FB3E-4F0B-9274-02D8CB281AF6} |  | High | Critical Infrastracture | Low | 0 | CHA | 3 |  |  | 2011-04-05 16:30 | No | Open
Central | Parwan | Chaharikar | Qala Naw | {EA3E5BDC-1F4D-4C1A-8071-79291E2727F0} | c0a8-0009-13dc97c5214-ecc722d2-21a8-5 | Hz-ID-17746 | MCPA - Mine Clearance Planning Agency | AF/0301/01396/BF0159 | 129 | 69.1945 | 35.0339 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-108/A | Parwan Demining Project-07/A | VTF-Japan | Yes | 2013-06-18 | 2013-07-09 | 1392 | ATC | {EA3E5BDC-1F4D-4C1A-8071-79291E2727F0} |  |  |  | Low | 3593 | CHA | 3 |  |  | 2013-02-10 16:30 | No | Complete
Central | Parwan | Chaharikar | Senjed dara | {A1CE6B9F-3D24-4908-A7D1-8CDFACD061F0} | c0a8-0057-12c3b76a001-67e65706-12ba1- | MF-HT-1376 | MCPA - Mine Clearance Planning Agency | AF/0301/00493/MF1823 | 25950 | 69.0898 | 34.9506 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-05-14 | 2013-06-13 | 1392 | OMAR | {A1CE6B9F-3D24-4908-A7D1-8CDFACD061F0} |  |  |  | Low | 21 | CHA | 2 |  |  | 2007-12-01 | No | Complete
Central | Parwan | Chaharikar | Senjed dara | {A1CE6B9F-3D24-4908-A7D1-8CDFACD061F0} | c0a8-0057-12c3ba2d236-548481d2-30a7d- | MF-CA-1389 | MCPA - Mine Clearance Planning Agency | AF/0301/00493/MF4271 | 40000 | 69.0679 | 34.9568 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-06-01 | 2013-06-06 | 1392 | OMAR | {A1CE6B9F-3D24-4908-A7D1-8CDFACD061F0} | Leftover project |  |  | Low | 4 | CHA | 2 |  |  | 2008-05-08 | No | Complete
Central | Parwan | Chaharikar | Totumdara-i-Sufla | {D5EB7995-6834-4A6D-A7C4-6A05232B0EE0} | c0a8-008e-1342d3a94f6-99d75f09-2-25b9 | MF-15918 | MCPA - Mine Clearance Planning Agency | AF/0301/01743/MF0154 | 27483 | 69.141 | 35.0581 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221/C | Parwan Demining Project-06 /C | GAGP | Yes |  |  | 1393 | HT | {D5EB7995-6834-4A6D-A7C4-6A05232B0EE0} |  | Low | Agriculture Blocked | Low | 20 | CHA | 5 |  |  | 2010-12-30 16:30 | No | Planned
Central | Parwan | Chaharikar | Totumdara-i-Ulya | {9FFF1226-5F2C-423C-951C-49C73A9DCC7A} | c0a8-0009-1473de505ca-e60815a0-71d-fd | Hz-ID-18857 | HT - HALO TRUST | H/8801 | 65000 | 69.1674 | 35.0728 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {9FFF1226-5F2C-423C-951C-49C73A9DCC7A} |  | Low | Critical Infrastracture | Low | 0 | CHA | 5 |  |  | 2014-06-21 16:30 | No | Open
Central | Parwan | Chaharikar | Totumdara-i-Ulya | {9FFF1226-5F2C-423C-951C-49C73A9DCC7A} | c0a8-00f6-1355231a3f4-f3ef67a3-469-79 | MF-15753 | MCPA - Mine Clearance Planning Agency | AF/0301/01743/MF0153 | 40000 | 69.1477 | 35.0697 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221/C | Parwan Demining Project-06 /C | GAGP | Yes |  |  | 1393 | HT | {9FFF1226-5F2C-423C-951C-49C73A9DCC7A} |  | Low | Agriculture Blocked | Low | 43 | CHA | 5 |  |  | 2011-02-23 16:30 | No | Planned
Central | Parwan | Jabalussaraj | Ashawa | {1774D293-A2C5-4099-88E9-80C3B1777BB5} | c0a8-00f6-137f9e7d177-89303cda-583-b6 | Hz-ID-17013 | HT - HALO TRUST | H/6776 | 32000 | 69.1359 | 35.0903 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-07-06 | 2013-08-07 | 1392 | OMAR | {1774D293-A2C5-4099-88E9-80C3B1777BB5} |  |  |  | Low | 209 | CHA | 2 |  |  | 2010-02-02 16:30 | No | Complete
Central | Parwan | Jabalussaraj | Dehe Bala | {784C8BD5-698F-4EDA-B33D-8FF634B022E9} | c0a8-0057-12c3b8a9535-f7e9c767-20e49- | MF-HT-657 | HT - HALO TRUST | H/3239 | 28500 | 69.213 | 35.1294 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-06-15 | 2013-07-11 | 1392 | OMAR | {784C8BD5-698F-4EDA-B33D-8FF634B022E9} |  |  |  | Low | 42 | CHA | 4 |  |  | 2007-12-17 14:09 | No | Complete
Central | Parwan | Jabalussaraj | Dihi Bala | {FEAAF759-E624-4AD0-8C4D-D18C610A6DF5} | c0a8-008e-1328a49aa09-f8ffa85b-6a0-55 | MF-15574 | HT - HALO TRUST | H/7230 | 27250 | 69.213 | 35.1294 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-07-01 | 2013-09-17 | 1392 | HT | {FEAAF759-E624-4AD0-8C4D-D18C610A6DF5} |  |  |  | Low | 28 | CHA | 5 |  |  | 2010-12-03 16:30 | No | Complete
Central | Parwan | Jabalussaraj | Lakar | {7D89ACEA-4028-49C0-B9C2-7351B153FEFA} | c0a8-0009-144961c73b5-e4116766-fae-89 | Hz-ID-18546 | HT - HALO TRUST | H/8533 | 63200 | 69.2748 | 35.1576 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221/B | Parwan Demining Project-06 /B | B-Germany | Yes |  |  | 1393 | HT | {7D89ACEA-4028-49C0-B9C2-7351B153FEFA} |  | Low | Agriculture Blocked | Low | 281 | CHA | 4 |  |  | 2014-02-17 16:30 | No | Planned
Central | Parwan | Jabalussaraj | Lakar | {7D89ACEA-4028-49C0-B9C2-7351B153FEFA} | c0a8-0009-145453733c5-7de468ed-26d-ee | Hz-ID-18552 | HT - HALO TRUST | H/8535 | 58460 | 69.2792 | 35.1566 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-221/B | Parwan Demining Project-06 /B | B-Germany | Yes |  |  | 1393 | HT | {7D89ACEA-4028-49C0-B9C2-7351B153FEFA} |  | Low | Agriculture Blocked | Low | 1914 | CHA | 4 |  |  | 2014-03-12 16:30 | No | Planned
Central | Parwan | Jabalussaraj | Lakar | {7D89ACEA-4028-49C0-B9C2-7351B153FEFA} | c0a8-0057-12c3b7f5c28-9a34339f-18fb8- | MF-HQ-10128 | ATC - Afghan Technical Consultants | AF/0302/01791/MF0032 | 19200 | 69.2798 | 35.1519 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-07-21 | 2013-08-25 | 1392 | OMAR | {7D89ACEA-4028-49C0-B9C2-7351B153FEFA} |  |  |  | Low | 870 | CHA | 1 | Yes | Confirmed have accident | 2009-04-06 | No | Complete
Central | Parwan | Jabalussaraj | Qal'a Bala | {04BBBECA-6A54-4EB8-9693-A475242B0473} | c0a8-00f6-134a754a320-65d0bc12-1c1-3c | MF-16473 | HT - HALO TRUST | H/8381 | 9700 | 69.2622 | 35.1512 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-03-30 | 2013-06-22 | 1392 | HT | {04BBBECA-6A54-4EB8-9693-A475242B0473} | Based on HALO Trust confirmation, the hazard is removed form their plan |  |  | Low | 34 | CHA | 5 |  |  | 2011-10-06 16:30 | No | Complete
Central | Parwan | Jabalussaraj | Qal'a Bala | {04BBBECA-6A54-4EB8-9693-A475242B0473} | c0a8-00f6-134a75a3201-41cff3ca-1ff-ff | MF-16467 | HT - HALO TRUST | H/8383 | 32500 | 69.2622 | 35.1512 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-03-30 | 2013-05-23 | 1392 | HT | {04BBBECA-6A54-4EB8-9693-A475242B0473} | Based on HALO Trust confirmation, the hazard is removed from their plan |  |  | Low | 41 | CHA | 5 |  |  | 2011-10-10 16:30 | No | Complete
Central | Parwan | Jabalussaraj | Shatutak | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} | c0a8-0057-12c3b8a8213-5668b50c-20d91- | MF-HT-693 | HT - HALO TRUST | H/3702 | 40000 | 69.1967 | 35.1215 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-06-06 | 2013-08-23 | 1392 | HT | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} |  |  |  | Low | 46 | CHA | 5 |  |  | 2007-12-17 18:18 | No | Complete
Central | Parwan | Jabalussaraj | Shatutak | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} | c0a8-0057-12c3b8a8702-461b52c0-20db5- | MF-HT-687 | HT - HALO TRUST | H/3397 | 1254 | 69.2138 | 35.1169 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-03-03 | 2013-03-18 | 1392 | HT | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} |  |  |  | Low | 60 | CHA | 3 |  |  | 2007-12-17 17:29 | No | Complete
Central | Parwan | Jabalussaraj | Shatutak | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} | c0a8-0057-12c3b8a8a5c-78717135-20ddb- | MF-HT-688 | HT - HALO TRUST | H/3398 | 40000 | 69.1992 | 35.1187 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-03-30 | 2013-06-20 | 1392 | HT | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} |  |  |  | Low | 46 | CHA | 5 |  |  | 2007-12-17 17:37 | No | Complete
Central | Parwan | Jabalussaraj | Shatutak | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} | c0a8-0057-12c3b8a8bf2-f264547b-20ded- | MF-HT-692 | HT - HALO TRUST | H/3701 | 40000 | 69.1951 | 35.1203 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-04-01 | 2013-06-23 | 1392 | HT | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} |  |  |  | Low | 19 | CHA | 5 |  |  | 2007-12-17 18:12 | No | Complete
Central | Parwan | Jabalussaraj | Shatutak | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} | c0a8-0057-12c3b8a8d97-53b24d8-20dff-5 | MF-HT-699 | HT - HALO TRUST | H/3705 | 29250 | 69.2081 | 35.1244 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-06-15 | 2013-07-15 | 1392 | OMAR | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} |  |  |  | Low | 14 | CHA | 4 |  |  | 2007-12-17 18:37 | No | Complete
Central | Parwan | Jabalussaraj | Shatutak | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} | c0a8-0057-12c3b8a8f4c-352ce026-20e11- | MF-HT-683 | HT - HALO TRUST | H/3330 | 40000 | 69.1977 | 35.1174 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-03-03 | 2013-06-20 | 1392 | HT | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} |  |  |  | Low | 19 | CHA | 5 |  |  | 2007-12-17 16:44 | No | Complete
Central | Parwan | Jabalussaraj | Shatutak | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} | c0a8-0057-12c3b8a9101-cc99efda-20e23- | MF-HT-690 | HT - HALO TRUST | H/3399 | 23000 | 69.2013 | 35.1197 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-03-30 | 2013-06-20 | 1392 | HT | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} |  |  |  | Low | 46 | CHA | 5 |  |  | 2007-12-17 18:04 | No | Complete
Central | Parwan | Jabalussaraj | Shatutak | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} | c0a8-0057-12c3b8a987f-3e470583-20e72- | MF-HT-695 | HT - HALO TRUST | H/3703 | 20500 | 69.2006 | 35.122 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-03-30 | 2013-06-05 | 1392 | HT | {CAA4DD61-E037-46A4-82DC-FFCDCDE35485} |  |  |  | Low | 27 | CHA | 5 |  |  | 2007-12-17 18:24 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0009-14227b144da-1cd2dd78-434a-b | Hz-ID-18205 | HT - HALO TRUST | H/8521 | 58000 | 69.2386 | 35.141 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-221/B | Parwan Demining Project-06 /B | B-Germany | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  | Low | Agriculture Blocked | Low | 24 | CHA | 5 |  |  | 2013-10-11 16:30 | No | Planned
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0057-12c3b740eb2-c872b7fd-10d2b- | MF-HQ-14833 | HT - HALO TRUST | H/7040 | 75000 | 69.2419 | 35.1456 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-07-11 | 2013-08-31 | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} | Removed from HT plan |  |  | Low | 39 | CHA | 4 |  |  | 2010-07-13 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0057-12c3b887bd1-b421296f-1f711- | MF-HQ-14862 | HT - HALO TRUST | H/7041 | 78000 | 69.2433 | 35.1481 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-08-01 | 2013-09-12 | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 42 | CHA | 4 |  |  | 2010-07-14 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0057-12c3b887d96-4e76339c-1f725- | MF-HQ-14839 | HT - HALO TRUST | H/7044 | 26100 | 69.245 | 35.1386 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes |  |  | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 20 | CHA | 4 |  |  | 2010-07-17 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0057-12c3b8c128b-f95d6c29-21f3a- | MF-HQ-14827 | HT - HALO TRUST | H/7034 | 63000 | 69.2409 | 35.1503 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes |  |  | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 27 | CHA | 4 |  |  | 2010-07-07 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0057-12c3b8c1633-1a57957d-21f61- | MF-HQ-14826 | HT - HALO TRUST | H/7033 | 65000 | 69.2403 | 35.149 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-05-01 | 2013-07-06 | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 24 | CHA | 4 |  |  | 2010-07-06 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0057-12c3b8c1845-9f3c3ef0-21f74- | MF-HQ-14824 | HT - HALO TRUST | H/7031 | 31800 | 69.2308 | 35.1372 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-04-04 | 2013-04-30 | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 24 | CHA | 4 |  |  | 2010-07-04 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0057-12c3b8c1bed-5545f554-21f9b- | MF-HQ-14800 | HT - HALO TRUST | H/7009 | 25325 | 69.2308 | 35.1372 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-04-13 | 2013-04-30 | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 33 | CHA | 4 |  |  | 2010-07-02 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0057-12c3b8c2521-4a97e5f2-21feb- | MF-HQ-14801 | HT - HALO TRUST | H/7010 | 20500 | 69.2376 | 35.1437 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes |  |  | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 24 | CHA | 4 |  |  | 2010-07-03 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0057-12c3b8c2a9d-429d00c8-22026- | MF-HQ-14825 | HT - HALO TRUST | H/7032 | 70000 | 69.2393 | 35.1471 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-05-16 | 2013-07-10 | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 24 | CHA | 4 |  |  | 2010-08-01 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0057-12c3b8c2c61-9d4b759d-2203a- | MF-HQ-14832 | HT - HALO TRUST | H/7038 | 67000 | 69.2437 | 35.1488 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-06-08 | 2013-07-31 | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 42 | CHA | 4 |  |  | 2010-07-11 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-0057-12c3b8c3019-7f602936-2204d- | MF-HQ-14830 | HT - HALO TRUST | H/7037 | 64000 | 69.2429 | 35.1474 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-04-14 | 2013-05-15 | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 39 | CHA | 4 |  |  | 2010-07-10 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-008e-1328f50b551-c3ed742a-100c-a | MF-15797 | HT - HALO TRUST | H/7660 | 28350 | 69.2449 | 35.1386 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-04-03 | 2013-06-21 | 1392 | HT | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 15 | CHA | 5 |  |  | 2010-11-12 16:30 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-00f6-134e4cce11c-519b9ff1-52d-d5 | MF-15894 | HT - HALO TRUST | H/7670 | 28400 | 69.2308 | 35.1372 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-08-01 | 2013-09-12 | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 24 | CHA | 4 |  |  | 2011-03-17 16:30 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-00f6-134e4cea1e9-2dbd0795-541-a5 | MF-15904 | HT - HALO TRUST | H/7665 | 29600 | 69.2308 | 35.1372 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-001 | Parwan Demining Project-01 | DOS | Yes | 2013-07-20 | 2013-08-20 | 1392 | OMAR | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 24 | CHA | 4 |  |  | 2011-03-18 16:30 | No | Complete
Central | Parwan | Jabalussaraj | Tajikan | {2AEB127B-B4D5-4164-9742-437E16121A7F} | c0a8-00f6-134e4e70657-5991f805-5d2-d1 | MF-15906 | HT - HALO TRUST | H/7668 | 25000 | 69.2308 | 35.1372 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-108 | Parwan Demining Project-07 | Bilateral | Yes | 2013-09-12 | 2013-11-23 | 1392 | HT | {2AEB127B-B4D5-4164-9742-437E16121A7F} |  |  |  | Low | 24 | CHA | 5 |  |  | 2011-03-15 16:30 | No | Complete
Central | Parwan | Jabalussaraj | Tutak | {9004B11A-8C2F-48AB-9D2A-10FDA7535349} | c0a8-00f6-134e4d2fc04-f47acc94-559-ba | MF-16518 | HT - HALO TRUST | H/8057 | 26500 | 69.1228 | 35.0891 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221/B | Parwan Demining Project-06 /B | B-Germany | Yes |  |  | 1393 | HT | {9004B11A-8C2F-48AB-9D2A-10FDA7535349} |  | Low | Agriculture Blocked | Low | 23 | CHA | 5 |  |  | 2011-06-12 16:30 | No | Planned
Central | Parwan | Kohi Safi | Ahmadza'i | {DF496A63-16CF-4A7B-8485-60C7955D98A7} | c0a8-0057-12c3b7e1b55-68f5c162-18220- | MF-HQ-14475 | DDG - Danish Demining Group | AF/0309/01694/MF6783 | 48500 | 69.4318 | 34.9238 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-09-01 | 2014-12-21 | 1393 | MCPA | {DF496A63-16CF-4A7B-8485-60C7955D98A7} |  | High with Victim | High with Victims | Substantial | 178 | CHA | 2 |  |  | 2010-02-21 | No | Planned
Central | Parwan | Kohi Safi | Ahmadza'i | {DF496A63-16CF-4A7B-8485-60C7955D98A7} | c0a8-0057-12c3bb07239-29e6f23f-38c82- | MF-HT-889 | DDG - Danish Demining Group | AF/0309/01694/MF1868 | 35500 | 69.4337 | 34.9249 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-18 | 2014-08-31 | 1393 | MCPA | {DF496A63-16CF-4A7B-8485-60C7955D98A7} |  | High with Victim | High with Victims | Substantial | 178 | CHA | 2 |  |  | 2010-03-02 | No | Planned
Central | Parwan | Kohi Safi | Ahmadza'i | {DF496A63-16CF-4A7B-8485-60C7955D98A7} | c0a8-0057-12c3bb0743c-b51e3813-38c98- | MF-HQ-14483 | DDG - Danish Demining Group | AF/0309/01694/MF6781 | 52400 | 69.4336 | 34.9251 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-01 | 2014-08-15 | 1393 | MCPA | {DF496A63-16CF-4A7B-8485-60C7955D98A7} |  | High with Victim | High with Victims | Substantial | 146 | CHA | 2 |  |  | 2010-02-23 | No | Planned
Central | Parwan | Kohi Safi | Ahmadza'i | {DF496A63-16CF-4A7B-8485-60C7955D98A7} | c0a8-00f6-1353852b0bc-407eccf6-239-d9 | MF-16617 | DDG - Danish Demining Group | AF/0309/01694/MF6782 | 57000 | 69.4407 | 34.9149 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-18 | 2014-10-25 | 1393 | MCPA | {DF496A63-16CF-4A7B-8485-60C7955D98A7} |  | High with Victim | High with Victims | Substantial | 253 | CHA | 2 |  |  | 2010-02-22 16:30 | No | Planned
Central | Parwan | Kohi Safi | Alikhwaja | {2BBAFB7D-D4E8-41C4-905C-04580A30F33A} | c0a8-0009-13c22a5a87d-bd6aab19-1c1-50 | Hz-ID-17580 | DDG - Danish Demining Group | AF/0309/01685/BF0001 | 81 | 69.3802 | 34.8349 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes |  |  | 1393 | MCPA | {2BBAFB7D-D4E8-41C4-905C-04580A30F33A} |  | Medium | Agriculture Blocked | Substantial | 0 | CHA | 3 |  |  | 2012-11-13 16:30 | No | Planned
Central | Parwan | Kohi Safi | Baba Ghumbakay | {6CE47E9C-C6E8-4950-8A19-15A5FDC7D691} | c0a8-0057-12c3ba38933-1514b78a-3113e- | BF-CA-811 | DDG - Danish Demining Group | AF/0309/01724/BF1725 | 235000 | 69.5126 | 34.7869 | Open | UXO Only | UXO Only | BF |  | MBT Project-055 | Parwan Demining Project-08 |  |  |  |  | 1396 |  | {6CE47E9C-C6E8-4950-8A19-15A5FDC7D691} | Based on HALO Trust confirmation, the hazard is removed from their plan | Low | Agriculture Blocked | Substantial | 237 | CHA | 5 |  |  | 2006-08-04 | No | Open
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0009-13c229edea9-bf9ba8f3-15d-a7 | Hz-ID-17578 | DDG - Danish Demining Group | AF/0309/01691/MF0006 | 228753 | 69.4002 | 34.8912 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/B | Parwan Demining Project-02/B | VTF | Yes | 2013-05-22 | 2013-11-14 | 1392 | OMAR | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} |  |  |  | Substantial | 182 | CHA | 2 |  |  | 2012-11-17 16:30 | No | Complete
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0009-13c2310ccb4-1c3eb1dd-a23-5b | Hz-ID-17599 | DDG - Danish Demining Group | AF/0309/01691/MF0007 | 137055 | 69.3932 | 34.8988 | Worked on | AP Only | AP Only | MineField | 1392/1393 | MBT Project-002/C | Parwan Demining Project-02/C | DOS | Yes | 2014-01-01 | 2014-08-22 | 1392 | HT | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} |  | High with Victim | High with Victims | Substantial | 171 | CHA | 2 |  |  | 2012-11-18 16:30 | No | Planned
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0009-140382c1d99-eda029d2-38-24e | Hz-ID-18060 | HT - HALO TRUST | H/8511 | 66000 | 69.4038 | 34.8979 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-09-16 | 2013-12-23 | 1392-1393 | HT | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} |  |  |  | Substantial | 128 | CHA | 1 |  |  | 2013-07-02 16:30 | No | Planned
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0009-142e569ff88-e64b3b41-6a1f-e | Hz-ID-18290 | DDG - Danish Demining Group | AF/0309/01691/MF0010 | 151 | 69.4187 | 34.8848 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2014-01-01 | 2014-01-23 | 1392-1393 | HT | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} |  |  |  | Substantial | 86 | CHA | 1 |  |  | 2013-12-02 16:30 | No | Planned
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0009-143cdf0bd5a-d3b7f51-2f9d-b1 | Hz-ID-18411 | DDG - Danish Demining Group | AF/0309/01691/MF0011 | 30507 | 69.4211 | 34.8813 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-221/A | Parwan Demining Project-06/A | GAGP | Yes |  |  | 1392-1393 | HT | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} |  |  |  | Substantial | 86 | CHA | 1 |  |  | 2013-12-17 16:30 | No | Complete
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0009-14655d38e49-f5e970db-140-52 | Hz-ID-18738 | DDG - Danish Demining Group | AF/0309/01691/MF0013 | 53766 | 69.4163 | 34.9038 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} |  | High with Victim | High with Victims | Substantial | 93 | CHA | 1 |  |  | 2014-04-21 16:30 | No | Planned
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0009-14655f53f78-5eeb70d6-207-9a | Hz-ID-18739 | DDG - Danish Demining Group | AF/0309/01691/MF0012 | 87224 | 69.406 | 34.9015 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-185 | Kabul new city Demining Project | VTF-Japan | Yes |  |  | 1393 | DDG | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} |  | High with Victim | High with Victims | Substantial | 108 | CHA | 1 |  |  | 2014-04-21 16:30 | No | Planned
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0057-12c3b8f4ce4-da8cade5-24255- | MF-HT-911 | DDG - Danish Demining Group | AF/0309/01691/MF3742 | 76400 | 69.4006 | 34.9115 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-002/F | Parwan Demining Project-02/F | GAGP | Yes | 2014-01-01 | 2014-04-22 | 1392-1393 | HT | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} |  |  |  | Substantial | 44 | CHA | 1 |  |  | 2007-08-01 | No | Complete
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0057-12c3b8f60f0-bed8e2a6-24329- | MF-HT-880 | DDG - Danish Demining Group | AF/0309/01692/MF3709 | 51200 | 69.406 | 34.9113 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/F | Parwan Demining Project-02/F | GAGP | Yes | 2014-01-01 | 2014-04-10 | 1392-1393 | HT | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} |  |  |  | Substantial | 44 | CHA | 1 |  |  | 2007-07-01 | No | Complete
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0057-12c3b975355-6e859bd9-2962b- | MF-HQ-13002 | DDG - Danish Demining Group | AF/0309/01691/MF1873 | 48100 | 69.3942 | 34.8989 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-03-30 | 2013-07-10 | 1392-1393 | HT | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | HALO Trust stated in their e-mail recived on 31 May 2012, H/1873 this task located in insecure area and you can remove it from our list. |  |  | Substantial | 243 | CHA | 2 |  |  | 2007-07-22 | No | Planned
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0057-12c3b975509-e6607b73-29642- | MF-HT-853 | DDG - Danish Demining Group | H/3390 | 64000 | 69.3955 | 34.8994 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-04-01 | 2013-07-15 | 1392-1393 | HT | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | Removed from HT 1390 plan |  |  | Substantial | 116 | CHA | 1 |  |  | 2007-12-23 15:40 | No | Planned
Central | Parwan | Kohi Safi | Gadaykhel | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | c0a8-0057-12c3b9758f0-3c8a96a6-29667- | MF-HT-855 | DDG - Danish Demining Group | H/3391 | 76600 | 69.3981 | 34.8989 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-03-30 | 2013-08-10 | 1392-1393 | HT | {78404C72-ECA9-42AA-9D6C-FFB9B889FEB5} | Removed from HT 1390 plan |  |  | Substantial | 189 | CHA | 1 |  |  | 2007-12-23 15:46 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b77b2c4-d0eafcc4-1380e- | MF-HQ-14172 | DDG - Danish Demining Group | AF/0309/01692/MF4244 | 193800 | 69.4486 | 34.8632 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-18 | 2014-12-31 | 1393 | MCPA | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  | High with Victim | High with Victims | Substantial | 13 | CHA | 5 |  |  | 2008-04-02 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f4ed7-ff3c85a4-2426b- | MF-HT-873 | DDG - Danish Demining Group | AF/0309/01692/MF3707 | 55800 | 69.3928 | 34.9041 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-06-18 | 2013-08-22 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 53 | CHA | 1 |  |  | 2007-07-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f509b-d4a857ce-2427f- | MF-HT-865 | DDG - Danish Demining Group | H/3394 | 37600 | 69.406 | 34.9015 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-03-30 | 2013-09-23 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | Removed from HT plan |  |  | Substantial | 199 | CHA | 1 |  |  | 2007-07-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f5250-354c0576-24291- | MF-HT-896 | DDG - Danish Demining Group | AF/0309/01692/MF3735 | 40000 | 69.4012 | 34.906 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-11-20 | 2014-04-22 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 73 | CHA | 1 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f53f5-573fa6b6-242a3- | MF-HT-904 | DDG - Danish Demining Group | AF/0309/01692/MF3738 | 45000 | 69.4015 | 34.9069 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2014-03-02 | 2014-04-22 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 117 | CHA | 1 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f55d9-28e4b385-242b5- | MF-HT-899 | DDG - Danish Demining Group | AF/0309/01692/MF3736 | 45350 | 69.4032 | 34.906 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/E | Parwan Demining Project-02/E | CIDA | Yes | 2014-01-03 | 2014-03-23 | 1392 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 73 | CHA | 1 |  |  | 2007-08-01 | No | Complete
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f579d-6d6f636c-242c8- | MF-HT-881 | HT - HALO TRUST | H/3710 | 66000 | 69.4038 | 34.8979 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-10-25 | 2014-03-23 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 73 | CHA | 1 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f5990-3aae9771-242db- | MF-HT-884 | HT - HALO TRUST | H/3731 | 62000 | 69.4038 | 34.8979 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-09-03 | 2014-03-23 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 73 | CHA | 1 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f5b64-be2da205-242f0- | MF-HT-901 | DDG - Danish Demining Group | AF/0309/01692/MF3737 | 50000 | 69.3984 | 34.9065 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/E | Parwan Demining Project-02/E | CIDA | Yes | 2014-01-01 | 2014-02-23 | 1392 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 126 | CHA | 1 |  |  | 2007-08-01 | No | Complete
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f5d48-a84ff0f0-24303- | MF-HT-866 | HT - HALO TRUST | H/3395 | 74000 | 69.4038 | 34.8979 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/C | Parwan Demining Project-02/C | DOS | Yes | 2014-01-01 | 2014-04-10 | 1392 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 199 | CHA | 1 |  |  | 2007-07-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f5f0c-fd86cd06-24317- | MF-HT-876 | DDG - Danish Demining Group | AF/0309/01692/MF3708 | 71300 | 69.4009 | 34.9028 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-09-02 | 2013-12-23 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 126 | CHA | 1 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f62a5-478e27da-2433d- | MF-HT-891 | DDG - Danish Demining Group | AF/0309/01692/MF3733 | 40000 | 69.4032 | 34.9042 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-10-17 | 2014-03-23 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 73 | CHA | 1 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f6469-2b15629e-2434f- | MF-HT-908 | DDG - Danish Demining Group | AF/0309/01692/MF3741 | 53200 | 69.3997 | 34.9102 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2014-01-01 | 2014-04-24 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 44 | CHA | 1 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f663d-ca465bbf-24362- | MF-HT-871 | DDG - Danish Demining Group | AF/0309/01692/MF3706 | 56200 | 69.41 | 34.9058 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-11-17 | 2014-04-22 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 199 | CHA | 1 |  |  | 2007-07-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f67e2-117d5a9-24376-1 | MF-HT-848 | DDG - Danish Demining Group | AF/0309/01692/MF3389 | 40000 | 69.3914 | 34.9028 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-03-30 | 2013-06-23 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | Removed from HT plan |  |  | Substantial | 148 | CHA | 1 |  |  | 2007-12-23 15:30 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f69b6-82252675-24387- | MF-HT-906 | DDG - Danish Demining Group | AF/0309/01692/MF3740 | 50000 | 69.4028 | 34.907 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-11-18 | 2014-03-18 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 117 | CHA | 1 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f6b8a-a69a6ca8-2439a- | MF-HT-804 | DDG - Danish Demining Group | AF/0309/01692/MF1874 | 59500 | 69.4065 | 34.9096 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/B | Parwan Demining Project-02/B | VTF | Yes |  |  | 1392 | OMAR | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 117 | CHA | 1 |  |  | 2007-12-23 11:52 | No | Complete
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f6d9d-8a8f1a71-243ad- | MF-HT-893 | DDG - Danish Demining Group | AF/0309/01692/MF3734 | 87000 | 69.3928 | 34.9061 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/D | Parwan Demining Project-002/D | B-Germany | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 126 | CHA | 1 |  |  | 2007-08-01 | No | Complete
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f6f51-5ce8aa47-243c2- | MF-HT-888 | DDG - Danish Demining Group | AF/0309/01692/MF3732 | 40000 | 69.4054 | 34.9042 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/D | Parwan Demining Project-002/D | B-Germany | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 73 | CHA | 1 |  |  | 2007-08-01 | No | Complete
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f7193-778e4fe0-243d4- | MF-HT-803 | DDG - Danish Demining Group | AF/0309/01692/MF1872 | 91800 | 69.3949 | 34.9014 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-002/C | Parwan Demining Project-02/C | DOS | Yes | 2013-12-01 | 2014-07-05 | 1392 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 53 | CHA | 1 |  |  | 2007-12-23 11:44 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f7386-b027d48d-243eb- | MF-HT-905 | DDG - Danish Demining Group | AF/0309/01692/MF3739 | 40050 | 69.3989 | 34.9083 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/E | Parwan Demining Project-02/E | CIDA | Yes | 2014-01-01 | 2014-03-23 | 1392 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 44 | CHA | 1 |  |  | 2007-08-01 | No | Complete
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b8f752b-297ea503-243ff- | MF-HT-937 | HT - HALO TRUST | H/3779 | 73000 | 69.4038 | 34.8979 | Worked on | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-07-11 | 2013-10-22 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  | High with Victim | High with Victims | Substantial | 73 | CHA | 1 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b90f40b-eaa8fd13-25387- | MF-HQ-13980 | DDG - Danish Demining Group | AF/0309/01692/MF4273 | 54700 | 69.4486 | 34.925 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-18 | 2014-09-30 | 1393 | MCPA | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | , | High with Victim | High with Victims | Substantial | 221 | CHA | 5 |  |  | 2010-01-13 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b90f69a-f5850e55-2539c- | MF-HQ-13982 | DDG - Danish Demining Group | AF/0309/01692/MF4274 | 51100 | 69.4484 | 34.9266 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-09-16 | 2014-12-27 | 1393 | MCPA | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | , | High with Victim | High with Victims | Substantial | 189 | CHA | 4 |  |  | 2010-01-13 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b9750e5-fe9994c7-29617- | MF-HT-858 | DDG - Danish Demining Group | H/3392 | 57600 | 69.4 | 34.8995 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-03-30 | 2013-06-23 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | Removed from HT 1390 plan |  |  | Substantial | 73 | CHA | 1 |  |  | 2007-12-23 15:52 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b9756ed-1e6726be-29655- | MF-HT-868 | HT - HALO TRUST | H/3396 | 55000 | 69.394 | 34.8988 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-07-16 | 2013-09-23 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} |  |  |  | Substantial | 126 | CHA | 1 |  |  | 2007-07-01 | No | Planned
Central | Parwan | Kohi Safi | Ghafurkhel | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | c0a8-0057-12c3b975ac4-bb7a9c61-2967a- | MF-HT-859 | DDG - Danish Demining Group | H/3393 | 27500 | 69.404 | 34.9013 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/A | Parwan Demining Project-02/A | Bilateral | Yes | 2013-03-30 | 2013-06-22 | 1392-1393 | HT | {D752C251-CE5F-4519-B76E-0D3B68BC0AD6} | Removed from HT 1390 plan |  |  | Substantial | 73 | CHA | 1 |  |  | 2007-12-23 15:59 | No | Planned
Central | Parwan | Kohi Safi | Hasanza'i | {0EC37E48-A839-40A6-9C60-856A84CBD4A8} | c0a8-0009-13c22af8b7b-42a6fae0-26b-3f | Hz-ID-17587 | DDG - Danish Demining Group | AF/0309/01683/BF0003 | 41 | 69.3347 | 34.8305 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes |  |  | 1393 | MCPA | {0EC37E48-A839-40A6-9C60-856A84CBD4A8} |  | High | Critical Infrastracture | Substantial | 235 | CHA | 3 |  |  | 2012-11-10 16:30 | No | Planned
Central | Parwan | Kohi Safi | Hasanza'i | {0EC37E48-A839-40A6-9C60-856A84CBD4A8} | c0a8-0009-13c22b2381c-d962f2e2-2a1-6a | Hz-ID-17592 | DDG - Danish Demining Group | AF/0309/01683/BF0004 | 108 | 69.3374 | 34.8322 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes |  |  | 1393 | MCPA | {0EC37E48-A839-40A6-9C60-856A84CBD4A8} |  | High | Critical Infrastracture | Substantial | 235 | CHA | 3 |  |  | 2012-12-12 16:30 | No | Planned
Central | Parwan | Kohi Safi | Hasanza'i | {0EC37E48-A839-40A6-9C60-856A84CBD4A8} | c0a8-0009-13c22c37201-726b94d4-479-83 | Hz-ID-17597 | DDG - Danish Demining Group | AF/0309/01683/BF0005 | 69 | 69.3736 | 34.8152 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-01 | 2014-06-30 | 1393 | MCPA | {0EC37E48-A839-40A6-9C60-856A84CBD4A8} |  | High | Critical Infrastracture | Substantial | 189 | CHA | 3 |  |  | 2012-11-11 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-133a5edacd8-1ccbf8c-56a-b7f | MF-16305 | DDG - Danish Demining Group | AF/0309/01682/MF8040 | 30000 | 69.356 | 34.875 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-08 | 2014-09-12 | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 8 | CHA | 1 |  |  | 2011-06-05 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-13407a63fe9-154c009b-190-7e | MF-16311 | DDG - Danish Demining Group | AF/0309/01682/MF8041 | 32000 | 69.363 | 34.895 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-18 | 2014-09-16 | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} | Kabul New City | High with Victim | High with Victims | Substantial | 14 | CHA | 1 |  |  | 2011-06-06 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-13407aca3ed-6b61f322-1a5-c8 | MF-16312 | DDG - Danish Demining Group | AF/0309/01682/MF8043 | 28100 | 69.356 | 34.875 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-18 | 2014-09-08 | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 6 | CHA | 1 |  |  | 2011-06-08 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-13407b0f332-53b36265-1cd-e3 | MF-16314 | DDG - Danish Demining Group | AF/0309/01682/MF8045 | 30000 | 69.356 | 34.875 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-09-13 | 2014-11-10 | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 26 | CHA | 1 |  |  | 2011-06-10 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-13407b354f6-da18bac0-1e1-cf | MF-16315 | DDG - Danish Demining Group | AF/0309/01682/MF8046 | 29000 | 69.356 | 34.875 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-09-17 | 2014-11-12 | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 20 | CHA | 1 |  |  | 2011-06-11 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-13407d9dad7-b9a8dd85-1f6-24 | MF-16316 | DDG - Danish Demining Group | AF/0309/01682/MF8047 | 31500 | 69.363 | 34.895 | Open | AP Only | AP Only | MineField | Blank | MBT Project-001/A | Parwan Demining Project-01/A |  | No |  |  | 1394 | Blank | {51EF32B8-3090-4689-9F39-21786280D5BE} | Kabul New City | High with Victim | High with Victims | Substantial | 20 | CHA | 1 |  |  | 2011-06-12 16:30 | No | Open
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-13465249410-8037e6d4-430-92 | MF-16300 | DDG - Danish Demining Group | AF/0309/01682/MF8036 | 38000 | 69.3564 | 34.875 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-09-09 | 2014-11-27 | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 12 | CHA | 1 |  |  | 2011-06-01 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-1346563c2a8-260313e7-531-6e | MF-16313 | DDG - Danish Demining Group | AF/0309/01682/MF8044 | 30000 | 69.3564 | 34.875 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-18 | 2014-08-18 | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 6 | CHA | 1 |  |  | 2011-06-09 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-134656551b7-4e98eb0a-546-17 | MF-16405 | DDG - Danish Demining Group | AF/0309/01682/MF8048 | 27500 | 69.3564 | 34.875 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-08-19 | 2014-10-17 | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 20 | CHA | 1 |  |  | 2011-06-13 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-134790737eb-31d9e545-90d-70 | MF-16409 | DDG - Danish Demining Group | AF/0309/01682/MF8049 | 29000 | 69.3564 | 34.875 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-01 | 2014-06-30 | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 20 | CHA | 1 |  |  | 2011-06-14 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-134790c59bf-a5d88239-924-27 | MF-16411 | DDG - Danish Demining Group | AF/0309/01682/MF8050 | 27000 | 69.3564 | 34.875 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes |  |  | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 20 | CHA | 1 |  |  | 2011-06-15 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-1347914ac00-37620ae0-93b-5b | MF-16412 | DDG - Danish Demining Group | AF/0309/01682/MF8051 | 28750 | 69.3564 | 34.875 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes |  |  | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 15 | CHA | 1 |  |  | 2011-06-16 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-13479226c64-a3a5920a-95d-89 | MF-16414 | DDG - Danish Demining Group | AF/0309/01682/MF8052 | 28800 | 69.3564 | 34.875 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-18 | 2014-09-10 | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 15 | CHA | 1 |  |  | 2011-06-17 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-13479285b2c-3681f0c-972-1fe | MF-16415 | DDG - Danish Demining Group | AF/0309/01682/MF8053 | 26000 | 69.3564 | 34.875 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-09-11 | 2014-12-27 | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 15 | CHA | 1 |  |  | 2011-06-18 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-134792cc72b-3b9ad06a-989-75 | MF-16416 | DDG - Danish Demining Group | AF/0309/01682/MF8054 | 29000 | 69.3564 | 34.875 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes |  |  | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 15 | CHA | 1 |  |  | 2011-06-19 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-1347943614e-334590b7-a30-84 | MF-16418 | DDG - Danish Demining Group | AF/0309/01682/MF8055 | 23000 | 69.3564 | 34.875 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes |  |  | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 15 | CHA | 1 |  |  | 2011-06-20 16:30 | No | Planned
Central | Parwan | Kohi Safi | Karezgay | {51EF32B8-3090-4689-9F39-21786280D5BE} | c0a8-008e-13479c3c4ce-4d4ecda8-af4-54 | MF-16310 | DDG - Danish Demining Group | AF/0309/01682/MF8042 | 29100 | 69.3564 | 34.875 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes |  |  | 1393 | MCPA | {51EF32B8-3090-4689-9F39-21786280D5BE} |  | High with Victim | High with Victims | Substantial | 14 | CHA | 1 |  |  | 2011-06-07 16:30 | No | Planned
Central | Parwan | Kohi Safi | Khawra Khawre | {C3D553B0-972E-4280-BF72-03E42E06D933} | c0a8-0057-12c3b951d65-228d989d-27f23- | MF-HT-923 | DDG - Danish Demining Group | AF/0309/01702/MF1890 | 66600 | 69.5043 | 34.7231 | Open | AP Only | AP Only | MineField |  | MBT Project-055 | Parwan Demining Project-08 |  |  |  |  | 1396 |  | {C3D553B0-972E-4280-BF72-03E42E06D933} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2006-08-01 | No | Open
Central | Parwan | Kohi Safi | Lala Baba | {A981E27F-C73B-45B6-AE7A-999108747488} | c0a8-0057-12c3b6a22a8-974725ad-94dc-b | BF-HQ-12119 | DDG - Danish Demining Group | AF/0309/01669/BF1727 | 10000 | 69.3863 | 34.7994 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-07-25 | 2014-09-24 | 1393 | MCPA | {A981E27F-C73B-45B6-AE7A-999108747488} | Based on HALO Trust confirmation, the hazard is removed from their plan | Medium | Agriculture Blocked | Substantial | 200 | CHA | 3 |  |  | 2009-09-10 | No | Planned
Central | Parwan | Kohi Safi | Lewani | {E86806D9-9156-4E2A-B457-CAA98C3392C9} | c0a8-0009-13c22ab762c-69211fa5-205-9b | Hz-ID-17585 | DDG - Danish Demining Group | AF/0309/01672/BF0002 | 69 | 69.3728 | 34.8147 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-09-23 | 2014-09-23 | 1393 | MCPA | {E86806D9-9156-4E2A-B457-CAA98C3392C9} |  | High | Critical Infrastracture | Substantial | 189 | CHA | 3 |  |  | 2012-11-12 16:30 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-004c-130209561b1-8ff83de1-8-b9d5 | MF-HQ-13981 | DDG - Danish Demining Group | AF/0309/01690/MF4263 | 42530 | 69.4196 | 34.9209 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  | Low | Agriculture Blocked | Substantial | 89 | CHA | 5 |  |  | 2008-05-15 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3b8fd746-a1857385-24836- | MF-HT-925 | DDG - Danish Demining Group | AF/0309/01690/MF3748 | 43500 | 69.4218 | 34.922 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  | Low | Agriculture Blocked | Substantial | 68 | CHA | 5 |  |  | 2007-12-24 13:58 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3b8fd9f4-2f3e5c75-24848- | MF-HT-917 | DDG - Danish Demining Group | AF/0309/01690/MF3744 | 51100 | 69.4232 | 34.9209 | Closed | AT Only | AT Only | MineField | 1392/1393 | MBT Project-221/A | Parwan Demining Project-06/A | GAGP | Yes |  |  | 1392-1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  |  |  | Substantial | 68 | CHA | 5 |  |  | 2007-08-01 | No | Complete
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3b8fdc26-6c032af8-24863- | MF-HT-927 | DDG - Danish Demining Group | AF/0309/01690/MF3749 | 53700 | 69.4239 | 34.9234 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  | Low | Agriculture Blocked | Substantial | 214 | CHA | 5 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3b8fde67-cbdcb80c-24879- | MF-HT-934 | DDG - Danish Demining Group | AF/0309/01690/MF3774 | 58100 | 69.4295 | 34.9271 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  | Low | Agriculture Blocked | Substantial | 146 | CHA | 4 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3b8fe03b-5923be7f-24890- | MF-HT-930 | DDG - Danish Demining Group | AF/0309/01690/MF3772 | 48400 | 69.4252 | 34.9253 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  | Low | Agriculture Blocked | Substantial | 146 | CHA | 5 |  |  | 2007-12-24 14:17 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3b8fe2bb-a7724ff5-248a3- | MF-HT-922 | DDG - Danish Demining Group | AF/0309/01690/MF3747 | 58700 | 69.4263 | 34.9205 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  | Low | Agriculture Blocked | Substantial | 68 | CHA | 5 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3b8fe5f6-89d2ddb0-248bd- | MF-HT-815 | DDG - Danish Demining Group | AF/0309/01690/MF1893 | 48525 | 69.4193 | 34.9167 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/B | Parwan Demining Project-02/B | VTF | Yes | 2013-12-02 | 2013-12-31 | 1392 | OMAR | {22F661EB-F509-479B-AFB2-D833F587CD93} |  |  |  | Substantial | 72 | CHA | 5 |  |  | 2007-12-23 13:07 | No | Complete
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3b8fe911-ed6c4358-248e2- | MF-HT-916 | DDG - Danish Demining Group | AF/0309/01690/MF3743 | 55150 | 69.422 | 34.9174 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-03-30 | 2014-05-23 | 1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  |  |  | Substantial | 36 | CHA | 4 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3b8feb62-29ed1200-248ff- | MF-HT-918 | DDG - Danish Demining Group | AF/0309/01690/MF3745 | 43875 | 69.424 | 34.9184 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-04-01 | 2014-06-23 | 1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  |  |  | Substantial | 68 | CHA | 5 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3b8fedc2-370f7d06-24917- | MF-HT-933 | DDG - Danish Demining Group | AF/0309/01690/MF3773 | 70250 | 69.428 | 34.9248 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  | Low | Agriculture Blocked | Substantial | 178 | CHA | 5 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3b8ff1a9-763a27d1-2492f- | MF-HT-920 | DDG - Danish Demining Group | AF/0309/01690/MF3746 | 50400 | 69.4201 | 34.9196 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-06-01 | 2014-09-23 | 1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  | Low | Agriculture Blocked | Substantial | 68 | CHA | 5 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3baefbc6-a368e72a-37eb6- | MF-HQ-13964 | DDG - Danish Demining Group | AF/0309/01690/MF4262 | 39050 | 69.419 | 34.9197 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-002/B | Parwan Demining Project-02/B | VTF | Yes |  |  | 1392 | OMAR | {22F661EB-F509-479B-AFB2-D833F587CD93} |  |  |  | Substantial | 89 | CHA | 5 |  |  | 2008-05-15 | No | Complete
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3baf0019-141f9a90-37ee0- | MF-HT-912 | DDG - Danish Demining Group | AF/0309/01690/MF1891 | 71345 | 69.4168 | 34.9196 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-185 | Kabul new city Demining Project | VTF-Japan | Yes |  |  | 1393 | DDG | {22F661EB-F509-479B-AFB2-D833F587CD93} |  | Low | Agriculture Blocked | Substantial | 89 | CHA | 5 |  |  | 2006-07-01 | No | Planned
Central | Parwan | Kohi Safi | Ni'mankhel | {22F661EB-F509-479B-AFB2-D833F587CD93} | c0a8-0057-12c3baf023b-9b4ffb01-37ef3- | MF-HQ-13973 | DDG - Danish Demining Group | AF/0309/01690/MF4264 | 58000 | 69.4208 | 34.9208 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {22F661EB-F509-479B-AFB2-D833F587CD93} |  |  |  | Substantial | 36 | CHA | 5 |  |  | 2008-05-15 | No | Planned
Central | Parwan | Kohi Safi | Senjalay | {B8485257-35B7-4823-BC76-C9C227D02D78} | c0a8-0009-13c0e8e8650-22d844d6-c0f-25 | Hz-ID-17532 | DDG - Danish Demining Group | AF/0309/01677/BF0009 | 203592 | 69.4251 | 34.8086 | Worked on | UXO Only | UXO Only | BF | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-18 | 2014-07-24 | 1393 | MCPA | {B8485257-35B7-4823-BC76-C9C227D02D78} |  | High with Victim | High with Victims | Substantial | 499 | CHA | 2 |  |  | 2012-12-04 16:30 | No | Planned
Central | Parwan | Kohi Safi | Shawo Kalay(Pas Asanzi) | {BC2F71AC-5FF6-4B14-B4B0-2BCCE44916C5} | c0a8-0057-12c3b7b366b-7ab51a05-160b8- | MF-HQ-14476 | DDG - Danish Demining Group | AF/0309/01684/MF6801 | 45000 | 69.3209 | 34.8343 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {BC2F71AC-5FF6-4B14-B4B0-2BCCE44916C5} |  | Low | Agriculture Blocked | Substantial | 39 | CHA | 5 |  |  | 2010-02-24 | No | Planned
Central | Parwan | Kohi Safi | Shawo Kalay(Pas Asanzi) | {BC2F71AC-5FF6-4B14-B4B0-2BCCE44916C5} | c0a8-0057-12c3b9d3627-788a6b03-2d354- | MF-HQ-14491 | DDG - Danish Demining Group | AF/0309/01684/MF6802 | 45000 | 69.3209 | 34.8329 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {BC2F71AC-5FF6-4B14-B4B0-2BCCE44916C5} |  | Low | Agriculture Blocked | Substantial | 31 | CHA | 5 |  |  | 2010-02-25 | No | Planned
Central | Parwan | Kohi Safi | Shawo Kalay(Pas Asanzi) | {BC2F71AC-5FF6-4B14-B4B0-2BCCE44916C5} | c0a8-0057-12c3b9d380b-7bbb1097-2d366- | MF-HT-919 | DDG - Danish Demining Group | AF/0309/01684/MF1897 | 45000 | 69.3209 | 34.8357 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {BC2F71AC-5FF6-4B14-B4B0-2BCCE44916C5} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2010-02-28 | No | Planned
Central | Parwan | Kohi Safi | Shawo Kalay(Pas Asanzi) | {BC2F71AC-5FF6-4B14-B4B0-2BCCE44916C5} | c0a8-0057-12c3b9d39cf-1c85e535-2d37b- | MF-HQ-14477 | DDG - Danish Demining Group | AF/0309/01684/MF6803 | 45000 | 69.3209 | 34.8316 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {BC2F71AC-5FF6-4B14-B4B0-2BCCE44916C5} |  | Low | Agriculture Blocked | Substantial | 31 | CHA | 5 |  |  | 2010-02-26 | No | Planned
Central | Parwan | Kohi Safi | Tereray | {F599B4AB-9697-40CD-A225-D1B95D2C22AE} | c0a8-0057-12c3b73257e-bb3307fd-10233- | BF-HQ-12102 | DDG - Danish Demining Group | AF/0309/01665/BF1729 | 8500 | 69.4334 | 34.8303 | Closed | UXO Only | UXO Only | BF | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes | 2014-06-01 | 2014-06-30 | 1393 | MCPA | {F599B4AB-9697-40CD-A225-D1B95D2C22AE} | Based on HALO Trust confirmation, the hazard is removed from their plan |  |  | Substantial | 47 | CHA | 2 |  |  | 2006-08-09 | No | Planned
Central | Parwan | Kohi Safi | Tereray | {F599B4AB-9697-40CD-A225-D1B95D2C22AE} | c0a8-0057-12c3b7853a2-86615451-13f76- | BF-HQ-12094 | DDG - Danish Demining Group | AF/0309/01665/BF1728 | 21250 | 69.424 | 34.8328 | Closed | UXO Only | UXO Only | BF | 1393 | MBT Project-002 | Parwan Demining Project-02 | VTF-Australia | Yes |  |  | 1393 | MCPA | {F599B4AB-9697-40CD-A225-D1B95D2C22AE} | Based on HALO Trust confirmation, the hazard is removed from their plan |  |  | Substantial | 0 | CHA | 2 |  |  | 2006-08-10 | No | Planned
Central | Parwan | Salang | Aghele Khan | {CF70F558-1274-419C-95D9-50AEEA371D17} | c0a8-0057-12c3babd77c-53b9e0f3-36022- | MF-HT-737 | HT - HALO TRUST | H/1902 | 17000 | 69.2229 | 35.2158 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {CF70F558-1274-419C-95D9-50AEEA371D17} |  | Low | Agriculture Blocked | Minimal | 388 | CHA | 4 |  |  | 2007-12-18 07:20 | No | Pledged
Central | Parwan | Salang | Ahengaran | {13A0E294-64A2-4B6A-A822-1CCAA70CBF93} | c0a8-0057-12c3b7283d5-d9bb9383-fa8f-4 | MF-HQ-13554 | HT - HALO TRUST | H/6293 | 20000 | 69.1421 | 35.2423 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {13A0E294-64A2-4B6A-A822-1CCAA70CBF93} |  | Low | Agriculture Blocked | Minimal | 91 | CHA | 4 |  |  | 2009-10-20 | No | Pledged
Central | Parwan | Salang | Ahengaran | {13A0E294-64A2-4B6A-A822-1CCAA70CBF93} | c0a8-0057-12c3b8a9dec-dab1abb-20ea9-7 | MF-HT-747 | HT - HALO TRUST | H/1915 | 42000 | 69.1625 | 35.2313 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {13A0E294-64A2-4B6A-A822-1CCAA70CBF93} |  | Low | Agriculture Blocked | Minimal | 73 | CHA | 4 |  |  | 2007-12-22 09:11 | No | Pledged
Central | Parwan | Salang | Ahengaran | {13A0E294-64A2-4B6A-A822-1CCAA70CBF93} | c0a8-0057-12c3b9cce43-460bf192-2cfa1- | MF-CA-2092 | HT - HALO TRUST | H/1911 | 32600 | 69.1535 | 35.2343 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {13A0E294-64A2-4B6A-A822-1CCAA70CBF93} |  | Low | Agriculture Blocked | Minimal | 228 | CHA | 5 |  |  | 2008-07-17 | No | Pledged
Central | Parwan | Salang | Ahengaran | {13A0E294-64A2-4B6A-A822-1CCAA70CBF93} | c0a8-0057-12c3ba8d948-844b8012-344b4- | MF-HT-729 | HT - HALO TRUST | H/1564 | 30200 | 69.1499 | 35.2431 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {13A0E294-64A2-4B6A-A822-1CCAA70CBF93} |  | Low | Agriculture Blocked | Minimal | 137 | CHA | 4 |  |  | 2010-10-16 | No | Pledged
Central | Parwan | Salang | Ahengaran | {13A0E294-64A2-4B6A-A822-1CCAA70CBF93} | c0a8-0057-12c3ba8dbf6-a51a018d-344cd- | MF-HQ-14840 | HT - HALO TRUST | H/6815 | 22000 | 69.151 | 35.2424 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {13A0E294-64A2-4B6A-A822-1CCAA70CBF93} |  | Low | Agriculture Blocked | Minimal | 137 | CHA | 4 |  |  | 2010-10-14 | No | Pledged
Central | Parwan | Salang | Aulang | {ED2C233C-7ACA-4661-A822-2233532E2B57} | c0a8-0057-12c3b87c13b-ba682cdd-1eefd- | MF-HT-752 | HT - HALO TRUST | H/1922 | 65000 | 69.1272 | 35.2606 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {ED2C233C-7ACA-4661-A822-2233532E2B57} |  | Medium | Critical Infrastracture | Minimal | 296 | CHA | 3 |  |  | 2007-12-22 09:59 | No | Pledged
Central | Parwan | Salang | Aulang | {ED2C233C-7ACA-4661-A822-2233532E2B57} | c0a8-0057-12c3b897f19-17c626e9-20256- | MF-HT-761 | HT - HALO TRUST | H/1931 | 96000 | 69.1014 | 35.294 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {ED2C233C-7ACA-4661-A822-2233532E2B57} |  | Low | Critical Infrastracture | Minimal | 88 | CHA | 4 |  |  | 2007-12-22 10:53 | No | Planned
Central | Parwan | Salang | Babashangul | {96FFF578-95F8-42B7-956F-FE0DE5A264AD} | c0a8-0057-12c3bb29943-c463585c-3a0e2- | MF-CA-2086 | HT - HALO TRUST | H/1899 | 32000 | 69.2208 | 35.2128 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {96FFF578-95F8-42B7-956F-FE0DE5A264AD} |  | Low | Agriculture Blocked | Minimal | 388 | CHA | 4 |  |  | 2008-08-14 | No | Pledged
Central | Parwan | Salang | Baghe Lala | {D4B05AC7-C71C-49C1-B519-46F08089B46E} | c0a8-0057-12c3b7b7cfb-8396c0f8-163d4- | MF-HQ-14165 | HT - HALO TRUST | H/6288 | 41000 | 69.2484 | 35.1702 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {D4B05AC7-C71C-49C1-B519-46F08089B46E} |  | Low | Agriculture Blocked | Minimal | 7 | CHA | 5 |  |  | 2009-10-13 | No | Planned
Central | Parwan | Salang | Baghe Maydan | {FA8AC7D7-83E2-4B8F-BDB5-65B677E58722} | c0a8-00f6-134e9f5c1da-b978a1af-abf-cf | MF-15497 | HT - HALO TRUST | H/7532 | 20000 | 69.2135 | 35.2219 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {FA8AC7D7-83E2-4B8F-BDB5-65B677E58722} |  | Low | Agriculture Blocked | Minimal | 9 | CHA | 4 |  |  | 2010-11-07 16:30 | No | Planned
Central | Parwan | Salang | Chapraq | {D13A2FC2-29A1-492A-A436-939554013069} | c0a8-008e-1328fa8e70d-7c8ee03-213f-99 | MF-16197 | MCPA - Mine Clearance Planning Agency | AF/0303/00020/MF0018 | 41385 | 69.2181 | 35.1924 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {D13A2FC2-29A1-492A-A436-939554013069} |  | Low | Critical Infrastracture | Minimal | 388 | CHA | 4 |  |  | 2011-08-11 16:30 | No | Pledged
Central | Parwan | Salang | Chapraq | {D13A2FC2-29A1-492A-A436-939554013069} | c0a8-008e-1328fb52a88-c42eb1db-23de-a | MF-16127 | MCPA - Mine Clearance Planning Agency | AF/0303/00020/MF0016 | 61914 | 69.2236 | 35.192 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {D13A2FC2-29A1-492A-A436-939554013069} |  | Low | Agriculture Blocked | Minimal | 184 | CHA | 4 |  |  | 2011-07-16 16:30 | No | Pledged
Central | Parwan | Salang | Chapraq | {D13A2FC2-29A1-492A-A436-939554013069} | c0a8-00f6-134d0317ce1-813a0f8c-cd0-18 | MF-16099 | HT - HALO TRUST | H/7813 | 31744 | 69.2163 | 35.1932 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {D13A2FC2-29A1-492A-A436-939554013069} |  | Medium | Critical Infrastracture | Minimal | 15 | CHA | 5 |  |  | 2011-04-03 16:30 | No | Pledged
Central | Parwan | Salang | Chapraq | {D13A2FC2-29A1-492A-A436-939554013069} | c0a8-00f6-134e4f57de4-f9be4b5f-5fc-ec | MF-16098 | HT - HALO TRUST | H/7814 | 51300 | 69.2176 | 35.1927 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {D13A2FC2-29A1-492A-A436-939554013069} |  | Medium | Critical Infrastracture | Minimal | 15 | CHA | 5 |  |  | 2011-04-04 16:30 | No | Planned
Central | Parwan | Salang | Chapraq | {D13A2FC2-29A1-492A-A436-939554013069} | c0a8-00f6-135c2de8648-35d42120-581-6e | MF-16653 | MCPA - Mine Clearance Planning Agency | AF/0303/00020/MF0022 | 17969 | 69.2187 | 35.1928 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {D13A2FC2-29A1-492A-A436-939554013069} |  | Low | Agriculture Blocked | Minimal | 174 | CHA | 5 |  |  | 2011-12-01 16:30 | No | Pledged
Central | Parwan | Salang | Deh Naw | {B4B83D5F-3D60-41D7-A286-13E746A76F9E} | c0a8-0057-12c3b7768ca-503407c2-134b1- | MF-HQ-14578 | HT - HALO TRUST | H/7004 | 23000 | 69.219 | 35.1854 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {B4B83D5F-3D60-41D7-A286-13E746A76F9E} |  | Low | Critical Infrastracture | Minimal | 250 | CHA | 4 |  |  | 2010-08-13 | No | Pledged
Central | Parwan | Salang | Dehe Horati | {32E1BA02-3735-45B4-8408-7C5D5785954C} | c0a8-0057-12c3ba105f7-be21b6f5-2f8fa- | MF-CA-2052 | HT - HALO TRUST | H/4348 | 16000 | 69.2007 | 35.1732 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {32E1BA02-3735-45B4-8408-7C5D5785954C} |  | Low | Agriculture Blocked | Minimal | 24 | CHA | 4 |  |  | 2008-07-20 | No | Planned
Central | Parwan | Salang | Dehe Horati | {32E1BA02-3735-45B4-8408-7C5D5785954C} | c0a8-0057-12c3ba107cb-6097b9ba-2f910- | MF-CA-2053 | HT - HALO TRUST | H/4349 | 6300 | 69.2042 | 35.1715 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {32E1BA02-3735-45B4-8408-7C5D5785954C} |  | Low | Agriculture Blocked | Minimal | 24 | CHA | 5 |  |  | 2008-07-21 | No | Planned
Central | Parwan | Salang | Fatula | {B2575548-EB57-4715-86E2-B299B29FE0BF} | c0a8-0009-13c188473d0-6e002e22-b45-74 | Hz-ID-17560 | HT - HALO TRUST | H/8396 | 17062 | 69.1044 | 35.2786 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {B2575548-EB57-4715-86E2-B299B29FE0BF} |  | Low | Agriculture Blocked | Minimal | 122 | CHA | 5 |  |  | 2012-12-06 16:30 | No | Planned
Central | Parwan | Salang | Fatula | {B2575548-EB57-4715-86E2-B299B29FE0BF} | c0a8-0057-12c3baf5d83-b72b4e82-38236- | MF-CA-2049 | HT - HALO TRUST | H/1923 | 44100 | 69.1004 | 35.2806 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-08-01 | 2014-10-20 | 1393 | HT | {B2575548-EB57-4715-86E2-B299B29FE0BF} | Based on HALO Trust statement (on the previous database cleanups we requested to remove from HALO workplan) the hazard removed from their plan | Low | Agriculture Blocked | Minimal | 158 | CHA | 5 |  |  | 2008-07-07 | No | Planned
Central | Parwan | Salang | Gamandi | {79782348-F48B-4B54-9FE3-DA51E6AE58DF} | c0a8-0009-13b4554bd27-c24b3117-51f3-f | Hz-ID-17392 | HT - HALO TRUST | H/8375 | 38000 | 69.1334 | 35.2464 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {79782348-F48B-4B54-9FE3-DA51E6AE58DF} |  | Medium | Critical Infrastracture | Minimal | 375 | CHA | 3 |  |  | 2012-10-13 16:30 | No | Planned
Central | Parwan | Salang | Gamandi | {79782348-F48B-4B54-9FE3-DA51E6AE58DF} | c0a8-0009-13b45ce085c-9d72ee5f-5798-c | Hz-ID-17391 | HT - HALO TRUST | H/8374 | 41500 | 69.1317 | 35.2461 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {79782348-F48B-4B54-9FE3-DA51E6AE58DF} |  | Medium | Critical Infrastracture | Minimal | 107 | CHA | 3 |  |  | 2012-10-14 16:30 | No | Planned
Central | Parwan | Salang | Ghaw | {F32B8F3A-A805-4007-9C1D-A3356F264BB1} | c0a8-00f6-1349d4c1663-9957ed7b-348-b9 | MF-16448 | HT - HALO TRUST | H/8172 | 3900 | 69.1649 | 35.2468 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {F32B8F3A-A805-4007-9C1D-A3356F264BB1} |  | Medium | Agriculture Blocked | Minimal | 384 | CHA | 3 |  |  | 2011-10-01 16:30 | No | Pledged
Central | Parwan | Salang | Hejan | {A6F99193-1589-4487-9EC9-943BA5A77514} | c0a8-0057-12c3b73ad04-67536043-10888- | MF-HQ-14701 | HT - HALO TRUST | H/7007 | 6000 | 69.1724 | 35.2334 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {A6F99193-1589-4487-9EC9-943BA5A77514} |  | Medium | Critical Infrastracture | Minimal | 181 | CHA | 3 |  |  | 2010-09-07 | No | Pledged
Central | Parwan | Salang | Hejan | {A6F99193-1589-4487-9EC9-943BA5A77514} | c0a8-0057-12c3b88868b-2f184018-1f783- | MF-HT-1316 | HT - HALO TRUST | H/3751 | 42375 | 69.1829 | 35.2482 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {A6F99193-1589-4487-9EC9-943BA5A77514} |  | Low | Agriculture Blocked | Minimal | 117 | CHA | 4 |  |  | 2007-08-01 | No | Planned
Central | Parwan | Salang | Hejan | {A6F99193-1589-4487-9EC9-943BA5A77514} | c0a8-0057-12c3ba9216e-2d4450ca-34764- | MF-HT-670 | HT - HALO TRUST | H/1944 | 5400 | 69.1779 | 35.2336 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {A6F99193-1589-4487-9EC9-943BA5A77514} |  | Medium | Critical Infrastracture | Minimal | 696 | CHA | 3 |  |  | 2004-07-01 | No | Planned
Central | Parwan | Salang | Hejan | {A6F99193-1589-4487-9EC9-943BA5A77514} | c0a8-0057-12c3bb36eb8-2ab7a12f-3a8ff- | MF-HT-667 | HT - HALO TRUST | H/1940 | 33250 | 69.1834 | 35.2446 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {A6F99193-1589-4487-9EC9-943BA5A77514} |  | Low | Agriculture Blocked | Minimal | 192 | CHA | 4 |  |  | 2004-01-07 | No | Pledged
Central | Parwan | Salang | Hejan | {A6F99193-1589-4487-9EC9-943BA5A77514} | c0a8-008e-1328f7c32a6-af290672-1318-8 | MF-16034 | MCPA - Mine Clearance Planning Agency | AF/0303/01876/MF0015 | 25944 | 69.1642 | 35.2326 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {A6F99193-1589-4487-9EC9-943BA5A77514} |  | Low | Agriculture Blocked | Minimal | 97 | CHA | 5 |  |  | 2011-05-24 16:30 | No | Planned
Central | Parwan | Salang | Hejane Belandi | {DA3ADB75-2329-4A36-8ACE-8C7BC12EB00C} | c0a8-0057-12c3ba9e768-49b6e5a7-34eae- | MF-CA-2020 | HT - HALO TRUST | H/1941 | 35200 | 69.1911 | 35.2443 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {DA3ADB75-2329-4A36-8ACE-8C7BC12EB00C} |  | Low | Agriculture Blocked | Minimal | 557 | CHA | 4 |  |  | 2008-06-20 | No | Pledged
Central | Parwan | Salang | Hejane Belandi | {DA3ADB75-2329-4A36-8ACE-8C7BC12EB00C} | c0a8-0057-12c3ba9e9aa-446b11c2-34ec3- | MF-CA-2019 | HT - HALO TRUST | H/1945 | 35250 | 69.1908 | 35.244 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {DA3ADB75-2329-4A36-8ACE-8C7BC12EB00C} |  | Low | Agriculture Blocked | Minimal | 557 | CHA | 4 |  |  | 2008-06-21 | No | Pledged
Central | Parwan | Salang | Hejane Belandi | {DA3ADB75-2329-4A36-8ACE-8C7BC12EB00C} | c0a8-008e-132900e84d5-cc7d2e1f-32c7-b | MF-16100 | HT - HALO TRUST | H/7815 | 30000 | 69.2014 | 35.2367 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {DA3ADB75-2329-4A36-8ACE-8C7BC12EB00C} |  | Low | Agriculture Blocked | Minimal | 171 | CHA | 4 |  |  | 2011-04-07 16:30 | No | Planned
Central | Parwan | Salang | Jafarake Bala | {3A33101C-8D8F-4CA8-93C2-486D452A8564} | c0a8-008e-13122197569-c8cfb476-417-14 | MF-HQ-14574 | HT - HALO TRUST | H/6779 | 32000 | 69.2073 | 35.2452 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {3A33101C-8D8F-4CA8-93C2-486D452A8564} |  | Low | Critical Infrastracture | Minimal | 38 | CHA | 4 |  |  | 2010-05-18 | No | Planned
Central | Parwan | Salang | Kaftarkhana | {CC05E6A5-0FEF-41DB-BEB0-310F9974B825} | c0a8-0057-12c3b875c72-d6035a07-1ea5a- | MF-CA-2051 | HT - HALO TRUST | H/1908 | 26500 | 69.1438 | 35.2502 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {CC05E6A5-0FEF-41DB-BEB0-310F9974B825} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 4 |  |  | 2008-07-10 | No | Planned
Central | Parwan | Salang | Kalari | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} | c0a8-0057-12c3b7ee085-187083b9-189f6- | MF-CA-2035 | HT - HALO TRUST | H/4341 | 12950 | 69.109 | 35.2826 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} |  | Medium | Critical Infrastracture | Minimal | 490 | CHA | 3 |  |  | 2008-06-16 | No | Pledged
Central | Parwan | Salang | Kalari | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} | c0a8-0057-12c3b83a905-3ac49012-1c080- | MF-CA-2023 | HT - HALO TRUST | H/4342 | 16179 | 69.1158 | 35.2878 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} |  | Low | Agriculture Blocked | Minimal | 581 | CHA | 4 |  |  | 2008-06-17 | No | Pledged
Central | Parwan | Salang | Kalari | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} | c0a8-008e-1329003c794-a7b3e806-316d-5 | MF-16092 | HT - HALO TRUST | H/7852 | 32500 | 69.1277 | 35.2739 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-08-01 | 2014-09-23 | 1393 | HT | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} |  | Low | Agriculture Blocked | Minimal | 118 | CHA | 4 |  |  | 2011-04-19 16:30 | No | Planned
Central | Parwan | Salang | Kalari | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} | c0a8-008e-132908d1945-563d3b8f-f7-4f8 | MF-16091 | HT - HALO TRUST | H/7853 | 27200 | 69.1293 | 35.2748 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} |  | Low | Agriculture Blocked | Minimal | 118 | CHA | 4 |  |  | 2011-04-20 16:30 | No | Planned
Central | Parwan | Salang | Kalari | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} | c0a8-00f6-134e4d58a8a-8ecae865-56c-9c | MF-16090 | HT - HALO TRUST | H/7854 | 26500 | 69.1255 | 35.2731 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} |  | Low | Agriculture Blocked | Minimal | 118 | CHA | 4 |  |  | 2011-04-21 16:30 | No | Planned
Central | Parwan | Salang | Kalari | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} | c0a8-00f6-134e4d826c5-1edabda1-590-92 | MF-16089 | HT - HALO TRUST | H/7855 | 25500 | 69.1255 | 35.2731 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} |  | Low | Agriculture Blocked | Minimal | 9 | CHA | 4 |  |  | 2011-04-22 16:30 | No | Planned
Central | Parwan | Salang | Kalari | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} | c0a8-00f6-13533b43f0c-33c2d9d7-268-2e | MF-16088 | HT - HALO TRUST | H/7856 | 16389 | 69.1255 | 35.2731 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {F8BC2E89-EF4F-49AC-8FBC-8BFE193660B5} |  | Low | Agriculture Blocked | Minimal | 9 | CHA | 4 |  |  | 2011-04-20 16:30 | No | Planned
Central | Parwan | Salang | Khanjakak (Babamardan) | {5EC9795A-8437-4282-8AF0-23143CCF64F0} | c0a8-0057-12c3b8a545f-2ba895a3-20b92- | MF-CA-2089 | HT - HALO TRUST | H/1932 | 33800 | 69.2266 | 35.1666 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {5EC9795A-8437-4282-8AF0-23143CCF64F0} |  | Low | Agriculture Blocked | Minimal | 37 | CHA | 4 |  |  | 2008-07-18 | No | Planned
Central | Parwan | Salang | Khanjakak (Babamardan) | {5EC9795A-8437-4282-8AF0-23143CCF64F0} | c0a8-00f6-135c2de1a4e-fb5bfc1-56e-a1b | MF-16654 | MCPA - Mine Clearance Planning Agency | AF/0303/00281/MF0021 | 34662 | 69.2198 | 35.1682 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {5EC9795A-8437-4282-8AF0-23143CCF64F0} |  | Low | Agriculture Blocked | Minimal | 531 | CHA | 5 |  |  | 2011-11-27 16:30 | No | Pledged
Central | Parwan | Salang | Khotangolo | {58968984-B768-41D2-B95F-60BE3F5EC142} | c0a8-0057-12c3ba2fe44-766c3750-30c1f- | MF-HQ-11413 | HT - HALO TRUST | H/4365 | 18000 | 69.1294 | 35.2705 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {58968984-B768-41D2-B95F-60BE3F5EC142} |  | Low | Agriculture Blocked | Minimal | 109 | CHA | 4 |  |  | 2008-08-24 | No | Pledged
Central | Parwan | Salang | Lalma-i-Sultan | {26AB2D8E-850E-42A8-84BB-7C26E23484A8} | c0a8-0057-12c3b8f40a4-63c49b1e-241d2- | MF-HQ-11411 | HT - HALO TRUST | H/4362 | 19920 | 69.2405 | 35.18 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {26AB2D8E-850E-42A8-84BB-7C26E23484A8} |  | Low | Agriculture Blocked | Minimal | 40 | CHA | 5 |  |  | 2008-07-22 | No | Planned
Central | Parwan | Salang | Lalma-i-Sultan | {26AB2D8E-850E-42A8-84BB-7C26E23484A8} | c0a8-0057-12c3b8f4269-5e5d5289-241e7- | MF-HQ-13983 | HT - HALO TRUST | H/4361 | 36100 | 69.2389 | 35.1785 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {26AB2D8E-850E-42A8-84BB-7C26E23484A8} |  | Low | Agriculture Blocked | Minimal | 20 | CHA | 5 |  |  | 2008-07-21 | No | Planned
Central | Parwan | Salang | Lalma-i-Sultan | {26AB2D8E-850E-42A8-84BB-7C26E23484A8} | c0a8-0057-12c3b8f443c-d21a9f9a-241fd- | MF-HQ-13978 | HT - HALO TRUST | H/4363 | 32300 | 69.2365 | 35.1862 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {26AB2D8E-850E-42A8-84BB-7C26E23484A8} |  | Low | Agriculture Blocked | Minimal | 10 | CHA | 5 |  |  | 2010-01-13 | No | Planned
Central | Parwan | Salang | Liwan | {73C5DFBE-825E-4016-966C-3EC5B491C769} | c0a8-0057-12c3baac23a-d5fbca7c-3561c- | MF-CA-2087 | HT - HALO TRUST | H/1910 | 51421 | 69.1449 | 35.2346 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {73C5DFBE-825E-4016-966C-3EC5B491C769} |  | Low | Agriculture Blocked | Minimal | 1055 | CHA | 4 |  |  | 2010-09-19 | No | Pledged
Central | Parwan | Salang | Molamarjoy | {951E50D5-9213-455F-B64A-8FAE0B6A60BD} | c0a8-0057-12c3b6fc7dd-c6ea3967-d965-8 | MF-HQ-14469 | HT - HALO TRUST | H/6800 | 30000 | 69.1158 | 35.2898 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {951E50D5-9213-455F-B64A-8FAE0B6A60BD} |  | Low | Agriculture Blocked | Minimal | 581 | CHA | 4 |  |  | 2010-03-16 | No | Pledged
Central | Parwan | Salang | Myanagl | {B2E950D4-37D5-486F-BB40-00A63A172B4E} | c0a8-0057-12c3b770181-a5435b57-13012- | MF-HQ-13589 | HT - HALO TRUST | H/6294 | 34500 | 69.0786 | 35.3069 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {B2E950D4-37D5-486F-BB40-00A63A172B4E} |  | Low | Agriculture Blocked | Minimal | 4 | CHA | 5 |  |  | 2009-10-21 | No | Planned
Central | Parwan | Salang | Nawache Pa'in | {97ABCD10-63D2-4A80-8EFA-AC772414F331} | c0a8-0057-12c3b87e426-c54e0e5-1f077-4 | MF-CA-2067 | HT - HALO TRUST | H/5364 | 37100 | 69.205 | 35.2205 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {97ABCD10-63D2-4A80-8EFA-AC772414F331} |  | Low | Agriculture Blocked | Minimal | 50 | CHA | 4 |  |  | 2008-08-21 | No | Planned
Central | Parwan | Salang | Paja | {41149368-471A-4D36-A7A9-FB9356742EAE} | c0a8-0009-1463c978a83-b2a6e163-1036-8 | Hz-ID-18736 | HT - HALO TRUST | H/8540 | 32500 | 69.2094 | 35.1884 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {41149368-471A-4D36-A7A9-FB9356742EAE} |  | Low | Agriculture Blocked | Minimal | 28 | CHA | 5 |  |  | 2014-04-26 16:30 | No | Open
Central | Parwan | Salang | Paja | {41149368-471A-4D36-A7A9-FB9356742EAE} | c0a8-0057-12c3b721fe6-24f80ae-f5e5-3f | MF-HQ-13420 | HT - HALO TRUST | H/6290 | 13000 | 69.2252 | 35.2011 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {41149368-471A-4D36-A7A9-FB9356742EAE} |  | Low | Agriculture Blocked | Minimal | 14 | CHA | 4 |  |  | 2010-08-20 | No | Planned
Central | Parwan | Salang | Paja | {41149368-471A-4D36-A7A9-FB9356742EAE} | c0a8-0057-12c3b80ce28-41d1eab3-19ffd- | MF-HT-778 | HT - HALO TRUST | H/3760 | 8200 | 69.2192 | 35.2034 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {41149368-471A-4D36-A7A9-FB9356742EAE} |  | Medium | Critical Infrastracture | Minimal | 48 | CHA | 3 |  |  | 2007-12-22 14:02 | No | Planned
Central | Parwan | Salang | Paja | {41149368-471A-4D36-A7A9-FB9356742EAE} | c0a8-0057-12c3ba20ce7-ad6cb32a-30328- | MF-CA-2062 | HT - HALO TRUST | H/4385 | 21000 | 69.2196 | 35.1998 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {41149368-471A-4D36-A7A9-FB9356742EAE} |  | Low | Agriculture Blocked | Minimal | 15 | CHA | 5 |  |  | 2010-08-14 | No | Planned
Central | Parwan | Salang | Paja | {41149368-471A-4D36-A7A9-FB9356742EAE} | c0a8-0057-12c3bb12e26-21242b73-39383- | MF-CA-2055 | HT - HALO TRUST | H/5362 | 41500 | 69.2196 | 35.1998 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {41149368-471A-4D36-A7A9-FB9356742EAE} |  | Low | Agriculture Blocked | Minimal | 15 | CHA | 5 |  |  | 2008-08-17 | No | Planned
Central | Parwan | Salang | Paja | {41149368-471A-4D36-A7A9-FB9356742EAE} | c0a8-008e-13290981dfb-7f26879e-249-fe | MF-16138 | MCPA - Mine Clearance Planning Agency | AF/0303/01868/MF0017 | 16160 | 69.2197 | 35.1998 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {41149368-471A-4D36-A7A9-FB9356742EAE} |  | Medium | Critical Infrastracture | Minimal | 48 | CHA | 3 |  |  | 2011-07-19 16:30 | No | Planned
Central | Parwan | Salang | Paja | {41149368-471A-4D36-A7A9-FB9356742EAE} | c0a8-008e-133a0b9f1ff-5b5eacb8-2fd-61 | MF-16350 | MCPA - Mine Clearance Planning Agency | AF/0303/01868/MF0019 | 39698 | 69.2214 | 35.1968 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {41149368-471A-4D36-A7A9-FB9356742EAE} |  | Low | Agriculture Blocked | Minimal | 184 | CHA | 4 |  |  | 2011-09-18 16:30 | No | Pledged
Central | Parwan | Salang | Paja | {41149368-471A-4D36-A7A9-FB9356742EAE} | c0a8-008e-13427071763-e4670ddb-5b4-f3 | MF-16404 | HT - HALO TRUST | H/8170 | 28500 | 69.2133 | 35.2039 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {41149368-471A-4D36-A7A9-FB9356742EAE} |  | Low | Agriculture Blocked | Minimal | 110 | CHA | 4 |  |  | 2011-11-13 16:30 | No | Pledged
Central | Parwan | Salang | Paja | {41149368-471A-4D36-A7A9-FB9356742EAE} | c0a8-008e-1342752bd8e-8be575e8-60d-45 | MF-16403 | HT - HALO TRUST | H/8186 | 10900 | 69.2135 | 35.2037 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {41149368-471A-4D36-A7A9-FB9356742EAE} |  | Low | Agriculture Blocked | Minimal | 110 | CHA | 4 |  |  | 2011-11-15 16:30 | No | Pledged
Central | Parwan | Salang | Paja | {41149368-471A-4D36-A7A9-FB9356742EAE} | c0a8-00f6-135526348b5-7330857c-1b-b81 | MF-16373 | MCPA - Mine Clearance Planning Agency | AF/0303/01868/MF0020 | 25488 | 69.2169 | 35.1964 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {41149368-471A-4D36-A7A9-FB9356742EAE} |  | Medium | Critical Infrastracture | Minimal | 189 | CHA | 3 |  |  | 2011-10-13 16:30 | No | Pledged
Central | Parwan | Salang | Qalai - Aulang | {8A644800-DE7D-48A2-975F-82B24F636F44} | c0a8-0009-13c0e312cff-c37ed80e-952-53 | Hz-ID-17522 | HT - HALO TRUST | H/8391 | 50000 | 69.1149 | 35.2694 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-05-01 | 2014-08-23 | 1393 | HT | {8A644800-DE7D-48A2-975F-82B24F636F44} |  | Low | Agriculture Blocked | Minimal | 21 | CHA | 5 |  |  | 2012-11-11 16:30 | No | Planned
Central | Parwan | Salang | Qalai - Aulang | {8A644800-DE7D-48A2-975F-82B24F636F44} | c0a8-0009-13e1c67b98f-2ba16d30-6923-a | Hz-ID-17822 | HT - HALO TRUST | H/8388 | 35650 | 69.1149 | 35.2694 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-08-13 | 2014-10-13 | 1393 | HT | {8A644800-DE7D-48A2-975F-82B24F636F44} |  | Low | Agriculture Blocked | Minimal | 30 | CHA | 5 |  |  | 2012-11-08 16:30 | No | Planned
Central | Parwan | Salang | Qalandarshah | {AFDA39EA-904A-456A-9876-1A46E8C5772B} | c0a8-0009-13b40170945-f609d42e-49f7-9 | Hz-ID-17396 | HT - HALO TRUST | H/8379 | 36050 | 69.1179 | 35.2785 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-05-01 | 2014-08-12 | 1393 | HT | {AFDA39EA-904A-456A-9876-1A46E8C5772B} |  | Medium | Critical Infrastracture | Minimal | 100 | CHA | 3 |  |  | 2012-10-16 16:30 | No | Planned
Central | Parwan | Salang | Qalandarshah | {AFDA39EA-904A-456A-9876-1A46E8C5772B} | c0a8-0009-13b4561029b-695494d-52e3-f2 | Hz-ID-17393 | HT - HALO TRUST | H/8376 | 45172 | 69.1243 | 35.273 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-05-01 | 2014-07-23 | 1393 | HT | {AFDA39EA-904A-456A-9876-1A46E8C5772B} |  |  |  | Minimal | 109 | CHA | 4 |  |  | 2012-10-05 16:30 | No | Planned
Central | Parwan | Salang | Qalandarshah | {AFDA39EA-904A-456A-9876-1A46E8C5772B} | c0a8-0009-13b45a746b2-f228bbb-55aa-20 | Hz-ID-17397 | HT - HALO TRUST | H/8380 | 54025 | 69.1256 | 35.2699 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-05-01 | 2014-07-23 | 1393 | HT | {AFDA39EA-904A-456A-9876-1A46E8C5772B} |  |  |  | Minimal | 109 | CHA | 3 |  |  | 2012-10-17 16:30 | No | Planned
Central | Parwan | Salang | Qalandarshah | {AFDA39EA-904A-456A-9876-1A46E8C5772B} | c0a8-0009-13b45a8e541-8cb2fcc1-55e7-a | Hz-ID-17395 | HT - HALO TRUST | H/8378 | 36025 | 69.1256 | 35.2699 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-08-01 | 2014-10-05 | 1393 | HT | {AFDA39EA-904A-456A-9876-1A46E8C5772B} |  | Low | Agriculture Blocked | Minimal | 109 | CHA | 4 |  |  | 2012-10-07 16:30 | No | Planned
Central | Parwan | Salang | Qalandarshah | {AFDA39EA-904A-456A-9876-1A46E8C5772B} | c0a8-0009-13b4a72222d-35fa3b2c-5a22-3 | Hz-ID-17394 | HT - HALO TRUST | H/8377 | 48050 | 69.1243 | 35.273 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-05-01 | 2014-07-23 | 1393 | HT | {AFDA39EA-904A-456A-9876-1A46E8C5772B} |  |  |  | Minimal | 109 | CHA | 4 |  |  | 2012-10-06 16:30 | No | Planned
Central | Parwan | Salang | Qalandarshah | {AFDA39EA-904A-456A-9876-1A46E8C5772B} | c0a8-0057-12c3ba14e7b-e7d45d5a-2fbcb- | MF-HT-768 | HT - HALO TRUST | H/3358 | 51100 | 69.1243 | 35.273 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {AFDA39EA-904A-456A-9876-1A46E8C5772B} |  | Low | Agriculture Blocked | Minimal | 218 | CHA | 4 |  |  | 2007-12-22 12:15 | No | Pledged
Central | Parwan | Salang | Qalandarshah | {AFDA39EA-904A-456A-9876-1A46E8C5772B} | c0a8-008e-13290729cb9-936003dc-18-6e1 | MF-16095 | HT - HALO TRUST | H/7817 | 25200 | 69.1318 | 35.2647 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-06-01 | 2014-07-16 | 1393 | HT | {AFDA39EA-904A-456A-9876-1A46E8C5772B} | Based on HALO Trust statement (on the previous database cleanups we requested to remove from HALO workplan) the hazard removed from their plan |  |  | Minimal | 210 | CHA | 4 |  |  | 2011-04-10 16:30 | No | Planned
Central | Parwan | Salang | Qalatak | {6A9BC0E8-8981-4489-AC0B-88D0E243B10D} | c0a8-0009-13fb7569f11-d72d987d-3dda-9 | Hz-ID-17998 | HT - HALO TRUST | H/8368 | 170 | 69.2076 | 35.231 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {6A9BC0E8-8981-4489-AC0B-88D0E243B10D} |  | High with Victim | High with Victims | Minimal | 1096 | CHA | 2 |  |  | 2012-09-16 16:30 | No | Planned
Central | Parwan | Salang | Qalatak | {6A9BC0E8-8981-4489-AC0B-88D0E243B10D} | c0a8-0057-12c3b93eeb4-271993a4-27295- | MF-HT-1326 | HT - HALO TRUST | H/3757 | 43092 | 69.2073 | 35.2286 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {6A9BC0E8-8981-4489-AC0B-88D0E243B10D} |  | High with Victim | High with Victims | Minimal | 890 | CHA | 2 |  |  | 2007-08-01 | No | Pledged
Central | Parwan | Salang | Qale Baqi | {8E423FE3-785A-4DF3-B109-F1A5BA2B5F78} | c0a8-0057-12c3b81f13f-5b75b1dd-1acf7- | MF-CA-2021 | HT - HALO TRUST | H/1907 | 5020 | 69.1242 | 35.2483 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-05-01 | 2014-06-23 | 1393 | HT | {8E423FE3-785A-4DF3-B109-F1A5BA2B5F78} |  | Low | Agriculture Blocked | Minimal | 116 | CHA | 2 |  |  | 2008-06-22 | No | Planned
Central | Parwan | Salang | Qale Baqi | {8E423FE3-785A-4DF3-B109-F1A5BA2B5F78} | c0a8-0057-12c3b81f304-96905094-1ad0c- | MF-CA-2022 | HT - HALO TRUST | H/4351 | 9800 | 69.1216 | 35.2491 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-05-01 | 2014-06-23 | 1393 | HT | {8E423FE3-785A-4DF3-B109-F1A5BA2B5F78} |  | Low | Agriculture Blocked | Minimal | 208 | CHA | 2 |  |  | 2008-06-22 | No | Planned
Central | Parwan | Salang | Sameda | {B53D8222-B14E-4A85-9109-95CDB0EC378D} | c0a8-0057-12c3b6d1873-58979173-b8ba-9 | MF-HQ-14580 | HT - HALO TRUST | H/7005 | 10000 | 69.1451 | 35.2464 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {B53D8222-B14E-4A85-9109-95CDB0EC378D} |  | Medium | Critical Infrastracture | Minimal | 92 | CHA | 3 |  |  | 2010-05-20 | No | Planned
Central | Parwan | Salang | Taghma | {8CD103EC-56DD-4E36-A096-04E78E0090E4} | c0a8-0057-12c3b7cf938-dbb68b88-1752f- | MF-HQ-14248 | HT - HALO TRUST | H/1961 | 24000 | 69.2055 | 35.1778 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {8CD103EC-56DD-4E36-A096-04E78E0090E4} |  | Low | Agriculture Blocked | Minimal | 141 | CHA | 4 |  |  | 2009-09-16 | No | Planned
Central | Parwan | Salang | Taj | {FDCD23A2-DB85-4D51-9057-F855609DFCC2} | c0a8-0057-12c3b95235e-d98791fb-27f5f- | MF-HT-754 | HT - HALO TRUST | H/1924 | 40000 | 69.114 | 35.2895 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-003 | Parwan Demining Project-03 | DOS | No |  |  | 1393 | WRA | {FDCD23A2-DB85-4D51-9057-F855609DFCC2} |  | Low | Agriculture Blocked | Minimal | 490 | CHA | 4 |  |  | 2010-02-25 | No | Pledged
Central | Parwan | Salang | Wolang | {EADE4D21-8542-4C30-8DE7-ECFDBE41B44B} | c0a8-0009-13bb6ce0030-f167a383-2a04-f | Hz-ID-17477 | HT - HALO TRUST | H/8389 | 37050 | 69.1149 | 35.2694 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {EADE4D21-8542-4C30-8DE7-ECFDBE41B44B} |  | High with Victim | High with Victims | Minimal | 10 | CHA | 2 |  |  | 2012-11-10 16:30 | No | Planned
Central | Parwan | Salang | Wolang | {EADE4D21-8542-4C30-8DE7-ECFDBE41B44B} | c0a8-0009-13bb6ce6fa4-cb47a965-2a48-e | Hz-ID-17478 | HT - HALO TRUST | H/8390 | 19250 | 69.1149 | 35.2694 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes | 2014-07-17 | 2014-09-03 | 1393 | HT | {EADE4D21-8542-4C30-8DE7-ECFDBE41B44B} |  | High with Victim | High with Victims | Minimal | 20 | CHA | 2 |  |  | 2012-11-08 16:30 | No | Planned
Central | Parwan | Shekh Ali | Bede Shekh'ali | {1ED3E50F-84B9-4E57-B7BF-AB9064DBB044} | c0a8-0057-12c3ba3c816-a88a279f-3137b- | MF-CA-1147 | HT - HALO TRUST | H/4224 | 1150 | 68.6128 | 34.9825 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {1ED3E50F-84B9-4E57-B7BF-AB9064DBB044} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-04-10 | No | Open
Central | Parwan | Shekh Ali | Behude Bala | {58DCA952-F119-474E-B902-A319EAD07644} | c0a8-0057-12c3b7f65c9-4dedd351-1902c- | MF-CA-1142 | HT - HALO TRUST | H/1992 | 4000 | 68.5956 | 34.9923 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {58DCA952-F119-474E-B902-A319EAD07644} |  | Low | Agriculture Blocked | Substantial | 19 | CHA | 5 |  |  | 2008-06-05 | No | Open
Central | Parwan | Shekh Ali | Behude Bala | {58DCA952-F119-474E-B902-A319EAD07644} | c0a8-0057-12c3b80dad5-88c0c497-1a093- | MF-CA-1144 | HT - HALO TRUST | H/4291 | 400 | 68.6109 | 35.0006 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-07-25 | 2013-07-25 | 1392 | OMAR | {58DCA952-F119-474E-B902-A319EAD07644} |  |  |  | Substantial | 8 | CHA | 3 |  |  | 2008-06-01 | No | Complete
Central | Parwan | Shekh Ali | Behude Bala | {58DCA952-F119-474E-B902-A319EAD07644} | c0a8-0057-12c3b80dc8a-31e0dbd6-1a0a5- | MF-CA-1145 | HT - HALO TRUST | H/1991 | 1700 | 68.6103 | 34.9999 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-07-25 | 2013-07-25 | 1392 | OMAR | {58DCA952-F119-474E-B902-A319EAD07644} |  |  |  | Substantial | 90 | CHA | 3 |  |  | 2008-06-02 | No | Complete
Central | Parwan | Shekh Ali | Behude Bala | {58DCA952-F119-474E-B902-A319EAD07644} | c0a8-0057-12c3b99889a-bb52a57d-2ada0- | MF-CA-1143 | HT - HALO TRUST | H/4292 | 2500 | 68.6006 | 34.9853 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {58DCA952-F119-474E-B902-A319EAD07644} |  | Low | Agriculture Blocked | Substantial | 209 | CHA | 5 |  |  | 2008-06-06 | No | Open
Central | Parwan | Shekh Ali | Behude Bala | {58DCA952-F119-474E-B902-A319EAD07644} | c0a8-0057-12c3ba3c558-28027257-31368- | MF-CA-1146 | HT - HALO TRUST | H/1990 | 2500 | 68.6133 | 34.9844 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {58DCA952-F119-474E-B902-A319EAD07644} |  | Low | Agriculture Blocked | Substantial | 30 | CHA | 5 |  |  | 2008-08-04 | No | Open
Central | Parwan | Shekh Ali | Beni Sayook | {21C2D549-BF86-4E1A-8983-0E34B6052500} | c0a8-0057-12c3b7b6e6b-c668debf-16331- | MF-HQ-11763 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | H/5982 | 19890 | 68.4943 | 34.9412 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-07-01 | 2013-07-15 | 1392 | OMAR | {21C2D549-BF86-4E1A-8983-0E34B6052500} |  |  |  | Substantial | 306 | CHA | 4 |  |  | 2009-06-06 | No | Complete
Central | Parwan | Shekh Ali | Bolaq | {1170E601-29D3-4242-8954-EAB8BAB754EC} | c0a8-0057-12c3b7c188c-a8435b21-16ade- | MF-CA-1224 | HT - HALO TRUST | H/4220 | 9400 | 68.4394 | 34.9962 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {1170E601-29D3-4242-8954-EAB8BAB754EC} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2008-04-06 | No | Open
Central | Parwan | Shekh Ali | Bolaq | {1170E601-29D3-4242-8954-EAB8BAB754EC} | c0a8-0057-12c3b7c1a32-58373f68-16af4- | MF-CA-1225 | HT - HALO TRUST | H/4221 | 8980 | 68.4434 | 34.9994 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {1170E601-29D3-4242-8954-EAB8BAB754EC} |  | Low | Agriculture Blocked | Substantial | 12 | CHA | 5 |  |  | 2008-04-07 | No | Open
Central | Parwan | Shekh Ali | Bolaq | {1170E601-29D3-4242-8954-EAB8BAB754EC} | c0a8-0057-12c3b95605c-39ab0a7d-28198- | MF-CA-1254 | HT - HALO TRUST | H/4219 | 10500 | 68.4176 | 35.0014 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {1170E601-29D3-4242-8954-EAB8BAB754EC} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2008-04-05 | No | Open
Central | Parwan | Shekh Ali | Dahane Jarf | {B739DE41-DF0B-4B98-8565-4E311AA04625} | c0a8-0057-12c3bb5ca0b-1383d744-3bf05- | MF-CA-1245 | HT - HALO TRUST | H/1980 | 64000 | 68.4692 | 34.9496 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {B739DE41-DF0B-4B98-8565-4E311AA04625} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-06-11 | No | Open
Central | Parwan | Shekh Ali | Dahane Jarf | {B739DE41-DF0B-4B98-8565-4E311AA04625} | c0a8-0057-12c3bb5cc3c-d585f473-3bf17- | MF-CA-1247 | HT - HALO TRUST | H/4294 | 52750 | 68.4634 | 34.9501 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {B739DE41-DF0B-4B98-8565-4E311AA04625} |  | Low | Agriculture Blocked | Substantial | 14 | CHA | 5 |  |  | 2008-06-08 | No | Open
Central | Parwan | Shekh Ali | Dahane Jarf | {B739DE41-DF0B-4B98-8565-4E311AA04625} | c0a8-0057-12c3bb5ce5e-6602f397-3bf2c- | MF-CA-1243 | HT - HALO TRUST | H/4293 | 51675 | 68.4658 | 34.9493 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {B739DE41-DF0B-4B98-8565-4E311AA04625} |  | Low | Agriculture Blocked | Substantial | 14 | CHA | 5 |  |  | 2008-06-07 | No | Open
Central | Parwan | Shekh Ali | Dahane Jarf | {B739DE41-DF0B-4B98-8565-4E311AA04625} | c0a8-0057-12c3bb5d071-9b4c56b6-3bf41- | MF-CA-1248 | HT - HALO TRUST | H/4295 | 48000 | 68.4599 | 34.9525 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {B739DE41-DF0B-4B98-8565-4E311AA04625} |  | Low | Agriculture Blocked | Substantial | 14 | CHA | 5 |  |  | 2008-06-10 | No | Open
Central | Parwan | Shekh Ali | Dahane Kotak | {803C4AEC-889D-4C57-884C-74111692F88E} | c0a8-0057-12c3b82b7b7-10be8531-1b5c6- | MF-CA-1221 | HT - HALO TRUST | H/1985 | 46000 | 68.3751 | 34.9862 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {803C4AEC-889D-4C57-884C-74111692F88E} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-05-14 | No | Open
Central | Parwan | Shekh Ali | Dahane Kotak | {803C4AEC-889D-4C57-884C-74111692F88E} | c0a8-0057-12c3b82b9ba-a56fe79f-1b5d9- | MF-CA-1220 | HT - HALO TRUST | H/1984 | 75000 | 68.4433 | 34.9838 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {803C4AEC-889D-4C57-884C-74111692F88E} |  | Low | Agriculture Blocked | Substantial | 19 | CHA | 5 |  |  | 2008-05-12 | No | Open
Central | Parwan | Shekh Ali | Dahan-e-Shingeryan | {FCF1C728-E6B6-4968-B9D4-1A0312F4D416} | c0a8-0057-12c3b853ab5-f0bf281c-1d2d2- | MF-CA-1152 | HT - HALO TRUST | H/2001 | 41200 | 68.486 | 34.9651 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-05-08 | 2013-05-25 | 1392 | OMAR | {FCF1C728-E6B6-4968-B9D4-1A0312F4D416} |  |  |  | Substantial | 75 | CHA | 4 |  |  | 2008-04-20 | No | Complete
Central | Parwan | Shekh Ali | Dahan-e-Shingeryan | {FCF1C728-E6B6-4968-B9D4-1A0312F4D416} | c0a8-0057-12c3b853cb8-46605e23-1d2e6- | MF-CA-1233 | HT - HALO TRUST | H/4216 | 43500 | 68.5116 | 34.9618 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-05-08 | 2013-05-30 | 1392 | OMAR | {FCF1C728-E6B6-4968-B9D4-1A0312F4D416} |  |  |  | Substantial | 8 | CHA | 4 |  |  | 2008-02-04 | No | Complete
Central | Parwan | Shekh Ali | Dahan-e-Shingeryan | {FCF1C728-E6B6-4968-B9D4-1A0312F4D416} | c0a8-0057-12c3b85407f-90c225ad-1d313- | MF-CA-1230 | HT - HALO TRUST | H/4218 | 55560 | 68.5139 | 34.9613 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-05-08 | 2013-05-30 | 1392 | OMAR | {FCF1C728-E6B6-4968-B9D4-1A0312F4D416} |  |  |  | Substantial | 31 | CHA | 4 |  |  | 2008-04-04 | No | Complete
Central | Parwan | Shekh Ali | Darwaz | {E0B3485E-4479-4B31-9E4E-456C1F1D61F9} | c0a8-008e-13068ba2f8f-aeaaca6f-3b5-71 | MF-CA-1149 | HT - HALO TRUST | H/1987 | 20550 | 68.5223 | 34.9541 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {E0B3485E-4479-4B31-9E4E-456C1F1D61F9} | Planned year and agency removed | Low | Agriculture Blocked | Substantial | 29 | CHA | 5 |  |  | 2008-04-17 | No | Open
Central | Parwan | Shekh Ali | Gandab | {59F0DBD8-D9D7-4212-8D08-63C9A2925860} | c0a8-0057-12c3bb576fd-4653b06b-3bbef- | MF-CA-1575 | HT - HALO TRUST | H/2022 | 6400 | 68.651 | 34.8423 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {59F0DBD8-D9D7-4212-8D08-63C9A2925860} |  | Low | Agriculture Blocked | Substantial | 142 | CHA | 5 |  |  | 2008-10-12 | No | Open
Central | Parwan | Shekh Ali | Gumbadak | {C932254E-A306-4D36-A2F6-AE51B23AD085} | c0a8-0057-12c3bae42c6-491ab4e6-37788- | MF-CA-1174 | HT - HALO TRUST | H/1996 | 56400 | 68.475 | 34.9701 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {C932254E-A306-4D36-A2F6-AE51B23AD085} |  | Low | Agriculture Blocked | Substantial | 18 | CHA | 5 |  |  | 2008-04-21 | No | Open
Central | Parwan | Shekh Ali | Kenderak | {59EADB2A-B532-4646-AC8B-9160B5DDD265} | c0a8-00f6-1353394fe4f-73141393-154-5d | MF-15909 | HT - HALO TRUST | H/7688 | 25837 | 68.4965 | 34.9539 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-06-01 | 2013-06-10 | 1392 | OMAR | {59EADB2A-B532-4646-AC8B-9160B5DDD265} |  |  |  | Substantial | 62 | CHA | 3 |  |  | 2011-03-14 16:30 | No | Complete
Central | Parwan | Shekh Ali | Kenderake Dektor | {0EBACADC-D18D-4AB9-BF7D-DD46DB9D85BC} | c0a8-008e-13112a722ee-f5b7be81-15a6-f | MF-CA-1253 | HT - HALO TRUST | H/2002 | 32000 | 68.4701 | 34.9703 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {0EBACADC-D18D-4AB9-BF7D-DD46DB9D85BC} |  | Low | Agriculture Blocked | Substantial | 5 | CHA | 5 |  |  | 2008-06-20 16:30 | No | Open
Central | Parwan | Shekh Ali | Kenderake Dektor | {0EBACADC-D18D-4AB9-BF7D-DD46DB9D85BC} | c0a8-008e-132d3a7ced5-ae8a8b1e-b179-5 | MF-15908 | HT - HALO TRUST | H/7687 | 31350 | 68.4701 | 34.9704 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {0EBACADC-D18D-4AB9-BF7D-DD46DB9D85BC} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2011-03-13 16:30 | No | Open
Central | Parwan | Shekh Ali | Khake Gholm'ali | {0AF82497-D6B7-4B2D-B363-01A57D6EA7DD} | c0a8-0057-12c3b7fdd48-e80e60e2-1958d- | MF-CA-1236 | HT - HALO TRUST | H/4246 | 31000 | 68.5566 | 34.9723 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {0AF82497-D6B7-4B2D-B363-01A57D6EA7DD} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-05-01 | No | Open
Central | Parwan | Shekh Ali | Khake Gholm'ali | {0AF82497-D6B7-4B2D-B363-01A57D6EA7DD} | c0a8-0057-12c3b7fdf1c-9966fb9d-195a1- | MF-CA-1234 | HT - HALO TRUST | H/4247 | 54000 | 68.5628 | 34.9705 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {0AF82497-D6B7-4B2D-B363-01A57D6EA7DD} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2008-05-11 | No | Open
Central | Parwan | Shekh Ali | Khake Gholm'ali | {0AF82497-D6B7-4B2D-B363-01A57D6EA7DD} | c0a8-0057-12c3b7fe0a2-ac85f1e4-195b4- | MF-CA-1235 | HT - HALO TRUST | H/1983 | 53000 | 68.5581 | 34.9632 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {0AF82497-D6B7-4B2D-B363-01A57D6EA7DD} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-05-09 | No | Open
Central | Parwan | Shekh Ali | Merka Nirkh | {4093042C-1A01-49F6-8C19-4548FE00C954} | c0a8-0057-12c3b9c0ba3-1359b7c-2c780-a | MF-CA-1190 | HT - HALO TRUST | H/4281 | 40000 | 68.4983 | 34.9133 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {4093042C-1A01-49F6-8C19-4548FE00C954} |  | Low | Agriculture Blocked | Substantial | 11 | CHA | 5 |  |  | 2008-05-22 | No | Open
Central | Parwan | Shekh Ali | Merka Nirkh | {4093042C-1A01-49F6-8C19-4548FE00C954} | c0a8-0057-12c3b9c0d58-bf14952b-2c794- | MF-CA-1189 | HT - HALO TRUST | H/1973 | 95000 | 68.5006 | 34.9166 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {4093042C-1A01-49F6-8C19-4548FE00C954} |  | Low | Agriculture Blocked | Substantial | 23 | CHA | 5 |  |  | 2008-05-20 | No | Open
Central | Parwan | Shekh Ali | Merka Nirkh | {4093042C-1A01-49F6-8C19-4548FE00C954} | c0a8-0057-12c3b9c0f0d-9d14a79-2c7aa-f | MF-CA-1198 | HT - HALO TRUST | H/4283 | 32700 | 68.4958 | 34.9091 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {4093042C-1A01-49F6-8C19-4548FE00C954} |  | Low | Agriculture Blocked | Substantial | 14 | CHA | 5 |  |  | 2008-05-18 | No | Open
Central | Parwan | Shekh Ali | Merka Nirkh | {4093042C-1A01-49F6-8C19-4548FE00C954} | c0a8-0057-12c3b9c110f-a3aa394-2c7be-f | MF-CA-1192 | HT - HALO TRUST | H/4282 | 37000 | 68.4964 | 34.9122 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {4093042C-1A01-49F6-8C19-4548FE00C954} |  | Low | Agriculture Blocked | Substantial | 14 | CHA | 5 |  |  | 2008-05-19 | No | Open
Central | Parwan | Shekh Ali | Merka Nirkh | {4093042C-1A01-49F6-8C19-4548FE00C954} | c0a8-0057-12c3b9c1312-7c2d305f-2c7d3- | MF-CA-1184 | HT - HALO TRUST | H/4279 | 44000 | 68.5008 | 34.9139 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {4093042C-1A01-49F6-8C19-4548FE00C954} |  | Low | Agriculture Blocked | Substantial | 19 | CHA | 5 |  |  | 2008-05-19 | No | Open
Central | Parwan | Shekh Ali | Merka Nirkh | {4093042C-1A01-49F6-8C19-4548FE00C954} | c0a8-0057-12c3b9c14e6-5e91dcb2-2c7e9- | MF-CA-1185 | HT - HALO TRUST | H/4280 | 48125 | 68.4997 | 34.914 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {4093042C-1A01-49F6-8C19-4548FE00C954} |  | Low | Agriculture Blocked | Substantial | 19 | CHA | 5 |  |  | 2008-05-21 | No | Open
Central | Parwan | Shekh Ali | Rabat (Masjed Rahim Baig) | {D663B18F-53E0-4E59-9688-BE5F75E795A1} | c0a8-0057-12c3ba0a8ad-1f6590f4-2f59b- | MF-CA-1252 | HT - HALO TRUST | H/4225 | 50420 | 68.5513 | 34.9579 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-05-08 | 2013-05-30 | 1392 | OMAR | {D663B18F-53E0-4E59-9688-BE5F75E795A1} |  |  |  | Substantial | 368 | CHA | 4 |  |  | 2008-04-11 | No | Complete
Central | Parwan | Shekh Ali | Saidan | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | c0a8-0009-142e56a786e-108bba9f-6a48-b | Hz-ID-18291 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0306/00002/MF0001 | 200661 | 68.5056 | 34.9443 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} |  | Low | Agriculture Blocked | Substantial | 90 | CHA | 5 |  |  | 2013-09-19 16:30 | No | Open
Central | Parwan | Shekh Ali | Saidan | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | c0a8-0009-142e56b1c7a-bc607146-6a6d-f | Hz-ID-18292 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0306/00002/MF0002 | 180000 | 68.5056 | 34.9443 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} |  | Medium | Critical Infrastracture | Substantial | 430 | CHA | 3 |  |  | 2013-09-19 16:30 | No | Open
Central | Parwan | Shekh Ali | Saidan | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | c0a8-0009-1432e9a35b8-cbf11515-388a-6 | Hz-ID-18293 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0306/00002/MF0003 | 145000 | 68.5056 | 34.9443 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} |  | Low | Agriculture Blocked | Substantial | 77 | CHA | 5 |  |  | 2013-09-19 16:30 | No | Open
Central | Parwan | Shekh Ali | Saidan | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | c0a8-0009-1432e9a9d3f-bb1dd4f6-38a2-4 | Hz-ID-18294 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0306/00002/MF0004 | 160696 | 68.5056 | 34.9443 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} |  | Low | Agriculture Blocked | Substantial | 321 | CHA | 5 |  |  | 2013-09-19 16:30 | No | Open
Central | Parwan | Shekh Ali | Saidan | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | c0a8-0057-12c3b69e03d-2d1940ee-91af-c | MF-HT-319 | HT - HALO TRUST | H/3768 | 48800 | 68.5028 | 34.9457 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-06-11 | 2013-07-25 | 1392 | OMAR | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | Based on HALO Trust e-mail recieved on 31 May 2012, the task is removed from HT plan (H/3767, H/3768, H/3769 you can remove all this 3 tasks from our list.) |  |  | Substantial | 335 | CHA | 3 |  |  | 2007-10-31 | No | Complete
Central | Parwan | Shekh Ali | Saidan | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | c0a8-0057-12c3b6ac3c5-9fe8a554-9c45-a | MF-HQ-15337 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | H/7571 | 113643 | 68.5056 | 34.9443 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-07-11 | 2013-09-30 | 1392 | OMAR | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} |  |  |  | Substantial | 452 | CHA | 3 |  |  | 2010-10-14 | No | Complete
Central | Parwan | Shekh Ali | Saidan | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | c0a8-0057-12c3b6c95de-44f1db64-b286-f | MF-HT-317 | HT - HALO TRUST | H/3769 | 24800 | 68.5042 | 34.9457 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-06-11 | 2013-07-04 | 1392 | OMAR | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | Based on HALO Trust e-mail recieved on 31 May 2012, the task is removed from HT plan (H/3767, H/3768, H/3769 you can remove all this 3 tasks from our list.) |  |  | Substantial | 108 | CHA | 3 |  |  | 2007-10-31 | No | Complete
Central | Parwan | Shekh Ali | Saidan | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | c0a8-0057-12c3b6cfb24-eb2a573d-b756-a | MF-HT-321 | HT - HALO TRUST | H/3767 | 38900 | 68.5 | 34.9448 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-06-11 | 2013-07-11 | 1392 | OMAR | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | Based on HALO Trust e-mail recieved on 31 May 2012, the task is removed from HT plan (H/3767, H/3768, H/3769 you can remove all this 3 tasks from our list.) |  |  | Substantial | 335 | CHA | 4 |  |  | 2007-11-30 | No | Complete
Central | Parwan | Shekh Ali | Saidan | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | c0a8-0057-12c3b80f98b-aa742c61-1a1d2- | MF-HT-314 | HT - HALO TRUST | H/3887 | 39300 | 68.4974 | 34.9438 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004/A | Parwan Demining Project-04/A | VTF-Australia | Yes | 2013-11-16 | 2013-12-31 | 1392 | ATC | {2A1ABD3E-2EAD-410F-BD6E-9EC582A513E3} | Removed from HT 1390 plan |  |  | Substantial | 227 | CHA | 4 |  |  | 2007-11-30 | No | Complete
Central | Parwan | Shekh Ali | Saie Paien | {7549A8B5-BADB-413C-9319-C7B1C07997B5} | c0a8-0057-12c3ba39341-1fcfce3a-311ac- | MF-CA-1250 | HT - HALO TRUST | H/4245 | 620 | 68.576 | 34.9514 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-07-25 | 2013-07-25 | 1392 | OMAR | {7549A8B5-BADB-413C-9319-C7B1C07997B5} |  |  |  | Substantial | 76 | CHA | 3 |  |  | 2008-05-07 | No | Complete
Central | Parwan | Shekh Ali | Saie Paien | {7549A8B5-BADB-413C-9319-C7B1C07997B5} | c0a8-0057-12c3ba39505-a114c8a9-311be- | MF-CA-1249 | HT - HALO TRUST | H/1989 | 3000 | 68.6102 | 34.9592 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004 | Parwan Demining Project-04 | DOS | Yes | 2013-07-25 | 2013-07-25 | 1392 | OMAR | {7549A8B5-BADB-413C-9319-C7B1C07997B5} |  |  |  | Substantial | 50 | CHA | 3 |  |  | 2008-05-08 | No | Complete
Central | Parwan | Shekh Ali | Saie Paien | {7549A8B5-BADB-413C-9319-C7B1C07997B5} | c0a8-0057-12c3ba396f9-1babb96b-311cf- | MF-CA-1251 | HT - HALO TRUST | H/1982 | 117000 | 68.5972 | 34.9592 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {7549A8B5-BADB-413C-9319-C7B1C07997B5} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-05-10 | No | Open
Central | Parwan | Shekh Ali | Shaykh Ali | {60D07FFF-FA1D-4B3B-A049-DBEA7C72EB40} | c0a8-0057-12c3b6ca75b-43a06492-b352-6 | MF-HT-1443 | HT - HALO TRUST | H/2000 | 34410 | 68.4957 | 34.9537 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {60D07FFF-FA1D-4B3B-A049-DBEA7C72EB40} | , | High with Victim | High with Victims | Substantial | 62 | CHA | 2 |  |  | 2007-11-01 | No | Open
Central | Parwan | Shekh Ali | Shina | {43C4B34C-8365-4183-9FDC-D1BA446DD36F} | c0a8-0057-12c3bb7f8e2-aeb641bd-3d2a1- | MF-CA-1209 | HT - HALO TRUST | H/4248 | 108000 | 68.5059 | 34.8726 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {43C4B34C-8365-4183-9FDC-D1BA446DD36F} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-05-03 | No | Open
Central | Parwan | Shekh Ali | Shina | {43C4B34C-8365-4183-9FDC-D1BA446DD36F} | c0a8-0057-12c3bb7faa6-56b8510f-3d2b4- | MF-CA-1211 | HT - HALO TRUST | H/1988 | 85000 | 68.5059 | 34.8726 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {43C4B34C-8365-4183-9FDC-D1BA446DD36F} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-05-04 | No | Open
Central | Parwan | Shekh Ali | Somuchak | {7F83E2F3-6E92-4BF8-9D50-F416875FE030} | c0a8-0057-12c3bb76a99-51f8d9ae-3cd4c- | MF-CA-1172 | HT - HALO TRUST | H/1995 | 63000 | 68.3756 | 34.9868 | Open | AP Only | AP Only | MineField |  | MBT Project-109 | Parwan Demining Project-09 |  |  |  |  | 1395 |  | {7F83E2F3-6E92-4BF8-9D50-F416875FE030} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-05-13 | No | Open
Central | Parwan | Shinwari | Baghe Afghan | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} | c0a8-008e-13170968070-4d3925a3-17d-44 | MF-CA-1397 | HT - HALO TRUST | H/4272 | 24000 | 69.1222 | 35.065 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} |  | Medium | Critical Infrastracture | Substantial | 24 | CHA | 5 |  |  | 2008-05-19 | No | Open
Central | Parwan | Shinwari | Baghe Afghan | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} | c0a8-008e-1317e612020-592e6cd8-2b9-95 | MF-CA-1393 | HT - HALO TRUST | H/4275 | 27000 | 69.1224 | 35.0644 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} |  | Medium | Critical Infrastracture | Substantial | 24 | CHA | 5 |  |  | 2008-05-20 | No | Open
Central | Parwan | Shinwari | Baghe Afghan | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} | c0a8-008e-1317e7d1d37-dc396ee2-488-73 | MF-CA-1395 | HT - HALO TRUST | H/4276 | 30000 | 69.1191 | 35.0744 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} |  | Medium | Critical Infrastracture | Substantial | 24 | CHA | 3 |  |  | 2008-05-21 | No | Open
Central | Parwan | Shinwari | Baghe Afghan | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} | c0a8-008e-1328f8731e5-74686b96-148e-e | MF-16171 | HT - HALO TRUST | H/8061 | 33500 | 69.122 | 35.0655 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} |  | Medium | Critical Infrastracture | Substantial | 24 | CHA | 5 |  |  | 2011-06-06 16:30 | No | Open
Central | Parwan | Shinwari | Baghe Afghan | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} | c0a8-008e-1328f893ff2-67a88dc6-1558-2 | MF-16182 | HT - HALO TRUST | H/7896 | 37000 | 69.122 | 35.0655 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} |  | Medium | Critical Infrastracture | Substantial | 24 | CHA | 5 |  |  | 2011-06-07 16:30 | No | Open
Central | Parwan | Shinwari | Baghe Afghan | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} | c0a8-008e-13290ae78ae-ef74f209-49d-d8 | MF-16187 | HT - HALO TRUST | H/7897 | 32500 | 69.122 | 35.0655 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {2D499646-4B24-4EA2-AA7E-B4F626D5A914} |  | Medium | Critical Infrastracture | Substantial | 24 | CHA | 5 |  |  | 2011-06-08 16:30 | No | Open
Central | Parwan | Shinwari | Chakar | {7BBE12EC-6443-4500-9DE4-664814608FDF} | c0a8-0057-12c3b8146c0-8f3dc1e6-1a569- | MF-HT-703 | HT - HALO TRUST | H/2003 | 60000 | 69.0698 | 35.0001 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {7BBE12EC-6443-4500-9DE4-664814608FDF} |  | Medium | Critical Infrastracture | Substantial | 72 | CHA | 3 |  |  | 2002-03-01 | No | Open
Central | Parwan | Shinwari | Chakar | {7BBE12EC-6443-4500-9DE4-664814608FDF} | c0a8-0057-12c3b9b87d6-f090252e-2c262- | MF-HT-60 | HT - HALO TRUST | H/3850 | 65000 | 69.0757 | 34.9801 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {7BBE12EC-6443-4500-9DE4-664814608FDF} |  | Low | Agriculture Blocked | Substantial | 12 | CHA | 5 |  |  | 2007-10-22 | No | Open
Central | Parwan | Shinwari | Chenardara | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} | c0a8-0009-1467f335d36-e5cc13ac-1e84-e | Hz-ID-18780 | HT - HALO TRUST | H/8547 | 48600 | 69.1303 | 35.0519 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2014-05-22 16:30 | No | Open
Central | Parwan | Shinwari | Chenardara | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} | c0a8-0009-1467f7f5164-2a5ddcfc-22bf-8 | Hz-ID-18806 | HT - HALO TRUST | H/8786 | 71500 | 69.1359 | 35.056 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-221 | Parwan Demining Project-06 | Bilateral | Yes |  |  | 1393 | HT | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} |  | Low | Agriculture Blocked | Substantial | 16 | CHA | 5 |  |  | 2014-05-09 16:30 | No | Planned
Central | Parwan | Shinwari | Chenardara | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} | c0a8-0009-1473dac521e-31d6cb76-2f3-e2 | Hz-ID-18854 | HT - HALO TRUST | H/8798 | 56250 | 69.1272 | 35.0476 | Open | AP Only | AP Only | MineField |  | MBT Project-001/A | Parwan Demining Project-01/A |  |  |  |  | 1394 |  | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2014-06-10 16:30 | No | Open
Central | Parwan | Shinwari | Chenardara | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} | c0a8-0057-12c3ba02359-b5a5f77-2f069-d | MF-CA-1428 | HT - HALO TRUST | H/4288 | 53750 | 69.1129 | 35.0391 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-07-23 | No | Open
Central | Parwan | Shinwari | Chenardara | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} | c0a8-0057-12c3ba0276e-cd42940c-2f091- | MF-CA-1429 | HT - HALO TRUST | H/4287 | 55120 | 69.1129 | 35.0391 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-07-23 | No | Open
Central | Parwan | Shinwari | Chenardara | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} | c0a8-0057-12c3bb2952e-3e956f43-3a0bc- | MF-CA-1420 | HT - HALO TRUST | H/4290 | 40000 | 69.1201 | 35.0511 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} |  | Low | Agriculture Blocked | Substantial | 26 | CHA | 5 |  |  | 2008-06-26 | No | Open
Central | Parwan | Shinwari | Chenardara | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} | c0a8-0057-12c3bb29740-1d596900-3a0cf- | MF-HQ-11812 | HT - HALO TRUST | H/4299 | 50000 | 69.1212 | 35.0538 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} |  | Low | Agriculture Blocked | Substantial | 40 | CHA | 5 |  |  | 2008-06-18 | No | Open
Central | Parwan | Shinwari | Chenardara | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} | c0a8-0057-12c3bb35fe9-eadc0ff-3a874-a | MF-CA-1412 | HT - HALO TRUST | H/4297 | 81000 | 69.1213 | 35.0497 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} |  | Low | Agriculture Blocked | Substantial | 26 | CHA | 5 |  |  | 2008-06-21 | No | Open
Central | Parwan | Shinwari | Chenardara | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} | c0a8-0057-12c3bb3620b-b5620a1f-3a88a- | MF-CA-1413 | HT - HALO TRUST | H/4289 | 40000 | 69.1235 | 35.0551 | Open | AP Only | AP Only | MineField | Blank | MBT Project-110 | Parwan Demining Project-10 |  | No |  |  | 1395 | None | {5DB83FB3-8F52-4516-B026-76FF9B8FA0E7} |  | Low | Agriculture Blocked | Substantial | 40 | CHA | 5 |  |  | 2008-06-19 | No | Open
Central | Parwan | Shinwari | Dahane Bedqol | {D2620FF9-2AF1-4743-8EBC-8FF2DFF9B3E3} | c0a8-0057-12c3b81d2d7-714e06d8-1abac- | MF-CA-1391 | HT - HALO TRUST | H/4277 | 40580 | 69.1218 | 35.0608 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {D2620FF9-2AF1-4743-8EBC-8FF2DFF9B3E3} |  | Low | Agriculture Blocked | Substantial | 24 | CHA | 5 |  |  | 2008-05-22 | No | Open
Central | Parwan | Shinwari | Dahane Bedqol | {D2620FF9-2AF1-4743-8EBC-8FF2DFF9B3E3} | c0a8-0057-12c3b81d7f5-3ae644c3-1abe8- | MF-CA-1394 | HT - HALO TRUST | H/4284 | 26500 | 69.1215 | 35.0654 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {D2620FF9-2AF1-4743-8EBC-8FF2DFF9B3E3} |  | Low | Agriculture Blocked | Substantial | 24 | CHA | 5 |  |  | 2008-05-23 | No | Open
Central | Parwan | Shinwari | Dahane Shato | {6E30C3F2-A6A3-41E8-A973-1816662E4AA6} | c0a8-0057-12c3bb302cd-2efefbb8-3a4f5- | MF-HQ-10686 | MCPA - Mine Clearance Planning Agency | AF/304/01732/MF0109 | 52210 | 69.1104 | 35.085 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {6E30C3F2-A6A3-41E8-A973-1816662E4AA6} |  | High with Victim | High with Victims | Substantial | 53 | CHA | 2 |  |  | 2009-05-06 | No | Open
Central | Parwan | Shinwari | Dahane Shato | {6E30C3F2-A6A3-41E8-A973-1816662E4AA6} | c0a8-0057-12c3bb304d0-c65aab92-3a50b- | MF-HQ-10673 | MCPA - Mine Clearance Planning Agency | AF/304/01732/MF0107 | 49765 | 69.1111 | 35.08 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {6E30C3F2-A6A3-41E8-A973-1816662E4AA6} |  | High with Victim | High with Victims | Substantial | 1185 | CHA | 2 |  |  | 2009-05-24 | No | Open
Central | Parwan | Shinwari | Dahane Shato | {6E30C3F2-A6A3-41E8-A973-1816662E4AA6} | c0a8-0057-12c3bb306f2-f3bc3a4e-3a521- | MF-HQ-10684 | MCPA - Mine Clearance Planning Agency | AF/304/01732/MF0108 | 37341 | 69.1111 | 35.08 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {6E30C3F2-A6A3-41E8-A973-1816662E4AA6} |  | High with Victim | High with Victims | Substantial | 1238 | CHA | 2 |  |  | 2009-05-24 | No | Open
Central | Parwan | Shinwari | Darwishkhel | {BFD12505-7294-488B-80C3-E8DFE760B62F} | c0a8-0057-12c3b812e60-3bfdc22f-1a43d- | MF-CA-1773 | HT - HALO TRUST | H/2005 | 25000 | 69.0659 | 35.1499 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {BFD12505-7294-488B-80C3-E8DFE760B62F} |  | Low | Agriculture Blocked | Substantial | 532 | CHA | 4 |  |  | 2008-11-18 | No | Open
Central | Parwan | Shinwari | Heir/ Qala | {1A03DE52-DE19-42C4-A247-E3CCE615161C} | c0a8-0057-12c3ba4dab9-4b54254e-31e1a- | MF-CA-1883 | HT - HALO TRUST | H/5421 | 38000 | 69.0659 | 35.1129 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {1A03DE52-DE19-42C4-A247-E3CCE615161C} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-10-21 | No | Open
Central | Parwan | Shinwari | Ishturshar | {F9BB0825-3BEA-4F45-A69F-41A4A915F9B8} | c0a8-0057-12c3b68c63a-5e6d2b9e-84f1-e | MF-HQ-12362 | HT - HALO TRUST | H/6261 | 43800 | 68.9679 | 35.0059 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {F9BB0825-3BEA-4F45-A69F-41A4A915F9B8} |  | Low | Agriculture Blocked | Substantial | 45 | CHA | 5 |  |  | 2009-08-02 | No | Open
Central | Parwan | Shinwari | Ishturshar | {F9BB0825-3BEA-4F45-A69F-41A4A915F9B8} | c0a8-0057-12c3b73e532-c6f786f7-10b3b- | MF-HQ-12415 | HT - HALO TRUST | H/6262 | 56300 | 68.9641 | 35.0061 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {F9BB0825-3BEA-4F45-A69F-41A4A915F9B8} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-08-02 | No | Open
Central | Parwan | Shinwari | Ishturshar | {F9BB0825-3BEA-4F45-A69F-41A4A915F9B8} | c0a8-0057-12c3b78218b-96492357-13d2a- | MF-HQ-12417 | HT - HALO TRUST | H/6255 | 60000 | 68.9678 | 35.0059 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {F9BB0825-3BEA-4F45-A69F-41A4A915F9B8} |  | Low | Agriculture Blocked | Substantial | 45 | CHA | 5 |  |  | 2009-08-02 | No | Open
Central | Parwan | Shinwari | Khake Sango | {2BBD89C7-2B8D-4C69-BB75-43AC768BDEF7} | c0a8-0057-12c3b77c1f0-5a9723a8-138af- | MF-HQ-12416 | HT - HALO TRUST | H/6254 | 1050 | 68.7666 | 35.0326 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {2BBD89C7-2B8D-4C69-BB75-43AC768BDEF7} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2009-08-01 | No | Open
Central | Parwan | Shinwari | Kololasang | {BAE5BFB8-120C-411E-8171-1AD568F55A55} | c0a8-0057-12c3ba4dc9c-c5cd04ad-31e32- | MF-HQ-11951 | HT - HALO TRUST | H/5422 | 26000 | 69.0741 | 35.1376 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {BAE5BFB8-120C-411E-8171-1AD568F55A55} |  | Low | Agriculture Blocked | Substantial | 34 | CHA | 5 |  |  | 2008-10-20 | No | Open
Central | Parwan | Shinwari | Mola'i | {FDF731DE-9829-4A71-9080-1C86CAA6D68B} | c0a8-0057-12c3b6e4a78-708d5f7-c74a-bc | MF-HQ-12374 | HT - HALO TRUST | H/6264 | 60000 | 69.1035 | 35.0775 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {FDF731DE-9829-4A71-9080-1C86CAA6D68B} |  | Low | Agriculture Blocked | Substantial | 291 | CHA | 4 |  |  | 2009-08-03 | No | Open
Central | Parwan | Shinwari | Mola'i | {FDF731DE-9829-4A71-9080-1C86CAA6D68B} | c0a8-008e-1328f9efd2d-2355296c-1efe-e | MF-15802 | HT - HALO TRUST | H/7630 | 13550 | 69.1002 | 35.0781 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {FDF731DE-9829-4A71-9080-1C86CAA6D68B} |  | Low | Agriculture Blocked | Substantial | 291 | CHA | 4 |  |  | 2011-01-13 16:30 | No | Open
Central | Parwan | Shinwari | Mola'i | {FDF731DE-9829-4A71-9080-1C86CAA6D68B} | c0a8-008e-1328fa04649-3a1acb67-1f5e-7 | MF-15801 | HT - HALO TRUST | H/7629 | 20456 | 69.1002 | 35.0781 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {FDF731DE-9829-4A71-9080-1C86CAA6D68B} |  | Low | Agriculture Blocked | Substantial | 291 | CHA | 4 |  |  | 2011-01-13 16:30 | No | Open
Central | Parwan | Shinwari | Mola'i | {FDF731DE-9829-4A71-9080-1C86CAA6D68B} | c0a8-00f6-134e9f98099-7290b730-ad9-1c | MF-15913 | HT - HALO TRUST | H/7683 | 33000 | 69.104 | 35.08 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {FDF731DE-9829-4A71-9080-1C86CAA6D68B} |  | Low | Agriculture Blocked | Substantial | 291 | CHA | 4 |  |  | 2011-03-11 16:30 | No | Open
Central | Parwan | Shinwari | Mula-ee | {E83D8C18-AFF1-42FA-82E1-598A65D0D81D} | c0a8-0057-12c3b6ebc0e-6ce1c820-cccc-7 | MF-HQ-12427 | HT - HALO TRUST | H/6267 | 27000 | 69.104 | 35.08 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {E83D8C18-AFF1-42FA-82E1-598A65D0D81D} |  | Low | Agriculture Blocked | Substantial | 291 | CHA | 4 |  |  | 2009-08-05 | No | Open
Central | Parwan | Shinwari | Qala Pain | {1F84AC01-9BD7-4785-B143-59188F5D9865} | c0a8-0057-12c3b926668-32c74501-26253- | MF-HT-55 | HT - HALO TRUST | H/3845 | 20000 | 68.9795 | 35.0778 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {1F84AC01-9BD7-4785-B143-59188F5D9865} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2007-10-22 | No | Open
Central | Parwan | Shinwari | Qashqal(Shinwari) | {D89FB43E-C64D-4C4A-ADBA-9FF36B05DCE1} | c0a8-0057-12c3b7be991-cbd6f604-168d9- | MF-HQ-13635 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0304/01550/MF0114 | 86625 | 69.0128 | 35.0362 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {D89FB43E-C64D-4C4A-ADBA-9FF36B05DCE1} |  | Low | Agriculture Blocked | Substantial | 0 | SHA | 5 |  |  | 2009-11-05 | No | Open
Central | Parwan | Shinwari | Qashqal(Shinwari) | {D89FB43E-C64D-4C4A-ADBA-9FF36B05DCE1} | c0a8-0057-12c3b943457-e51a0ade-2757d- | MF-HT-58 | HT - HALO TRUST | H/3848 | 59300 | 69.0003 | 35.0436 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {D89FB43E-C64D-4C4A-ADBA-9FF36B05DCE1} |  | Low | Agriculture Blocked | Substantial | 529 | CHA | 4 |  |  | 2007-10-22 | No | Open
Central | Parwan | Shinwari | Qashqal(Shinwari) | {D89FB43E-C64D-4C4A-ADBA-9FF36B05DCE1} | c0a8-0057-12c3b97dae8-440e50c9-29b99- | MF-HQ-13634 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0304/01550/MF0115 | 248000 | 69.0129 | 35.0363 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {D89FB43E-C64D-4C4A-ADBA-9FF36B05DCE1} |  | Low | Agriculture Blocked | Substantial | 12 | SHA | 5 |  |  | 2009-11-05 | No | Open
Central | Parwan | Shinwari | Qashqal(Shinwari) | {D89FB43E-C64D-4C4A-ADBA-9FF36B05DCE1} | c0a8-0057-12c3ba0559f-89e985db-2f25f- | MF-HQ-12348 | HT - HALO TRUST | H/2013 | 80000 | 69.0333 | 35.0089 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {D89FB43E-C64D-4C4A-ADBA-9FF36B05DCE1} |  | Low | Agriculture Blocked | Substantial | 17 | CHA | 5 |  |  | 2004-09-08 16:30 | No | Open
Central | Parwan | Shinwari | Qashqal(Shinwari) | {D89FB43E-C64D-4C4A-ADBA-9FF36B05DCE1} | c0a8-0057-12c3ba057b1-35b289d4-2f270- | MF-HQ-11788 | HT - HALO TRUST | H/2010 | 14050 | 69.0122 | 35.0219 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {D89FB43E-C64D-4C4A-ADBA-9FF36B05DCE1} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-10-25 | No | Open
Central | Parwan | Shinwari | Qol-e-Heer | {5A25BE20-75EF-4FE0-AB04-B2CE56046454} | c0a8-0057-12c3b76250a-ee4f88b6-125d8- | MF-HT-1345 | HT - HALO TRUST | H/3789 | 260 | 69.0608 | 35.1499 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {5A25BE20-75EF-4FE0-AB04-B2CE56046454} |  | Medium | Agriculture Blocked | Substantial | 532 | CHA | 3 |  |  | 2007-08-01 | No | Open
Central | Parwan | Shinwari | Saeed Ali Khil | {9F4A15F5-562B-4258-987F-A94889ABE6CB} | c0a8-0009-13c1879b269-3de689b8-b07-c1 | Hz-ID-17559 | HT - HALO TRUST | H/8395 | 24500 | 69.132 | 35.0869 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {9F4A15F5-562B-4258-987F-A94889ABE6CB} |  | Medium | Critical Infrastracture | Substantial | 69 | CHA | 3 |  |  | 2012-12-07 16:30 | No | Open
Central | Parwan | Shinwari | Shatoot | {CBBFBB3B-28C0-47C9-BB7F-36DC2E9A1EDA} | c0a8-0057-12c3b771e24-d30020b1-13161- | MF-HT-1281 | HT - HALO TRUST | H/3720 | 28600 | 69.11 | 35.0741 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {CBBFBB3B-28C0-47C9-BB7F-36DC2E9A1EDA} |  | Medium | Critical Infrastracture | Substantial | 1446 | CHA | 3 |  |  | 2000-08-02 | No | Open
Central | Parwan | Shinwari | Shatoot | {CBBFBB3B-28C0-47C9-BB7F-36DC2E9A1EDA} | c0a8-0057-12c3b77293c-56fd236b-131e3- | MF-HT-1330 | HT - HALO TRUST | H/3761 | 45000 | 69.11 | 35.0741 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {CBBFBB3B-28C0-47C9-BB7F-36DC2E9A1EDA} |  | Medium | Critical Infrastracture | Substantial | 261 | CHA | 3 |  |  | 2007-08-01 | No | Open
Central | Parwan | Shinwari | Shewa | {BF09BE63-3079-4F72-8272-30A90F15B628} | c0a8-008e-1342c9d89e9-48480ccc-1df-f6 | MF-16419 | HT - HALO TRUST | H/8336 | 35500 | 68.9929 | 35.0147 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {BF09BE63-3079-4F72-8272-30A90F15B628} |  | High with Victim | High with Victims | Substantial | 14 | CHA | 2 |  |  | 2011-11-17 16:30 | No | Open
Central | Parwan | Shinwari | Shewa | {BF09BE63-3079-4F72-8272-30A90F15B628} | c0a8-008e-1342cc06890-a1557a20-484-66 | MF-16417 | HT - HALO TRUST | H/8337 | 26250 | 68.9929 | 35.0147 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {BF09BE63-3079-4F72-8272-30A90F15B628} |  | High with Victim | High with Victims | Substantial | 14 | CHA | 2 |  |  | 2011-11-19 16:30 | No | Open
Central | Parwan | Shinwari | Sufikhel | {E1EA7100-96C8-45C7-B632-BD88B3058290} | c0a8-008e-1342d20f8f7-470632f3-5c-3b1 | MF-15912 | HT - HALO TRUST | H/7682 | 16000 | 69.0496 | 35.0401 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {E1EA7100-96C8-45C7-B632-BD88B3058290} |  | Low | Agriculture Blocked | Substantial | 5 | CHA | 5 |  |  | 2011-03-14 16:30 | No | Open
Central | Parwan | Shinwari | Tahi Kanda | {A91F7D4A-5E97-4733-8D76-61B9B1A2E053} | c0a8-00f6-1352d9992af-fbf13290-20f-3d | MF-16596 | HT - HALO TRUST | H/8081 | 22500 | 69.1215 | 35.0654 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {A91F7D4A-5E97-4733-8D76-61B9B1A2E053} |  | Medium | Critical Infrastracture | Substantial | 36 | CHA | 5 |  |  | 2011-07-06 16:30 | No | Open
Central | Parwan | Shinwari | Tajiki Kafshan | {164DD829-BB6E-4AAB-898A-B031208669E8} | c0a8-0057-12c3b9a8da4-dcf1716c-2b86b- | MF-HT-704 | HT - HALO TRUST | H/2006 | 31500 | 68.9882 | 35.0773 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {164DD829-BB6E-4AAB-898A-B031208669E8} |  | Low | Infrastructure | Substantial | 1 | CHA | 5 |  |  | 2002-03-01 | No | Open
Central | Parwan | Shinwari | Tauskhel | {E72F7C8F-7EFC-4635-B85F-7CF5194EF5C7} | c0a8-0057-12c3b9a6f8a-937a58a6-2b729- | MF-CA-1788 | HT - HALO TRUST | H/5424 | 58800 | 69.084 | 35.006 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {E72F7C8F-7EFC-4635-B85F-7CF5194EF5C7} |  | Low | Agriculture Blocked | Substantial | 27 | CHA | 5 |  |  | 2008-10-23 | No | Open
Central | Parwan | Shinwari | Toghzar | {EC3CB14C-96AA-49CC-B9ED-F4ECF154587D} | c0a8-0057-12c3b7c79fc-fe68f32e-16f4d- | MF-CA-1864 | HT - HALO TRUST | H/5423 | 22000 | 69.0741 | 35.1376 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {EC3CB14C-96AA-49CC-B9ED-F4ECF154587D} |  | Low | Agriculture Blocked | Substantial | 34 | CHA | 5 |  |  | 2008-10-22 | No | Open
Central | Parwan | Shinwari | Toghzar | {EC3CB14C-96AA-49CC-B9ED-F4ECF154587D} | c0a8-0057-12c3b7c7b82-19262ad6-16f63- | MF-HQ-11835 | HT - HALO TRUST | H/5426 | 35000 | 69.0715 | 35.1335 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {EC3CB14C-96AA-49CC-B9ED-F4ECF154587D} |  | Low | Agriculture Blocked | Substantial | 72 | CHA | 5 |  |  | 2008-11-03 | No | Open
Central | Parwan | Shinwari | Wolang | {E4C8D0FA-5F56-40C5-9111-072B692C9CED} | c0a8-0009-13fb75ac6ea-43a6ee07-3f20-d | Hz-ID-18000 | HT - HALO TRUST | H/8501 | 24500 | 68.976 | 35.041 | Open | AP Only | AP Only | MineField |  | MBT Project-110 | Parwan Demining Project-10 |  |  |  |  | 1395 |  | {E4C8D0FA-5F56-40C5-9111-072B692C9CED} |  | Low | Agriculture Blocked | Substantial | 50 | CHA | 5 |  |  | 2013-03-17 16:30 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Baghe Kham | {824951E7-D7E0-4D72-A6D2-AA7809302A93} | c0a8-0057-12c3b7f5871-4b8ac80f-18f90- | MF-HQ-11740 | HT - HALO TRUST | H/5483 | 54500 | 68.6978 | 35.0132 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {824951E7-D7E0-4D72-A6D2-AA7809302A93} |  | Low | Agriculture Blocked | Substantial | 21 | CHA | 5 |  |  | 2008-12-02 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Baghe Kham | {824951E7-D7E0-4D72-A6D2-AA7809302A93} | c0a8-0057-12c3b7f5a26-4afd0d10-18fa4- | MF-HQ-11849 | HT - HALO TRUST | H/1826 | 43840 | 68.6978 | 35.0131 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {824951E7-D7E0-4D72-A6D2-AA7809302A93} |  | Low | Agriculture Blocked | Substantial | 21 | CHA | 5 |  |  | 2008-12-01 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Baghe Kham | {824951E7-D7E0-4D72-A6D2-AA7809302A93} | c0a8-0057-12c3ba3f58b-99bddc16-3156b- | MF-HQ-10376 | HT - HALO TRUST | H/1856 | 25300 | 68.6948 | 34.9922 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {824951E7-D7E0-4D72-A6D2-AA7809302A93} |  | Low | Agriculture Blocked | Substantial | 1133 | CHA | 3 |  |  | 2009-04-04 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Baghe Kham | {824951E7-D7E0-4D72-A6D2-AA7809302A93} | c0a8-0057-12c3bab56e9-edb64c45-35b92- | MF-HQ-10373 | HT - HALO TRUST | H/5930 | 49520 | 68.7134 | 34.994 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {824951E7-D7E0-4D72-A6D2-AA7809302A93} |  | Low | Agriculture Blocked | Substantial | 564 | CHA | 4 |  |  | 2009-04-07 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Bakas | {7F89E72B-0511-4201-9442-6FF7355E56A9} | c0a8-0057-12c3b6d9501-cb167135-beae-5 | MF-HQ-10417 | HT - HALO TRUST | H/5975 | 3480 | 68.7408 | 35.0681 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {7F89E72B-0511-4201-9442-6FF7355E56A9} |  | Low | Agriculture Blocked | Substantial | 35 | CHA | 5 |  |  | 2009-04-10 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Bakas | {7F89E72B-0511-4201-9442-6FF7355E56A9} | c0a8-0057-12c3b700df1-c77d8c32-dccc-8 | MF-HQ-10423 | HT - HALO TRUST | H/5976 | 3600 | 68.742 | 35.0713 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {7F89E72B-0511-4201-9442-6FF7355E56A9} |  | Low | Agriculture Blocked | Substantial | 36 | CHA | 5 |  |  | 2009-04-10 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Bakas | {7F89E72B-0511-4201-9442-6FF7355E56A9} | c0a8-0057-12c3b7a1566-ea691c30-153d4- | MF-HQ-10265 | HT - HALO TRUST | H/5970 | 10000 | 68.7518 | 35.0379 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {7F89E72B-0511-4201-9442-6FF7355E56A9} |  | Low | Agriculture Blocked | Substantial | 5 | CHA | 4 |  |  | 2009-04-13 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Balakhel | {4B77B3E7-79AB-425B-B458-91FD92677DEA} | c0a8-0057-12c3b6d4463-b8076e0b-bad9-9 | MF-HQ-10430 | HT - HALO TRUST | H/5957 | 2000 | 68.8709 | 34.9387 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {4B77B3E7-79AB-425B-B458-91FD92677DEA} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-04-21 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Balakhel | {4B77B3E7-79AB-425B-B458-91FD92677DEA} | c0a8-0057-12c3b809e62-a081a5ce-19e0f- | MF-HQ-14005 | HT - HALO TRUST | H/1841 | 2230 | 68.9056 | 34.959 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {4B77B3E7-79AB-425B-B458-91FD92677DEA} |  | Low | Agriculture Blocked | Substantial | 37 | CHA | 5 |  |  | 2009-04-05 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Chahar Deh-ye Ghowr Band | {C282639A-CB38-4F4E-94EA-D842AA411756} | c0a8-00f6-1353dc0dc22-f32fb3f8-1967-8 | MF-16652 | HT - HALO TRUST | H/6822 | 42500 | 68.7652 | 34.9849 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {C282639A-CB38-4F4E-94EA-D842AA411756} |  | High with Victim | High with Victims | Substantial | 38 | CHA | 2 |  |  | 2010-03-13 16:30 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Chelan | {F0E1ECAC-7FA6-42E5-B59B-AC127BF8635F} | c0a8-0057-12c3b9d75b5-5930b9e0-2d5c9- | MF-HQ-12004 | HT - HALO TRUST | H/1829 | 50000 | 68.7199 | 34.9791 | Open | AP Only | AP Only | MineField |  | MBT Project-140 | Kapisa Demining Project-09 |  |  |  |  | 1399 |  | {F0E1ECAC-7FA6-42E5-B59B-AC127BF8635F} |  | Low | Agriculture Blocked | Substantial | 74 | CHA | 4 |  |  | 2008-11-12 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Chelan | {F0E1ECAC-7FA6-42E5-B59B-AC127BF8635F} | c0a8-0057-12c3b9d7779-4402081a-2d5dd- | MF-HQ-11973 | HT - HALO TRUST | H/5433 | 39000 | 68.7216 | 34.9809 | Open | AP Only | AP Only | MineField |  | MBT Project-140 | Kapisa Demining Project-09 |  |  |  |  | 1399 |  | {F0E1ECAC-7FA6-42E5-B59B-AC127BF8635F} |  | Low | Agriculture Blocked | Substantial | 74 | CHA | 4 |  |  | 2008-11-10 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Chelan | {F0E1ECAC-7FA6-42E5-B59B-AC127BF8635F} | c0a8-0057-12c3b9d796c-707eca89-2d5f1- | MF-HQ-11962 | HT - HALO TRUST | H/5434 | 39000 | 68.7235 | 34.9817 | Open | AP Only | AP Only | MineField |  | MBT Project-140 | Kapisa Demining Project-09 |  |  |  |  | 1399 |  | {F0E1ECAC-7FA6-42E5-B59B-AC127BF8635F} | Removed from HT 1390 plan | Low | Agriculture Blocked | Substantial | 74 | CHA | 4 |  |  | 2008-11-11 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Dahane Lor | {90A100BF-1B12-413F-81F5-99818316C7F1} | c0a8-0057-12c3b6da1fc-15bb98fe-bf55-b | MF-HQ-14588 | HT - HALO TRUST | H/6890 | 6500 | 68.7789 | 35.0587 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {90A100BF-1B12-413F-81F5-99818316C7F1} |  | Low | Agriculture Blocked | Substantial | 26 | CHA | 5 |  |  | 2010-05-14 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Do Ab | {3C71354A-77D3-49CC-8512-5EA0FE027740} | c0a8-0057-12c3b94f6b4-f9c32074-27d88- | MF-HQ-11987 | HT - HALO TRUST | H/1832 | 10000 | 68.6562 | 34.966 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {3C71354A-77D3-49CC-8512-5EA0FE027740} |  | Low | Agriculture Blocked | Substantial | 19 | CHA | 5 |  |  | 2008-11-14 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Do Ab | {3C71354A-77D3-49CC-8512-5EA0FE027740} | c0a8-0057-12c3baf5308-e9312a50-381d7- | MF-HQ-11416 | HT - HALO TRUST | H/1831 | 15000 | 68.6477 | 34.959 | Open | AP Only | AP Only | MineField |  | MBT Project-140 | Kapisa Demining Project-09 |  |  |  |  | 1399 |  | {3C71354A-77D3-49CC-8512-5EA0FE027740} |  | Medium | Critical Infrastracture | Substantial | 654 | CHA | 3 |  |  | 2008-11-13 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b7d33b7-928c1e5d-177d9- | MF-HQ-11969 | HT - HALO TRUST | H/5435 | 38500 | 68.6563 | 34.9783 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 36 | CHA | 2 |  |  | 2008-11-30 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b7d353d-dcdbd535-177ec- | MF-HQ-11396 | HT - HALO TRUST | H/1843 | 34000 | 68.6563 | 34.9784 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 36 | CHA | 2 |  |  | 2008-11-29 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b861e0f-b477bd83-1dc9d- | MF-HQ-11846 | HT - HALO TRUST | H/1833 | 37665 | 68.7061 | 34.9768 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 184 | CHA | 2 |  |  | 2008-11-15 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b8a7b11-17eb23aa-20d49- | MF-HQ-11989 | HT - HALO TRUST | H/5428 | 70000 | 68.6756 | 34.9407 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 64 | CHA | 2 |  |  | 2008-11-05 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b8a7cd5-ec70a56d-20d5b- | MF-HQ-11803 | HT - HALO TRUST | H/5430 | 70000 | 68.6759 | 34.947 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 49 | CHA | 2 |  |  | 2008-11-07 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b8a7e9a-1afe3f4f-20d6d- | MF-HQ-11785 | HT - HALO TRUST | H/1837 | 70000 | 68.676 | 34.9375 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 44 | CHA | 2 |  |  | 2008-11-18 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b8a805e-84922897-20d7f- | MF-HQ-11808 | HT - HALO TRUST | H/5429 | 70000 | 68.676 | 34.9438 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 49 | CHA | 2 |  |  | 2008-11-06 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b8b5b20-3c0b1d6d-216bf- | MF-HQ-11734 | HT - HALO TRUST | H/5420 | 47500 | 68.6603 | 35.0686 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 13 | CHA | 2 |  |  | 2008-10-25 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b8f3cae-3aed2c83-241ac- | MF-HQ-11395 | HT - HALO TRUST | H/1855 | 40000 | 68.6823 | 34.9859 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 1786 | CHA | 2 |  |  | 2008-11-22 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b91ff14-f141e463-25e40- | MF-HQ-11806 | HT - HALO TRUST | H/5427 | 50000 | 68.6879 | 34.9728 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 2 | CHA | 2 |  |  | 2008-11-04 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b920126-1fb5aca3-25e52- | MF-HQ-11854 | HT - HALO TRUST | H/1834 | 50000 | 68.6888 | 34.9723 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 2 | CHA | 2 |  |  | 2008-11-08 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3b942e5e-1d815e60-27545- | MF-HQ-11776 | HT - HALO TRUST | H/1835 | 7500 | 68.7062 | 34.9768 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 228 | CHA | 2 |  |  | 2008-11-16 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3ba0d325-53dca1d5-2f737- | MF-HQ-11820 | HT - HALO TRUST | H/1854 | 37056 | 68.6809 | 34.9909 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 1861 | CHA | 2 |  |  | 2008-11-21 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3bae00e7-35924cd7-37518- | MF-HQ-11415 | HT - HALO TRUST | H/1839 | 35000 | 68.7106 | 34.9774 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 263 | CHA | 2 |  |  | 2008-10-08 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Ferenjal | {A52CD62B-2762-43F8-9365-D1AE675EFE58} | c0a8-0057-12c3bb1f9fa-abe31c4a-39b4c- | MF-HQ-11977 | HT - HALO TRUST | H/1838 | 20000 | 68.7168 | 34.9716 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {A52CD62B-2762-43F8-9365-D1AE675EFE58} |  | High with Victim | High with Victims | Substantial | 63 | CHA | 2 |  |  | 2008-11-07 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Galyan | {C467E512-6924-4DB2-B983-92512DF012D6} | c0a8-0057-12c3b693550-d6441260-89cd-4 | MF-HQ-14836 | HT - HALO TRUST | H/6821 | 50000 | 68.7637 | 34.9924 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {C467E512-6924-4DB2-B983-92512DF012D6} |  | Low | Agriculture Blocked | Substantial | 117 | CHA | 5 |  |  | 2010-03-12 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Galyan | {C467E512-6924-4DB2-B983-92512DF012D6} | c0a8-0057-12c3b6dba8a-38fe8319-c06f-7 | MF-HQ-14586 | HT - HALO TRUST | H/6888 | 53000 | 68.7679 | 34.9847 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {C467E512-6924-4DB2-B983-92512DF012D6} |  | Low | Agriculture Blocked | Substantial | 47 | CHA | 4 |  |  | 2010-05-11 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Galyan | {C467E512-6924-4DB2-B983-92512DF012D6} | c0a8-0057-12c3b6e4089-6eca0297-c6cb-f | MF-HQ-14587 | HT - HALO TRUST | H/6889 | 46300 | 68.7659 | 34.9867 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {C467E512-6924-4DB2-B983-92512DF012D6} |  | Low | Agriculture Blocked | Substantial | 38 | CHA | 4 |  |  | 2010-05-11 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Galyan | {C467E512-6924-4DB2-B983-92512DF012D6} | c0a8-0057-12c3b72ef24-73ca73d1-ffa6-1 | MF-HQ-14584 | HT - HALO TRUST | H/6887 | 41000 | 68.7663 | 34.9835 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {C467E512-6924-4DB2-B983-92512DF012D6} |  | Low | Agriculture Blocked | Substantial | 36 | CHA | 4 |  |  | 2010-05-10 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Galyan | {C467E512-6924-4DB2-B983-92512DF012D6} | c0a8-0057-12c3b761b59-d06bd16c-1256f- | MF-HQ-14583 | HT - HALO TRUST | H/6886 | 50000 | 68.7642 | 34.9863 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {C467E512-6924-4DB2-B983-92512DF012D6} |  | Low | Agriculture Blocked | Substantial | 38 | CHA | 4 |  |  | 2010-05-10 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Galyan | {C467E512-6924-4DB2-B983-92512DF012D6} | c0a8-0057-12c3b8e5f5d-54534c41-2389b- | MF-HQ-11982 | HT - HALO TRUST | H/1836 | 53000 | 68.7557 | 34.9976 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {C467E512-6924-4DB2-B983-92512DF012D6} |  | Medium | Critical Infrastracture | Substantial | 545 | CHA | 3 |  |  | 2008-11-17 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Joy-dukhtar | {0B95C305-466C-4CBD-8DDF-66EAE2BD7B4B} | c0a8-0057-12c3b89f198-f782ed09-20718- | MF-HQ-11863 | HT - HALO TRUST | H/1844 | 40000 | 68.7649 | 35.0361 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {0B95C305-466C-4CBD-8DDF-66EAE2BD7B4B} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-11-19 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Lich | {88E6B3B8-D1CB-4E42-99CB-854068BA3998} | c0a8-0057-12c3ba1e201-5079f90f-30191- | MF-HQ-10382 | HT - HALO TRUST | H/5926 | 40000 | 68.7479 | 35.0178 | Open | AP Only | AP Only | MineField |  | MBT Project-054 | Parwan Demining Project-05 |  |  |  |  | 1394 |  | {88E6B3B8-D1CB-4E42-99CB-854068BA3998} |  | Low | Agriculture Blocked | Substantial | 11 | CHA | 4 |  |  | 2009-04-13 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Mazana | {1485039F-C6A3-4198-9F7A-4E8F146511B3} | c0a8-0057-12c3b868d15-4ba2dd46-1e166- | MF-CA-1218 | HT - HALO TRUST | H/1849 | 2750 | 68.6351 | 35.007 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {1485039F-C6A3-4198-9F7A-4E8F146511B3} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-05-06 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Mazana | {1485039F-C6A3-4198-9F7A-4E8F146511B3} | c0a8-0057-12c3ba7d6ea-ab1ae6f6-33b63- | MF-CA-1219 | HT - HALO TRUST | H/1852 | 32500 | 68.6491 | 34.9979 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {1485039F-C6A3-4198-9F7A-4E8F146511B3} |  | Low | Agriculture Blocked | Substantial | 92 | CHA | 5 |  |  | 2008-05-05 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Myandeh | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} | c0a8-0057-12c3b809ada-abd3caeb-19de6- | MF-HQ-10386 | HT - HALO TRUST | H/5956 | 700 | 68.9058 | 34.9606 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2009-04-16 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Myandeh | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} | c0a8-0057-12c3b809c7f-17b79a57-19dfb- | MF-HQ-10377 | HT - HALO TRUST | H/5952 | 1050 | 68.9017 | 34.9673 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2009-04-19 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Myandeh | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} | c0a8-0057-12c3b80a027-d9cc827d-19e26- | MF-HQ-10381 | HT - HALO TRUST | H/5955 | 25 | 68.9016 | 34.9652 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2009-04-16 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Myandeh | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} | c0a8-0057-12c3b80a1eb-db4a753c-19e3a- | MF-HQ-10259 | HT - HALO TRUST | H/5954 | 145 | 68.9014 | 34.9653 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2009-04-17 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Myandeh | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} | c0a8-0057-12c3b80a3a0-a26ca6a8-19e4e- | MF-HQ-10378 | HT - HALO TRUST | H/5953 | 130 | 68.9014 | 34.9663 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2009-04-18 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Myandeh | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} | c0a8-0057-12c3bb18ce7-7c002e91-39701- | MF-HQ-11991 | HT - HALO TRUST | H/5432 | 32 | 68.892 | 34.9801 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} |  | Low | Agriculture Blocked | Substantial | 29 | CHA | 5 |  |  | 2008-11-09 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Myandeh | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} | c0a8-0057-12c3bb18eda-6d498003-39715- | MF-HQ-11857 | HT - HALO TRUST | H/1853 | 20 | 68.8911 | 34.9801 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {624AE2A3-795F-4EBC-B960-E8DF8AEAA0B4} |  | Low | Agriculture Blocked | Substantial | 17 | CHA | 5 |  |  | 2008-11-20 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Qabila | {38D2565A-8C4F-4611-810E-CCE696540857} | c0a8-0057-12c3b78fe22-5599e769-14732- | MF-HQ-10432 | HT - HALO TRUST | H/5958 | 690 | 68.9148 | 34.9567 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {38D2565A-8C4F-4611-810E-CCE696540857} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2009-04-15 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Qemchaq | {087485E9-0E87-4B2E-9289-FFEBD6377C0D} | c0a8-0057-12c3b714d3e-6fdc6fdf-ebde-9 | MF-HQ-10420 | HT - HALO TRUST | H/5959 | 2000 | 68.8415 | 35.0717 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {087485E9-0E87-4B2E-9289-FFEBD6377C0D} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2009-04-21 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Qemchaq | {087485E9-0E87-4B2E-9289-FFEBD6377C0D} | c0a8-0057-12c3b789f22-437b4aef-142ca- | MF-HQ-10435 | HT - HALO TRUST | H/5960 | 41350 | 68.8477 | 35.0765 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {087485E9-0E87-4B2E-9289-FFEBD6377C0D} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2009-04-20 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Saqa | {A28D0336-D640-46D7-930F-FC3122E5C2C5} | c0a8-0009-13fb7611323-7a79edb-40c1-e8 | Hz-ID-18001 | HT - HALO TRUST | H/8502 | 28428 | 68.7294 | 35.0053 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {A28D0336-D640-46D7-930F-FC3122E5C2C5} |  | Low | Agriculture Blocked | Substantial | 531 | CHA | 4 |  |  | 2013-03-03 16:30 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Saqa | {A28D0336-D640-46D7-930F-FC3122E5C2C5} | c0a8-0009-13fb76f45e0-eb970bd0-4402-3 | Hz-ID-18002 | HT - HALO TRUST | H/8503 | 19263 | 68.7294 | 35.0053 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {A28D0336-D640-46D7-930F-FC3122E5C2C5} |  | Low | Agriculture Blocked | Substantial | 547 | CHA | 4 |  |  | 2013-03-04 16:30 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Syahgerd | {03CE7965-1020-4D91-8882-9AF1B2DC0B6D} | c0a8-0057-12c3bb3af02-dc7c74d7-3ab6c- | MF-HQ-11816 | HT - HALO TRUST | H/3081 | 2290 | 68.6256 | 34.9691 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {03CE7965-1020-4D91-8882-9AF1B2DC0B6D} |  | Low | Agriculture Blocked | Substantial | 103 | CHA | 5 |  |  | 2008-12-03 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Zaynal | {D074F892-F715-4E40-811B-8348C9662C44} | c0a8-0057-12c3b689c2e-7abc45eb-831e-6 | MF-HQ-10411 | HT - HALO TRUST | H/5973 | 1435 | 68.7492 | 35.0549 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {D074F892-F715-4E40-811B-8348C9662C44} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2009-04-11 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Zaynal | {D074F892-F715-4E40-811B-8348C9662C44} | c0a8-0057-12c3b6a6571-f999e4c3-97dc-f | MF-HQ-10436 | HT - HALO TRUST | H/5974 | 5950 | 68.7464 | 35.0572 | Open | AP Only | AP Only | MineField |  | MBT Project-140 | Kapisa Demining Project-09 |  |  |  |  | 1399 |  | {D074F892-F715-4E40-811B-8348C9662C44} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 4 |  |  | 2009-04-10 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Zaynal | {D074F892-F715-4E40-811B-8348C9662C44} | c0a8-0057-12c3b6a9cb6-614799e1-9a7f-8 | MF-HQ-11687 | HT - HALO TRUST | H/6226 | 10300 | 68.7276 | 35.0528 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {D074F892-F715-4E40-811B-8348C9662C44} |  | Low | Agriculture Blocked | Substantial | 83 | CHA | 5 |  |  | 2009-06-18 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Zaynal | {D074F892-F715-4E40-811B-8348C9662C44} | c0a8-0057-12c3b776042-43acb4bc-13457- | MF-HQ-10422 | HT - HALO TRUST | H/5972 | 24200 | 68.7513 | 35.0513 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {D074F892-F715-4E40-811B-8348C9662C44} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2009-04-12 | No | Open
Central | Parwan | Sia Gird ( Ghorbund) | Zaynal | {D074F892-F715-4E40-811B-8348C9662C44} | c0a8-0057-12c3b7abf69-5bbbf7eb-15b86- | MF-HQ-10414 | HT - HALO TRUST | H/5971 | 1650 | 68.7536 | 35.047 | Open | AP Only | AP Only | MineField |  | MBT Project-222 | Parwan Demining Project-11 |  |  |  |  | 1400 |  | {D074F892-F715-4E40-811B-8348C9662C44} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2009-04-12 | No | Open
Central | Parwan | Surkhi Parsa | Bedak | {C9595E8D-0849-4E66-8877-E3C0BE3ABDF5} | c0a8-0057-12c3b704fc0-c32ad2cb-dfff-2 | MF-HQ-14571 | HT - HALO TRUST | H/6899 | 25000 | 68.562 | 34.8395 | Open | AP Only | AP Only | MineField |  | MBT Project-056 | Parwan Demining Project-12 |  |  |  |  | 1400 |  | {C9595E8D-0849-4E66-8877-E3C0BE3ABDF5} |  | Low | Agriculture Blocked | Low | 38 | CHA | 5 |  |  | 2010-05-04 | No | Open
Central | Parwan | Surkhi Parsa | Dahane Lokhak | {FD95520F-BF62-443F-A7EE-D9FBCC840469} | c0a8-0057-12c3ba7ce81-7f610a28-33b07- | MF-HQ-10385 | HT - HALO TRUST | H/5967 | 19500 | 68.7227 | 34.7852 | Open | AP Only | AP Only | MineField |  | MBT Project-056 | Parwan Demining Project-12 |  |  |  |  | 1400 |  | {FD95520F-BF62-443F-A7EE-D9FBCC840469} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2009-04-21 | No | Open
Central | Parwan | Surkhi Parsa | Khrakin | {CDB5325E-36D5-4F52-9963-DBFC7454D4C6} | c0a8-0057-12c3b78b6a7-1a4d1f12-143e1- | MF-HQ-14566 | HT - HALO TRUST | H/6850 | 36425 | 68.6522 | 34.8433 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004/A | Parwan Demining Project-04/A | VTF-Australia | Yes | 2013-10-01 | 2013-11-15 | 1392 | ATC | {CDB5325E-36D5-4F52-9963-DBFC7454D4C6} |  |  |  | Low | 376 | CHA | 4 |  |  | 2010-05-01 | No | Complete
Central | Parwan | Surkhi Parsa | Lokhak | {AEBA8C72-8DF5-4705-ABC6-EA00E80C6FD2} | c0a8-0057-12c3b727d7f-d0531329-fa4a-3 | MF-HQ-10357 | HT - HALO TRUST | H/5969 | 1450 | 68.7178 | 34.8326 | Open | AP Only | AP Only | MineField |  | MBT Project-056 | Parwan Demining Project-12 |  |  |  |  | 1400 |  | {AEBA8C72-8DF5-4705-ABC6-EA00E80C6FD2} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2009-04-22 | No | Open
Central | Parwan | Surkhi Parsa | Lokhak | {AEBA8C72-8DF5-4705-ABC6-EA00E80C6FD2} | c0a8-0057-12c3b7676ff-b655473d-129a3- | MF-HQ-10364 | HT - HALO TRUST | H/5968 | 8750 | 68.7219 | 34.8085 | Open | AP Only | AP Only | MineField |  | MBT Project-056 | Parwan Demining Project-12 |  |  |  |  | 1400 |  | {AEBA8C72-8DF5-4705-ABC6-EA00E80C6FD2} |  | Low | Agriculture Blocked | Low | 8 | CHA | 5 |  |  | 2009-04-23 | No | Open
Central | Parwan | Surkhi Parsa | Miyanaji | {4F28E6DD-ACEB-4BFC-B2BD-1D23874CAB75} | c0a8-0057-12c3baf5b42-e9cadf88-38220- | MF-CA-1590 | HT - HALO TRUST | H/2020 | 60000 | 68.6647 | 34.7105 | Open | AP Only | AP Only | MineField |  | MBT Project-056 | Parwan Demining Project-12 |  |  |  |  | 1400 |  | {4F28E6DD-ACEB-4BFC-B2BD-1D23874CAB75} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2008-10-22 | No | Open
Central | Parwan | Surkhi Parsa | Sebak | {32CC98C5-2286-4072-A830-E544FD8843D9} | c0a8-0057-12c3ba18439-4082bc32-2fdd4- | MF-CA-1558 | HT - HALO TRUST | H/2023 | 15400 | 68.5941 | 34.8327 | Open | AP Only | AP Only | MineField |  | MBT Project-056 | Parwan Demining Project-12 |  |  |  |  | 1400 |  | {32CC98C5-2286-4072-A830-E544FD8843D9} |  | Low | Agriculture Blocked | Low | 13 | CHA | 5 |  |  | 2008-10-11 | No | Open
Central | Parwan | Surkhi Parsa | Tangi (2) | {9F2A4E28-48EF-4788-8CD8-A0149577F191} | c0a8-0057-12c3b6a7d25-de8bfdba-9908-e | MF-HQ-14568 | HT - HALO TRUST | H/6897 | 41725 | 68.6531 | 34.8522 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004/A | Parwan Demining Project-04/A | VTF-Australia | Yes | 2013-07-01 | 2013-09-30 | 1392 | ATC | {9F2A4E28-48EF-4788-8CD8-A0149577F191} |  |  |  | Low | 37 | CHA | 4 |  |  | 2010-05-02 | No | Complete
Central | Parwan | Surkhi Parsa | Tangi (2) | {9F2A4E28-48EF-4788-8CD8-A0149577F191} | c0a8-0057-12c3b6ac9ce-ae0efca0-9c9b-3 | MF-HQ-14569 | HT - HALO TRUST | H/6898 | 38375 | 68.6522 | 34.8522 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-004/A | Parwan Demining Project-04/A | VTF-Australia | Yes | 2013-07-01 | 2013-09-30 | 1392 | ATC | {9F2A4E28-48EF-4788-8CD8-A0149577F191} |  |  |  | Low | 37 | CHA | 4 |  |  | 2010-05-03 | No | Complete
East | Kunar | Khas Kunar | Charakay Kalai | {B7DD8C03-AAFE-433B-97E8-53C1EF6A6C39} | c0a8-00f6-135522b66fe-5ca7c8ae-3f2-8d | MF-15763 | MCPA - Mine Clearance Planning Agency | AF/1015/00021/MF0015 | 2469 | 70.8709 | 34.6389 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-171 | Kunar Demining Project-02 |  |  |  |  | 1395 |  | {B7DD8C03-AAFE-433B-97E8-53C1EF6A6C39} |  | Medium | Water Blocked | Substantial | 554 | CHA | 3 |  |  | 2011-03-09 16:30 | No | Open
East | Kunar | Khas Kunar | Shamkar | {83442F6B-0C12-428F-A631-6B63E5E466AC} | c0a8-008e-1313cc621d5-40448559-678-e0 | MF-HQ-13630 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1015/10698/MF014 | 187130 | 70.9863 | 34.6808 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-171 | Kunar Demining Project-02 |  |  |  |  | 1395 |  | {83442F6B-0C12-428F-A631-6B63E5E466AC} |  | High with Victim | High with Victims | Substantial | 8 | SHA | 2 |  |  | 2009-11-05 | No | Open
East | Kunar | Khas Kunar | Shamkar | {83442F6B-0C12-428F-A631-6B63E5E466AC} | c0a8-008e-1328fb48749-870ceaed-2398-f | MF-15765 | MCPA - Mine Clearance Planning Agency | AF/1015/10698/MF0016 | 158355 | 70.9559 | 34.6722 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-171 | Kunar Demining Project-02 |  |  |  |  | 1395 |  | {83442F6B-0C12-428F-A631-6B63E5E466AC} |  | High with Victim | High with Victims | Substantial | 13 | CHA | 2 |  |  | 2011-03-09 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-008e-1328a3dc1f5-523dba1a-44a-50 | MF-15642 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0026 | 74434 | 71.2092 | 34.8563 | Open | AP Only | AP Only | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 163 | CHA | 1 |  |  | 2010-11-29 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-008e-132c95d2021-d3b57b37-31b1-5 | MF-15614 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0033 | 78204 | 71.2119 | 34.8518 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 22 | CHA | 1 |  |  | 2010-12-07 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-008e-132c95d7980-ee4664ba-31fd-a | MF-15639 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0034 | 78876 | 71.2119 | 34.8518 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 22 | CHA | 1 |  |  | 2010-12-08 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-008e-132c963f297-2526bf24-32c2-e | MF-15682 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0024 | 75510 | 71.215 | 34.8601 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 67 | CHA | 1 |  |  | 2010-11-27 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-008e-132c970c765-74d09a26-3321-b | MF-15684 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0023 | 60024 | 71.215 | 34.8601 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 67 | CHA | 1 |  |  | 2010-11-25 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-008e-132c97316c3-543435ae-3416-b | MF-15697 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0029 | 39120 | 71.2092 | 34.8563 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 100 | CHA | 1 |  |  | 2010-12-02 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-008e-132c9733635-c5e7fd19-342f-d | MF-15693 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0037 | 71750 | 71.2119 | 34.8518 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 17 | CHA | 1 |  |  | 2010-12-12 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-008e-132c973d2de-d6cc5f7d-3456-e | MF-15691 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0028 | 77110 | 71.2036 | 34.8603 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2010-12-01 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-008e-132c9740b99-b319f6c0-3469-9 | MF-15687 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0031 | 74937 | 71.2119 | 34.8518 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 115 | CHA | 1 |  |  | 2010-12-05 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-00f6-13552026529-c972bbfc-2c-53c | MF-15694 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0036 | 66270 | 71.1603 | 34.8834 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 17 | CHA | 1 |  |  | 2010-12-11 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-00f6-1355264033d-76d323a9-2e-746 | MF-15692 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0038 | 75888 | 71.2119 | 34.8518 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 17 | CHA | 1 |  |  | 2010-12-13 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-00f6-138469be51c-125808e6-1f10-4 | Hz-ID-17088 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/1002/10614/MF0053 | 19394 | 71.2056 | 34.8603 | Open | AP Only | AP Only | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 48 | CHA | 1 |  |  | 2012-06-16 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-00f6-138469eb2c5-ae1ea6e1-1f28-d | Hz-ID-17090 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/1002/10614/MF0055 | 23799 | 71.2053 | 34.8614 | Open | AP Only | AP Only | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 48 | CHA | 1 |  |  | 2012-06-18 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-00f6-138470b24fb-5f7e83ab-1f6d-4 | Hz-ID-17089 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/1002/10614/MF0054 | 35419 | 71.1969 | 34.8502 | Open | AP Only | AP Only | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 39 | CHA | 1 |  |  | 2012-06-17 16:30 | No | Open
East | Kunar | Marawara | Chinar | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} | c0a8-00f6-1384b523454-a7d7361c-2190-c | Hz-ID-17068 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/1002/10614/MF0052 | 22407 | 71.2119 | 34.8519 | Open | AP Only | AP Only | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {47C005F9-EFB0-4FD5-95C5-7330ECC92052} |  | High with Victim | High with Victims | High | 115 | CHA | 1 |  |  | 2012-06-14 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-008e-1329f124492-1d54e772-f7b-cf | MF-15648 | MCPA - Mine Clearance Planning Agency | AF/1002/31913/MF0049 | 91575 | 71.2217 | 34.9145 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 60 | CHA | 1 |  |  | 2010-12-26 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-008e-1329f147895-141c5050-fb8-5b | MF-15659 | MCPA - Mine Clearance Planning Agency | AF/1002/31913/MF0043 | 89750 | 71.2296 | 34.91 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 99 | CHA | 1 |  |  | 2010-12-19 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-008e-1329f16ad41-1cb96fa8-1053-6 | MF-15653 | MCPA - Mine Clearance Planning Agency | AF/1002/31913/MF0041 | 79810 | 71.2296 | 34.91 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 131 | CHA | 1 |  |  | 2010-12-16 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-008e-1329f178dd3-6091f3ce-10ba-7 | MF-15652 | MCPA - Mine Clearance Planning Agency | AF/1002/31913/MF0042 | 97357 | 71.2296 | 34.91 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 116 | CHA | 1 |  |  | 2010-12-18 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-008e-1329f187104-274ada2b-10e7-a | MF-15646 | MCPA - Mine Clearance Planning Agency | AF/1002/31913/MF0050 | 82790 | 71.2217 | 34.9145 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 60 | CHA | 1 |  |  | 2010-12-26 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-008e-1329f1e95c3-b0560dfb-1264-1 | MF-15634 | MCPA - Mine Clearance Planning Agency | AF/1002/31913/MF0044 | 80545 | 71.2296 | 34.91 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 83 | CHA | 1 |  |  | 2010-12-20 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-008e-1329f232bba-28105c79-137a-b | MF-15675 | MCPA - Mine Clearance Planning Agency | AF/1002/31913/MF0048 | 78320 | 71.2217 | 34.9145 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 87 | CHA | 1 |  |  | 2010-12-25 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-008e-132c8840049-a5e6437d-24c9-2 | MF-15655 | MCPA - Mine Clearance Planning Agency | AF/1002/31913/MF0040 | 92208 | 71.2296 | 34.91 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 169 | CHA | 1 |  |  | 2010-12-15 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-008e-132c8862925-9882082e-2593-7 | MF-15672 | MCPA - Mine Clearance Planning Agency | AF/1002/31913/MF0046 | 84197 | 71.2203 | 34.9171 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 87 | CHA | 1 |  |  | 2010-12-22 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-008e-132c887444e-fb79be50-25e8-c | MF-15676 | MCPA - Mine Clearance Planning Agency | AF/1002/31913/MF0047 | 81445 | 71.2217 | 34.9145 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 8 | CHA | 1 |  |  | 2010-12-23 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-008e-132c963c5ed-d17658fb-32b0-e | MF-15679 | MCPA - Mine Clearance Planning Agency | AF/1002/31913/MF0045 | 75240 | 71.2296 | 34.91 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 398 | CHA | 1 |  |  | 2010-12-21 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-00f6-1356fda7b02-ab3b3f87-3e-cc9 | MF-15635 | MCPA - Mine Clearance Planning Agency | AF/1002/10614/MF0032 | 73710 | 71.2119 | 34.8518 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 100 | CHA | 1 |  |  | 2010-12-06 16:30 | No | Open
East | Kunar | Marawara | Marawara | {933307C3-F875-4900-A86E-3786019DF780} | c0a8-00f6-1384b23c11c-3ef60db6-203c-2 | Hz-ID-17091 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/1002/31913/MF0056 | 29727 | 71.2335 | 34.9123 | Open | AP Only | AP Only | MineField |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {933307C3-F875-4900-A86E-3786019DF780} |  | High with Victim | High with Victims | High | 38 | CHA | 1 |  |  | 2012-06-19 16:30 | No | Open
East | Kunar | Marawara | Petaw | {B84C9743-B3D2-4302-B261-657D09629879} | c0a8-008e-1328a469b64-828c63d3-619-b1 | BF-15028 | MCPA - Mine Clearance Planning Agency | AF/1002/10615/BF0051 | 163443 | 71.2328 | 34.8529 | Open | UXO Only | UXO Only | BF |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {B84C9743-B3D2-4302-B261-657D09629879} |  | High with Victim | High with Victims | High | 102 | CHA | 2 |  |  | 2011-01-19 16:30 | No | Open
East | Kunar | Narang | Kodu | {45F88A42-3F8F-44AA-B57C-EAED9E26D8DE} | c0a8-0009-143851865f1-1885fa89-4440-c | Hz-ID-18380 | MCPA - Mine Clearance Planning Agency | AF/1012/10397/BF0001 | 519658 | 71.0215 | 34.7587 | Open | UXO Only | UXO Only | BF |  | MBT Project-171 | Kunar Demining Project-02 |  |  |  |  | 1395 |  | {45F88A42-3F8F-44AA-B57C-EAED9E26D8DE} |  | Low | Agriculture Blocked | Substantial | 188 | CHA | 4 |  |  | 2013-10-05 16:30 | No | Open
East | Kunar | Narang | Kodu | {45F88A42-3F8F-44AA-B57C-EAED9E26D8DE} | c0a8-0009-14385253eae-82bb16fd-45e1-e | Hz-ID-18383 | MCPA - Mine Clearance Planning Agency | AF/1012/10397/BF0002 | 314651 | 71.0215 | 34.7587 | Open | UXO Only | UXO Only | BF |  | MBT Project-171 | Kunar Demining Project-02 |  |  |  |  | 1395 |  | {45F88A42-3F8F-44AA-B57C-EAED9E26D8DE} |  | Low | Agriculture Blocked | Substantial | 19 | CHA | 5 |  |  | 2013-10-05 16:30 | No | Open
East | Kunar | Nari | Narai | {E0E02B2E-7267-491E-B587-983015FECF86} | c0a8-008e-1328fcbd48e-e8fc2068-289e-5 | BF-15093 | MCPA - Mine Clearance Planning Agency | AF/1005/10419/BF0035 | 243804 | 71.5201 | 35.2157 | Open | UXO Only | UXO Only | BF |  | MBT Project-154 | Kunar Demining Project-01 |  |  |  |  | 1396 |  | {E0E02B2E-7267-491E-B587-983015FECF86} |  | High with Victim | High with Victims | High | 381 | CHA | 1 |  |  | 2011-06-05 16:30 | No | Open
East | Kunar | Shaygal wa shital | Bar Shurtan | {14B98C41-73F7-4B4C-9415-4B53D64288DC} | c0a8-008e-1313ccb6728-29b4ddbc-6e8-db | MF-HQ-14602 | MCPA - Mine Clearance Planning Agency | AF/1004/10494/MF0026 | 16488 | 71.2821 | 34.9598 | Open | AP Only | AP Only | MineField |  | MBT Project-171 | Kunar Demining Project-02 |  |  |  |  | 1395 |  | {14B98C41-73F7-4B4C-9415-4B53D64288DC} | Kunar CBD Project | High with Victim | High with Victims | High | 565 | CHA | 3 |  |  | 2010-02-11 | No | Open
East | Laghman | Mihtarlam | Ghunday | {3331EA73-59D7-4E6A-8F0E-BD46349A220E} | c0a8-0009-143cde4185f-5998ca03-2f68-f | Hz-ID-18409 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0901/09796/MF0019 | 280834 | 70.1181 | 34.6442 | Open | AT Only | AT Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {3331EA73-59D7-4E6A-8F0E-BD46349A220E} |  | Low | Infrastructure | High | 207 | CHA | 4 |  |  | 2013-12-04 16:30 | No | Open
East | Laghman | Mihtarlam | Kharoti | {0E9AF600-AEEA-4E64-ADE2-72C9949C87C6} | c0a8-0009-143cde9cebe-9162f913-2f84-7 | Hz-ID-18410 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0901/09794/MF0020 | 67951 | 70.1716 | 34.6552 | Open | AT Only | AT Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {0E9AF600-AEEA-4E64-ADE2-72C9949C87C6} |  | Medium | Critical Infrastracture | High | 236 | CHA | 3 |  |  | 2013-12-07 16:30 | No | Open
East | Laghman | Qarghayi | Kam Dergi | {B2AED62F-DAB3-4C44-86FF-7EC8027CC04F} | c0a8-0057-12c3bb6edbe-6731e7b3-3c905- | MF-HQ-11234 | MCPA - Mine Clearance Planning Agency | AF/0902/09878/MF0194 | 78900 | 69.9041 | 34.4834 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {B2AED62F-DAB3-4C44-86FF-7EC8027CC04F} | Funding status updated | Low | Agriculture Blocked | High | 32 | CHA | 5 |  |  | 2009-03-28 | No | Open
East | Laghman | Qarghayi | Kam Dergi | {B2AED62F-DAB3-4C44-86FF-7EC8027CC04F} | c0a8-008e-1313cdae5e5-918c21a1-808-f0 | MF-HQ-10518 | MCPA - Mine Clearance Planning Agency | AF/0902/09878/MF0192 | 63786 | 69.9041 | 34.4834 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {B2AED62F-DAB3-4C44-86FF-7EC8027CC04F} |  | Low | Agriculture Blocked | High | 32 | CHA | 5 |  |  | 2009-03-28 | No | Open
East | Laghman | Qarghayi | Kam Dergi | {B2AED62F-DAB3-4C44-86FF-7EC8027CC04F} | c0a8-008e-1314127e207-9e54f131-17fa-9 | MF-HQ-10519 | MCPA - Mine Clearance Planning Agency | AF/0902/09878/MF0193 | 68368 | 69.9041 | 34.4834 | Open | AP Only | AP Only | MineField | Blank | MBT Project-250 | Laghman Demining Project-01 |  | No |  |  | 1397 | None | {B2AED62F-DAB3-4C44-86FF-7EC8027CC04F} |  | Low | Agriculture Blocked | High | 32 | CHA | 5 |  |  | 2009-03-26 | No | Open
East | Laghman | Qarghayi | Mansur Kalay | {F60631EF-4B89-49D5-8A52-C59C6418BE38} | c0a8-0009-1440683836e-e6824796-a6f-2b | Hz-ID-18488 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09918/MF0241 | 10512 | 70.3026 | 34.4891 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-250/A | Laghman Demining Project-01/A | DOS | Yes | 2014-02-17 | 2014-03-31 | 1392 | OMAR | {F60631EF-4B89-49D5-8A52-C59C6418BE38} |  |  |  | High | 152 | CHA | 4 |  |  | 2014-01-22 16:30 | No | Complete
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-13e3bad7d2e-53575f25-c79-18 | Hz-ID-17820 | MDC - Mine Detection and Dog Center | AF/0902/09882/MF0240 | 26177 | 69.9425 | 34.5051 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 91 | CHA | 1 |  |  | 2013-03-28 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-145d518f378-fc6b4b48-3148-d | Hz-ID-18630 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0243 | 45249 | 69.9234 | 34.5051 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 30 | CHA | 1 |  |  | 2014-03-24 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-145d51b1fa5-5042aa6b-3166-5 | Hz-ID-18631 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0244 | 44552 | 69.9283 | 34.505 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 30 | CHA | 1 |  |  | 2014-03-25 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-145d529ca7e-e404a08b-3217-a | Hz-ID-18633 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0246 | 44941 | 69.9303 | 34.505 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 39 | CHA | 1 |  |  | 2014-03-27 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-145d52c071f-1b648f16-3231-1 | Hz-ID-18634 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0247 | 44939 | 69.9303 | 34.505 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 9 | CHA | 1 |  |  | 2014-03-29 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-145d52e5147-8034ee70-326b-c | Hz-ID-18635 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0248 | 79875 | 69.9331 | 34.505 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 9 | CHA | 1 |  |  | 2014-03-30 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-145d53238a7-b05332b2-3287-2 | Hz-ID-18636 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0249 | 63991 | 69.9331 | 34.505 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 9 | CHA | 1 |  |  | 2014-03-31 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-145fea81d53-7571b7a5-d68-e2 | Hz-ID-18629 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | MF/0902/09882/MF0242 | 44658 | 69.9234 | 34.5051 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 30 | CHA | 1 |  |  | 2014-03-23 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-145fea94694-b5ddbfef-d84-d9 | Hz-ID-18632 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0245 | 44942 | 69.9283 | 34.505 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 39 | CHA | 1 |  |  | 2014-03-26 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-146606333ed-d230ab73-65a6-9 | Hz-ID-18742 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0250 | 64215 | 69.9464 | 34.5028 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 72 | CHA | 1 |  |  | 2014-04-23 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-146606576a7-8d84384d-66b2-4 | Hz-ID-18743 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0251 | 65720 | 69.9464 | 34.5028 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 72 | CHA | 1 |  |  | 2014-04-22 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-146606dcc84-cba018f4-68cd-f | Hz-ID-18744 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0252 | 76382 | 69.9464 | 34.5028 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 63 | CHA | 1 |  |  | 2014-04-21 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-146606fd921-d2322436-69f7-5 | Hz-ID-18745 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0253 | 86944 | 69.9464 | 34.5028 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 63 | CHA | 1 |  |  | 2014-04-20 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-1466078e3eb-f0cd9b9b-6a6d-2 | Hz-ID-18746 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0254 | 67933 | 69.9464 | 34.5028 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 86 | CHA | 1 |  |  | 2014-04-17 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-14660849dc7-79f285a7-6bd1-7 | Hz-ID-18747 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0255 | 62977 | 69.9464 | 34.5028 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 86 | CHA | 1 |  |  | 2014-04-19 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-1466085c8fc-baa0ef7b-6c2b-4 | Hz-ID-18750 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0256 | 67972 | 69.9464 | 34.5028 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 23 | CHA | 1 |  |  | 2014-04-16 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-147334f0679-c885cd61-2c0-76 | Hz-ID-18862 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0258 | 78131 | 69.9179 | 34.5041 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 180 | CHA | 1 |  |  | 2014-05-24 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-14743169c26-f4611e26-1ff1-7 | Hz-ID-18861 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0257 | 75143 | 69.9179 | 34.5041 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 180 | CHA | 1 |  |  | 2014-05-22 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-14743175a36-a2f7d40-200f-d8 | Hz-ID-18863 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0259 | 78063 | 69.9179 | 34.5041 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 180 | CHA | 1 |  |  | 2014-05-25 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0009-14743184291-127e93e1-202e-9 | Hz-ID-18864 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0260 | 77369 | 69.9104 | 34.5036 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2014-05-26 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b73dc4d-e8f1186c-10ac3- | MF-HQ-11229 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0232 | 88540 | 69.8963 | 34.5008 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | , | High with Victim | High with Victims | High | 11 | CHA | 1 | Yes | according to communiy required and request | 2009-04-18 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b74707f-a04aedb4-111b6- | MF-HQ-11266 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0222 | 84100 | 69.9372 | 34.5055 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 35 | CHA | 1 | Yes | according to communiy required and request | 2009-04-14 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b76d90b-cfdf81e8-12e40- | MF-HQ-11264 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0223 | 85000 | 69.9372 | 34.5055 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 35 | CHA | 1 | Yes | according to communiy required and request | 2009-04-16 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b788fb7-d414d749-14217- | MF-HQ-11280 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0200 | 93847 | 69.9425 | 34.5062 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-250/A | Laghman Demining Project-01/A | DOS | Yes | 2014-01-01 | 2014-03-31 | 1392 | OMAR | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | , |  |  | High | 172 | CHA | 1 | Yes | according to communiy required and request | 2009-04-07 | No | Complete
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b7892f2-74b94a24-1423f- | MF-HQ-11265 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0221 | 92300 | 69.9372 | 34.5055 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 35 | CHA | 1 | Yes | according to communiy required and request | 2009-04-12 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b7f28e9-72d976d3-18d50- | MF-HQ-11221 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0226 | 75000 | 69.932 | 34.5051 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-250/A | Laghman Demining Project-01/A | DOS | Yes | 2014-01-01 | 2014-03-31 | 1392 | OMAR | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  |  |  | High | 57 | CHA | 1 | Yes | according to communiy required and request | 2009-04-20 | No | Complete
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b7f2aae-4269e68b-18d62- | MF-HQ-11294 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0215 | 75000 | 69.9133 | 34.5033 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 35 | CHA | 1 | Yes | according to communiy required and request | 2009-04-08 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b7f2c72-4b141abe-18d76- | MF-HQ-11271 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0216 | 73876 | 69.9133 | 34.5033 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | , | High with Victim | High with Victims | High | 35 | CHA | 1 | Yes | according to communiy required and request | 2009-04-07 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b7f33b2-8c3b010e-18dc3- | MF-HQ-11276 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0211 | 75000 | 69.9217 | 34.5049 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 17 | CHA | 1 | Yes | according to communiy required and request | 2009-04-01 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b7f35a5-48855fb9-18dd7- | MF-HQ-11269 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0218 | 73786 | 69.9257 | 34.505 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-250/A | Laghman Demining Project-01/A | DOS | Yes | 2014-01-01 | 2014-03-31 | 1392 | OMAR | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  |  |  | High | 23 | CHA | 1 |  |  | 2009-04-13 | No | Complete
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b8142f9-60a65dd4-1a539- | MF-HQ-11260 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0173 | 64946 | 69.973 | 34.5153 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | , | High with Victim | High with Victims | High | 348 | CHA | 2 |  |  | 2009-03-22 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3b8d6172-57cb621c-22d2e- | MF-HQ-11272 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0233 | 98135 | 69.9015 | 34.5023 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 30 | CHA | 1 | Yes | according to communiy required and request | 2009-04-09 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3badf276-3f0ffd5c-374a3- | MF-HQ-11218 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0195 | 67993 | 69.8688 | 34.498 | Open | AP Only | AP Only | MineField | Blank | MBT Project-250 | Laghman Demining Project-01 |  | No | 2012-01-01 | 2012-03-31 | 1397 | None | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 1 | CHA | 1 |  |  | 2009-03-29 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3badf534-cc4971fe-374b5- | MF-HQ-11219 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0196 | 65995 | 69.8688 | 34.498 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 1 | CHA | 1 | Yes | according to communiy required and request | 2009-03-31 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3bb111c0-76d7c3e0-39268- | MF-HQ-11282 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0203 | 60183 | 69.8551 | 34.5007 | Open | AP Only | AP Only | MineField | Blank | MBT Project-250 | Laghman Demining Project-01 |  | No | 2012-01-01 | 2012-03-31 | 1397 | None | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 1 | CHA | 1 |  |  | 2009-04-04 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-0057-12c3bb116bf-a975c9cb-3928d- | MF-HQ-11284 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0202 | 68046 | 69.8551 | 34.5007 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | , | High with Victim | High with Victims | High | 1 | CHA | 1 |  |  | 2009-04-01 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-008e-1313ce9d0df-fd6db67b-a71-c9 | MF-HQ-11288 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0205 | 68920 | 69.9015 | 34.5023 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 41 | CHA | 1 | Yes | according to communiy required and request | 2009-04-12 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-008e-1313cebf345-217e35d2-b17-89 | MF-HQ-11273 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0234 | 84690 | 69.8987 | 34.5019 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 11 | CHA | 1 |  |  | 2009-04-15 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-008e-1313cef3af0-96b715d0-bee-6a | MF-HQ-11213 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0180 | 56489 | 69.8371 | 34.4983 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | , | High with Victim | High with Victims | High | 1 | CHA | 1 |  |  | 2009-03-30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-008e-132c97f17de-f9131-35f5-8798 | MF-15982 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0235 | 50738 | 69.8986 | 34.5019 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 11 | CHA | 1 | Yes | according to communiy required and request | 2011-03-09 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-008e-134508dd237-c29f9813-eb-5e4 | MF-16425 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0237 | 43188 | 69.8531 | 34.4992 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 1 | CHA | 1 |  |  | 2011-06-04 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-008e-134559fcc4c-369c2611-78b-d5 | MF-16134 | MCPA - Mine Clearance Planning Agency | AF/0902/09882/MF0236 | 61344 | 69.8364 | 34.4984 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 1 | CHA | 1 |  |  | 2011-06-06 16:30 | No | Open
East | Laghman | Qarghayi | Sar Kand Ow Baba Ziarat | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} | c0a8-00f6-13706f06d47-ae313484-70d-ae | MF-16759 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0902/09882/MF0239 | 41250 | 69.9218 | 34.5026 | Open | AP Only | AP Only | MineField |  | MBT Project-250 | Laghman Demining Project-01 |  |  |  |  | 1397 |  | {BF2ABE16-6BFB-4359-8DDB-26EFBE0F66AB} |  | High with Victim | High with Victims | High | 17 | CHA | 1 |  |  | 2011-12-31 16:30 | No | Open
East | Nangarhar | Acheen | Bandar Kholeh | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} | c0a8-0009-13bf9edb3fa-46bec399-677a-c | Hz-ID-17471 | MCPA - Mine Clearance Planning Agency | AF/0810/09175/MF0043 | 34105 | 70.7679 | 34.0719 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} |  | Low | Agriculture Blocked | High | 73 | CHA | 4 |  |  | 2012-09-27 16:30 | No | Pledged
East | Nangarhar | Acheen | Bandar Kholeh | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} | c0a8-0009-140526dd144-4b13744d-7311-b | Hz-ID-18063 | MDC - Mine Detection and Dog Center | AF/0810/09175/MF0050 | 44996 | 70.7668 | 34.0969 | Open | AT Only | AT Only | MineField |  | MBT Project-251 | Nangarhar Demining Project-04 | DOS |  |  |  | 1393 |  | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} |  | Low | Critical Infrastracture | High | 557 | CHA | 5 |  |  | 2013-05-09 16:30 | No | Pledged
East | Nangarhar | Acheen | Bandar Kholeh | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} | c0a8-00f6-13a919bab72-ad1463c4-57a-22 | Hz-ID-17315 | MCPA - Mine Clearance Planning Agency | AF/0810/09175/MF0048 | 112903 | 70.7658 | 34.0979 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2013-04-01 | 2013-04-30 | 1392 | MDC | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} |  |  |  | High | 86 | CHA | 4 |  |  | 2012-10-04 16:30 | No | Planned
East | Nangarhar | Acheen | Bandar Kholeh | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} | c0a8-00f6-13ad57edcb9-b2c9562f-439b-c | Hz-ID-17309 | MCPA - Mine Clearance Planning Agency | AF/0810/09175/MF0046 | 44274 | 70.7643 | 34.0812 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} |  | Low | Critical Infrastracture | High | 733 | CHA | 4 |  |  | 2012-09-29 16:30 | No | Pledged
East | Nangarhar | Acheen | Bandar Kholeh | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} | c0a8-00f6-13ad58e1fb6-4896154d-44c2-f | Hz-ID-17312 | MCPA - Mine Clearance Planning Agency | AF/0810/09175/MF0044 | 84956 | 70.7694 | 34.0911 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} |  | Low | Critical Infrastracture | High | 161 | CHA | 4 |  |  | 2012-10-06 16:30 | No | Pledged
East | Nangarhar | Acheen | Bandar Kholeh | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} | c0a8-00f6-13ad592a466-1ff1f6d8-4547-b | Hz-ID-17313 | MCPA - Mine Clearance Planning Agency | AF/0810/09175/MF0045 | 153826 | 70.7694 | 34.0911 | Open | AT Only | AT Only | MineField |  | MBT Project-251 | Nangarhar Demining Project-04 | DOS |  |  |  | 1393 |  | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} | , | Low | Infrastructure | High | 119 | CHA | 4 |  |  | 2012-10-03 16:30 | No | Pledged
East | Nangarhar | Acheen | Bandar Kholeh | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} | c0a8-00f6-13ad5992691-8db4fed7-4570-a | Hz-ID-17314 | MCPA - Mine Clearance Planning Agency | AF/0810/09175/MF0047 | 63633 | 70.765 | 34.0883 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} |  | Low | Critical Infrastracture | High | 819 | CHA | 4 |  |  | 2012-10-03 16:30 | No | Pledged
East | Nangarhar | Acheen | Bandar Kholeh | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} | c0a8-00f6-13ad5aa7aa5-8362a597-46b3-e | Hz-ID-17316 | MCPA - Mine Clearance Planning Agency | AF/0810/09175/MF0049 | 146348 | 70.775 | 34.0935 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {22DF9BD3-F39A-484D-B670-9817A0C6B44E} |  | Low | Infrastructure | High | 744 | CHA | 4 |  |  | 2012-10-09 16:30 | No | Pledged
East | Nangarhar | Acheen | Goshtal | {739F26C8-A357-4FA8-99BE-E8D8C40DF8AC} | c0a8-0009-13b5eef7c91-803541b9-2857-f | Hz-ID-17350 | MCPA - Mine Clearance Planning Agency | AF/0810/09188/MF0035 | 37811 | 70.7017 | 34.0794 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {739F26C8-A357-4FA8-99BE-E8D8C40DF8AC} |  | Low | Critical Infrastracture | High | 1547 | CHA | 4 |  |  | 2012-09-23 16:30 | No | Pledged
East | Nangarhar | Acheen | Khogakhel | {574A74B0-8113-4D34-A4BF-53FE5941A538} | c0a8-0009-13b5efcfd21-76a33308-2895-7 | Hz-ID-17428 | MCPA - Mine Clearance Planning Agency | AF/0810/09204/MF0039 | 125297 | 70.7454 | 34.152 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes | 2014-08-26 | 2014-09-30 | 1393 | MDC | {574A74B0-8113-4D34-A4BF-53FE5941A538} |  | Low | Critical Infrastracture | High | 0 | CHA | 5 |  |  | 2012-09-26 16:30 | No | Planned
East | Nangarhar | Acheen | Khogakhel | {574A74B0-8113-4D34-A4BF-53FE5941A538} | c0a8-0009-13b8352c9db-b1e28e4-69-14f7 | Hz-ID-17467 | MCPA - Mine Clearance Planning Agency | AF/0810/09204/MF0040 | 150129 | 70.7454 | 34.152 | Open | AT Only | AT Only | MineField |  | MBT Project-251 | Nangarhar Demining Project-04 | DOS |  |  |  | 1393 |  | {574A74B0-8113-4D34-A4BF-53FE5941A538} | , | Low | Critical Infrastracture | High | 0 | CHA | 4 |  |  | 2012-09-24 16:30 | No | Pledged
East | Nangarhar | Acheen | Khogakhel | {574A74B0-8113-4D34-A4BF-53FE5941A538} | c0a8-00f6-13a917b3537-fc2d100b-528-8a | Hz-ID-17308 | MCPA - Mine Clearance Planning Agency | AF/0810/09204/MF0038 | 155644 | 70.7489 | 34.1533 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes | 2014-08-16 | 2014-09-30 | 1393 | MDC | {574A74B0-8113-4D34-A4BF-53FE5941A538} |  | Low | Critical Infrastracture | High | 0 | CHA | 5 |  |  | 2012-09-29 16:30 | No | Planned
East | Nangarhar | Acheen | Pakhel (2) | {2084E68A-D59E-4F04-B727-86D2EF2D600E} | c0a8-0009-13b837bab6d-b564a861-26c-4b | Hz-ID-17469 | MCPA - Mine Clearance Planning Agency | AF/0810/09198/MF0042 | 29829 | 70.7237 | 34.1248 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {2084E68A-D59E-4F04-B727-86D2EF2D600E} |  | Medium | Critical Infrastracture | High | 304 | CHA | 3 |  |  | 2012-09-22 16:30 | No | Pledged
East | Nangarhar | Acheen | Shekhmarkhel | {118CD1D3-59D1-4587-91BB-800FE2152803} | c0a8-0009-13b8329e033-beaa3bee-93c-3f | Hz-ID-17466 | MCPA - Mine Clearance Planning Agency | AF/0810/09209/MF0037 | 131872 | 70.7391 | 34.1463 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {118CD1D3-59D1-4587-91BB-800FE2152803} |  | Low | Critical Infrastracture | High | 427 | CHA | 4 |  |  | 2012-10-13 16:30 | No | Pledged
East | Nangarhar | Acheen | Shekhmarkhel | {118CD1D3-59D1-4587-91BB-800FE2152803} | c0a8-00f6-13ad5855a15-5bf4c491-4448-8 | Hz-ID-17310 | MCPA - Mine Clearance Planning Agency | AF/0810/09209/MF0036 | 95253 | 70.7371 | 34.1452 | Open | AT Only | AT Only | MineField |  | MBT Project-251 | Nangarhar Demining Project-04 | DOS |  |  |  | 1393 |  | {118CD1D3-59D1-4587-91BB-800FE2152803} | , | Medium | Critical Infrastracture | High | 427 | CHA | 3 |  |  | 2012-10-15 16:30 | No | Pledged
East | Nangarhar | Acheen | Shekhmarkhel | {118CD1D3-59D1-4587-91BB-800FE2152803} | c0a8-00f6-13ad5887465-14f4a789-44a1-c | Hz-ID-17311 | MCPA - Mine Clearance Planning Agency | AF/0810/09209/MF0041 | 97660 | 70.7371 | 34.1452 | Open | AT Only | AT Only | MineField |  | MBT Project-251 | Nangarhar Demining Project-04 | DOS |  |  |  | 1393 |  | {118CD1D3-59D1-4587-91BB-800FE2152803} | , | Medium | Critical Infrastracture | High | 427 | CHA | 3 |  |  | 2012-10-17 16:30 | No | Pledged
East | Nangarhar | Bihsud | Chora Galai (Tagab Comp) | {45D5A912-22A8-4FD5-B1E7-6B76E0768271} | c0a8-0009-14511c3bf56-827256d4-29d-96 | Hz-ID-18567 | DAFA - Demining Agency for Afghanistan | AF/0801/32585/BF0279 | 54110 | 70.5709 | 34.3591 | Open | UXO Only | UXO Only | BF |  | MBT Project-251 | Nangarhar Demining Project-04 | DOS |  |  |  | 1393 |  | {45D5A912-22A8-4FD5-B1E7-6B76E0768271} |  | Medium | Critical Infrastracture | High | 95 | CHA | 3 |  |  | 2014-03-03 16:30 | No | Pledged
East | Nangarhar | Bihsud | Kariz-e Kabir | {BD23F635-5E7C-4CC6-AB27-8685A2FA26A7} | c0a8-00f6-13923e15d00-3830a8a5-3ba1-9 | Hz-ID-17181 | MCPA - Mine Clearance Planning Agency | AF/0821/09391/BF0274 | 152 | 70.5305 | 34.3778 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {BD23F635-5E7C-4CC6-AB27-8685A2FA26A7} |  | High with Victim | High with Victims | High | 806 | CHA | 2 |  |  | 2012-07-10 16:30 | No | Pledged
East | Nangarhar | Bihsud | Kariz-e Kabir | {BD23F635-5E7C-4CC6-AB27-8685A2FA26A7} | c0a8-00f6-13976f54da1-50f6ca3d-4ef-70 | Hz-ID-17238 | MCPA - Mine Clearance Planning Agency | AF/0809/09391/BF0275 | 5303 | 70.5038 | 34.3713 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {BD23F635-5E7C-4CC6-AB27-8685A2FA26A7} |  | High with Victim | High with Victims | High | 94 | CHA | 2 |  |  | 2012-07-14 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Aghzo Kalay | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} | c0a8-004c-13026d46e0a-b1890e76-e6b-23 | MF-HQ-10158 | MCPA - Mine Clearance Planning Agency | AF/0806/09019/MF0040 | 48108 | 70.4433 | 34.2861 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-181/B | Nangarhar Demining Project-02/B | DOS | Yes | 2013-12-30 | 2014-03-31 | 1392 | MCPA | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} |  |  |  | High | 2 | CHA | 5 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2009-02-15 | No | Complete
East | Nangarhar | Chaparhar | Aghzo Kalay | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} | c0a8-004c-13026d54e37-81ff6338-e87-6f | MF-HQ-10157 | MCPA - Mine Clearance Planning Agency | AF/0806/09019/MF0039 | 85938 | 70.4433 | 34.2861 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-181/B | Nangarhar Demining Project-02/B | DOS | Yes | 2013-12-30 | 2014-03-31 | 1392 | MCPA | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} |  |  |  | High | 53 | CHA | 5 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2009-02-14 | No | Complete
East | Nangarhar | Chaparhar | Aghzo Kalay | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} | c0a8-008e-1342d1c6a53-f9792199-49-6fb | MF-15701 | MCPA - Mine Clearance Planning Agency | AF/0806/09019/MF0208 | 92192 | 70.4403 | 34.2865 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-181/B | Nangarhar Demining Project-02/B | DOS | Yes | 2013-12-30 | 2014-03-31 | 1392 | MCPA | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} |  |  |  | High | 3 | CHA | 5 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-01-05 16:30 | No | Complete
East | Nangarhar | Chaparhar | Aghzo Kalay | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} | c0a8-008e-13454e0db9b-f81603c6-645-5a | MF-16431 | MCPA - Mine Clearance Planning Agency | AF/0806/09019/MF0210 | 63960 | 70.436 | 34.2934 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-181/B | Nangarhar Demining Project-02/B | DOS | Yes | 2013-12-01 | 2014-03-31 | 1392 | MCPA | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} |  |  |  | High | 2 | CHA | 5 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-01-05 16:30 | No | Complete
East | Nangarhar | Chaparhar | Aghzo Kalay | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} | c0a8-008e-13454e33f5e-c04ad9ca-65c-e2 | MF-16430 | MCPA - Mine Clearance Planning Agency | AF/0806/09019/MF0209 | 83839 | 70.4403 | 34.2865 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-181/B | Nangarhar Demining Project-02/B | DOS | Yes | 2013-12-01 | 2014-03-31 | 1392 | MCPA | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} |  |  |  | High | 2 | CHA | 5 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-01-05 16:30 | No | Complete
East | Nangarhar | Chaparhar | Aghzo Kalay | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} | c0a8-008e-13454e5ca18-9c9a0956-671-8b | MF-16429 | MCPA - Mine Clearance Planning Agency | AF/0806/09019/MF0207 | 79777 | 70.4393 | 34.2873 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-181/B | Nangarhar Demining Project-02/B | DOS | Yes | 2013-12-01 | 2014-03-31 | 1392 | MCPA | {373E2BD3-CD0D-4010-A6F6-A8B2657CECA2} |  |  |  | High | 2 | CHA | 5 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-01-05 16:30 | No | Complete
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-0009-13e88dc056a-5ad7d43e-436d-9 | Hz-ID-17902 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0235 | 72056 | 70.3258 | 34.3147 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {FA198158-861B-4A01-8C1D-03EAB21140A9} |  | Medium | Critical Infrastracture | High | 288 | CHA | 5 |  |  | 2013-03-28 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-0009-13e88e6c173-1e079de8-4531-3 | Hz-ID-17898 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0234 | 77782 | 70.3261 | 34.3156 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {FA198158-861B-4A01-8C1D-03EAB21140A9} |  | Medium | Critical Infrastracture | High | 205 | CHA | 5 |  |  | 2013-03-28 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-0009-13e88e8efc2-a1455160-4565-b | Hz-ID-17897 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0232 | 79143 | 70.3261 | 34.3156 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {FA198158-861B-4A01-8C1D-03EAB21140A9} |  | Medium | Critical Infrastracture | High | 0 | CHA | 5 |  |  | 2013-03-26 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-0009-13e88ec6e24-53564c7e-45f0-d | Hz-ID-17903 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0243 | 391 | 70.4417 | 34.3112 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {FA198158-861B-4A01-8C1D-03EAB21140A9} |  | Medium | Critical Infrastracture | High | 29 | CHA | 5 |  |  | 2013-03-10 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-004c-13026d7f229-b36a7b43-ea4-9e | MF-HQ-10132 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0049 | 162830 | 70.3248 | 34.2923 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {FA198158-861B-4A01-8C1D-03EAB21140A9} | East CIDA RFP Alternative Plan | Low | Agriculture Blocked | High | 108 | CHA | 4 |  |  | 2009-02-08 | No | Pledged
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-004c-13026d94dbb-ad42ae46-eb7-80 | MF-HQ-10134 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0050 | 143849 | 70.3189 | 34.275 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {FA198158-861B-4A01-8C1D-03EAB21140A9} | East CIDA RFP Alternative Plan | Low | Agriculture Blocked | High | 56 | CHA | 5 |  |  | 2009-02-10 | No | Pledged
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-004c-13026dbe6c4-41deb18a-ed0-44 | MF-HQ-10138 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0057 | 121742 | 70.3063 | 34.3067 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {FA198158-861B-4A01-8C1D-03EAB21140A9} | East CIDA RFP Alternative Plan | Low | Agriculture Blocked | High | 110 | CHA | 5 |  |  | 2009-03-10 | No | Pledged
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-0057-12c3b825d97-dcfd84df-1b1b4- | MF-EA-253 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0059 | 177682 | 70.3248 | 34.2923 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {FA198158-861B-4A01-8C1D-03EAB21140A9} | East CIDA RFP Alternative Plan | High Requested | Resettlment/Local Request | High | 140 | CHA | 4 |  |  | 2006-11-01 | No | Pledged
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-0057-12c3b825fe8-d1a61977-1b1eb- | MF-HQ-10125 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0048 | 82016 | 70.3239 | 34.3144 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {FA198158-861B-4A01-8C1D-03EAB21140A9} | East CIDA RFP Demining | High Requested | Resettlment/Local Request | High | 83 | CHA | 5 |  |  | 2009-02-05 | No | Pledged
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-0057-12c3b826304-5972d492-1b201- | MF-EA-259 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0061 | 134574 | 70.3358 | 34.3054 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {FA198158-861B-4A01-8C1D-03EAB21140A9} | East CIDA RPF Demining project | High Requested | Resettlment/Local Request | High | 130 | CHA | 4 |  |  | 2007-01-31 | No | Pledged
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-008e-1336443c9d8-1a30b05c-1d74-7 | MF-15727 | DAFA - Demining Agency for Afghanistan | AF/0806/09001/MF0222 | 56064 | 70.3213 | 34.3066 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-181/B | Nangarhar Demining Project-02/B | DOS | Yes | 2013-12-01 | 2014-03-31 | 1392 | MCPA | {FA198158-861B-4A01-8C1D-03EAB21140A9} | East CIDA RFP Demining Project |  |  | High | 287 | CHA | 1 | Yes | according to communiy required and request | 2011-01-05 16:30 | Yes | Complete
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-008e-1345f395da5-56f7b916-1ccb-c | MF-16435 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0214 | 170895 | 70.3415 | 34.3027 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {FA198158-861B-4A01-8C1D-03EAB21140A9} |  | Low | Agriculture Blocked | High | 85 | CHA | 5 |  |  | 2011-01-05 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Chine | {70095AED-8F22-4F11-B857-05E1780DAB25} | c0a8-0009-13e88dec08c-2fd947ad-439c-d | Hz-ID-17905 | MCPA - Mine Clearance Planning Agency | AF/0806/09025/MF0242 | 26918 | 70.4399 | 34.3125 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {70095AED-8F22-4F11-B857-05E1780DAB25} |  | Medium | Critical Infrastracture | High | 303 | CHA | 5 |  |  | 2013-03-14 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Dago | {AB6A0A3A-7F24-4861-89A4-20B1404F99F2} | c0a8-004c-13026de1be0-18ba15f4-efc-23 | MF-HQ-10061 | MCPA - Mine Clearance Planning Agency | AF/0806/00515/MF0027 | 121352 | 70.3169 | 34.2688 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {AB6A0A3A-7F24-4861-89A4-20B1404F99F2} |  | Low | Agriculture Blocked | High | 25 | CHA | 4 |  |  | 2009-02-04 | No | Pledged
East | Nangarhar | Chaparhar | Dago | {AB6A0A3A-7F24-4861-89A4-20B1404F99F2} | c0a8-004c-13026decc39-52326706-f15-52 | MF-HQ-10062 | MCPA - Mine Clearance Planning Agency | AF/0806/00515/MF0028 | 66979 | 70.3175 | 34.2692 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {AB6A0A3A-7F24-4861-89A4-20B1404F99F2} |  | Low | Agriculture Blocked | High | 6 | CHA | 5 |  |  | 2009-02-04 | No | Pledged
East | Nangarhar | Chaparhar | Dago | {AB6A0A3A-7F24-4861-89A4-20B1404F99F2} | c0a8-008e-132c972a3f6-a9f4660f-33ea-b | MF-15705 | DAFA - Demining Agency for Afghanistan | AF/0806/00515/MF0216 | 131173 | 70.3272 | 34.26 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {AB6A0A3A-7F24-4861-89A4-20B1404F99F2} |  | Low | Agriculture Blocked | High | 1069 | CHA | 4 |  |  | 2011-01-05 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Dawlatzi | {787C66FB-219C-43D3-B969-1F2E3D562528} | c0a8-0009-13daf7ad52f-5d3e8601-19e4-1 | Hz-ID-17725 | MCPA - Mine Clearance Planning Agency | AF/0806/09022/MF0227 | 128802 | 70.3744 | 34.3252 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes | 2014-04-01 | 2014-06-30 | 1393 | MDC | {787C66FB-219C-43D3-B969-1F2E3D562528} |  |  |  | High | 27 | CHA | 5 |  |  | 2013-01-25 16:30 | No | Planned
East | Nangarhar | Chaparhar | Dawlatzi | {787C66FB-219C-43D3-B969-1F2E3D562528} | c0a8-0009-13daf7c4780-34c6f487-1a96-1 | Hz-ID-17722 | MCPA - Mine Clearance Planning Agency | AF/0806/09022/MF0224 | 99924 | 70.3744 | 34.3252 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2014-02-16 | 2014-03-31 | 1392 | MDC | {787C66FB-219C-43D3-B969-1F2E3D562528} |  |  |  | High | 0 | CHA | 5 |  |  | 2013-01-16 16:30 | No | Planned
East | Nangarhar | Chaparhar | Dawlatzi | {787C66FB-219C-43D3-B969-1F2E3D562528} | c0a8-0009-13daf86bbe0-3ff636ee-1c8e-6 | Hz-ID-17727 | MCPA - Mine Clearance Planning Agency | AF/0806/09022/MF0229 | 20119 | 70.378 | 34.3124 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2013-11-20 | 2013-12-31 | 1392 | MDC | {787C66FB-219C-43D3-B969-1F2E3D562528} |  |  |  | High | 52 | CHA | 3 |  |  | 2013-01-26 16:30 | No | Planned
East | Nangarhar | Chaparhar | Dawlatzi | {787C66FB-219C-43D3-B969-1F2E3D562528} | c0a8-0009-13daf87cb3b-d5d48b5f-1cf3-3 | Hz-ID-17728 | MCPA - Mine Clearance Planning Agency | AF/0806/09022/MF0230 | 13876 | 70.3922 | 34.316 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2013-11-21 | 2013-12-31 | 1392 | MDC | {787C66FB-219C-43D3-B969-1F2E3D562528} |  |  |  | High | 0 | CHA | 5 |  |  | 2013-01-29 16:30 | No | Planned
East | Nangarhar | Chaparhar | Dawlatzi | {787C66FB-219C-43D3-B969-1F2E3D562528} | c0a8-0009-13daf8878d7-70a73501-1d43-2 | Hz-ID-17723 | MCPA - Mine Clearance Planning Agency | AF/0806/09022/MF0225 | 127750 | 70.3716 | 34.3191 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2013-12-01 | 2014-02-15 | 1392 | MDC | {787C66FB-219C-43D3-B969-1F2E3D562528} |  |  |  | High | 27 | CHA | 5 |  |  | 2013-01-20 16:30 | No | Planned
East | Nangarhar | Chaparhar | Dawlatzi | {787C66FB-219C-43D3-B969-1F2E3D562528} | c0a8-0009-13dc00b2e27-fad280e1-65f0-a | Hz-ID-17719 | MCPA - Mine Clearance Planning Agency | AF/0806/09022/MF0223 | 95912 | 70.3807 | 34.3341 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2014-02-21 | 2014-03-31 | 1392 | MDC | {787C66FB-219C-43D3-B969-1F2E3D562528} |  |  |  | High | 0 | CHA | 5 |  |  | 2013-01-16 16:30 | No | Planned
East | Nangarhar | Chaparhar | Dawlatzi | {787C66FB-219C-43D3-B969-1F2E3D562528} | c0a8-0009-13de864f817-d3230a18-93d2-1 | Hz-ID-17726 | MCPA - Mine Clearance Planning Agency | AF/0806/09022/MF0228 | 84254 | 70.3786 | 34.3157 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2013-10-01 | 2013-11-20 | 1392 | MDC | {787C66FB-219C-43D3-B969-1F2E3D562528} |  |  |  | High | 57 | CHA | 5 |  |  | 2013-01-29 16:30 | No | Planned
East | Nangarhar | Chaparhar | Dawlatzi | {787C66FB-219C-43D3-B969-1F2E3D562528} | c0a8-0009-13e3003978c-f48c6b45-1059-d | Hz-ID-17724 | MCPA - Mine Clearance Planning Agency | AF/0806/09022/MF0226 | 133625 | 70.3888 | 34.3159 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes |  |  | 1392 | MDC | {787C66FB-219C-43D3-B969-1F2E3D562528} |  |  |  | High | 611 | CHA | 5 |  |  | 2013-01-21 16:30 | No | Planned
East | Nangarhar | Chaparhar | Dawlatzi | {787C66FB-219C-43D3-B969-1F2E3D562528} | c0a8-0009-13f09a72b69-b06ccafa-1d89-4 | Hz-ID-17943 | MCPA - Mine Clearance Planning Agency | AF/0806/09022/MF0251 | 115332 | 70.4061 | 34.3345 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-181/B | Nangarhar Demining Project-02/B | DOS | Yes | 2013-12-01 | 2014-03-31 | 1392 | MCPA | {787C66FB-219C-43D3-B969-1F2E3D562528} |  |  |  | High | 33 | CHA | 5 |  |  | 2013-04-21 16:30 | No | Complete
East | Nangarhar | Chaparhar | Dawlatzi | {787C66FB-219C-43D3-B969-1F2E3D562528} | c0a8-0009-13f09a91605-b6386765-1ddb-7 | Hz-ID-17942 | MCPA - Mine Clearance Planning Agency | AF/0806/09022/MF0250 | 106632 | 70.4105 | 34.3417 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-181/B | Nangarhar Demining Project-02/B | DOS | Yes | 2013-12-01 | 2014-03-31 | 1392 | MCPA | {787C66FB-219C-43D3-B969-1F2E3D562528} |  |  |  | High | 10 | CHA | 5 |  |  | 2013-04-17 16:30 | No | Complete
East | Nangarhar | Chaparhar | Dawlatzi | {787C66FB-219C-43D3-B969-1F2E3D562528} | c0a8-0009-14405a4e568-3fbbfc6b-254-3b | Hz-ID-18479 | MCPA - Mine Clearance Planning Agency | AF/0806/09022/MF0254 | 153720 | 70.417 | 34.3524 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-17 | 2015-03-31 | 1393 | MCPA | {787C66FB-219C-43D3-B969-1F2E3D562528} |  | High with Victim | High with Victims | High | 9 | CHA | 5 |  |  | 2014-02-03 16:30 | No | Planned
East | Nangarhar | Chaparhar | Geratek | {6502E877-5256-4DD3-8718-63E59160CE79} | c0a8-0057-12c3b7d2cd4-625d543b-1778c- | MF-HQ-10142 | MCPA - Mine Clearance Planning Agency | AF/0806/08992/MF0055 | 9835 | 70.3462 | 34.2453 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {6502E877-5256-4DD3-8718-63E59160CE79} |  | High Requested | Resettlment/Local Request | High | 92 | CHA | 4 |  |  | 2009-03-23 | No | Pledged
East | Nangarhar | Chaparhar | Hafezan | {01419D89-1C73-43C2-9095-475458B4D57A} | c0a8-0057-12c3b8d8fc1-c96ba610-22f23- | MF-HQ-10147 | MCPA - Mine Clearance Planning Agency | AF/0806/09015/MF0035 | 126130 | 70.3563 | 34.2982 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {01419D89-1C73-43C2-9095-475458B4D57A} |  | High Requested | Resettlment/Local Request | High | 516 | CHA | 4 |  |  | 2009-02-18 | No | Pledged
East | Nangarhar | Chaparhar | Hafezan | {01419D89-1C73-43C2-9095-475458B4D57A} | c0a8-0057-12c3b8d91e3-8611286-22f3f-e | MF-HQ-10145 | MCPA - Mine Clearance Planning Agency | AF/0806/09015/MF0034 | 100144 | 70.3644 | 34.2901 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {01419D89-1C73-43C2-9095-475458B4D57A} |  | High Requested | Resettlment/Local Request | High | 516 | CHA | 4 |  |  | 2009-02-17 | No | Pledged
East | Nangarhar | Chaparhar | Hafezan | {01419D89-1C73-43C2-9095-475458B4D57A} | c0a8-0057-12c3b8d9463-5db30cf8-22f5a- | MF-HQ-10149 | MCPA - Mine Clearance Planning Agency | AF/0806/09015/MF0051 | 150746 | 70.3563 | 34.2982 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {01419D89-1C73-43C2-9095-475458B4D57A} |  | High Requested | Resettlment/Local Request | High | 52 | CHA | 5 |  |  | 2009-02-15 | No | Pledged
East | Nangarhar | Chaparhar | Hajian | {B4BFE47D-F411-439E-B304-742E90E52A94} | c0a8-0009-13dd3f49749-af193939-22c4-2 | Hz-ID-17767 | MCPA - Mine Clearance Planning Agency | AF/0806/09000/MF0233 | 21887 | 70.3273 | 34.3013 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {B4BFE47D-F411-439E-B304-742E90E52A94} |  | Low | Agriculture Blocked | High | 101 | CHA | 4 |  |  | 2013-02-12 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Kandibagh | {0BA07474-D792-470B-88B0-03F614403D14} | c0a8-0009-13dd3f46aea-6650410c-22a5-6 | Hz-ID-17761 | MCPA - Mine Clearance Planning Agency | AF/0806/09017/MF0239 | 149877 | 70.3823 | 34.2808 | Open | AT Only | AT Only | MineField |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {0BA07474-D792-470B-88B0-03F614403D14} |  | High with Victim | High with Victims | High | 1665 | CHA | 2 |  |  | 2013-02-16 16:30 | No | Open
East | Nangarhar | Chaparhar | Kandibagh | {0BA07474-D792-470B-88B0-03F614403D14} | c0a8-0009-13e7e8ab387-2ae1f789-2f11-8 | Hz-ID-17883 | MCPA - Mine Clearance Planning Agency | AF/0806/09017/BF0241 | 225 | 70.387 | 34.2886 | Open | UXO Only | UXO Only | BF |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {0BA07474-D792-470B-88B0-03F614403D14} |  | High with Victim | High with Victims | High | 977 | CHA | 2 |  |  | 2013-03-02 16:30 | No | Open
East | Nangarhar | Chaparhar | Kandibagh | {0BA07474-D792-470B-88B0-03F614403D14} | c0a8-0009-13e88fdad2f-d83d52db-4713-d | Hz-ID-17881 | MCPA - Mine Clearance Planning Agency | AF/0806/09017/BF0240 | 150 | 70.3772 | 34.2821 | Open | UXO Only | UXO Only | BF |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {0BA07474-D792-470B-88B0-03F614403D14} |  | High with Victim | High with Victims | High | 353 | CHA | 2 |  |  | 2013-03-03 16:30 | No | Open
East | Nangarhar | Chaparhar | Kariz-e Akhundzadagan | {C5FCF5B4-F74F-4805-8437-2ED1967C9D7E} | c0a8-0057-12c3b82d19d-a104f69-1b6e9-e | MF-HQ-10121 | MCPA - Mine Clearance Planning Agency | AF/0806/08998/MF0032 | 108771 | 70.354 | 34.2866 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {C5FCF5B4-F74F-4805-8437-2ED1967C9D7E} |  | High Requested | Resettlment/Local Request | High | 857 | CHA | 4 |  |  | 2009-01-14 | No | Pledged
East | Nangarhar | Chaparhar | Kariz-e Akhundzadagan | {C5FCF5B4-F74F-4805-8437-2ED1967C9D7E} | c0a8-0057-12c3b82d351-85948eb7-1b6fe- | MF-HQ-10117 | MCPA - Mine Clearance Planning Agency | AF/0806/08998/MF0029 | 184169 | 70.8509 | 34.2884 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {C5FCF5B4-F74F-4805-8437-2ED1967C9D7E} |  | High Requested | Resettlment/Local Request | High | 396 | CHA | 4 |  |  | 2009-02-10 | No | Pledged
East | Nangarhar | Chaparhar | Kariz-e Akhundzadagan | {C5FCF5B4-F74F-4805-8437-2ED1967C9D7E} | c0a8-0057-12c3b82d545-bd4dcfb2-1b712- | MF-HQ-10122 | MCPA - Mine Clearance Planning Agency | AF/0806/08998/MF0033 | 135750 | 70.3644 | 34.2901 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {C5FCF5B4-F74F-4805-8437-2ED1967C9D7E} |  | High Requested | Resettlment/Local Request | High | 516 | CHA | 4 |  |  | 2009-02-15 | No | Pledged
East | Nangarhar | Chaparhar | Kariz-e Akhundzadagan | {C5FCF5B4-F74F-4805-8437-2ED1967C9D7E} | c0a8-0057-12c3b82d6ea-ba116d41-1b726- | MF-HQ-10118 | MCPA - Mine Clearance Planning Agency | AF/0806/08998/MF0030 | 132455 | 70.3509 | 34.2884 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {C5FCF5B4-F74F-4805-8437-2ED1967C9D7E} |  | High Requested | Resettlment/Local Request | High | 396 | CHA | 4 |  |  | 2009-02-11 | No | Pledged
East | Nangarhar | Chaparhar | Kariz-e Akhundzadagan | {C5FCF5B4-F74F-4805-8437-2ED1967C9D7E} | c0a8-0057-12c3b82d88f-c583dfda-1b738- | MF-HQ-10120 | MCPA - Mine Clearance Planning Agency | AF/0806/08998/MF0031 | 127361 | 70.354 | 34.2866 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {C5FCF5B4-F74F-4805-8437-2ED1967C9D7E} |  | High Requested | Resettlment/Local Request | High | 396 | CHA | 4 |  |  | 2009-02-12 | No | Pledged
East | Nangarhar | Chaparhar | Lawangpur | {143BC49D-80B5-4E59-89D3-A73CA8DCE96A} | c0a8-0009-13e88d2e540-16b7763-4295-fd | Hz-ID-17899 | MCPA - Mine Clearance Planning Agency | AF/0806/09010/MF0244 | 40146 | 70.3787 | 34.2721 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {143BC49D-80B5-4E59-89D3-A73CA8DCE96A} |  | Medium | Critical Infrastracture | High | 119 | CHA | 5 |  |  | 2013-03-19 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Manu | {B28429EF-2D10-4489-BDBB-7C164F5F7213} | c0a8-0009-13dd3f3c4a4-651ced0c-223c-9 | Hz-ID-17763 | MCPA - Mine Clearance Planning Agency | AF/0806/08985/MF0237 | 78162 | 70.3075 | 34.2482 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {B28429EF-2D10-4489-BDBB-7C164F5F7213} |  | Low | Agriculture Blocked | High | 1471 | CHA | 4 |  |  | 2013-02-02 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Manu | {B28429EF-2D10-4489-BDBB-7C164F5F7213} | c0a8-0009-13dd3f3e437-1bafe11d-225b-c | Hz-ID-17766 | MCPA - Mine Clearance Planning Agency | AF/0806/08985/MF0236 | 117592 | 70.3075 | 34.2482 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {B28429EF-2D10-4489-BDBB-7C164F5F7213} |  | Low | Comunity Centers | High | 936 | CHA | 4 |  |  | 2013-02-02 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Manu | {B28429EF-2D10-4489-BDBB-7C164F5F7213} | c0a8-0009-13dd3f41122-af2806c9-227a-9 | Hz-ID-17762 | MCPA - Mine Clearance Planning Agency | AF/0806/08985/MF0238 | 149658 | 70.3088 | 34.2539 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {B28429EF-2D10-4489-BDBB-7C164F5F7213} |  | Low | Agriculture Blocked | High | 1471 | CHA | 4 |  |  | 2013-02-04 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Manu | {B28429EF-2D10-4489-BDBB-7C164F5F7213} | c0a8-004c-13026dfe4a9-3dc23007-f2a-f9 | MF-HQ-10041 | MCPA - Mine Clearance Planning Agency | AF/0806/08985/MF0036 | 115484 | 70.3154 | 34.2567 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes |  |  | 1393 | MCPA | {B28429EF-2D10-4489-BDBB-7C164F5F7213} |  | High Requested | Resettlment/Local Request | High | 560 | CHA | 1 | Yes | according to communiy required and request | 2009-02-02 | No | Planned
East | Nangarhar | Chaparhar | Manu | {B28429EF-2D10-4489-BDBB-7C164F5F7213} | c0a8-0057-12c3bad45d4-b71910e-36e29-b | MF-HQ-10048 | MCPA - Mine Clearance Planning Agency | AF/0806/08985/MF0037 | 105928 | 70.3154 | 34.2567 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {B28429EF-2D10-4489-BDBB-7C164F5F7213} |  | High Requested | Resettlment/Local Request | High | 560 | CHA | 4 |  |  | 2009-02-03 | No | Pledged
East | Nangarhar | Chaparhar | Manu | {B28429EF-2D10-4489-BDBB-7C164F5F7213} | c0a8-0057-12c3bad4a37-ec03cf84-36e54- | MF-HQ-10055 | MCPA - Mine Clearance Planning Agency | AF/08/06/08985/MF0038 | 109703 | 70.3088 | 34.2539 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {B28429EF-2D10-4489-BDBB-7C164F5F7213} |  | High Requested | Resettlment/Local Request | High | 535 | CHA | 4 |  |  | 2009-02-05 | No | Pledged
East | Nangarhar | Chaparhar | Patiray | {DD79C421-4C2A-4C57-8775-388B35AF370F} | c0a8-0009-13dd3f4b6ad-dba6f58e-22de-e | Hz-ID-17768 | MCPA - Mine Clearance Planning Agency | AF/0806/08999/MF0231 | 104116 | 70.3101 | 34.2865 | Open | AP Only | AP Only | MineField |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {DD79C421-4C2A-4C57-8775-388B35AF370F} |  | High with Victim | High with Victims | High | 51 | CHA | 1 |  |  | 2013-02-09 16:30 | No | Open
East | Nangarhar | Chaparhar | Patiray | {DD79C421-4C2A-4C57-8775-388B35AF370F} | c0a8-0057-12c3ba1ccdc-73f5ae33-300b9- | MF-HQ-10135 | MCPA - Mine Clearance Planning Agency | AF/0806/08999/MF0053 | 58291 | 70.3148 | 34.2893 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {DD79C421-4C2A-4C57-8775-388B35AF370F} |  | High with Victim | High with Victims | High | 152 | CHA | 5 |  |  | 2009-02-22 | No | Pledged
East | Nangarhar | Chaparhar | Patiray | {DD79C421-4C2A-4C57-8775-388B35AF370F} | c0a8-008e-1328a5fed15-4e5ef954-76d-b1 | MF-15759 | MCPA - Mine Clearance Planning Agency | AF/0806/08999/MF0211 | 78082 | 70.3148 | 34.2893 | Open | AP Only | AP Only | MineField |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {DD79C421-4C2A-4C57-8775-388B35AF370F} |  | High with Victim | High with Victims | High | 152 | CHA | 3 |  |  | 2011-01-05 16:30 | No | Open
East | Nangarhar | Chaparhar | Patiray | {DD79C421-4C2A-4C57-8775-388B35AF370F} | c0a8-008e-134560b382a-5e15bb54-9e9-61 | MF-16433 | MCPA - Mine Clearance Planning Agency | AF/0806/08999/MF0212 | 112062 | 70.3141 | 34.2854 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {DD79C421-4C2A-4C57-8775-388B35AF370F} |  | High with Victim | High with Victims | High | 155 | CHA | 5 |  |  | 2011-01-05 16:30 | No | Pledged
East | Nangarhar | Chaparhar | Spin Masjid | {792559DD-0A76-46FF-9513-029689A5C204} | c0a8-0009-13e88d5e780-9e4b0520-42c5-c | Hz-ID-17900 | MCPA - Mine Clearance Planning Agency | AF/0806/08926/MF0245 | 59292 | 70.4233 | 34.2212 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-01 | 2014-08-31 | 1393 | MCPA | {792559DD-0A76-46FF-9513-029689A5C204} |  | High with Victim | High with Victims | High | 421 | CHA | 1 |  |  | 2013-03-24 16:30 | No | Planned
East | Nangarhar | Chaparhar | Spin Masjid | {792559DD-0A76-46FF-9513-029689A5C204} | c0a8-0057-12c3baa088f-fc10fc44-34fc6- | MF-HQ-11177 | MCPA - Mine Clearance Planning Agency | AF/0806/08926/MF0218 | 205473 | 70.4445 | 34.2718 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-17 | 2014-11-15 | 1393 | MCPA | {792559DD-0A76-46FF-9513-029689A5C204} | , | High with Victim | High with Victims | High | 6 | CHA | 1 |  |  | 2009-02-08 | No | Planned
East | Nangarhar | Chaparhar | Spin Masjid | {792559DD-0A76-46FF-9513-029689A5C204} | c0a8-0057-12c3baa0ad0-eeb17c43-34fdb- | MF-HQ-11179 | MCPA - Mine Clearance Planning Agency | AF/0806/08926/MF0213 | 175364 | 70.4372 | 34.2579 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-01 | 2015-02-28 | 1393 | MCPA | {792559DD-0A76-46FF-9513-029689A5C204} |  | High with Victim | High with Victims | High | 6 | CHA | 1 |  |  | 2009-02-03 | No | Planned
East | Nangarhar | Chaparhar | Spin Masjid | {792559DD-0A76-46FF-9513-029689A5C204} | c0a8-0057-12c3baa0cd3-71c3a1e6-34ff0- | MF-HQ-10495 | MCPA - Mine Clearance Planning Agency | AF/0809/08926/MF0219 | 170698 | 70.4423 | 34.267 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-01 | 2015-02-28 | 1393 | MCPA | {792559DD-0A76-46FF-9513-029689A5C204} | , | High with Victim | High with Victims | High | 3 | CHA | 1 |  |  | 2009-02-05 | No | Planned
East | Nangarhar | Chaparhar | Spin Masjid | {792559DD-0A76-46FF-9513-029689A5C204} | c0a8-0057-12c3baa0e97-9f6531ce-3500a- | MF-HQ-10498 | MCPA - Mine Clearance Planning Agency | AF/0809/08926/MF0220 | 145100 | 70.4423 | 34.267 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-17 | 2014-10-05 | 1393 | MCPA | {792559DD-0A76-46FF-9513-029689A5C204} |  | High with Victim | High with Victims | High | 3 | CHA | 1 |  |  | 2009-02-08 | No | Planned
East | Nangarhar | Chaparhar | Spin Masjid | {792559DD-0A76-46FF-9513-029689A5C204} | c0a8-0057-12c3baa105b-8ae42cb8-35022- | MF-HQ-10500 | MCPA - Mine Clearance Planning Agency | AF/0809/08926/MF0221 | 160455 | 70.4445 | 34.2718 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-17 | 2014-10-15 | 1393 | MCPA | {792559DD-0A76-46FF-9513-029689A5C204} | , | High with Victim | High with Victims | High | 5 | CHA | 1 |  |  | 2009-02-10 | No | Planned
East | Nangarhar | Chaparhar | Spin Masjid | {792559DD-0A76-46FF-9513-029689A5C204} | c0a8-0057-12c3baa12fa-ba71918c-3503a- | MF-HQ-11178 | MCPA - Mine Clearance Planning Agency | AF/0809/08926/MF0253 | 179196 | 70.4372 | 34.2579 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-01 | 2015-02-28 | 1393 | MCPA | {792559DD-0A76-46FF-9513-029689A5C204} |  | High with Victim | High with Victims | High | 3 | CHA | 1 |  |  | 2009-02-05 | No | Planned
East | Nangarhar | Chaparhar | Sra Kala | {9CABB161-2343-4B60-A299-34451A973AD6} | c0a8-0057-12c3b82ad1d-eaa1ed97-1b532- | MF-HQ-10143 | MCPA - Mine Clearance Planning Agency | AF/0806/09016/MF0044 | 59993 | 70.3699 | 34.2975 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {9CABB161-2343-4B60-A299-34451A973AD6} |  | High with Victim | High with Victims | High | 204 | CHA | 1 |  |  | 2009-02-22 | No | Pledged
East | Nangarhar | Chaparhar | Sra Kala | {9CABB161-2343-4B60-A299-34451A973AD6} | c0a8-0057-12c3b82af00-3cd285a5-1b54c- | MF-HQ-10141 | MCPA - Mine Clearance Planning Agency | AF/0806/09016/MF0043 | 79758 | 70.3711 | 34.2985 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {9CABB161-2343-4B60-A299-34451A973AD6} |  | High with Victim | High with Victims | High | 204 | CHA | 1 |  |  | 2009-02-21 | No | Pledged
East | Nangarhar | Chaparhar | Sra Kala | {9CABB161-2343-4B60-A299-34451A973AD6} | c0a8-0057-12c3b82b298-4e16e434-1b581- | MF-HQ-10140 | MCPA - Mine Clearance Planning Agency | AF/0806/09016/MF0041 | 37776 | 70.3734 | 34.3008 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {9CABB161-2343-4B60-A299-34451A973AD6} |  | High with Victim | High with Victims | High | 228 | CHA | 1 |  |  | 2009-02-18 | No | Pledged
East | Nangarhar | Chaparhar | Sra Kala | {9CABB161-2343-4B60-A299-34451A973AD6} | c0a8-0057-12c3b82b45d-9cbbcf96-1b59b- | MF-HQ-10144 | MCPA - Mine Clearance Planning Agency | AF/0806/09016/MF0045 | 84484 | 70.3699 | 34.2975 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {9CABB161-2343-4B60-A299-34451A973AD6} |  | High with Victim | High with Victims | High | 253 | CHA | 1 |  |  | 2009-02-23 | No | Pledged
East | Nangarhar | Deh Bala | Oghz | {5142CED1-FBD1-411E-A8E3-FEB4138EBBB5} | c0a8-0009-13b3b23640b-ceee8f5e-48d3-7 | Hz-ID-17317 | MCPA - Mine Clearance Planning Agency | AF/0808/09085/BF0023 | 25 | 70.4639 | 34.0534 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {5142CED1-FBD1-411E-A8E3-FEB4138EBBB5} |  | Medium | Critical Infrastracture | High | 36 | CHA | 3 |  |  | 2012-09-13 16:30 | No | Pledged
East | Nangarhar | Deh Bala | Shpola | {DD0DEEA8-1631-4A94-B740-99240FCB2679} | c0a8-00f6-139b4be9816-48238a58-2d4f-e | Hz-ID-17254 | MCPA - Mine Clearance Planning Agency | AF/0808/08925/BF0022 | 132829 | 70.4752 | 34.1934 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {DD0DEEA8-1631-4A94-B740-99240FCB2679} | Removed from MCPA EOD plan 1391 | High with Victim | High with Victims | High | 334 | CHA | 2 |  |  | 2012-08-12 16:30 | No | Pledged
East | Nangarhar | Dur Baba | Khaca Chinga | {05F61AA9-0B34-4FC7-A183-CE68A604DA37} | c0a8-0009-13cc3064cc8-76f2aa5d-148-a7 | Hz-ID-17623 | MCPA - Mine Clearance Planning Agency | AF/0812/08874/MF0023 | 97899 | 70.9297 | 34.1546 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {05F61AA9-0B34-4FC7-A183-CE68A604DA37} |  | Low | Critical Infrastracture | Substantial | 399 | CHA | 4 |  |  | 2012-12-05 16:30 | No | Pledged
East | Nangarhar | Dur Baba | Khaca Chinga | {05F61AA9-0B34-4FC7-A183-CE68A604DA37} | c0a8-0009-13cc318c1ab-578a6ffc-35d-bd | Hz-ID-17624 | MCPA - Mine Clearance Planning Agency | AF/0812/00327/MF002 | 31252 | 71.0136 | 34.0823 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {05F61AA9-0B34-4FC7-A183-CE68A604DA37} |  | Low | Agriculture Blocked | Substantial | 63 | CHA | 5 |  |  | 2012-12-06 16:30 | No | Pledged
East | Nangarhar | Dur Baba | Khaca Chinga | {05F61AA9-0B34-4FC7-A183-CE68A604DA37} | c0a8-0009-13cc32164b3-ee3d3b68-467-a6 | Hz-ID-17621 | MCPA - Mine Clearance Planning Agency | AF/0812/08874/MF0021 | 32688 | 70.9408 | 34.1357 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {05F61AA9-0B34-4FC7-A183-CE68A604DA37} |  | Low | Infrastructure | Substantial | 321 | CHA | 5 |  |  | 2012-12-03 16:30 | No | Pledged
East | Nangarhar | Dur Baba | Khaca Chinga | {05F61AA9-0B34-4FC7-A183-CE68A604DA37} | c0a8-0009-13d0acf7075-39b1c70-3508-8f | Hz-ID-17622 | MCPA - Mine Clearance Planning Agency | AF/0812/08874/MF0022 | 34150 | 70.9462 | 34.1164 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {05F61AA9-0B34-4FC7-A183-CE68A604DA37} |  | Low | Agriculture Blocked | Substantial | 117 | CHA | 4 |  |  | 2012-12-04 16:30 | No | Pledged
East | Nangarhar | Dur Baba | Sasobi (Zangoor) | {D7EAB28F-8C9E-4D5C-9AA6-477707687B49} | c0a8-0009-13d0bd3cde3-334bdd78-36c0-4 | Hz-ID-17662 | MCPA - Mine Clearance Planning Agency | AF/0812/00827/MF0024 | 31252 | 71.0136 | 34.0823 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {D7EAB28F-8C9E-4D5C-9AA6-477707687B49} |  | Low | Agriculture Blocked | Substantial | 63 | CHA | 5 |  |  | 2012-12-06 16:30 | No | Pledged
East | Nangarhar | Dur Baba | Tawda China | {7A390CA0-A233-404F-9FEA-531F9B4C7146} | c0a8-0009-13cc2d9726a-9d782d15-8f6-c7 | Hz-ID-17626 | MCPA - Mine Clearance Planning Agency | AF/0812/08844/MF0026 | 21510 | 70.9239 | 34.1122 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {7A390CA0-A233-404F-9FEA-531F9B4C7146} |  | Low | Other | Substantial | 155 | CHA | 4 |  |  | 2012-12-05 16:30 | No | Pledged
East | Nangarhar | Dur Baba | Tawda China | {7A390CA0-A233-404F-9FEA-531F9B4C7146} | c0a8-0009-13cc3121b1e-a676835b-236-45 | Hz-ID-17625 | MCPA - Mine Clearance Planning Agency | AF/0812/08844/MF0025 | 86477 | 70.9215 | 34.1123 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {7A390CA0-A233-404F-9FEA-531F9B4C7146} |  | Low | Other | Substantial | 83 | CHA | 4 |  |  | 2012-12-03 16:30 | No | Pledged
East | Nangarhar | Dur Baba | Tawda China | {7A390CA0-A233-404F-9FEA-531F9B4C7146} | c0a8-0009-13cc3152d9b-c956847d-2db-4b | Hz-ID-17628 | MCPA - Mine Clearance Planning Agency | AF/0812/08844/MF0027 | 94239 | 70.9311 | 34.1211 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {7A390CA0-A233-404F-9FEA-531F9B4C7146} |  | Low | Other | Substantial | 15 | CHA | 4 |  |  | 2012-12-05 16:30 | No | Pledged
East | Nangarhar | Hesarak | Alikhel | {361724E3-E8A9-4F09-8201-9618C550AF37} | c0a8-008e-134078a1172-cda3a27f-179-3f | MF-16382 | ATC - Afghan Technical Consultants | AF/0803/09493/MF0068 | 19435 | 69.8158 | 34.3101 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {361724E3-E8A9-4F09-8201-9618C550AF37} | OMAR Contingency Plan 1392 | Medium | Agriculture Blocked | High | 45 | CHA | 3 |  |  | 2011-03-19 16:30 | No | Pledged
East | Nangarhar | Kama | Darbanak | {D186A9B5-CAE1-4262-B57C-0981D0733C99} | c0a8-0009-13e88073946-ae63bad0-2315-1 | Hz-ID-17891 | MCPA - Mine Clearance Planning Agency | AF/0818/09238/MF0025 | 51836 | 70.5762 | 34.4745 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {D186A9B5-CAE1-4262-B57C-0981D0733C99} |  | Low | Water Blocked | Substantial | 21 | CHA | 5 |  |  | 2013-03-23 16:30 | No | Pledged
East | Nangarhar | Kama | Mangoli | {DBB9BA05-1FF9-47EC-AA05-5C339C47B7EB} | c0a8-0009-13e87e8a80c-c784d2de-22f1-d | Hz-ID-17893 | MCPA - Mine Clearance Planning Agency | AF/0818/09273/MF0026 | 64239 | 70.6415 | 34.4537 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {DBB9BA05-1FF9-47EC-AA05-5C339C47B7EB} |  | Low | Agriculture Blocked | Substantial | 5 | CHA | 5 |  |  | 2013-03-26 16:30 | No | Pledged
East | Nangarhar | Khogayani | Ahmadkhel(Wazir) | {FB67E87A-490B-49AC-A3FB-221D21475E28} | c0a8-0057-12c3b9de47c-3808a348-2da2a- | MF-HQ-10159 | MCPA - Mine Clearance Planning Agency | AF/0805/09633/MF0084 | 2454 | 70.1644 | 34.2161 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes |  |  | 1392 | MDC | {FB67E87A-490B-49AC-A3FB-221D21475E28} |  |  |  | High | 362 | CHA | 1 |  |  | 2009-01-27 | Yes | Planned
East | Nangarhar | Khogayani | Ahmadkhel(Wazir) | {FB67E87A-490B-49AC-A3FB-221D21475E28} | c0a8-0057-12c3bb34162-e3e09c1d-3a75c- | MF-HQ-10161 | MCPA - Mine Clearance Planning Agency | AF/0805/09633/MF0085 | 1603 | 70.1642 | 34.2181 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes |  |  | 1392 | MDC | {FB67E87A-490B-49AC-A3FB-221D21475E28} |  |  |  | High | 1202 | CHA | 1 |  |  | 2009-01-28 | Yes | Planned
East | Nangarhar | Khogayani | Bar Arghach | {9614DE7F-9FF2-48B2-B869-96A56B112D43} | c0a8-0009-13c7f75b1d4-819ff908-6f43-f | Hz-ID-17604 | MDC - Mine Detection and Dog Center | AF/0805/09655/MF0263 | 183798 | 70.1928 | 34.3429 | Closed | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2013-10-01 | 2013-12-31 | 1392 | MDC | {9614DE7F-9FF2-48B2-B869-96A56B112D43} |  |  |  | High | 913 | CHA | 5 |  |  | 2012-12-10 16:30 | No | Planned
East | Nangarhar | Khogayani | Bar Arghach | {9614DE7F-9FF2-48B2-B869-96A56B112D43} | c0a8-0009-14511d934ba-875385b2-2ce-f6 | Hz-ID-18568 | MDC - Mine Detection and Dog Center | AF/0805/09655/MF0276 | 109472 | 70.1887 | 34.3304 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes | 2014-07-06 | 2014-08-14 | 1393 | MDC | {9614DE7F-9FF2-48B2-B869-96A56B112D43} |  | Low | Agriculture Blocked | High | 36 | CHA | 5 |  |  | 2014-02-24 16:30 | No | Planned
East | Nangarhar | Khogayani | Bar Arghach | {9614DE7F-9FF2-48B2-B869-96A56B112D43} | c0a8-008e-133a5967981-c8e030de-44c-b7 | MF-16351 | MCPA - Mine Clearance Planning Agency | AF/0805/09655/MF0117 | 14952 | 70.1926 | 34.2796 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {9614DE7F-9FF2-48B2-B869-96A56B112D43} | OMAR Contingency Plan 1392 | High Requested | Resettlment/Local Request | High | 276 | CHA | 1 | Yes | Chimtala Emigrants town | 2011-09-19 16:30 | No | Pledged
East | Nangarhar | Khogayani | Lokhay | {2AECD18F-F099-4800-9133-8896754C7BB5} | c0a8-0009-13dd3f37b80-cb1de1b6-2223-7 | Hz-ID-17758 | MCPA - Mine Clearance Planning Agency | AF/0805/09681/MF0266 | 155057 | 70.1911 | 34.3383 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2014-01-01 | 2014-03-10 | 1392 | MDC | {2AECD18F-F099-4800-9133-8896754C7BB5} |  |  |  | High | 827 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2013-02-13 16:30 | No | Planned
East | Nangarhar | Kot | Anarkhel | {458EA248-403D-4499-BD91-B43CC917664D} | c0a8-0009-13aedc9d3de-84798e1d-28-fce | Hz-ID-17357 | MCPA - Mine Clearance Planning Agency | AF/0809/08954/BF0248 | 49683 | 70.6573 | 34.2142 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {458EA248-403D-4499-BD91-B43CC917664D} |  | Medium | Critical Infrastracture | Substantial | 270 | CHA | 3 |  |  | 2012-09-15 16:30 | No | Pledged
East | Nangarhar | Kot | Hayderkhel | {B54A23D2-CFE6-40C1-9AB4-098397174E35} | c0a8-0009-13ade9037a4-ee12674f-896-a4 | Hz-ID-17320 | MCPA - Mine Clearance Planning Agency | AF/0809/08919/MF0244 | 156899 | 70.6518 | 34.1805 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2013-01-03 | 2013-04-30 | 1392 | MDC | {B54A23D2-CFE6-40C1-9AB4-098397174E35} |  |  |  | Substantial | 6 | CHA | 5 |  |  | 2012-09-13 16:30 | No | Planned
East | Nangarhar | Kot | Hayderkhel | {B54A23D2-CFE6-40C1-9AB4-098397174E35} | c0a8-0009-13adebeee1e-7758bba9-d55-8a | Hz-ID-17352 | MCPA - Mine Clearance Planning Agency | AF/0809/08919/MF0245 | 173278 | 70.6691 | 34.1784 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2013-09-21 | 2013-10-03 | 1392 | MDC | {B54A23D2-CFE6-40C1-9AB4-098397174E35} |  |  |  | Substantial | 25 | CHA | 5 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2012-09-08 16:30 | No | Planned
East | Nangarhar | Kot | Hayderkhel | {B54A23D2-CFE6-40C1-9AB4-098397174E35} | c0a8-0009-13adebf64f3-8669e277-d74-10 | Hz-ID-17354 | MCPA - Mine Clearance Planning Agency | AF/0809/08919/MF0247 | 186600 | 70.6691 | 34.1784 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2013-05-01 | 2013-08-19 | 1392 | MDC | {B54A23D2-CFE6-40C1-9AB4-098397174E35} |  |  |  | Substantial | 308 | CHA | 5 |  |  | 2012-09-18 16:30 | No | Planned
East | Nangarhar | Kot | Hayderkhel | {B54A23D2-CFE6-40C1-9AB4-098397174E35} | c0a8-0009-14037fb0232-b0895af0-2dd3-9 | Hz-ID-18089 | MDC - Mine Detection and Dog Center | AF/0809/08919/MF0249 | 72317 | 70.6495 | 34.1816 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2014-01-21 | 2014-02-20 | 1392 | MDC | {B54A23D2-CFE6-40C1-9AB4-098397174E35} |  |  |  | Substantial | 105 | CHA | 4 |  |  | 2013-07-20 16:30 | No | Planned
East | Nangarhar | Kot | Hayderkhel | {B54A23D2-CFE6-40C1-9AB4-098397174E35} | c0a8-0009-14037fb8a06-8cc65d65-2df1-3 | Hz-ID-18090 | MDC - Mine Detection and Dog Center | AF/0809/08919/MF0250 | 135104 | 70.6535 | 34.1804 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2013-11-04 | 2014-01-30 | 1392 | MDC | {B54A23D2-CFE6-40C1-9AB4-098397174E35} |  |  |  | Substantial | 134 | CHA | 4 |  |  | 2013-07-20 16:30 | No | Planned
East | Nangarhar | Kot | Hayderkhel | {B54A23D2-CFE6-40C1-9AB4-098397174E35} | c0a8-0009-14495e8c5ec-26698a0b-e7b-d3 | Hz-ID-18512 | MDC - Mine Detection and Dog Center | AF/0809/08919/MF0251 | 41583 | 70.6518 | 34.1888 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes |  |  | 1393 | MDC | {B54A23D2-CFE6-40C1-9AB4-098397174E35} |  |  |  | Substantial | 195 | CHA | 3 |  |  | 2014-02-01 16:30 | No | Planned
East | Nangarhar | Kot | Hayderkhel | {B54A23D2-CFE6-40C1-9AB4-098397174E35} | c0a8-0009-14495ea966f-bec9cd2-e93-ee0 | Hz-ID-18513 | MDC - Mine Detection and Dog Center | AF/0809/08919/MF0252 | 48016 | 70.6518 | 34.1888 | Closed | Mixed | Mixed AT UXO | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes |  |  | 1393 | MDC | {B54A23D2-CFE6-40C1-9AB4-098397174E35} |  |  |  | Substantial | 195 | CHA | 3 |  |  | 2014-02-01 16:30 | No | Planned
East | Nangarhar | Kot | Hayderkhel | {B54A23D2-CFE6-40C1-9AB4-098397174E35} | c0a8-0009-145da3ef319-5e1aac21-eba-e0 | Hz-ID-18693 | MDC - Mine Detection and Dog Center | AF/0809/08919/MF0253 | 58675 | 70.6513 | 34.1868 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes |  |  | 1393 | MDC | {B54A23D2-CFE6-40C1-9AB4-098397174E35} |  | Low | Comunity Centers | Substantial | 194 | CHA | 4 |  |  | 2014-05-01 16:30 | No | Planned
East | Nangarhar | Kot | Hayderkhel | {B54A23D2-CFE6-40C1-9AB4-098397174E35} | c0a8-0009-145da4fce92-834f52cf-f0c-1d | Hz-ID-18694 | MDC - Mine Detection and Dog Center | AF/0809/08919/MF0254 | 121322 | 70.6509 | 34.1809 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes | 2014-07-01 | 2014-08-25 | 1393 | MDC | {B54A23D2-CFE6-40C1-9AB4-098397174E35} |  | Low | Critical Infrastracture | Substantial | 72 | CHA | 5 |  |  | 2014-05-01 16:30 | No | Planned
East | Nangarhar | Kot | Hayderkhel | {B54A23D2-CFE6-40C1-9AB4-098397174E35} | c0a8-0009-145da5338e7-86f94d65-f3b-b0 | Hz-ID-18695 | MDC - Mine Detection and Dog Center | AF/0809/8919/MF0255 | 140855 | 70.6548 | 34.1801 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes | 2014-09-04 | 2014-09-30 | 1393 | MDC | {B54A23D2-CFE6-40C1-9AB4-098397174E35} |  | Medium | Critical Infrastracture | Substantial | 2 | CHA | 3 |  |  | 2014-05-01 16:30 | No | Planned
East | Nangarhar | Kot | Metrani | {1176DC14-FF6D-4171-BA68-2C26BEA54E64} | c0a8-00f6-13923b6f1b1-b7efad96-38dc-7 | Hz-ID-17185 | MCPA - Mine Clearance Planning Agency | AF/0809/08936/MF0228 | 99879 | 70.6347 | 34.205 | Closed | AT Only | AT Only | MineField | Blank | MBT Project-044 | Nangarhar Demining Project-01 | DOS | No |  |  | 1392 | None | {1176DC14-FF6D-4171-BA68-2C26BEA54E64} |  |  |  | Substantial | 576 | CHA | 4 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2012-07-30 16:30 | No | Planned
East | Nangarhar | Kot | Metrani | {1176DC14-FF6D-4171-BA68-2C26BEA54E64} | c0a8-00f6-13923d3ea75-f6f796ba-3a79-a | Hz-ID-17200 | MCPA - Mine Clearance Planning Agency | AF/0809/08936/MF0233 | 9661 | 70.6335 | 34.1981 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2014-01-21 | 2014-01-25 | 1392 | MDC | {1176DC14-FF6D-4171-BA68-2C26BEA54E64} |  |  |  | Substantial | 289 | CHA | 3 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2012-07-31 16:30 | No | Planned
East | Nangarhar | Kot | Purshakhel | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} | c0a8-00f6-139b506e5cb-3a8ff284-3104-f | Hz-ID-17250 | MCPA - Mine Clearance Planning Agency | AF/0822/08916/MF0239 | 147082 | 70.514 | 34.0924 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} |  | High with Victim | High with Victims | Substantial | 288 | CHA | 5 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2012-08-06 16:30 | No | Pledged
East | Nangarhar | Kot | Purshakhel | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} | c0a8-00f6-13a3aee5a30-5d2d2e7-102cd-6 | Hz-ID-17251 | MCPA - Mine Clearance Planning Agency | AF/0809/08916/MF0240 | 200320 | 70.5169 | 34.1047 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} |  | High with Victim | High with Victims | Substantial | 424 | CHA | 3 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2012-08-05 16:30 | No | Pledged
East | Nangarhar | Kuz Kunar | Loy Tangay | {6AF9D7FD-1F83-44C1-807A-CF0C9BC49AC2} | c0a8-0009-13dce89e10f-1de69bcc-ed-a32 | Hz-ID-17764 | MCPA - Mine Clearance Planning Agency | AF/0819/10720/MF0066 | 4817 | 70.7117 | 34.533 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {6AF9D7FD-1F83-44C1-807A-CF0C9BC49AC2} |  | Medium | Small Hazards | Substantial | 2 | CHA | 5 |  |  | 2013-02-13 16:30 | No | Pledged
East | Nangarhar | Lal Por | Kama Daka | {D4B10A60-7223-40F3-9D56-BA66306EF84E} | c0a8-0009-14241a20e11-a69a975b-3e25-9 | Hz-ID-18209 | MCPA - Mine Clearance Planning Agency | AF/0815/32377/BF0001 | 53739 | 71.1204 | 34.2274 | Open | UXO Only | UXO Only | BF |  | MBT Project-251 | Nangarhar Demining Project-04 | DOS |  |  |  | 1393 |  | {D4B10A60-7223-40F3-9D56-BA66306EF84E} |  | Low | Infrastructure | Substantial | 7 | CHA | 5 |  |  | 2013-09-28 16:30 | No | Pledged
East | Nangarhar | Muhmand Dara | Daga | {47717AC7-302C-4DEE-8796-4535CDF84D7D} | c0a8-003c-13063ab3eb3-37503494-2b1-1f | MF-HQ-10036 | MCPA - Mine Clearance Planning Agency | AF/0814/09038/MF041 | 86000 | 71.1037 | 34.2021 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {47717AC7-302C-4DEE-8796-4535CDF84D7D} |  | High with Victim | High with Victims | Substantial | 4 | CHA | 2 |  |  | 2009-03-30 | No | Pledged
East | Nangarhar | Muhmand Dara | Daga | {47717AC7-302C-4DEE-8796-4535CDF84D7D} | c0a8-00f6-135523fe9e4-75353392-502-d0 | MF-16684 | MCPA - Mine Clearance Planning Agency | AF/0814/09038/MF0053 | 57864 | 71.1037 | 34.2021 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-17 | 2014-11-17 | 1393 | MCPA | {47717AC7-302C-4DEE-8796-4535CDF84D7D} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 2 |  |  | 2011-12-13 16:30 | No | Planned
East | Nangarhar | Muhmand Dara | Daga | {47717AC7-302C-4DEE-8796-4535CDF84D7D} | c0a8-00f6-135565d6e8b-6f2dcbf6-523-a8 | MF-16690 | MCPA - Mine Clearance Planning Agency | AF/0814/09038/MF0054 | 64463 | 71.1074 | 34.1929 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes |  |  | 1393 | MCPA | {47717AC7-302C-4DEE-8796-4535CDF84D7D} |  | High with Victim | High with Victims | Substantial | 7 | CHA | 2 |  |  | 2011-12-15 16:30 | No | Planned
East | Nangarhar | Nazyan | Damah | {EF186355-2661-421B-8AC9-70AF0549B2A7} | c0a8-0057-12c3ba6e667-12c42ccf-33262- | MF-HQ-13766 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0811/00740/MF0025 | 31900 | 70.8706 | 34.0043 | Open | AP Only | AP Only | Converted From SHA | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {EF186355-2661-421B-8AC9-70AF0549B2A7} | OMAR Contingency Plan 1392 | High Requested | Resettlment/Local Request | Substantial | 140 | SHA | 4 |  |  | 2009-12-05 | No | Pledged
East | Nangarhar | Nazyan | Karmo Khail | {2A792323-DE3A-474B-8EB6-61AEF91DBD52} | c0a8-0057-12c3b83def2-f8f08313-1c2ee- | MF-HQ-10632 | MCPA - Mine Clearance Planning Agency | AF/0811/00119/MF0008 | 63589 | 70.8508 | 34.0152 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {2A792323-DE3A-474B-8EB6-61AEF91DBD52} |  | High Requested | Resettlment/Local Request | Substantial | 353 | CHA | 4 |  |  | 2009-03-08 | No | Pledged
East | Nangarhar | Nazyan | Karmo Khail | {2A792323-DE3A-474B-8EB6-61AEF91DBD52} | c0a8-0057-12c3b83e0c6-6e34954f-1c308- | MF-HQ-10635 | MCPA - Mine Clearance Planning Agency | AF/0811/00119/MF0011 | 69976 | 70.8584 | 34.0179 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {2A792323-DE3A-474B-8EB6-61AEF91DBD52} | OMAR Contingency Plan 1392 | High Requested | Resettlment/Local Request | Substantial | 287 | CHA | 4 |  |  | 2009-05-13 | No | Pledged
East | Nangarhar | Nazyan | Lalmay | {9A1DBBF4-C27A-4B36-AEB0-70E356FF10F9} | c0a8-0057-12c3b8ac22e-7cc98fe8-21048- | MF-HQ-13763 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0811/09069/MF0024 | 43000 | 70.8098 | 34.0239 | Open | AP Only | AP Only | Converted From SHA | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {9A1DBBF4-C27A-4B36-AEB0-70E356FF10F9} | OMAR Contingency Plan 1392 | High Requested | Resettlment/Local Request | Substantial | 54 | SHA | 6 |  |  | 2009-12-05 | No | Pledged
East | Nangarhar | Nazyan | Murchal | {867D80B0-FFA6-4389-85A6-E6276A51205D} | c0a8-0057-12c3ba1c6f3-a03c4d75-30075- | MF-HQ-11252 | MCPA - Mine Clearance Planning Agency | AF/0811/09074/MF0021 | 91900 | 70.822 | 34.0443 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {867D80B0-FFA6-4389-85A6-E6276A51205D} | OMAR Contingency Plan 1392 | High Requested | Resettlment/Local Request | Substantial | 12 | CHA | 5 |  |  | 2009-03-15 | No | Pledged
East | Nangarhar | Nazyan | Murchal | {867D80B0-FFA6-4389-85A6-E6276A51205D} | c0a8-0057-12c3ba1c905-4964ccda-3008d- | MF-HQ-11191 | MCPA - Mine Clearance Planning Agency | AF/0811/09074/MF0022 | 99856 | 70.822 | 34.0443 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {867D80B0-FFA6-4389-85A6-E6276A51205D} |  | High Requested | Resettlment/Local Request | Substantial | 5 | CHA | 5 |  |  | 2009-03-17 | No | Pledged
East | Nangarhar | Nazyan | Shar Moukhail (Sharmoukhai) | {D2E3C46F-8C9E-4F34-9355-2DBDA07ACFEB} | c0a8-0057-12c3bb40376-abcb883d-3ae8f- | MF-HQ-11245 | MCPA - Mine Clearance Planning Agency | AF/0811/00652/MF0014 | 71380 | 70.8218 | 34.103 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {D2E3C46F-8C9E-4F34-9355-2DBDA07ACFEB} |  | High Requested | Resettlment/Local Request | Substantial | 3 | CHA | 1 | Yes | according to communiy required and request | 2009-03-14 | No | Pledged
East | Nangarhar | Nazyan | Shar Moukhail (Sharmoukhai) | {D2E3C46F-8C9E-4F34-9355-2DBDA07ACFEB} | c0a8-0057-12c3bb40634-5c566307-3aea5- | MF-HQ-11249 | MCPA - Mine Clearance Planning Agency | AF/0811/00652/MF0030 | 92625 | 70.8141 | 34.0973 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {D2E3C46F-8C9E-4F34-9355-2DBDA07ACFEB} |  | High Requested | Resettlment/Local Request | Substantial | 61 | CHA | 1 | Yes | according to communiy required and request | 2009-03-08 | No | Pledged
East | Nangarhar | Nazyan | Shar Moukhail (Sharmoukhai) | {D2E3C46F-8C9E-4F34-9355-2DBDA07ACFEB} | c0a8-0057-12c3bb40895-bde6e6a6-3aebc- | MF-HQ-11250 | MCPA - Mine Clearance Planning Agency | AF/0811/00652/MF0013 | 85370 | 70.8141 | 34.0973 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {D2E3C46F-8C9E-4F34-9355-2DBDA07ACFEB} |  | High Requested | Resettlment/Local Request | Substantial | 17 | CHA | 1 | Yes | according to communiy required and request | 2009-03-11 | No | Pledged
East | Nangarhar | Pachier Agam | Bamokhel | {A01F4317-B19E-4DE9-A745-792891334357} | c0a8-008e-1328f85e2d0-65d976f4-1447-4 | MF-16204 | MCPA - Mine Clearance Planning Agency | AF/0807/09695/MF0035 | 99840 | 70.2546 | 34.1952 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {A01F4317-B19E-4DE9-A745-792891334357} |  | High Requested | Resettlment/Local Request | High | 702 | CHA | 3 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-07-28 16:30 | No | Open
East | Nangarhar | Pachier Agam | Bamokhel | {A01F4317-B19E-4DE9-A745-792891334357} | c0a8-008e-1328fab3591-d7d897fe-21c0-2 | MF-16207 | MCPA - Mine Clearance Planning Agency | AF/0807/09695/MF0038 | 91000 | 70.245 | 34.1734 | Open | Mixed | Mixed AT UXO | MineField | Blank | MBT Project-201 | Nangarhar Demining Project-03 |  | No |  |  | 1393 | Blank | {A01F4317-B19E-4DE9-A745-792891334357} |  | High Requested | Resettlment/Local Request | High | 118 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-08-02 16:30 | No | Open
East | Nangarhar | Pachier Agam | Bamokhel | {A01F4317-B19E-4DE9-A745-792891334357} | c0a8-008e-1328fabfa06-24241c21-21d2-7 | MF-16206 | MCPA - Mine Clearance Planning Agency | AF/0807/09695/MF0037 | 101425 | 70.245 | 34.1734 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {A01F4317-B19E-4DE9-A745-792891334357} |  | High Requested | Resettlment/Local Request | High | 254 | CHA | 3 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-07-31 16:30 | No | Open
East | Nangarhar | Pachier Agam | Bamokhel | {A01F4317-B19E-4DE9-A745-792891334357} | c0a8-008e-1328fd6f89b-e42438ec-2a6d-b | MF-16205 | MCPA - Mine Clearance Planning Agency | AF/0807/09695/MF0036 | 97315 | 70.2546 | 34.1952 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {A01F4317-B19E-4DE9-A745-792891334357} |  | High Requested | Resettlment/Local Request | High | 702 | CHA | 3 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-08-30 16:30 | No | Open
East | Nangarhar | Pachier Agam | Bamokhel | {A01F4317-B19E-4DE9-A745-792891334357} | c0a8-008e-13478b85e4d-cb17124f-48-688 | MF-16447 | MCPA - Mine Clearance Planning Agency | AF/0807/09695/MF0041 | 50651 | 70.2428 | 34.191 | Open | AT Only | AT Only | MineField |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {A01F4317-B19E-4DE9-A745-792891334357} |  | High Requested | Resettlment/Local Request | High | 616 | CHA | 3 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-08-27 16:30 | No | Open
East | Nangarhar | Pachier Agam | Bamokhel | {A01F4317-B19E-4DE9-A745-792891334357} | c0a8-008e-13478fcfa1e-fe45a25-8e5-2ac | MF-16446 | MCPA - Mine Clearance Planning Agency | AF/0807/08981/MF0040 | 49173 | 70.2428 | 34.191 | Open | AT Only | AT Only | MineField |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {A01F4317-B19E-4DE9-A745-792891334357} |  | High Requested | Resettlment/Local Request | High | 616 | CHA | 3 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-08-24 16:30 | No | Open
East | Nangarhar | Pachier Agam | Kaki Kalay | {EC7F6E96-28F6-497E-B7ED-ED8BFAFACC88} | c0a8-0057-12c3b98fdcb-fcc3e5c6-2a7d1- | MF-HQ-12963 | MCPA - Mine Clearance Planning Agency | AF/0807/09698/MF0022 | 223146 | 70.2658 | 34.2023 | Open | AT Only | AT Only | MineField | Blank | MBT Project-201 | Nangarhar Demining Project-03 |  | No | 2010-06-02 | 2010-09-30 | 1393 | None | {EC7F6E96-28F6-497E-B7ED-ED8BFAFACC88} | The task is suspended due to security problem in the area. | High Requested | Resettlment/Local Request | High | 539 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2009-10-05 | No | Open
East | Nangarhar | Pachier Agam | Khan Kalay | {514C2CE4-9E06-4EE0-8CC3-F0DBEE2B876F} | c0a8-0009-142419f5447-9383668b-3dfb-2 | Hz-ID-18211 | MCPA - Mine Clearance Planning Agency | AF/0807/09687/BF0043 | 588932 | 70.2325 | 34.129 | Open | UXO Only | UXO Only | BF |  | MBT Project-251 | Nangarhar Demining Project-04 | DOS |  |  |  | 1393 |  | {514C2CE4-9E06-4EE0-8CC3-F0DBEE2B876F} |  | Medium | Agriculture Blocked | High | 4 | CHA | 3 |  |  | 2013-09-03 16:30 | No | Pledged
East | Nangarhar | Pachier Agam | Landikhel | {C83CB364-4925-46A2-8298-3F81FBB06D02} | c0a8-0009-141019b0bf4-419a6483-10d8-f | Hz-ID-18140 | MCPA - Mine Clearance Planning Agency | AF/0807/09701/MF0042 | 56593 | 70.264 | 34.2153 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-17 | 2014-09-20 | 1393 | MCPA | {C83CB364-4925-46A2-8298-3F81FBB06D02} |  | High with Victim | High with Victims | High | 697 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2013-07-27 16:30 | No | Planned
East | Nangarhar | Pachier Agam | Merkhani | {6EFA7E06-450F-41D6-961B-3D6A0167BC71} | c0a8-0057-12c3b99e529-9db0ad5a-2b15f- | BF-HQ-12962 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/8807/09685/BLU0021 | 1717200 | 70.2456 | 34.1013 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {6EFA7E06-450F-41D6-961B-3D6A0167BC71} | Removed from MCPA plan 1391 | High Requested | Resettlment/Local Request | High | 119 | CHA | 4 |  |  | 2009-10-05 | No | Pledged
East | Nangarhar | Pachier Agam | Morgi | {01BD714B-5A59-48A9-8440-C976080F8331} | c0a8-008e-1329e9b43ef-34dca5f1-49-231 | MF-16203 | MCPA - Mine Clearance Planning Agency | AF/0807/09693/MF0034 | 115360 | 70.2547 | 34.1723 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-01 | 2014-11-30 | 1393 | MCPA | {01BD714B-5A59-48A9-8440-C976080F8331} |  | High Requested | Resettlment/Local Request | High | 140 | CHA | 1 | Yes | according to communiy required and request | 2011-07-28 16:30 | No | Planned
East | Nangarhar | Pachier Agam | Nasir (Gari Khel) | {9780126E-7A04-4EB5-9BE9-2CF73C62EBBB} | c0a8-0009-142419c1a58-4b97633-3ddd-8b | Hz-ID-18212 | MCPA - Mine Clearance Planning Agency | AF/0807/00458/BF0044 | 713067 | 70.2367 | 34.1229 | Open | UXO Only | UXO Only | BF |  | MBT Project-251 | Nangarhar Demining Project-04 | DOS |  |  |  | 1393 |  | {9780126E-7A04-4EB5-9BE9-2CF73C62EBBB} |  | Medium | Agriculture Blocked | High | 12 | CHA | 3 |  |  | 2013-09-05 16:30 | No | Pledged
East | Nangarhar | Pachier Agam | Nasir (Gari Khel) | {9780126E-7A04-4EB5-9BE9-2CF73C62EBBB} | c0a8-0057-12c3b959214-7ba49761-28404- | MF-HQ-12961 | MCPA - Mine Clearance Planning Agency | AF/8807/00458/BF0020 | 884030 | 70.2346 | 34.1238 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {9780126E-7A04-4EB5-9BE9-2CF73C62EBBB} |  | High Requested | Resettlment/Local Request | High | 38 | CHA | 6 |  |  | 2009-10-05 | No | Pledged
East | Nangarhar | Pachier Agam | Semace | {9907B93E-75C7-46F6-81D9-7AC8FF57CA57} | c0a8-008e-132c9814da4-b7cdc04d-3648-c | MF-15997 | MCPA - Mine Clearance Planning Agency | AF/0807/08981/MF0028 | 127760 | 70.2971 | 34.2353 | Open | AT Only | AT Only | MineField |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {9907B93E-75C7-46F6-81D9-7AC8FF57CA57} |  | High Requested | Resettlment/Local Request | High | 71 | CHA | 3 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-07-04 16:30 | No | Open
East | Nangarhar | Pachier Agam | Semace | {9907B93E-75C7-46F6-81D9-7AC8FF57CA57} | c0a8-008e-13478ec1526-3d79ab7d-8c4-6b | MF-16449 | MCPA - Mine Clearance Planning Agency | AF/0807/08981/MF0039 | 59256 | 70.299 | 34.2456 | Open | AT Only | AT Only | MineField |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {9907B93E-75C7-46F6-81D9-7AC8FF57CA57} |  | High Requested | Resettlment/Local Request | High | 27 | CHA | 3 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-08-22 16:30 | No | Open
East | Nangarhar | Pachier Agam | Sra Kala (2) | {2D9DA381-FC49-4884-8829-A86E64FBB237} | c0a8-008e-1328fa60a4f-da7ed2e4-212b-8 | MF-16198 | MCPA - Mine Clearance Planning Agency | AF/0807/09696/MF0029 | 19533 | 70.275 | 34.1807 | Open | Mixed | Mixed AT UXO | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes |  |  | 1393 | MCPA | {2D9DA381-FC49-4884-8829-A86E64FBB237} |  | High Requested | Resettlment/Local Request | High | 316 | CHA | 1 | Yes | according to communiy required and request | 2011-07-24 16:30 | No | Planned
East | Nangarhar | Pachier Agam | Sra Kala (2) | {2D9DA381-FC49-4884-8829-A86E64FBB237} | c0a8-008e-13290bbf621-ad15a0c8-5e3-1a | MF-16201 | MCPA - Mine Clearance Planning Agency | AF/0807/09696/MF0032 | 31173 | 70.2788 | 34.1834 | Open | Mixed | Mixed AT UXO | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-09-21 | 2014-11-05 | 1393 | MCPA | {2D9DA381-FC49-4884-8829-A86E64FBB237} |  | High Requested | Resettlment/Local Request | High | 4652 | CHA | 1 | Yes | according to communiy required and request | 2011-07-27 16:30 | No | Planned
East | Nangarhar | Pachier Agam | Zamerkhel | {66EBC963-E5C7-468E-AF72-2A1CA02021A3} | c0a8-008e-1328fadf7dd-cd8d4adb-2238-1 | MF-16202 | MCPA - Mine Clearance Planning Agency | AF/0807/09700/MF0033 | 100000 | 70.2714 | 34.2206 | Open | Mixed | Mixed AT UXO | MineField | Blank | MBT Project-201 | Nangarhar Demining Project-03 |  | No |  |  | 1393 | None | {66EBC963-E5C7-468E-AF72-2A1CA02021A3} |  | High Requested | Resettlment/Local Request | High | 85 | CHA | 1 | Yes | according to communiy required and request | 2011-07-27 16:30 | No | Open
East | Nangarhar | Pachier Agam | Zamerkhel | {66EBC963-E5C7-468E-AF72-2A1CA02021A3} | c0a8-008e-1328fae95ce-d9c45f17-2249-2 | MF-16199 | MCPA - Mine Clearance Planning Agency | AF/0807/09700/MF0030 | 47880 | 70.287 | 34.1901 | Open | Mixed | Mixed AT UXO | MineField | 1392 | MBT Project-181 | Nangarhar Demining Project-02 |  | No |  |  | 1393 |  | {66EBC963-E5C7-468E-AF72-2A1CA02021A3} |  | High Requested | Resettlment/Local Request | High | 65 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-07-26 16:30 | No | Open
East | Nangarhar | Rodat | Charagaly, Camp-e-Muhajerin & Camp-e-Hesar Shahi | {CB6517B3-66C4-4D21-8FC7-20AED0BD769D} | c0a8-0009-143852b990a-cefbca19-46f2-a | Hz-ID-18386 | MDC - Mine Detection and Dog Center | AF/0809/00004/BF0267 | 65766 | 70.577 | 34.3296 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes | 2014-06-26 | 2014-08-15 | 1393 | MDC | {CB6517B3-66C4-4D21-8FC7-20AED0BD769D} |  | High with Victim | High with Victims | High | 10 | CHA | 2 |  |  | 2013-12-15 16:30 | No | Planned
East | Nangarhar | Rodat | Charagaly, Camp-e-Muhajerin & Camp-e-Hesar Shahi | {CB6517B3-66C4-4D21-8FC7-20AED0BD769D} | c0a8-0009-14405bc91b5-aec84bb0-47f-ed | Hz-ID-18239 | MDC - Mine Detection and Dog Center | AF/0809/00004/BF0266 | 144036 | 70.5676 | 34.3383 | Worked on | UXO Only | UXO Only | BF | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes |  |  | 1393 | MDC | {CB6517B3-66C4-4D21-8FC7-20AED0BD769D} |  | High with Victim | High with Victims | High | 41 | CHA | 3 |  |  | 2013-11-20 16:30 | No | Planned
East | Nangarhar | Rodat | Kan | {E1083C8B-35DF-4D3E-8BC4-E5977E2AE791} | c0a8-00f6-135604db523-7fca41bf-1353-b | MF-16689 | MCPA - Mine Clearance Planning Agency | AF/0809/08970/MF0247 | 22096 | 70.5088 | 34.3041 | Open | AT Only | AT Only | MineField |  | MBT Project-181 | Nangarhar Demining Project-02 |  |  |  |  | 1393 |  | {E1083C8B-35DF-4D3E-8BC4-E5977E2AE791} |  | High with Victim | High with Victims | High | 5 | CHA | 2 |  |  | 2011-12-19 16:30 | No | Open
East | Nangarhar | Rodat | Sangar | {39C8FAB3-EE8A-4254-B334-3E5BD9174535} | c0a8-0009-13f09a57065-52a1853-1cf5-95 | Hz-ID-17945 | MCPA - Mine Clearance Planning Agency | AF/0809/08961/MF0254 | 181339 | 70.6714 | 34.2607 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-181/D | Nangarhar Demining Project-02/D | DOS | Yes | 2014-01-05 | 2014-03-31 | 1392 | OMAR | {39C8FAB3-EE8A-4254-B334-3E5BD9174535} |  |  |  | High | 369 | CHA | 4 |  |  | 2013-04-25 16:30 | No | Complete
East | Nangarhar | Rodat | Sangar | {39C8FAB3-EE8A-4254-B334-3E5BD9174535} | c0a8-0009-13f09a6b724-c8b00a08-1d6a-5 | Hz-ID-17944 | MCPA - Mine Clearance Planning Agency | AF/0809/08961/MF0253 | 151568 | 70.6714 | 34.2607 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-181/D | Nangarhar Demining Project-02/D | DOS | Yes | 2014-01-05 | 2014-03-31 | 1392 | OMAR | {39C8FAB3-EE8A-4254-B334-3E5BD9174535} |  |  |  | High | 584 | CHA | 4 |  |  | 2013-04-24 16:30 | No | Complete
East | Nangarhar | Rodat | Sangar | {39C8FAB3-EE8A-4254-B334-3E5BD9174535} | c0a8-0009-13f09acb0eb-51ab1a4c-1f0d-8 | Hz-ID-17947 | MCPA - Mine Clearance Planning Agency | AF/0809/08961/MF0255 | 169087 | 70.6643 | 34.2611 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-181/D | Nangarhar Demining Project-02/D | DOS | Yes | 2014-01-05 | 2014-03-31 | 1392 | OMAR | {39C8FAB3-EE8A-4254-B334-3E5BD9174535} |  |  |  | High | 611 | CHA | 4 |  |  | 2013-04-28 16:30 | No | Complete
East | Nangarhar | Rodat | Sangar | {39C8FAB3-EE8A-4254-B334-3E5BD9174535} | c0a8-0009-13f0dea001a-f6af5485-3da-80 | Hz-ID-17948 | MCPA - Mine Clearance Planning Agency | AF/0809/08961/MF0256 | 176786 | 70.6643 | 34.2611 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-181/D | Nangarhar Demining Project-02/D | DOS | Yes | 2014-01-05 | 2014-03-31 | 1392 | OMAR | {39C8FAB3-EE8A-4254-B334-3E5BD9174535} |  |  |  | High | 2305 | CHA | 4 |  |  | 2013-04-29 16:30 | No | Complete
East | Nangarhar | Rodat | Tarilay | {487A3E65-0AB6-4CAD-9310-B9892F517134} | c0a8-0009-13fe0b9eeff-8c01244b-2e33-3 | Hz-ID-18044 | MCPA - Mine Clearance Planning Agency | AF/0809/08959/MF0263 | 112720 | 70.6352 | 34.232 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-201/A | Nangarhar Demining Project-03/A | DOS | Yes | 2013-11-27 | 2014-03-30 | 1392 | DAFA | {487A3E65-0AB6-4CAD-9310-B9892F517134} |  |  |  | High | 1 | CHA | 2 |  |  | 2013-05-27 16:30 | No | Complete
East | Nangarhar | Rodat | Tarilay | {487A3E65-0AB6-4CAD-9310-B9892F517134} | c0a8-0009-13fe0c1281f-1468b3f7-2e57-1 | Hz-ID-18045 | MCPA - Mine Clearance Planning Agency | AF/0809/08959/MF0262 | 111137 | 70.6379 | 34.2461 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-201/A | Nangarhar Demining Project-03/A | DOS | Yes | 2014-01-01 | 2014-03-30 | 1392 | DAFA | {487A3E65-0AB6-4CAD-9310-B9892F517134} |  |  |  | High | 53 | CHA | 2 |  |  | 2013-05-30 16:30 | No | Complete
East | Nangarhar | Rodat | Tarilay | {487A3E65-0AB6-4CAD-9310-B9892F517134} | c0a8-0009-13fe0dae965-68025a0c-3090-4 | Hz-ID-18057 | MCPA - Mine Clearance Planning Agency | AF/0809/08959/MF0257 | 53901 | 70.6707 | 34.2359 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-181/D | Nangarhar Demining Project-02/D | DOS | Yes | 2014-02-23 | 2014-03-31 | 1392 | OMAR | {487A3E65-0AB6-4CAD-9310-B9892F517134} |  |  |  | High | 207 | CHA | 2 |  |  | 2013-05-11 16:30 | No | Complete
East | Nangarhar | Rodat | Tarilay | {487A3E65-0AB6-4CAD-9310-B9892F517134} | c0a8-0009-14023a9bbbd-22caa860-5d2-9f | Hz-ID-18066 | MCPA - Mine Clearance Planning Agency | AF/0809/08959/MF0264 | 132265 | 70.6352 | 34.232 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-201/A | Nangarhar Demining Project-03/A | DOS | Yes | 2013-11-27 | 2014-03-30 | 1392 | DAFA | {487A3E65-0AB6-4CAD-9310-B9892F517134} |  |  |  | High | 2 | CHA | 2 |  |  | 2013-06-03 16:30 | No | Complete
East | Nangarhar | Rodat | Tarilay | {487A3E65-0AB6-4CAD-9310-B9892F517134} | c0a8-0009-14023c39270-4b9149cb-653-cb | Hz-ID-18065 | MCPA - Mine Clearance Planning Agency | AF/0809/08959/MF0261 | 76498 | 70.6292 | 34.2243 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-181/D | Nangarhar Demining Project-02/D | DOS | Yes | 2014-02-23 | 2014-03-31 | 1392 | OMAR | {487A3E65-0AB6-4CAD-9310-B9892F517134} |  |  |  | High | 5 | CHA | 2 |  |  | 2013-06-01 16:30 | No | Complete
East | Nangarhar | Rodat | Tarilay | {487A3E65-0AB6-4CAD-9310-B9892F517134} | c0a8-0009-1402931399f-b25e21ae-d60-25 | Hz-ID-18047 | MCPA - Mine Clearance Planning Agency | AF/0809/08959/MF0260 | 155606 | 70.6281 | 34.2148 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-201/A | Nangarhar Demining Project-03/A | DOS | Yes | 2013-11-27 | 2014-03-30 | 1392 | DAFA | {487A3E65-0AB6-4CAD-9310-B9892F517134} |  |  |  | High | 4 | CHA | 2 |  |  | 2013-05-28 16:30 | No | Complete
East | Nangarhar | Shinwar | Shergar | {D2217F9C-45F2-4084-A714-EDC7C38C3CAE} | c0a8-0009-13d0be1a8a5-4d9c4b65-36df-5 | Hz-ID-17663 | MCPA - Mine Clearance Planning Agency | AF/0813/08851/MF0024 | 59841 | 70.7773 | 34.1754 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-181/A | Nangarhar Demining Project-02/A | B-Germany | Yes |  |  | 1392 | MDC | {D2217F9C-45F2-4084-A714-EDC7C38C3CAE} |  |  |  | Substantial | 155 | CHA | 1 |  |  | 2012-12-16 16:30 | No | Complete
East | Nangarhar | Shinwar | Shergar | {D2217F9C-45F2-4084-A714-EDC7C38C3CAE} | c0a8-0009-13d0fab95bf-e48866de-3a7c-c | Hz-ID-17664 | MCPA - Mine Clearance Planning Agency | AF/0813/08851/MF0025 | 94127 | 70.7773 | 34.1754 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-01 | 2014-10-31 | 1393 | MCPA | {D2217F9C-45F2-4084-A714-EDC7C38C3CAE} | , | High with Victim | High with Victims | Substantial | 0 | CHA | 1 |  |  | 2012-12-12 16:30 | No | Planned
East | Nangarhar | Shinwar | Shergar | {D2217F9C-45F2-4084-A714-EDC7C38C3CAE} | c0a8-0009-13d0fb24eed-53ab807b-3ae0-3 | Hz-ID-17665 | MCPA - Mine Clearance Planning Agency | AF/0813/08851/BF0026 | 42 | 70.8201 | 34.2467 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes |  |  | 1393 | MCPA | {D2217F9C-45F2-4084-A714-EDC7C38C3CAE} | , | High with Victim | High with Victims | Substantial | 835 | CHA | 1 |  |  | 2012-12-15 16:30 | No | Planned
East | Nangarhar | Shinwar | Shergar | {D2217F9C-45F2-4084-A714-EDC7C38C3CAE} | c0a8-0009-13d0fbd1f28-6a1148de-3b15-1 | Hz-ID-17666 | MCPA - Mine Clearance Planning Agency | AF/0813/08851/MF0027 | 142934 | 70.7634 | 34.169 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2013-06-09 | 2013-09-30 | 1392 | MDC | {D2217F9C-45F2-4084-A714-EDC7C38C3CAE} |  |  |  | Substantial | 0 | CHA | 1 |  |  | 2012-12-18 16:30 | No | Planned
East | Nangarhar | Shinwar | Shergar | {D2217F9C-45F2-4084-A714-EDC7C38C3CAE} | c0a8-0009-13d0fc2fed5-9968482d-3b45-f | Hz-ID-17667 | MCPA - Mine Clearance Planning Agency | AF/0813/08851/MF0028 | 134871 | 70.7634 | 34.169 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-181/E | Nangarhar Demining Project-02/E | VTF-Australia | Yes | 2014-06-17 | 2014-12-06 | 1393 | MCPA | {D2217F9C-45F2-4084-A714-EDC7C38C3CAE} | , | High with Victim | High with Victims | Substantial | 0 | CHA | 1 |  |  | 2012-12-20 16:30 | No | Planned
East | Nangarhar | Surkh Rod | Chaharbaghe Safa | {767DEBC5-8432-4581-83A0-CAC7E95D9763} | c0a8-00f6-135522b49ce-7c7f2497-3de-1a | BF-15052 | MCPA - Mine Clearance Planning Agency | AF/0802/09393/BF0386 | 77943 | 70.3756 | 34.4057 | Open | UXO Only | UXO Only | BF | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes | 2014-03-11 | 2014-03-31 | 1392 | MDC | {767DEBC5-8432-4581-83A0-CAC7E95D9763} |  | High with Victim | High with Victims | Substantial | 76 | CHA | 1 |  |  | 2011-03-26 16:30 | No | Planned
East | Nangarhar | Surkh Rod | Fatehabad | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} | c0a8-0009-13daf866a76-6485d577-1c72-9 | Hz-ID-17730 | MCPA - Mine Clearance Planning Agency | AF/0802/09333/MF0391 | 106182 | 70.198 | 34.3526 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes |  |  | 1392 | MDC | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} |  |  |  | Substantial | 1980 | CHA | 2 |  |  | 2013-01-09 16:30 | No | Planned
East | Nangarhar | Surkh Rod | Fatehabad | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} | c0a8-0009-13df213119a-5027c858-13e-47 | Hz-ID-17729 | MCPA - Mine Clearance Planning Agency | AF/0802/09333/MF0390 | 4397 | 70.2528 | 34.3619 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} |  | High with Victim | High with Victims | Substantial | 339 | CHA | 2 |  |  | 2013-01-08 16:30 | No | Pledged
East | Nangarhar | Surkh Rod | Fatehabad | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} | c0a8-0009-1440619260e-4d6396e6-819-ef | Hz-ID-18482 | MDC - Mine Detection and Dog Center | AF/0802/09333/MF0394 | 5773 | 70.226 | 34.3679 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes |  |  | 1393 | MDC | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} |  |  |  | Substantial | 943 | CHA | 1 |  |  | 2014-01-20 16:30 | No | Planned
East | Nangarhar | Surkh Rod | Fatehabad | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} | c0a8-0009-1440685a9c1-2ff87176-a91-91 | Hz-ID-18487 | MDC - Mine Detection and Dog Center | AF/0802/09333/MF0396 | 161919 | 70.2002 | 34.3603 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes | 2014-05-01 | 2014-07-05 | 1393 | MDC | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} |  | High with Victim | High with Victims | Substantial | 52 | CHA | 1 |  |  | 2014-01-27 16:30 | No | Planned
East | Nangarhar | Surkh Rod | Fatehabad | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} | c0a8-0009-1441103897f-8923a628-349f-c | Hz-ID-18485 | MDC - Mine Detection and Dog Center | AF/0802/09333/MF0395 | 65750 | 70.211 | 34.3595 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-044/A | Nangarhar Demining Project-01/A | DOS | Yes | 2014-04-01 | 2014-05-31 | 1393 | MDC | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} |  |  |  | Substantial | 1755 | CHA | 1 |  |  | 2014-01-22 16:30 | No | Planned
East | Nangarhar | Surkh Rod | Fatehabad | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} | c0a8-0009-14511de937a-c72d6963-2ee-4e | Hz-ID-18571 | MDC - Mine Detection and Dog Center | AF/0802/09333/MF0397 | 162998 | 70.1984 | 34.3595 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-251 | Nangarhar Demining Project-04 | DOS |  |  |  | 1393 |  | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} |  | High with Victim | High with Victims | Substantial | 878 | CHA | 1 |  |  | 2014-02-17 16:30 | No | Pledged
East | Nangarhar | Surkh Rod | Fatehabad | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} | c0a8-0009-1451275cd22-56ccdb99-32d-dc | Hz-ID-18572 | MDC - Mine Detection and Dog Center | AF/0802/09333/MF0398 | 206830 | 70.1935 | 34.3625 | Open | AT Only | AT Only | MineField |  | MBT Project-251 | Nangarhar Demining Project-04 | DOS |  |  |  | 1393 |  | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} |  | High with Victim | High with Victims | Substantial | 52 | CHA | 1 |  |  | 2014-02-19 16:30 | No | Pledged
East | Nangarhar | Surkh Rod | Fatehabad | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} | c0a8-0057-12c3b6fdea8-3fe8f46b-da90-3 | MF-HQ-14766 | MCPA - Mine Clearance Planning Agency | AF/0802/09333/MF0364 | 100000 | 70.1756 | 34.3395 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-044 | Nangarhar Demining Project-01 | DOS | Yes |  |  | 1392 | MDC | {93FA0CD4-509B-4AC2-9545-3382237C5D9A} |  |  |  | Substantial | 82 | CHA | 2 |  |  | 2010-08-09 | No | Planned
East | Nangarhar | Surkh Rod | Naghrak | {9AB78C8B-DD50-46E7-8F68-EE5A8FB1BF1A} | c0a8-0057-12c3b771658-7629181f-1310e- | MF-HQ-14634 | MCPA - Mine Clearance Planning Agency | AF/0802/08823/MF0332 | 460 | 70.3839 | 34.4344 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-251 | Nangarhar Demining Project-04 | DOS | No |  |  | 1393 | WRA | {9AB78C8B-DD50-46E7-8F68-EE5A8FB1BF1A} |  | High | Water Blocked | Substantial | 0 | CHA | 3 |  |  | 2010-04-19 | No | Pledged
East | Nuristan | Kamdesh | Kamdesh | {BB7E492E-3163-4F61-9B15-2D44E289F27C} | c0a8-0057-12c3b86844e-b00e9456-1e100- | MF-HQ-11058 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3002/10632/MF002 | 1800450 | 71.3338 | 35.4083 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-200 | Nuristan Demining Project-01 |  |  |  |  | 1396 |  | {BB7E492E-3163-4F61-9B15-2D44E289F27C} |  | High with Victim | High with Victims | High | 4406 | SHA | 1 |  |  | 2009-07-05 | No | Open
East | Nuristan | Kamdesh | Pule Rustam | {72DE9CFC-4C7E-4026-9A27-A70F1F24C4E3} | c0a8-0057-12c3bb7d29d-5b1127fa-3d128- | MF-HQ-11057 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3002/10635/MF001 | 200000 | 71.3199 | 35.5615 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-200 | Nuristan Demining Project-01 |  |  |  |  | 1396 |  | {72DE9CFC-4C7E-4026-9A27-A70F1F24C4E3} |  | High with Victim | High with Victims | High | 48 | SHA | 3 |  |  | 2009-07-05 | No | Open
North | Balkh | Balkh | Dandowkai (1) | {9054D9E0-C5B3-4C4F-A89E-672BBB4D65E5} | c0a8-0057-12c3b9fda59-5abe2623-2ed3d- | MF-NA-1352 | DDG - Danish Demining Group | AF/1406/14713/MF2523 | 2500 | 66.784 | 36.8359 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {9054D9E0-C5B3-4C4F-A89E-672BBB4D65E5} | Alternative plan for North CIDA RFP Demining Project 1390 | High Requested | Resettlment/Local Request | Moderate | 180 | CHA | 3 |  |  | 2009-03-01 | No | Open
North | Balkh | Balkh | Salarzai | {8B2D5E11-10FD-4574-BC33-CE0781270599} | c0a8-0057-12c3b6a4573-368071eb-9656-a | MF-HQ-13647 | DDG - Danish Demining Group | AF/1606/14733/MF0017 | 3742 | 66.7837 | 36.8683 | Open | AT Only | AT Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {8B2D5E11-10FD-4574-BC33-CE0781270599} | , | Medium | Critical Infrastracture | Moderate | 0 | CHA | 3 |  |  | 2009-11-19 | No | Open
North | Balkh | Chahar Bolak | Elman-i-Uchawna | {26B525DA-C255-49F5-8BC2-980E685E9D9B} | c0a8-0057-12e56032032-f3772b11-119-df | MF-HQ-12013 | DDG - Danish Demining Group | AF/1606/14704/MF2526 | 3000 | 66.7742 | 36.7355 | Open | AP Only | AP Only | MineField | Blank | MBT Project-038 | Balkh Demining Project-2 |  | No |  |  | 1398 | None | {26B525DA-C255-49F5-8BC2-980E685E9D9B} | Plan year and funding status updated | Medium | Critical Infrastracture | Moderate | 0 | CHA | 3 |  |  | 2009-08-10 | No | Open
North | Balkh | Chahar Bolak | Kukrak | {69EF522D-A283-4955-8C2E-E75BC16F133D} | c0a8-0057-12c3badfc64-a73fc79b-374e1- | MF-NA-1293 | DDG - Danish Demining Group | AF/1606/15256/MF2537 | 1500 | 66.7666 | 36.7375 | Open | AP Only | AP Only | MineField | Blank | MBT Project-038 | Balkh Demining Project-2 |  | No |  |  | 1398 | None | {69EF522D-A283-4955-8C2E-E75BC16F133D} | Plan year and funding status updated | High | Water Blocked | Moderate | 2585 | CHA | 3 |  |  | 2009-01-01 | No | Open
North | Balkh | Chahar Bolak | Nauwarid (10) | {BE284B1E-5095-4FAE-AB2F-181ADE116AE0} | c0a8-0057-12c3b9d97d4-dd7c8969-2d70c- | MF-NA-908 | DDG - Danish Demining Group | AF/1607/15296/MF2535 | 4000 | 66.716 | 36.8004 | Open | AP Only | AP Only | MineField | Blank | MBT Project-038 | Balkh Demining Project-2 |  | No |  |  | 1398 | None | {BE284B1E-5095-4FAE-AB2F-181ADE116AE0} | Plan year and funding status updated | Medium | Water Blocked | Moderate | 167 | CHA | 3 |  |  | 2008-06-01 | No | Open
North | Balkh | Chahar Bolak | Qizil Qala | {3E164B72-74AE-48F6-B8FB-4D1E41E67F7F} | c0a8-0057-12c3b9238c6-cf868187-2606e- | MF-NA-673 | DDG - Danish Demining Group | AF/1607/15290/MF0001 | 59410 | 66.7417 | 36.814 | Open | AP Only | AP Only | MineField | Blank | MBT Project-038 | Balkh Demining Project-2 |  | No |  |  | 1398 | None | {3E164B72-74AE-48F6-B8FB-4D1E41E67F7F} | , | Medium | Water Blocked | Moderate | 1083 | CHA | 3 |  |  | 2007-01-01 | No | Open
North | Balkh | Chahar Kint | Chahar Mahalleh | {993AE659-BAB2-42F7-9B7D-508504C895F7} | c0a8-00f6-139235a54dc-2988b87-322e-59 | Hz-ID-17167 | HT - HALO TRUST | H/8240 | 5200 | 67.1796 | 36.5193 | Closed | AT Only | AT Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes | 2012-10-01 | 2012-12-23 | 1391 | HT | {993AE659-BAB2-42F7-9B7D-508504C895F7} |  |  |  | Moderate | 7 | CHA | 5 |  |  | 2012-07-05 16:30 | No | Complete
North | Balkh | Chahar Kint | Pas Quduq | {1478BAB5-2EE6-43CF-A6DB-AEFB74D86C7D} | c0a8-0057-12c3ba40e87-4ab2b18c-3165c- | MF-NA-1285 | MCPA - Mine Clearance Planning Agency | AF/1611/14863/MF5822 | 46876 | 67.3435 | 36.3468 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {1478BAB5-2EE6-43CF-A6DB-AEFB74D86C7D} |  | Low | Agriculture Blocked | Moderate | 23 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Pas Quduq | {1478BAB5-2EE6-43CF-A6DB-AEFB74D86C7D} | c0a8-0057-12c3baebab2-5746aa2-37c31-7 | MF-HQ-10671 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1611/14863/MF0004 | 150000 | 67.462 | 36.3376 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-127 | Balkh Demining Project-3 | Bilateral | Yes |  |  | 1393 | HT | {1478BAB5-2EE6-43CF-A6DB-AEFB74D86C7D} |  | Low | Agriculture Blocked | Moderate | 4 | CHA | 5 |  |  | 2009-06-17 | No | Planned
North | Balkh | Chahar Kint | Safid Chashma | {6D074103-A3F6-408B-9C70-AB3F3764FBE6} | c0a8-0009-13b83175d5e-c904a258-309-96 | Hz-ID-17460 | MCPA - Mine Clearance Planning Agency | AF/1611/14877/MF0011 | 27250 | 67.2109 | 36.4558 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {6D074103-A3F6-408B-9C70-AB3F3764FBE6} |  | High with Victim | High with Victims | Moderate | 11 | CHA | 2 |  |  | 2012-08-28 16:30 | No | Planned
North | Balkh | Chahar Kint | Safid Chashma | {6D074103-A3F6-408B-9C70-AB3F3764FBE6} | c0a8-0009-13b83196953-c401477b-3a4-9a | Hz-ID-17461 | MCPA - Mine Clearance Planning Agency | AF/1611/14877/MF0012 | 55657 | 67.2109 | 36.4558 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {6D074103-A3F6-408B-9C70-AB3F3764FBE6} |  | High with Victim | High with Victims | Moderate | 11 | CHA | 2 |  |  | 2012-08-29 16:30 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-0057-12c3b6e821a-ede9b43c-c9f4-6 | MF-NA-1273 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF5864 | 3339 | 67.2312 | 36.2788 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Medium | Critical Infrastracture | Moderate | 36 | CHA | 3 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-0057-12c3b7443a6-75268700-10fa5- | MF-HT-99 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF3441 | 22245 | 67.2164 | 36.2873 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127 | Balkh Demining Project-3 | Bilateral | Yes |  |  | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Low | Agriculture Blocked | Moderate | 32 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-0057-12c3bad9e20-898229b3-37152- | MF-NA-1262 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF5863 | 7970 | 67.2614 | 36.2787 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Low | Agriculture Blocked | Moderate | 14 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-0057-12c3bada503-d73a8f43-3719c- | MF-HT-97 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF3428 | 803 | 67.2216 | 36.2921 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Low | Agriculture Blocked | Moderate | 116 | CHA | 5 |  |  | 2007-04-17 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-0057-12c3bada705-ab19ac6d-371af- | MF-HT-96 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF3427 | 2280 | 67.2238 | 36.2932 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Low | Agriculture Blocked | Moderate | 116 | CHA | 5 |  |  | 2007-04-06 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-0057-12c3bada918-7dfdb783-371c3- | MF-NA-1254 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF5862 | 9602 | 67.2553 | 36.274 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes | 2014-07-01 | 2014-07-23 | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-00f6-1392335f8b8-6831636-2ff7-db | Hz-ID-17188 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF0005 | 5993 | 67.2457 | 36.2986 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Low | Agriculture Blocked | Moderate | 254 | CHA | 4 |  |  | 2012-06-25 16:30 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-00f6-139233c197e-c08aeacf-306a-5 | Hz-ID-17191 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF0006 | 4170 | 67.2725 | 36.2595 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Low | Agriculture Blocked | Moderate | 26 | CHA | 5 |  |  | 2012-06-30 16:30 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-00f6-139233e7015-f7777f31-309d-3 | Hz-ID-17195 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF0007 | 5221 | 67.2696 | 36.2629 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Low | Agriculture Blocked | Moderate | 26 | CHA | 5 |  |  | 2012-06-12 16:30 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-00f6-13923409b1a-185018-3104-324 | Hz-ID-17198 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF0008 | 4809 | 67.2312 | 36.2788 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Medium | Critical Infrastracture | Moderate | 81 | CHA | 3 |  |  | 2012-07-05 16:30 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-00f6-139234390dc-3681c8a4-313f-6 | Hz-ID-17201 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF0009 | 775 | 67.2334 | 36.2829 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Low | Agriculture Blocked | Moderate | 34 | CHA | 5 |  |  | 2012-07-08 16:30 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir (1) | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} | c0a8-00f6-13923468f16-b1900fb-316d-d3 | Hz-ID-17204 | MCPA - Mine Clearance Planning Agency | AF/1611/14844/MF0010 | 806 | 67.22 | 36.2849 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {FB3DD103-3158-4C51-B411-0545E0BCC3BB} |  | Medium | Agriculture Blocked | Moderate | 32 | CHA | 3 |  |  | 2012-07-07 16:30 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir(2) | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} | c0a8-0057-12c3b9224ab-9f7446ad-25fbe- | MF-NA-1269 | MCPA - Mine Clearance Planning Agency | AF/1611/14871/MF5861 | 8179 | 67.267 | 36.2678 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} |  | Low | Agriculture Blocked | Moderate | 33 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir(2) | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} | c0a8-0057-12c3bad9bb0-65aa4d2b-37139- | MF-HT-101 | MCPA - Mine Clearance Planning Agency | AF/1611/14871/MF3443 | 5833 | 67.2181 | 36.2833 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} |  | Low | Other | Moderate | 26 | CHA | 5 |  |  | 2007-04-20 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir(2) | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} | c0a8-0057-12c3bada042-b2162fa6-3716a- | MF-HT-98 | MCPA - Mine Clearance Planning Agency | AF/1611/14871/MF3429 | 4575 | 67.2169 | 36.287 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} |  | Low | Agriculture Blocked | Moderate | 66 | CHA | 5 |  |  | 2007-04-17 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir(2) | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} | c0a8-0057-12c3bb1bdd5-9f7da4a1-398b8- | MF-HT-107 | MCPA - Mine Clearance Planning Agency | AF/1611/14871/MF2538 | 10579 | 67.2593 | 36.2678 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes | 2014-07-01 | 2014-07-23 | 1393 | HT | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} |  | Low | Agriculture Blocked | Moderate | 14 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir(2) | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} | c0a8-0057-12c3bb2bd75-7c69faa6-3a226- | MF-NA-1282 | MCPA - Mine Clearance Planning Agency | AF/1611/14871/MF5856 | 80974 | 67.278 | 36.2556 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes | 2014-08-01 | 2014-09-23 | 1393 | HT | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} |  | Low | Agriculture Blocked | Moderate | 35 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir(2) | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} | c0a8-0057-12c3bb59630-4e01a8b0-3bcf6- | MF-NA-1278 | MCPA - Mine Clearance Planning Agency | AF/1611/14871/MF5858 | 8260 | 67.273 | 36.2605 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes | 2014-07-01 | 2014-07-23 | 1393 | HT | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} |  | Low | Agriculture Blocked | Moderate | 38 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir(2) | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} | c0a8-0057-12c3bb59bcb-703a9959-3bd2a- | MF-NA-1279 | MCPA - Mine Clearance Planning Agency | AF/1611/14871/MF5857 | 9959 | 67.2765 | 36.2611 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes | 2014-08-01 | 2014-08-23 | 1393 | HT | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} |  | Low | Agriculture Blocked | Moderate | 12 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Shah Anjir(2) | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} | c0a8-008e-13213e1e419-c78cb937-1050-4 | MF-HT-103 | MCPA - Mine Clearance Planning Agency | AF/1611/14871/MF3445 | 2912 | 67.2233 | 36.2819 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {D6ACBF05-BDF3-4A96-A7A5-C103240C0516} |  | Low | Agriculture Blocked | Moderate | 26 | CHA | 5 |  |  | 2007-04-20 | No | Planned
North | Balkh | Chahar Kint | Shar Shar | {2E7BA219-8E4A-4670-826A-9278B67F89D7} | c0a8-0057-12c3b6a54de-b7c5903-970c-45 | BF-HT-93 | MCPA - Mine Clearance Planning Agency | B/2074 | 41522 | 67.2008 | 36.3931 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-127/A | Balkh Demining Project-3/A | DOS | Yes |  |  | 1393 | HT | {2E7BA219-8E4A-4670-826A-9278B67F89D7} |  | Medium | Critical Infrastracture | Moderate | 13 | CHA | 3 |  |  | 2007-04-16 | No | Planned
North | Balkh | Chahar Kint | Shar Shar | {2E7BA219-8E4A-4670-826A-9278B67F89D7} | c0a8-0057-12c3b9a7361-469bd69e-2b750- | MF-HT-1307 | MCPA - Mine Clearance Planning Agency | AF/1611/00002/MF3426 | 31265 | 67.2004 | 36.3914 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127/B | Balkh Demining Project-3/B | B-Germany | Yes |  |  | 1393 | HT | {2E7BA219-8E4A-4670-826A-9278B67F89D7} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Taralai | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} | c0a8-0057-12c3b8e780b-593b2223-23996- | MF-HT-85 | MCPA - Mine Clearance Planning Agency | AF/1611/14786/MF3423 | 39287 | 67.1518 | 36.5737 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-127 | Balkh Demining Project-3 | Bilateral | Yes | 2014-05-09 |  | 1393 | HT | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} |  | Low | Agriculture Blocked | Moderate | 6 | CHA | 5 |  |  | 2007-04-14 | No | Planned
North | Balkh | Chahar Kint | Taralai | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} | c0a8-0057-12c3b8e79ee-681e4dcb-239a8- | MF-NA-1267 | HT - HALO TRUST | H/3421 | 11200 | 67.1301 | 36.5618 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127 | Balkh Demining Project-3 | Bilateral | Yes | 2014-06-01 |  | 1393 | HT | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} |  | Low | Agriculture Blocked | Moderate | 8 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Taralai | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} | c0a8-0057-12c3b8e7bb3-e93fb825-239bf- | MF-HT-87 | MCPA - Mine Clearance Planning Agency | AF/1611/14786/MF3425 | 49327 | 67.1597 | 36.5789 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-127 | Balkh Demining Project-3 | Bilateral | Yes | 2014-05-18 | 2014-09-23 | 1393 | HT | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} |  | Low | Agriculture Blocked | Moderate | 7 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Taralai | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} | c0a8-0057-12c3b8e7de4-aceb5ef6-239d2- | MF-HT-84 | MCPA - Mine Clearance Planning Agency | AF/1611/14786/MF3422 | 19757 | 67.1378 | 36.5637 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-127 | Balkh Demining Project-3 | Bilateral | Yes | 2014-08-01 | 2014-09-23 | 1393 | HT | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} |  | Low | Agriculture Blocked | Moderate | 21 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Balkh | Chahar Kint | Taralai | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} | c0a8-0057-12c3b8e7f89-31451a42-239e9- | MF-HT-86 | MCPA - Mine Clearance Planning Agency | AF/1611/14786/MF3424 | 37518 | 67.156 | 36.5831 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-127 | Balkh Demining Project-3 | Bilateral | Yes | 2014-05-01 | 2014-07-23 | 1393 | HT | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} |  | Low | Agriculture Blocked | Moderate | 7 | CHA | 4 |  |  | 2007-04-01 | No | Planned
North | Balkh | Chahar Kint | Taralai | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} | c0a8-0057-12c3bb65f27-88b40b0f-3c429- | MF-HT-109 | MCPA - Mine Clearance Planning Agency | AF/1611/14786/MF2587 | 31169 | 67.1378 | 36.5637 | Closed | AP Only | AP Only | MineField | 1391/1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-01-01 | 2013-06-23 | 1392 | HT | {099C0BBB-1D6F-4A0D-A480-FF8EDCC262F8} |  |  |  | Moderate | 29 | CHA | 3 |  |  | 2007-04-12 | No | Complete
North | Balkh | Chimtal | Arabmazari | {B5647455-FA10-44BD-94A5-C6B0D74AC3A2} | c0a8-0057-12e5608861a-77ce9b16-136-25 | MF-HQ-12228 | DDG - Danish Demining Group | AF/1608/15339/MF2541 | 500 | 66.5825 | 36.6716 | Open | AP Only | AP Only | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {B5647455-FA10-44BD-94A5-C6B0D74AC3A2} |  | Medium | Agriculture Blocked | Substantial | 0 | CHA | 3 |  |  | 2009-09-09 | No | Open
North | Balkh | Chimtal | Arabmazari | {B5647455-FA10-44BD-94A5-C6B0D74AC3A2} | c0a8-0057-12e560a4869-3ab9b755-142-39 | MF-HQ-12232 | DDG - Danish Demining Group | AF/1608/15339/MF2540 | 500 | 66.5953 | 36.6755 | Open | AP Only | AP Only | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {B5647455-FA10-44BD-94A5-C6B0D74AC3A2} |  | Medium | Critical Infrastracture | Substantial | 0 | CHA | 3 |  |  | 2009-09-09 | No | Open
North | Balkh | Chimtal | Asya-i-Sharaf | {64141DAD-6A5F-4CCB-9C63-C5348F73E1EA} | c0a8-0057-12c3b9bdc2b-d64ad9c2-2c5b3- | MF-HQ-12352 | DDG - Danish Demining Group | AF/1608/15344/MF2542 | 48300 | 66.78 | 36.6308 | Open | AP Only | AP Only | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {64141DAD-6A5F-4CCB-9C63-C5348F73E1EA} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2009-09-09 | No | Open
North | Balkh | Chimtal | Bargah | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} | c0a8-0057-12d56040554-9268e55b-1f50-1 | MF-NA-815 | DDG - Danish Demining Group | AF/1708/16037/MF0001 | 19296 | 66.4543 | 36.6468 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-06-01 | No | Open
North | Balkh | Chimtal | Bargah | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} | c0a8-0057-12d599038a8-13350d11-257b-e | MF-NA-580 | DDG - Danish Demining Group | AF/1608/16037/MF0001 | 67730 | 66.3914 | 36.66 | Open | AP Only | AP Only | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2004-01-01 | No | Open
North | Balkh | Chimtal | Bargah | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} | c0a8-0057-12d5991d041-e2ee7cff-25a1-c | MF-NA-814 | DDG - Danish Demining Group | AF/1708/16037/MF0003 | 34080 | 66.3957 | 36.6593 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-06-01 | No | Open
North | Balkh | Chimtal | Bargah | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} | c0a8-0057-12d5998524b-d4e54d4a-263d-b | MF-NA-817 | DDG - Danish Demining Group | AF/1708/16037/MF0002 | 51974 | 66.4736 | 36.643 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2008-06-01 | No | Open
North | Balkh | Chimtal | Bargah | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} | c0a8-0057-12e560d3ad9-b7226466-169-b1 | MF-HQ-12236 | DDG - Danish Demining Group | AF/1708/16037/MF2544 | 200000 | 66.4199 | 36.666 | Open | AP Only | AP Only | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} |  | Medium | Critical Infrastracture | Substantial | 0 | CHA | 3 |  |  | 2009-09-09 | No | Open
North | Balkh | Chimtal | Bargah | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} | c0a8-0057-12e560f2264-9d9d565e-183-c0 | MF-HQ-12241 | DDG - Danish Demining Group | AF/1708/16037/MF2543 | 7000 | 66.4509 | 36.6529 | Open | AP Only | AP Only | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {B19B2157-F403-4D73-9AEF-1BD29325B2BB} |  | Medium | Critical Infrastracture | Substantial | 0 | CHA | 3 |  |  | 2009-09-09 | No | Open
North | Balkh | Chimtal | Bay Temor | {F89EB6F1-5B44-4003-B485-5651E0A1A2B3} | c0a8-0057-12c3b72e2f4-45afb75f-ff0c-6 | MF-HQ-12349 | DDG - Danish Demining Group | AF/1608/15345/MF2545 | 10000 | 66.7528 | 36.6675 | Open | AP Only | AP Only | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {F89EB6F1-5B44-4003-B485-5651E0A1A2B3} |  | High with Victim | High with Victims | Substantial | 381 | CHA | 2 |  |  | 2009-09-09 | No | Open
North | Balkh | Chimtal | Bukshor | {ADB128BC-864A-468A-8AF6-89DCE165D30D} | c0a8-0057-12c3baf2130-f7ec3d9c-37ff5- | MF-NA-1311 | DDG - Danish Demining Group | AF/1605/14906/MF0002 | 2561 | 66.8314 | 36.9272 | Open | AP Only | AP Only | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {ADB128BC-864A-468A-8AF6-89DCE165D30D} |  | High | Critical Infrastracture | Substantial | 2051 | CHA | 3 |  |  | 2009-01-01 | No | Open
North | Balkh | Chimtal | Chimtal | {537BEB83-3AFE-41C2-8B0E-89038424AE05} | c0a8-0057-12c3b7872a6-d455316f-140d3- | MF-HQ-12208 | DDG - Danish Demining Group | AF/1608/31902/MF2548 | 20000 | 66.4077 | 36.6277 | Open | AP Only | AP Only | MineField |  | MBT Project-038 | Balkh Demining Project-2 |  |  |  |  | 1398 |  | {537BEB83-3AFE-41C2-8B0E-89038424AE05} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 2 |  |  | 2009-09-12 | No | Open
North | Balkh | Dihdadi | Ghonde Radar | {17E87A63-1AB2-4C82-A562-3E844808C9B3} | c0a8-00f6-13695f7efde-97ebbe02-1149-b | BF-15218 | MCPA - Mine Clearance Planning Agency | AF/1612/32512/BF0009 | 283226 | 67.0469 | 36.6361 | Open | UXO Only | UXO Only | BF |  | MBT Project-244 | Balkh Demining Project-3 AT |  |  |  |  | 1396 |  | {17E87A63-1AB2-4C82-A562-3E844808C9B3} |  | Low | Agriculture Blocked | Low | 8 | CHA | 5 |  |  | 2012-03-08 16:30 | No | Open
North | Balkh | Dihdadi | Sherabad | {88445F4C-4572-4A84-A7DE-D359B63B9BBE} | c0a8-00f6-135384b99e4-3a8455b8-20e-bf | BF-15195 | MCPA - Mine Clearance Planning Agency | AF/1612/14821/BF0008 | 18538 | 67.0414 | 36.7037 | Open | UXO Only | UXO Only | BF |  | MBT Project-244 | Balkh Demining Project-3 AT |  |  |  |  | 1396 |  | {88445F4C-4572-4A84-A7DE-D359B63B9BBE} |  | High with Victim | High with Victims | Low | 67 | CHA | 2 |  |  | 2011-12-11 16:30 | No | Open
North | Balkh | Kaldar | Bazarak | {7B658A24-1CFF-447E-90CA-AF97F89AF290} | c0a8-0009-14656fd2df8-40ca1fc7-87a-b6 | Hz-ID-18741 | DDG - Danish Demining Group | AF/1613/14586/MF0002 | 7522 | 67.7127 | 37.1738 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {7B658A24-1CFF-447E-90CA-AF97F89AF290} |  | Low | Agriculture Blocked | Moderate | 17 | CHA | 5 |  |  | 2014-04-15 16:30 | No | Open
North | Balkh | Kaldar | Kaldar | {75C0A6F4-F766-4A2B-942D-BAD0696F7F83} | c0a8-00f6-1352d6e8205-7c203b5c-178-e2 | MF-15994 | DDG - Danish Demining Group | AF/1613/31895/MF0001 | 906 | 67.312 | 37.0776 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2014-02-04 | 2014-04-23 | 1392 | HT | {75C0A6F4-F766-4A2B-942D-BAD0696F7F83} |  |  |  | Moderate | 0 | CHA | 2 |  |  | 2011-05-16 16:30 | No | Complete
North | Balkh | Khulm | Chetgari | {B719AE2E-9DB7-42BD-9C6C-1336918F1A0A} | c0a8-008e-1329ecd2c00-2a84b83d-4ec-dd | MF-16122 | DDG - Danish Demining Group | AF/1614/32219/MF0040 | 59526 | 67.6511 | 36.6237 | Open | AP Only | AP Only | MineField | Blank | MBT Project-037/B | Balkh Demining Project-1/B |  | No |  |  | 1394 | Blank | {B719AE2E-9DB7-42BD-9C6C-1336918F1A0A} | , | High with Victim | High with Victims | Moderate | 4 | CHA | 1 |  |  | 2011-06-14 16:30 | No | Open
North | Balkh | Khulm | Chetgari | {B719AE2E-9DB7-42BD-9C6C-1336918F1A0A} | c0a8-00f6-13518271150-61612100-1d5-79 | MF-16120 | DDG - Danish Demining Group | AF/1614/32219/MF0039 | 78840 | 67.6592 | 36.625 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {B719AE2E-9DB7-42BD-9C6C-1336918F1A0A} |  | High with Victim | High with Victims | Moderate | 4 | CHA | 1 |  |  | 2011-06-09 16:30 | No | Open
North | Balkh | Khulm | Haji Ali | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} | c0a8-0009-13f2d055731-4cfe6703-5af7-5 | Hz-ID-17975 | DDG - Danish Demining Group | AF/1614/14569/MF0050 | 102933 | 67.7897 | 36.633 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2013-03-29 16:30 | No | Open
North | Balkh | Khulm | Haji Ali | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} | c0a8-0009-13f2d0ea559-e8e915af-5b9d-4 | Hz-ID-17977 | DDG - Danish Demining Group | AF/1614/14569/MF0051 | 51597 | 67.7897 | 36.633 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2013-03-30 16:30 | No | Open
North | Balkh | Khulm | Haji Ali | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} | c0a8-0009-13f2d140db7-e81aa012-5bd6-8 | Hz-ID-17979 | DDG - Danish Demining Group | AF/1614/14569/MF0049 | 86883 | 67.7897 | 36.633 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2013-03-27 16:30 | No | Open
North | Balkh | Khulm | Haji Ali | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} | c0a8-0009-13f2d144fd5-39f6cb62-5c12-9 | Hz-ID-17976 | DDG - Danish Demining Group | AF/1614/14569/MF0048 | 1989 | 67.8023 | 36.6497 | Open | AT Only | AT Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} |  | Medium | Critical Infrastracture | Moderate | 0 | CHA | 3 |  |  | 2013-03-30 16:30 | No | Open
North | Balkh | Khulm | Haji Ali | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} | c0a8-0009-13f2d1bc5d8-6550208e-5c72-a | Hz-ID-17981 | DDG - Danish Demining Group | AF/1614/14569/MF0047 | 2784 | 67.8023 | 36.6997 | Open | AT Only | AT Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2013-03-29 16:30 | No | Open
North | Balkh | Khulm | Haji Ali | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} | c0a8-0009-13f2d1fbd1e-f5d7e9c3-5cd2-a | Hz-ID-17980 | DDG - Danish Demining Group | AF/1614/14569/MF0046 | 4760 | 67.8023 | 36.6497 | Open | AT Only | AT Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {D82D57DD-C648-4750-A0AB-ADDBCD5F35C9} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2013-03-27 16:30 | No | Open
North | Balkh | Khulm | Ismail Khayl | {ACAC0FF9-40A9-4E6F-B1DC-874CA1EF4258} | c0a8-0009-1409a5dcdf5-88a7830f-b54-59 | Hz-ID-18096 | DDG - Danish Demining Group | AF/1614/14568/MF0053 | 99840 | 67.7545 | 36.7052 | Open | AT Only | AT Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {ACAC0FF9-40A9-4E6F-B1DC-874CA1EF4258} |  | High with Victim | High with Victims | Moderate | 156 | CHA | 2 |  |  | 2013-07-26 16:30 | No | Open
North | Balkh | Khulm | Ismail Khayl | {ACAC0FF9-40A9-4E6F-B1DC-874CA1EF4258} | c0a8-0009-140d8544cec-eeb39e1a-153a-e | Hz-ID-18097 | DDG - Danish Demining Group | AF/1614/14568/MF0054 | 2169 | 67.7499 | 36.7064 | Open | AT Only | AT Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {ACAC0FF9-40A9-4E6F-B1DC-874CA1EF4258} |  | High with Victim | High with Victims | Moderate | 3204 | CHA | 2 |  |  | 2013-07-30 16:30 | No | Open
North | Balkh | Khulm | Mola Sultan Bashi | {33621215-87A4-46A9-804D-F8FC845613CD} | c0a8-0009-13f2d141b9c-b4fad8ca-5bf1-5 | Hz-ID-17978 | DDG - Danish Demining Group | AF/1614/00147/MF0052 | 2200 | 67.6992 | 36.6541 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {33621215-87A4-46A9-804D-F8FC845613CD} |  | Medium | Critical Infrastracture | Moderate | 19 | CHA | 3 |  |  | 2013-03-31 16:30 | No | Open
North | Balkh | Khulm | Nawabad | {6EDCA68D-281C-4747-81C9-8C70D71F25B3} | c0a8-00f6-135e264b822-4655a8ae-e3e9-b | BF-15213 | MCPA - Mine Clearance Planning Agency | AF/1614/32220/BF0039 | 77215 | 67.4955 | 36.7721 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-037 | Balkh Demining Project-1 | B-Sweden | Yes | 2013-12-01 | 2013-12-24 | 1392-1393 | DDG | {6EDCA68D-281C-4747-81C9-8C70D71F25B3} |  |  |  | Moderate | 4 | CHA | 3 |  |  | 2012-01-17 16:30 | No | Complete
North | Balkh | Khulm | Nawabad | {6EDCA68D-281C-4747-81C9-8C70D71F25B3} | c0a8-00f6-135e26615e6-963c1802-e407-2 | BF-15214 | DDG - Danish Demining Group | AF/1614/32220/BF0040 | 53114 | 67.4929 | 36.7703 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-037 | Balkh Demining Project-1 | B-Sweden | Yes | 2013-12-01 | 2013-12-24 | 1392-1393 | DDG | {6EDCA68D-281C-4747-81C9-8C70D71F25B3} |  |  |  | Moderate | 1 | CHA | 3 |  |  | 2012-01-19 16:30 | No | Complete
North | Balkh | Khulm | Nawabad | {6EDCA68D-281C-4747-81C9-8C70D71F25B3} | c0a8-00f6-135e2682fc5-f6a17627-e42a-9 | BF-15215 | DDG - Danish Demining Group | AF/1614/32220/BF0041 | 14090 | 67.4929 | 36.7703 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-037 | Balkh Demining Project-1 | B-Sweden | Yes | 2013-12-01 | 2013-12-24 | 1392-1393 | DDG | {6EDCA68D-281C-4747-81C9-8C70D71F25B3} |  |  |  | Moderate | 1 | CHA | 3 |  |  | 2012-02-23 16:30 | No | Complete
North | Balkh | Khulm | Oljatu | {899C4E50-B5F3-48A8-A444-12E4B95C088E} | c0a8-0057-12c3b69b6cd-e3a6aaad-8fb1-d | MF-NA-1271 | DDG - Danish Demining Group | AF/1614/14541/MF5809 | 145000 | 67.5437 | 36.6293 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {899C4E50-B5F3-48A8-A444-12E4B95C088E} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Balkh | Khulm | Oljatu | {899C4E50-B5F3-48A8-A444-12E4B95C088E} | c0a8-0057-12c3b6adc83-d51158c6-9d77-7 | MF-NA-1274 | HT - HALO TRUST | H/5810 | 27560 | 67.5315 | 36.6349 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {899C4E50-B5F3-48A8-A444-12E4B95C088E} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Balkh | Khulm | Oljatu | {899C4E50-B5F3-48A8-A444-12E4B95C088E} | c0a8-0057-12c3b7d4370-24b328a1-1788f- | MF-NA-1252 | DDG - Danish Demining Group | AF/1614/14541/MF5814 | 70000 | 67.6627 | 36.64 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {899C4E50-B5F3-48A8-A444-12E4B95C088E} |  | Low | Agriculture Blocked | Moderate | 4 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Balkh | Khulm | Oljatu | {899C4E50-B5F3-48A8-A444-12E4B95C088E} | c0a8-0057-12c3b7d492a-9abc488-178df-1 | MF-NA-1246 | DDG - Danish Demining Group | AF/1614/14541/MF5811 | 28880 | 67.6851 | 36.6479 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {899C4E50-B5F3-48A8-A444-12E4B95C088E} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Balkh | Khulm | Sad Dawai | {87E85F42-A338-46BC-B87A-7C61FBD07686} | c0a8-0057-12c3b9d0e0f-d2a2ba83-2d1b8- | MF-NA-1266 | HT - HALO TRUST | H/4074 | 4848 | 67.8025 | 36.6435 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {87E85F42-A338-46BC-B87A-7C61FBD07686} | , | Low | Small Hazards | Moderate | 18 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Balkh | Khulm | Sad Dawai | {87E85F42-A338-46BC-B87A-7C61FBD07686} | c0a8-0057-12c3b9d1f7c-8a970f98-2d25a- | MF-NA-1265 | HT - HALO TRUST | H/4073 | 4590 | 67.8037 | 36.6487 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {87E85F42-A338-46BC-B87A-7C61FBD07686} | , | Low | Small Hazards | Moderate | 4 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Balkh | Khulm | Sayghanchi | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} | c0a8-0009-13f2cfd5e88-acff06f6-5a61-6 | Hz-ID-17971 | DDG - Danish Demining Group | AF/1614/14547/MF0042 | 8631 | 67.7133 | 36.6136 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-037 | Balkh Demining Project-1 | B-Sweden | Yes | 2013-12-01 | 2013-12-24 | 1392-1393 | DDG | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} |  |  |  | Moderate | 9 | CHA | 5 |  |  | 2013-03-08 16:30 | No | Complete
North | Balkh | Khulm | Sayghanchi | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} | c0a8-0009-13f2cffbebf-2eed77d7-5a7e-7 | Hz-ID-17972 | DDG - Danish Demining Group | AF/1614/14547/MF0043 | 7851 | 67.7139 | 36.6133 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-037 | Balkh Demining Project-1 | B-Sweden | Yes | 2013-12-01 | 2013-12-24 | 1392-1393 | DDG | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} |  |  |  | Moderate | 9 | CHA | 5 |  |  | 2013-03-10 16:30 | No | Complete
North | Balkh | Khulm | Sayghanchi | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} | c0a8-0009-13f2d0d0065-baaee572-5b63-6 | Hz-ID-17973 | DDG - Danish Demining Group | AF/1614/14547/MF0044 | 58915 | 67.7308 | 36.6079 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2013-03-28 16:30 | No | Open
North | Balkh | Khulm | Sayghanchi | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} | c0a8-0009-1403806f971-b77decce-2f23-7 | Hz-ID-17974 | DDG - Danish Demining Group | AF/1614/14547/MF0045 | 70473 | 67.7319 | 36.6088 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} |  | Low | Agriculture Blocked | Moderate | 7 | CHA | 5 |  |  | 2013-03-29 16:30 | No | Open
North | Balkh | Khulm | Sayghanchi | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} | c0a8-0057-12c3bb52777-9b1a34c8-3b93f- | MF-NA-1258 | DDG - Danish Demining Group | AF/1614/1457/MF5807 | 105000 | 67.7124 | 36.6144 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-037 | Balkh Demining Project-1 | B-Sweden | Yes | 2012-10-16 | 2013-03-31 | 1392-1393 | DDG | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} |  |  |  | Moderate | 15 | CHA | 5 |  |  | 2009-01-01 | No | Complete
North | Balkh | Khulm | Sayghanchi | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} | c0a8-0057-12c3bb529c8-5df70f81-3b95b- | MF-NA-1259 | DDG - Danish Demining Group | AF/1614/14547/MF5808 | 112500 | 67.7124 | 36.6144 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-037 | Balkh Demining Project-1 | B-Sweden | Yes | 2013-10-01 | 2014-05-15 | 1392-1393 | DDG | {7D93E756-CD44-4DAA-8554-9F575F7BC5B7} | Alternative plan for North CIDA RFP Demining Project 1390 |  |  | Moderate | 15 | CHA | 5 |  |  | 2009-01-01 | No | Complete
North | Balkh | Khulm | Yangi Aegh | {EC0F11FC-32CE-44A3-9AAB-95B23E61F29E} | c0a8-0057-12e560b7780-cc955948-150-2b | MF-HQ-12234 | DDG - Danish Demining Group | AF/1614/14546/MF2857 | 100000 | 68.1469 | 36.707 | Open | Mixed Mine | Mixed Mine | MineField | Blank | MBT Project-094 | Balkh Demining Project-1 (AT) |  | No |  |  | 1395 | Blank | {EC0F11FC-32CE-44A3-9AAB-95B23E61F29E} | , | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2009-09-09 | No | Open
North | Balkh | Kishindih | Chokhi Chakana-i- Pain | {97EC4591-195A-40AD-8F21-3140ACD26C65} | c0a8-0009-13dbfbe06ba-fdd9c0a6-5881-e | Hz-ID-17462 | MCPA - Mine Clearance Planning Agency | AF/1610/30207/MF0016 | 14273 | 66.9908 | 36.0396 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {97EC4591-195A-40AD-8F21-3140ACD26C65} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2012-08-04 16:30 | No | Open
North | Balkh | Kishindih | Jok Kushinda-i-Bala | {D77118D2-4B80-44A3-B026-8598CE9049D0} | c0a8-0009-13b83221ab9-40fba38e-85d-57 | Hz-ID-17463 | MCPA - Mine Clearance Planning Agency | AF/1609/30211/MF0017 | 17659 | 67.0117 | 36.1066 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {D77118D2-4B80-44A3-B026-8598CE9049D0} |  | Low | Agriculture Blocked | Moderate | 23 | CHA | 5 |  |  | 2012-07-25 16:30 | No | Open
North | Balkh | Kishindih | Jok Kushinda-i-Bala | {D77118D2-4B80-44A3-B026-8598CE9049D0} | c0a8-0009-13b832485a0-897f2174-921-5e | Hz-ID-17464 | MCPA - Mine Clearance Planning Agency | AF/1609/30211/MF0018 | 3140 | 67.0179 | 36.0919 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {D77118D2-4B80-44A3-B026-8598CE9049D0} |  | Low | Agriculture Blocked | Moderate | 32 | CHA | 5 |  |  | 2012-07-31 16:30 | No | Open
North | Balkh | Marmul | Charmaghz Say | {67CA7BF6-3295-408B-89CE-BA9065CFF25D} | c0a8-008e-132a3dd30bf-306d6270-1d5-65 | MF-HQ-12054 | DDG - Danish Demining Group | AF/1615/00316/MF0002 | 18169 | 67.2796 | 36.6118 | Open | Mixed Mine | Mixed Mine | MineField | Blank | MBT Project-244 | Balkh Demining Project-3 AT |  | No |  |  | 1396 | None | {67CA7BF6-3295-408B-89CE-BA9065CFF25D} | Remove from MCPA plan | High with Victim | High with Victims | Moderate | 23 | CHA | 1 |  |  | 2009-06-08 | No | Open
North | Balkh | Marmul | Ghandaki | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} | c0a8-0009-1409a45391b-39f25141-ad0-32 | Hz-ID-18094 | DDG - Danish Demining Group | AF/1615/14810/MF0058 | 62567 | 67.2791 | 36.6091 | Open | AT Only | AT Only | MineField |  | MBT Project-244 | Balkh Demining Project-3 AT |  |  |  |  | 1396 |  | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} |  | Low | Agriculture Blocked | Moderate | 30 | CHA | 5 |  |  | 2013-07-16 16:30 | No | Open
North | Balkh | Marmul | Ghandaki | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} | c0a8-0009-1409a50912e-72999d4b-b03-1e | Hz-ID-18095 | DDG - Danish Demining Group | AF/1615/14810/MF0059 | 12831 | 67.2791 | 36.6091 | Open | AT Only | AT Only | MineField |  | MBT Project-244 | Balkh Demining Project-3 AT |  |  |  |  | 1396 |  | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} |  | Low | Agriculture Blocked | Moderate | 3 | CHA | 5 |  |  | 2013-07-30 16:30 | No | Open
North | Balkh | Marmul | Ghandaki | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} | c0a8-0057-12c3b71e22b-1812630f-f30b-f | MF-HT-1334 | DDG - Danish Demining Group | AF/1615/14810/MF3452 | 40000 | 67.2872 | 36.6512 | Open | AP Only | AP Only | MineField | Blank | MBT Project-244 | Balkh Demining Project-3 AT |  | No |  |  | 1396 | Blank | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} | , | Low | Critical Infrastracture | Moderate | 49 | CHA | 5 |  |  | 2007-05-01 | No | Open
North | Balkh | Marmul | Ghandaki | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} | c0a8-00f6-1353d4d14eb-12e37e57-1623-d | MF-16644 | DDG - Danish Demining Group | AF/1615/14810/MF0010 | 19534 | 67.2844 | 36.652 | Open | AT Only | AT Only | MineField |  | MBT Project-244 | Balkh Demining Project-3 AT |  |  |  |  | 1396 |  | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} |  | Low | Critical Infrastracture | Moderate | 38 | CHA | 5 |  |  | 2011-11-01 16:30 | No | Open
North | Balkh | Marmul | Ghandaki | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} | c0a8-00f6-1353d500373-b9287fc4-163f-8 | MF-16645 | DDG - Danish Demining Group | AF/1615/14810/MF0014 | 13686 | 67.2862 | 36.6546 | Open | AT Only | AT Only | MineField |  | MBT Project-244 | Balkh Demining Project-3 AT |  |  |  |  | 1396 |  | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} |  | Low | Critical Infrastracture | Moderate | 28 | CHA | 5 |  |  | 2011-11-17 16:30 | No | Open
North | Balkh | Marmul | Ghandaki | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} | c0a8-00f6-1353d516453-95be2fff-1659-f | MF-16646 | DDG - Danish Demining Group | AF/1615/14810/MF0013 | 7759 | 67.2815 | 36.6612 | Open | AT Only | AT Only | MineField |  | MBT Project-244 | Balkh Demining Project-3 AT |  |  |  |  | 1396 |  | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} |  | Low | Agriculture Blocked | Moderate | 28 | CHA | 5 |  |  | 2011-11-03 16:30 | No | Open
North | Balkh | Marmul | Ghandaki | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} | c0a8-00f6-1353d52bc1e-791fac2b-1671-e | MF-16647 | DDG - Danish Demining Group | AF/1615/14810/MF0011 | 135156 | 67.2862 | 36.6546 | Open | AT Only | AT Only | MineField |  | MBT Project-244 | Balkh Demining Project-3 AT |  |  |  |  | 1396 |  | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} |  | Low | Critical Infrastracture | Moderate | 72 | CHA | 5 |  |  | 2011-11-02 16:30 | No | Open
North | Balkh | Marmul | Ghandaki | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} | c0a8-00f6-1353d550f25-d8d015e2-169d-5 | MF-16648 | DDG - Danish Demining Group | AF/1615/14810/MF0012 | 183042 | 67.2806 | 36.6634 | Open | AT Only | AT Only | MineField |  | MBT Project-244 | Balkh Demining Project-3 AT |  |  |  |  | 1396 |  | {A4A72B43-F25F-43C4-81F2-1C58093BA3DB} |  | Low | Critical Infrastracture | Moderate | 78 | CHA | 5 |  |  | 2011-11-02 16:30 | No | Open
North | Balkh | Nahri Shahi | Nauwarid | {F19E512B-A808-4E3C-A620-22355E88093F} | c0a8-008e-1328fb3cddc-ff64ce43-233d-b | MF-15866 | MCPA - Mine Clearance Planning Agency | AF/1605/14799/MF0010 | 32024 | 67.1773 | 37.0393 | Open | AT Only | AT Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 | None | {F19E512B-A808-4E3C-A620-22355E88093F} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 3 |  |  | 2011-03-24 16:30 | No | Open
North | Balkh | Nahri Shahi | Nauwarid | {F19E512B-A808-4E3C-A620-22355E88093F} | c0a8-008e-1328fccf6ca-e6048d1a-28f2-4 | BF-15106 | MCPA - Mine Clearance Planning Agency | AF/1602/14813/BF0013 | 268421 | 67.2724 | 37.0562 | Closed | UXO Only | UXO Only | BF | 1392/1393 | MBT Project-151 | Balkh Demining Project-2 (AT) | SIDA | Yes | 2014-02-15 | 2014-06-22 | 1393 | DDG | {F19E512B-A808-4E3C-A620-22355E88093F} | , |  |  | Moderate | 0 | CHA | 3 |  |  | 2011-05-30 16:30 | No | Planned
North | Balkh | Nahri Shahi | Nauwarid | {F19E512B-A808-4E3C-A620-22355E88093F} | c0a8-008e-1329e9681b4-d2c45f52-2-d8a8 | BF-15083 | MCPA - Mine Clearance Planning Agency | AF/1605/14799/BF0011 | 237190 | 67.2788 | 37.0541 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-151 | Balkh Demining Project-2 (AT) | SIDA | Yes |  |  | 1393 | DDG | {F19E512B-A808-4E3C-A620-22355E88093F} | , | High with Victim | High with Victims | Moderate | 0 | CHA | 5 |  |  | 2011-04-27 16:30 | No | Planned
North | Balkh | Nahri Shahi | Nauwarid | {F19E512B-A808-4E3C-A620-22355E88093F} | c0a8-008e-1329e98b74b-80d34896-14-250 | BF-15084 | MCPA - Mine Clearance Planning Agency | AF/1602/14813/BF0012 | 363803 | 67.2788 | 37.0541 | Worked on | UXO Only | UXO Only | BF | 1393 | MBT Project-151 | Balkh Demining Project-2 (AT) | SIDA | Yes |  |  | 1393 | DDG | {F19E512B-A808-4E3C-A620-22355E88093F} | , | High with Victim | High with Victims | Moderate | 0 | CHA | 3 |  |  | 2011-05-01 16:30 | No | Planned
North | Balkh | Nahri Shahi | Nauwarid | {F19E512B-A808-4E3C-A620-22355E88093F} | c0a8-008e-1329efae997-3b92991-b8e-d93 | MF-15416 | MCPA - Mine Clearance Planning Agency | AF/1605/14813/MF0007 | 216782 | 67.2245 | 37.0399 | Open | AT Only | AT Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 | None | {F19E512B-A808-4E3C-A620-22355E88093F} |  | High with Victim | High with Victims | Moderate | 7 | CHA | 5 |  |  | 2010-11-06 16:30 | No | Open
North | Balkh | Nahri Shahi | Nauwarid | {F19E512B-A808-4E3C-A620-22355E88093F} | c0a8-008e-132c94e2fc5-c3d89b17-2f80-f | MF-15417 | MCPA - Mine Clearance Planning Agency | AF/1605/14799/MF0008 | 142321 | 67.2247 | 37.041 | Open | AT Only | AT Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {F19E512B-A808-4E3C-A620-22355E88093F} |  | High with Victim | High with Victims | Moderate | 10 | CHA | 3 |  |  | 2010-11-09 16:30 | No | Open
North | Balkh | Nahri Shahi | Nauwarid | {F19E512B-A808-4E3C-A620-22355E88093F} | c0a8-00f6-135e67400d8-2f4d5713-2bb-e5 | BF-15208 | MCPA - Mine Clearance Planning Agency | AF/1602/14813/BF0014 | 58024 | 67.2845 | 37.0517 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-151 | Balkh Demining Project-2 (AT) | SIDA | Yes |  |  | 1393 | DDG | {F19E512B-A808-4E3C-A620-22355E88093F} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 5 |  |  | 2012-01-03 16:30 | No | Planned
North | Balkh | Nahri Shahi | Nauwarid | {F19E512B-A808-4E3C-A620-22355E88093F} | c0a8-00f6-135e675c01b-7d81c480-2ce-74 | BF-15209 | MCPA - Mine Clearance Planning Agency | AF/1602/14813/BF0015 | 77169 | 67.263 | 37.049 | Closed | UXO Only | UXO Only | BF | 1392/1393 | MBT Project-151 | Balkh Demining Project-2 (AT) | SIDA | Yes | 2014-02-15 | 2014-06-22 | 1393 | DDG | {F19E512B-A808-4E3C-A620-22355E88093F} |  |  |  | Moderate | 0 | CHA | 3 |  |  | 2012-01-05 16:30 | No | Planned
North | Balkh | Nahri Shahi | Nauwarid | {F19E512B-A808-4E3C-A620-22355E88093F} | c0a8-00f6-135e677caae-c0b8b9ad-2fd-fd | BF-15210 | MCPA - Mine Clearance Planning Agency | AF/1602/14813/BF0016 | 15633 | 67.2694 | 37.0478 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-151 | Balkh Demining Project-2 (AT) | SIDA | Yes |  |  | 1393 | DDG | {F19E512B-A808-4E3C-A620-22355E88093F} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 5 |  |  | 2012-01-07 16:30 | No | Planned
North | Balkh | Nahri Shahi | Nauwarid | {F19E512B-A808-4E3C-A620-22355E88093F} | c0a8-00f6-135e6791985-2fdcf5a5-30f-d3 | BF-15211 | MCPA - Mine Clearance Planning Agency | AF/1602/14813/BF0017 | 11274 | 67.2706 | 37.049 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-151 | Balkh Demining Project-2 (AT) | SIDA | Yes |  |  | 1393 | DDG | {F19E512B-A808-4E3C-A620-22355E88093F} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 5 |  |  | 2012-01-09 16:30 | No | Planned
North | Balkh | Nahri Shahi | Nauwarid | {F19E512B-A808-4E3C-A620-22355E88093F} | c0a8-00f6-135e67b00c1-cd2ee126-33b-69 | BF-15212 | MCPA - Mine Clearance Planning Agency | AF/1602/14813/BF0018 | 29892 | 67.263 | 37.047 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-151 | Balkh Demining Project-2 (AT) | SIDA | Yes | 2014-02-15 | 2014-04-15 | 1393 | DDG | {F19E512B-A808-4E3C-A620-22355E88093F} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 3 |  |  | 2012-01-11 16:30 | No | Planned
North | Balkh | Nahri Shahi | Qizilabad | {6F4FBBE5-1D46-4E95-AD37-E76B094229C5} | c0a8-0009-13e7e7e38dc-bfa5765a-2eb4-7 | Hz-ID-17876 | MCPA - Mine Clearance Planning Agency | AF/1602/14808/BF0057 | 104733 | 67.1823 | 36.7296 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-151 | Balkh Demining Project-2 (AT) | SIDA | Yes |  |  | 1393 | DDG | {6F4FBBE5-1D46-4E95-AD37-E76B094229C5} |  | High with Victim | High with Victims | Moderate | 4 | CHA | 1 |  |  | 2013-03-09 16:30 | No | Planned
North | Balkh | Nahri Shahi | Qizilabad | {6F4FBBE5-1D46-4E95-AD37-E76B094229C5} | c0a8-00f6-13518361f68-73a6fa89-218-be | BF-15088 | MCPA - Mine Clearance Planning Agency | AF/1602/14808/BF0056 | 12529 | 67.1795 | 36.7296 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-151 | Balkh Demining Project-2 (AT) | SIDA | Yes |  |  | 1393 | DDG | {6F4FBBE5-1D46-4E95-AD37-E76B094229C5} |  | High with Victim | High with Victims | Moderate | 2 | CHA | 5 |  |  | 2011-04-09 16:30 | No | Planned
North | Balkh | Nahri Shahi | Qizilabad | {6F4FBBE5-1D46-4E95-AD37-E76B094229C5} | c0a8-00f6-1351839ca58-7900fb9-235-a69 | BF-15086 | MCPA - Mine Clearance Planning Agency | AF/1602/14808/BF0054 | 63835 | 67.1753 | 36.7301 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-151 | Balkh Demining Project-2 (AT) | SIDA | Yes |  |  | 1393 | DDG | {6F4FBBE5-1D46-4E95-AD37-E76B094229C5} |  | High with Victim | High with Victims | Moderate | 6 | CHA | 3 |  |  | 2011-04-27 16:30 | No | Planned
North | Balkh | Sharak Hairatan | Hayratan | {ECBE52A1-58E8-427B-AFCA-718AE3489083} | c0a8-0057-12c3ba8fd1c-179751b-345f6-e | MF-NA-1027 | HT - HALO TRUST | H/4812 | 21045 | 67.4291 | 37.2252 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {ECBE52A1-58E8-427B-AFCA-718AE3489083} | There is only one hazard within Sharak Hayratan but the gov authirity does not allow to be cleared this task due to some insecur status of the area and for your further information this hazard is located under Uzbak-Afghan borther bridge which Amo revir c | High with Victim | High with Victims | Moderate | 30 | CHA | 2 |  |  | 2008-08-01 | No | Open
North | Balkh | Sharak Hairatan | Towz Laq | {0F7CDA0A-0624-47CE-A013-3661494BE511} | c0a8-0009-13e88255081-e21861d9-2382-b | Hz-ID-17873 | MCPA - Mine Clearance Planning Agency | AF/1613/00001/BF0024 | 82014 | 67.4049 | 37.1994 | Open | UXO Only | UXO Only | BF |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {0F7CDA0A-0624-47CE-A013-3661494BE511} |  | Medium | Critical Infrastracture | Moderate | 82 | CHA | 5 |  |  | 2013-03-07 16:30 | No | Open
North | Balkh | Sholgara | Jangali | {1EC7097E-377A-4CFE-ABC4-6A7E73269C48} | c0a8-0057-12fbf934292-dcd2b622-24e0-5 | MF-NA-1221 | HT - HALO TRUST | H/2594 | 2100 | 66.9378 | 36.4749 | Open | AP Only | AP Only | MineField | Blank | MBT Project-094 | Balkh Demining Project-1 (AT) |  | No |  |  | 1395 | Blank | {1EC7097E-377A-4CFE-ABC4-6A7E73269C48} |  | Low | Small Hazards | Moderate | 347 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Balkh | Sholgara | Sarband-i- Haji Tala Bai | {ADA19839-A752-4E99-879C-D84EDF9DF5B9} | c0a8-0009-13e7e745b72-a332206c-2e92-d | Hz-ID-17878 | MCPA - Mine Clearance Planning Agency | AF/1609/14978/MF0014 | 781 | 66.8979 | 36.2427 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {ADA19839-A752-4E99-879C-D84EDF9DF5B9} |  | High | Water Blocked | Moderate | 0 | CHA | 3 |  |  | 2013-03-14 16:30 | No | Open
North | Balkh | Shortepa | Basherly Toqa | {9C213F3C-B3A6-4B5F-B60F-F5E22598B1A5} | c0a8-008e-132e7095e50-42653488-9a-8f3 | MF-HT-138 | DDG - Danish Demining Group | AF/1604/00474/MF2600 | 52342 | 67.2048 | 37.2226 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {9C213F3C-B3A6-4B5F-B60F-F5E22598B1A5} |  | Medium | Critical Infrastracture | Moderate | 273 | CHA | 3 |  |  | 2007-05-31 | No | Open
North | Balkh | Shortepa | Chaqar (Tash Guzar) | {2EC7D938-972A-4A65-8B49-E5D92F28A41D} | c0a8-008e-13455ba9a9d-2ecd3de9-838-b9 | MF-16209 | DDG - Danish Demining Group | AF/1604/00134/MF0003 | 4107 | 67.195 | 37.2088 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {2EC7D938-972A-4A65-8B49-E5D92F28A41D} |  | Medium | Agriculture Blocked | Moderate | 10 | CHA | 3 |  |  | 2011-05-22 16:30 | No | Open
North | Balkh | Shortepa | Chaqar (Tash Guzar) | {2EC7D938-972A-4A65-8B49-E5D92F28A41D} | c0a8-00f6-1355227f0be-b7dc8aec-389-fd | MF-16210 | DDG - Danish Demining Group | AF/1604/00134/MF0002 | 27969 | 67.2031 | 37.1979 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {2EC7D938-972A-4A65-8B49-E5D92F28A41D} |  | Low | Agriculture Blocked | Moderate | 27 | CHA | 5 |  |  | 2011-08-23 16:30 | No | Open
North | Balkh | Shortepa | Chaqar (Tash Guzar) | {2EC7D938-972A-4A65-8B49-E5D92F28A41D} | c0a8-00f6-135522d9c0d-7457f7a0-432-b4 | MF-16211 | DDG - Danish Demining Group | AF/1604/00134/MF0001 | 13048 | 67.206 | 37.181 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {2EC7D938-972A-4A65-8B49-E5D92F28A41D} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2011-08-23 16:30 | No | Open
North | Balkh | Shortepa | Tash Guzar | {9D636B66-5594-4064-BABD-B0E51724651E} | c0a8-008e-132f7de17a7-995cba20-26f-ca | MF-NA-1202 | DDG - Danish Demining Group | AF/1604/15227/MF4128 | 16000 | 67.1992 | 37.2476 | Open | AP Only | AP Only | MineField |  | MBT Project-037/B | Balkh Demining Project-1/B |  |  |  |  | 1394 |  | {9D636B66-5594-4064-BABD-B0E51724651E} |  | Medium | Agriculture Blocked | Moderate | 13 | CHA | 3 |  |  | 2009-01-01 | No | Open
North | Balkh | Zari | Qsh Kalan | {B801E3C3-C600-49C4-A547-DEE7C030D25A} | c0a8-0009-13b83134179-4061c1e5-10e-5f | Hz-ID-17458 | MCPA - Mine Clearance Planning Agency | AF/1617/15107/MF0005 | 2372 | 66.801 | 35.8957 | Open | AP Only | AP Only | MineField |  | MBT Project-094 | Balkh Demining Project-1 (AT) |  |  |  |  | 1395 |  | {B801E3C3-C600-49C4-A547-DEE7C030D25A} |  | Medium | Comunity Centers | Low | 17 | CHA | 5 |  |  | 2012-09-11 16:30 | No | Open
North | Faryab | Almar | Khwaja Gawhar | {6ABE3DAF-67BD-4062-BCB6-C6F3BD37389B} | c0a8-0057-12c3b8663f3-4754a5d5-1dfa8- | MF-NA-918 | MCPA - Mine Clearance Planning Agency | AF/1803/16442/MF0004 | 2700 | 64.2802 | 35.9189 | Open | AT Only | AT Only | MineField | Blank | MBT Project-245 | Faryab Demining Project-2 |  | No |  |  | 1394 | None | {6ABE3DAF-67BD-4062-BCB6-C6F3BD37389B} |  | High with Victim | High with Victims | Moderate | 318 | CHA | 2 |  |  | 2008-06-01 | No | Open
North | Faryab | Almar | Khwaja Gawhar | {6ABE3DAF-67BD-4062-BCB6-C6F3BD37389B} | c0a8-0057-12c3b928c2e-f7b19101-263d3- | MF-NA-915 | MCPA - Mine Clearance Planning Agency | AF/1803/16442/MF0003 | 6800 | 64.2762 | 35.9196 | Open | AT Only | AT Only | MineField | Blank | MBT Project-245 | Faryab Demining Project-2 |  | No |  |  | 1394 | None | {6ABE3DAF-67BD-4062-BCB6-C6F3BD37389B} |  | High with Victim | High with Victims | Moderate | 37 | CHA | 2 |  |  | 2008-06-01 | No | Open
North | Faryab | Almar | Nughayli Pa'in | {935EAABE-027C-4847-B38E-99DFC40C481C} | c0a8-0057-12c3b8911a8-e08fd0ae-1fdc4- | MF-NA-916 | MCPA - Mine Clearance Planning Agency | AF/1803/16451/MF0001 | 8248 | 64.5344 | 35.8627 | Open | AT Only | AT Only | MineField | Blank | MBT Project-245 | Faryab Demining Project-2 |  | No |  |  | 1394 | None | {935EAABE-027C-4847-B38E-99DFC40C481C} |  | High Requested | Resettlment/Local Request | Moderate | 625 | CHA | 4 |  |  | 2008-05-01 | No | Open
North | Faryab | Dawlatabad | Qoraish | {0BED66DD-CFD7-4E39-807A-6E4559CB18DE} | c0a8-0009-145caab3815-b7ccca25-167c-e | Hz-ID-18655 | MCPA - Mine Clearance Planning Agency | AF/1809/16771/BF0001 | 4718 | 64.9193 | 36.4195 | Open | UXO Only | UXO Only | BF |  | MBT Project-245 | Faryab Demining Project-2 |  |  |  |  | 1394 |  | {0BED66DD-CFD7-4E39-807A-6E4559CB18DE} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 3 |  |  | 2014-03-24 16:30 | No | Open
North | Faryab | Ghormach | Ab-i-Garmak(1) | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} | c0a8-0057-12c3ba30843-80cc25c-30c80-c | MF-HQ-10982 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1905/17122/MF0046 | 450000 | 63.824 | 35.731 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} |  | Low | Agriculture Blocked | High | 167 | SHA | 4 |  |  | 2009-06-17 | No | Open
North | Faryab | Ghormach | Ab-i-Garmak(1) | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} | c0a8-0057-12c3ba92554-18ea734c-34795- | MF-HQ-8289 | MCPA - Mine Clearance Planning Agency | AF/1905/17122/MF0035 | 20495 | 63.8238 | 35.7308 | Open | AP Only | AP Only | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} |  | Low | Agriculture Blocked | High | 211 | CHA | 5 |  |  | 2001-07-21 | No | Open
North | Faryab | Ghormach | Ab-i-Garmak(1) | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} | c0a8-008e-130ab5f8aa3-d69d4525-c56-f5 | MF-HQ-8281 | MCPA - Mine Clearance Planning Agency | AF/1905/17122/MF0034 | 26410 | 63.8757 | 35.7223 | Open | Mixed | Mixed AP UXO | MineField | Blank | MBT Project-199 | Faryab Demining Project-1 |  | No |  |  | 1397 | None | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} |  | Medium | Critical Infrastracture | High | 188 | CHA | 3 |  |  | 2001-07-09 | No | Open
North | Faryab | Ghormach | Ab-i-Garmak(1) | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} | c0a8-008e-130ab6170b6-6fd67ab0-d00-52 | MF-WA-18 | MCPA - Mine Clearance Planning Agency | AF/1905/17122/MF0040 | 6720 | 63.8066 | 35.7394 | Open | AP Only | AP Only | MineField | Blank | MBT Project-199 | Faryab Demining Project-1 |  | No |  |  | 1397 | None | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} | Planned year and agency removed | Medium | Water Blocked | High | 74 | CHA | 3 |  |  | 2003-06-30 | No | Open
North | Faryab | Ghormach | Ab-i-Garmak(1) | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} | c0a8-008e-130ab631652-6d5505ac-d95-4f | MF-WA-50 | MCPA - Mine Clearance Planning Agency | AF/1905/17122/MF0041 | 16344 | 63.7977 | 35.7385 | Open | AP Only | AP Only | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} |  | Medium | Water Blocked | High | 134 | CHA | 3 |  |  | 2003-06-30 | No | Open
North | Faryab | Ghormach | Ab-i-Garmak(1) | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} | c0a8-008e-130ab645c52-2df5904-e22-54b | MF-WA-72 | MCPA - Mine Clearance Planning Agency | AF/1905/17122/MF0033 | 51240 | 63.818 | 35.7343 | Open | AP Only | AP Only | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {2F00E548-7AB9-40A5-BC73-3BF83D682A8A} |  | Low | Agriculture Blocked | High | 329 | CHA | 5 |  |  | 2003-06-30 | No | Open
North | Faryab | Ghormach | Ghormach | {58E2C52F-96B1-4C01-9693-84B9DE4102A3} | c0a8-008e-130ab607d28-fab0c37a-c98-af | MF-HQ-7296 | MCPA - Mine Clearance Planning Agency | AF/1905/17137/MF0029 | 71665 | 63.8664 | 35.6809 | Open | Mixed | Mixed AP AT UXO | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {58E2C52F-96B1-4C01-9693-84B9DE4102A3} |  | High with Victim | High with Victims | High | 12 | CHA | 1 |  |  | 2000-06-25 | No | Open
North | Faryab | Ghormach | Hajian | {F79DCAC7-734D-4669-B966-72A138C98B2F} | c0a8-0057-12c3b7fe256-e073e750-195c7- | MF-HQ-10977 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1905/00778/MF0047 | 140525 | 63.7968 | 35.7953 | Open | Mixed Mine | Mixed Mine | Converted From SHA | Blank | MBT Project-199 | Faryab Demining Project-1 |  | No |  |  | 1397 | None | {F79DCAC7-734D-4669-B966-72A138C98B2F} |  | Low | Infrastructure | High | 15 | SHA | 5 |  |  | 2009-06-17 | No | Open
North | Faryab | Ghormach | Petaw | {6C531F9F-B1B3-47E8-9190-D629667E01BC} | c0a8-0057-12c3b94120a-7682dc74-27405- | MF-HQ-10976 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1905/17143/MF0048 | 32775 | 63.8185 | 35.7539 | Open | AP Only | AP Only | Converted From SHA | Blank | MBT Project-199 | Faryab Demining Project-1 |  | No |  |  | 1397 | None | {6C531F9F-B1B3-47E8-9190-D629667E01BC} |  | High with Victim | High with Victims | High | 76 | SHA | 1 |  |  | 2009-06-17 | No | Open
North | Faryab | Ghormach | Petaw | {6C531F9F-B1B3-47E8-9190-D629667E01BC} | c0a8-0057-12c3babacb5-6dc22d1e-35ed8- | MF-HQ-10975 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1905/17143/MF0049 | 26775 | 63.8185 | 35.7539 | Open | AP Only | AP Only | Converted From SHA | Blank | MBT Project-199 | Faryab Demining Project-1 |  | No |  |  | 1397 | None | {6C531F9F-B1B3-47E8-9190-D629667E01BC} |  | High with Victim | High with Victims | High | 76 | SHA | 1 |  |  | 2009-06-17 | No | Open
North | Faryab | Ghormach | Qala-i-Wali (1) | {6244B5E5-4606-4062-8EF4-33D1DEA17A00} | c0a8-0057-12c3b8678e9-d65b424f-1e089- | MF-HQ-10974 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1905/17091/MF0050 | 100000 | 63.769 | 35.815 | Open | AP Only | AP Only | Converted From SHA | Blank | MBT Project-199 | Faryab Demining Project-1 |  | No |  |  | 1397 | None | {6244B5E5-4606-4062-8EF4-33D1DEA17A00} |  | Medium | Critical Infrastracture | High | 18 | SHA | 3 |  |  | 2009-06-17 | No | Open
North | Faryab | Ghormach | Qala-i-Wali (1) | {6244B5E5-4606-4062-8EF4-33D1DEA17A00} | c0a8-0057-12c3bab231d-7fdc422d-359b9- | MF-HQ-10973 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1905/17091/MF0051 | 181300 | 63.7784 | 35.8227 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {6244B5E5-4606-4062-8EF4-33D1DEA17A00} |  | Low | Agriculture Blocked | High | 33 | SHA | 5 |  |  | 2009-06-17 | No | Open
North | Faryab | Ghormach | Sari Chashmai Pamakhtu | {BC38A4C9-6EBD-410D-B0BB-47A846A1E7CC} | c0a8-0057-12c3ba6ccbf-dc260012-3314f- | MF-HQ-10981 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1905/00581/MF0052 | 300000 | 63.8815 | 35.6277 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {BC38A4C9-6EBD-410D-B0BB-47A846A1E7CC} |  | Low | Agriculture Blocked | High | 8 | SHA | 4 |  |  | 2009-06-17 | No | Open
North | Faryab | Ghormach | Shadi Kam (2) | {D6C8A32A-7644-46D5-8EDF-9006A359686D} | c0a8-0057-12c3b7f678d-205b596-1903e-8 | MF-HQ-10972 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1905/17135/MF0053 | 320000 | 63.9135 | 35.6441 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {D6C8A32A-7644-46D5-8EDF-9006A359686D} |  | Low | Agriculture Blocked | High | 335 | SHA | 4 |  |  | 2009-06-17 | No | Open
North | Faryab | Ghormach | Shadi Kam (2) | {D6C8A32A-7644-46D5-8EDF-9006A359686D} | c0a8-0057-12c3bb24ba1-71c67452-39e3e- | MF-HQ-10970 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1905/17135/MF0055 | 105000 | 63.907 | 35.6527 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {D6C8A32A-7644-46D5-8EDF-9006A359686D} |  | Low | Agriculture Blocked | High | 34 | SHA | 5 |  |  | 2009-06-17 | No | Open
North | Faryab | Ghormach | Shadi Kam (2) | {D6C8A32A-7644-46D5-8EDF-9006A359686D} | c0a8-0057-12c3bb33429-d25cc46a-3a6e5- | MF-HQ-10971 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1905/17135/MF0054 | 900000 | 63.9148 | 35.6448 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {D6C8A32A-7644-46D5-8EDF-9006A359686D} |  | Low | Agriculture Blocked | High | 515 | SHA | 4 |  |  | 2009-06-17 | No | Open
North | Faryab | Kohistan | Qudoghak (2) | {53CF9FFB-53EB-4CA6-9F78-1659CFECAA5C} | c0a8-0057-12fbfaa3b6b-d26a084b-2736-4 | MF-NA-825 | MCPA - Mine Clearance Planning Agency | AF/1805/16413/MF0002 | 5967 | 64.8022 | 35.3638 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {53CF9FFB-53EB-4CA6-9F78-1659CFECAA5C} |  | Medium | Agriculture Blocked | Moderate | 13 | CHA | 3 |  |  | 2008-05-01 | No | Open
North | Faryab | Kohistan | Qudoghak (2) | {53CF9FFB-53EB-4CA6-9F78-1659CFECAA5C} | c0a8-008e-131944aa558-ca56eaff-ed2-76 | MF-NA-824 | MCPA - Mine Clearance Planning Agency | AF/1805/16413/MF0001 | 12352 | 64.794 | 35.3635 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {53CF9FFB-53EB-4CA6-9F78-1659CFECAA5C} |  | Medium | Agriculture Blocked | Moderate | 15 | CHA | 3 |  |  | 2008-05-01 | No | Open
North | Faryab | Maymana | Hemat Abad | {B3FDAF1C-C3ED-4583-AE52-D79AC44619A3} | c0a8-0009-13dbff30712-78f747cc-5d42-2 | Hz-ID-17714 | MCPA - Mine Clearance Planning Agency | AF/1801/16351/BF0011 | 185 | 64.7951 | 35.9057 | Open | UXO Only | UXO Only | BF |  | MBT Project-245 | Faryab Demining Project-2 |  |  |  |  | 1394 |  | {B3FDAF1C-C3ED-4583-AE52-D79AC44619A3} |  | Medium | Agriculture Blocked | Low | 134 | CHA | 3 |  |  | 2013-01-14 16:30 | No | Open
North | Faryab | Maymana | Pat Abad (1) | {B6F1599B-6A85-4C89-8E30-474503993E82} | c0a8-0057-12c3b891531-7cd2af3f-1fddf- | MF-NA-917 | MCPA - Mine Clearance Planning Agency | AF/1803/16188/MF0002 | 24678 | 64.5343 | 35.8996 | Open | AT Only | AT Only | MineField | Blank | MBT Project-245 | Faryab Demining Project-2 |  | No |  |  | 1394 | None | {B6F1599B-6A85-4C89-8E30-474503993E82} |  | High Requested | Resettlment/Local Request | Low | 81 | CHA | 5 |  |  | 2008-05-01 | No | Open
North | Faryab | Pashtun Kot | Bad Qaq | {2C942765-A6CA-41AE-96F4-3230E0DAF5C2} | c0a8-0057-12c3b844033-2c72191c-1c759- | MF-NA-849 | MCPA - Mine Clearance Planning Agency | AF/1813/16326/MF0006 | 4331 | 64.6649 | 36.0992 | Open | AT Only | AT Only | MineField | Blank | MBT Project-245 | Faryab Demining Project-2 |  | No |  |  | 1394 | None | {2C942765-A6CA-41AE-96F4-3230E0DAF5C2} |  | High Requested | Resettlment/Local Request | Moderate | 83 | CHA | 3 |  |  | 2008-06-01 | No | Open
North | Faryab | Pashtun Kot | Hasan Bulaq | {2F472026-4483-4DFB-A2C6-CF5FB9AA2C87} | c0a8-0057-12c3bac29ee-c49eb4c7-36375- | MF-HQ-11150 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1802/16329/MF0011 | 21000 | 64.7101 | 36.0866 | Open | AT Only | AT Only | MineField | Blank | MBT Project-245 | Faryab Demining Project-2 |  | No |  |  | 1394 | None | {2F472026-4483-4DFB-A2C6-CF5FB9AA2C87} |  | High Requested | Resettlment/Local Request | Moderate | 16 | CHA | 5 |  |  | 2009-06-21 | No | Open
North | Faryab | Pashtun Kot | Hasan Bulaq | {2F472026-4483-4DFB-A2C6-CF5FB9AA2C87} | c0a8-0057-12c3bac3035-8826a20d-3638c- | MF-NA-850 | MCPA - Mine Clearance Planning Agency | AF/1813/16329/MF0007 | 70840 | 64.6728 | 36.0965 | Open | AT Only | AT Only | MineField | Blank | MBT Project-245 | Faryab Demining Project-2 |  | No |  |  | 1394 | None | {2F472026-4483-4DFB-A2C6-CF5FB9AA2C87} |  | High Requested | Resettlment/Local Request | Moderate | 1724 | CHA | 4 |  |  | 2008-06-01 | No | Open
North | Faryab | Pashtun Kot | Takatozi | {FD1ADF72-EE8B-448F-B6D4-2A1977ABB6AF} | c0a8-0057-12c3b99d17a-9b509746-2b087- | MF-NA-848 | MCPA - Mine Clearance Planning Agency | AF/1813/16272/MF0005 | 24120 | 64.7465 | 36.0963 | Open | AT Only | AT Only | MineField | Blank | MBT Project-245 | Faryab Demining Project-2 |  | No |  |  | 1394 | None | {FD1ADF72-EE8B-448F-B6D4-2A1977ABB6AF} |  | High Requested | Resettlment/Local Request | Moderate | 14 | CHA | 5 |  |  | 2008-06-01 | No | Open
North | Faryab | Qaysar | Alat (2) | {6FBE7D87-89C8-4FAC-B5B3-90CE327011C8} | c0a8-0057-12c3b89cdb4-c645b774-20585- | MF-NA-865 | MCPA - Mine Clearance Planning Agency | AF/1804/16603/MF0014 | 58500 | 64.0986 | 35.5431 | Open | AP Only | AP Only | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {6FBE7D87-89C8-4FAC-B5B3-90CE327011C8} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-06-01 | No | Open
North | Faryab | Qaysar | Do Abi | {18DCB05A-D4CB-4163-9762-155E36DEE535} | c0a8-0057-12c3b7db006-95fbd5c6-17d50- | MF-HQ-10672 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1808/16559/MF0014 | 666298 | 63.9083 | 35.7466 | Open | AP Only | AP Only | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {18DCB05A-D4CB-4163-9762-155E36DEE535} |  | Low | Agriculture Blocked | Substantial | 334 | CHA | 4 |  |  | 2009-06-17 | No | Open
North | Faryab | Qaysar | Do Abi | {18DCB05A-D4CB-4163-9762-155E36DEE535} | c0a8-0057-12c3b879e8f-5094a93d-1ed3f- | MF-HQ-7207 | MCPA - Mine Clearance Planning Agency | AF/1804/00066/MF0010 | 90349 | 63.9236 | 35.7517 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {18DCB05A-D4CB-4163-9762-155E36DEE535} |  | Medium | Agriculture Blocked | Substantial | 798 | CHA | 3 |  |  | 2000-05-03 | No | Open
North | Faryab | Qaysar | Do Abi | {18DCB05A-D4CB-4163-9762-155E36DEE535} | c0a8-0057-12c3bb54bb9-11773d45-3ba7c- | MF-HQ-7223 | MCPA - Mine Clearance Planning Agency | AF/1804/00066/MF0013 | 59698 | 64.0705 | 35.7484 | Open | AP Only | AP Only | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {18DCB05A-D4CB-4163-9762-155E36DEE535} |  | Low | Agriculture Blocked | Substantial | 19 | CHA | 4 |  |  | 2000-05-24 | No | Open
North | Faryab | Qaysar | Karez (1) | {F48B9909-93A4-426C-A290-D37A6DBCCCAB} | c0a8-0057-12c3ba1905a-8d086122-2fe43- | MF-NA-866 | MCPA - Mine Clearance Planning Agency | AF/1804/14146/MF0016 | 54341 | 63.9072 | 35.766 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {F48B9909-93A4-426C-A290-D37A6DBCCCAB} |  | High with Victim | High with Victims | Substantial | 480 | CHA | 3 |  |  | 2008-06-01 | No | Open
North | Faryab | Qaysar | Qaysar | {856686A2-C8C8-4A71-99F9-A6F139CF198B} | c0a8-008e-131364a9aef-a3ddf504-3-bbbf | BF-NA-914 | MCPA - Mine Clearance Planning Agency | AF/1804/31906/BF0015 | 120 | 64.2938 | 35.6893 | Open | UXO Only | UXO Only | BF |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {856686A2-C8C8-4A71-99F9-A6F139CF198B} |  | High with Victim | High with Victims | Substantial | 686 | CHA | 1 |  |  | 2008-06-01 | No | Open
North | Faryab | Qaysar | Tash Bulaq | {C0152B92-C41E-4218-948C-B2A8F37D613F} | c0a8-008e-132e711afe7-fe41dcd-138-479 | MF-NA-867 | MCPA - Mine Clearance Planning Agency | AF/1804/16606//MF0017 | 56400 | 64.1348 | 35.5367 | Open | AP Only | AP Only | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {C0152B92-C41E-4218-948C-B2A8F37D613F} |  | Low | Critical Infrastracture | Substantial | 0 | CHA | 5 |  |  | 2008-06-01 | No | Open
North | Faryab | Qaysar | Tash Bulaq | {C0152B92-C41E-4218-948C-B2A8F37D613F} | c0a8-008e-132e717d4fc-641d3330-17d-b6 | MF-NA-868 | MCPA - Mine Clearance Planning Agency | AF/1804/16606/MF0018 | 95074 | 64.1363 | 35.5293 | Open | AP Only | AP Only | MineField |  | MBT Project-199 | Faryab Demining Project-1 |  |  |  |  | 1397 |  | {C0152B92-C41E-4218-948C-B2A8F37D613F} |  | Low | Critical Infrastracture | Substantial | 2 | CHA | 5 |  |  | 2008-06-01 | No | Open
North | Faryab | Qurghan | Bagh-i-Bustan | {E6F8419A-6D1A-41F2-B954-7D9F4E874BF0} | c0a8-0009-145cb241de7-6c1a1864-1ae3-2 | Hz-ID-18672 | MCPA - Mine Clearance Planning Agency | AF/1812/16128/SERW0001 | 93 | 65.0833 | 36.9505 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-245 | Faryab Demining Project-2 |  |  |  |  | 1394 |  | {E6F8419A-6D1A-41F2-B954-7D9F4E874BF0} |  | Medium | Small Hazards | Low | 3572 | CHA | 3 |  |  | 2014-03-15 16:30 | No | Open
North | Faryab | Shirin Tagab | Jalaier (5) | {60A79567-8427-4F92-8228-14C02FAEFBF9} | c0a8-0057-12c3b7fe9a6-8d4ed654-19619- | MF-HQ-10670 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1808/16559/MF0006 | 121566 | 64.5978 | 36.3417 | Open | AP Only | AP Only | MineField |  | MBT Project-245 | Faryab Demining Project-2 |  |  |  |  | 1394 |  | {60A79567-8427-4F92-8228-14C02FAEFBF9} |  | Low | Agriculture Blocked | High | 14 | CHA | 5 |  |  | 2009-06-17 | No | Open
North | Jawzjan | Khwaja Du Koh | Khvajeh Do Kuh Now | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} | c0a8-0009-13adefdc420-6cd7bd09-145b-8 | Hz-ID-17346 | ATC - Afghan Technical Consultants | AF/1702/15377/MF0031 | 57883 | 65.5785 | 36.8118 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} |  | High Requested | Resettlment/Local Request | Low | 406 | CHA | 1 | Yes | This area was in conflict of two parties General Dostom and Taliban, so this area located close to the community about less than one km | 2012-09-24 16:30 | No | Open
North | Jawzjan | Khwaja Du Koh | Khvajeh Do Kuh Now | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} | c0a8-0009-13adf00a7ba-d95b98da-1478-a | Hz-ID-17349 | ATC - Afghan Technical Consultants | AF/1702/15377/MF0032 | 68736 | 65.5772 | 36.824 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} |  | High Requested | Resettlment/Local Request | Low | 406 | CHA | 1 | Yes |  | 2012-09-26 16:30 | No | Open
North | Jawzjan | Khwaja Du Koh | Khvajeh Do Kuh Now | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} | c0a8-0009-13adf06979a-de2e31a5-14cb-a | Hz-ID-17353 | ATC - Afghan Technical Consultants | AF/1702/15377/MF0033 | 44816 | 65.576 | 36.8261 | Open | AP Only | AP Only | MineField |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} |  | High Requested | Resettlment/Local Request | Low | 225 | CHA | 1 | Yes |  | 2012-09-26 16:30 | No | Open
North | Jawzjan | Khwaja Du Koh | Khvajeh Do Kuh Now | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} | c0a8-0009-13d152831cb-31cf79de-2864-3 | Hz-ID-17673 | MCPA - Mine Clearance Planning Agency | AF/1702/15377/BF0036 | 1829 | 65.5739 | 36.8161 | Open | UXO Only | UXO Only | BF |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} |  | Medium | Agriculture Blocked | Low | 0 | CHA | 3 |  |  | 2012-11-21 16:30 | No | Open
North | Jawzjan | Khwaja Du Koh | Khvajeh Do Kuh Now | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} | c0a8-0009-13d160407e0-785bef2f-2da1-4 | Hz-ID-17674 | MCPA - Mine Clearance Planning Agency | AF/1702/15377/BF0035 | 1565 | 65.5739 | 36.818 | Open | UXO Only | UXO Only | BF |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} |  | Medium | Agriculture Blocked | Low | 0 | CHA | 3 |  |  | 2012-11-21 16:30 | No | Open
North | Jawzjan | Khwaja Du Koh | Khvajeh Do Kuh Now | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} | c0a8-0009-13d1a24aaa2-a4bc784-105-9aa | Hz-ID-17675 | MCPA - Mine Clearance Planning Agency | AF/1702/15377/MF0034 | 43315 | 65.5163 | 36.9909 | Open | AT Only | AT Only | MineField |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} |  | Low | Critical Infrastracture | Low | 0 | CHA | 5 |  |  | 2012-11-21 16:30 | No | Open
North | Jawzjan | Khwaja Du Koh | Khvajeh Do Kuh Now | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} | c0a8-0009-13d1a26bc9b-2fd52bb7-15c-11 | Hz-ID-17676 | MCPA - Mine Clearance Planning Agency | AF/1702/15377/MF0037 | 10280 | 65.5176 | 37.0005 | Open | AT Only | AT Only | MineField |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {5340AE3E-E3B1-4CB5-A5A1-CEE9D0AEE2A9} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2012-11-22 16:30 | No | Open
North | Jawzjan | Khwaja Du Koh | Khwaja Du Koh | {1B9A8298-16EE-4E6D-9A15-FF6E04AF271C} | c0a8-0009-13d1a38b073-37991c34-1f7-a7 | Hz-ID-17678 | MCPA - Mine Clearance Planning Agency | AF/1702/31057/BF0040 | 12826 | 65.6118 | 36.8275 | Open | UXO Only | UXO Only | BF |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {1B9A8298-16EE-4E6D-9A15-FF6E04AF271C} |  | High with Victim | High with Victims | Low | 58 | CHA | 2 |  |  | 2012-12-05 16:30 | No | Open
North | Jawzjan | Khwaja Du Koh | Qizilayaq Kalan | {9D33DDF7-A9AE-48C8-BBA7-9659E8302E69} | c0a8-0009-13d1523aa94-8aa9ffb0-2837-f | Hz-ID-17672 | MCPA - Mine Clearance Planning Agency | AF/1702/15374/BF0038 | 77856 | 65.7155 | 36.9134 | Open | UXO Only | UXO Only | BF |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {9D33DDF7-A9AE-48C8-BBA7-9659E8302E69} |  | Low | Infrastructure | Low | 0 | CHA | 5 |  |  | 2012-11-25 16:30 | No | Open
North | Jawzjan | Khwaja Du Koh | Qizilayaq Kalan | {9D33DDF7-A9AE-48C8-BBA7-9659E8302E69} | c0a8-0009-13d1a2b2598-acbee589-188-e4 | Hz-ID-17677 | MCPA - Mine Clearance Planning Agency | AF/1702/15374/MF0039 | 1764 | 65.7306 | 37.0152 | Open | AT Only | AT Only | MineField |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {9D33DDF7-A9AE-48C8-BBA7-9659E8302E69} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2012-11-26 16:30 | No | Open
North | Jawzjan | Mardyan | Khan Aregh | {C2FD1723-C133-4908-AC43-1B347D9B8AFE} | c0a8-0009-13d0fe85298-597fb946-3bf0-8 | Hz-ID-17669 | MCPA - Mine Clearance Planning Agency | AF/1707/16005/BF0001 | 1286 | 66.3194 | 36.9907 | Open | UXO Only | UXO Only | BF |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {C2FD1723-C133-4908-AC43-1B347D9B8AFE} |  | High | Water Blocked | Low | 202 | CHA | 3 |  |  | 2012-12-10 16:30 | No | Open
North | Jawzjan | Qush Tepa | Chaqma Choqor | {30E8F1F7-FD84-4C44-82C2-DFB1B42B64CB} | c0a8-008e-132e71902e4-2fadca56-19a-96 | MF-NA-819 | MCPA - Mine Clearance Planning Agency | AF/1703/15695/MF0005 | 46716 | 65.4782 | 36.1622 | Open | AP Only | AP Only | MineField |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {30E8F1F7-FD84-4C44-82C2-DFB1B42B64CB} |  | Low | Agriculture Blocked | High | 79 | CHA | 4 |  |  | 2008-05-01 | No | Open
North | Jawzjan | Qush Tepa | Chaqma Choqor | {30E8F1F7-FD84-4C44-82C2-DFB1B42B64CB} | c0a8-008e-132e719df93-cbe0f5ac-1ad-ac | MF-NA-818 | MCPA - Mine Clearance Planning Agency | AF/1703/15695/MF0004 | 47738 | 65.4782 | 36.1622 | Open | AP Only | AP Only | MineField |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {30E8F1F7-FD84-4C44-82C2-DFB1B42B64CB} |  | Low | Agriculture Blocked | High | 79 | CHA | 4 |  |  | 2008-05-01 | No | Open
North | Jawzjan | Shibirghan | Shor Jar (2) | {BD894A8B-5EE8-4429-9C6F-B7D0D816C98E} | c0a8-0009-13d0ff358e0-384d9b88-3c30-a | Hz-ID-17670 | MCPA - Mine Clearance Planning Agency | AF/1701/15388/BF0012 | 153957 | 65.7277 | 36.563 | Open | UXO Only | UXO Only | BF |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {BD894A8B-5EE8-4429-9C6F-B7D0D816C98E} |  | Low | Agriculture Blocked | Moderate | 62 | CHA | 5 |  |  | 2012-11-14 16:30 | No | Open
North | Jawzjan | Shibirghan | Shor Jar (2) | {BD894A8B-5EE8-4429-9C6F-B7D0D816C98E} | c0a8-0009-13d14c05475-2a5a2a0d-271e-e | Hz-ID-17671 | MCPA - Mine Clearance Planning Agency | AF/1701/15388/BF0013 | 151598 | 65.7277 | 36.563 | Open | UXO Only | UXO Only | BF |  | MBT Project-039 | Jawzjan Demining Project-1 |  |  |  |  | 1394 |  | {BD894A8B-5EE8-4429-9C6F-B7D0D816C98E} |  | Low | Agriculture Blocked | Moderate | 62 | CHA | 5 |  |  | 2012-11-15 16:30 | No | Open
North | Samangan | Aybak | Aybak | {AF842378-BABE-49D0-AA98-612B500A85CA} | c0a8-0057-12c3b68ec40-b128ce3f-86a6-e | MF-HQ-11824 | HT - HALO TRUST | H/4805 | 2000 | 68.4955 | 36.1939 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {AF842378-BABE-49D0-AA98-612B500A85CA} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2008-06-04 | No | Open
North | Samangan | Aybak | Aybak | {AF842378-BABE-49D0-AA98-612B500A85CA} | c0a8-0057-12c3b77e354-3c2b7f27-13a46- | MF-HQ-11821 | HT - HALO TRUST | H/4804 | 40150 | 68.4676 | 36.2127 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {AF842378-BABE-49D0-AA98-612B500A85CA} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2008-06-04 | No | Open
North | Samangan | Aybak | Darrah-i-Zendan | {0E3FE3E4-DCCA-4FBF-9AD0-D08CAADC9CF5} | c0a8-0009-143851ced28-9f671606-44e5-1 | Hz-ID-18390 | HT - HALO TRUST | H/8896 | 63262 | 68.0192 | 36.1902 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {0E3FE3E4-DCCA-4FBF-9AD0-D08CAADC9CF5} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2013-12-09 16:30 | No | Open
North | Samangan | Aybak | Darrah-i-Zendan | {0E3FE3E4-DCCA-4FBF-9AD0-D08CAADC9CF5} | c0a8-0009-14385213a8b-f63223de-455f-7 | Hz-ID-18392 | HT - HALO TRUST | H/8898 | 23127 | 68.0095 | 36.1861 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {0E3FE3E4-DCCA-4FBF-9AD0-D08CAADC9CF5} |  | Low | Agriculture Blocked | Low | 7 | CHA | 5 |  |  | 2013-12-10 16:30 | No | Open
North | Samangan | Aybak | Darrah-i-Zendan | {0E3FE3E4-DCCA-4FBF-9AD0-D08CAADC9CF5} | c0a8-0057-12c3b9bd549-2d1c42c8-2c565- | MF-HQ-11461 | HT - HALO TRUST | H/2755 | 24380 | 68.0624 | 36.216 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-041/A | Samangan Demining Project-10 /A | B-Sweden | Yes | 2013-12-01 | 2013-12-24 | 1392 | DDG | {0E3FE3E4-DCCA-4FBF-9AD0-D08CAADC9CF5} |  |  |  | Low | 19 | CHA | 5 |  |  | 2008-08-03 | No | Complete
North | Samangan | Aybak | Darrah-i-Zendan (2) | {6348AC52-98DE-4B33-8CB4-8C1FF9373E51} | c0a8-0057-12c3b6b4cc1-f27567b-a2c5-b1 | MF-NA-1224 | HT - HALO TRUST | H/5837 | 496500 | 67.9741 | 36.1947 | Open | AT Only | AT Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {6348AC52-98DE-4B33-8CB4-8C1FF9373E51} |  | High Requested | Resettlment/Local Request | Low | 5 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Aybak | Darrah-i-Zendan (2) | {6348AC52-98DE-4B33-8CB4-8C1FF9373E51} | c0a8-0057-12c3b6bf29f-8b00cec4-aab4-b | MF-NA-1228 | HT - HALO TRUST | H/5839 | 2200 | 68.0923 | 36.1968 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {6348AC52-98DE-4B33-8CB4-8C1FF9373E51} |  | High Requested | Resettlment/Local Request | Low | 12 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Aybak | Darrah-i-Zendan (2) | {6348AC52-98DE-4B33-8CB4-8C1FF9373E51} | c0a8-0057-12c3b70b2a6-83c24077-e499-f | MF-NA-1227 | HT - HALO TRUST | H/5838 | 101400 | 68.0001 | 36.1978 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {6348AC52-98DE-4B33-8CB4-8C1FF9373E51} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Aybak | Orlamish | {FBB20C68-D7F4-4DA5-81E3-2388ECD90374} | c0a8-0057-12c3b798ca9-3a59c931-14dba- | MF-HQ-11954 | HT - HALO TRUST | H/5207 | 1200 | 67.7715 | 36.2398 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {FBB20C68-D7F4-4DA5-81E3-2388ECD90374} |  | Low | Agriculture Blocked | Low | 62 | CHA | 5 |  |  | 2008-09-19 | No | Planned
North | Samangan | Aybak | Royancha(2) | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} | c0a8-008e-1342ccb8ab5-a1e7e59f-4ef-44 | MF-16406 | HT - HALO TRUST | H/8256 | 39900 | 67.8143 | 36.1406 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130/A | Samangan Demining Project-11/A |  | No |  |  | 1395 | DDG | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} |  | Low | Agriculture Blocked | Low | 51 | CHA | 5 |  |  | 2011-11-20 16:30 | No | Open
North | Samangan | Aybak | Royancha(2) | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} | c0a8-00f6-135286719b9-efcc6109-5bc-18 | MF-16550 | HT - HALO TRUST | H/8261 | 9800 | 67.7347 | 36.2194 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-130/A | Samangan Demining Project-11/A |  | No |  |  | 1395 | DDG | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} |  | Low | Critical Infrastracture | Low | 7 | CHA | 5 |  |  | 2011-12-13 16:30 | No | Open
North | Samangan | Aybak | Royancha(2) | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} | c0a8-00f6-1352868d5d0-2d4abcaf-5d7-25 | MF-16551 | HT - HALO TRUST | H/8258 | 18500 | 67.7979 | 36.0882 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130/A | Samangan Demining Project-11/A |  | No |  |  | 1395 | DDG | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} |  | Low | Agriculture Blocked | Low | 5 | CHA | 5 |  |  | 2011-12-05 16:30 | No | Open
North | Samangan | Aybak | Royancha(2) | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} | c0a8-00f6-135286a745a-b9598610-5f8-7c | MF-16552 | HT - HALO TRUST | H/8257 | 57540 | 67.7961 | 36.0332 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130/A | Samangan Demining Project-11/A |  | No |  |  | 1395 | DDG | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} |  | Low | Agriculture Blocked | Low | 12 | CHA | 5 |  |  | 2011-12-04 16:30 | No | Open
North | Samangan | Aybak | Royancha(2) | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} | c0a8-00f6-1352e30ae9b-32213ec4-b1-99f | MF-16559 | HT - HALO TRUST | H/8259 | 4100 | 67.7993 | 36.0868 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130/A | Samangan Demining Project-11/A |  | No |  |  | 1395 | DDG | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} |  | Low | Agriculture Blocked | Low | 15 | CHA | 5 |  |  | 2011-12-05 16:30 | No | Open
North | Samangan | Aybak | Royancha(2) | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} | c0a8-00f6-1352e50cb12-52599760-163-b8 | MF-16556 | HT - HALO TRUST | H/8260 | 5200 | 67.7641 | 36.2631 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-130/A | Samangan Demining Project-11/A |  | No |  |  | 1395 | DDG | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} |  | Low | Critical Infrastracture | Low | 11 | CHA | 5 |  |  | 2011-12-12 16:30 | No | Open
North | Samangan | Aybak | Royancha(2) | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} | c0a8-00f6-135e28fd484-9ece44e2-e620-2 | MF-16713 | HT - HALO TRUST | H/8262 | 60 | 67.7005 | 36.0932 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {C2D08DFD-CE56-4506-A486-CF2989F5BF27} |  | Medium | Critical Infrastracture | Low | 0 | CHA | 3 |  |  | 2012-01-01 16:30 | No | Open
North | Samangan | Aybak | Senjetak | {0262046E-429C-4FC1-BF0C-A5B107AC80FB} | c0a8-0057-12c3b7164c4-86a45e58-ecf9-9 | MF-HQ-14927 | MCPA - Mine Clearance Planning Agency | AF/1501/14166/MF0029 | 23311 | 68.0302 | 36.243 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {0262046E-429C-4FC1-BF0C-A5B107AC80FB} |  | Low | Agriculture Blocked | Low | 115 | CHA | 5 |  |  | 2010-09-21 | No | Planned
North | Samangan | Aybak | Shahr-i-Qadim | {3A52EFEA-84C6-4C9B-A8EE-C610D3381636} | c0a8-0009-13fdc675f2b-ba816526-2598-8 | Hz-ID-18052 | HT - HALO TRUST | H/8552 | 202 | 68.0466 | 36.2388 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {3A52EFEA-84C6-4C9B-A8EE-C610D3381636} |  |  |  | Low | 165 | CHA | 3 |  |  | 2013-06-11 16:30 | No | Planned
North | Samangan | Aybak | Shahr-i-Qadim | {3A52EFEA-84C6-4C9B-A8EE-C610D3381636} | c0a8-0009-13fdc682315-493b0058-25b1-9 | HZ-ID-18051 | HT - HALO TRUST | H/8551 | 164 | 68.045 | 36.2395 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {3A52EFEA-84C6-4C9B-A8EE-C610D3381636} |  |  |  | Low | 330 | CHA | 3 |  |  | 2013-06-11 16:30 | No | Planned
North | Samangan | Aybak | Shahr-i-Qadim | {3A52EFEA-84C6-4C9B-A8EE-C610D3381636} | c0a8-0009-143852788b7-fbb2cfb-4651-fd | Hz-ID-18393 | HT - HALO TRUST | H/8905 | 550 | 68.0495 | 36.2371 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes |  |  | 1392 | HT | {3A52EFEA-84C6-4C9B-A8EE-C610D3381636} |  |  |  | Low | 241 | CHA | 3 |  |  | 2014-01-10 16:30 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-0057-12c3b6bd2b1-5339beec-a916-6 | MF-HQ-14753 | HT - HALO TRUST | H/6580 | 4872 | 67.5274 | 35.6845 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-09-01 | 2013-10-23 | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} |  |  |  | Moderate | 119 | CHA | 5 |  |  | 2010-06-01 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-0057-12c3b6c55c3-a3aa57ea-af67-8 | MF-HQ-14548 | HT - HALO TRUST | H/6578 | 30200 | 67.6228 | 35.733 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089/A | Samangan Demining Project-3/A | B-Germany | Yes | 2013-10-01 | 2013-10-23 | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} |  |  |  | Moderate | 46 | CHA | 5 |  |  | 2010-05-17 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-0057-12c3b6d2c51-38bf9fb5-b9b9-3 | MF-HQ-14544 | HT - HALO TRUST | H/6574 | 25960 | 67.6054 | 35.7221 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-07-01 | 2013-08-23 | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} |  |  |  | Moderate | 26 | CHA | 5 |  |  | 2010-05-02 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-0057-12c3b6dce77-ca0fe1a6-c159-8 | MF-HQ-14547 | HT - HALO TRUST | H/6577 | 4790 | 67.6367 | 35.7422 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089/A | Samangan Demining Project-3/A | B-Germany | Yes | 2013-10-01 | 2013-10-23 | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} |  |  |  | Moderate | 14 | CHA | 5 |  |  | 2010-05-18 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-0057-12c3b726d2a-8c2440bc-f97f-c | MF-HQ-11786 | HT - HALO TRUST | H/6189 | 38283 | 67.6091 | 35.725 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-09-01 | 2013-09-23 | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} |  |  |  | Moderate | 8 | CHA | 5 |  |  | 2009-06-18 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-0057-12c3b72e4b8-1038819a-ff22-4 | MF-HQ-14546 | HT - HALO TRUST | H/6576 | 3000 | 67.6315 | 35.7349 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089/A | Samangan Demining Project-3/A | B-Germany | Yes | 2013-10-01 | 2013-10-23 | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} |  |  |  | Moderate | 20 | CHA | 5 |  |  | 2010-05-06 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-0057-12c3b7343c7-582b72eb-103a0- | MF-HQ-11781 | HT - HALO TRUST | H/6187 | 45700 | 67.6013 | 35.7133 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-07-01 | 2013-07-23 | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} |  |  |  | Moderate | 53 | CHA | 5 |  |  | 2009-06-18 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-0057-12c3b795c37-86a28739-14b8a- | MF-HQ-14543 | HT - HALO TRUST | H/6573 | 18810 | 67.5995 | 35.7084 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-07-25 |  | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2010-05-01 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-0057-12c3b7a9e14-7f64d347-15a01- | MF-HQ-11784 | HT - HALO TRUST | H/6188 | 55100 | 67.6017 | 35.7155 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-07-01 | 2013-07-23 | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} |  |  |  | Moderate | 26 | CHA | 5 |  |  | 2009-06-18 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-0057-12c3b7ae511-e934542f-15d33- | MF-HQ-14545 | HT - HALO TRUST | H/6575 | 33000 | 67.6054 | 35.7221 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-07-01 | 2013-07-23 | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} |  |  |  | Moderate | 34 | CHA | 5 |  |  | 2010-05-03 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-008e-13068bba1bc-5238fc64-3cc-f7 | MF-HQ-11801 | HT - HALO TRUST | H/6186 | 66312 | 67.5436 | 35.6783 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089/A | Samangan Demining Project-3/A | B-Germany | Yes | 2013-10-01 | 2013-11-23 | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | Planned year and agency updated |  |  | Moderate | 40 | CHA | 5 |  |  | 2009-06-16 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alamle | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} | c0a8-008e-13068bcc8c7-5592e85c-3ed-3b | MF-HQ-11798 | HT - HALO TRUST | H/6185 | 114365 | 67.5438 | 35.6783 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes |  |  | 1392 | HT | {09890B81-F2E7-4B3D-93D9-FA38F1A31F68} |  |  |  | Moderate | 40 | CHA | 5 |  |  | 2009-06-16 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alimiran | {D3DF20C3-7D92-4D81-A234-12A26B3ABD2A} | c0a8-0009-141029a5dd4-dda93234-6380-e | Hz-ID-18152 | HT - HALO TRUST | H/8586 | 22865 | 67.1401 | 35.7983 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-09-01 | 2014-09-23 | 1393 | HT | {D3DF20C3-7D92-4D81-A234-12A26B3ABD2A} |  | Low | Comunity Centers | Moderate | 139 | CHA | 4 |  |  | 2013-08-23 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Alimiran | {D3DF20C3-7D92-4D81-A234-12A26B3ABD2A} | c0a8-0057-12c3b6f90a8-6312f6f9-d6cb-e | MF-HQ-14342 | HT - HALO TRUST | H/6569 | 41800 | 67.1408 | 35.7998 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-06-01 | 2013-06-22 | 1392 | HT | {D3DF20C3-7D92-4D81-A234-12A26B3ABD2A} |  |  |  | Moderate | 187 | CHA | 4 |  |  | 2010-04-12 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alimiran | {D3DF20C3-7D92-4D81-A234-12A26B3ABD2A} | c0a8-0057-12c3b736b82-e8850824-1056d- | MF-HQ-14341 | HT - HALO TRUST | H/6570 | 25960 | 67.1424 | 35.8017 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-09-01 | 2013-09-23 | 1392 | HT | {D3DF20C3-7D92-4D81-A234-12A26B3ABD2A} |  |  |  | Moderate | 187 | CHA | 4 |  |  | 2010-04-13 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alimiran | {D3DF20C3-7D92-4D81-A234-12A26B3ABD2A} | c0a8-0057-12c3b77e180-ae99aace-13a2c- | MF-HQ-14323 | HT - HALO TRUST | H/6571 | 57200 | 67.1391 | 35.7992 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-07-01 | 2013-08-23 | 1392 | HT | {D3DF20C3-7D92-4D81-A234-12A26B3ABD2A} |  |  |  | Moderate | 231 | CHA | 4 |  |  | 2010-04-15 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Alimiran | {D3DF20C3-7D92-4D81-A234-12A26B3ABD2A} | c0a8-0057-12c3b78d7ed-590e7d3f-14575- | MF-HQ-14340 | HT - HALO TRUST | H/6572 | 53900 | 67.1367 | 35.7981 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-07-01 | 2013-08-23 | 1392 | HT | {D3DF20C3-7D92-4D81-A234-12A26B3ABD2A} |  |  |  | Moderate | 231 | CHA | 4 |  |  | 2010-04-16 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Ashliz | {9B58CD1E-E16E-4DF0-AF03-E29251292E43} | c0a8-0009-1417d1cf822-a41109e4-7c1-52 | Hz-ID-18182 | HT - HALO TRUST | H/8600 | 31845 | 67.1953 | 35.8143 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129/A | Samangan Demining Project-4/A | CIDA | Yes | 2013-12-01 | 2014-01-23 | 1392 | HT | {9B58CD1E-E16E-4DF0-AF03-E29251292E43} |  |  |  | Moderate | 5 | CHA | 5 |  |  | 2013-09-21 16:30 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Ashliz | {9B58CD1E-E16E-4DF0-AF03-E29251292E43} | c0a8-0057-12c3b6d2ec1-f183af37-b9d2-3 | MF-HQ-14452 | HT - HALO TRUST | H/6567 | 9460 | 67.1863 | 35.799 | Worked on | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-07-01 | 2013-07-23 | 1392 | HT | {9B58CD1E-E16E-4DF0-AF03-E29251292E43} |  | Low | Agriculture Blocked | Moderate | 15 | CHA | 5 |  |  | 2010-04-12 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Ashliz | {9B58CD1E-E16E-4DF0-AF03-E29251292E43} | c0a8-0057-12c3b710ab4-da2b193e-e8be-c | MF-HQ-14441 | HT - HALO TRUST | H/6566 | 3622 | 67.1853 | 35.8019 | Worked on | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-07-01 | 2013-07-23 | 1392 | HT | {9B58CD1E-E16E-4DF0-AF03-E29251292E43} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2010-04-11 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Binimang (3) | {813C00D4-8083-4E3B-BAC0-B523DCBB3B62} | c0a8-0057-12c3b76619c-e1792267-1289e- | MF-HT-591 | HT - HALO TRUST | H/3440 | 28875 | 67.2176 | 35.6495 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {813C00D4-8083-4E3B-BAC0-B523DCBB3B62} |  | Low | Agriculture Blocked | Moderate | 24 | CHA | 5 |  |  | 2010-06-08 | No | Open
North | Samangan | Dara-I-Sufi Bala | Dahane Shorabe Ghaznichi | {6C6759B8-E981-4442-9F27-BF9B9A4975C0} | c0a8-0009-1409a712150-8408ad54-bcb-f1 | Hz-ID-18098 | HT - HALO TRUST | H/8561 | 30676 | 67.2786 | 35.8282 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {6C6759B8-E981-4442-9F27-BF9B9A4975C0} |  | Medium | Water Blocked | Moderate | 28 | CHA | 3 |  |  | 2013-07-24 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Dahane Shorabe Ghaznichi | {6C6759B8-E981-4442-9F27-BF9B9A4975C0} | c0a8-0009-1409a776b16-f5e82df1-c17-dd | Hz-ID-18100 | HT - HALO TRUST | H/8562 | 52138 | 67.2786 | 35.8282 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089/A | Samangan Demining Project-3/A | B-Germany | Yes | 2013-10-01 | 2014-01-23 | 1392 | HT | {6C6759B8-E981-4442-9F27-BF9B9A4975C0} |  |  |  | Moderate | 7 | CHA | 3 |  |  | 2013-07-25 16:30 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Garmak | {B9EF6035-AC3F-4907-AE87-B2E33B089165} | c0a8-0057-12c3b9cf6d8-64e1f03-2d0f7-c | MF-HT-555 | HT - HALO TRUST | H/2807 | 370 | 67.3668 | 35.8138 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-07-20 |  | 1392 | HT | {B9EF6035-AC3F-4907-AE87-B2E33B089165} |  |  |  | Moderate | 175 | CHA | 3 |  |  | 2002-10-01 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Hasani | {F068817C-B78B-4D3D-A728-57D6F14A38A8} | c0a8-0057-12e55ee60ed-f571f0cc-56-954 | BF-HQ-12278 | HT - HALO TRUST | B/1789 | 200 | 67.2333 | 35.8147 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-07-12 | 2013-07-13 | 1392 | HT | {F068817C-B78B-4D3D-A728-57D6F14A38A8} |  |  |  | Moderate | 0 | CHA | 3 |  |  | 2002-04-13 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Kamach | {B68B26E2-22C0-4ABE-B401-E2078FDAB152} | c0a8-0057-12c3b6a1550-aed05d75-9437-2 | MF-HT-707 | HT - HALO TRUST | H/3491 | 36960 | 67.2928 | 35.7023 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-05-01 | 2014-05-22 | 1393 | HT | {B68B26E2-22C0-4ABE-B401-E2078FDAB152} |  |  |  | Moderate | 12 | CHA | 4 |  |  | 2010-06-06 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Kamach | {B68B26E2-22C0-4ABE-B401-E2078FDAB152} | c0a8-0057-12c3b700c4c-dcffbf8a-dcaf-3 | MF-HQ-14751 | HT - HALO TRUST | H/6650 | 58200 | 67.2971 | 35.7002 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-05-01 | 2014-05-22 | 1393 | HT | {B68B26E2-22C0-4ABE-B401-E2078FDAB152} |  |  |  | Moderate | 135 | CHA | 5 |  |  | 2010-06-07 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Kamach | {B68B26E2-22C0-4ABE-B401-E2078FDAB152} | c0a8-0057-12c3b8e56c5-1e4125b6-2383b- | MF-HT-638 | HT - HALO TRUST | H/2800 | 14025 | 67.2923 | 35.701 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-05-01 | 2014-05-22 | 1393 | HT | {B68B26E2-22C0-4ABE-B401-E2078FDAB152} |  |  |  | Moderate | 29 | CHA | 5 |  |  | 2010-06-09 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Khawal | {75B316F5-75D8-4B5E-9D30-DB594E9C6A6E} | c0a8-0009-1438509d250-47612894-422f-b | Hz-ID-18388 | HT - HALO TRUST | H/8894 | 95202 | 67.1314 | 35.5346 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {75B316F5-75D8-4B5E-9D30-DB594E9C6A6E} |  | Low | Agriculture Blocked | Moderate | 6 | CHA | 5 |  |  | 2013-12-04 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Khawal | {75B316F5-75D8-4B5E-9D30-DB594E9C6A6E} | c0a8-0009-143851370ad-258673ef-436d-e | Hz-ID-18389 | HT - HALO TRUST | H/8895 | 39270 | 67.1378 | 35.5338 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {75B316F5-75D8-4B5E-9D30-DB594E9C6A6E} |  | Low | Agriculture Blocked | Moderate | 3 | CHA | 5 |  |  | 2013-12-06 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Khawal | {75B316F5-75D8-4B5E-9D30-DB594E9C6A6E} | c0a8-0057-12c3b690cf9-b9e01012-8814-7 | MF-HQ-14737 | HT - HALO TRUST | H/6653 | 64400 | 67.1371 | 35.5337 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089/A | Samangan Demining Project-3/A | B-Germany | Yes | 2013-10-01 | 2013-11-23 | 1392 | HT | {75B316F5-75D8-4B5E-9D30-DB594E9C6A6E} |  |  |  | Moderate | 2 | CHA | 5 |  |  | 2010-06-16 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Khawal | {75B316F5-75D8-4B5E-9D30-DB594E9C6A6E} | c0a8-0057-12c3b6c8809-53164e66-b1cc-c | MF-HQ-14740 | HT - HALO TRUST | H/6652 | 72400 | 67.1372 | 35.5335 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129/A | Samangan Demining Project-4/A | CIDA | Yes | 2013-10-01 | 2013-11-23 | 1392 | HT | {75B316F5-75D8-4B5E-9D30-DB594E9C6A6E} |  |  |  | Moderate | 2 | CHA | 5 |  |  | 2010-06-15 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Khwajabedak | {947E7A4B-B091-42D9-8EB9-DA706A00C4F0} | c0a8-0009-140ba1d43e1-41c831b9-4d-bfd | Hz-ID-18102 | HT - HALO TRUST | H/8564 | 26234 | 67.136 | 35.8063 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-09-01 |  | 1393 | HT | {947E7A4B-B091-42D9-8EB9-DA706A00C4F0} |  | High with Victim | High with Victims | Moderate | 17 | CHA | 1 |  |  | 2013-07-20 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Khwajabedak | {947E7A4B-B091-42D9-8EB9-DA706A00C4F0} | c0a8-0009-140c8c81ff2-69f368ff-106a-9 | Hz-ID-18101 | HT - HALO TRUST | H/8563 | 48711 | 67.1351 | 35.8036 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {947E7A4B-B091-42D9-8EB9-DA706A00C4F0} |  | High with Victim | High with Victims | Moderate | 17 | CHA | 1 |  |  | 2013-07-19 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Kota | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} | c0a8-0009-140804478cb-10049918-3-47f8 | Hz-ID-18099 | HT - HALO TRUST | H/8569 | 92945 | 67.1165 | 35.4341 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-06-01 | 2014-06-21 | 1393 | HT | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2013-07-22 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Kota | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} | c0a8-0057-12c3b6b26ea-1be2473d-a0e6-6 | MF-HT-592 | HT - HALO TRUST | H/2786 | 6710 | 67.1368 | 35.42 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-105 | Samangan Demining Project-15 | DOS | Yes | 2014-09-01 | 2014-09-23 | 1393 | HT | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} |  | Low | Agriculture Blocked | Moderate | 133 | CHA | 5 |  |  | 2010-06-12 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Kota | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} | c0a8-0057-12c3b6ee0dc-9a3ac164-ce75-b | MF-HQ-14755 | HT - HALO TRUST | H/6651 | 6160 | 67.15 | 35.4281 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-105 | Samangan Demining Project-15 | DOS | Yes | 2014-09-01 | 2014-09-23 | 1393 | HT | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} |  | Low | Agriculture Blocked | Moderate | 20 | CHA | 5 |  |  | 2010-06-11 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Kota | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} | c0a8-0057-12c3b8196f1-b42676a8-1a8f7- | MF-HT-625 | HT - HALO TRUST | H/3479 | 24420 | 67.1279 | 35.4152 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-105 | Samangan Demining Project-15 | DOS | Yes | 2014-09-01 | 2014-09-23 | 1393 | HT | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} |  | Low | Agriculture Blocked | Moderate | 10 | CHA | 5 |  |  | 2010-06-13 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Kota | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} | c0a8-0057-12c3b8e86ba-e12b01d7-23a23- | MF-HQ-10077 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1507/14229/MF0027 | 137613 | 67.0857 | 35.4364 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-105 | Samangan Demining Project-15 | DOS | Yes | 2014-07-01 | 2014-08-23 | 1393 | HT | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2009-04-29 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Kota | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} | c0a8-0057-12c3baa5872-e0196d0f-3525a- | MF-HT-697 | HT - HALO TRUST | H/3477 | 57212 | 67.1165 | 35.4341 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-105 | Samangan Demining Project-15 | DOS | Yes | 2014-06-01 | 2014-06-21 | 1393 | HT | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} |  |  |  | Moderate | 2 | CHA | 5 |  |  | 2007-05-01 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Kota | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} | c0a8-0057-12c3baa5b20-99dcd477-3526d- | MF-HT-617 | HT - HALO TRUST | H/3478 | 13200 | 67.0756 | 35.4407 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-105 | Samangan Demining Project-15 | DOS | Yes | 2014-09-01 | 2014-09-23 | 1393 | HT | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2010-06-10 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Kota | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} | c0a8-0057-12c3bac39c6-3535c862-363fe- | MF-HT-628 | HT - HALO TRUST | H/3480 | 17600 | 67.1513 | 35.4295 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-105 | Samangan Demining Project-15 | DOS | Yes | 2014-09-01 | 2014-09-23 | 1393 | HT | {569E5BA4-55C3-49E0-B84E-0D52DCEE040E} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2010-06-14 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Maschetak | {E9D740D9-3B8C-4E09-9F01-2CC44E0B2B14} | c0a8-0009-14101fa20a1-a370e410-1a23-a | Hz-ID-18149 | MCPA - Mine Clearance Planning Agency | H/8585 | 19980 | 67.2158 | 35.5336 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-06-11 | 2014-07-03 | 1393 | HT | {E9D740D9-3B8C-4E09-9F01-2CC44E0B2B14} |  | Medium | Critical Infrastracture | Moderate | 190 | CHA | 3 |  |  | 2013-08-20 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Mooshak | {4C358644-AA07-481E-9BB6-7F092FE1FD11} | c0a8-0057-12c3b8eeda6-45d8cf21-23e29- | MF-HT-553 | HT - HALO TRUST | H/2806 | 10880 | 67.3752 | 35.9006 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-090 | Samangan Demining Project-5 | DOS | Yes | 2013-07-01 | 2013-09-23 | 1392 | HT | {4C358644-AA07-481E-9BB6-7F092FE1FD11} |  |  |  | Moderate | 2 | CHA | 5 |  |  | 2010-05-19 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Myana | {3FBF75E1-8FE0-475B-80AA-9082E958BBB4} | c0a8-0057-12c3b920386-79369910-25e64- | MF-HT-598 | HT - HALO TRUST | H/2788 | 5940 | 67.2757 | 35.8928 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-06-01 | 2013-06-22 | 1392 | HT | {3FBF75E1-8FE0-475B-80AA-9082E958BBB4} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2010-05-21 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Qala | {14E0B50D-E6BC-49F1-B73B-CB29D2DA5223} | c0a8-0057-12c3b715b52-f1a33391-ec85-8 | MF-HT-1276 | HT - HALO TRUST | H/3489 | 14070 | 67.3081 | 35.8866 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-04-10 | 2013-05-12 | 1392 | HT | {14E0B50D-E6BC-49F1-B73B-CB29D2DA5223} |  |  |  | Moderate | 16 | CHA | 5 |  |  | 2010-05-14 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Qala | {14E0B50D-E6BC-49F1-B73B-CB29D2DA5223} | c0a8-0057-12c3bb421ee-ead78542-3afa7- | MF-HT-706 | HT - HALO TRUST | H/3488 | 23650 | 67.2994 | 35.9034 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-04-01 | 2013-06-23 | 1392 | HT | {14E0B50D-E6BC-49F1-B73B-CB29D2DA5223} |  |  |  | Moderate | 24 | CHA | 5 |  |  | 2010-05-15 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Qarah Khawal | {4E30C0BA-771A-4999-9652-CC809CA5B522} | c0a8-0057-12c3b6beb01-6969e395-aa62-6 | MF-HQ-11462 | HT - HALO TRUST | H/4819 | 1440 | 67.6039 | 35.9878 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {4E30C0BA-771A-4999-9652-CC809CA5B522} |  | Medium | Agriculture Blocked | Moderate | 12 | CHA | 3 |  |  | 2008-05-14 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Qarah Khawal | {4E30C0BA-771A-4999-9652-CC809CA5B522} | c0a8-0057-12c3b6e6171-a3d5b660-c862-c | MF-HQ-11463 | HT - HALO TRUST | H/4820 | 3500 | 67.6053 | 35.9942 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {4E30C0BA-771A-4999-9652-CC809CA5B522} |  | Low | Agriculture Blocked | Moderate | 32 | CHA | 5 |  |  | 2008-05-13 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Qarah Khawal | {4E30C0BA-771A-4999-9652-CC809CA5B522} | c0a8-0057-12c3b73d57a-98722fb7-10a66- | MF-HQ-14752 | HT - HALO TRUST | H/6585 | 10000 | 67.6058 | 35.9999 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {4E30C0BA-771A-4999-9652-CC809CA5B522} |  | Low | Agriculture Blocked | Moderate | 26 | CHA | 5 |  |  | 2010-06-12 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Qarah Khawal | {4E30C0BA-771A-4999-9652-CC809CA5B522} | c0a8-0057-12c3b776512-680eda6a-13487- | MF-HQ-11452 | HT - HALO TRUST | H/4818 | 2500 | 67.6092 | 35.983 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {4E30C0BA-771A-4999-9652-CC809CA5B522} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-05-15 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Qara'i (1) | {6A6C0F28-A4CE-40BF-A0C1-76F49AB82777} | c0a8-0057-12c3b75cdc7-7a02ba59-121ca- | MF-HT-1182 | HT - HALO TRUST | H/2808 | 20130 | 67.3162 | 35.8827 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-04-17 | 2013-05-18 | 1392 | HT | {6A6C0F28-A4CE-40BF-A0C1-76F49AB82777} |  |  |  | Moderate | 31 | CHA | 5 |  |  | 2010-05-16 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Shorab | {A96D43B5-4333-4747-A4FB-D822EBFEC043} | c0a8-0009-1438507654d-c9e74f2e-41f0-4 | Hz-ID-18387 | HT - HALO TRUST | H/8861 | 62046 | 67.1935 | 35.8098 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {A96D43B5-4333-4747-A4FB-D822EBFEC043} |  | Low | Agriculture Blocked | Moderate | 5 | CHA | 5 |  |  | 2013-12-01 16:30 | No | Open
North | Samangan | Dara-I-Sufi Bala | Shorab | {A96D43B5-4333-4747-A4FB-D822EBFEC043} | c0a8-0057-12c3b6c4649-dfdfca33-aead-f | MF-HQ-14343 | HT - HALO TRUST | H/6565 | 16610 | 67.1906 | 35.8039 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129/A | Samangan Demining Project-4/A | CIDA | Yes | 2013-10-01 | 2013-10-23 | 1392 | HT | {A96D43B5-4333-4747-A4FB-D822EBFEC043} |  |  |  | Moderate | 8 | CHA | 5 |  |  | 2010-04-10 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Shorab | {A96D43B5-4333-4747-A4FB-D822EBFEC043} | c0a8-0057-12c3b90abaa-9132f49f-2506f- | MF-HQ-11450 | HT - HALO TRUST | H/4167 | 52778 | 67.1913 | 35.7998 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-07-01 | 2013-07-23 | 1392 | HT | {A96D43B5-4333-4747-A4FB-D822EBFEC043} |  |  |  | Moderate | 3 | CHA | 5 |  |  | 2008-07-16 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Shorab | {A96D43B5-4333-4747-A4FB-D822EBFEC043} | c0a8-0057-12c3b90ae58-5f449cb-25085-6 | MF-HQ-12022 | HT - HALO TRUST | H/4166 | 28000 | 67.1914 | 35.8001 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-09-01 | 2013-09-23 | 1392 | HT | {A96D43B5-4333-4747-A4FB-D822EBFEC043} |  |  |  | Moderate | 3 | CHA | 5 |  |  | 2009-04-16 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Shorab | {A96D43B5-4333-4747-A4FB-D822EBFEC043} | c0a8-0057-12c3b90b02c-9adcf607-250a3- | MF-HQ-11449 | HT - HALO TRUST | H/2815 | 10750 | 67.1946 | 35.807 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129/A | Samangan Demining Project-4/A | CIDA | Yes | 2013-10-01 | 2013-10-23 | 1392 | HT | {A96D43B5-4333-4747-A4FB-D822EBFEC043} |  |  |  | Moderate | 3 | CHA | 5 |  |  | 2008-04-17 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Surkhdeh | {8C549C47-ECE7-4EC6-ADC3-C1AE30C6D3F9} | c0a8-0009-1410199bd0a-f4f45531-fb3-cc | Hz-ID-18145 | HT - HALO TRUST | H/8583 | 26370 | 67.0607 | 35.6157 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-07-01 | 2014-08-23 | 1393 | HT | {8C549C47-ECE7-4EC6-ADC3-C1AE30C6D3F9} |  | Low | Agriculture Blocked | Moderate | 3 | CHA | 5 |  |  | 2013-08-18 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Surkhdeh | {8C549C47-ECE7-4EC6-ADC3-C1AE30C6D3F9} | c0a8-0009-141019a3554-cda1c6a2-100e-3 | Hz-ID-18143 | HT - HALO TRUST | H/8582 | 9940 | 67.03 | 35.61 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-08-01 | 2014-08-23 | 1393 | HT | {8C549C47-ECE7-4EC6-ADC3-C1AE30C6D3F9} |  | Low | Agriculture Blocked | Moderate | 17 | CHA | 5 |  |  | 2013-08-17 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Surkhdeh | {8C549C47-ECE7-4EC6-ADC3-C1AE30C6D3F9} | c0a8-0009-141019a9cec-d87ac5db-1074-d | Hz-ID-18141 | HT - HALO TRUST | H/8581 | 7522 | 67.03 | 35.61 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-08-01 | 2014-08-23 | 1393 | HT | {8C549C47-ECE7-4EC6-ADC3-C1AE30C6D3F9} |  | Low | Agriculture Blocked | Moderate | 19 | CHA | 5 |  |  | 2013-08-16 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Surkhdeh | {8C549C47-ECE7-4EC6-ADC3-C1AE30C6D3F9} | c0a8-0009-14101f8c421-ddb3da8c-193d-3 | Hz-ID-18147 | HT - HALO TRUST | H/8584 | 30030 | 67.0486 | 35.6111 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-07-01 | 2014-08-23 | 1393 | HT | {8C549C47-ECE7-4EC6-ADC3-C1AE30C6D3F9} |  | Low | Critical Infrastracture | Moderate | 5 | CHA | 5 |  |  | 2013-08-19 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Surkhdeh | {8C549C47-ECE7-4EC6-ADC3-C1AE30C6D3F9} | c0a8-0009-14106d43d9d-6fc7f478-8e00-1 | Hz-ID-18148 | HT - HALO TRUST | H/8570 | 13034 | 67.03 | 35.61 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-07-01 | 2014-07-23 | 1393 | HT | {8C549C47-ECE7-4EC6-ADC3-C1AE30C6D3F9} |  | Low | Agriculture Blocked | Moderate | 140 | CHA | 4 |  |  | 2013-08-15 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Takhti Joy | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} | c0a8-0057-12c3b703e14-9dde6c7-df1b-e1 | MF-HT-717 | HT - HALO TRUST | H/3497 | 22660 | 67.3004 | 35.9262 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-05-17 | 2013-06-16 | 1392 | HT | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} |  |  |  | Moderate | 3 | CHA | 4 |  |  | 2010-04-05 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Takhti Joy | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} | c0a8-0057-12c3b719574-202b2e5d-ef5a-c | MF-HQ-14345 | HT - HALO TRUST | H/6564 | 1705 | 67.2998 | 35.9158 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-05-01 | 2013-05-16 | 1392 | HT | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2010-04-02 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Takhti Joy | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} | c0a8-0057-12c3b7e15aa-ba445c57-181d9- | MF-HT-567 | HT - HALO TRUST | H/2816 | 8690 | 67.2993 | 35.9129 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-05-01 | 2013-05-16 | 1392 | HT | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} |  |  |  | Moderate | 22 | CHA | 4 |  |  | 2010-04-03 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Takhti Joy | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} | c0a8-0057-12c3b7e1991-7ac2bfd3-18208- | MF-HT-714 | HT - HALO TRUST | H/3496 | 1551 | 67.2966 | 35.9279 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-04-08 | 2013-04-11 | 1392 | HT | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} |  |  |  | Moderate | 8 | CHA | 4 |  |  | 2010-04-01 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Takhti Joy | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} | c0a8-0057-12c3b974023-ca7931a5-2956c- | MF-HT-578 | HT - HALO TRUST | H/3051 | 43131 | 67.2791 | 35.9129 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-04-01 | 2013-06-23 | 1392 | HT | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} |  |  |  | Moderate | 539 | CHA | 5 |  |  | 2002-11-01 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Takhti Joy | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} | c0a8-008e-1328a418ce4-f482519a-507-fe | MF-HT-713 | HT - HALO TRUST | H/3495 | 33500 | 67.286 | 35.9169 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-05-01 | 2013-05-08 | 1392 | HT | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} |  |  |  | Moderate | 176 | CHA | 3 |  |  | 2007-05-01 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Takhti Joy | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} | c0a8-008e-1328a49f309-403a5388-6b4-c8 | MF-HT-718 | HT - HALO TRUST | H/3498 | 22990 | 67.286 | 35.9169 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-05-07 |  | 1392 | HT | {550A9D64-A999-4E4B-AC65-ECFB07F624F2} |  |  |  | Moderate | 3 | CHA | 5 |  |  | 2007-05-01 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Tangi Ya'qub | {059178E8-60B3-475D-8C8E-49A443D6968F} | c0a8-0057-12c3b7300ef-af5b5e10-10079- | MF-HQ-13650 | HT - HALO TRUST | AF/1507/14385/MF0031 | 77629 | 67.2947 | 35.9295 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-04-11 | 2013-06-22 | 1392 | HT | {059178E8-60B3-475D-8C8E-49A443D6968F} |  |  |  | Moderate | 26 | CHA | 5 |  |  | 2009-11-10 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Tangi Ya'qub | {059178E8-60B3-475D-8C8E-49A443D6968F} | c0a8-0057-12c3b77b8cc-44da5158-1384e- | MF-HQ-13649 | HT - HALO TRUST | AF/1504/14385/MF0030 | 86084 | 67.2936 | 35.9314 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-04-01 | 2013-06-23 | 1392 | HT | {059178E8-60B3-475D-8C8E-49A443D6968F} |  |  |  | Moderate | 8 | CHA | 5 |  |  | 2009-11-09 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Tangi Ya'qub | {059178E8-60B3-475D-8C8E-49A443D6968F} | c0a8-0057-12c3b792f2f-9a09d7f2-1496a- | MF-HQ-13648 | HT - HALO TRUST | AF/1504/14385/MF0029 | 66824 | 67.2998 | 35.9049 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-04-01 | 2013-08-20 | 1392 | HT | {059178E8-60B3-475D-8C8E-49A443D6968F} |  |  |  | Moderate | 52 | CHA | 5 |  |  | 2009-11-08 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Tolanak | {C4521955-E130-4BC7-A725-D18BDF9A5B26} | c0a8-0057-12c3b76e3d4-19cdb978-12eb6- | MF-HQ-14754 | HT - HALO TRUST | H/6654 | 19800 | 67.0177 | 35.3593 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes | 2014-07-01 | 2014-07-23 | 1393 | HT | {C4521955-E130-4BC7-A725-D18BDF9A5B26} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2010-06-19 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Yarghawak | {C21602FB-63AA-42BF-A697-2A822FF829DA} | c0a8-0057-12c3b79e321-b7649ae3-15179- | MF-HQ-14311 | HT - HALO TRUST | H/6568 | 36540 | 67.1816 | 35.7978 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129 | Samangan Demining Project-4 | Bilateral | Yes | 2013-07-01 | 2013-09-23 | 1392 | HT | {C21602FB-63AA-42BF-A697-2A822FF829DA} |  |  |  | Moderate | 8 | CHA | 5 |  |  | 2010-04-13 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Zeraki | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} | c0a8-0009-13dc445ba3b-6cb3d94-ef9-728 | MF-HT-700 | HT - HALO TRUST | H/3483 | 41700 | 67.2798 | 35.8462 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-090 | Samangan Demining Project-5 | DOS | Yes | 2013-07-01 | 2013-09-23 | 1392 | HT | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} |  |  |  | Moderate | 5 | CHA | 5 |  |  | 2007-05-01 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Zeraki | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} | c0a8-0057-12c3b9373a2-55b761fa-26d67- | MF-HT-620 | HT - HALO TRUST | H/2792 | 21000 | 67.2943 | 35.8262 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-090 | Samangan Demining Project-5 | DOS | Yes | 2013-06-01 | 2013-06-22 | 1392 | HT | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} |  |  |  | Moderate | 23 | CHA | 5 |  |  | 2007-05-04 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Zeraki | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} | c0a8-0057-12c3b9ee110-bdb05eec-2e3de- | MF-HQ-11974 | HT - HALO TRUST | H/4158 | 13950 | 67.2526 | 35.8092 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-090 | Samangan Demining Project-5 | DOS | Yes |  |  | 1392 | HT | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} |  |  |  | Moderate | 14 | CHA | 5 |  |  | 2008-04-07 | Yes | Complete
North | Samangan | Dara-I-Sufi Bala | Zeraki | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} | c0a8-0057-12c3b9ee535-a1ad3af6-2e411- | MF-HQ-11966 | HT - HALO TRUST | H/2826 | 2600 | 67.2518 | 35.8067 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-090 | Samangan Demining Project-5 | DOS | Yes |  |  | 1392 | HT | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} |  |  |  | Moderate | 10 | CHA | 5 |  |  | 2008-04-07 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Zeraki | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} | c0a8-0057-12c3ba0c782-f2c9f1ce-2f6bc- | MF-HT-573 | HT - HALO TRUST | H/2827 | 12000 | 67.2858 | 35.816 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-090 | Samangan Demining Project-5 | DOS | Yes |  |  | 1392 | HT | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} |  |  |  | Moderate | 30 | CHA | 3 |  |  | 2003-04-01 | Yes | Complete
North | Samangan | Dara-I-Sufi Bala | Zeraki | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} | c0a8-0057-12c3ba0cafb-3e163465-2f6db- | MF-HT-570 | HT - HALO TRUST | H/2824 | 1316 | 67.4758 | 35.9692 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} |  | Medium | Agriculture Blocked | Moderate | 75 | CHA | 3 |  |  | 2003-04-01 | No | Planned
North | Samangan | Dara-I-Sufi Bala | Zeraki | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} | c0a8-008e-13068bdb831-12b13544-409-22 | MF-HQ-11978 | HT - HALO TRUST | H/4159 | 6300 | 67.2532 | 35.8125 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-090 | Samangan Demining Project-5 | DOS | Yes |  |  | 1392 | HT | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} |  |  |  | Moderate | 14 | CHA | 5 |  |  | 2008-04-08 | Yes | Complete
North | Samangan | Dara-I-Sufi Bala | Zeraki | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} | c0a8-008e-13068be89b0-4053f13a-432-f8 | MF-HQ-11970 | HT - HALO TRUST | H/4157 | 780 | 67.2518 | 35.8067 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-090 | Samangan Demining Project-5 | DOS | Yes |  |  | 1392 | HT | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} |  |  |  | Moderate | 10 | CHA | 5 |  |  | 2008-04-07 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Zeraki | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} | c0a8-008e-1328a5fe181-d761065-75c-1f8 | MF-HT-637 | HT - HALO TRUST | H/3481 | 42000 | 67.2798 | 35.8462 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-090 | Samangan Demining Project-5 | DOS | Yes |  |  | 1392 | HT | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} |  |  |  | Moderate | 21 | CHA | 5 |  |  | 2007-05-01 | Yes | Complete
North | Samangan | Dara-I-Sufi Bala | Zeraki | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} | c0a8-008e-1328a62318c-7ea5b077-7eb-2b | MF-HT-639 | HT - HALO TRUST | H/3482 | 41700 | 67.2798 | 35.8462 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-090 | Samangan Demining Project-5 | DOS | Yes |  |  | 1392 | HT | {4FD95F02-D5A9-4F0C-AEB2-6362BA6B3B65} |  |  |  | Moderate | 5 | CHA | 5 |  |  | 2007-05-01 | No | Complete
North | Samangan | Dara-I-Sufi Bala | Zere Chapar | {72A90B0C-962F-4546-BCDA-2A87660E8C73} | c0a8-0009-141a0a00fc2-399bc6bb-2d08-8 | Hz-ID-18199 | HT - HALO TRUST | H/8599 | 40347 | 67.117 | 35.7646 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {72A90B0C-962F-4546-BCDA-2A87660E8C73} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2013-09-20 16:30 | No | Planned
North | Samangan | Dara-I-Sufi Payin | Ahengaran | {159ECB63-FD6B-4BFF-AE95-D4784EB1A1CF} | c0a8-008e-132909ecc28-4802941d-379-52 | MF-15996 | MCPA - Mine Clearance Planning Agency | AF/1508/14391/MF0032 | 34732 | 67.3642 | 35.9645 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-129/A | Samangan Demining Project-4/A | CIDA | Yes |  |  | 1392 | HT | {159ECB63-FD6B-4BFF-AE95-D4784EB1A1CF} |  |  |  | Moderate | 19 | CHA | 1 |  |  | 2011-05-25 16:30 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Balghaly (1) | {B491CAED-B4EC-419E-9134-7D612883C703} | c0a8-0057-12c3b72d203-733fc9c8-fe4c-5 | MF-HT-1176 | HT - HALO TRUST | H/3476 | 500 | 67.3221 | 36.0557 | Open | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes |  |  | 1392 | HT | {B491CAED-B4EC-419E-9134-7D612883C703} |  | High with Victim | High with Victims | Moderate | 12 | CHA | 2 |  |  | 2007-05-01 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Balghaly (2) | {84F61366-F01E-4D0A-873C-3E69F23B2F10} | c0a8-0057-12c3b70acae-b437de64-e45c-4 | BF-HQ-11755 | HT - HALO TRUST | B/2724 | 0 | 67.3174 | 36.0634 | Open | UXO Only | UXO Only | BF |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {84F61366-F01E-4D0A-873C-3E69F23B2F10} |  | High Requested | Resettlment/Local Request | Moderate | 0 | CHA | 1 |  |  | 2009-06-10 | No | Open
North | Samangan | Dara-I-Sufi Payin | Bayanan | {3C26030A-D395-4FF3-8CCA-8825A052DC93} | c0a8-0057-12c3bb39b15-dad4cc85-3aaae- | MF-HT-1214 | HT - HALO TRUST | H/3486 | 2780 | 67.3797 | 35.9166 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {3C26030A-D395-4FF3-8CCA-8825A052DC93} |  | Low | Agriculture Blocked | Moderate | 25 | CHA | 4 |  |  | 2010-06-03 | No | Open
North | Samangan | Dara-I-Sufi Payin | Bayanan | {3C26030A-D395-4FF3-8CCA-8825A052DC93} | c0a8-0057-12c3bb39d84-f3c59bb1-3aaca- | MF-HT-1196 | HT - HALO TRUST | H/3487 | 4100 | 67.3715 | 35.9193 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {3C26030A-D395-4FF3-8CCA-8825A052DC93} |  | Medium | Agriculture Blocked | Moderate | 45 | CHA | 3 |  |  | 2010-06-05 | No | Planned
North | Samangan | Dara-I-Sufi Payin | Big Mod | {5C5B98A4-7D7F-43B9-A3BF-B30A8BA0C682} | c0a8-0009-13e1c6b26ff-9d16c625-693d-6 | Hz-ID-17778 | HT - HALO TRUST | H/8454 | 20000 | 67.6582 | 36.1909 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {5C5B98A4-7D7F-43B9-A3BF-B30A8BA0C682} |  | Low | Agriculture Blocked | Moderate | 4 | CHA | 5 |  |  | 2013-03-15 16:30 | No | Open
North | Samangan | Dara-I-Sufi Payin | Chak Abi | {77B2780D-96E7-4144-8EF9-DF627E10DDA8} | c0a8-0009-145639d8cad-aa25a729-2182-f | Hz-ID-17955 | HT - HALO TRUST | H/8479 | 1320 | 67.3746 | 36.0153 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {77B2780D-96E7-4144-8EF9-DF627E10DDA8} |  | Low | Agriculture Blocked | Moderate | 37 | CHA | 5 |  |  | 2013-05-16 16:30 | No | Open
North | Samangan | Dara-I-Sufi Payin | Chak Abi | {77B2780D-96E7-4144-8EF9-DF627E10DDA8} | c0a8-0057-12c3b928809-673b64c6-263a6- | MF-HQ-10069 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1508/14445/MF0025 | 2720 | 67.3778 | 36.0164 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {77B2780D-96E7-4144-8EF9-DF627E10DDA8} |  | Medium | Critical Infrastracture | Moderate | 22 | CHA | 3 |  |  | 2009-04-29 | No | Planned
North | Samangan | Dara-I-Sufi Payin | Chobaki | {214EFA3C-127C-4209-980E-2048F322F0D1} | c0a8-0057-12c3b720cb4-8aac5701-f4d2-b | MF-HT-1257 | HT - HALO TRUST | H/3517 | 6700 | 67.222 | 36.0078 | Open | AT Only | AT Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {214EFA3C-127C-4209-980E-2048F322F0D1} |  | Low | Critical Infrastracture | Moderate | 58 | CHA | 5 |  |  | 2007-05-01 | No | Open
North | Samangan | Dara-I-Sufi Payin | Chochman Qotan | {D69FD761-6557-43BF-B260-4A286833B484} | c0a8-0057-12c3b9e6982-db975f4c-2df5f- | MF-HQ-11884 | HT - HALO TRUST | H/2830 | 5000 | 67.4703 | 36.3303 | Open | AT Only | AT Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {D69FD761-6557-43BF-B260-4A286833B484} |  | Low | Agriculture Blocked | Moderate | 4 | CHA | 5 |  |  | 2008-04-22 | No | Open
North | Samangan | Dara-I-Sufi Payin | Chochman Qotan | {D69FD761-6557-43BF-B260-4A286833B484} | c0a8-0057-12c3b9e6d97-b168d342-2df7b- | MF-HQ-11453 | HT - HALO TRUST | H/4146 | 7150 | 67.4701 | 36.3345 | Open | AT Only | AT Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {D69FD761-6557-43BF-B260-4A286833B484} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2008-04-23 | No | Open
North | Samangan | Dara-I-Sufi Payin | Dihee | {A36259AF-5BDF-4E6A-9E0C-A5BB12934E91} | c0a8-0057-12c3b6a4f43-b1c9e0ba-96c7-8 | MF-HQ-13540 | HT - HALO TRUST | H/6513 | 8500 | 67.2231 | 35.9661 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-05-01 | 2013-05-22 | 1392 | HT | {A36259AF-5BDF-4E6A-9E0C-A5BB12934E91} |  |  |  | Moderate | 4 | CHA | 5 |  |  | 2009-10-18 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Dihee | {A36259AF-5BDF-4E6A-9E0C-A5BB12934E91} | c0a8-0057-12c3b6bcb22-fcb10436-a8c6-f | MF-HQ-13501 | HT - HALO TRUST | H/6511 | 35000 | 67.2379 | 35.9653 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-05-01 | 2013-05-22 | 1392 | HT | {A36259AF-5BDF-4E6A-9E0C-A5BB12934E91} |  |  |  | Moderate | 5 | CHA | 5 |  |  | 2009-10-18 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Dihee | {A36259AF-5BDF-4E6A-9E0C-A5BB12934E91} | c0a8-0057-12c3b6c412a-9a795c10-ae69-1 | MF-HQ-14715 | HT - HALO TRUST | H/6586 | 4000 | 67.2546 | 35.9917 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-08-01 | 2013-09-23 | 1392 | HT | {A36259AF-5BDF-4E6A-9E0C-A5BB12934E91} |  |  |  | Moderate | 5 | CHA | 5 |  |  | 2010-07-25 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Dihee | {A36259AF-5BDF-4E6A-9E0C-A5BB12934E91} | c0a8-0057-12c3b71e43e-a4b3d14c-f324-6 | MF-HQ-13538 | HT - HALO TRUST | H/6512 | 9300 | 67.2272 | 35.9667 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-05-01 | 2013-05-22 | 1392 | HT | {A36259AF-5BDF-4E6A-9E0C-A5BB12934E91} |  |  |  | Moderate | 6 | CHA | 5 |  |  | 2009-10-18 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Dihee | {A36259AF-5BDF-4E6A-9E0C-A5BB12934E91} | c0a8-0057-12c3b78ad36-1124e646-14365- | MF-HQ-13500 | HT - HALO TRUST | H/6510 | 9100 | 67.2503 | 35.9645 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-05-02 | 2013-05-20 | 1392 | HT | {A36259AF-5BDF-4E6A-9E0C-A5BB12934E91} |  |  |  | Moderate | 61 | CHA | 3 |  |  | 2009-10-18 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Galawan Sai | {6B6F2F41-2A7B-482A-AA54-2BB662400B13} | c0a8-0057-12c3b704e1b-5493d9b7-dfe5-2 | MF-HQ-11753 | HT - HALO TRUST | H/6142 | 3107 | 67.3474 | 36.0159 | Open | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes |  |  | 1392 | HT | {6B6F2F41-2A7B-482A-AA54-2BB662400B13} |  | High Requested | Resettlment/Local Request | Moderate | 3 | CHA | 3 |  |  | 2009-06-03 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Khana Sangi | {17F1DCF6-64CE-4350-ADD8-7C5B5E5936EA} | c0a8-0009-13b45d10214-db750df1-5802-7 | Hz-ID-17420 | HT - HALO TRUST | H/8409 | 2200 | 67.2171 | 36.0363 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {17F1DCF6-64CE-4350-ADD8-7C5B5E5936EA} |  | Low | Agriculture Blocked | Moderate | 3 | CHA | 5 |  |  | 2012-10-19 16:30 | No | Open
North | Samangan | Dara-I-Sufi Payin | Nawazan (1) | {7ABD93D8-13C2-4BD1-B8AB-5B60F8A4E6D8} | c0a8-0057-12c3b71b810-86be59da-f115-4 | MF-HQ-13827 | HT - HALO TRUST | H/6526 | 21500 | 67.2551 | 35.9958 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-05-01 | 2013-05-22 | 1392 | HT | {7ABD93D8-13C2-4BD1-B8AB-5B60F8A4E6D8} |  |  |  | Moderate | 2 | CHA | 5 |  |  | 2009-12-15 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Oimatan (2) | {B160F24D-3FF0-4AFA-BF66-005E8C9FDD0F} | c0a8-0009-140a4da39c6-4fef3e1b-3988-4 | Hz-ID-18106 | HT - HALO TRUST | H/8568 | 469 | 67.1173 | 36.0303 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {B160F24D-3FF0-4AFA-BF66-005E8C9FDD0F} |  | Medium | Agriculture Blocked | Moderate | 14 | CHA | 3 |  |  | 2013-07-18 16:30 | No | Open
North | Samangan | Dara-I-Sufi Payin | Oimatan (2) | {B160F24D-3FF0-4AFA-BF66-005E8C9FDD0F} | c0a8-0009-140a4de8253-d72b6401-39ab-7 | Hz-ID-18105 | HT - HALO TRUST | H/8567 | 4833 | 67.1173 | 36.0303 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {B160F24D-3FF0-4AFA-BF66-005E8C9FDD0F} |  | Medium | Agriculture Blocked | Moderate | 14 | CHA | 3 |  |  | 2013-07-17 16:30 | No | Open
North | Samangan | Dara-I-Sufi Payin | Oimatan (2) | {B160F24D-3FF0-4AFA-BF66-005E8C9FDD0F} | c0a8-0009-140a4e53c22-ab7c34f0-39d4-a | Hz-ID-18104 | HT - HALO TRUST | H/8566 | 2858 | 67.1173 | 36.0303 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {B160F24D-3FF0-4AFA-BF66-005E8C9FDD0F} |  | Medium | Agriculture Blocked | Moderate | 14 | CHA | 3 |  |  | 2013-07-16 16:30 | No | Open
North | Samangan | Dara-I-Sufi Payin | Oimatan (2) | {B160F24D-3FF0-4AFA-BF66-005E8C9FDD0F} | c0a8-0009-14107662240-221e9cad-af50-7 | Hz-ID-18103 | HT - HALO TRUST | H/8565 | 8281 | 67.1173 | 36.0303 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {B160F24D-3FF0-4AFA-BF66-005E8C9FDD0F} |  | Low | Agriculture Blocked | Moderate | 18 | CHA | 5 |  |  | 2013-07-15 16:30 | No | Open
North | Samangan | Dara-I-Sufi Payin | Oimatan (3) | {E8EB7B7E-2361-47EF-B3D8-8BC093D5A50F} | c0a8-00f6-139aeff0126-120c87c7-47ae-4 | Hz-ID-17230 | HT - HALO TRUST | H/8238 | 21017 | 67.1173 | 36.0303 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-07-01 | 2013-07-23 | 1392 | HT | {E8EB7B7E-2361-47EF-B3D8-8BC093D5A50F} |  |  |  | Moderate | 17 | CHA | 5 |  |  | 2012-07-15 16:30 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Otah Kiti | {410F7BD9-A7E9-4BDC-82C5-C374904196AD} | c0a8-0057-12c3bb70b7a-d2eeb0cc-3ca06- | MF-HQ-10066 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1508/14520/MF0026 | 2760 | 67.5463 | 36.1407 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-08-01 | 2013-09-23 | 1392 | HT | {410F7BD9-A7E9-4BDC-82C5-C374904196AD} |  |  |  | Moderate | 74 | CHA | 4 |  |  | 2009-04-29 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Qara Jangal (1) | {04629073-F28A-432C-BA5B-356CBC9ACFD0} | c0a8-0009-13b45ed322c-c314862-5977-13 | Hz-ID-17419 | HT - HALO TRUST | H/8295 | 9365 | 67.1441 | 36.006 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {04629073-F28A-432C-BA5B-356CBC9ACFD0} |  | Low | Agriculture Blocked | Moderate | 27 | CHA | 5 |  |  | 2012-10-18 16:30 | No | Open
North | Samangan | Dara-I-Sufi Payin | Qara Jangal (1) | {04629073-F28A-432C-BA5B-356CBC9ACFD0} | c0a8-0057-12c3b6d7477-7f31e8b9-bcfe-1 | MF-HT-1265 | HT - HALO TRUST | H/3519 | 4220 | 67.1145 | 36.0064 | Open | AT Only | AT Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {04629073-F28A-432C-BA5B-356CBC9ACFD0} |  | Low | Small Hazards | Moderate | 10 | CHA | 5 |  |  | 2007-05-01 | No | Open
North | Samangan | Dara-I-Sufi Payin | Qara Jangal (1) | {04629073-F28A-432C-BA5B-356CBC9ACFD0} | c0a8-0057-12c3b9b6691-b14cd47a-2c0f8- | MF-HQ-12023 | HT - HALO TRUST | H/2809 | 10650 | 67.1539 | 36.0269 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {04629073-F28A-432C-BA5B-356CBC9ACFD0} |  | Low | Agriculture Blocked | Moderate | 24 | CHA | 5 |  |  | 2008-04-04 | No | Open
North | Samangan | Dara-I-Sufi Payin | Qara Jangal (1) | {04629073-F28A-432C-BA5B-356CBC9ACFD0} | c0a8-0057-12c3b9b709f-6de0db23-2c15c- | MF-HQ-11826 | HT - HALO TRUST | H/4153 | 14280 | 67.1573 | 36.0131 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {04629073-F28A-432C-BA5B-356CBC9ACFD0} |  | Low | Agriculture Blocked | Moderate | 10 | CHA | 5 |  |  | 2008-04-06 | No | Open
North | Samangan | Dara-I-Sufi Payin | Qara Jangal (2) | {6214AF33-86A2-4B63-97C1-4EE097D45676} | c0a8-0057-12c3b9b68b3-c9b35806-2c10c- | MF-HQ-11447 | HT - HALO TRUST | H/4155 | 29400 | 67.1544 | 36.0118 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {6214AF33-86A2-4B63-97C1-4EE097D45676} |  | Low | Agriculture Blocked | Moderate | 10 | CHA | 5 |  |  | 2008-04-05 | No | Open
North | Samangan | Dara-I-Sufi Payin | Qara Jangal (2) | {6214AF33-86A2-4B63-97C1-4EE097D45676} | c0a8-0057-12c3b9b6b61-1f140fd6-2c128- | MF-HQ-11448 | HT - HALO TRUST | H/4154 | 26200 | 67.155 | 36.0123 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {6214AF33-86A2-4B63-97C1-4EE097D45676} |  | Low | Agriculture Blocked | Moderate | 10 | CHA | 5 |  |  | 2008-04-05 | No | Open
North | Samangan | Dara-I-Sufi Payin | Qara Jangal (2) | {6214AF33-86A2-4B63-97C1-4EE097D45676} | c0a8-0057-12c3b9b6db2-b2331f51-2c143- | MF-HQ-11441 | HT - HALO TRUST | H/4156 | 14600 | 67.1414 | 36.0056 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {6214AF33-86A2-4B63-97C1-4EE097D45676} |  | Low | Agriculture Blocked | Moderate | 22 | CHA | 5 |  |  | 2008-04-04 | No | Open
North | Samangan | Dara-I-Sufi Payin | Qeshlaq Khalifa | {7044F02E-107F-4B10-B5CD-256C7FB215CE} | c0a8-0057-12c3b7b1d40-34df0862-15fa4- | MF-HT-1209 | HT - HALO TRUST | H/3468 | 3330 | 67.1968 | 36.0198 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes |  |  | 1392 | HT | {7044F02E-107F-4B10-B5CD-256C7FB215CE} |  |  |  | Moderate | 459 | CHA | 3 |  |  | 2007-05-01 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Shamallak | {66840215-AC33-41C1-B38A-CE0C58007C5C} | c0a8-00f6-13923fd8646-fcaba30b-3cd4-2 | Hz-ID-17168 | HT - HALO TRUST | H/8236 | 21577 | 67.1079 | 36.0709 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-06-01 | 2013-07-23 | 1392 | HT | {66840215-AC33-41C1-B38A-CE0C58007C5C} |  |  |  | Moderate | 96 | CHA | 4 |  |  | 2012-07-07 16:30 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Shamallak | {66840215-AC33-41C1-B38A-CE0C58007C5C} | c0a8-00f6-139241fe313-d252bf1e-3ee4-6 | Hz-ID-17223 | HT - HALO TRUST | H/8237 | 10497 | 67.1079 | 36.0709 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-091 | Samangan Demining Project-6 | VTF-Australia | Yes | 2013-05-01 | 2013-07-19 | 1392 | HT | {66840215-AC33-41C1-B38A-CE0C58007C5C} |  |  |  | Moderate | 16 | CHA | 5 |  |  | 2012-07-08 16:30 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Ziraki | {21E525E0-011D-471F-80FE-C02B0656546F} | c0a8-0057-12c3b69f043-4bbb6305-926d-8 | MF-HQ-11160 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1508/14416/MF0027 | 359 | 67.4594 | 35.9818 | Open | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes |  |  | 1392 | HT | {21E525E0-011D-471F-80FE-C02B0656546F} |  | Medium | Agriculture Blocked | Moderate | 75 | CHA | 3 |  |  | 2009-07-02 | No | Complete
North | Samangan | Dara-I-Sufi Payin | Ziraki | {21E525E0-011D-471F-80FE-C02B0656546F} | c0a8-0057-12c3b72cbcc-edbe6a72-fe04-4 | MF-HQ-12055 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1508/14416/MF0028 | 2336 | 67.4591 | 35.9829 | Open | AP Only | AP Only | MineField | 1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes |  |  | 1392 | HT | {21E525E0-011D-471F-80FE-C02B0656546F} |  | Medium | Agriculture Blocked | Moderate | 0 | CHA | 3 |  |  | 2009-07-02 | No | Complete
North | Samangan | Feroz Nakhchir | Chenar Gai | {F3CAE643-AF42-4027-A238-02705B036032} | c0a8-0009-13ec588b0a8-5a8a6c40-2955-6 | Hz-ID-17913 | HT - HALO TRUST | H/8469 | 61670 | 67.6596 | 36.623 | Open | AP Only | AP Only | MineField |  | MBT Project-246 | Samangan Demining Project-7 |  |  |  |  | 1396 |  | {F3CAE643-AF42-4027-A238-02705B036032} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2013-04-07 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Chenar Gai | {F3CAE643-AF42-4027-A238-02705B036032} | c0a8-0009-13ec592c070-c96fa222-2978-d | Hz-ID-17912 | HT - HALO TRUST | H/8468 | 51250 | 67.6737 | 36.6245 | Open | AP Only | AP Only | MineField |  | MBT Project-246 | Samangan Demining Project-7 |  |  |  |  | 1396 |  | {F3CAE643-AF42-4027-A238-02705B036032} |  | Low | Critical Infrastracture | Low | 1 | CHA | 5 |  |  | 2013-04-05 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Chenar Gai | {F3CAE643-AF42-4027-A238-02705B036032} | c0a8-0009-13fa2c1855a-dc987727-84c-56 | Hz-ID-17911 | HT - HALO TRUST | H/8466 | 66210 | 67.6497 | 36.622 | Open | AP Only | AP Only | MineField |  | MBT Project-042 | Samangan Demining Project-1 (AT) |  |  |  |  | 1396 |  | {F3CAE643-AF42-4027-A238-02705B036032} |  | Low | Agriculture Blocked | Low | 3 | CHA | 5 |  |  | 2013-04-03 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Chenar Gai | {F3CAE643-AF42-4027-A238-02705B036032} | c0a8-008e-1328fa05b10-5e1a8964-1f75-6 | MF-16126 | MCPA - Mine Clearance Planning Agency | AF/1509/14549/MF0001 | 49849 | 67.6511 | 36.6237 | Open | AP Only | AP Only | MineField |  | MBT Project-246 | Samangan Demining Project-7 |  |  |  |  | 1396 |  | {F3CAE643-AF42-4027-A238-02705B036032} |  | Low | Critical Infrastracture | Low | 9 | CHA | 5 |  |  | 2011-06-12 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Chenar Gai | {F3CAE643-AF42-4027-A238-02705B036032} | c0a8-008e-13290736d3a-31a99f12-2a-b78 | MF-16080 | HT - HALO TRUST | H/7500 | 21340 | 67.6402 | 36.6202 | Open | AP Only | AP Only | MineField |  | MBT Project-246 | Samangan Demining Project-7 |  |  |  |  | 1396 |  | {F3CAE643-AF42-4027-A238-02705B036032} |  | Medium | Critical Infrastracture | Low | 1 | CHA | 5 |  |  | 2011-05-10 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Chenar Gai | {F3CAE643-AF42-4027-A238-02705B036032} | c0a8-008e-132c991bede-13389c80-3772-d | MF-16292 | HT - HALO TRUST | H/8213 | 64050 | 67.6219 | 36.6146 | Open | AP Only | AP Only | MineField |  | MBT Project-246 | Samangan Demining Project-7 |  |  |  |  | 1396 |  | {F3CAE643-AF42-4027-A238-02705B036032} |  | Medium | Critical Infrastracture | Low | 1 | CHA | 5 |  |  | 2011-08-05 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Chenar Gai | {F3CAE643-AF42-4027-A238-02705B036032} | c0a8-008e-132c99222bd-a3a1a4-3789-1f0 | MF-16068 | HT - HALO TRUST | H/7493 | 44000 | 67.6357 | 36.6176 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {F3CAE643-AF42-4027-A238-02705B036032} |  | Medium | Critical Infrastracture | Low | 0 | CHA | 5 |  |  | 2011-05-10 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Daulat-i Koh (1) | {4C0AEE21-AB48-4097-B7B4-5F6360DC8F9C} | c0a8-0057-12c3ba2c6c1-277b5bd4-30a07- | MF-NA-1255 | HT - HALO TRUST | H/2566 | 60000 | 67.7785 | 36.5702 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {4C0AEE21-AB48-4097-B7B4-5F6360DC8F9C} | Planned year removed | High Requested | Resettlment/Local Request | Low | 3 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Feroz Nakhchir | Dolta Khana | {5088F402-6D83-49B6-B996-30029F632002} | c0a8-0057-12c3b73cdbd-901d436b-10a06- | MF-NA-1344 | HT - HALO TRUST | H/2835 | 10130 | 67.6943 | 36.2844 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {5088F402-6D83-49B6-B996-30029F632002} |  | Low | Agriculture Blocked | Low | 33 | CHA | 5 |  |  | 2009-03-01 | No | Open
North | Samangan | Feroz Nakhchir | Pir Nakhchir (1) | {AB484A97-8414-4B26-8178-ED1552C3612B} | c0a8-0009-13de3dbc5ec-fd7bc765-551f-8 | Hz-ID-17776 | HT - HALO TRUST | H/8458 | 6450 | 67.6192 | 36.5565 | Open | AP Only | AP Only | MineField |  | MBT Project-042 | Samangan Demining Project-1 (AT) |  |  |  |  | 1396 |  | {AB484A97-8414-4B26-8178-ED1552C3612B} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2013-03-18 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Pir Nakhchir (1) | {AB484A97-8414-4B26-8178-ED1552C3612B} | c0a8-008e-132b37bf41f-cf42af43-323-91 | MF-16299 | HT - HALO TRUST | H/8206 | 6832 | 67.7262 | 36.5568 | Open | AT Only | AT Only | MineField |  | MBT Project-042 | Samangan Demining Project-1 (AT) |  |  |  |  | 1396 |  | {AB484A97-8414-4B26-8178-ED1552C3612B} |  | Low | Critical Infrastracture | Low | 0 | CHA | 5 |  |  | 2011-08-10 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Pir Nakhchir (1) | {AB484A97-8414-4B26-8178-ED1552C3612B} | c0a8-008e-132b37fe9c4-5e5877-366-e6ab | MF-16298 | HT - HALO TRUST | H/8207 | 1638 | 67.7201 | 36.5359 | Open | AT Only | AT Only | MineField |  | MBT Project-042 | Samangan Demining Project-1 (AT) |  |  |  |  | 1396 |  | {AB484A97-8414-4B26-8178-ED1552C3612B} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-08-10 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Pir Nakhchir (1) | {AB484A97-8414-4B26-8178-ED1552C3612B} | c0a8-008e-132c47bc5b9-8e04160-139a-69 | MF-16297 | HT - HALO TRUST | H/8208 | 6450 | 67.7251 | 36.5267 | Open | AT Only | AT Only | MineField |  | MBT Project-042 | Samangan Demining Project-1 (AT) |  |  |  |  | 1396 |  | {AB484A97-8414-4B26-8178-ED1552C3612B} |  | Low | Critical Infrastracture | Low | 3 | CHA | 5 |  |  | 2011-08-11 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Pir Nakhchir (1) | {AB484A97-8414-4B26-8178-ED1552C3612B} | c0a8-008e-132c992b0a8-55c61a7d-37d7-1 | MF-16293 | HT - HALO TRUST | H/8212 | 2344 | 67.6899 | 36.4977 | Open | AT Only | AT Only | MineField |  | MBT Project-042 | Samangan Demining Project-1 (AT) |  |  |  |  | 1396 |  | {AB484A97-8414-4B26-8178-ED1552C3612B} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2011-08-16 16:30 | No | Open
North | Samangan | Feroz Nakhchir | Pir Nakhchir (2) | {41F9B695-02CD-4350-8749-21F28C5D6DBF} | c0a8-008e-132c9928b9b-37082c80-37bc-1 | MF-16295 | HT - HALO TRUST | H/8210 | 49200 | 67.6481 | 36.6011 | Closed | AT Only | AT Only | MineField | 1391/1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2012-12-11 | 2014-03-23 | 1392 | HT | {41F9B695-02CD-4350-8749-21F28C5D6DBF} |  |  |  | Low | 1 | CHA | 5 |  |  | 2011-08-18 16:30 | No | Complete
North | Samangan | Feroz Nakhchir | Pir Nakhchir (2) | {41F9B695-02CD-4350-8749-21F28C5D6DBF} | c0a8-008e-132e8bc8968-97239ea4-1af8-2 | MF-16294 | HT - HALO TRUST | H/8211 | 16200 | 67.6444 | 36.6054 | Open | AT Only | AT Only | MineField | 1391/1392 | MBT Project-089 | Samangan Demining Project-3 | Bilateral | Yes | 2013-03-04 |  | 1392 | HT | {41F9B695-02CD-4350-8749-21F28C5D6DBF} |  | Low | Critical Infrastracture | Low | 1 | CHA | 5 |  |  | 2011-08-13 16:30 | No | Complete
North | Samangan | Hazrati Sultan | Dalkhaki | {A9F8F3A2-EDD8-412C-80A8-1D9AC185CD02} | c0a8-008e-13290a7e081-81a928c4-41d-1f | MF-16137 | MCPA - Mine Clearance Planning Agency | AF/1502/14606/MF0012 | 365986 | 67.9391 | 36.3638 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {A9F8F3A2-EDD8-412C-80A8-1D9AC185CD02} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2011-06-13 16:30 | No | Open
North | Samangan | Hazrati Sultan | Doulatabad | {AFE52E88-E898-4E1A-92F1-AE9B39B5AD00} | c0a8-00f6-1353dbc3bee-37caebf-1921-27 | MF-16634 | HT - HALO TRUST | H/8214 | 14850 | 67.8503 | 36.5189 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-040 | Samangan Demining Project-1 | VTF | Yes |  |  | 1392 | OMAR | {AFE52E88-E898-4E1A-92F1-AE9B39B5AD00} |  |  |  | Low | 44 | CHA | 3 |  |  | 2011-09-13 16:30 | No | Complete
North | Samangan | Hazrati Sultan | Gadi | {BC09AB9D-EA33-4A1D-9ADF-AB5B976BAA68} | c0a8-0057-12c3b7b53ca-306bc0d5-16201- | MF-NA-1345 | HT - HALO TRUST | H/2845 | 1300 | 68.1229 | 36.4222 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {BC09AB9D-EA33-4A1D-9ADF-AB5B976BAA68} |  | High with Victim | High with Victims | Low | 8 | CHA | 5 |  |  | 2009-03-01 | No | Open
North | Samangan | Hazrati Sultan | Kokjar | {A262A7C7-E7A2-41CB-A524-B93765B130DE} | c0a8-0009-13de3e29365-fce3e256-559b-6 | Hz-ID-17777 | HT - HALO TRUST | H/8453 | 411 | 67.9207 | 36.3415 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {A262A7C7-E7A2-41CB-A524-B93765B130DE} |  | Medium | Comunity Centers | Low | 1099 | CHA | 4 |  |  | 2013-03-05 16:30 | No | Planned
North | Samangan | Hazrati Sultan | Kokjar | {A262A7C7-E7A2-41CB-A524-B93765B130DE} | c0a8-0057-12c3ba47ba9-3cc0aeed-31aa0- | MF-NA-1340 | HT - HALO TRUST | H/5208 | 104000 | 67.7717 | 36.2185 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {A262A7C7-E7A2-41CB-A524-B93765B130DE} |  | High Requested | Resettlment/Local Request | Low | 50 | CHA | 5 |  |  | 2009-03-01 | No | Open
North | Samangan | Hazrati Sultan | Kokjar | {A262A7C7-E7A2-41CB-A524-B93765B130DE} | c0a8-0057-12c3ba47dfa-36a39560-31ab5- | MF-NA-1336 | HT - HALO TRUST | H/2838 | 94500 | 67.7776 | 36.2189 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {A262A7C7-E7A2-41CB-A524-B93765B130DE} | Planned Year removed | High Requested | Resettlment/Local Request | Low | 29 | CHA | 5 |  |  | 2009-03-01 | No | Open
North | Samangan | Hazrati Sultan | Qaracha Bulaq | {38B5483A-6A4B-460D-988B-B287E78E4F3B} | c0a8-0009-13de3f47c55-9e9e76db-57aa-a | Hz-ID-17779 | HT - HALO TRUST | H/8455 | 6600 | 68.0617 | 36.5383 | Open | AT Only | AT Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {38B5483A-6A4B-460D-988B-B287E78E4F3B} |  | Low | Agriculture Blocked | Low | 14 | CHA | 5 |  |  | 2013-03-02 16:30 | No | Open
North | Samangan | Hazrati Sultan | Sarqia-i-Ozbakia | {AA52CC96-82F3-4210-AA72-EB0EF5EA4CEB} | c0a8-0009-13de4093001-d6a28cbe-583d-a | Hz-ID-17781 | HT - HALO TRUST | H/8457 | 15172 | 67.8666 | 36.3935 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {AA52CC96-82F3-4210-AA72-EB0EF5EA4CEB} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2013-03-16 16:30 | No | Open
North | Samangan | Hazrati Sultan | Sarqia-i-Ozbakia | {AA52CC96-82F3-4210-AA72-EB0EF5EA4CEB} | c0a8-0009-13df37db6aa-1139832b-10ab-6 | Hz-ID-17780 | HT - HALO TRUST | H/8456 | 12768 | 67.8708 | 36.3887 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {AA52CC96-82F3-4210-AA72-EB0EF5EA4CEB} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2013-03-14 16:30 | No | Open
North | Samangan | Hazrati Sultan | Sarqia-i-Ozbakia | {AA52CC96-82F3-4210-AA72-EB0EF5EA4CEB} | c0a8-0057-12c3b768f30-bf81d379-12ac8- | MF-HT-1295 | HT - HALO TRUST | H/2850 | 1900 | 67.8964 | 36.4167 | Open | AT Only | AT Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {AA52CC96-82F3-4210-AA72-EB0EF5EA4CEB} | , | High Requested | Resettlment/Local Request | Low | 862 | CHA | 4 |  |  | 2006-10-01 | No | Open
North | Samangan | Hazrati Sultan | Zeri Lopan | {25EB00C5-B042-4246-AFFB-E5D79BB97FFD} | c0a8-0057-12c3bb33cff-9b007e96-3a732- | MF-NA-1343 | HT - HALO TRUST | H/2856 | 80300 | 67.9138 | 36.3732 | Open | AP Only | AP Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {25EB00C5-B042-4246-AFFB-E5D79BB97FFD} | , | High Requested | Resettlment/Local Request | Low | 51 | CHA | 4 |  |  | 2009-03-01 | No | Open
North | Samangan | Khuram Wa Sarbagh | Abdulmalek | {C0C5472C-1BAF-4380-AF88-2DDCD31EF80B} | c0a8-008e-132c9495c63-b45e9925-2ded-b | MF-15430 | HT - HALO TRUST | H/7385 | 29400 | 67.9976 | 35.9505 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {C0C5472C-1BAF-4380-AF88-2DDCD31EF80B} |  |  |  | Low | 15 | CHA | 5 |  |  | 2010-10-21 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Abdulmalek | {C0C5472C-1BAF-4380-AF88-2DDCD31EF80B} | c0a8-008e-132c9498e1c-ce0ac64c-2e08-6 | MF-15429 | HT - HALO TRUST | H/7384 | 6250 | 67.9995 | 35.9371 | Worked on | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {C0C5472C-1BAF-4380-AF88-2DDCD31EF80B} |  | Low | Agriculture Blocked | Low | 54 | CHA | 5 |  |  | 2010-10-20 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Baba Qambar (2) | {3C273DF7-95C9-4288-B41A-2D1CEA0B03F3} | c0a8-008e-13118b1ffbf-ca3984cc-808-9e | MF-HQ-13155 | HT - HALO TRUST | H/6344 | 3250 | 68.178 | 36.058 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-08-01 | 2013-08-10 | 1392 | OMAR | {3C273DF7-95C9-4288-B41A-2D1CEA0B03F3} | Planned Year and planned agency remove |  |  | Low | 75 | CHA | 5 |  |  | 2009-09-10 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Beshqul | {3E4A28EA-92A4-4165-A827-0EC8312ED75D} | c0a8-0057-12c3b6a3da7-10f5e4ff-95ef-4 | MF-HQ-13156 | HT - HALO TRUST | H/6343 | 41500 | 68.2492 | 35.8846 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-06-18 | 2013-07-20 | 1392 | OMAR | {3E4A28EA-92A4-4165-A827-0EC8312ED75D} |  |  |  | Low | 4 | CHA | 5 |  |  | 2010-10-12 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Beshqul | {3E4A28EA-92A4-4165-A827-0EC8312ED75D} | c0a8-008e-1328fb2c6de-3b200dcc-22e1-7 | MF-15383 | HT - HALO TRUST | H/7382 | 41500 | 68.246 | 35.883 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-07-13 | 2013-08-13 | 1392 | OMAR | {3E4A28EA-92A4-4165-A827-0EC8312ED75D} |  |  |  | Low | 4 | CHA | 5 |  |  | 2010-10-13 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Darun Zaw | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} | c0a8-0009-13f0d931231-7818aebf-2636-8 | Hz-ID-17914 | HT - HALO TRUST | H/8470 | 16950 | 68.0252 | 36.0284 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} |  | Low | Agriculture Blocked | Low | 8 | CHA | 5 |  |  | 2013-04-19 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Darun Zaw | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} | c0a8-0009-13fa2c66fe5-cffe2928-8d2-61 | Hz-ID-17915 | HT - HALO TRUST | H/8473 | 32850 | 68.032 | 36.0237 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2013-04-20 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Darun Zaw | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} | c0a8-0057-12c3b93e64b-2f739bc7-27230- | MF-NA-997 | HT - HALO TRUST | H/2757 | 18400 | 68.0544 | 36.0415 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-08-17 | 2013-08-25 | 1392 | OMAR | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} |  |  |  | Low | 22 | CHA | 5 |  |  | 2008-08-01 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Darun Zaw | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} | c0a8-0057-12c3b93e82f-b5e69a37-27248- | MF-NA-998 | HT - HALO TRUST | H/4809 | 7069 | 68.057 | 36.0402 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} |  |  |  | Low | 17 | CHA | 5 |  |  | 2008-08-01 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Darun Zaw | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} | c0a8-0057-12c3b95eec2-28e3c8b-287d0-a | MF-NA-996 | HT - HALO TRUST | H/4808 | 20637 | 68.0455 | 36.0452 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-08-17 | 2013-08-25 | 1392 | OMAR | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} |  |  |  | Low | 11 | CHA | 5 |  |  | 2008-08-01 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Darun Zaw | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} | c0a8-0057-12c3b95f0b5-fcc1f8ee-287e9- | MF-NA-1045 | HT - HALO TRUST | H/5163 | 30160 | 68.0268 | 36.0311 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-08-17 | 2013-08-26 | 1392 | OMAR | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} |  |  |  | Low | 6 | CHA | 5 |  |  | 2008-09-01 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Darun Zaw | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} | c0a8-0057-12c3b95f2f6-b4556462-287ff- | MF-NA-1046 | HT - HALO TRUST | H/5164 | 32240 | 68.0253 | 36.0298 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-08-17 | 2013-08-29 | 1392 | OMAR | {454E49B9-AAA6-4D7B-BFAF-FA08CB3FD2E4} |  |  |  | Low | 20 | CHA | 5 |  |  | 2008-09-01 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Deh-i-Naw | {C4A3F623-3EAE-4EA3-8B2A-74525F01E533} | c0a8-00f6-1384643ad3f-42600af2-1cd4-7 | Hz-ID-17086 | HT - HALO TRUST | H/8227 | 47300 | 68.0296 | 36.018 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-08-21 | 2013-08-29 | 1392 | OMAR | {C4A3F623-3EAE-4EA3-8B2A-74525F01E533} |  |  |  | Low | 2 | CHA | 5 |  |  | 2012-05-16 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Habash | {4AEB3655-4D49-4154-9529-8A3AF0860041} | c0a8-0009-13b5a408757-d7ea6138-2616-a | Hz-ID-17422 | HT - HALO TRUST | H/8410 | 37800 | 68.0627 | 35.8932 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {4AEB3655-4D49-4154-9529-8A3AF0860041} |  | Low | Agriculture Blocked | Low | 6 | CHA | 5 |  |  | 2012-10-09 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Habash | {4AEB3655-4D49-4154-9529-8A3AF0860041} | c0a8-0009-13b5a45b6dd-c8774f2-2637-f3 | Hz-ID-17423 | HT - HALO TRUST | H/8411 | 37680 | 68.0634 | 35.8932 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {4AEB3655-4D49-4154-9529-8A3AF0860041} |  | Low | Agriculture Blocked | Low | 6 | CHA | 5 |  |  | 2012-10-09 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Habash | {4AEB3655-4D49-4154-9529-8A3AF0860041} | c0a8-0009-13b5a47929b-7485cc34-265c-a | Hz-ID-17424 | HT - HALO TRUST | H/8412 | 20320 | 68.0883 | 35.8668 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {4AEB3655-4D49-4154-9529-8A3AF0860041} |  | Low | Agriculture Blocked | Low | 5 | CHA | 5 |  |  | 2012-10-10 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Habash | {4AEB3655-4D49-4154-9529-8A3AF0860041} | c0a8-0009-13b5a4a615d-322a332f-267d-1 | Hz-ID-17425 | HT - HALO TRUST | H/8413 | 26000 | 68.1046 | 35.8616 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {4AEB3655-4D49-4154-9529-8A3AF0860041} |  | Low | Agriculture Blocked | Low | 3 | CHA | 5 |  |  | 2012-10-14 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Habash | {4AEB3655-4D49-4154-9529-8A3AF0860041} | c0a8-0009-13b5a4b138b-98aad629-269f-4 | Hz-ID-17426 | HT - HALO TRUST | H/8414 | 11600 | 68.1034 | 35.8711 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {4AEB3655-4D49-4154-9529-8A3AF0860041} |  | Low | Agriculture Blocked | Low | 6 | CHA | 5 |  |  | 2012-10-16 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Habash | {4AEB3655-4D49-4154-9529-8A3AF0860041} | c0a8-0009-13b5a8bd79d-2db06fde-2702-b | Hz-ID-17427 | HT - HALO TRUST | H/8415 | 9700 | 68.1088 | 35.8744 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {4AEB3655-4D49-4154-9529-8A3AF0860041} |  | Low | Agriculture Blocked | Low | 7 | CHA | 5 |  |  | 2012-10-16 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Junjushka | {C3A1007E-6417-454E-AA29-91F64B55355D} | c0a8-0009-13fdc68d3ad-6bdbb54d-25cb-d | Hz-ID-18048 | HT - HALO TRUST | H/8500 | 14670 | 68.2231 | 35.8283 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {C3A1007E-6417-454E-AA29-91F64B55355D} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2013-06-09 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Junjushka | {C3A1007E-6417-454E-AA29-91F64B55355D} | c0a8-0009-13fdc69437f-54bbddf5-25e7-9 | Hz-ID-18046 | HT - HALO TRUST | H/8498 | 21161 | 68.21 | 35.8326 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {C3A1007E-6417-454E-AA29-91F64B55355D} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2013-06-06 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Junjushka | {C3A1007E-6417-454E-AA29-91F64B55355D} | c0a8-0057-12c3b705913-44146947-e072-b | MF-HQ-13217 | HT - HALO TRUST | H/6483 | 3900 | 68.2292 | 35.8332 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-06-01 | 2013-06-17 | 1392 | OMAR | {C3A1007E-6417-454E-AA29-91F64B55355D} |  |  |  | Low | 19 | CHA | 5 |  |  | 2009-09-11 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Junjushka | {C3A1007E-6417-454E-AA29-91F64B55355D} | c0a8-0057-12c3b74390b-987c1b0f-10f2b- | MF-HQ-13216 | HT - HALO TRUST | H/6484 | 6000 | 68.2254 | 35.8273 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-06-01 | 2013-06-20 | 1392 | OMAR | {C3A1007E-6417-454E-AA29-91F64B55355D} |  |  |  | Low | 10 | CHA | 5 |  |  | 2009-09-11 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Junjushka | {C3A1007E-6417-454E-AA29-91F64B55355D} | c0a8-0057-12c3b775a49-956af04f-13405- | MF-HQ-13218 | HT - HALO TRUST | H/6482 | 6550 | 68.2348 | 35.8385 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-06-01 | 2013-07-04 | 1392 | OMAR | {C3A1007E-6417-454E-AA29-91F64B55355D} |  |  |  | Low | 4 | CHA | 5 |  |  | 2009-09-11 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Junjushka | {C3A1007E-6417-454E-AA29-91F64B55355D} | c0a8-0057-12c3b7b7b08-50085470-163ba- | MF-HQ-13147 | HT - HALO TRUST | H/6481 | 5800 | 68.2354 | 35.8455 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-06-01 | 2013-06-17 | 1392 | OMAR | {C3A1007E-6417-454E-AA29-91F64B55355D} |  |  |  | Low | 5 | CHA | 5 |  |  | 2009-09-11 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Khwaja Qashqar-i-Pa'in | {D6B56CEF-EE6D-47D2-923B-9F794F82FE52} | c0a8-0057-12c3b6910ff-ab47ce33-8841-7 | MF-HQ-15340 | HT - HALO TRUST | H/7326 | 3700 | 68.2768 | 36.0379 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-040 | Samangan Demining Project-1 | VTF | Yes | 2013-07-13 | 2013-07-18 | 1392 | OMAR | {D6B56CEF-EE6D-47D2-923B-9F794F82FE52} |  |  |  | Low | 20 | CHA | 3 |  |  | 2010-10-02 | No | Complete
North | Samangan | Khuram Wa Sarbagh | Khwaja Qashqar-i-Pa'in | {D6B56CEF-EE6D-47D2-923B-9F794F82FE52} | c0a8-0057-12c3b76ca7a-a8594add-12d90- | MF-HQ-15341 | HT - HALO TRUST | H/7327 | 7300 | 68.283 | 36.0331 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-07-20 | 2013-07-31 | 1392 | OMAR | {D6B56CEF-EE6D-47D2-923B-9F794F82FE52} |  |  |  | Low | 9 | CHA | 5 |  |  | 2010-10-04 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3cc8f-8689aa9a-3ac78- | MF-NA-973 | HT - HALO TRUST | H/4919 | 50000 | 67.9534 | 35.8368 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  | High Requested | Resettlment/Local Request | Low | 14 | CHA | 5 | Yes | High Requested | 2008-08-01 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3ce73-b6262c84-3ac8c- | MF-NA-961 | HT - HALO TRUST | H/4928 | 58797 | 67.9537 | 35.8407 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-041/A | Samangan Demining Project-10 /A | B-Sweden | Yes | 2013-07-01 | 2013-10-22 | 1392 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  |  |  | Low | 3 | CHA | 5 | Yes | High Requested | 2008-06-01 | No | Complete
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3d056-c31bc2d1-3aca0- | MF-HT-945 | HT - HALO TRUST | H/2745 | 50000 | 67.9557 | 35.8426 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-041/A | Samangan Demining Project-10 /A | B-Sweden | Yes | 2013-04-16 | 2013-06-30 | 1392 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  |  |  | Low | 11 | CHA | 5 |  |  | 2008-08-01 | No | Complete
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3d278-50d97feb-3acb2- | MF-NA-954 | HT - HALO TRUST | H/4921 | 50000 | 67.9512 | 35.8329 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  | No |  |  | 1395 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  | High Requested | Resettlment/Local Request | Low | 11 | CHA | 5 | Yes | High Requested | 2008-06-01 | No | Open
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3d43d-840c28fb-3acc8- | MF-NA-968 | HT - HALO TRUST | H/4915 | 50000 | 67.9557 | 35.8385 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-041/A | Samangan Demining Project-10 /A | B-Sweden | Yes | 2013-05-16 | 2013-07-30 | 1392 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  |  |  | Low | 2 | CHA | 5 |  |  | 2008-08-01 | No | Complete
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3d640-97a0130c-3acda- | MF-NA-956 | HT - HALO TRUST | H/4926 | 50000 | 67.9514 | 35.8384 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  | No |  |  | 1395 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  | High Requested | Resettlment/Local Request | Low | 9 | CHA | 5 | Yes | High Requested | 2008-06-01 | No | Open
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3d862-8622aac5-3acee- | MF-NA-959 | HT - HALO TRUST | H/4927 | 50000 | 67.9525 | 35.8396 | Open | AP Only | AP Only | MineField | 1392 | MBT Project-093 | Samangan Demining Project-9 |  | No |  |  | 1395 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 5 | Yes | High Requested | 2008-06-01 | No | Open
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3da26-56ce6641-3ad03- | MF-NA-966 | HT - HALO TRUST | H/4924 | 50000 | 67.9491 | 35.836 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  | No |  |  | 1395 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  | High Requested | Resettlment/Local Request | Low | 9 | CHA | 5 | Yes | High Requested | 2008-08-01 | No | Open
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3de7a-884db3e0-3ad2e- | MF-NA-962 | HT - HALO TRUST | H/4923 | 50000 | 67.9476 | 35.8343 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  | No |  |  | 1395 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  | High Requested | Resettlment/Local Request | Low | 7 | CHA | 5 | Yes | High Requested | 2008-06-01 | No | Open
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3e05d-5e6277d0-3ad42- | MF-NA-960 | HT - HALO TRUST | H/4929 | 36250 | 67.9533 | 35.8432 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-041/A | Samangan Demining Project-10 /A | B-Sweden | Yes | 2013-08-01 | 2013-09-22 | 1392 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  |  |  | Low | 1 | CHA | 5 | Yes | High Requested | 2008-06-01 | No | Complete
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3e260-98d0ea0b-3ad56- | MF-NA-955 | HT - HALO TRUST | H/4925 | 50000 | 67.9503 | 35.8372 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  | No |  |  | 1395 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  | High Requested | Resettlment/Local Request | Low | 9 | CHA | 5 | Yes | High Requested | 2008-06-01 | No | Open
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3e472-970da8ac-3ad6a- | MF-NA-977 | HT - HALO TRUST | H/4916 | 50000 | 67.9543 | 35.8375 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  | High Requested | Resettlment/Local Request | Low | 2 | CHA | 5 | Yes | High Requested | 2008-08-01 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3e878-1e5db882-3ad9b- | MF-NA-976 | HT - HALO TRUST | H/4917 | 50000 | 67.9529 | 35.8363 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130/A | Samangan Demining Project-11/A |  | No |  |  | 1395 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} | , | High Requested | Resettlment/Local Request | Low | 9 | CHA | 5 | Yes | High Requested | 2008-08-01 | No | Open
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3ead8-88ebd13-3adaf-e | MF-NA-963 | HT - HALO TRUST | H/4922 | 51234 | 67.9483 | 35.8328 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  | No |  |  | 1395 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  | High Requested | Resettlment/Local Request | Low | 11 | CHA | 5 | Yes | High Requested | 2008-06-01 | No | Open
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3ecfa-ffb367cc-3adc5- | MF-NA-972 | HT - HALO TRUST | H/4920 | 50000 | 67.9541 | 35.8334 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130/A | Samangan Demining Project-11/A |  | No |  |  | 1395 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} | , | High Requested | Resettlment/Local Request | Low | 14 | CHA | 5 | Yes | High Requested | 2008-08-01 | No | Open
North | Samangan | Khuram Wa Sarbagh | Koloro Dahshil(Khoram) | {8983829E-1656-40D1-AA4A-2F331626DAF0} | c0a8-0057-12c3bb3f19c-1ae9cb6c-3adef- | MF-NA-974 | HT - HALO TRUST | H/4918 | 52500 | 67.9516 | 35.8349 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  | No |  |  | 1395 | DDG | {8983829E-1656-40D1-AA4A-2F331626DAF0} |  | High Requested | Resettlment/Local Request | Low | 9 | CHA | 5 | Yes | High Requested | 2008-08-01 | No | Open
North | Samangan | Khuram Wa Sarbagh | Langar | {8A1FE9DD-D162-4F6A-BEA5-AD0F149EABBE} | c0a8-008e-132fb4a27b9-8bfae126-31b-a6 | MF-16328 | MCPA - Mine Clearance Planning Agency | AF/1506/14144/MF0020 | 6646 | 68.056 | 35.9768 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {8A1FE9DD-D162-4F6A-BEA5-AD0F149EABBE} |  |  |  | Low | 19 | CHA | 5 |  |  | 2011-07-13 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Langar | {8A1FE9DD-D162-4F6A-BEA5-AD0F149EABBE} | c0a8-008e-132fb4c7816-de040cfd-32f-10 | MF-16329 | MCPA - Mine Clearance Planning Agency | AF/1506/14144/MF0021 | 7227 | 68.0595 | 35.9763 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {8A1FE9DD-D162-4F6A-BEA5-AD0F149EABBE} |  |  |  | Low | 21 | CHA | 5 |  |  | 2011-07-14 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Langar | {8A1FE9DD-D162-4F6A-BEA5-AD0F149EABBE} | c0a8-008e-132fb4f0247-78528a74-34e-cf | MF-16330 | MCPA - Mine Clearance Planning Agency | AF/1506/14144/MF0022 | 3318 | 68.0575 | 35.9771 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {8A1FE9DD-D162-4F6A-BEA5-AD0F149EABBE} |  |  |  | Low | 10 | CHA | 5 |  |  | 2011-07-16 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Langar | {8A1FE9DD-D162-4F6A-BEA5-AD0F149EABBE} | c0a8-008e-132fb4fe247-52bc5dfb-361-6d | MF-16331 | MCPA - Mine Clearance Planning Agency | AF/1506/14144/MF0023 | 15960 | 68.0595 | 35.9763 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {8A1FE9DD-D162-4F6A-BEA5-AD0F149EABBE} |  |  |  | Low | 8 | CHA | 5 |  |  | 2011-07-17 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Langar | {8A1FE9DD-D162-4F6A-BEA5-AD0F149EABBE} | c0a8-008e-1345f4ac366-c5972cd3-1d1a-6 | MF-16440 | HT - HALO TRUST | H/7438 | 16200 | 68.0574 | 35.9771 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {8A1FE9DD-D162-4F6A-BEA5-AD0F149EABBE} |  |  |  | Low | 11 | CHA | 5 |  |  | 2011-06-19 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Mankot | {859C9D05-DCA5-44EC-8891-C98BD3883FE0} | c0a8-0057-12c3b764c29-ec9ec299-127a5- | MF-HQ-15345 | HT - HALO TRUST | H/7329 | 950 | 68.316 | 36.0063 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-07-21 | 2013-07-31 | 1392 | OMAR | {859C9D05-DCA5-44EC-8891-C98BD3883FE0} |  |  |  | Low | 3 | CHA | 5 |  |  | 2010-10-07 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Mankot | {859C9D05-DCA5-44EC-8891-C98BD3883FE0} | c0a8-0057-12c3b77e548-935ab96-13a5e-2 | MF-HQ-15343 | HT - HALO TRUST | H/7328 | 29000 | 68.3047 | 35.9984 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-07-21 | 2013-08-20 | 1392 | OMAR | {859C9D05-DCA5-44EC-8891-C98BD3883FE0} |  |  |  | Low | 1 | CHA | 5 |  |  | 2010-10-05 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Mankot | {859C9D05-DCA5-44EC-8891-C98BD3883FE0} | c0a8-008e-132c94aafac-49cbdee0-2e7f-b | MF-15424 | HT - HALO TRUST | H/7330 | 3600 | 68.3153 | 36.0143 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-08-21 | 2013-08-31 | 1392 | OMAR | {859C9D05-DCA5-44EC-8891-C98BD3883FE0} |  |  |  | Low | 14 | CHA | 5 |  |  | 2010-10-06 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Mankot | {859C9D05-DCA5-44EC-8891-C98BD3883FE0} | c0a8-00f6-138465ce352-1672cd41-1da7-a | Hz-ID-17084 | HT - HALO TRUST | B/2794 | 1350 | 68.2836 | 36.0117 | Open | UXO Only | UXO Only | BF |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {859C9D05-DCA5-44EC-8891-C98BD3883FE0} |  | High | Critical Infrastracture | Low | 172 | CHA | 3 |  |  | 2012-05-17 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Nawbolaq | {1BD66A62-ACAF-4B14-BA68-8CB8802BAC01} | c0a8-0057-12c3b7eeed7-75fc4e55-18a94- | MF-NA-1042 | HT - HALO TRUST | H/5156 | 26800 | 68.2513 | 35.9475 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-07-21 | 2013-08-11 | 1392 | OMAR | {1BD66A62-ACAF-4B14-BA68-8CB8802BAC01} |  |  |  | Low | 127 | CHA | 5 |  |  | 2008-09-01 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Nawbolaq | {1BD66A62-ACAF-4B14-BA68-8CB8802BAC01} | c0a8-0057-12c3b9cbd71-adf8467d-2cef4- | MF-NA-1051 | HT - HALO TRUST | H/2861 | 37800 | 68.2631 | 35.9426 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-040 | Samangan Demining Project-1 | VTF | Yes | 2013-06-22 | 2013-07-22 | 1392 | OMAR | {1BD66A62-ACAF-4B14-BA68-8CB8802BAC01} |  |  |  | Low | 130 | CHA | 4 |  |  | 2008-09-01 | No | Complete
North | Samangan | Khuram Wa Sarbagh | Nawbolaq | {1BD66A62-ACAF-4B14-BA68-8CB8802BAC01} | c0a8-008e-132c94a443e-ca328b2-2e4c-74 | MF-15427 | HT - HALO TRUST | H/7381 | 17480 | 68.2947 | 35.981 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-040 | Samangan Demining Project-1 | VTF | Yes | 2013-07-23 | 2013-08-15 | 1392 | OMAR | {1BD66A62-ACAF-4B14-BA68-8CB8802BAC01} |  |  |  | Low | 0 | CHA | 4 |  |  | 2010-10-09 16:30 | No | Complete
North | Samangan | Khuram Wa Sarbagh | Qaradang | {FD1C746C-DBE3-4F07-A8AF-6C71D6870CBF} | c0a8-0057-12c3b76f60c-8681ae2c-12f7f- | MF-HQ-13161 | HT - HALO TRUST | H/6340 | 7700 | 68.2427 | 35.961 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-08-28 | 2013-09-03 | 1392 | OMAR | {FD1C746C-DBE3-4F07-A8AF-6C71D6870CBF} | Based on HALO Trust e-mail received on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet) the hazard removed from |  |  | Low | 24 | CHA | 5 |  |  | 2009-09-07 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Qazangozar | {5F9E54F1-183A-4289-B1B3-145DC06B7424} | c0a8-008e-132c94a1c55-882a12d7-2e36-e | MF-15428 | HT - HALO TRUST | H/7383 | 12800 | 68.2027 | 35.865 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-06-18 | 2013-07-11 | 1392 | OMAR | {5F9E54F1-183A-4289-B1B3-145DC06B7424} |  |  |  | Low | 11 | CHA | 5 |  |  | 2010-10-18 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Qghreqol | {92454DFC-60F1-4C5C-8BC6-11B6A572F19B} | c0a8-0057-12c3b6d561e-13a06abe-bb8c-9 | MF-HQ-13158 | HT - HALO TRUST | H/6342 | 28500 | 68.2569 | 35.9027 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-06-01 | 2013-07-04 | 1392 | OMAR | {92454DFC-60F1-4C5C-8BC6-11B6A572F19B} | Based on HALO Trust e-mail received on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet) the hazard removed from |  |  | Low | 14 | CHA | 5 |  |  | 2009-09-08 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Qghreqol | {92454DFC-60F1-4C5C-8BC6-11B6A572F19B} | c0a8-0057-12c3b6f1025-76c029c4-d0a8-a | MF-HQ-13159 | HT - HALO TRUST | H/6341 | 17500 | 68.2588 | 35.9056 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes | 2013-06-01 | 2013-06-17 | 1392 | OMAR | {92454DFC-60F1-4C5C-8BC6-11B6A572F19B} | Based on HALO Trust e-mail received on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet) the hazard removed from |  |  | Low | 9 | CHA | 5 |  |  | 2009-09-08 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Rabatak | {B068C12E-00D8-481B-AA50-918471FCC94D} | c0a8-0009-142e55daf8a-c40e6d5b-6702-4 | Hz-ID-18266 | HT - HALO TRUST | H/8854 | 8570 | 68.4079 | 36.1036 | Open | AT Only | AT Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {B068C12E-00D8-481B-AA50-918471FCC94D} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2013-11-13 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Rabatak | {B068C12E-00D8-481B-AA50-918471FCC94D} | c0a8-0009-142e55eef47-bebc69fd-6744-a | Hz-ID-18267 | HT - HALO TRUST | H/8855 | 1121 | 68.4128 | 36.1118 | Open | AT Only | AT Only | MineField |  | MBT Project-128 | Samangan Demining Project-2 |  |  |  |  | 1394 |  | {B068C12E-00D8-481B-AA50-918471FCC94D} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2013-11-15 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Rabatak | {B068C12E-00D8-481B-AA50-918471FCC94D} | c0a8-0009-142e55ff0ec-6f6cc3eb-6769-4 | Hz-ID-18268 | HT - HALO TRUST | H/8856 | 644 | 68.4096 | 36.1491 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-095 | Samangan Demining Project-2 (AT) | Bilateral | Yes |  |  | 1393 | HT | {B068C12E-00D8-481B-AA50-918471FCC94D} |  | High with Victim | High with Victims | Low | 425 | CHA | 2 |  |  | 2013-11-17 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Rabatak | {B068C12E-00D8-481B-AA50-918471FCC94D} | c0a8-008e-1342cc3cc07-43a11eee-4b1-f6 | MF-16407 | HT - HALO TRUST | H/8249 | 37500 | 68.2975 | 36.2006 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-040 | Samangan Demining Project-1 | VTF | Yes |  |  | 1392 | OMAR | {B068C12E-00D8-481B-AA50-918471FCC94D} |  |  |  | Low | 13 | CHA | 2 |  |  | 2011-11-21 16:30 | No | Complete
North | Samangan | Khuram Wa Sarbagh | Rabatak | {B068C12E-00D8-481B-AA50-918471FCC94D} | c0a8-00f6-1352e359735-2fb383b1-ca-d6b | MF-16560 | HT - HALO TRUST | H/8250 | 870 | 68.3001 | 36.1853 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-040 | Samangan Demining Project-1 | VTF | Yes |  |  | 1392 | OMAR | {B068C12E-00D8-481B-AA50-918471FCC94D} |  |  |  | Low | 14 | CHA | 2 |  |  | 2011-12-20 16:30 | No | Complete
North | Samangan | Khuram Wa Sarbagh | Rabatak | {B068C12E-00D8-481B-AA50-918471FCC94D} | c0a8-00f6-1353c918678-3aa83bda-1489-c | MF-16633 | HT - HALO TRUST | H/8241 | 7950 | 68.4071 | 36.1472 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-040 | Samangan Demining Project-1 | VTF | Yes |  |  | 1392 | OMAR | {B068C12E-00D8-481B-AA50-918471FCC94D} |  |  |  | Low | 481 | CHA | 2 |  |  | 2011-09-11 16:30 | No | Complete
North | Samangan | Khuram Wa Sarbagh | Robatak | {07788238-556B-45FA-A75D-61C72DE3105C} | c0a8-0057-12c3bab761c-1aff4d2-35cd3-a | MF-NA-1040 | HT - HALO TRUST | H/2858 | 26000 | 68.3586 | 36.1012 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {07788238-556B-45FA-A75D-61C72DE3105C} |  |  |  | Low | 0 | CHA | 5 |  |  | 2008-09-01 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Robatak | {07788238-556B-45FA-A75D-61C72DE3105C} | c0a8-00f6-138472d0fd8-5ffffe63-1f87-5 | Hz-ID-17087 | HT - HALO TRUST | H/8228 | 6020 | 68.4123 | 36.1526 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-040 | Samangan Demining Project-1 | VTF | Yes |  |  | 1392 | OMAR | {07788238-556B-45FA-A75D-61C72DE3105C} |  |  |  | Low | 318 | CHA | 3 |  |  | 2012-05-20 16:30 | No | Complete
North | Samangan | Khuram Wa Sarbagh | Shahre Naw | {5FBB5F04-0558-4843-A663-FDD38E5DCBC5} | c0a8-0009-142e55cd1ca-a1e738fc-66b4-c | Hz-ID-18265 | HT - HALO TRUST | H/8853 | 16082 | 68.0707 | 35.9638 | Open | AP Only | AP Only | MineField |  | MBT Project-093 | Samangan Demining Project-9 |  |  |  |  | 1395 |  | {5FBB5F04-0558-4843-A663-FDD38E5DCBC5} |  | Low | Agriculture Blocked | Low | 14 | CHA | 5 |  |  | 2013-11-11 16:30 | No | Open
North | Samangan | Khuram Wa Sarbagh | Shahre Naw | {5FBB5F04-0558-4843-A663-FDD38E5DCBC5} | c0a8-0057-12c3ba77a3b-19dd564e-337f4- | MF-NA-1022 | HT - HALO TRUST | H/4907 | 47500 | 68.0611 | 35.9563 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {5FBB5F04-0558-4843-A663-FDD38E5DCBC5} | Planned Year removed |  |  | Low | 11 | CHA | 5 |  |  | 2008-08-01 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Shahre Naw | {5FBB5F04-0558-4843-A663-FDD38E5DCBC5} | c0a8-00f6-1349d2cf67b-8da04543-1d0-77 | MF-16472 | HT - HALO TRUST | H/8247 | 37250 | 68.022 | 35.9631 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {5FBB5F04-0558-4843-A663-FDD38E5DCBC5} |  |  |  | Low | 12 | CHA | 5 |  |  | 2011-10-18 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Shahre Naw | {5FBB5F04-0558-4843-A663-FDD38E5DCBC5} | c0a8-00f6-1349d2efd46-b7525917-203-b7 | MF-16470 | HT - HALO TRUST | H/8246 | 37100 | 68.022 | 35.9631 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {5FBB5F04-0558-4843-A663-FDD38E5DCBC5} |  |  |  | Low | 12 | CHA | 5 |  |  | 2011-10-17 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Shahre Naw | {5FBB5F04-0558-4843-A663-FDD38E5DCBC5} | c0a8-00f6-1349d32345e-266a380a-23f-59 | MF-16469 | HT - HALO TRUST | H/8245 | 34880 | 68.0314 | 35.956 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-092 | Samangan Demining Project-8 | VTF | Yes |  |  | 1392 | OMAR | {5FBB5F04-0558-4843-A663-FDD38E5DCBC5} |  |  |  | Low | 50 | CHA | 5 |  |  | 2011-10-16 16:30 | No | Planned
North | Samangan | Khuram Wa Sarbagh | Tana Chob | {E3872D13-3732-4D83-9D1B-132F0D0B2A06} | c0a8-00f6-1349d29bd43-1762d4d1-18b-a7 | MF-16474 | HT - HALO TRUST | H/8248 | 3140 | 68.1136 | 35.9855 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130/A | Samangan Demining Project-11/A |  | No |  |  | 1395 | DDG | {E3872D13-3732-4D83-9D1B-132F0D0B2A06} |  | Low | Agriculture Blocked | Low | 5 | CHA | 5 |  |  | 2011-10-21 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b6ab8ae-719e879-9bd2-34 | MF-NA-1174 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5033 | 24504 | 68.1355 | 35.5049 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes | 2014-05-01 | 2014-06-22 | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  |  |  | Low | 4 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b6c089e-2491eaf6-abbe-c | MF-NA-1171 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF2888 | 13098 | 68.132 | 35.4989 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes | 2014-05-01 | 2014-06-22 | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  |  |  | Low | 4 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b6e39a7-be6b2c72-c672-6 | MF-NA-1180 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5036 | 25378 | 68.132 | 35.4989 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes | 2014-05-01 | 2014-06-22 | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 5 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b71a56b-9c2e03ac-f01d-a | MF-NA-1179 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5035 | 4181 | 68.132 | 35.4989 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes | 2014-05-01 | 2014-06-22 | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  |  |  | Low | 0 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b759145-5fd9f85a-11f1d- | MF-NA-1182 | MCPA - Mine Clearance Planning Agency | H/5039 | 7337 | 68.1436 | 35.5276 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes | 2014-05-01 | 2014-06-22 | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b775e2f-9d78d21a-1343e- | MF-NA-1185 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5041 | 10886 | 68.1471 | 35.528 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b78ed31-aa27bec0-14677- | MF-NA-1183 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5037 | 26925 | 68.144 | 35.5259 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b78eef5-2e3ce081-1468e- | MF-NA-1181 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5038 | 19167 | 68.144 | 35.5259 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b831c13-1906e328-1ba1b- | MF-NA-1152 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5045 | 35689 | 68.1511 | 35.5404 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b831ef0-93c00346-1ba33- | MF-NA-1151 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5044 | 28984 | 68.1508 | 35.5385 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b832122-248fe2-1ba4d-ca | MF-NA-1147 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5042 | 20412 | 68.15 | 35.5335 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3b832315-ee327c46-1ba67- | MF-NA-1149 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5043 | 12540 | 68.1497 | 35.5362 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3bb0e371-b2a6e3ae-3908e- | MF-NA-1153 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5155 | 41923 | 68.0998 | 35.4684 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 5 | CHA | 6 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3bb0e62f-423e8a23-390a2- | MF-NA-1156 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5152 | 19467 | 68.1051 | 35.4676 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 2 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3bb0e870-48dbfca1-390b9- | MF-NA-1158 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5150 | 20839 | 68.1089 | 35.4716 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 2 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3bb0ead0-b881919d-390cf- | MF-NA-1159 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5050 | 17289 | 68.1105 | 35.4779 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 5 | CHA | 5 |  |  | 2010-12-04 16:30 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3bb0ee59-d19d8b79-390e6- | MF-NA-1154 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5154 | 25168 | 68.0998 | 35.4684 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 2 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-0057-12c3bb0f0aa-4f02e68a-390fb- | MF-NA-1157 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF5151 | 8878 | 68.1089 | 35.4716 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | High Requested | Resettlment/Local Request | Low | 2 | CHA | 5 |  |  | 2009-01-01 | No | Planned
North | Samangan | Ruyi Du Ab | Ahengaran | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} | c0a8-008e-132c949edf6-d2b1059b-2e21-b | MF-15491 | MCPA - Mine Clearance Planning Agency | AF/1505/14652/MF7310 | 28651 | 68.1362 | 35.5042 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-130 | Samangan Demining Project-11 | SIDA | Yes |  |  | 1393 | DDG | {C6D57991-5329-4AE7-8E8C-2BC8A7E852D1} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2010-11-12 16:30 | No | Planned
North | Samangan | Ruyi Du Ab | Alawuddin | {01DC2093-1D3D-4B33-9603-96D4888B4422} | c0a8-0057-12c3b8e490f-313b7e35-237a0- | MF-NA-1092 | HT - HALO TRUST | H/2872 | 28400 | 67.609 | 35.5944 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {01DC2093-1D3D-4B33-9603-96D4888B4422} |  | High Requested | Resettlment/Local Request | Low | 5 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Alawuddin | {01DC2093-1D3D-4B33-9603-96D4888B4422} | c0a8-0057-12c3bafc6b0-f5f8de7e-3862c- | MF-NA-1089 | HT - HALO TRUST | H/5181 | 7150 | 67.5631 | 35.5845 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {01DC2093-1D3D-4B33-9603-96D4888B4422} |  | High Requested | Resettlment/Local Request | Low | 4 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Alawuddin | {01DC2093-1D3D-4B33-9603-96D4888B4422} | c0a8-0057-12c3bafc8d2-eed6a9ee-38645- | MF-NA-1088 | HT - HALO TRUST | H/2871 | 8520 | 67.5568 | 35.5831 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {01DC2093-1D3D-4B33-9603-96D4888B4422} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Alawuddin | {01DC2093-1D3D-4B33-9603-96D4888B4422} | c0a8-0057-12c3bafcb04-44d734d2-3865e- | MF-NA-1091 | HT - HALO TRUST | H/5183 | 6680 | 67.5701 | 35.5804 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {01DC2093-1D3D-4B33-9603-96D4888B4422} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Alawuddin | {01DC2093-1D3D-4B33-9603-96D4888B4422} | c0a8-0057-12c3bafcd45-59e60ab5-38679- | MF-NA-1090 | HT - HALO TRUST | H/5182 | 12350 | 67.57 | 35.5807 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {01DC2093-1D3D-4B33-9603-96D4888B4422} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Balaghli | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} | c0a8-0057-12c3b72e9b7-1d300e8a-ff63-7 | MF-NA-1194 | HT - HALO TRUST | H/5190 | 47179 | 67.5338 | 35.6021 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} |  | High Requested | Resettlment/Local Request | Low | 16 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Balaghli | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} | c0a8-0057-12c3b755ba5-e3a5f5c2-11ca1- | MF-NA-1192 | HT - HALO TRUST | H/5188 | 48800 | 67.531 | 35.6067 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} |  | High Requested | Resettlment/Local Request | Low | 9 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Balaghli | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} | c0a8-0057-12c3b773e61-87de72b5-132c9- | MF-NA-1189 | HT - HALO TRUST | H/5185 | 37600 | 67.5366 | 35.6071 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} |  | High Requested | Resettlment/Local Request | Low | 10 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Balaghli | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} | c0a8-0057-12c3b77df5e-728fb269-13a16- | MF-NA-1191 | HT - HALO TRUST | H/5187 | 61200 | 67.5333 | 35.6056 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} |  | High Requested | Resettlment/Local Request | Low | 16 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Balaghli | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} | c0a8-0057-12c3b78915d-80374736-1422b- | MF-NA-1190 | HT - HALO TRUST | H/5186 | 35600 | 67.5366 | 35.6071 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} |  | High Requested | Resettlment/Local Request | Low | 10 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Balaghli | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} | c0a8-0057-12c3b7b3ea5-4a94f722-1611c- | MF-NA-1193 | HT - HALO TRUST | H/5189 | 59400 | 67.5333 | 35.6045 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {931174A8-8EA9-4C56-8BD3-FD6A4EC816BB} |  | High Requested | Resettlment/Local Request | Low | 16 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Chaharmaghzsay(Saray) (1) | {A3D3E969-1921-40FD-8D3D-C714F7EDCAD9} | c0a8-00f6-1349d0a8342-9bb3545d-17-828 | MF-16480 | MCPA - Mine Clearance Planning Agency | AF/1505/14636/MF8255 | 6440 | 67.8507 | 35.4972 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {A3D3E969-1921-40FD-8D3D-C714F7EDCAD9} |  | High with Victim | High with Victims | Low | 21 | CHA | 4 |  |  | 2011-10-20 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Chaharmaghzsay(Saray) (1) | {A3D3E969-1921-40FD-8D3D-C714F7EDCAD9} | c0a8-00f6-1349d0ed67d-8572e972-33-984 | MF-16478 | MCPA - Mine Clearance Planning Agency | AF/1505/14636/MF8254 | 6056 | 67.8426 | 35.4984 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {A3D3E969-1921-40FD-8D3D-C714F7EDCAD9} |  | High with Victim | High with Victims | Low | 106 | CHA | 3 |  |  | 2011-10-20 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Chaharmaghzsay(Saray) (2) | {1460556D-2A0C-4778-9E93-E756AC52B5C8} | c0a8-0057-12c3b884e0e-95882e29-1f4f9- | MF-NA-1127 | MCPA - Mine Clearance Planning Agency | AF/1505/14637/MF5019 | 35809 | 67.8147 | 35.504 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {1460556D-2A0C-4778-9E93-E756AC52B5C8} |  | High Requested | Resettlment/Local Request | Low | 11 | CHA | 4 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Chaharmaghzsay(Saray) (2) | {1460556D-2A0C-4778-9E93-E756AC52B5C8} | c0a8-0057-12c3ba2667a-ca04f75d-30645- | MF-NA-1128 | HT - HALO TRUST | H/2875 | 41600 | 67.8522 | 35.5035 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {1460556D-2A0C-4778-9E93-E756AC52B5C8} |  | High Requested | Resettlment/Local Request | Low | 14 | CHA | 4 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Chaharmaghzsay(Saray) (2) | {1460556D-2A0C-4778-9E93-E756AC52B5C8} | c0a8-0057-12c3ba2688c-1870c833-3065a- | MF-NA-1129 | HT - HALO TRUST | H/5031 | 45850 | 67.8518 | 35.5029 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {1460556D-2A0C-4778-9E93-E756AC52B5C8} |  | High Requested | Resettlment/Local Request | Low | 14 | CHA | 4 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3b899b9e-7f337073-2031a- | MF-NA-1111 | HT - HALO TRUST | H/4942 | 45680 | 67.9788 | 35.6078 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 11 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3b899d72-5a02a8e1-20332- | MF-NA-1118 | HT - HALO TRUST | H/4947 | 45400 | 67.9645 | 35.6077 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 15 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3b899f36-83508ca4-2034b- | MF-NA-1114 | HT - HALO TRUST | H/4944 | 29840 | 67.9867 | 35.6086 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 48 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3b89a139-af663c66-20363- | MF-NA-1113 | HT - HALO TRUST | H/4943 | 24160 | 67.9788 | 35.6078 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 49 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3b89a32c-e19eaee6-2037d- | MF-NA-1116 | MCPA - Mine Clearance Planning Agency | AF/1505/14687/MF4945 | 44277 | 67.9701 | 35.6046 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 15 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3b89a4f0-45836520-20396- | MF-NA-1110 | HT - HALO TRUST | H/2886 | 30080 | 67.9788 | 35.6078 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 16 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3b89a6e3-30f15326-203ae- | MF-NA-1117 | MCPA - Mine Clearance Planning Agency | AF/1505/14687/MF4946 | 40103 | 67.9674 | 35.6089 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 16 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3b89a898-b4e8d21f-203c6- | MF-NA-1119 | HT - HALO TRUST | H/4948 | 44240 | 67.9645 | 35.6076 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 4 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3b89aa8b-51c3d1ab-203dd- | MF-NA-1121 | MCPA - Mine Clearance Planning Agency | AF/1505/14687/MF4949 | 45000 | 67.9623 | 35.6083 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 4 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3b89ac5f-5e1dd8ff-203f6- | MF-NA-1122 | MCPA - Mine Clearance Planning Agency | AF/1505/14687/MF4950 | 38745 | 67.9597 | 35.6073 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 4 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3bab7aec-9f852901-35d03- | MF-NA-1120 | HT - HALO TRUST | H/4938 | 63320 | 68.031 | 35.5865 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 5 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3bab7d4d-aee0228-35d19-f | MF-NA-1126 | HT - HALO TRUST | H/4941 | 7000 | 68.0221 | 35.6019 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 5 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3bab7f7e-6d2cae25-35d2e- | MF-NA-1123 | HT - HALO TRUST | H/4939 | 26410 | 68.0302 | 35.5874 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 5 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3bab8181-a0d6db90-35d44- | MF-NA-1115 | HT - HALO TRUST | H/4937 | 40291 | 68.0299 | 35.5851 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 5 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3bab83d2-aa20d6ff-35d58- | MF-NA-1112 | HT - HALO TRUST | H/4936 | 52500 | 68.0295 | 35.5845 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 8 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-0057-12c3bab85e4-aa2d464d-35d6c- | MF-NA-1125 | HT - HALO TRUST | H/4940 | 18800 | 68.0063 | 35.5968 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 27 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Changez | {11A7858E-0945-4448-BCC7-29C0574635C1} | c0a8-008e-132c92f8b34-e57583cd-2ba8-d | MF-15380 | MCPA - Mine Clearance Planning Agency | AF/1505/14687/MF7312 | 35027 | 67.9586 | 35.6067 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  | No |  |  | 1394 | DDG | {11A7858E-0945-4448-BCC7-29C0574635C1} |  | High with Victim | High with Victims | Low | 8 | CHA | 5 |  |  | 2010-10-08 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Khame Bayaz | {FA9AA9C2-E1A9-4F97-BFC6-6BA3872DF9CE} | c0a8-0009-14240eda48c-a04ce94-347f-c6 | Hz-ID-18229 | MCPA - Mine Clearance Planning Agency | AF/1505/14640/BF0010 | 4 | 68.0099 | 35.5074 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {FA9AA9C2-E1A9-4F97-BFC6-6BA3872DF9CE} |  | High | Critical Infrastracture | Low | 0 | CHA | 3 |  |  | 2013-09-12 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Khame Bayaz | {FA9AA9C2-E1A9-4F97-BFC6-6BA3872DF9CE} | c0a8-00f6-1349d24ee76-7339af57-137-87 | MF-16475 | HT - HALO TRUST | H/8251 | 14640 | 68.0313 | 35.5074 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {FA9AA9C2-E1A9-4F97-BFC6-6BA3872DF9CE} |  | Low | Agriculture Blocked | Low | 29 | CHA | 5 |  |  | 2011-10-16 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Madrak | {7793CB12-A209-46B9-B59A-A390734B424B} | c0a8-0009-14241044b66-11f07009-386d-d | Hz-ID-18227 | MCPA - Mine Clearance Planning Agency | AF/1505/14639/BF0007 | 4 | 67.9043 | 35.5114 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {7793CB12-A209-46B9-B59A-A390734B424B} |  | High | Critical Infrastracture | Low | 490 | CHA | 3 |  |  | 2013-09-01 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Madrak | {7793CB12-A209-46B9-B59A-A390734B424B} | c0a8-0057-12c3b82c167-f534f1a4-1b637- | MF-NA-1142 | MCPA - Mine Clearance Planning Agency | AF/1505/14639/MF5018 | 24450 | 67.8807 | 35.5168 | Open | AP Only | AP Only | MineField |  | MBT Project-096 | Samangan Demining Project-14 |  |  |  |  | 1394 |  | {7793CB12-A209-46B9-B59A-A390734B424B} |  | High Requested | Resettlment/Local Request | Low | 4 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0009-14241004840-a848f747-3842-d | Hz-ID-18230 | MCPA - Mine Clearance Planning Agency | AF/1505/14624/BF0009 | 4 | 67.6401 | 35.511 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | Medium | Agriculture Blocked | Low | 1 | CHA | 3 |  |  | 2013-09-10 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c4ef8-3d669d99-2ca50- | MF-NA-1095 | HT - HALO TRUST | H/5167 | 56000 | 67.6285 | 35.5192 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c50eb-84d40e34-2ca68- | MF-NA-1102 | HT - HALO TRUST | H/5174 | 56000 | 67.6325 | 35.5247 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c52cf-8f3ce8c2-2ca81- | MF-NA-1103 | HT - HALO TRUST | H/5175 | 54400 | 67.6305 | 35.5261 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c5493-dacf3e3b-2ca99- | MF-NA-1105 | HT - HALO TRUST | H/5177 | 59200 | 67.6327 | 35.5272 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c5667-aa1de9a9-2cab1- | MF-NA-1100 | HT - HALO TRUST | H/5172 | 51520 | 67.6299 | 35.5238 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c585a-c4aada34-2cac9- | MF-NA-1108 | HT - HALO TRUST | H/5180 | 64000 | 67.6348 | 35.5282 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c5a3e-1bb46d27-2cae1- | MF-NA-1104 | HT - HALO TRUST | H/5176 | 68800 | 67.6353 | 35.5255 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c5c12-2468beb-2caf9-b | MF-NA-1107 | HT - HALO TRUST | H/5179 | 59200 | 67.6361 | 35.5273 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c5de6-2e45dfb1-2cb11- | MF-NA-1096 | HT - HALO TRUST | H/5168 | 60800 | 67.6286 | 35.5203 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c5fc9-7469a8f8-2cb29- | MF-NA-1093 | HT - HALO TRUST | H/2870 | 54000 | 67.6283 | 35.518 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c619d-abc709d8-2cb41- | MF-NA-1098 | HT - HALO TRUST | H/5170 | 46400 | 67.629 | 35.5228 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c6362-e9d4e139-2cb59- | MF-NA-1094 | HT - HALO TRUST | H/5166 | 57600 | 67.6283 | 35.518 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c6555-edb1902c-2cb71- | MF-NA-1099 | HT - HALO TRUST | H/5171 | 49600 | 67.6291 | 35.5234 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c6729-4d1ad32d-2cb89- | MF-NA-1101 | HT - HALO TRUST | H/5173 | 56480 | 67.628 | 35.5249 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c68ed-84b83667-2cba1- | MF-NA-1097 | HT - HALO TRUST | H/5169 | 53320 | 67.6288 | 35.5215 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Maymana | {F6091C62-9202-4A57-82BF-D018271D2A32} | c0a8-0057-12c3b9c6ad1-4ab60c42-2cbb9- | MF-NA-1106 | HT - HALO TRUST | H/5178 | 60800 | 67.6382 | 35.5259 | Open | AP Only | AP Only | MineField |  | MBT Project-131 | Samangan Demining Project-12 |  |  |  |  | 1396 |  | {F6091C62-9202-4A57-82BF-D018271D2A32} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Mohu | {D4A5EAC0-AED2-4852-BDDA-DA495ACDAD05} | c0a8-0057-12c3b6f1d4e-eb5b1ddb-d147-3 | MF-NA-1166 | HT - HALO TRUST | H/2879 | 22920 | 67.8964 | 35.717 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {D4A5EAC0-AED2-4852-BDDA-DA495ACDAD05} |  | High Requested | Resettlment/Local Request | Low | 2 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Mohu | {D4A5EAC0-AED2-4852-BDDA-DA495ACDAD05} | c0a8-0057-12c3b7060b1-ac6f2c8b-e0c4-e | MF-NA-1195 | HT - HALO TRUST | H/5197 | 61840 | 67.8743 | 35.6849 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {D4A5EAC0-AED2-4852-BDDA-DA495ACDAD05} |  | High Requested | Resettlment/Local Request | Low | 6 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Mohu | {D4A5EAC0-AED2-4852-BDDA-DA495ACDAD05} | c0a8-0057-12c3b737754-203ac174-10603- | MF-NA-1196 | HT - HALO TRUST | H/5198 | 43800 | 67.8828 | 35.6964 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {D4A5EAC0-AED2-4852-BDDA-DA495ACDAD05} |  | High Requested | Resettlment/Local Request | Low | 4 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Mohu | {D4A5EAC0-AED2-4852-BDDA-DA495ACDAD05} | c0a8-0057-12c3b74c2f1-49605ae0-11590- | MF-NA-1167 | HT - HALO TRUST | H/2880 | 15240 | 67.8749 | 35.6936 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {D4A5EAC0-AED2-4852-BDDA-DA495ACDAD05} |  | High Requested | Resettlment/Local Request | Low | 11 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Ortaleq | {37D664CA-6CAE-44A4-B0C2-460F2BE03099} | c0a8-0057-12c3b811f34-51a88eb9-1a38c- | MF-NA-1080 | HT - HALO TRUST | H/2882 | 49600 | 67.6014 | 35.6453 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {37D664CA-6CAE-44A4-B0C2-460F2BE03099} |  | Low | Agriculture Blocked | Low | 19 | CHA | 5 |  |  | 2008-12-01 | No | Open
North | Samangan | Ruyi Du Ab | Ortaleq | {37D664CA-6CAE-44A4-B0C2-460F2BE03099} | c0a8-0057-12c3b812117-b4e30446-1a3aa- | MF-NA-1081 | HT - HALO TRUST | H/5184 | 44300 | 67.603 | 35.6483 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {37D664CA-6CAE-44A4-B0C2-460F2BE03099} |  | High Requested | Resettlment/Local Request | Low | 11 | CHA | 6 |  |  | 2008-12-01 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-0057-12c3b7c2cd7-8796a18f-16bca- | MF-NA-1175 | HT - HALO TRUST | H/5004 | 26000 | 67.8886 | 35.5554 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | High Requested | Resettlment/Local Request | Low | 34 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-0057-12c3b7c2ef9-be3113fd-16beb- | MF-NA-1176 | HT - HALO TRUST | H/5005 | 29000 | 67.8796 | 35.5585 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | High Requested | Resettlment/Local Request | Low | 49 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-0057-12c3b7c311b-4be503b9-16c06- | MF-NA-1168 | HT - HALO TRUST | H/2885 | 35200 | 67.8769 | 35.5567 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | High Requested | Resettlment/Local Request | Low | 46 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-0057-12c3b7c330e-dc70a722-16c23- | MF-NA-1173 | HT - HALO TRUST | H/5003 | 47200 | 67.8813 | 35.5575 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | High Requested | Resettlment/Local Request | Low | 36 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-0057-12c3b7c355f-53b0dd58-16c3e- | MF-NA-1172 | HT - HALO TRUST | H/5002 | 31285 | 67.8807 | 35.56 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | High Requested | Resettlment/Local Request | Low | 29 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-0057-12c3b7c3791-74103c26-16c5c- | MF-NA-1170 | HT - HALO TRUST | H/5001 | 20280 | 67.8794 | 35.5592 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | High Requested | Resettlment/Local Request | Low | 13 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-0057-12c3b7c39f1-4c799c89-16c78- | MF-NA-1178 | HT - HALO TRUST | H/5006 | 43000 | 67.8667 | 35.5518 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | High Requested | Resettlment/Local Request | Low | 10 | CHA | 4 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-0057-12c3b7d6689-c59ad630-17a22- | MF-NA-1164 | HT - HALO TRUST | H/5007 | 6840 | 67.8741 | 35.5372 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | High Requested | Resettlment/Local Request | Low | 10 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-0057-12c3b81df74-df310c9-1ac3d-1 | MF-NA-1162 | HT - HALO TRUST | H/2884 | 16380 | 67.8687 | 35.5304 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | High Requested | Resettlment/Local Request | Low | 5 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-0057-12c3ba9b65b-b48cad85-34cb6- | MF-NA-1124 | HT - HALO TRUST | H/2869 | 28000 | 67.7981 | 35.5159 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | High Requested | Resettlment/Local Request | Low | 26 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-008e-132c92a1e44-f7cd14e-2af0-40 | MF-15374 | HT - HALO TRUST | H/7307 | 30400 | 68.033 | 35.5927 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | Low | Agriculture Blocked | Low | 5 | CHA | 5 |  |  | 2010-10-03 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-008e-132c92bea51-890098f8-2b47-f | MF-15377 | HT - HALO TRUST | H/7308 | 61200 | 68.033 | 35.5927 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | Low | Agriculture Blocked | Low | 6 | CHA | 5 |  |  | 2010-10-04 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-008e-132d38a530e-68886108-9d6b-3 | MF-15379 | HT - HALO TRUST | H/7309 | 43200 | 68.033 | 35.5927 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | Low | Agriculture Blocked | Low | 7 | CHA | 5 |  |  | 2010-10-05 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Paye Tangi | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} | c0a8-008e-13426a6564a-1d901b66-43-8e8 | MF-16389 | MCPA - Mine Clearance Planning Agency | AF/1505/14687/MF0005 | 18420 | 67.8664 | 35.5425 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {3663F874-B1E0-46AA-BD53-2A9E4DB233BC} |  | Medium | Critical Infrastracture | Low | 149 | CHA | 3 |  |  | 2011-09-29 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Qashqa | {34426E0B-3084-46D8-92C1-5A1826B69FAB} | c0a8-0009-14240eb93fe-d96939d9-33ef-e | Hz-ID-18226 | MCPA - Mine Clearance Planning Agency | AF/1505/14654/MF0008 | 17553 | 67.6232 | 35.6661 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {34426E0B-3084-46D8-92C1-5A1826B69FAB} |  | High with Victim | High with Victims | Low | 1 | CHA | 5 |  |  | 2013-09-03 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Qashqa | {34426E0B-3084-46D8-92C1-5A1826B69FAB} | c0a8-0009-14240f2b5f1-6334ab64-3631-a | Hz-ID-18228 | MCPA - Mine Clearance Planning Agency | AF/1505/14654/BF0011 | 25 | 67.6685 | 35.6476 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {34426E0B-3084-46D8-92C1-5A1826B69FAB} |  | High with Victim | High with Victims | Low | 0 | CHA | 3 |  |  | 2013-09-17 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Qashqa | {34426E0B-3084-46D8-92C1-5A1826B69FAB} | c0a8-0057-12c3b69c37a-2f413dd4-904c-8 | MF-NA-1188 | HT - HALO TRUST | H/5046 | 64480 | 67.6226 | 35.7125 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {34426E0B-3084-46D8-92C1-5A1826B69FAB} |  | High with Victim | High with Victims | Low | 11 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Qashqa | {34426E0B-3084-46D8-92C1-5A1826B69FAB} | c0a8-0057-12c3b70c2cc-6e06dcd8-e56b-7 | MF-NA-1187 | HT - HALO TRUST | H/5048 | 56000 | 67.6215 | 35.7109 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {34426E0B-3084-46D8-92C1-5A1826B69FAB} |  | High with Victim | High with Victims | Low | 16 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Qashqa | {34426E0B-3084-46D8-92C1-5A1826B69FAB} | c0a8-0057-12c3b74e1c6-27564fb-116f8-8 | MF-NA-1186 | HT - HALO TRUST | H/5047 | 57900 | 67.6244 | 35.7093 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {34426E0B-3084-46D8-92C1-5A1826B69FAB} |  | High with Victim | High with Victims | Low | 6 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Qashqa | {34426E0B-3084-46D8-92C1-5A1826B69FAB} | c0a8-00f6-1349d411df5-ce12a5a1-2d0-b9 | MF-16468 | HT - HALO TRUST | H/8215 | 68700 | 67.7029 | 35.6325 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {34426E0B-3084-46D8-92C1-5A1826B69FAB} |  | High with Victim | High with Victims | Low | 0 | CHA | 5 |  |  | 2011-10-08 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Ru'i(Habash) | {32C1DD00-BD7E-48F6-A17C-924D1F8A974A} | c0a8-0057-12c3b7549da-9f5a9830-11bc5- | MF-NA-1169 | HT - HALO TRUST | H/2881 | 13200 | 67.8668 | 35.778 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {32C1DD00-BD7E-48F6-A17C-924D1F8A974A} |  | High Requested | Resettlment/Local Request | Low | 521 | CHA | 4 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Ruyi Du Ab | {C8E6D1E0-4106-42F5-98FC-C3F0A4EC5437} | c0a8-008e-1328f8b98e2-3380c0a2-166f-7 | MF-15603 | HT - HALO TRUST | H/7317 | 73350 | 67.8425 | 35.5615 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {C8E6D1E0-4106-42F5-98FC-C3F0A4EC5437} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-12-06 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Ruyi Du Ab | {C8E6D1E0-4106-42F5-98FC-C3F0A4EC5437} | c0a8-008e-1328f9ae519-636daee3-1c9b-2 | MF-15604 | HT - HALO TRUST | H/7318 | 67230 | 67.8425 | 35.5615 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {C8E6D1E0-4106-42F5-98FC-C3F0A4EC5437} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-12-07 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Ruyi Du Ab | {C8E6D1E0-4106-42F5-98FC-C3F0A4EC5437} | c0a8-008e-1328f9b0c86-73bdb65b-1caf-e | MF-15601 | HT - HALO TRUST | H/7316 | 76500 | 67.8425 | 35.5615 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {C8E6D1E0-4106-42F5-98FC-C3F0A4EC5437} |  | Low | Agriculture Blocked | Low | 15 | CHA | 5 |  |  | 2010-12-05 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Ruyi Du Ab | {C8E6D1E0-4106-42F5-98FC-C3F0A4EC5437} | c0a8-008e-1328f9b347f-54daf3f8-1cc7-8 | MF-15600 | HT - HALO TRUST | H/7315 | 57150 | 67.8363 | 35.5583 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {C8E6D1E0-4106-42F5-98FC-C3F0A4EC5437} |  | Low | Water Blocked | Low | 19 | CHA | 5 |  |  | 2010-12-13 16:30 | No | Open
North | Samangan | Ruyi Du Ab | Sartangi (1) | {1B7CA8E0-2565-4C18-93CE-3769E2E932AF} | c0a8-0057-12c3b7da195-c43da8e4-17cab- | MF-NA-1145 | MCPA - Mine Clearance Planning Agency | AF/1505/14646/MF5010 | 14173 | 67.9174 | 35.5363 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {1B7CA8E0-2565-4C18-93CE-3769E2E932AF} |  | High Requested | Resettlment/Local Request | Low | 13 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Sartangi (1) | {1B7CA8E0-2565-4C18-93CE-3769E2E932AF} | c0a8-0057-12c3b7da35a-da829a38-17cc0- | MF-NA-1146 | MCPA - Mine Clearance Planning Agency | AF/1505/14646/MF5009 | 15393 | 67.9216 | 35.5357 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {1B7CA8E0-2565-4C18-93CE-3769E2E932AF} |  | High Requested | Resettlment/Local Request | Low | 11 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Sartangi (1) | {1B7CA8E0-2565-4C18-93CE-3769E2E932AF} | c0a8-0057-12c3b7da721-4f43f350-17ce9- | MF-NA-1150 | MCPA - Mine Clearance Planning Agency | AF/1505/14646/MF2878 | 62664 | 67.9284 | 35.5307 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {1B7CA8E0-2565-4C18-93CE-3769E2E932AF} |  | High Requested | Resettlment/Local Request | Low | 10 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Sartangi (1) | {1B7CA8E0-2565-4C18-93CE-3769E2E932AF} | c0a8-0057-12c3b7da8e5-d822d4cc-17d01- | MF-NA-1144 | MCPA - Mine Clearance Planning Agency | AF/1505/14646/MF5011 | 500 | 67.9228 | 35.5247 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {1B7CA8E0-2565-4C18-93CE-3769E2E932AF} |  | High Requested | Resettlment/Local Request | Low | 13 | CHA | 6 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Sartangi (1) | {1B7CA8E0-2565-4C18-93CE-3769E2E932AF} | c0a8-0057-12c3b7daad8-5fad48be-17d13- | MF-NA-1143 | MCPA - Mine Clearance Planning Agency | AF/1505/14646/MF5012 | 37617 | 67.912 | 35.5346 | Open | AP Only | AP Only | MineField |  | MBT Project-247 | Samangan Demining Project-13 |  |  |  |  | 1396 |  | {1B7CA8E0-2565-4C18-93CE-3769E2E932AF} |  | High Requested | Resettlment/Local Request | Low | 27 | CHA | 5 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Surqal'a | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} | c0a8-0057-12c3b9290cf-3a1311f9-26408- | MF-NA-1130 | MCPA - Mine Clearance Planning Agency | AF/1505/14647/MF2890 | 51488 | 67.9639 | 35.5221 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} | , | High with Victim | High with Victims | Low | 14 | CHA | 2 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Surqal'a | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} | c0a8-0057-12c3b9292b3-235996a-26420-a | MF-NA-1131 | MCPA - Mine Clearance Planning Agency | AF/1505/14647/MF5028 | 10457 | 67.9585 | 35.5148 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Surqal'a | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} | c0a8-0057-12c3b929496-8e0e9b45-26435- | MF-NA-1133 | MCPA - Mine Clearance Planning Agency | AF/1505/14647/MF5030 | 56912 | 67.9639 | 35.5221 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} | , | High with Victim | High with Victims | Low | 14 | CHA | 2 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Surqal'a | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} | c0a8-0057-12c3baf08ef-5e4a90f3-37f2e- | MF-NA-1135 | MCPA - Mine Clearance Planning Agency | AF/1505/14647/MF5023 | 48860 | 67.9599 | 35.5316 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} |  | High with Victim | High with Victims | Low | 3 | CHA | 2 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Surqal'a | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} | c0a8-0057-12c3baf0d24-b3a71bb7-37f61- | MF-NA-1137 | MCPA - Mine Clearance Planning Agency | AF/1505/14647/MF5025 | 40789 | 67.9599 | 35.5316 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} |  | High with Victim | High with Victims | Low | 41 | CHA | 2 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Surqal'a | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} | c0a8-0057-12c3baf0f46-905c1473-37f79- | MF-NA-1134 | MCPA - Mine Clearance Planning Agency | AF/1505/14647/MF5022 | 1118 | 67.9584 | 35.5295 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} |  | High with Victim | High with Victims | Low | 14 | CHA | 2 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Surqal'a | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} | c0a8-0057-12c3baf16a5-a1921cc7-37f92- | MF-NA-1139 | MCPA - Mine Clearance Planning Agency | AF/1505/14647/MF5026 | 45933 | 67.9599 | 35.5316 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} |  | High with Victim | High with Victims | Low | 41 | CHA | 2 |  |  | 2009-01-01 | No | Open
North | Samangan | Ruyi Du Ab | Surqal'a | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} | c0a8-0057-12c3baf1889-88c731ce-37faa- | MF-NA-1136 | MCPA - Mine Clearance Planning Agency | AF/1505/14647/MF5024 | 52077 | 67.9599 | 35.5316 | Open | AP Only | AP Only | MineField |  | MBT Project-041 | Samangan Demining Project-10 |  |  |  |  | 1394 |  | {8CADE1B9-6822-4545-B5BC-D32EFDF30545} |  | High with Victim | High with Victims | Low | 12 | CHA | 2 |  |  | 2009-01-01 | No | Open
North | Sari Pul | Balkhab | Jare Akhzara | {4AA8B81E-220C-44F8-8029-0D0B8F5E3E80} | c0a8-0009-143cdde9c23-3f500198-2f4c-8 | Hz-ID-18408 | MCPA - Mine Clearance Planning Agency | AF/3104/15624/MF0001 | 63943 | 66.5452 | 35.5071 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {4AA8B81E-220C-44F8-8029-0D0B8F5E3E80} |  | Low | Agriculture Blocked | Low | 121 | CHA | 4 |  |  | 2013-12-03 16:30 | No | Open
North | Sari Pul | Gosfandi | Abdara | {585F2133-D22A-47A1-A21E-853B0DA7AA9F} | c0a8-0009-13b40693828-7430217f-4c98-8 | Hz-ID-17406 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3107/15015/MF8299 | 39600 | 66.5256 | 35.7919 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {585F2133-D22A-47A1-A21E-853B0DA7AA9F} |  | High Requested | Resettlment/Local Request | Low | 8 | CHA | 1 | Yes |  | 2012-08-12 16:30 | No | Open
North | Sari Pul | Gosfandi | Abdara | {585F2133-D22A-47A1-A21E-853B0DA7AA9F} | c0a8-0009-13b40ca0dec-7bc37510-4d95-1 | Hz-ID-17404 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3107/15015/MF8297 | 60800 | 66.5284 | 35.7851 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {585F2133-D22A-47A1-A21E-853B0DA7AA9F} |  | High Requested | Resettlment/Local Request | Low | 15 | CHA | 1 | Yes |  | 2012-08-10 16:30 | No | Open
North | Sari Pul | Gosfandi | Abkhor | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} | c0a8-0009-13adefc1f0c-7a5d667e-143c-2 | Hz-ID-17345 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15553/BF0033 | 6927 | 66.57 | 35.8625 | Open | UXO Only | UXO Only | BF |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} |  | High with Victim | High with Victims | Low | 245 | CHA | 1 |  |  | 2012-09-18 16:30 | No | Open
North | Sari Pul | Gosfandi | Abkhor | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} | c0a8-0009-13bea462823-6f0a032f-10f-67 | Hz-ID-17480 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15553/MF0049 | 7110 | 66.5629 | 35.8698 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} |  | High with Victim | High with Victims | Low | 22 | CHA | 1 |  |  | 2012-11-07 16:30 | No | Open
North | Sari Pul | Gosfandi | Abkhor | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} | c0a8-0009-13c1e20bc66-ada6dfd5-7e99-3 | Hz-ID-17496 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15553/MF0053 | 1806 | 66.5607 | 35.8719 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} |  | High with Victim | High with Victims | Low | 22 | CHA | 1 |  |  | 2012-11-17 16:30 | No | Open
North | Sari Pul | Gosfandi | Abkhor | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} | c0a8-0009-13c1e32bde5-bda80608-8179-5 | Hz-ID-17498 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15553/MF0054 | 16128 | 66.5767 | 35.8513 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} |  | High with Victim | High with Victims | Low | 2 | CHA | 1 |  |  | 2012-11-12 16:30 | No | Open
North | Sari Pul | Gosfandi | Abkhor | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} | c0a8-0009-13c1e3b7c21-e56a6661-82ce-4 | Hz-ID-17504 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15553/MF0056 | 7888 | 66.5831 | 35.8295 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} |  | High with Victim | High with Victims | Low | 0 | CHA | 1 |  |  | 2012-11-11 16:30 | No | Open
North | Sari Pul | Gosfandi | Abkhor | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} | c0a8-0009-13c1e3bdf46-951b451-82eb-73 | Hz-ID-17501 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15553/MF0055 | 680 | 66.578 | 35.8432 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} |  | High with Victim | High with Victims | Low | 2 | CHA | 1 |  |  | 2012-11-12 16:30 | No | Open
North | Sari Pul | Gosfandi | Abkhor | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} | c0a8-0009-13c1e3c8d31-ca65c4ab-8309-b | Hz-ID-17491 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15553/MF0052 | 16138 | 66.5652 | 35.8721 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} |  | High with Victim | High with Victims | Low | 34 | CHA | 1 |  |  | 2012-11-17 16:30 | No | Open
North | Sari Pul | Gosfandi | Abkhor | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} | c0a8-0009-13c23645db4-251f0557-fe5-4e | Hz-ID-17490 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15553/MF0050 | 61590 | 66.5644 | 35.8662 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} |  | High with Victim | High with Victims | Low | 33 | CHA | 1 |  |  | 2012-11-14 16:30 | No | Open
North | Sari Pul | Gosfandi | Abkhor | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} | c0a8-0009-13e2c18189b-51b67cc8-d9c-e9 | Hz-ID-17481 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15583/MF0051 | 34376 | 66.5647 | 35.8644 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {9DBEF4CC-630F-40BD-943E-7599A947B2CD} |  | High with Victim | High with Victims | Low | 11 | CHA | 2 |  |  | 2012-11-14 16:30 | No | Open
North | Sari Pul | Gosfandi | Mirzabay | {9414F0FD-AC7A-4923-BD98-4AAB64C9E25A} | c0a8-0009-13c1e3cf2d5-e7ce1439-831f-c | Hz-ID-17505 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15552/MF0057 | 3356 | 66.6066 | 35.8087 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {9414F0FD-AC7A-4923-BD98-4AAB64C9E25A} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2012-11-06 16:30 | No | Open
North | Sari Pul | Gosfandi | Pala | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} | c0a8-0009-13bdbb8e76b-728e5c2e-14a3-d | Hz-ID-17479 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15531/MF0039 | 49157 | 66.4599 | 35.8166 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2012-11-04 16:30 | No | Open
North | Sari Pul | Gosfandi | Pala | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} | c0a8-0009-13bea4d5226-147dc7f-12c-bc3 | Hz-ID-17482 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15531/MF0040 | 37500 | 66.4564 | 35.8107 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2012-11-05 16:30 | No | Open
North | Sari Pul | Gosfandi | Pala | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} | c0a8-0009-13bea5422f4-1c5189d-25c-7c6 | Hz-ID-17483 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15531/MF0041 | 34315 | 66.4534 | 35.8043 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2012-11-06 16:30 | No | Open
North | Sari Pul | Gosfandi | Pala | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} | c0a8-0009-13bea58e938-31a34559-2a9-1d | Hz-ID-17484 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15531/MF0043 | 67978 | 66.4501 | 35.8006 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} |  | Low | Agriculture Blocked | Low | 8 | CHA | 5 |  |  | 2012-11-06 16:30 | No | Open
North | Sari Pul | Gosfandi | Pala | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} | c0a8-0009-13bea5ab329-b2bdd6b3-2d9-62 | Hz-ID-17485 | ATC - Afghan Technical Consultants | AF/3102/15531/MF0044 | 50744 | 66.8184 | 35.4901 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2012-11-10 16:30 | No | Open
North | Sari Pul | Gosfandi | Pala | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} | c0a8-0009-13bea7162eb-6ae834b0-3f8-66 | Hz-ID-17486 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15531/MF0045 | 77916 | 66.4894 | 35.8122 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} |  | Low | Agriculture Blocked | Low | 5 | CHA | 5 |  |  | 2012-11-12 16:30 | No | Open
North | Sari Pul | Gosfandi | Pala | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} | c0a8-0009-13bea7718cc-edc71157-414-c5 | Hz-ID-17487 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15531/MF0046 | 31170 | 66.4924 | 35.8247 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2012-11-11 16:30 | No | Open
North | Sari Pul | Gosfandi | Pala | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} | c0a8-0009-13bf9f23073-e3cc4df1-67a7-d | Hz-ID-17488 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15531/MF0047 | 58450 | 66.4924 | 35.8247 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2012-11-11 16:30 | No | Open
North | Sari Pul | Gosfandi | Pala | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} | c0a8-0009-13bfa18ecce-3a5b5d25-6803-3 | Hz-ID-17489 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15531/MF0048 | 73723 | 66.8347 | 35.4747 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2012-11-13 16:30 | No | Open
North | Sari Pul | Gosfandi | Pala | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} | c0a8-0009-13cc25c2e6d-4a886b57-112c-9 | Hz-ID-17627 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15531/MF0038 | 49996 | 66.4599 | 35.8166 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} |  | Low | Critical Infrastracture | Low | 4 | CHA | 5 | No |  | 2012-11-04 16:30 | No | Open
North | Sari Pul | Gosfandi | Pala | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} | c0a8-0009-13cc2cbade4-b7ce8e52-641-79 | Hz-ID-17588 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15531/MF0042 | 31372 | 66.4506 | 35.8024 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {07C6ABE2-A459-43BE-95F3-0140F9D1B1E1} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2012-11-06 16:30 | No | Open
North | Sari Pul | Gosfandi | Qeshlaqe Khwaja Nalan | {36BA506C-16DF-4733-9847-6A22203B72EE} | c0a8-0009-13b45907b72-c5bc36b-5348-8a | Hz-ID-17401 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15536/MF8292 | 39000 | 66.5256 | 35.7919 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {36BA506C-16DF-4733-9847-6A22203B72EE} |  | High with Victim | High with Victims | Low | 7 | CHA | 1 | Yes |  | 2012-08-12 16:30 | No | Open
North | Sari Pul | Gosfandi | Qeshlaqe Khwaja Nalan | {36BA506C-16DF-4733-9847-6A22203B72EE} | c0a8-0009-13b4594ac5f-80a63f33-538e-c | Hz-ID-17402 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15536/MF8294 | 41400 | 66.5256 | 35.7919 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {36BA506C-16DF-4733-9847-6A22203B72EE} |  | High with Victim | High with Victims | Low | 7 | CHA | 1 | Yes |  | 2012-08-11 16:30 | No | Open
North | Sari Pul | Gosfandi | Qeshlaqe Khwaja Nalan | {36BA506C-16DF-4733-9847-6A22203B72EE} | c0a8-0009-13b4597c0d7-f280edd3-541f-d | Hz-ID-17403 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15536/MF8296 | 25600 | 66.5284 | 35.7851 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {36BA506C-16DF-4733-9847-6A22203B72EE} |  | High with Victim | High with Victims | Low | 7 | CHA | 1 | Yes |  | 2012-08-13 16:30 | No | Open
North | Sari Pul | Gosfandi | Qeshlaqe Khwaja Nalan | {36BA506C-16DF-4733-9847-6A22203B72EE} | c0a8-0009-13b4598d63a-bae693ce-543c-e | Hz-ID-17405 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15536/MF8298 | 45000 | 66.5256 | 35.7919 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {36BA506C-16DF-4733-9847-6A22203B72EE} |  | High with Victim | High with Victims | Low | 2 | CHA | 1 | Yes |  | 2012-08-11 16:30 | No | Open
North | Sari Pul | Gosfandi | Qeshlaqe Khwaja Nalan | {36BA506C-16DF-4733-9847-6A22203B72EE} | c0a8-0009-13b45c9b7af-f9d34d8c-5709-4 | Hz-ID-17417 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15536/MF8300 | 43600 | 66.5256 | 35.7919 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {36BA506C-16DF-4733-9847-6A22203B72EE} |  | High with Victim | High with Victims | Low | 15 | CHA | 1 |  |  | 2012-08-13 16:30 | No | Open
North | Sari Pul | Gosfandi | Qeshlaqe Khwaja Nalan | {36BA506C-16DF-4733-9847-6A22203B72EE} | c0a8-0009-13b45f05728-78691a8f-5999-a | Hz-ID-17400 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15536/MF8230 | 45200 | 66.5256 | 35.7919 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {36BA506C-16DF-4733-9847-6A22203B72EE} |  | High with Victim | High with Victims | Low | 421 | CHA | 1 |  |  | 2012-08-20 16:30 | No | Open
North | Sari Pul | Gosfandi | Qeshlaqe Khwaja Nalan | {36BA506C-16DF-4733-9847-6A22203B72EE} | c0a8-0009-13c22e698a0-91cd58f0-699-9e | Hz-ID-17593 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15536/MF0060 | 142337 | 66.5224 | 35.8748 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {36BA506C-16DF-4733-9847-6A22203B72EE} |  | High with Victim | High with Victims | Low | 6 | CHA | 1 |  |  | 2012-11-12 16:30 | No | Open
North | Sari Pul | Gosfandi | Qeshlaqe Khwaja Nalan | {36BA506C-16DF-4733-9847-6A22203B72EE} | c0a8-0009-13c22ef8e0b-ec4da44d-70b-9c | Hz-ID-17594 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15536/MF0061 | 71184 | 66.5227 | 35.8049 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {36BA506C-16DF-4733-9847-6A22203B72EE} |  | High with Victim | High with Victims | Low | 2 | CHA | 1 |  |  | 2012-11-12 16:30 | No | Open
North | Sari Pul | Gosfandi | Qeshlaqe Khwaja Nalan | {36BA506C-16DF-4733-9847-6A22203B72EE} | c0a8-0009-13c80c3495d-bff257d1-cd7-cd | Hz-ID-17605 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15536/MF0059 | 135095 | 66.5224 | 35.8748 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {36BA506C-16DF-4733-9847-6A22203B72EE} |  | High with Victim | High with Victims | Low | 5 | CHA | 1 |  |  | 2012-11-12 16:30 | No | Open
North | Sari Pul | Gosfandi | Qeshlaqe Khwaja Nalan | {36BA506C-16DF-4733-9847-6A22203B72EE} | c0a8-0009-13c84a1c09d-6311d93-40c-9e8 | Hz-ID-17606 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15536/MF0064 | 142145 | 66.5227 | 35.8049 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {36BA506C-16DF-4733-9847-6A22203B72EE} |  | High with Victim | High with Victims | Low | 7 | CHA | 1 |  |  | 2012-11-12 16:30 | No | Open
North | Sari Pul | Gosfandi | Qeshlaqe Khwaja Nalan | {36BA506C-16DF-4733-9847-6A22203B72EE} | c0a8-0057-12c3b8c07c2-8ddf60cc-21eaf- | MF-NA-650 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/3102/15536/MF0015 | 70794 | 66.5234 | 35.8043 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {36BA506C-16DF-4733-9847-6A22203B72EE} | , | High with Victim | High with Victims | Low | 2 | CHA | 1 |  |  | 2006-09-01 | No | Open
North | Sari Pul | Sangcharak | Qalmaqi | {95059EFE-8812-48C2-A289-A7E832114710} | c0a8-0009-14385350456-ba3a048f-479f-f | Hz-ID-18391 | MCPA - Mine Clearance Planning Agency | AF/3102/15483/BF0002 | 100 | 66.3999 | 35.8714 | Open | UXO Only | UXO Only | BF |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {95059EFE-8812-48C2-A289-A7E832114710} |  | High | Critical Infrastracture | Moderate | 476 | CHA | 3 |  |  | 2013-11-02 16:30 | No | Open
North | Sari Pul | Sangcharak | Tebir | {A14EDBCD-20A7-4E5A-B45B-B2F9D923B567} | c0a8-0009-14385321cd7-8e67c51d-4745-6 | Hz-ID-18394 | MCPA - Mine Clearance Planning Agency | AF/3102/15495/MF0001 | 4562 | 66.3902 | 36.0055 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {A14EDBCD-20A7-4E5A-B45B-B2F9D923B567} |  | High with Victim | High with Victims | Moderate | 807 | CHA | 2 |  |  | 2013-11-01 16:30 | No | Open
North | Sari Pul | Sari Pul | Angut | {901AC8F3-7C5C-444A-8CC3-922D57E588B0} | c0a8-0009-145cab33c56-4af16431-16d2-e | Hz-ID-18658 | MCPA - Mine Clearance Planning Agency | AF/3101/15757/MF0008 | 688 | 66.0226 | 36.1862 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {901AC8F3-7C5C-444A-8CC3-922D57E588B0} |  | High | Critical Infrastracture | Moderate | 100 | CHA | 3 |  |  | 2014-03-29 16:30 | No | Open
North | Sari Pul | Sari Pul | Gul Tepa | {93A3B7E5-6035-4F68-A7EF-B43A1F55741F} | c0a8-0009-145caf82052-502c1944-1989-b | Hz-ID-18661 | MCPA - Mine Clearance Planning Agency | AF/3101/15737/MF0010 | 18122 | 65.9012 | 36.3345 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {93A3B7E5-6035-4F68-A7EF-B43A1F55741F} |  | Medium | Critical Infrastracture | Moderate | 212 | CHA | 3 |  |  | 2014-03-18 16:30 | No | Open
North | Sari Pul | Sari Pul | Sari Pul | {F2B7806E-F014-4761-AB5C-5FA78BF8EF19} | c0a8-0009-14491962c78-71805b57-a5e-71 | Hz-ID-18414 | MCPA - Mine Clearance Planning Agency | AF/3101/31795/BF0009 | 6384 | 65.9399 | 36.2095 | Open | UXO Only | UXO Only | BF |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {F2B7806E-F014-4761-AB5C-5FA78BF8EF19} |  | High with Victim | High with Victims | Moderate | 431 | CHA | 1 |  |  | 2014-01-23 16:30 | No | Open
North | Sari Pul | Sari Pul | Sari Pul | {F2B7806E-F014-4761-AB5C-5FA78BF8EF19} | c0a8-008e-13112f195fc-5ac94b31-19df-4 | MF-HQ-11430 | HT - HALO TRUST | H/4040 | 1700 | 66.1889 | 36.4608 | Open | AT Only | AT Only | MineField | Blank | MBT Project-088 | Sari Pul Demining Project-1 |  | No |  |  | 1394 | None | {F2B7806E-F014-4761-AB5C-5FA78BF8EF19} |  | High with Victim | High with Victims | Moderate | 14 | CHA | 2 |  |  | 2007-11-16 | No | Open
North | Sari Pul | Sayyad | Bazar Kami | {A768C45C-6AB3-428B-9F8F-0C9770100D31} | c0a8-0009-145cb098ff0-16d88363-1a89-5 | Hz-ID-18666 | MCPA - Mine Clearance Planning Agency | AF/3106/15715/MF0017 | 5340 | 65.7292 | 36.1398 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {A768C45C-6AB3-428B-9F8F-0C9770100D31} |  | Low | Agriculture Blocked | Substantial | 38 | CHA | 5 |  |  | 2014-03-25 16:30 | No | Open
North | Sari Pul | Sayyad | Bazar Kami | {A768C45C-6AB3-428B-9F8F-0C9770100D31} | c0a8-0009-145cbaf1334-a8d741bd-1b2e-d | Hz-ID-18668 | MCPA - Mine Clearance Planning Agency | AF/3106/15715/MF0019 | 15353 | 65.7308 | 36.1547 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {A768C45C-6AB3-428B-9F8F-0C9770100D31} |  | Low | Agriculture Blocked | Substantial | 51 | CHA | 5 |  |  | 2014-03-22 16:30 | No | Open
North | Sari Pul | Sayyad | Bazar Kami | {A768C45C-6AB3-428B-9F8F-0C9770100D31} | c0a8-0009-145cbbd28e0-1f84469f-1b57-2 | Hz-ID-18669 | MCPA - Mine Clearance Planning Agency | AF/3106/15715/MF0020 | 23878 | 65.7319 | 36.1656 | Open | AT Only | AT Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {A768C45C-6AB3-428B-9F8F-0C9770100D31} |  | Low | Agriculture Blocked | Substantial | 51 | CHA | 5 |  |  | 2014-03-27 16:30 | No | Open
North | Sari Pul | Sayyad | Bazar Kami | {A768C45C-6AB3-428B-9F8F-0C9770100D31} | c0a8-0009-145cbc02d90-e5e6dc23-1b82-d | Hz-ID-18670 | MCPA - Mine Clearance Planning Agency | AF/3106/15715/MF0021 | 6256 | 65.7533 | 36.1653 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {A768C45C-6AB3-428B-9F8F-0C9770100D31} |  | Low | Agriculture Blocked | Substantial | 36 | CHA | 5 |  |  | 2014-03-17 16:30 | No | Open
North | Sari Pul | Sayyad | Bazar Kami | {A768C45C-6AB3-428B-9F8F-0C9770100D31} | c0a8-0009-146b28c7ac5-73310cf6-90d-5e | Hz-ID-18667 | MCPA - Mine Clearance Planning Agency | AF/3106/15715/MF0018 | 14684 | 65.7271 | 36.1413 | Open | AT Only | AT Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {A768C45C-6AB3-428B-9F8F-0C9770100D31} |  | Low | Critical Infrastracture | Substantial | 0 | CHA | 5 |  |  | 2014-03-26 16:30 | No | Open
North | Sari Pul | Sayyad | Dara Band | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} | c0a8-008e-132e71af953-ca4a9e5a-1bd-d2 | MF-HQ-11599 | HT - HALO TRUST | H/3978 | 12200 | 65.7354 | 36.1357 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} |  | Low | Agriculture Blocked | Substantial | 39 | CHA | 5 |  |  | 2007-11-11 | No | Open
North | Sari Pul | Sayyad | Dara Band | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} | c0a8-008e-132e71da53d-4809e1de-1d3-d5 | MF-NA-872 | MCPA - Mine Clearance Planning Agency | AF/3106/15675/MF0005 | 9435 | 65.7263 | 36.13 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} |  | Low | Agriculture Blocked | Substantial | 18 | CHA | 5 |  |  | 2008-06-01 | No | Open
North | Sari Pul | Sayyad | Dara Band | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} | c0a8-008e-132e71ea9e9-6c2ec7f0-1e3-7d | MF-HQ-11438 | MCPA - Mine Clearance Planning Agency | AF/3106/15675/MF3977 | 7831 | 65.7345 | 36.1335 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} |  | Low | Agriculture Blocked | Substantial | 57 | CHA | 5 |  |  | 2007-11-12 | No | Open
North | Sari Pul | Sayyad | Dara Band | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} | c0a8-008e-132e720b009-3fe8e32d-20d-be | MF-HQ-11437 | HT - HALO TRUST | H/3979 | 5000 | 65.7232 | 36.1367 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} |  | Low | Agriculture Blocked | Substantial | 18 | CHA | 5 |  |  | 2007-11-14 | No | Open
North | Sari Pul | Sayyad | Dara Band | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} | c0a8-008e-132e7220304-229021a4-224-9d | MF-NA-870 | MCPA - Mine Clearance Planning Agency | AF/3106/15675/MF0003 | 38472 | 65.7189 | 36.1078 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} |  | Low | Critical Infrastracture | Substantial | 38 | CHA | 5 |  |  | 2008-06-01 | No | Open
North | Sari Pul | Sayyad | Dara Band | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} | c0a8-008e-132e722f116-7924e4c5-239-79 | MF-NA-871 | MCPA - Mine Clearance Planning Agency | AF/3106/15675/MF0004 | 1989 | 65.7305 | 36.1265 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {17BA8D81-30A8-4CA1-8474-93F3A9119E67} |  | Low | Agriculture Blocked | Substantial | 47 | CHA | 5 |  |  | 2008-06-01 | No | Open
North | Sari Pul | Sayyad | Sar-i-Chashma | {0614352D-0F06-454B-A47C-4A3C2ADDEE26} | c0a8-0009-145cb009252-a9ea5917-19e3-a | Hz-ID-18663 | MCPA - Mine Clearance Planning Agency | AF/3106/15718/MF0016 | 13594 | 65.831 | 36.1195 | Open | AP Only | AP Only | MineField |  | MBT Project-088 | Sari Pul Demining Project-1 |  |  |  |  | 1394 |  | {0614352D-0F06-454B-A47C-4A3C2ADDEE26} |  | Low | Agriculture Blocked | Substantial | 89 | CHA | 5 |  |  | 2014-03-23 16:30 | No | Open
North East | Badakhshan | Argo | Absiti | {62A58468-5F53-4EA4-8B20-6030CE068BBC} | c0a8-0009-13bdb2af161-9b7d03c3-114b-d | Hz-ID-17515 | HT - HALO TRUST | H/8432 | 1070 | 70.504 | 37.1609 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {62A58468-5F53-4EA4-8B20-6030CE068BBC} |  | Low | Agriculture Blocked | Minimal | 26 | CHA | 5 |  |  | 2012-11-06 16:30 | No | Open
North East | Badakhshan | Argo | Ali Mangu | {A13719C5-D89F-4ADB-83FE-40CA0D425DF0} | c0a8-0009-13b7e5db7f9-7c1e3ed8-4f53-7 | Hz-ID-17439 | MCPA - Mine Clearance Planning Agency | AF/1101/11201/MF0002 | 640 | 70.4639 | 36.9805 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {A13719C5-D89F-4ADB-83FE-40CA0D425DF0} |  | Medium | Agriculture Blocked | Minimal | 107 | CHA | 3 |  |  | 2012-09-03 16:30 | No | Open
North East | Badakhshan | Argo | Artin Jelow | {88A37BCE-C071-4941-80DE-AAFE0DAA509E} | c0a8-0057-12c3b71ff1d-535fcd08-f460-c | MF-HQ-15010 | MCPA - Mine Clearance Planning Agency | AF/1101/10904/MF6689 | 9418 | 70.1495 | 37.0488 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {88A37BCE-C071-4941-80DE-AAFE0DAA509E} |  | Low | Critical Infrastracture | Minimal | 16 | CHA | 5 |  |  | 2010-09-14 | No | Open
North East | Badakhshan | Argo | Dogh Gahalat | {E2D32BF1-6090-4152-906E-2070C81F5359} | c0a8-0057-12c3b896717-92b72163-2014d- | MF-HT-363 | MCPA - Mine Clearance Planning Agency | AF/1101/10837/MF2189 | 23775 | 70.4376 | 37.1181 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-026/A | Badakhshan Demining Project-01/A | Bilateral | Yes | 2014-09-01 |  | 1393 | HT | {E2D32BF1-6090-4152-906E-2070C81F5359} | Based on HALO Trust confirmation, the hazard removed from 1391 IWP | Low | Agriculture Blocked | Minimal | 13 | CHA | 5 |  |  | 2007-04-01 | No | Planned
North East | Badakhshan | Argo | Enaw | {519EE415-6D03-4AAD-9296-575617B8BC93} | c0a8-0057-12c3b72f28d-49c0d76e-ffbb-3 | MF-HQ-15213 | MCPA - Mine Clearance Planning Agency | AF/1101/12207/MF7342 | 5290 | 70.1322 | 37.0389 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {519EE415-6D03-4AAD-9296-575617B8BC93} |  | Low | Agriculture Blocked | Minimal | 89 | CHA | 5 |  |  | 2010-09-22 | No | Open
North East | Badakhshan | Argo | Enaw | {519EE415-6D03-4AAD-9296-575617B8BC93} | c0a8-0057-12c3b9d4830-70451503-2d403- | MF-HQ-15115 | HT - HALO TRUST | H/6687 | 6600 | 70.1191 | 37.0297 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {519EE415-6D03-4AAD-9296-575617B8BC93} |  | Low | Agriculture Blocked | Minimal | 119 | CHA | 5 |  |  | 2010-08-20 | No | Open
North East | Badakhshan | Argo | Ganda Chashma | {5FC18E93-1EF0-4CE7-92C5-233B52A6E6E7} | c0a8-0057-12c3b8e7656-302c2bb3-23980- | MF-HT-362 | MCPA - Mine Clearance Planning Agency | AF/1101/10954/MF2186 | 8709 | 70.4385 | 37.0587 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {5FC18E93-1EF0-4CE7-92C5-233B52A6E6E7} |  | Low | Critical Infrastracture | Minimal | 32 | CHA | 5 |  |  | 2007-04-01 | No | Open
North East | Badakhshan | Argo | Hazar Mishi | {6DE184BD-DF4F-41FA-8430-59B8A673B16B} | c0a8-0057-12c3b8ff8ba-386cb-24964-131 | MF-HT-431 | MCPA - Mine Clearance Planning Agency | AF/1101/10952/MF3199 | 31197 | 70.4442 | 37.0873 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-026/A | Badakhshan Demining Project-01/A | Bilateral | Yes | 2014-05-18 | 2014-08-23 | 1393 | HT | {6DE184BD-DF4F-41FA-8430-59B8A673B16B} |  | Low | Agriculture Blocked | Minimal | 10 | CHA | 4 |  |  | 2007-04-01 | No | Planned
North East | Badakhshan | Argo | Hazar Mishi | {6DE184BD-DF4F-41FA-8430-59B8A673B16B} | c0a8-0057-12c3ba91963-d73b810f-34721- | MF-HT-429 | MCPA - Mine Clearance Planning Agency | AF/1101/10952/MF3198 | 10298 | 70.4244 | 37.0737 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-026/A | Badakhshan Demining Project-01/A | Bilateral | Yes | 2014-06-01 | 2014-08-23 | 1393 | HT | {6DE184BD-DF4F-41FA-8430-59B8A673B16B} |  | Low | Agriculture Blocked | Minimal | 94 | CHA | 4 |  |  | 2007-04-01 | No | Planned
North East | Badakhshan | Argo | Hazar Mishi | {6DE184BD-DF4F-41FA-8430-59B8A673B16B} | c0a8-0057-12c3ba91eee-a97ccdf1-34737- | MF-HT-432 | MCPA - Mine Clearance Planning Agency | AF/1101/10952/MF3200 | 58306 | 70.4408 | 37.0827 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-026/A | Badakhshan Demining Project-01/A | Bilateral | Yes | 2014-05-11 | 2014-09-23 | 1393 | HT | {6DE184BD-DF4F-41FA-8430-59B8A673B16B} |  | Low | Agriculture Blocked | Minimal | 10 | CHA | 4 |  |  | 2007-04-01 | No | Planned
North East | Badakhshan | Argo | Khwaja Eshtel | {0972CF1F-EBB8-49FF-8D1D-9352CE2E35B0} | c0a8-00f6-139239cad0e-ae99def1-367f-6 | Hz-ID-17226 | MCPA - Mine Clearance Planning Agency | AF/1115/10955/MF0001 | 4394 | 70.4609 | 37.1035 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {0972CF1F-EBB8-49FF-8D1D-9352CE2E35B0} |  | Medium | Agriculture Blocked | Minimal | 391 | CHA | 3 |  |  | 2012-06-15 16:30 | No | Open
North East | Badakhshan | Argo | Kuhna Bataz | {B8B0B504-426F-4EF4-ABE1-3D85267A5038} | c0a8-0009-13f3c81aa37-d54f0015-556-6c | Hz-ID-17970 | HT - HALO TRUST | H/8478 | 8615 | 70.5427 | 37.045 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-026 | Badakhshan Demining Project-01 | Bilateral | Yes | 2013-07-01 | 2013-07-26 | 1392-1393 | HT | {B8B0B504-426F-4EF4-ABE1-3D85267A5038} |  |  |  | Minimal | 15 | CHA | 5 |  |  | 2013-05-07 16:30 | No | Planned
North East | Badakhshan | Argo | Kuhna Bataz | {B8B0B504-426F-4EF4-ABE1-3D85267A5038} | c0a8-004c-130178b7bd1-280685a4-7-4384 | MF-HT-1342 | MCPA - Mine Clearance Planning Agency | AF/1101/31572/MF3431 | 9601 | 70.5296 | 37.0582 | Closed | AP Only | AP Only | MineField | 1391/1392 | MBT Project-026 | Badakhshan Demining Project-01 | Bilateral | Yes | 2012-12-12 | 2013-06-23 | 1392-1393 | HT | {B8B0B504-426F-4EF4-ABE1-3D85267A5038} |  |  |  | Minimal | 38 | CHA | 3 |  |  | 2007-04-01 | No | Planned
North East | Badakhshan | Argo | Kuhna Bataz | {B8B0B504-426F-4EF4-ABE1-3D85267A5038} | c0a8-0057-12c3b85520b-8bcb4990-1d3dd- | MF-HT-1337 | MCPA - Mine Clearance Planning Agency | AF/1101/31572/MF3430 | 26754 | 70.5428 | 37.0473 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-026 | Badakhshan Demining Project-01 | Bilateral | Yes | 2012-12-10 | 2014-05-12 | 1392-1393 | HT | {B8B0B504-426F-4EF4-ABE1-3D85267A5038} |  |  |  | Minimal | 25 | CHA | 3 |  |  | 2007-04-01 | No | Planned
North East | Badakhshan | Argo | Qara Mughul | {D0E37B4C-6A3A-4A06-A67A-FBB677C1A059} | c0a8-0009-13ec57ea563-2282731a-28ff-3 | Hz-ID-17916 | HT - HALO TRUST | H/8475 | 7620 | 70.5447 | 37.0483 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-026 | Badakhshan Demining Project-01 | Bilateral | Yes | 2013-09-09 | 2014-02-23 | 1392-1393 | HT | {D0E37B4C-6A3A-4A06-A67A-FBB677C1A059} |  |  |  | Minimal | 35 | CHA | 5 |  |  | 2013-04-21 16:30 | No | Planned
North East | Badakhshan | Argo | Qara Mughul | {D0E37B4C-6A3A-4A06-A67A-FBB677C1A059} | c0a8-0009-13f0ddc92f8-f51c986a-291-db | Hz-ID-17928 | HT - HALO TRUST | H/8476 | 37020 | 70.5428 | 37.0473 | Worked on | AP Only | AP Only | MineField | 1392/1393 | MBT Project-026 | Badakhshan Demining Project-01 | Bilateral | Yes | 2013-07-04 | 2014-01-23 | 1392-1393 | HT | {D0E37B4C-6A3A-4A06-A67A-FBB677C1A059} |  | Low | Critical Infrastracture | Minimal | 34 | CHA | 5 |  |  | 2013-04-21 16:30 | No | Planned
North East | Badakhshan | Darayim | Pengani | {19EAADA9-3B0E-4701-98FE-245A905FD95E} | c0a8-0009-13b454993fa-d9ba0297-4ff4-a | Hz-ID-17378 | HT - HALO TRUST | H/8404 | 3740 | 70.2689 | 37.0133 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-026 | Badakhshan Demining Project-01 | Bilateral | Yes | 2013-06-01 | 2013-06-11 | 1392-1393 | HT | {19EAADA9-3B0E-4701-98FE-245A905FD95E} |  |  |  | Moderate | 71 | CHA | 1 | Yes | Priority of Those tasks are high but there are seasonal problem | 2012-10-06 16:30 | No | Planned
North East | Badakhshan | Darayim | Pengani | {19EAADA9-3B0E-4701-98FE-245A905FD95E} | c0a8-0009-13b454fcb7b-b7bbb6db-514c-5 | Hz-ID-17379 | HT - HALO TRUST | H/8405 | 580 | 70.2661 | 37.0258 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-026 | Badakhshan Demining Project-01 | Bilateral | Yes | 2013-06-03 | 2013-06-09 | 1392-1393 | HT | {19EAADA9-3B0E-4701-98FE-245A905FD95E} |  |  |  | Moderate | 13 | CHA | 1 | Yes | Priority of Those tasks are high but there are seasonal problem | 2012-10-06 16:30 | No | Planned
North East | Badakhshan | Darayim | Pengani | {19EAADA9-3B0E-4701-98FE-245A905FD95E} | c0a8-0009-13b45835284-45fd0264-52fe-9 | Hz-ID-17380 | HT - HALO TRUST | H/8406 | 5920 | 70.2676 | 37.0285 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-026 | Badakhshan Demining Project-01 | Bilateral | Yes | 2013-06-10 | 2013-06-20 | 1392-1393 | HT | {19EAADA9-3B0E-4701-98FE-245A905FD95E} |  |  |  | Moderate | 17 | CHA | 1 | Yes | Priority of Those tasks are high but there are seasonal problem | 2012-10-06 16:30 | No | Planned
North East | Badakhshan | Darayim | Pengani | {19EAADA9-3B0E-4701-98FE-245A905FD95E} | c0a8-0009-13b458b1774-d22d78a0-5325-5 | Hz-ID-17381 | HT - HALO TRUST | H/8407 | 2950 | 70.2725 | 37.0056 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-026 | Badakhshan Demining Project-01 | Bilateral | Yes | 2013-06-01 | 2013-06-10 | 1392-1393 | HT | {19EAADA9-3B0E-4701-98FE-245A905FD95E} |  |  |  | Moderate | 368 | CHA | 1 | Yes | Priority of Those tasks are high but there are seasonal problem | 2012-10-06 16:30 | No | Planned
North East | Badakhshan | Darayim | Pengani | {19EAADA9-3B0E-4701-98FE-245A905FD95E} | c0a8-0009-13b4a857ab0-afcd7670-5aa3-8 | Hz-ID-17382 | HT - HALO TRUST | H/8408 | 2000 | 70.2812 | 37.003 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-026 | Badakhshan Demining Project-01 | Bilateral | Yes | 2013-06-10 | 2013-06-20 | 1392-1393 | HT | {19EAADA9-3B0E-4701-98FE-245A905FD95E} |  |  |  | Moderate | 0 | CHA | 1 | Yes | Priority of Those tasks are high but there are seasonal problem | 2012-10-06 16:30 | No | Planned
North East | Badakhshan | Darwaz | Darwaz (Nusay) | {33E3C09B-29BC-40A1-9503-1B42F56E2B52} | c0a8-00f6-137f956dfd4-c5e18077-469-ed | Hz-ID-17029 | FSD - Swiss Foundation for Mine Action | AF/1110/11687/MF0008 | 33872 | 70.8415 | 38.3804 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {33E3C09B-29BC-40A1-9503-1B42F56E2B52} |  | Low | Critical Infrastracture | Minimal | 27 | CHA | 5 |  |  | 2011-10-18 16:30 | No | Open
North East | Badakhshan | Darwaz | Jamarj-i-Payan | {44230520-32ED-450A-BF75-2C75D5045B96} | c0a8-00f6-1369ab10f2f-98d1ea72-1092-e | MF-16740 | FSD - Swiss Foundation for Mine Action | AF/1110/11701/MF0005 | 4850 | 70.9689 | 38.4652 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-117 | Badakhshan Demining Project-03 | PATRIP | Yes | 2013-09-26 | 2013-10-09 | 1392-1393 | FSD | {44230520-32ED-450A-BF75-2C75D5045B96} |  |  |  | Minimal | 15 | CHA | 3 |  |  | 2011-10-17 16:30 | No | Planned
North East | Badakhshan | Darwaz | Jamarj-i-Payan | {44230520-32ED-450A-BF75-2C75D5045B96} | c0a8-00f6-13846ad9cfe-fb67f9bb-1f56-7 | Hz-ID-17094 | FSD - Swiss Foundation for Mine Action | AF/1110/11701/MF0007 | 17393 | 70.9483 | 38.4312 | Open | AP Only | AP Only | MineField | 1392 | MBT Project-117/A | Badakhshan Demining Project-03/A |  | Yes | 2013-05-31 | 2013-07-11 | 1398 | FSD | {44230520-32ED-450A-BF75-2C75D5045B96} |  | Medium | Critical Infrastracture | Minimal | 5 | CHA | 3 |  |  | 2011-10-17 16:30 | No | Open
North East | Badakhshan | Darwaz | Madud | {593FD58F-B75F-4882-A331-AAF918EC7D82} | c0a8-0057-12c3bb85bf7-1eacd434-3d59f- | MF-HT-491 | HT - HALO TRUST | H/3546 | 48500 | 70.9006 | 38.0196 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {593FD58F-B75F-4882-A331-AAF918EC7D82} |  | High with Victim | High with Victims | Minimal | 0 | CHA | 6 |  |  | 2007-06-01 | No | Open
North East | Badakhshan | Darwaz | Madud | {593FD58F-B75F-4882-A331-AAF918EC7D82} | c0a8-00f6-1392419c50a-3bf21cba-3dbf-d | Hz-ID-17190 | FSD - Swiss Foundation for Mine Action | AF/1110/11643/MF0011 | 47291 | 70.9266 | 38.1068 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {593FD58F-B75F-4882-A331-AAF918EC7D82} |  | High with Victim | High with Victims | Minimal | 1 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwaz | Madud | {593FD58F-B75F-4882-A331-AAF918EC7D82} | c0a8-00f6-139241b4060-f9e5bcbf-3e33-d | Hz-ID-17199 | FSD - Swiss Foundation for Mine Action | AF/1110/11643/MF0013 | 73262 | 70.9124 | 38.1161 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {593FD58F-B75F-4882-A331-AAF918EC7D82} |  | High with Victim | High with Victims | Minimal | 23 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwaz | Madud | {593FD58F-B75F-4882-A331-AAF918EC7D82} | c0a8-00f6-139241ce46b-f8f0616d-3e94-b | Hz-ID-17203 | FSD - Swiss Foundation for Mine Action | AF/1110/11643/MF0010 | 65478 | 70.8822 | 38.1023 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {593FD58F-B75F-4882-A331-AAF918EC7D82} |  | High with Victim | High with Victims | Minimal | 5 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwaz | Madud | {593FD58F-B75F-4882-A331-AAF918EC7D82} | c0a8-00f6-139b3b7379f-4267d605-273a-e | Hz-ID-17193 | FSD - Swiss Foundation for Mine Action | AF/1110/11643/MF0012 | 31230 | 70.8996 | 38.0884 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {593FD58F-B75F-4882-A331-AAF918EC7D82} |  | High with Victim | High with Victims | Minimal | 12 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwaz | Rawan | {47249EE5-DC83-488D-B099-BC26BD5FB99F} | c0a8-00f6-13923a6ccab-12e7800a-37ee-7 | Hz-ID-17209 | FSD - Swiss Foundation for Mine Action | AF/1110/11662/BF0015 | 599847 | 70.8688 | 38.3167 | Open | UXO Only | UXO Only | BF |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {47249EE5-DC83-488D-B099-BC26BD5FB99F} |  | Low | Agriculture Blocked | Minimal | 19 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwaz | Rawan | {47249EE5-DC83-488D-B099-BC26BD5FB99F} | c0a8-00f6-13923abd772-6f2fc212-3837-c | Hz-ID-17211 | FSD - Swiss Foundation for Mine Action | AF/1110/11662/BF0016 | 380611 | 70.8617 | 38.3225 | Open | UXO Only | UXO Only | BF |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {47249EE5-DC83-488D-B099-BC26BD5FB99F} |  | Medium | Critical Infrastracture | Minimal | 166 | CHA | 3 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwaz | Rawan | {47249EE5-DC83-488D-B099-BC26BD5FB99F} | c0a8-00f6-139241e7016-80583a81-3eae-5 | Hz-ID-17206 | FSD - Swiss Foundation for Mine Action | AF/1110/11662/MF0014 | 35225 | 70.8594 | 38.3279 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {47249EE5-DC83-488D-B099-BC26BD5FB99F} |  | Low | Agriculture Blocked | Minimal | 11 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwaz | Sar-i-Deh | {3921D284-050B-42CF-9525-AFF6B02DDEC8} | c0a8-00f6-13923d396e9-217919ad-3a62-c | Hz-ID-17228 | FSD - Swiss Foundation for Mine Action | AF/1110/11637/MF0019 | 27046 | 70.8378 | 38.4384 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {3921D284-050B-42CF-9525-AFF6B02DDEC8} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwaz | Sar-i-Deh | {3921D284-050B-42CF-9525-AFF6B02DDEC8} | c0a8-00f6-13923d8d78f-8c86781b-3af6-5 | Hz-ID-17229 | FSD - Swiss Foundation for Mine Action | AF/1110/11637/MF0020 | 28698 | 70.8286 | 38.4387 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {3921D284-050B-42CF-9525-AFF6B02DDEC8} |  | Low | Agriculture Blocked | Minimal | 14 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwaz | Sar-i-Deh | {3921D284-050B-42CF-9525-AFF6B02DDEC8} | c0a8-00f6-13923e0e3ac-3100d566-3b74-5 | Hz-ID-17208 | FSD - Swiss Foundation for Mine Action | AF/1110/11637/MF0017 | 185158 | 70.8155 | 38.4349 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {3921D284-050B-42CF-9525-AFF6B02DDEC8} |  | Low | Agriculture Blocked | Minimal | 139 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwaz | Sar-i-Deh | {3921D284-050B-42CF-9525-AFF6B02DDEC8} | c0a8-00f6-13923f1d195-537e4d9d-3c5e-f | Hz-ID-17217 | FSD - Swiss Foundation for Mine Action | AF/1110/11637/MF0018 | 45919 | 70.8193 | 38.4344 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {3921D284-050B-42CF-9525-AFF6B02DDEC8} |  | Low | Agriculture Blocked | Minimal | 13 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwazbala | Bagh-i-Tal | {B87458E5-579E-428A-8894-6F8ED2A10D13} | c0a8-0009-1471989d921-998961be-f33-b1 | Hz-ID-18839 | FSD - Swiss Foundation for Mine Action | AF/1110/11717/MF0007 | 26863 | 71.318 | 38.2706 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {B87458E5-579E-428A-8894-6F8ED2A10D13} |  | Low | Critical Infrastracture | Minimal | 0 | CHA | 5 |  |  | 2014-05-12 16:30 | No | Open
North East | Badakhshan | Darwazbala | Bini Kamar | {AC06D145-AAE2-4595-ACDD-66832E2344F9} | c0a8-0009-145cbd3d452-dc068356-1ba7-8 | Hz-ID-18673 | FSD - Swiss Foundation for Mine Action | AF/1110/11715/MF0006 | 56652 | 71.324 | 38.3017 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-117 | Badakhshan Demining Project-03 | PATRIP | Yes |  |  | 1392-1393 | FSD | {AC06D145-AAE2-4595-ACDD-66832E2344F9} | It is part of MF0005 that DT-02 was working dueto fund problem the team could not progress and made a completion for 236882sqm area and the remain area is cover in MF0006 | High with Victim | High with Victims | Minimal | 0 | CHA | 1 |  |  | 2014-03-08 16:30 | No | Planned
North East | Badakhshan | Darwazbala | Bini Kamar | {AC06D145-AAE2-4595-ACDD-66832E2344F9} | c0a8-00f6-139239427fb-c47015e7-35f7-b | Hz-ID-17207 | FSD - Swiss Foundation for Mine Action | AF/1111/11715/MF0004 | 13053 | 71.3166 | 38.2958 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-117 | Badakhshan Demining Project-03 | PATRIP | Yes | 2013-06-13 | 2013-07-13 | 1392-1393 | FSD | {AC06D145-AAE2-4595-ACDD-66832E2344F9} |  |  |  | Minimal | 0 | CHA | 3 |  |  | 2012-07-10 16:30 | No | Planned
North East | Badakhshan | Darwazbala | Bini Kamar | {AC06D145-AAE2-4595-ACDD-66832E2344F9} | c0a8-00f6-13923a3d997-1fac17ca-3765-e | Hz-ID-17202 | FSD - Swiss Foundation for Mine Action | AF/1117/11715/MF0005 | 266165 | 71.3125 | 38.302 | Closed | AP Only | AP Only | MineField | 1391/1392 | MBT Project-117 | Badakhshan Demining Project-03 | PATRIP | Yes | 2013-12-26 | 2013-12-26 | 1392-1393 | FSD | {AC06D145-AAE2-4595-ACDD-66832E2344F9} |  |  |  | Minimal | 16 | CHA | 5 |  |  | 2012-07-11 16:30 | No | Planned
North East | Badakhshan | Darwazbala | Dashtake Ghaz Dara | {F28BBED6-C8E8-46DB-A48A-893CA492B74A} | c0a8-0057-12c3b8dc496-62af0c37-23167- | MF-HT-1131 | HT - HALO TRUST | H/3544 | 21500 | 71.1754 | 38.3627 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {F28BBED6-C8E8-46DB-A48A-893CA492B74A} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 5 |  |  | 2007-06-01 | No | Open
North East | Badakhshan | Darwazbala | Ghumay (3) | {38A7BA5D-CC6C-42FE-A092-FE2BC9D9BDE3} | c0a8-0009-147c8963de8-dc6d7029-307-a9 | Hz-ID-18880 | FSD - Swiss Foundation for Mine Action | AF/1117/11659/MF0013 | 50168 | 71.3376 | 38.1337 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {38A7BA5D-CC6C-42FE-A092-FE2BC9D9BDE3} |  | Low | Critical Infrastracture | Minimal | 4 | CHA | 5 |  |  | 2014-06-22 16:30 | No | Open
North East | Badakhshan | Darwazbala | Ghumay (3) | {38A7BA5D-CC6C-42FE-A092-FE2BC9D9BDE3} | c0a8-0009-147c89c4b3a-55141192-44b-38 | Hz-ID-18881 | FSD - Swiss Foundation for Mine Action | AF/1117/11659/MF0014 | 68764 | 71.3408 | 38.1463 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {38A7BA5D-CC6C-42FE-A092-FE2BC9D9BDE3} |  | Low | Critical Infrastracture | Minimal | 17 | CHA | 5 |  |  | 2014-06-24 16:30 | No | Open
North East | Badakhshan | Darwazbala | Jamarj-e Bala | {461D713A-B19E-404B-828A-187E8EC55DF3} | c0a8-0009-1471e7269fa-ed901ce4-814-b5 | Hz-ID-18841 | FSD - Swiss Foundation for Mine Action | AF/1110/11719/MF0009 | 6135 | 71.318 | 38.2745 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {461D713A-B19E-404B-828A-187E8EC55DF3} |  | Low | Critical Infrastracture | Minimal | 0 | CHA | 5 |  |  | 2014-05-08 16:30 | No | Open
North East | Badakhshan | Darwazbala | Jamarj-e Bala | {461D713A-B19E-404B-828A-187E8EC55DF3} | c0a8-0009-147c890387f-e9b19ab9-228-3f | Hz-ID-18840 | FSD - Swiss Foundation for Mine Action | AF/1110/11719/MF0008 | 1145 | 71.3181 | 38.2817 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {461D713A-B19E-404B-828A-187E8EC55DF3} |  | Medium | Agriculture Blocked | Minimal | 12 | CHA | 3 |  |  | 2014-05-13 16:30 | No | Open
North East | Badakhshan | Darwazbala | Jashtak | {67295752-9584-4593-8604-F215F6E97DF1} | c0a8-0057-12c3b9825ca-1865fb71-29ee6- | MF-HT-1461 | HT - HALO TRUST | H/3543 | 46000 | 71.1798 | 38.3565 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-117 | Badakhshan Demining Project-03 | PATRIP | Yes | 2013-04-16 | 2013-06-12 | 1392-1393 | FSD | {67295752-9584-4593-8604-F215F6E97DF1} |  |  |  | Minimal | 0 | CHA | 5 |  |  | 2007-06-01 | No | Planned
North East | Badakhshan | Darwazbala | Jashtak | {67295752-9584-4593-8604-F215F6E97DF1} | c0a8-0057-12c3ba9a6d1-3b398d60-34c2e- | MF-HT-488 | HT - HALO TRUST | H/3545 | 45000 | 71.1655 | 38.3678 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {67295752-9584-4593-8604-F215F6E97DF1} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 5 |  |  | 2007-06-01 | No | Open
North East | Badakhshan | Darwazbala | Jashtak | {67295752-9584-4593-8604-F215F6E97DF1} | c0a8-0057-12c3bb18ab5-fec4cc24-396ea- | MF-HT-486 | HT - HALO TRUST | H/3542 | 24620 | 71.1765 | 38.3612 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {67295752-9584-4593-8604-F215F6E97DF1} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 5 |  |  | 2007-06-01 | No | Open
North East | Badakhshan | Darwazbala | Maymay | {33D65708-BA8C-4A97-B7EB-CE8F38335F9E} | c0a8-00f6-1398ab31175-92972090-13-9f2 | Hz-ID-17222 | FSD - Swiss Foundation for Mine Action | AF/1117/11728/MF0001 | 94825 | 71.0392 | 38.416 | Open | AP Only | AP Only | MineField | 1392 | MBT Project-117/A | Badakhshan Demining Project-03/A |  | Yes | 2013-09-16 | 2014-08-11 | 1398 | FSD | {33D65708-BA8C-4A97-B7EB-CE8F38335F9E} |  | Low | Agriculture Blocked | Minimal | 243 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Darwazbala | Rawand | {F6173A78-E5BC-4959-84D0-286C9A52B50B} | c0a8-0009-1471e812a46-ce018394-938-c8 | Hz-ID-18845 | FSD - Swiss Foundation for Mine Action | AF/1110/11652/MF0012 | 20885 | 71.2918 | 38.0474 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {F6173A78-E5BC-4959-84D0-286C9A52B50B} |  | Low | Critical Infrastracture | Minimal | 0 | CHA | 5 |  |  | 2014-06-04 16:30 | No | Open
North East | Badakhshan | Darwazbala | Sadwad | {834BD048-395E-4F44-B02C-78615F422104} | c0a8-0009-1471e759fe7-c371169c-848-5d | Hz-ID-18842 | FSD - Swiss Foundation for Mine Action | AF/1110/11651/MF0010 | 151208 | 71.2925 | 38.0317 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {834BD048-395E-4F44-B02C-78615F422104} |  | Low | Critical Infrastracture | Minimal | 0 | CHA | 5 |  |  | 2014-05-29 16:30 | No | Open
North East | Badakhshan | Darwazbala | Sadwad | {834BD048-395E-4F44-B02C-78615F422104} | c0a8-0009-1471e797389-e5bf6ab7-87f-57 | Hz-ID-18844 | FSD - Swiss Foundation for Mine Action | AF/1110/11651/MF0011 | 190549 | 71.2789 | 38.035 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {834BD048-395E-4F44-B02C-78615F422104} |  | Low | Critical Infrastracture | Minimal | 215 | CHA | 5 |  |  | 2014-05-30 16:30 | No | Open
North East | Badakhshan | Fayzabad | Ashe | {D4085561-E8FD-4733-8659-01A9D1A35BBB} | c0a8-0057-12c3ba8f38b-bdc11f18-345b6- | MF-HQ-14730 | HT - HALO TRUST | H/6643 | 4100 | 70.5889 | 37.1582 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-026/A | Badakhshan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {D4085561-E8FD-4733-8659-01A9D1A35BBB} | , | Medium | Agriculture Blocked | Minimal | 15 | CHA | 3 |  |  | 2010-06-13 | No | Planned
North East | Badakhshan | Fayzabad | Ashe | {D4085561-E8FD-4733-8659-01A9D1A35BBB} | c0a8-0057-12c3ba8f781-1ec444a-345d0-9 | MF-HT-526 | HT - HALO TRUST | H/3196 | 38700 | 70.5878 | 37.1543 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-026/A | Badakhshan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {D4085561-E8FD-4733-8659-01A9D1A35BBB} | , | Low | Agriculture Blocked | Minimal | 3 | CHA | 5 |  |  | 2010-06-13 | No | Planned
North East | Badakhshan | Fayzabad | Malmunj | {C92321E0-B684-4FA7-838B-7BB4DB968B7B} | c0a8-0009-13bdaeb1836-aacdd603-e48-f5 | Hz-ID-17514 | HT - HALO TRUST | H/8431 | 89600 | 70.6316 | 37.2023 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {C92321E0-B684-4FA7-838B-7BB4DB968B7B} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2012-11-20 16:30 | No | Open
North East | Badakhshan | Fayzabad | Safich Kha | {48E6F56B-A789-4B9F-9768-6AFAB8EE550B} | c0a8-0057-12c3baf2dae-7d2c7409-38073- | MF-HT-336 | HT - HALO TRUST | H/2172 | 8600 | 70.5962 | 37.1623 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-026/A | Badakhshan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {48E6F56B-A789-4B9F-9768-6AFAB8EE550B} | , | Low | Agriculture Blocked | Minimal | 119 | CHA | 5 |  |  | 2010-06-14 | No | Planned
North East | Badakhshan | Khwahan | Chashma-i-Tut | {10DB0047-14F0-416F-8141-595354EF18AF} | c0a8-0009-145cfd5537a-6729e62b-24a3-6 | Hz-ID-18674 | FSD - Swiss Foundation for Mine Action | AF/1111/11766/BF0002 | 2119 | 70.2195 | 37.8891 | Open | UXO Only | UXO Only | BF |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {10DB0047-14F0-416F-8141-595354EF18AF} |  | Medium | Comunity Centers | Minimal | 35 | CHA | 3 |  |  | 2014-03-08 16:30 | No | Open
North East | Badakhshan | Khwahan | Chashma-i-Tut | {10DB0047-14F0-416F-8141-595354EF18AF} | c0a8-0009-1470f19d625-f9b032f4-17a8-8 | Hz-ID-18837 | FSD - Swiss Foundation for Mine Action | AF/1111/11766/BF0003 | 13401 | 70.2191 | 37.8905 | Open | UXO Only | UXO Only | BF |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {10DB0047-14F0-416F-8141-595354EF18AF} |  | Medium | Critical Infrastracture | Minimal | 0 | CHA | 5 |  |  | 2014-05-12 16:30 | No | Open
North East | Badakhshan | Khwahan | Du Dargah | {32B2045C-30B4-476B-BD49-DA01EFDF99D2} | c0a8-0009-1470f2d619b-f4d7e855-185d-b | Hz-ID-18838 | FSD - Swiss Foundation for Mine Action | AF/1111/11764/MF0001 | 6903 | 70.2869 | 37.8603 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {32B2045C-30B4-476B-BD49-DA01EFDF99D2} |  | Low | Critical Infrastracture | Minimal | 0 | CHA | 5 |  |  | 2014-05-26 16:30 | No | Open
North East | Badakhshan | Khwahan | Khwahan | {095A4CB4-2DFF-41E4-B723-B0855F8EB80A} | c0a8-00f6-13923b64fa9-8756be0f-38c6-6 | Hz-ID-17221 | FSD - Swiss Foundation for Mine Action | AF/1111/11767/BF0001 | 357397 | 70.2184 | 37.888 | Worked on | UXO Only | UXO Only | BF | 1392 | MBT Project-117 | Badakhshan Demining Project-03 | PATRIP | Yes | 2013-11-10 | 2014-09-30 | 1392-1393 | FSD | {095A4CB4-2DFF-41E4-B723-B0855F8EB80A} |  | High | Critical Infrastracture | Minimal | 1001 | CHA | 3 |  |  | 2012-06-24 16:30 | No | Planned
North East | Badakhshan | Kuf Ab | Chatniw | {5205A91D-CEB0-4EB8-B0C0-818324AF24CA} | c0a8-0009-141a09bbecb-62990dc4-2c96-8 | Hz-ID-18197 | HT - HALO TRUST | H/8852 | 63700 | 70.6313 | 37.9035 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {5205A91D-CEB0-4EB8-B0C0-818324AF24CA} |  | Low | Agriculture Blocked | Minimal | 107 | CHA | 4 |  |  | 2013-09-17 16:30 | No | Open
North East | Badakhshan | Kuf Ab | Kherch | {AF042680-C990-43BF-8502-E8467798AF5E} | c0a8-0009-141a10a4970-9059c5-3af5-96e | Hz-ID-18198 | HT - HALO TRUST | H/8851 | 22040 | 70.3844 | 38.0609 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {AF042680-C990-43BF-8502-E8467798AF5E} |  | Low | Critical Infrastracture | Minimal | 0 | CHA | 5 |  |  | 2013-09-19 16:30 | No | Open
North East | Badakhshan | Kuf Ab | Labgard (1) | {49D06788-28F5-469A-B03B-20D214688922} | c0a8-00f6-13923c1cf7d-3f6e8184-3966-9 | Hz-ID-17227 | FSD - Swiss Foundation for Mine Action | AF/1119/11780/MF0001 | 94825 | 70.3432 | 38.0082 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {49D06788-28F5-469A-B03B-20D214688922} |  | Low | Agriculture Blocked | Minimal | 243 | CHA | 5 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Askazir | {486C4724-3D0D-4D3F-AEC4-6D31F58DEE8B} | c0a8-0057-12c3b6f6ac1-a132a4e8-d4fb-4 | MF-HQ-14253 | MCPA - Mine Clearance Planning Agency | AF/1104/12015/MF3628 | 4000 | 70.7116 | 36.0302 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {486C4724-3D0D-4D3F-AEC4-6D31F58DEE8B} |  | Low | Agriculture Blocked | Moderate | 10 | CHA | 5 |  |  | 2007-08-16 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Askazir | {486C4724-3D0D-4D3F-AEC4-6D31F58DEE8B} | c0a8-0057-12c3b9ded14-296ab13c-2da7a- | MF-HT-372 | MCPA - Mine Clearance Planning Agency | AF/1104/12015/MF2197 | 6000 | 70.7142 | 36.0372 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {486C4724-3D0D-4D3F-AEC4-6D31F58DEE8B} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2007-08-01 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Dasht | {AA52D314-B20B-4ED4-9E03-C82426871A15} | c0a8-0009-1417cea8853-f78c58fa-60d-45 | Hz-ID-18175 | MCPA - Mine Clearance Planning Agency | AF/1104/12032/BF0001 | 2 | 70.9165 | 35.9528 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {AA52D314-B20B-4ED4-9E03-C82426871A15} |  | High | Water Blocked | Moderate | 0 | CHA | 3 |  |  | 2013-08-18 16:30 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Ferazen | {FDEA0306-5753-4070-8A55-F3D3F4C2B4E1} | c0a8-0057-12c3b850083-5695ab60-1d031- | MF-HQ-12371 | HT - HALO TRUST | H/6327 | 11070 | 70.5497 | 35.6158 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {FDEA0306-5753-4070-8A55-F3D3F4C2B4E1} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2009-08-07 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Razer | {A15538B1-4E08-41EF-92FF-9E705A60E3FA} | c0a8-0057-12c3b8ea2f1-268777e9-23b4e- | MF-HT-380 | MCPA - Mine Clearance Planning Agency | AF/1104/12020/MF2201 | 102766 | 70.7335 | 36.0224 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {A15538B1-4E08-41EF-92FF-9E705A60E3FA} |  | Medium | Critical Infrastracture | Moderate | 172 | CHA | 3 |  |  | 2007-08-01 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Razer | {A15538B1-4E08-41EF-92FF-9E705A60E3FA} | c0a8-0057-12c3bafcf76-d026d4be-38692- | MF-HQ-12366 | MCPA - Mine Clearance Planning Agency | AF/1104/12017/MF6330 | 74170 | 70.7554 | 36.0075 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {A15538B1-4E08-41EF-92FF-9E705A60E3FA} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2009-08-09 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Razer | {A15538B1-4E08-41EF-92FF-9E705A60E3FA} | c0a8-0057-12c3bafd14a-d5fca5b4-386a7- | MF-HT-375 | MCPA - Mine Clearance Planning Agency | AF/1104/12017/MF2199 | 12000 | 70.7907 | 36.0233 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {A15538B1-4E08-41EF-92FF-9E705A60E3FA} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2007-08-01 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Razer | {A15538B1-4E08-41EF-92FF-9E705A60E3FA} | c0a8-0057-12c3bb2cc63-c37734c6-3a2bd- | MF-HT-373 | MCPA - Mine Clearance Planning Agency | AF/1104/12017/MF2198 | 42611 | 70.725 | 35.9992 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {A15538B1-4E08-41EF-92FF-9E705A60E3FA} |  | Medium | Critical Infrastracture | Moderate | 108 | CHA | 3 |  |  | 2007-08-01 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Robat | {2D5762FB-90CD-4F37-8668-7E84F900CF5F} | c0a8-0057-12c3b8439dd-acf751d4-1c71b- | MF-HQ-11003 | MCPA - Mine Clearance Planning Agency | AF/1104/12042/MF0003 | 101172 | 70.7915 | 36.011 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {2D5762FB-90CD-4F37-8668-7E84F900CF5F} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 2 |  |  | 2009-07-01 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Robat | {2D5762FB-90CD-4F37-8668-7E84F900CF5F} | c0a8-0057-12c3b973a4a-eee79a31-2952f- | MF-HT-377 | MCPA - Mine Clearance Planning Agency | AF/1104/12042/MF2200 | 99873 | 70.8025 | 36.0363 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {2D5762FB-90CD-4F37-8668-7E84F900CF5F} |  | High with Victim | High with Victims | Moderate | 158 | CHA | 2 |  |  | 2007-08-01 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Shahe Pari | {B552D391-FB83-4044-8D8C-423B38539589} | c0a8-0057-12c3b7a0a4f-80fe2a7c-1534e- | MF-HT-521 | MCPA - Mine Clearance Planning Agency | AF/1104/12029/MF6328 | 192500 | 70.9114 | 35.8963 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {B552D391-FB83-4044-8D8C-423B38539589} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 2 |  |  | 2009-08-08 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Shahe Pari | {B552D391-FB83-4044-8D8C-423B38539589} | c0a8-0057-12c3b973c7b-104a7b3c-29542- | MF-HQ-12368 | MCPA - Mine Clearance Planning Agency | AF/1104/12029/MF6329 | 97500 | 70.9633 | 35.8568 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {B552D391-FB83-4044-8D8C-423B38539589} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 2 |  |  | 2009-08-08 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Shahran | {E57CCB0A-7CC3-4AD6-B714-99BB018527A4} | c0a8-0009-1417cdb83c0-533c3430-5af-42 | Hz-ID-18177 | MCPA - Mine Clearance Planning Agency | AF/1104/12028/MF0002 | 47588 | 70.897 | 36.0016 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {E57CCB0A-7CC3-4AD6-B714-99BB018527A4} |  | High with Victim | High with Victims | Moderate | 4 | CHA | 2 |  |  | 2013-08-20 16:30 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Tili | {330C2069-55F7-48B2-A80C-857926E7855C} | c0a8-0057-12c3b81b6b0-24e77166-1aa6e- | MF-HQ-12397 | MCPA - Mine Clearance Planning Agency | AF/1104/12024/MF6323 | 68000 | 70.815 | 35.7884 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {330C2069-55F7-48B2-A80C-857926E7855C} |  | Low | Critical Infrastracture | Moderate | 0 | CHA | 5 |  |  | 2009-08-04 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Tili | {330C2069-55F7-48B2-A80C-857926E7855C} | c0a8-0057-12c3bb15f14-a013c66d-3953e- | MF-HQ-12393 | MCPA - Mine Clearance Planning Agency | AF/1104/12024/MF6326 | 55500 | 70.9397 | 35.719 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {330C2069-55F7-48B2-A80C-857926E7855C} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2009-08-05 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Tili | {330C2069-55F7-48B2-A80C-857926E7855C} | c0a8-0057-12c3bb43e82-66938ff0-3b0aa- | MF-HQ-12411 | MCPA - Mine Clearance Planning Agency | AF/1104/12024/MF6325 | 15900 | 70.8111 | 35.7921 | Open | AP Only | AP Only | MineField |  | MBT Project-134 | Badakhshan Demining Project-04 |  |  |  |  | 1395 |  | {330C2069-55F7-48B2-A80C-857926E7855C} |  | Medium | Critical Infrastracture | Moderate | 8 | CHA | 3 |  |  | 2009-08-04 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Tili | {330C2069-55F7-48B2-A80C-857926E7855C} | c0a8-0057-12c3bb440b4-ee32fe28-3b0c1- | MF-HQ-12414 | MCPA - Mine Clearance Planning Agency | AF/1104/12024/MF6324 | 15200 | 70.8056 | 35.7888 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {330C2069-55F7-48B2-A80C-857926E7855C} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2009-08-04 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Wulf | {2ED50CE8-6CEA-4547-829D-4E09A2CCFC7E} | c0a8-0057-12c3b7d0346-6d4e2dd1-175a3- | MF-HQ-12391 | MCPA - Mine Clearance Planning Agency | AF/1104/12037/MF6333 | 303111 | 71.082 | 36.0167 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {2ED50CE8-6CEA-4547-829D-4E09A2CCFC7E} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 5 |  |  | 2009-08-10 | No | Open
North East | Badakhshan | Kuran Wa Munjan | Wulf | {2ED50CE8-6CEA-4547-829D-4E09A2CCFC7E} | c0a8-0057-12c3b7db5a1-5a8b54d7-17d8a- | MF-HQ-12389 | MCPA - Mine Clearance Planning Agency | AF/1104/12037/MF6332 | 3273 | 71.0375 | 36.039 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {2ED50CE8-6CEA-4547-829D-4E09A2CCFC7E} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 3 |  |  | 2009-08-10 | No | Open
North East | Badakhshan | Shaki | Ghumay (1) | {12D9B40F-62FC-4441-AB3F-E037295DB299} | c0a8-00f6-1384b323683-e03dec20-207b-7 | Hz-ID-17098 | FSD - Swiss Foundation for Mine Action | AF/1122/11585/MF0003 | 197728 | 70.6107 | 38.2835 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {12D9B40F-62FC-4441-AB3F-E037295DB299} | contact persons are Alauddin, Nasrullah | High with Victim | High with Victims | Minimal | 24 | CHA | 2 |  |  | 2011-12-07 16:30 | No | Open
North East | Badakhshan | Shaki | Ghumay (1) | {12D9B40F-62FC-4441-AB3F-E037295DB299} | c0a8-00f6-13923aef7ad-401e0987-3877-c | Hz-ID-17213 | FSD - Swiss Foundation for Mine Action | AF/1122/11585/BF0006 | 24650 | 70.6127 | 38.2893 | Open | UXO Only | UXO Only | BF |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {12D9B40F-62FC-4441-AB3F-E037295DB299} |  | High with Victim | High with Victims | Minimal | 280 | CHA | 2 |  |  | 2012-06-24 16:30 | No | Open
North East | Badakhshan | Shaki | Ghumay (1) | {12D9B40F-62FC-4441-AB3F-E037295DB299} | c0a8-00f6-13923f42193-632125d-3c78-c4 | Hz-ID-17220 | FSD - Swiss Foundation for Mine Action | AF/1122/11585/MF0012 | 5164 | 70.6094 | 38.2919 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {12D9B40F-62FC-4441-AB3F-E037295DB299} |  | High with Victim | High with Victims | Minimal | 42 | CHA | 2 |  |  | 2012-07-05 16:30 | No | Open
North East | Badakhshan | Shaki | Ghumay (1) | {12D9B40F-62FC-4441-AB3F-E037295DB299} | c0a8-00f6-13a4fba6f89-45913d9c-857-ca | Hz-ID-17216 | FSD - Swiss Foundation for Mine Action | AF/1110/11585/MF0013 | 7517 | 70.6093 | 38.2951 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {12D9B40F-62FC-4441-AB3F-E037295DB299} |  | High with Victim | High with Victims | Minimal | 42 | CHA | 2 |  |  | 2012-07-06 16:30 | No | Open
North East | Badakhshan | Shaki | Laron Ab Darrah | {391FD9B0-CD8F-4C4B-A347-250E302FCC3E} | c0a8-0057-12d93445508-7225823-418c-5f | MF-HT-1145 | HT - HALO TRUST | H/3547 | 44700 | 70.422 | 38.0856 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {391FD9B0-CD8F-4C4B-A347-250E302FCC3E} |  | Low | Critical Infrastracture | Minimal | 4 | CHA | 5 |  |  | 2007-06-01 | No | Open
North East | Badakhshan | Shaki | Mah-e-Now | {428B4AD0-B81D-470E-B8D3-8E88EC6DCACF} | c0a8-00f6-137d9d4ba70-ad75f4f2-1204-f | Hz-ID-17030 | FSD - Swiss Foundation for Mine Action | AF/1122/11624/MF0002 | 206725 | 70.6988 | 38.407 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {428B4AD0-B81D-470E-B8D3-8E88EC6DCACF} |  | Low | Agriculture Blocked | Minimal | 318 | CHA | 4 |  |  | 2011-12-07 16:30 | No | Open
North East | Badakhshan | Shaki | Mah-e-Now | {428B4AD0-B81D-470E-B8D3-8E88EC6DCACF} | c0a8-00f6-139238a2daa-e1c1e2fd-3574-e | Hz-ID-17210 | FSD - Swiss Foundation for Mine Action | AF/1122/11624/MF0010 | 7214 | 70.6952 | 38.4042 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {428B4AD0-B81D-470E-B8D3-8E88EC6DCACF} |  | Low | Agriculture Blocked | Minimal | 280 | CHA | 5 |  |  | 2012-07-02 16:30 | No | Open
North East | Badakhshan | Shaki | Mah-e-Now | {428B4AD0-B81D-470E-B8D3-8E88EC6DCACF} | c0a8-00f6-13923a6b9f6-e7adb5db-37b8-8 | Hz-ID-17212 | FSD - Swiss Foundation for Mine Action | AF/1122/11624/MF0007 | 17363 | 70.6984 | 38.4018 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {428B4AD0-B81D-470E-B8D3-8E88EC6DCACF} |  | Low | Agriculture Blocked | Minimal | 358 | CHA | 4 |  |  | 2012-07-01 16:30 | No | Open
North East | Badakhshan | Shaki | Mah-e-Now | {428B4AD0-B81D-470E-B8D3-8E88EC6DCACF} | c0a8-00f6-1392409cea2-9744888b-3d84-f | Hz-ID-17218 | FSD - Swiss Foundation for Mine Action | AF/1122/11624/MF0011 | 12679 | 70.7026 | 38.4055 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {428B4AD0-B81D-470E-B8D3-8E88EC6DCACF} |  | Low | Agriculture Blocked | Minimal | 78 | CHA | 4 |  |  | 2012-07-04 16:30 | No | Open
North East | Badakhshan | Shaki | Mah-e-Now | {428B4AD0-B81D-470E-B8D3-8E88EC6DCACF} | c0a8-00f6-139241f1b42-5c49ebf0-3eca-7 | Hz-ID-17214 | FSD - Swiss Foundation for Mine Action | AF/1122/11624/MF0009 | 28482 | 70.6984 | 38.3996 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {428B4AD0-B81D-470E-B8D3-8E88EC6DCACF} |  | Medium | Critical Infrastracture | Minimal | 280 | CHA | 3 |  |  | 2012-07-03 16:30 | No | Open
North East | Badakhshan | Shaki | Meymik | {1A3F38B2-75D9-4CA0-8FD1-B6A1DD7BDF04} | c0a8-00f6-13846a47daf-b5c2f29c-1f3e-9 | Hz-ID-17095 | FSD - Swiss Foundation for Mine Action | AF/1122/11575/MF0004 | 4224 | 70.5682 | 38.2433 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {1A3F38B2-75D9-4CA0-8FD1-B6A1DD7BDF04} |  | Medium | Agriculture Blocked | Minimal | 31 | CHA | 3 |  |  | 2011-12-07 16:30 | No | Open
North East | Badakhshan | Shaki | Meymik | {1A3F38B2-75D9-4CA0-8FD1-B6A1DD7BDF04} | c0a8-00f6-1384b0fd37b-9b72d6c0-2001-2 | Hz-ID-17096 | FSD - Swiss Foundation for Mine Action | AF/1122/11575/MF0005 | 47223 | 70.5662 | 38.2604 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {1A3F38B2-75D9-4CA0-8FD1-B6A1DD7BDF04} |  | Low | Critical Infrastracture | Minimal | 41 | CHA | 5 |  |  | 2011-12-07 16:30 | No | Open
North East | Badakhshan | Shaki | Meymik | {1A3F38B2-75D9-4CA0-8FD1-B6A1DD7BDF04} | c0a8-00f6-1384b1a9a9c-e1337c4-201b-98 | Hz-ID-17097 | FSD - Swiss Foundation for Mine Action | AF/1122/11575/MF0008 | 25625 | 70.5567 | 38.2475 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {1A3F38B2-75D9-4CA0-8FD1-B6A1DD7BDF04} |  | Medium | Critical Infrastracture | Minimal | 260 | CHA | 3 |  |  | 2011-12-07 16:30 | No | Open
North East | Badakhshan | Shaki | Shahri Sabz | {1986CA43-32CD-4CAA-9C29-208FF9F457DB} | c0a8-00f6-137d9da470c-31640ce2-13e6-9 | Hz-ID-17031 | FSD - Swiss Foundation for Mine Action | AF/1122/11567/MF0001 | 212391 | 70.5131 | 38.1341 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {1986CA43-32CD-4CAA-9C29-208FF9F457DB} |  | Low | Critical Infrastracture | Minimal | 282 | CHA | 4 |  |  | 2011-12-07 16:30 | No | Open
North East | Badakhshan | Shighnan | Baved (Deh Shar Sarcheshma) | {50D0DF00-2447-4739-B6B8-C2A655218F22} | c0a8-0057-12c3b99bc94-63edd54a-2afb5- | MF-HT-1121 | MCPA - Mine Clearance Planning Agency | AF/1109/30836/MF3626 | 11358 | 71.4176 | 37.5915 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {50D0DF00-2447-4739-B6B8-C2A655218F22} |  | Low | Critical Infrastracture | Minimal | 722 | CHA | 4 |  |  | 2007-08-01 | No | Open
North East | Badakhshan | Shighnan | Wer | {0EE34310-21D5-47CB-ABD4-A529649D24E0} | c0a8-0009-14037f98eaa-4c49be2b-2db8-1 | Hz-ID-18088 | MCPA - Mine Clearance Planning Agency | AF/1109/30851/MF0001 | 30100 | 71.2999 | 37.416 | Open | AP Only | AP Only | MineField |  | MBT Project-117/A | Badakhshan Demining Project-03/A |  |  |  |  | 1398 |  | {0EE34310-21D5-47CB-ABD4-A529649D24E0} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2013-06-27 16:30 | No | Open
North East | Badakhshan | Wakhan | Qazi Deh (1) | {3DF02E91-E1E5-454F-ABD4-850A51E6FD68} | c0a8-0057-12d5993bebf-171f872d-25d2-d | MF-HT-499 | HT - HALO TRUST | H/3550 | 33100 | 71.7764 | 36.5607 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {3DF02E91-E1E5-454F-ABD4-850A51E6FD68} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2007-07-01 | No | Open
North East | Badakhshan | Wakhan | Qazi Deh (1) | {3DF02E91-E1E5-454F-ABD4-850A51E6FD68} | c0a8-0057-12d59995bca-2cd8b03a-2671-4 | MF-HT-495 | HT - HALO TRUST | H/3548 | 20000 | 71.7772 | 36.5692 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {3DF02E91-E1E5-454F-ABD4-850A51E6FD68} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2007-07-01 | No | Open
North East | Badakhshan | Wakhan | Qazi Deh (1) | {3DF02E91-E1E5-454F-ABD4-850A51E6FD68} | c0a8-0057-12d599a8306-97485e9d-269a-1 | MF-HT-497 | HT - HALO TRUST | H/3549 | 15000 | 71.7772 | 36.5691 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {3DF02E91-E1E5-454F-ABD4-850A51E6FD68} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2007-07-01 | No | Open
North East | Badakhshan | Zebak | Deh-Gol | {FDBA81DA-8F2C-43BC-A968-3B1D49F15544} | c0a8-0057-12d55fed444-6cbfe0f5-1eee-b | MF-HT-502 | HT - HALO TRUST | H/3551 | 24000 | 71.4016 | 36.4186 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {FDBA81DA-8F2C-43BC-A968-3B1D49F15544} |  | Low | Agriculture Blocked | Minimal | 6 | CHA | 5 |  |  | 2007-07-01 | No | Open
North East | Badakhshan | Zebak | Deh-Gol | {FDBA81DA-8F2C-43BC-A968-3B1D49F15544} | c0a8-0057-12d598e4d75-f852a30-253c-ac | MF-HT-1149 | HT - HALO TRUST | H/3552 | 20000 | 71.4016 | 36.4186 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {FDBA81DA-8F2C-43BC-A968-3B1D49F15544} |  | Low | Agriculture Blocked | Minimal | 6 | CHA | 5 |  |  | 2007-07-01 | No | Open
North East | Badakhshan | Zebak | Redkhor Bala | {F70E0EB5-00B1-4F50-A822-CAE2ACC515E0} | c0a8-0057-12d55fdfcad-c75bb2d4-1edc-2 | MF-HT-1167 | HT - HALO TRUST | H/3559 | 30600 | 71.5106 | 36.5392 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {F70E0EB5-00B1-4F50-A822-CAE2ACC515E0} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2007-07-01 | No | Open
North East | Badakhshan | Zebak | Reed Khurd Bala | {3CB943C9-0603-4BA4-84D6-DE41B2C0D932} | c0a8-0057-12d55fd0a27-6b0daa6c-1ec7-2 | MF-HT-512 | HT - HALO TRUST | H/3558 | 58300 | 71.5237 | 36.5064 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {3CB943C9-0603-4BA4-84D6-DE41B2C0D932} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2007-07-01 | No | Open
North East | Badakhshan | Zebak | Sanglich | {40662DD4-E474-4C92-93E3-D9433F598BBB} | c0a8-0057-12c3b805abf-6a16053b-19ae4- | MF-HT-507 | HT - HALO TRUST | H/3556 | 60000 | 71.2052 | 36.1326 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {40662DD4-E474-4C92-93E3-D9433F598BBB} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 5 |  |  | 2007-07-01 | No | Open
North East | Badakhshan | Zebak | Sanglich | {40662DD4-E474-4C92-93E3-D9433F598BBB} | c0a8-0057-12c3babf43f-5419197-36135-7 | MF-HT-505 | HT - HALO TRUST | H/3555 | 30000 | 71.2531 | 36.1744 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {40662DD4-E474-4C92-93E3-D9433F598BBB} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 5 |  |  | 2007-07-01 | No | Open
North East | Badakhshan | Zebak | Sanglich | {40662DD4-E474-4C92-93E3-D9433F598BBB} | c0a8-0057-12c3baf2304-9c8869e2-3800b- | MF-NE-984 | HT - HALO TRUST | H/3554 | 60000 | 71.1627 | 36.2528 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {40662DD4-E474-4C92-93E3-D9433F598BBB} |  | High Requested | Resettlment/Local Request | Minimal | 6 | CHA | 5 |  |  | 2007-07-13 | No | Open
North East | Badakhshan | Zebak | Sanglich | {40662DD4-E474-4C92-93E3-D9433F598BBB} | c0a8-0057-12c3baf24b9-31b76365-38023- | MF-NE-983 | HT - HALO TRUST | H/3553 | 15000 | 71.1783 | 36.2698 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {40662DD4-E474-4C92-93E3-D9433F598BBB} |  | High Requested | Resettlment/Local Request | Minimal | 0 | CHA | 5 |  |  | 2007-07-12 | No | Open
North East | Badakhshan | Zebak | Sanglich | {40662DD4-E474-4C92-93E3-D9433F598BBB} | c0a8-0057-12c3baf26ac-5c53369d-3803b- | MF-NE-982 | HT - HALO TRUST | H/3557 | 10000 | 71.1505 | 36.2565 | Open | AP Only | AP Only | MineField |  | MBT Project-078 | Badakhshan Demining Project-02 |  |  |  |  | 1395 |  | {40662DD4-E474-4C92-93E3-D9433F598BBB} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 5 |  |  | 2007-07-16 | No | Open
North East | Baghlan | Andarab | Andarab(Banu) | {CCCF0067-A54C-4DC4-83D8-BFC775F5A7EC} | c0a8-0009-141a10aca42-dd903140-3b1c-9 | Hz-ID-18194 | HT - HALO TRUST | H/8593 | 13014 | 69.0336 | 35.6478 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {CCCF0067-A54C-4DC4-83D8-BFC775F5A7EC} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 2 |  |  | 2013-09-06 16:30 | No | Open
North East | Baghlan | Andarab | Andarab(Banu) | {CCCF0067-A54C-4DC4-83D8-BFC775F5A7EC} | c0a8-0009-141a1103eee-49f04c64-3b4b-e | Hz-ID-18196 | HT - HALO TRUST | H/8594 | 85973 | 69.0341 | 35.6499 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {CCCF0067-A54C-4DC4-83D8-BFC775F5A7EC} |  | High with Victim | High with Victims | Moderate | 5 | CHA | 2 |  |  | 2013-09-07 16:30 | No | Open
North East | Baghlan | Andarab | Andarab(Banu) | {CCCF0067-A54C-4DC4-83D8-BFC775F5A7EC} | c0a8-0057-12c3b7c3ba6-7762eaf-16c98-4 | MF-HQ-12168 | HT - HALO TRUST | H/2247 | 7000 | 69.3422 | 35.6689 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {CCCF0067-A54C-4DC4-83D8-BFC775F5A7EC} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 2 |  |  | 2009-09-12 | No | Open
North East | Baghlan | Andarab | Andarab(Banu) | {CCCF0067-A54C-4DC4-83D8-BFC775F5A7EC} | c0a8-0057-12c3b9241f9-e61105e9-260e5- | MF-HQ-10383 | HT - HALO TRUST | H/6103 | 7000 | 69.272 | 35.6377 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {CCCF0067-A54C-4DC4-83D8-BFC775F5A7EC} |  | High with Victim | High with Victims | Moderate | 64 | CHA | 2 |  |  | 2009-04-20 | No | Open
North East | Baghlan | Andarab | Andarab(Banu) | {CCCF0067-A54C-4DC4-83D8-BFC775F5A7EC} | c0a8-0057-12c3b9fad41-9822029a-2eba3- | MF-HQ-10387 | HT - HALO TRUST | H/2210 | 19500 | 69.252 | 35.6391 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {CCCF0067-A54C-4DC4-83D8-BFC775F5A7EC} |  | High with Victim | High with Victims | Moderate | 1040 | CHA | 2 |  |  | 2009-04-20 | No | Open
North East | Baghlan | Andarab | Arzangane Sufla | {9CB0746C-E062-4F7F-8626-112EE9D926AA} | c0a8-0057-12c3b92eb68-f375d620-267bb- | MF-HQ-11315 | HT - HALO TRUST | H/2205 | 675 | 69.2902 | 35.6431 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {9CB0746C-E062-4F7F-8626-112EE9D926AA} |  | Medium | Agriculture Blocked | Moderate | 46 | CHA | 3 |  |  | 2009-05-06 | No | Open
North East | Baghlan | Andarab | Arzangane Sufla | {9CB0746C-E062-4F7F-8626-112EE9D926AA} | c0a8-0057-12c3b99745f-6bfec449-2acbf- | MF-HQ-11316 | HT - HALO TRUST | H/2206 | 1115 | 69.2952 | 35.644 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {9CB0746C-E062-4F7F-8626-112EE9D926AA} |  | Medium | Agriculture Blocked | Moderate | 73 | CHA | 3 |  |  | 2009-05-05 | No | Open
North East | Baghlan | Andarab | Dane Khushdara | {C72E9AB9-023A-409C-815B-07DD958DDDA2} | c0a8-0057-12c3ba37102-5727fb02-3104b- | MF-HT-351 | HT - HALO TRUST | H/2219 | 27688 | 69.0717 | 35.6262 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {C72E9AB9-023A-409C-815B-07DD958DDDA2} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 1 |  |  | 2007-12-12 13:39 | No | Open
North East | Baghlan | Andarab | Dane Khushdara | {C72E9AB9-023A-409C-815B-07DD958DDDA2} | c0a8-0057-12c3bb18874-dff880f6-396cb- | MF-HT-359 | HT - HALO TRUST | H/2220 | 7100 | 69.1015 | 35.6229 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {C72E9AB9-023A-409C-815B-07DD958DDDA2} |  | High with Victim | High with Victims | Moderate | 873 | CHA | 2 |  |  | 2009-04-05 | No | Open
North East | Baghlan | Andarab | Darrahe Kanda | {9C408E53-0DF0-44A2-A3F1-8DEA8EC0786D} | c0a8-0057-12c3b697230-816754de-8c75-9 | MF-HQ-14530 | HT - HALO TRUST | H/6561 | 7050 | 68.9488 | 35.7499 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {9C408E53-0DF0-44A2-A3F1-8DEA8EC0786D} |  | Low | Agriculture Blocked | Moderate | 3 | CHA | 5 |  |  | 2010-03-15 | No | Open
North East | Baghlan | Andarab | Darrahe Kanda | {9C408E53-0DF0-44A2-A3F1-8DEA8EC0786D} | c0a8-0057-12c3b6de679-d67191f6-c291-c | BF-HQ-12105 | HT - HALO TRUST | B/2717 | 0 | 68.9399 | 35.7655 | Open | UXO Only | UXO Only | BF |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {9C408E53-0DF0-44A2-A3F1-8DEA8EC0786D} |  | Medium | Agriculture Blocked | Moderate | 0 | CHA | 3 |  |  | 2009-09-10 | No | Open
North East | Baghlan | Andarab | Darrahe Kanda | {9C408E53-0DF0-44A2-A3F1-8DEA8EC0786D} | c0a8-0057-12c3b6e3ef4-d3ddea13-c6b7-c | MF-HQ-14497 | HT - HALO TRUST | H/6562 | 1325 | 68.9481 | 35.7495 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {9C408E53-0DF0-44A2-A3F1-8DEA8EC0786D} |  | Low | Agriculture Blocked | Moderate | 3 | CHA | 5 |  |  | 2010-03-17 | No | Open
North East | Baghlan | Andarab | Darrahe Kanda | {9C408E53-0DF0-44A2-A3F1-8DEA8EC0786D} | c0a8-0057-12c3b7285f7-318f31c9-faa6-4 | MF-HQ-14510 | HT - HALO TRUST | H/6560 | 16700 | 68.9505 | 35.7518 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {9C408E53-0DF0-44A2-A3F1-8DEA8EC0786D} |  | Low | Agriculture Blocked | Moderate | 9 | CHA | 5 |  |  | 2010-03-16 | No | Open
North East | Baghlan | Andarab | Darrahe Kanda | {9C408E53-0DF0-44A2-A3F1-8DEA8EC0786D} | c0a8-0057-12c3b733e8a-d424c59f-10366- | MF-HQ-14496 | HT - HALO TRUST | H/6563 | 4100 | 68.9531 | 35.7473 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {9C408E53-0DF0-44A2-A3F1-8DEA8EC0786D} |  | Low | Agriculture Blocked | Moderate | 4 | CHA | 5 |  |  | 2010-03-17 | No | Open
North East | Baghlan | Andarab | Enal | {51B69FE1-5395-4D97-A8C4-9375A14C72FF} | c0a8-0009-142416349cb-8ddf145c-394b-5 | Hz-ID-18223 | HT - HALO TRUST | H/8595 | 54612 | 69.0456 | 35.6217 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {51B69FE1-5395-4D97-A8C4-9375A14C72FF} |  | Low | Agriculture Blocked | Moderate | 8 | CHA | 5 |  |  | 2013-10-08 16:30 | No | Open
North East | Baghlan | Andarab | Enal | {51B69FE1-5395-4D97-A8C4-9375A14C72FF} | c0a8-0057-12c3b6ad8ea-2ca7bd59-9d4c-a | MF-HT-1175 | HT - HALO TRUST | H/2215 | 70227 | 69.0455 | 35.626 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-120/A | Baghlan Demining Project-13/A | GAGP | Yes |  |  | 1392-1393 | HT | {51B69FE1-5395-4D97-A8C4-9375A14C72FF} |  |  |  | Moderate | 33 | CHA | 5 |  |  | 2009-04-06 | No | Planned
North East | Baghlan | Andarab | Fach | {18EC60A1-28E4-4952-B062-32700AD2F796} | c0a8-0057-12c3b832d23-86e2b485-1badb- | MF-HT-337 | HT - HALO TRUST | H/2217 | 1800 | 69.1336 | 35.6162 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {18EC60A1-28E4-4952-B062-32700AD2F796} |  | Medium | Agriculture Blocked | Moderate | 0 | CHA | 3 |  |  | 2007-12-12 11:11 | No | Open
North East | Baghlan | Andarab | Fach | {18EC60A1-28E4-4952-B062-32700AD2F796} | c0a8-0057-12c3b886314-da37a67c-1f5f1- | MF-HT-342 | HT - HALO TRUST | H/2218 | 4400 | 69.1358 | 35.6238 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {18EC60A1-28E4-4952-B062-32700AD2F796} |  | Medium | Agriculture Blocked | Moderate | 306 | CHA | 3 |  |  | 2007-12-12 12:32 | No | Open
North East | Baghlan | Andarab | Foj | {779BA467-5B2F-46BC-A4FB-B97C6DE00331} | c0a8-0009-141a10484b3-6895808f-3ad4-6 | Hz-ID-18192 | HT - HALO TRUST | H/8591 | 6154 | 69.1625 | 35.6179 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {779BA467-5B2F-46BC-A4FB-B97C6DE00331} |  | Medium | Critical Infrastracture | Moderate | 699 | CHA | 3 |  |  | 2013-09-02 16:30 | No | Open
North East | Baghlan | Andarab | Foj | {779BA467-5B2F-46BC-A4FB-B97C6DE00331} | c0a8-0009-141a14cc9d1-93194392-3def-6 | Hz-ID-18193 | HT - HALO TRUST | H/8592 | 6816 | 69.1491 | 35.6094 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {779BA467-5B2F-46BC-A4FB-B97C6DE00331} |  | Medium | Critical Infrastracture | Moderate | 0 | CHA | 3 |  |  | 2013-09-04 16:30 | No | Open
North East | Baghlan | Andarab | Foj | {779BA467-5B2F-46BC-A4FB-B97C6DE00331} | c0a8-0057-12c3b70ea77-b43d18d4-e73b-4 | MF-HT-143 | HT - HALO TRUST | H/2216 | 215 | 69.1601 | 35.619 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {779BA467-5B2F-46BC-A4FB-B97C6DE00331} |  | Medium | Water Blocked | Moderate | 699 | CHA | 3 |  |  | 2007-10-01 | No | Open
North East | Baghlan | Andarab | Garmakcheshma | {11557B65-EB3E-4FD7-A145-C9BC1C6079A1} | c0a8-0057-12c3b7946b5-cf5bd58d-14a81- | MF-HT-1186 | HT - HALO TRUST | H/3033 | 3960 | 69.0806 | 35.6097 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {11557B65-EB3E-4FD7-A145-C9BC1C6079A1} |  | Medium | Agriculture Blocked | Moderate | 68 | CHA | 3 |  |  | 2009-04-06 | No | Open
North East | Baghlan | Andarab | Kaftarkhana | {E7B222D8-E4D7-445B-B398-DA13E68080AA} | c0a8-0057-12c3b6f29bd-dd052693-d1e7-6 | MF-HT-1201 | HT - HALO TRUST | H/3988 | 400 | 69.1538 | 35.6117 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {E7B222D8-E4D7-445B-B398-DA13E68080AA} |  | Medium | Critical Infrastracture | Moderate | 157 | CHA | 3 |  |  | 2007-10-01 | No | Open
North East | Baghlan | Andarab | Kaftarkhana | {E7B222D8-E4D7-445B-B398-DA13E68080AA} | c0a8-0057-12c3b7a5a61-ab6a992f-156f1- | MF-HT-1220 | HT - HALO TRUST | H/3987 | 85 | 69.1404 | 35.6288 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {E7B222D8-E4D7-445B-B398-DA13E68080AA} |  | Medium | Critical Infrastracture | Moderate | 165 | CHA | 3 |  |  | 2007-09-01 | No | Open
North East | Baghlan | Andarab | Kaftarkhana | {E7B222D8-E4D7-445B-B398-DA13E68080AA} | c0a8-0057-12c3ba55708-e3557d9c-322f5- | MF-HQ-12978 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1307/13572/MF0001 | 100 | 69.1404 | 35.6288 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {E7B222D8-E4D7-445B-B398-DA13E68080AA} |  | Medium | Critical Infrastracture | Moderate | 165 | SHA | 3 |  |  | 2009-10-05 | No | Open
North East | Baghlan | Andarab | Khazena | {E1FEF0FB-66CE-4668-B572-1B33CD6108FF} | c0a8-0057-12c3b6ee9c1-17402a1f-ceed-7 | MF-HQ-14059 | HT - HALO TRUST | H/2226 | 20000 | 69.0423 | 35.784 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {E1FEF0FB-66CE-4668-B572-1B33CD6108FF} |  | Low | Agriculture Blocked | Moderate | 15 | CHA | 5 |  |  | 2002-09-19 | No | Open
North East | Baghlan | Andarab | Khazena | {E1FEF0FB-66CE-4668-B572-1B33CD6108FF} | c0a8-0057-12c3b7abbf0-ae5a812e-15b60- | MF-HQ-14058 | HT - HALO TRUST | H/2224 | 2000 | 69.1097 | 35.8128 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {E1FEF0FB-66CE-4668-B572-1B33CD6108FF} |  | Low | Agriculture Blocked | Moderate | 122 | CHA | 5 |  |  | 2002-09-13 | No | Open
North East | Baghlan | Andarab | Khej | {FF3C7A00-D8E1-446D-B401-C80D552D43C4} | c0a8-0057-12c3ba02e61-fc32edc2-2f0d3- | MF-HQ-11303 | HT - HALO TRUST | H/6114 | 69080 | 69.3751 | 35.6245 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {FF3C7A00-D8E1-446D-B401-C80D552D43C4} |  | Low | Agriculture Blocked | Moderate | 7 | CHA | 5 |  |  | 2009-05-02 | No | Open
North East | Baghlan | Andarab | Kohi Matran | {46D069D6-42B8-46BA-8771-90A69EF04361} | c0a8-0057-12c3b785a95-d4b42037-13fc2- | MF-HQ-12167 | HT - HALO TRUST | H/2227 | 22596 | 68.9837 | 35.7128 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {46D069D6-42B8-46BA-8771-90A69EF04361} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2009-09-12 | No | Open
North East | Baghlan | Andarab | Layn | {2FE01315-AB64-40A9-98E2-62C62A2B51B0} | c0a8-0057-12c3b90cffa-a32ca49a-251e3- | MF-HQ-11309 | HT - HALO TRUST | H/2211 | 5100 | 69.278 | 35.6514 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {2FE01315-AB64-40A9-98E2-62C62A2B51B0} |  | Low | Agriculture Blocked | Moderate | 202 | CHA | 4 |  |  | 2009-05-08 | No | Open
North East | Baghlan | Andarab | Layn | {2FE01315-AB64-40A9-98E2-62C62A2B51B0} | c0a8-0057-12c3bb79273-fac6035e-3cee8- | MF-HQ-11307 | HT - HALO TRUST | H/2209 | 40000 | 69.2712 | 35.6548 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {2FE01315-AB64-40A9-98E2-62C62A2B51B0} |  | Low | Agriculture Blocked | Moderate | 35 | CHA | 5 |  |  | 2009-05-08 | No | Open
North East | Baghlan | Andarab | Mirwa | {A9BC5924-D069-4D0E-A8CE-8DE9ED05E37E} | c0a8-0057-12c3b865ca3-27dcf7cd-1df56- | MF-HQ-11304 | HT - HALO TRUST | H/2230 | 333 | 69.2994 | 35.6229 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {A9BC5924-D069-4D0E-A8CE-8DE9ED05E37E} |  | Medium | Critical Infrastracture | Moderate | 20 | CHA | 3 |  |  | 2009-05-01 | No | Open
North East | Baghlan | Andarab | Mirwa | {A9BC5924-D069-4D0E-A8CE-8DE9ED05E37E} | c0a8-0057-12c3b981a17-2a96decb-29e66- | MF-HQ-11302 | HT - HALO TRUST | H/6113 | 181 | 69.3017 | 35.6295 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {A9BC5924-D069-4D0E-A8CE-8DE9ED05E37E} |  | Medium | Agriculture Blocked | Moderate | 20 | CHA | 3 |  |  | 2009-05-01 | No | Open
North East | Baghlan | Andarab | Pulkhah | {22804EF7-571A-4A5E-866E-9E69B48A2E98} | c0a8-0057-12c3b86b8b6-52a58cc8-1e30f- | MF-HQ-10445 | HT - HALO TRUST | H/2238 | 23000 | 69.2141 | 35.6363 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {22804EF7-571A-4A5E-866E-9E69B48A2E98} |  | Low | Agriculture Blocked | Moderate | 8 | CHA | 5 |  |  | 2009-04-04 | No | Open
North East | Baghlan | Andarab | Qeshnabad | {18576748-39AC-4AC1-8276-2D8A07F9035A} | c0a8-0057-12c3b828967-9b00d1b9-1b3ba- | MF-HQ-10444 | HT - HALO TRUST | H/2237 | 600 | 69.2046 | 35.618 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {18576748-39AC-4AC1-8276-2D8A07F9035A} |  | Medium | Agriculture Blocked | Moderate | 142 | CHA | 3 |  |  | 2009-04-01 | No | Open
North East | Baghlan | Andarab | Qeshnabad | {18576748-39AC-4AC1-8276-2D8A07F9035A} | c0a8-0057-12c3b828b3b-3cf4f910-1b3cc- | MF-HQ-10393 | HT - HALO TRUST | H/6037 | 280 | 69.2005 | 35.5976 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {18576748-39AC-4AC1-8276-2D8A07F9035A} |  | Medium | Agriculture Blocked | Moderate | 124 | CHA | 3 |  |  | 2009-04-02 | No | Open
North East | Baghlan | Andarab | Qeshnabad | {18576748-39AC-4AC1-8276-2D8A07F9035A} | c0a8-008e-132c955c46e-1e2b5779-2fd4-7 | BF-HQ-12145 | HT - HALO TRUST | B/2719 | 0 | 69.2166 | 35.6197 | Open | UXO Only | UXO Only | BF |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {18576748-39AC-4AC1-8276-2D8A07F9035A} |  | Medium | Water Blocked | Moderate | 0 | CHA | 3 |  |  | 2009-04-01 | No | Open
North East | Baghlan | Andarab | Ronu | {DF3ABBCF-F13A-4B7B-9674-1FE57E9B3EAF} | c0a8-0057-12c3b89f3e9-90c7a416-2072e- | MF-HQ-10443 | HT - HALO TRUST | H/2242 | 9500 | 69.2852 | 35.6334 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {DF3ABBCF-F13A-4B7B-9674-1FE57E9B3EAF} |  | Medium | Critical Infrastracture | Moderate | 28 | CHA | 3 |  |  | 2009-04-16 | No | Open
North East | Baghlan | Andarab | Sherqalaq | {82F5EB89-4CB7-4E47-8CF5-E9DD83C27195} | c0a8-0057-12c3b84d050-ab469dec-1ce07- | MF-NE-506 | HT - HALO TRUST | H/4142 | 30000 | 68.9729 | 35.7709 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {82F5EB89-4CB7-4E47-8CF5-E9DD83C27195} |  | Low | Agriculture Blocked | Moderate | 157 | CHA | 4 |  |  | 2008-04-20 | No | Open
North East | Baghlan | Andarab | Sherqalaq | {82F5EB89-4CB7-4E47-8CF5-E9DD83C27195} | c0a8-0057-12c3b8c9002-86fecab4-2246c- | MF-NE-509 | HT - HALO TRUST | H/4143 | 115000 | 68.9729 | 35.7709 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {82F5EB89-4CB7-4E47-8CF5-E9DD83C27195} |  | Low | Agriculture Blocked | Moderate | 567 | CHA | 4 |  |  | 2008-04-20 | No | Open
North East | Baghlan | Andarab | Spech | {5EF97CE7-D721-4073-9AEB-1400AF1F72A2} | c0a8-0009-142e1afb129-b598ccb6-585e-f | Hz-ID-18263 | HT - HALO TRUST | H/8596 | 20610 | 68.9465 | 35.6859 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {5EF97CE7-D721-4073-9AEB-1400AF1F72A2} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2013-11-18 16:30 | No | Open
North East | Baghlan | Andarab | Spech | {5EF97CE7-D721-4073-9AEB-1400AF1F72A2} | c0a8-0009-142e55c0c69-d02ea43a-6694-1 | Hz-ID-18264 | HT - HALO TRUST | H/8597 | 13784 | 68.9476 | 35.6884 | Open | AP Only | AP Only | MineField |  | MBT Project-149 | Baghlan Demining Project-08 |  |  |  |  | 1400 |  | {5EF97CE7-D721-4073-9AEB-1400AF1F72A2} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2013-11-19 16:30 | No | Open
North East | Baghlan | Andarab | Spech | {5EF97CE7-D721-4073-9AEB-1400AF1F72A2} | c0a8-0057-12c3b6a3186-81183497-956c-7 | MF-HQ-12239 | HT - HALO TRUST | H/2228 | 67019 | 68.9562 | 35.6882 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {5EF97CE7-D721-4073-9AEB-1400AF1F72A2} |  | Medium | Critical Infrastracture | Moderate | 1014 | CHA | 2 |  |  | 2009-09-09 | No | Open
North East | Baghlan | Andarab | Spech | {5EF97CE7-D721-4073-9AEB-1400AF1F72A2} | c0a8-0057-12c3b8ec35c-c61e05eb-23c9b- | MF-HQ-12353 | HT - HALO TRUST | H/2229 | 81990 | 68.9434 | 35.7576 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {5EF97CE7-D721-4073-9AEB-1400AF1F72A2} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 2 |  |  | 2002-09-19 16:30 | No | Open
North East | Baghlan | Baghlani Jadid | Badal Mast | {B3C61919-92D0-4552-BA90-51941DF3A1AD} | c0a8-0009-14375990d0e-3247e8d6-25b4-d | Hz-ID-18351 | MCPA - Mine Clearance Planning Agency | AF/1301/13013/MF0040 | 13901 | 68.8124 | 36.089 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {B3C61919-92D0-4552-BA90-51941DF3A1AD} |  | Low | Agriculture Blocked | Substantial | 13 | CHA | 5 |  |  | 2013-11-24 16:30 | No | Open
North East | Baghlan | Baghlani Jadid | Baghlan | {477D7F36-2CC5-4474-A232-B59D50E23E4A} | c0a8-0057-12c3b87e677-5e29968b-1f08f- | MF-NE-940 | MCPA - Mine Clearance Planning Agency | AF/1312/12974/MF5118 | 19000 | 68.6628 | 36.1155 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {477D7F36-2CC5-4474-A232-B59D50E23E4A} | Planned Agency Removed | High with Victim | High with Victims | Substantial | 117 | CHA | 2 |  |  | 2008-09-04 | No | Open
North East | Baghlan | Baghlani Jadid | Baghlan | {477D7F36-2CC5-4474-A232-B59D50E23E4A} | c0a8-008e-1306d45939d-de5a067d-19-431 | MF-NE-941 | MCPA - Mine Clearance Planning Agency | AF/1312/12974/MF5117 | 7360 | 68.7159 | 36.143 | Open | AT Only | AT Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {477D7F36-2CC5-4474-A232-B59D50E23E4A} |  | High with Victim | High with Victims | Substantial | 846 | CHA | 2 |  |  | 2008-09-03 | No | Open
North East | Baghlan | Baghlani Jadid | Baghlani Jadid | {55BDCD44-E378-45CF-B647-DEBE033E3F1F} | c0a8-0057-12c3b735248-4cf0b1a7-10455- | BF-HQ-11612 | MCPA - Mine Clearance Planning Agency | AF/1312/31917/BF2480 | 2500 | 68.689 | 36.1281 | Open | UXO Only | UXO Only | BF |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {55BDCD44-E378-45CF-B647-DEBE033E3F1F} |  | High with Victim | High with Victims | Substantial | 396 | CHA | 1 |  |  | 2008-09-01 | No | Open
North East | Baghlan | Baghlani Jadid | Gaz | {58654A9D-1450-421A-808F-79E2B0EF382C} | c0a8-0009-14491018095-ddcf4cff-764-8c | Hz-ID-18396 | MDC - Mine Detection and Dog Center | AF/1312/00262/MF0043 | 5491 | 68.8305 | 36.0964 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {58654A9D-1450-421A-808F-79E2B0EF382C} |  | High with Victim | High with Victims | Substantial | 4 | CHA | 2 |  |  | 2013-12-16 16:30 | No | Open
North East | Baghlan | Baghlani Jadid | Gaz | {58654A9D-1450-421A-808F-79E2B0EF382C} | c0a8-0057-12c3b9e7e0b-e8e85eae-2e022- | MF-NE-932 | MCPA - Mine Clearance Planning Agency | AF/1312/00262/MF5147 | 33000 | 68.8242 | 36.0852 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-150/A | Baghlan Demining Project-21/A | B-Germany | Yes |  |  | 1392 | MDC | {58654A9D-1450-421A-808F-79E2B0EF382C} |  |  |  | Substantial | 0 | CHA | 2 |  |  | 2008-10-07 | No | Complete
North East | Baghlan | Baghlani Jadid | Gaz | {58654A9D-1450-421A-808F-79E2B0EF382C} | c0a8-0057-12c3b9e80f8-61c47a52-2e038- | MF-NE-929 | MCPA - Mine Clearance Planning Agency | AF/1312/00262/MF2488 | 32000 | 68.8278 | 36.0941 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-150/A | Baghlan Demining Project-21/A | B-Germany | Yes |  |  | 1392 | MDC | {58654A9D-1450-421A-808F-79E2B0EF382C} |  |  |  | Substantial | 2 | CHA | 2 |  |  | 2008-10-06 | No | Complete
North East | Baghlan | Baghlani Jadid | Gaz | {58654A9D-1450-421A-808F-79E2B0EF382C} | c0a8-0057-12c3b9e82cc-7b61d63d-2e057- | MF-NE-935 | MCPA - Mine Clearance Planning Agency | AF/1312/00262/MF5144 | 45000 | 68.8263 | 36.0914 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-150/A | Baghlan Demining Project-21/A | B-Germany | Yes |  |  | 1392 | MDC | {58654A9D-1450-421A-808F-79E2B0EF382C} |  |  |  | Substantial | 2 | CHA | 2 |  |  | 2008-10-06 | No | Complete
North East | Baghlan | Baghlani Jadid | Gaz | {58654A9D-1450-421A-808F-79E2B0EF382C} | c0a8-0057-12c3b9e84bf-35a1e27d-2e06d- | MF-NE-931 | MCPA - Mine Clearance Planning Agency | AF/1312/00262/MF5148 | 45000 | 68.8227 | 36.0836 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-150/A | Baghlan Demining Project-21/A | B-Germany | Yes |  |  | 1392 | MDC | {58654A9D-1450-421A-808F-79E2B0EF382C} |  |  |  | Substantial | 0 | CHA | 2 |  |  | 2008-10-07 | No | Complete
North East | Baghlan | Baghlani Jadid | Gaz | {58654A9D-1450-421A-808F-79E2B0EF382C} | c0a8-0057-12c3b9e871f-292991c2-2e085- | MF-NE-936 | MCPA - Mine Clearance Planning Agency | AF/1312/00262/MF5143 | 37200 | 68.8272 | 36.094 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-150/A | Baghlan Demining Project-21/A | B-Germany | Yes |  |  | 1392 | MDC | {58654A9D-1450-421A-808F-79E2B0EF382C} |  |  |  | Substantial | 2 | CHA | 2 |  |  | 2008-10-06 | No | Complete
North East | Baghlan | Baghlani Jadid | Gaz | {58654A9D-1450-421A-808F-79E2B0EF382C} | c0a8-0057-12c3b9e88e4-df3e26ac-2e09e- | MF-NE-930 | MCPA - Mine Clearance Planning Agency | AF/1312/00262/MF5149 | 53000 | 68.8207 | 36.0831 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {58654A9D-1450-421A-808F-79E2B0EF382C} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 2 |  |  | 2008-10-07 | No | Open
North East | Baghlan | Baghlani Jadid | Gaz | {58654A9D-1450-421A-808F-79E2B0EF382C} | c0a8-0057-12c3b9e8ad7-f7a291f4-2e0b2- | MF-NE-933 | MCPA - Mine Clearance Planning Agency | AF/1312/00262/MF5146 | 39000 | 68.8275 | 36.0893 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {58654A9D-1450-421A-808F-79E2B0EF382C} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 2 |  |  | 2008-10-06 | No | Open
North East | Baghlan | Baghlani Jadid | Gaz | {58654A9D-1450-421A-808F-79E2B0EF382C} | c0a8-00c9-12fdda0f00d-36c5b9b2-805-8c | MF-NE-934 | MCPA - Mine Clearance Planning Agency | AF/1312/00262/MF5145 | 37600 | 68.8263 | 36.0914 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {58654A9D-1450-421A-808F-79E2B0EF382C} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 2 |  |  | 2008-10-06 | No | Open
North East | Baghlan | Baghlani Jadid | Jelaw Gir (2) | {E2CA55FA-9789-412B-BD08-98DA3C8CA84F} | c0a8-0057-12c3b7362bc-1f606ae0-1050c- | MF-HQ-11624 | MCPA - Mine Clearance Planning Agency | AF/1405/13062/MF4760 | 8000 | 68.9478 | 36.4275 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {E2CA55FA-9789-412B-BD08-98DA3C8CA84F} |  | High Requested | Resettlment/Local Request | Substantial | 3 | CHA | 5 |  |  | 2008-05-17 | No | Open
North East | Baghlan | Baghlani Jadid | Kakamangal | {AFE4F6AE-1286-4180-9ABF-D952F87FE442} | c0a8-0009-142e54c8353-c1bf1386-6391-5 | Hz-ID-18232 | MCPA - Mine Clearance Planning Agency | AF/1312/00534/MF0036 | 10100 | 68.8071 | 36.2335 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {AFE4F6AE-1286-4180-9ABF-D952F87FE442} |  | Medium | Critical Infrastracture | Substantial | 613 | CHA | 3 |  |  | 2013-11-05 16:30 | No | Open
North East | Baghlan | Baghlani Jadid | Kakamangal | {AFE4F6AE-1286-4180-9ABF-D952F87FE442} | c0a8-0057-12c3b7db3be-9bc8fe44-17d62- | MF-NE-863 | MCPA - Mine Clearance Planning Agency | AF/1312/00534/MF5245 | 770 | 68.8074 | 36.2327 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {AFE4F6AE-1286-4180-9ABF-D952F87FE442} |  | High | Water Blocked | Substantial | 400 | CHA | 3 |  |  | 2008-10-18 | No | Open
North East | Baghlan | Baghlani Jadid | Khaja Ston | {52FFC896-E7D6-49A2-8BA8-F87B9E701FDF} | c0a8-0057-12c3b739aeb-76c1d2f9-107c4- | BF-HQ-11602 | HT - HALO TRUST | B/2481 |  | 68.5107 | 36.1866 | Open | UXO Only | UXO Only | BF |  | MBT Project-248 | Baghlan Demining Project-4 (AT) |  |  |  |  | 1400 |  | {52FFC896-E7D6-49A2-8BA8-F87B9E701FDF} |  | Low | Infrastructure | Substantial | 0 | CHA | 5 |  |  | 2008-09-22 | No | Open
North East | Baghlan | Baghlani Jadid | Khaja Ston | {52FFC896-E7D6-49A2-8BA8-F87B9E701FDF} | c0a8-0057-12c3b8e3cb1-921c9e46-2371a- | MF-NE-899 | MCPA - Mine Clearance Planning Agency | AF/1312/00246/MF5122 | 54000 | 68.509 | 36.1981 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {52FFC896-E7D6-49A2-8BA8-F87B9E701FDF} |  | Low | Agriculture Blocked | Substantial | 13 | CHA | 5 |  |  | 2008-09-06 | No | Open
North East | Baghlan | Baghlani Jadid | Khaja Ston | {52FFC896-E7D6-49A2-8BA8-F87B9E701FDF} | c0a8-0057-12c3b987d98-1fe2e680-2a24e- | MF-NE-900 | MCPA - Mine Clearance Planning Agency | AF/1312/00246/MF2261 | 51000 | 68.5019 | 36.1949 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {52FFC896-E7D6-49A2-8BA8-F87B9E701FDF} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-09-11 | No | Open
North East | Baghlan | Baghlani Jadid | Khugak | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} | c0a8-0057-12c3b7c7692-a8e12182-16f1b- | MF-NE-884 | MCPA - Mine Clearance Planning Agency | AF/1312/00219/MF2262 | 32000 | 68.5826 | 36.1498 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-09-06 | No | Open
North East | Baghlan | Baghlani Jadid | Khugak | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} | c0a8-0057-12c3b83be1a-9545a330-1c173- | MF-NE-891 | MCPA - Mine Clearance Planning Agency | AF/1312/00219/MF5128 | 36700 | 68.5702 | 36.1551 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2008-09-09 | No | Open
North East | Baghlan | Baghlani Jadid | Khugak | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} | c0a8-0057-12c3ba86a90-f705545d-340f7- | MF-NE-894 | MCPA - Mine Clearance Planning Agency | AF/1312/00219/MF5130 | 60000 | 68.568 | 36.1523 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} |  | Low | Agriculture Blocked | Substantial | 12 | CHA | 5 |  |  | 2008-09-10 | No | Open
North East | Baghlan | Baghlani Jadid | Khugak | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} | c0a8-0057-12c3ba86d00-6cf71d09-3410b- | MF-NE-895 | MCPA - Mine Clearance Planning Agency | AF/1312/00219/MF5131 | 61000 | 68.568 | 36.1523 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} |  | Low | Agriculture Blocked | Substantial | 16 | CHA | 5 |  |  | 2008-09-10 | No | Open
North East | Baghlan | Baghlani Jadid | Khugak | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} | c0a8-0057-12c3ba8700c-b22ea7f7-34122- | MF-NE-897 | MCPA - Mine Clearance Planning Agency | AF/1312/00219/MF5129 | 57000 | 68.568 | 36.1523 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} |  | Low | Agriculture Blocked | Substantial | 21 | CHA | 5 |  |  | 2008-09-10 | No | Open
North East | Baghlan | Baghlani Jadid | Khugak | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} | c0a8-0057-12c3bb27f00-9ec97863-3a015- | MF-NE-889 | MCPA - Mine Clearance Planning Agency | AF/1312/00219/MF5124 | 7000 | 68.5853 | 36.1459 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-09-06 | No | Open
North East | Baghlan | Baghlani Jadid | Khugak | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} | c0a8-00c9-12fdda2c685-5e3716e0-8c0-a9 | MF-NE-882 | MCPA - Mine Clearance Planning Agency | AF/1312/00219/MF5126 | 44000 | 68.5829 | 36.1345 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2008-09-07 | No | Open
North East | Baghlan | Baghlani Jadid | Khugak | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} | c0a8-00c9-12fdda44e32-6c434b7b-8db-8c | MF-NE-887 | MCPA - Mine Clearance Planning Agency | AF/1312/00219/MF5125 | 43000 | 68.5992 | 36.1296 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-09-07 | No | Open
North East | Baghlan | Baghlani Jadid | Khugak | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} | c0a8-00c9-12fdda5b4aa-85c02e66-8f8-39 | MF-NE-885 | MCPA - Mine Clearance Planning Agency | AF/1312/00219/MF5123 | 12000 | 68.5852 | 36.1467 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-09-06 | No | Open
North East | Baghlan | Baghlani Jadid | Khugak | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} | c0a8-00c9-12fdda75584-c575ad38-911-95 | MF-NE-892 | MCPA - Mine Clearance Planning Agency | AF/1312/00219/MF5127 | 20000 | 68.5687 | 36.1576 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {05490DA7-E5A4-4E33-BEF9-C9AF091001E3} |  | Low | Agriculture Blocked | Substantial | 19 | CHA | 5 |  |  | 2008-09-08 | No | Open
North East | Baghlan | Baghlani Jadid | Qandahari (4) | {22916443-487C-4AE2-986A-2514C31492BE} | c0a8-0009-14375a82ebb-2df0043b-263d-1 | Hz-ID-18352 | MCPA - Mine Clearance Planning Agency | AF/1312/12992/MF0041 | 7500 | 68.7208 | 36.3878 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {22916443-487C-4AE2-986A-2514C31492BE} |  | Medium | Water Blocked | Substantial | 352 | CHA | 3 |  |  | 2013-11-14 16:30 | No | Open
North East | Baghlan | Baghlani Jadid | Qara Batur Qeshlaq | {F2EA382E-E92C-4337-B9BE-4B69F94CD7C2} | c0a8-0009-14375e2f9fd-bc19dc8a-290d-2 | Hz-ID-18354 | MCPA - Mine Clearance Planning Agency | AF/1404/14099/MF0042 | 200000 | 68.6546 | 36.514 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {F2EA382E-E92C-4337-B9BE-4B69F94CD7C2} |  | Medium | Critical Infrastracture | Substantial | 481 | CHA | 3 |  |  | 2013-11-27 16:30 | No | Open
North East | Baghlan | Baghlani Jadid | Qaysar Khel | {4908A2E5-A23B-4E8D-BC67-9D31325B9C27} | c0a8-0057-12c3bad3782-76dca4f2-36dc6- | MF-NE-928 | MCPA - Mine Clearance Planning Agency | AF/1307/12984/MF2264 | 868 | 68.6839 | 36.1404 | Open | AP Only | AP Only | MineField | Blank | MBT Project-248 | Baghlan Demining Project-4 (AT) |  | No | 2010-06-03 | 2010-06-07 | 1400 | None | {4908A2E5-A23B-4E8D-BC67-9D31325B9C27} | Planned for EOD Teams | Low | Small Hazards | Substantial | 0 | CHA | 5 |  |  | 2008-09-02 | No | Open
North East | Baghlan | Baghlani Jadid | Rafak | {8D685DD4-7553-492D-A01C-5782772A2184} | c0a8-0057-12c3bb1d52c-837c01b7-399b8- | MF-NE-902 | MCPA - Mine Clearance Planning Agency | AF/1312/00428/MF5287 | 58500 | 68.8512 | 36.0574 | Open | AP Only | AP Only | MineField |  | MBT Project-248 | Baghlan Demining Project-4 (AT) |  |  |  |  | 1400 |  | {8D685DD4-7553-492D-A01C-5782772A2184} | , | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-10-10 | No | Open
North East | Baghlan | Baghlani Jadid | Rafak | {8D685DD4-7553-492D-A01C-5782772A2184} | c0a8-0057-12c3bb1dde3-245598c0-39a1b- | MF-NE-906 | MCPA - Mine Clearance Planning Agency | AF/1312/00428/MF5291 | 40000 | 68.8557 | 36.0478 | Open | AP Only | AP Only | MineField |  | MBT Project-248 | Baghlan Demining Project-4 (AT) |  |  |  |  | 1400 |  | {8D685DD4-7553-492D-A01C-5782772A2184} | , | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-10 | No | Open
North East | Baghlan | Baghlani Jadid | Rafak | {8D685DD4-7553-492D-A01C-5782772A2184} | c0a8-0057-12c3bb1dfe5-fe94e38a-39a31- | MF-NE-905 | MCPA - Mine Clearance Planning Agency | AF/1312/00428/MF5290 | 52000 | 68.8544 | 36.0502 | Open | AP Only | AP Only | MineField |  | MBT Project-248 | Baghlan Demining Project-4 (AT) |  |  |  |  | 1400 |  | {8D685DD4-7553-492D-A01C-5782772A2184} | , | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-10 | No | Open
North East | Baghlan | Baghlani Jadid | Rafak | {8D685DD4-7553-492D-A01C-5782772A2184} | c0a8-0057-12c3bb1e88c-b141e8a-39a8c-f | MF-NE-904 | MCPA - Mine Clearance Planning Agency | AF/1312/00428/MF5289 | 52000 | 68.853 | 36.0528 | Open | AP Only | AP Only | MineField |  | MBT Project-248 | Baghlan Demining Project-4 (AT) |  |  |  |  | 1400 |  | {8D685DD4-7553-492D-A01C-5782772A2184} | , | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-10 | No | Open
North East | Baghlan | Baghlani Jadid | Rafak | {8D685DD4-7553-492D-A01C-5782772A2184} | c0a8-0057-12c3bb1f105-c874d1ed-39aeb- | MF-NE-903 | MCPA - Mine Clearance Planning Agency | AF/1312/00428/MF5288 | 46000 | 68.8524 | 36.0551 | Open | AP Only | AP Only | MineField |  | MBT Project-248 | Baghlan Demining Project-4 (AT) |  |  |  |  | 1400 |  | {8D685DD4-7553-492D-A01C-5782772A2184} | , | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-10-10 | No | Open
North East | Baghlan | Baghlani Jadid | Rafak | {8D685DD4-7553-492D-A01C-5782772A2184} | c0a8-0057-12c3bb1f327-31d6b598-39b01- | MF-NE-901 | MCPA - Mine Clearance Planning Agency | AF/1312/00428/MF5286 | 45000 | 68.8489 | 36.06 | Open | AP Only | AP Only | MineField |  | MBT Project-248 | Baghlan Demining Project-4 (AT) |  |  |  |  | 1400 |  | {8D685DD4-7553-492D-A01C-5782772A2184} | , | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-10-10 | No | Open
North East | Baghlan | Baghlani Jadid | Shekh Jalal | {8B491B5A-EEAE-4045-939A-868EDD84CB5C} | c0a8-0009-142e53be5e3-8dfd855-60ef-d0 | Hz-ID-18234 | MCPA - Mine Clearance Planning Agency | AF/1301/13439/MF0038 | 3042 | 68.8707 | 36.1021 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {8B491B5A-EEAE-4045-939A-868EDD84CB5C} |  | High with Victim | High with Victims | Substantial | 286 | CHA | 2 |  |  | 2013-11-10 16:30 | No | Open
North East | Baghlan | Baghlani Jadid | Shekh Jalal | {8B491B5A-EEAE-4045-939A-868EDD84CB5C} | c0a8-0009-142e54b12d6-246d342d-6374-d | Hz-ID-18233 | MCPA - Mine Clearance Planning Agency | AF/1301/13439/MF0037 | 16881 | 68.8634 | 36.1083 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {8B491B5A-EEAE-4045-939A-868EDD84CB5C} |  | High with Victim | High with Victims | Substantial | 118 | CHA | 2 |  |  | 2013-11-09 16:30 | No | Open
North East | Baghlan | Baghlani Jadid | Shekh Jalal | {8B491B5A-EEAE-4045-939A-868EDD84CB5C} | c0a8-0057-12c3ba1e8a5-849ef44f-301ca- | MF-NE-923 | MCPA - Mine Clearance Planning Agency | AF/1312/13439/MF2260 | 30000 | 68.8475 | 36.1177 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {8B491B5A-EEAE-4045-939A-868EDD84CB5C} | , | High with Victim | High with Victims | Substantial | 47 | CHA | 2 |  |  | 2008-09-18 | No | Open
North East | Baghlan | Baghlani Jadid | Shekh Jalal | {8B491B5A-EEAE-4045-939A-868EDD84CB5C} | c0a8-00c9-12fdda87916-37863142-92d-b6 | MF-NE-919 | MCPA - Mine Clearance Planning Agency | AF/1312/13439/MF5136 | 24000 | 68.8643 | 36.1296 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {8B491B5A-EEAE-4045-939A-868EDD84CB5C} | , | High with Victim | High with Victims | Substantial | 0 | CHA | 2 |  |  | 2008-09-18 | No | Open
North East | Baghlan | Baghlani Jadid | Ta-i-Khunak | {C26665AC-8E12-4EBD-96EB-1768BD0BB724} | c0a8-0057-12c3b729cf0-2ae9a5a8-fbc3-8 | MF-HQ-11947 | MCPA - Mine Clearance Planning Agency | AF/1312/14204/MF4803 | 38250 | 68.4661 | 36.2114 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {C26665AC-8E12-4EBD-96EB-1768BD0BB724} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2009-07-14 | No | Open
North East | Baghlan | Baghlani Jadid | Ta-i-Khunak | {C26665AC-8E12-4EBD-96EB-1768BD0BB724} | c0a8-0057-12c3b7904b6-533b837f-1477e- | MF-HQ-11928 | MCPA - Mine Clearance Planning Agency | AF/1312/14204/MF2771 | 165000 | 68.4941 | 36.2014 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {C26665AC-8E12-4EBD-96EB-1768BD0BB724} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2009-07-14 | No | Open
North East | Baghlan | Baghlani Jadid | Ushtur Ghal | {225FDEFB-70F3-4CA9-911E-66D1E836C7CF} | c0a8-0057-12c3b7f4a9c-31d8c7d0-18edb- | MF-NE-939 | MCPA - Mine Clearance Planning Agency | AF/1312/13014/MF2268 | 30000 | 68.8574 | 36.1541 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {225FDEFB-70F3-4CA9-911E-66D1E836C7CF} |  | Low | Agriculture Blocked | Substantial | 27 | CHA | 5 |  |  | 2008-10-05 | No | Open
North East | Baghlan | Baghlani Jadid | Ushtur Ghal | {225FDEFB-70F3-4CA9-911E-66D1E836C7CF} | c0a8-0057-12c3b7f4c7f-46b6e809-18ef6- | MF-NE-924 | MCPA - Mine Clearance Planning Agency | AF/1312/13014/MF5140 | 28000 | 68.8643 | 36.1543 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {225FDEFB-70F3-4CA9-911E-66D1E836C7CF} |  | Low | Agriculture Blocked | Substantial | 22 | CHA | 5 |  |  | 2008-10-05 | No | Open
North East | Baghlan | Baghlani Jadid | Ushtur Ghal | {225FDEFB-70F3-4CA9-911E-66D1E836C7CF} | c0a8-0057-12c3b85dcac-1173400f-1d9ca- | MF-NE-926 | MCPA - Mine Clearance Planning Agency | AF/1312/13014/MF5138 | 32000 | 68.8627 | 36.1371 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {225FDEFB-70F3-4CA9-911E-66D1E836C7CF} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-05 | No | Open
North East | Baghlan | Baghlani Jadid | Ushtur Ghal | {225FDEFB-70F3-4CA9-911E-66D1E836C7CF} | c0a8-0057-12c3b85deaf-9378ea84-1d9e0- | MF-NE-927 | MCPA - Mine Clearance Planning Agency | AF/1312/13014/MF5137 | 35000 | 68.8627 | 36.1371 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {225FDEFB-70F3-4CA9-911E-66D1E836C7CF} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-05 | No | Open
North East | Baghlan | Baghlani Jadid | Ushtur Ghal | {225FDEFB-70F3-4CA9-911E-66D1E836C7CF} | c0a8-0057-12c3b85e0a2-7efd6b43-1d9f8- | MF-NE-925 | MCPA - Mine Clearance Planning Agency | AF/1312/13014/MF5139 | 45000 | 68.8627 | 36.1371 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {225FDEFB-70F3-4CA9-911E-66D1E836C7CF} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-05 | No | Open
North East | Baghlan | Baghlani Jadid | Zard Kamar | {AE75DF36-0865-43C2-8C6E-37F7DC044C8E} | c0a8-0009-143758a9bfa-23a58a16-2527-5 | Hz-ID-18350 | MCPA - Mine Clearance Planning Agency | AF/1301/13016/BF0039 | 392 | 68.7932 | 36.1949 | Open | UXO Only | UXO Only | BF |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {AE75DF36-0865-43C2-8C6E-37F7DC044C8E} |  | High | Critical Infrastracture | Substantial | 0 | CHA | 3 |  |  | 2013-11-20 16:30 | No | Open
North East | Baghlan | Burka | Aaq Say Qaracha | {30597A46-E896-4659-BA9F-000CBA8618BD} | c0a8-0057-12c3b9a16b3-456c4607-2b35d- | MF-NE-770 | HT - HALO TRUST | H/4881 | 64000 | 69.098 | 36.127 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {30597A46-E896-4659-BA9F-000CBA8618BD} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2008-08-16 | No | Open
North East | Baghlan | Burka | Burka | {2C93A02B-0941-41B7-A2CE-A82FCCB0BB48} | c0a8-0057-12c3b85655c-2baa6544-1d4c0- | MF-NE-671 | HT - HALO TRUST | H/2271 | 1440 | 69.1523 | 36.2216 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {2C93A02B-0941-41B7-A2CE-A82FCCB0BB48} |  | High with Victim | High with Victims | Substantial | 823 | CHA | 3 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Burka | {2C93A02B-0941-41B7-A2CE-A82FCCB0BB48} | c0a8-0057-12e55ed4719-2f322e2a-4a-b5f | BF-HQ-12275 | HT - HALO TRUST | B/1731 | 15 | 69.1512 | 36.2256 | Open | UXO Only | UXO Only | BF |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {2C93A02B-0941-41B7-A2CE-A82FCCB0BB48} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 3 |  |  | 2009-09-09 | No | Open
North East | Baghlan | Burka | Byram, Koor Quduq | {F8B96B23-200E-4531-98A8-6347DAEEB43F} | c0a8-0057-12c3b7dae61-687ed479-17d3e- | BF-NE-699 | HT - HALO TRUST | B/2482 | 10 | 69.0066 | 36.2428 | Open | UXO Only | UXO Only | BF |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {F8B96B23-200E-4531-98A8-6347DAEEB43F} |  | Medium | Agriculture Blocked | Substantial | 8 | CHA | 3 |  |  | 2008-09-10 | No | Open
North East | Baghlan | Burka | Byram, Koor Quduq | {F8B96B23-200E-4531-98A8-6347DAEEB43F} | c0a8-0057-12c3b99a0ea-874bff-2ae7a-5f | MF-NE-682 | HT - HALO TRUST | H/2283 | 11700 | 68.9542 | 36.245 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F8B96B23-200E-4531-98A8-6347DAEEB43F} |  | Low | Agriculture Blocked | Substantial | 34 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Byram, Koor Quduq | {F8B96B23-200E-4531-98A8-6347DAEEB43F} | c0a8-0057-12c3b9ac69e-e3e3de50-2bada- | MF-NE-681 | HT - HALO TRUST | H/2276 | 9968 | 68.9318 | 36.2461 | Open | AT Only | AT Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F8B96B23-200E-4531-98A8-6347DAEEB43F} |  | Low | Agriculture Blocked | Substantial | 38 | CHA | 4 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Byram, Koor Quduq | {F8B96B23-200E-4531-98A8-6347DAEEB43F} | c0a8-0057-12c3b9b8c39-3d5ed9e1-2c290- | MF-NE-683 | HT - HALO TRUST | H/4889 | 1130 | 68.9568 | 36.2503 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F8B96B23-200E-4531-98A8-6347DAEEB43F} |  | Low | Agriculture Blocked | Substantial | 37 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Byram, Koor Quduq | {F8B96B23-200E-4531-98A8-6347DAEEB43F} | c0a8-0057-12c3babf1cf-f36d1a6e-36120- | MF-NE-698 | HT - HALO TRUST | H/4883 | 18550 | 68.9854 | 36.2318 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F8B96B23-200E-4531-98A8-6347DAEEB43F} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2008-08-18 | No | Open
North East | Baghlan | Burka | Byram, Koor Quduq | {F8B96B23-200E-4531-98A8-6347DAEEB43F} | c0a8-0057-12c3bb75d7f-d79eb224-3ccd3- | MF-NE-676 | HT - HALO TRUST | H/4882 | 7850 | 68.9771 | 36.2369 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F8B96B23-200E-4531-98A8-6347DAEEB43F} |  | Low | Agriculture Blocked | Substantial | 21 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Byram, Koor Quduq | {F8B96B23-200E-4531-98A8-6347DAEEB43F} | c0a8-0057-12c3bb8843e-24f8f726-3d741- | MF-NE-677 | HT - HALO TRUST | H/2279 | 13100 | 68.9742 | 36.2405 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F8B96B23-200E-4531-98A8-6347DAEEB43F} |  | Low | Agriculture Blocked | Substantial | 150 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Chapa | {E439B687-C3B0-4A5C-9552-D19A282120F2} | c0a8-0057-12c3ba52271-f7b3fb41-320c9- | MF-NE-656 | HT - HALO TRUST | H/2275 | 2480 | 69.1299 | 36.2105 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {E439B687-C3B0-4A5C-9552-D19A282120F2} |  | Low | Agriculture Blocked | Substantial | 10 | CHA | 4 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Chapa | {E439B687-C3B0-4A5C-9552-D19A282120F2} | c0a8-0057-12c3baa9b1b-4354962-354e2-d | MF-NE-697 | HT - HALO TRUST | H/4880 | 8800 | 69.13 | 36.19 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {E439B687-C3B0-4A5C-9552-D19A282120F2} |  | Medium | Critical Infrastracture | Substantial | 76 | CHA | 3 |  |  | 2008-08-15 | No | Open
North East | Baghlan | Burka | Chapa | {E439B687-C3B0-4A5C-9552-D19A282120F2} | c0a8-0057-12c3baab494-d81dcddb-355a9- | MF-NE-657 | HT - HALO TRUST | H/4879 | 11350 | 69.1026 | 36.1485 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {E439B687-C3B0-4A5C-9552-D19A282120F2} |  | Low | Agriculture Blocked | Substantial | 5 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Chapsay | {47D9E748-8035-4AD7-9A70-4769BB5EE267} | c0a8-0057-12c3ba22076-cc7be24e-303cd- | MF-HQ-13992 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1310/13539/MF0015 | 15000 | 69.2341 | 36.1488 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {47D9E748-8035-4AD7-9A70-4769BB5EE267} |  | Low | Agriculture Blocked | Substantial | 1 | SHA | 5 |  |  | 2009-12-21 | No | Open
North East | Baghlan | Burka | Chara-i-Hazarqaq | {0EEF283B-9D3B-4067-91E6-2B269C5327DE} | c0a8-0057-12c3b8c71e8-2ede51c7-2231b- | MF-NE-664 | HT - HALO TRUST | H/2274 | 1280 | 68.9802 | 36.2346 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {0EEF283B-9D3B-4067-91E6-2B269C5327DE} |  | Low | Agriculture Blocked | Substantial | 21 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Chara-i-Hazarqaq | {0EEF283B-9D3B-4067-91E6-2B269C5327DE} | c0a8-0057-12c3b8d32b5-6a95ff83-22b38- | MF-NE-662 | HT - HALO TRUST | H/4888 | 420 | 69.0049 | 36.2449 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {0EEF283B-9D3B-4067-91E6-2B269C5327DE} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Chara-i-Hazarqaq | {0EEF283B-9D3B-4067-91E6-2B269C5327DE} | c0a8-0057-12c3b8fd360-9e66c039-247fd- | MF-NE-663 | HT - HALO TRUST | H/2277 | 2720 | 68.9913 | 36.2458 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {0EEF283B-9D3B-4067-91E6-2B269C5327DE} |  | Medium | Agriculture Blocked | Substantial | 0 | CHA | 3 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Chara-i-Hazarqaq | {0EEF283B-9D3B-4067-91E6-2B269C5327DE} | c0a8-0057-12c3b946044-64dadcec-27732- | MF-HQ-13991 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1310/13523/MF0016 | 5000 | 68.9766 | 36.2873 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {0EEF283B-9D3B-4067-91E6-2B269C5327DE} |  | Medium | Critical Infrastracture | Substantial | 19 | SHA | 3 |  |  | 2009-12-21 | No | Open
North East | Baghlan | Burka | Folowl-e Bala | {0F0E2959-016B-4539-978E-FAC6AAD87301} | c0a8-0057-12c3ba7e607-2cd17411-33bf5- | MF-NE-675 | HT - HALO TRUST | H/2286 | 5500 | 69.2862 | 36.1932 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {0F0E2959-016B-4539-978E-FAC6AAD87301} |  | Low | Agriculture Blocked | Substantial | 10 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Folowl-e Bala | {0F0E2959-016B-4539-978E-FAC6AAD87301} | c0a8-0057-12c3baf49c5-51f2c012-38184- | MF-NE-689 | HT - HALO TRUST | H/4887 | 77500 | 69.2721 | 36.1897 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {0F0E2959-016B-4539-978E-FAC6AAD87301} |  | Low | Agriculture Blocked | Substantial | 5 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Islam Darra | {315CBF6D-22DC-45CB-98F1-884B027CC754} | c0a8-0057-12c3b97d4b1-5d02b50d-29b74- | MF-NE-635 | HT - HALO TRUST | H/4878 | 27000 | 69.2442 | 36.1669 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {315CBF6D-22DC-45CB-98F1-884B027CC754} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-08-14 | No | Open
North East | Baghlan | Burka | Islam Darra | {315CBF6D-22DC-45CB-98F1-884B027CC754} | c0a8-0057-12c3b9aa1a1-cd498f60-2b93e- | MF-NE-642 | HT - HALO TRUST | H/2282 | 12500 | 69.2381 | 36.1553 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {315CBF6D-22DC-45CB-98F1-884B027CC754} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Jam Ali | {9BE8F531-23BB-4054-9EC0-A57F9350617F} | c0a8-0057-12c3b8cece0-4413ee6e-2284c- | MF-NE-661 | HT - HALO TRUST | H/2280 | 3360 | 69.0062 | 36.3303 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {9BE8F531-23BB-4054-9EC0-A57F9350617F} |  | Low | Agriculture Blocked | Substantial | 10 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Pahlawan Tash (1) | {E24285A4-AF96-46BF-B8D6-DB3A35093FC3} | c0a8-0057-12c3b8eeb45-f1f41d70-23e0f- | MF-NE-672 | HT - HALO TRUST | H/2284 | 1288 | 69.1479 | 36.2916 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {E24285A4-AF96-46BF-B8D6-DB3A35093FC3} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Pahlawan Tash (1) | {E24285A4-AF96-46BF-B8D6-DB3A35093FC3} | c0a8-0057-12c3bb7fd06-fad2c4c6-3d2c7- | MF-NE-673 | HT - HALO TRUST | H/2285 | 1828 | 69.1147 | 36.304 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {E24285A4-AF96-46BF-B8D6-DB3A35093FC3} |  | Low | Agriculture Blocked | Substantial | 65 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Pasha-ee | {39B3D8B2-FA33-4E5E-B288-069B0C2129A5} | c0a8-0057-12c3b81e473-8f88398-1ac75-c | MF-NE-655 | HT - HALO TRUST | H/4885 | 9620 | 68.9278 | 36.2798 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {39B3D8B2-FA33-4E5E-B288-069B0C2129A5} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Pasha-ee | {39B3D8B2-FA33-4E5E-B288-069B0C2129A5} | c0a8-0057-12c3bab7052-6a5dc759-35c9b- | MF-NE-653 | HT - HALO TRUST | H/2278 | 16750 | 68.9311 | 36.2863 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {39B3D8B2-FA33-4E5E-B288-069B0C2129A5} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-08-01 | No | Open
North East | Baghlan | Burka | Qamare Jum'a'ali | {8783C81B-873C-4913-8DB4-BD67F6980E63} | c0a8-0057-12c3b8bbfea-966141a0-21b16- | MF-NE-666 | HT - HALO TRUST | H/2281 | 76700 | 69.2651 | 36.1942 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {8783C81B-873C-4913-8DB4-BD67F6980E63} |  | Low | Agriculture Blocked | Substantial | 6 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Qamare Jum'a'ali | {8783C81B-873C-4913-8DB4-BD67F6980E63} | c0a8-0057-12c3b93bc13-558bfd1a-2705c- | MF-NE-669 | HT - HALO TRUST | H/2273 | 14000 | 69.173 | 36.2482 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {8783C81B-873C-4913-8DB4-BD67F6980E63} |  | Low | Agriculture Blocked | Substantial | 24 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Saqaw | {795010A0-3064-4719-9DDA-113B83E42D89} | c0a8-0057-12c3ba2bfcf-cb3f5a52-309c5- | MF-NE-625 | HT - HALO TRUST | H/4875 | 20900 | 69.1913 | 36.1251 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {795010A0-3064-4719-9DDA-113B83E42D89} |  | Low | Agriculture Blocked | Substantial | 104 | CHA | 4 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Saqaw | {795010A0-3064-4719-9DDA-113B83E42D89} | c0a8-0057-12c3ba2c24e-a06d9a06-309db- | MF-NE-626 | HT - HALO TRUST | H/4876 | 21687 | 69.1913 | 36.1251 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {795010A0-3064-4719-9DDA-113B83E42D89} |  | Low | Agriculture Blocked | Substantial | 106 | CHA | 4 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Saye Hazarah, Jangi Beg | {EA412174-B37B-4430-9946-15D099D876B2} | c0a8-0057-12c3b864943-fb853df5-1de63- | MF-NE-688 | HT - HALO TRUST | H/4884 | 79200 | 69.3967 | 36.1657 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {EA412174-B37B-4430-9946-15D099D876B2} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Saye Hazarah, Jangi Beg | {EA412174-B37B-4430-9946-15D099D876B2} | c0a8-0057-12c3b8ea715-1b696cc2-23b78- | MF-NE-684 | HT - HALO TRUST | H/2287 | 57300 | 69.35 | 36.2028 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {EA412174-B37B-4430-9946-15D099D876B2} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Saye Hazarah, Jangi Beg | {EA412174-B37B-4430-9946-15D099D876B2} | c0a8-0057-12c3b9f0976-fc37085b-2e55a- | MF-NE-686 | HT - HALO TRUST | H/4874 | 16000 | 69.2746 | 36.1545 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {EA412174-B37B-4430-9946-15D099D876B2} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Saye Hazarah, Jangi Beg | {EA412174-B37B-4430-9946-15D099D876B2} | c0a8-0057-12c3b9f0b5a-d1a73cb1-2e574- | MF-NE-685 | HT - HALO TRUST | H/4873 | 18 | 69.276 | 36.1552 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {EA412174-B37B-4430-9946-15D099D876B2} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Saye Hazarah, Jangi Beg | {EA412174-B37B-4430-9946-15D099D876B2} | c0a8-0057-12c3bb5d2c1-862b3c7f-3bf57- | MF-NE-687 | HT - HALO TRUST | H/2292 | 1120 | 69.2868 | 36.1707 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {EA412174-B37B-4430-9946-15D099D876B2} |  | Medium | Agriculture Blocked | Substantial | 0 | CHA | 3 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Shor Quduq | {349DDD65-F19E-4A41-997B-0C0C0E858B0F} | c0a8-0057-12c3b982a5c-ba4e0191-29f14- | MF-NE-448 | HT - HALO TRUST | H/4191 | 16480 | 68.9532 | 36.4311 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {349DDD65-F19E-4A41-997B-0C0C0E858B0F} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-04-22 | No | Open
North East | Baghlan | Burka | Shor Quduq | {349DDD65-F19E-4A41-997B-0C0C0E858B0F} | c0a8-0057-12c3b9c889d-af5dc0e3-2cce0- | MF-NE-956 | HT - HALO TRUST | H/4193 | 2140 | 69.0008 | 36.4378 | Open | AT Only | AT Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {349DDD65-F19E-4A41-997B-0C0C0E858B0F} |  | Low | Small Hazards | Substantial | 7 | CHA | 5 |  |  | 2008-04-17 | No | Open
North East | Baghlan | Burka | Shor Quduq | {349DDD65-F19E-4A41-997B-0C0C0E858B0F} | c0a8-0057-12c3b9d9a92-1efe4ceb-2d749- | MF-NE-442 | HT - HALO TRUST | H/2619 | 17690 | 68.9613 | 36.4201 | Open | AT Only | AT Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {349DDD65-F19E-4A41-997B-0C0C0E858B0F} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-04-30 | No | Open
North East | Baghlan | Burka | Shorachah(2) | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} | c0a8-0057-12c3ba90382-e92b0b18-3464f- | MF-NE-694 | HT - HALO TRUST | H/5203 | 42000 | 69.209 | 36.1065 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-09-05 | No | Open
North East | Baghlan | Burka | Shorachah(2) | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} | c0a8-0057-12c3ba905a4-1295c993-34663- | MF-NE-696 | HT - HALO TRUST | H/5202 | 52400 | 69.2063 | 36.1055 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} |  | Low | Agriculture Blocked | Substantial | 6 | CHA | 5 |  |  | 2008-09-05 | No | Open
North East | Baghlan | Burka | Shorachah(2) | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} | c0a8-0057-12c3ba90769-47160333-3467c- | MF-NE-692 | HT - HALO TRUST | H/5204 | 51000 | 69.2122 | 36.1074 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-09-06 | No | Open
North East | Baghlan | Burka | Shorachah(2) | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} | c0a8-0057-12c3ba90a55-3e1d807-34690-4 | MF-NE-690 | HT - HALO TRUST | H/4877 | 61700 | 69.2011 | 36.0925 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2008-08-12 | No | Open
North East | Baghlan | Burka | Shorachah(2) | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} | c0a8-0057-12c3ba90c49-48a6f47a-346ae- | MF-NE-691 | HT - HALO TRUST | H/5206 | 49000 | 69.2161 | 36.105 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-09-07 | No | Open
North East | Baghlan | Burka | Shorachah(2) | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} | c0a8-0057-12c3ba90e0d-164a2aca-346c2- | MF-NE-693 | HT - HALO TRUST | H/5205 | 43000 | 69.2148 | 36.1071 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-09-07 | No | Open
North East | Baghlan | Burka | Shorachah(2) | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} | c0a8-0057-12c3babd06a-64e85c82-35fe1- | MF-NE-631 | HT - HALO TRUST | H/2288 | 105000 | 69.199 | 36.0974 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} |  | Low | Agriculture Blocked | Substantial | 15 | CHA | 5 |  |  | 2008-08-11 | No | Open
North East | Baghlan | Burka | Shorachah(2) | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} | c0a8-0057-12c3bb588e7-722ffdf3-3bc85- | MF-NE-628 | HT - HALO TRUST | H/4886 | 880 | 69.1582 | 36.139 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {F0E0F5FE-07C4-48C2-A2ED-50A102C55610} |  | Medium | Critical Infrastracture | Substantial | 41 | CHA | 3 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Shorcha | {72CD2321-B7CF-4F96-83D8-CC74AA91C4CE} | c0a8-0057-12c3b80a7b5-69ebfd07-19e7b- | MF-NE-735 | HT - HALO TRUST | H/5201 | 66400 | 69.2012 | 36.1042 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {72CD2321-B7CF-4F96-83D8-CC74AA91C4CE} |  | Low | Agriculture Blocked | Substantial | 5 | CHA | 5 |  |  | 2008-09-04 | No | Open
North East | Baghlan | Burka | Tangi Murch | {8CAE1608-F98D-47B4-B6CD-361A88E06968} | c0a8-0057-12c3ba0aafd-59bff414-2f5b1- | MF-NE-674 | HT - HALO TRUST | H/2272 | 14800 | 69.152 | 36.2683 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {8CAE1608-F98D-47B4-B6CD-361A88E06968} |  | Low | Agriculture Blocked | Substantial | 10 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Burka | Tangi Murch | {8CAE1608-F98D-47B4-B6CD-361A88E06968} | c0a8-0057-12c3ba8d6c8-47ff2122-34493- | MF-NE-670 | HT - HALO TRUST | H/2291 | 14300 | 69.1906 | 36.2766 | Open | AP Only | AP Only | MineField |  | MBT Project-180 | Baghlan Demining Project-05 |  |  |  |  | 1395 |  | {8CAE1608-F98D-47B4-B6CD-361A88E06968} |  | Low | Agriculture Blocked | Substantial | 110 | CHA | 5 |  |  | 2008-10-01 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Chahe Ana | {7DB7B57A-E7FD-4959-AE05-F7FAAD50EAE1} | c0a8-0057-12c3b98af31-50eae113-2a48d- | MF-NE-386 | HT - HALO TRUST | H/4129 | 9500 | 68.4665 | 35.8809 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {7DB7B57A-E7FD-4959-AE05-F7FAAD50EAE1} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-01-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Chahe Jungan | {AB521681-FD8A-4B88-9CD7-1B18F42285DB} | c0a8-0057-12c3b95513f-839a7aa0-280f5- | MF-NE-995 | MDC - Mine Detection and Dog Center | AF/1303/13206/MF0006 | 14928 | 68.4783 | 35.9267 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {AB521681-FD8A-4B88-9CD7-1B18F42285DB} |  | Low | Agriculture Blocked | Substantial | 57 | CHA | 5 |  |  | 2008-10-22 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Chahe Jungan | {AB521681-FD8A-4B88-9CD7-1B18F42285DB} | c0a8-0057-12c3ba8a454-8bff9fd0-342c8- | MF-NE-373 | HT - HALO TRUST | H/4136 | 45000 | 68.4578 | 35.9323 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {AB521681-FD8A-4B88-9CD7-1B18F42285DB} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2008-09-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Chahe Jungan | {AB521681-FD8A-4B88-9CD7-1B18F42285DB} | c0a8-0057-12c3ba8a6b4-41bec13f-342e1- | MF-NE-372 | HT - HALO TRUST | H/4134 | 30000 | 68.4581 | 35.9291 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {AB521681-FD8A-4B88-9CD7-1B18F42285DB} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2008-09-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Chahe Jungan | {AB521681-FD8A-4B88-9CD7-1B18F42285DB} | c0a8-0057-12c3ba8a8f5-1cc5e69c-342f5- | MF-NE-374 | HT - HALO TRUST | H/4135 | 32000 | 68.4581 | 35.9291 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {AB521681-FD8A-4B88-9CD7-1B18F42285DB} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-09-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Chercherak | {F1F157C2-83D2-48D4-B687-35B058904EC7} | c0a8-0057-12c3b93c8ee-49e2991f-270e2- | MF-HT-518 | HT - HALO TRUST | H/3577 | 40000 | 68.4144 | 35.8014 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {F1F157C2-83D2-48D4-B687-35B058904EC7} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2007-12-16 11:44 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Chercherak | {F1F157C2-83D2-48D4-B687-35B058904EC7} | c0a8-0057-12c3bb1c026-88df4bf4-398e6- | MF-HT-529 | HT - HALO TRUST | H/3579 | 53000 | 68.4144 | 35.8014 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {F1F157C2-83D2-48D4-B687-35B058904EC7} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2007-12-16 12:09 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Chercherak | {F1F157C2-83D2-48D4-B687-35B058904EC7} | c0a8-0057-12c3bb1c1ea-238de146-398f9- | MF-HT-523 | HT - HALO TRUST | H/3578 | 53000 | 68.4144 | 35.8014 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {F1F157C2-83D2-48D4-B687-35B058904EC7} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2007-12-16 11:58 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Cinza'i (Gawargan) | {CE8FD8D8-1F2C-46D3-9881-55D6C9C19308} | c0a8-0057-12c3b6fbad3-3475f64-d8c6-1d | MF-HQ-9931 | HT - HALO TRUST | H/6034 | 582 | 68.5452 | 35.9805 | Open | AT Only | AT Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {CE8FD8D8-1F2C-46D3-9881-55D6C9C19308} |  | Low | Comunity Centers | Substantial | 114 | CHA | 4 |  |  | 2009-03-30 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Dahana | {4E153322-BB91-4406-841C-32094D581D12} | c0a8-0057-12c3b7cec9b-9ee0ba15-17499- | MF-NE-381 | HT - HALO TRUST | H/4130 | 22500 | 68.4711 | 35.8875 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {4E153322-BB91-4406-841C-32094D581D12} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2008-01-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Dahana | {4E153322-BB91-4406-841C-32094D581D12} | c0a8-0057-12c3ba466d2-dc3f8e95-319c8- | MF-NE-384 | HT - HALO TRUST | H/2303 | 65000 | 68.4671 | 35.8818 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {4E153322-BB91-4406-841C-32094D581D12} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2008-01-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Dahana | {4E153322-BB91-4406-841C-32094D581D12} | c0a8-0057-12c3bb47808-eccc2c98-3b282- | MF-NE-385 | HT - HALO TRUST | H/4131 | 24000 | 68.4731 | 35.8939 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {4E153322-BB91-4406-841C-32094D581D12} |  | Low | Agriculture Blocked | Substantial | 23 | CHA | 5 |  |  | 2008-01-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Dahana-I-Ghori | {FB41DD37-AC0B-4162-9042-E5DD6DAED142} | c0a8-0057-12c3b9994f8-e3154961-2ae0b- | MF-NE-382 | HT - HALO TRUST | H/4133 | 29000 | 68.4961 | 35.8698 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {FB41DD37-AC0B-4162-9042-E5DD6DAED142} |  | High with Victim | High with Victims | Substantial | 5 | CHA | 2 |  |  | 2008-08-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Nilan | {BC109468-3660-4E71-8834-11BDB7593321} | c0a8-0057-12c3b7f7478-8e9617b-190c9-d | MF-NE-378 | HT - HALO TRUST | H/4132 | 34000 | 68.4118 | 35.8144 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {BC109468-3660-4E71-8834-11BDB7593321} |  | Low | Agriculture Blocked | Substantial | 55 | CHA | 4 |  |  | 2008-07-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Nilan | {BC109468-3660-4E71-8834-11BDB7593321} | c0a8-0057-12c3b87c908-e68d400c-1ef4c- | MF-NE-380 | HT - HALO TRUST | H/2296 | 25000 | 68.4118 | 35.8144 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {BC109468-3660-4E71-8834-11BDB7593321} |  | Low | Comunity Centers | Substantial | 48 | CHA | 5 |  |  | 2008-04-07 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Pasha Qol | {C0F6BFA1-F9EF-46D5-9A66-D88E4CB3BC40} | c0a8-0057-12c3b73239b-29868ad-10221-d | MF-HT-1301 | HT - HALO TRUST | H/3613 | 14000 | 68.4111 | 35.7946 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {C0F6BFA1-F9EF-46D5-9A66-D88E4CB3BC40} |  | High with Victim | High with Victims | Substantial | 1 | CHA | 2 |  |  | 2007-07-01 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Pasha Qol | {C0F6BFA1-F9EF-46D5-9A66-D88E4CB3BC40} | c0a8-0057-12c3b84dc51-e75f1b7f-1ce85- | MF-NE-388 | HT - HALO TRUST | H/3612 | 5500 | 68.4243 | 35.7917 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {C0F6BFA1-F9EF-46D5-9A66-D88E4CB3BC40} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 2 |  |  | 2008-01-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Pasha Qol | {C0F6BFA1-F9EF-46D5-9A66-D88E4CB3BC40} | c0a8-0057-12c3b84de06-1947068-1ce99-4 | MF-NE-387 | HT - HALO TRUST | H/2297 | 42000 | 68.4164 | 35.7792 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {C0F6BFA1-F9EF-46D5-9A66-D88E4CB3BC40} |  | High with Victim | High with Victims | Substantial | 2 | CHA | 2 |  |  | 2008-01-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Pasha Qol | {C0F6BFA1-F9EF-46D5-9A66-D88E4CB3BC40} | c0a8-0057-12c3bb5791f-b1e341e6-3bc03- | MF-HT-556 | HT - HALO TRUST | H/3614 | 11000 | 68.4111 | 35.7946 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {C0F6BFA1-F9EF-46D5-9A66-D88E4CB3BC40} |  | High with Victim | High with Victims | Substantial | 1 | CHA | 2 |  |  | 2007-12-16 14:02 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Pashimandara | {6AA5D785-847E-4BFB-8967-65D83C5EFDD1} | c0a8-0057-12c3b70d330-6fa1b7ee-e61b-2 | MF-HQ-11600 | HT - HALO TRUST | H/5885 | 1950 | 68.5244 | 35.9428 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {6AA5D785-847E-4BFB-8967-65D83C5EFDD1} |  | Medium | Agriculture Blocked | Substantial | 0 | CHA | 3 |  |  | 2009-02-14 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Qarlogh | {9C9C5DEB-6383-4452-86E7-863521377E58} | c0a8-0057-12c3b950840-222250ad-27e42- | MF-HT-541 | HT - HALO TRUST | H/3611 | 40000 | 68.4111 | 35.7946 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {9C9C5DEB-6383-4452-86E7-863521377E58} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2007-12-16 12:29 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Qarlogh | {9C9C5DEB-6383-4452-86E7-863521377E58} | c0a8-0057-12c3b9ee8fc-b86e9b74-2e43b- | MF-HT-546 | HT - HALO TRUST | H/3621 | 42000 | 68.4936 | 35.8191 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {9C9C5DEB-6383-4452-86E7-863521377E58} |  | Medium | Critical Infrastracture | Substantial | 173 | CHA | 3 |  |  | 2007-12-16 13:15 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Qarlogh | {9C9C5DEB-6383-4452-86E7-863521377E58} | c0a8-0057-12c3bb6718e-dae4e2fe-3c4c9- | MF-HT-551 | HT - HALO TRUST | H/3622 | 37000 | 68.4936 | 35.8191 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {9C9C5DEB-6383-4452-86E7-863521377E58} |  | Medium | Critical Infrastracture | Substantial | 93 | CHA | 3 |  |  | 2007-12-16 13:31 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Sayad | {1E8B1F32-8AB2-4171-A7BB-13FE3C4DDD6A} | c0a8-0057-12c3b859cb1-5aec97d4-1d72a- | MF-HT-562 | HT - HALO TRUST | H/3619 | 5500 | 68.4355 | 35.8716 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {1E8B1F32-8AB2-4171-A7BB-13FE3C4DDD6A} |  | Medium | Critical Infrastracture | Substantial | 140 | CHA | 3 |  |  | 2007-12-16 14:22 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Sayad | {1E8B1F32-8AB2-4171-A7BB-13FE3C4DDD6A} | c0a8-0057-12c3b8b0287-3725b72-21301-e | MF-HT-566 | HT - HALO TRUST | H/3620 | 45000 | 68.4355 | 35.8716 | Open | AP Only | AP Only | MineField |  | MBT Project-150 | Baghlan Demining Project-21 |  |  |  |  | 1396 |  | {1E8B1F32-8AB2-4171-A7BB-13FE3C4DDD6A} |  | Medium | Critical Infrastracture | Substantial | 1199 | CHA | 3 |  |  | 2007-12-16 14:39 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Sayad | {1E8B1F32-8AB2-4171-A7BB-13FE3C4DDD6A} | c0a8-0057-12c3b9d55c7-78137c7b-2d484- | MF-NE-383 | HT - HALO TRUST | H/4137 | 44000 | 68.4098 | 35.858 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {1E8B1F32-8AB2-4171-A7BB-13FE3C4DDD6A} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-11-04 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Tajek-ha-i-Kole Amchi | {5586D25B-3FA0-4709-BA2F-2109D2A6B135} | c0a8-0057-12c3b929aec-8d58392e-26474- | MF-HQ-14145 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1303/13071/MF0007 | 30000 | 68.5089 | 35.9751 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-248 | Baghlan Demining Project-4 (AT) |  |  |  |  | 1400 |  | {5586D25B-3FA0-4709-BA2F-2109D2A6B135} |  | Low | Agriculture Blocked | Substantial | 34 | SHA | 5 |  |  | 2010-02-01 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Wakhshak | {9BC707F9-9A7D-4009-844A-63A3B29C595D} | c0a8-0057-12c3b855a65-8d5de031-1d443- | MF-NE-379 | HT - HALO TRUST | H/4127 | 15500 | 68.4234 | 35.8882 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {9BC707F9-9A7D-4009-844A-63A3B29C595D} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2008-04-30 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Wakhshak | {9BC707F9-9A7D-4009-844A-63A3B29C595D} | c0a8-0057-12c3b855c58-7fbcce1-1d45a-c | MF-NE-375 | HT - HALO TRUST | H/2302 | 43500 | 68.374 | 35.9087 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {9BC707F9-9A7D-4009-844A-63A3B29C595D} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-04-30 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Wakhshak | {9BC707F9-9A7D-4009-844A-63A3B29C595D} | c0a8-0057-12c3b855e0c-8fd90248-1d46f- | MF-NE-376 | HT - HALO TRUST | H/4126 | 11000 | 68.374 | 35.9087 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {9BC707F9-9A7D-4009-844A-63A3B29C595D} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2008-04-30 | No | Open
North East | Baghlan | Dahana-I- Ghuri | Wakhshak | {9BC707F9-9A7D-4009-844A-63A3B29C595D} | c0a8-0057-12c3ba97ca6-5283afc1-34ac2- | MF-NE-371 | HT - HALO TRUST | H/2301 | 38000 | 68.391 | 35.9004 | Open | AP Only | AP Only | MineField |  | MBT Project-122 | Baghlan Demining Project-17 |  |  |  |  | 1400 |  | {9BC707F9-9A7D-4009-844A-63A3B29C595D} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-04-30 | No | Open
North East | Baghlan | Dih Salah | Arzangane Ulya | {283C63AE-E194-4C49-8410-E96637AFF52B} | c0a8-0009-14384f78d6c-5e47fd24-4069-5 | Hz-ID-18385 | HT - HALO TRUST | H/8900 | 1620 | 69.3032 | 35.6562 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {283C63AE-E194-4C49-8410-E96637AFF52B} |  | Medium | Critical Infrastracture | Moderate | 31 | CHA | 3 |  |  | 2013-12-15 16:30 | No | Open
North East | Baghlan | Dih Salah | Arzangane Ulya | {283C63AE-E194-4C49-8410-E96637AFF52B} | c0a8-0057-12c3b7a6b13-fde503e5-157b2- | MF-HQ-11956 | HT - HALO TRUST | H/6115 | 831 | 69.3058 | 35.6588 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {283C63AE-E194-4C49-8410-E96637AFF52B} |  | Medium | Agriculture Blocked | Moderate | 905 | CHA | 3 |  |  | 2009-05-03 | No | Open
North East | Baghlan | Dih Salah | Arzangane Ulya | {283C63AE-E194-4C49-8410-E96637AFF52B} | c0a8-0057-12c3b89c358-6626563b-20511- | MF-HQ-11300 | HT - HALO TRUST | H/6116 | 1258 | 69.3085 | 35.6597 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {283C63AE-E194-4C49-8410-E96637AFF52B} |  | Medium | Agriculture Blocked | Moderate | 0 | CHA | 3 |  |  | 2009-05-03 | No | Open
North East | Baghlan | Dih Salah | Arzangane Ulya | {283C63AE-E194-4C49-8410-E96637AFF52B} | c0a8-0057-12c3b9ba0f1-64d7734e-2c354- | MF-HQ-11306 | HT - HALO TRUST | H/2204 | 3300 | 69.313 | 35.6622 | Open | AP Only | AP Only | MineField |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {283C63AE-E194-4C49-8410-E96637AFF52B} |  | Low | Agriculture Blocked | Moderate | 64 | CHA | 5 |  |  | 2009-05-03 | No | Open
North East | Baghlan | Dih Salah | Arzangane Ulya | {283C63AE-E194-4C49-8410-E96637AFF52B} | c0a8-0057-12c3bb235a2-65ba8473-39d85- | MF-HQ-11301 | HT - HALO TRUST | H/6117 | 620 | 69.3162 | 35.6689 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {283C63AE-E194-4C49-8410-E96637AFF52B} |  | Medium | Agriculture Blocked | Moderate | 168 | CHA | 3 |  |  | 2009-05-03 | No | Open
North East | Baghlan | Dih Salah | Arzangane Ulya | {283C63AE-E194-4C49-8410-E96637AFF52B} | c0a8-00c9-12fdda9d63d-a038ad92-958-27 | MF-HQ-13984 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1313/13608/MF004 | 6600 | 69.3033 | 35.663 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {283C63AE-E194-4C49-8410-E96637AFF52B} |  | Medium | Critical Infrastracture | Moderate | 865 | SHA | 3 |  |  | 2009-12-21 | No | Open
North East | Baghlan | Dih Salah | Baghe Jabaq | {7B6A2B9E-A299-4F04-B7B4-D7E12A55BD41} | c0a8-0009-14400a38934-f46b1b04-8bd7-3 | Hz-ID-18472 | HT - HALO TRUST | H/8908 | 5788 | 69.2877 | 35.6636 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {7B6A2B9E-A299-4F04-B7B4-D7E12A55BD41} |  | Low | Agriculture Blocked | Moderate | 1744 | CHA | 4 |  |  | 2014-01-18 16:30 | No | Open
North East | Baghlan | Dih Salah | Kharpushta | {03A13D27-EA94-4B18-8A6B-213394F6D292} | c0a8-0009-14400b39026-4d0ec580-8c26-3 | Hz-ID-18473 | HT - HALO TRUST | H/8907 | 1918 | 69.3063 | 35.7343 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {03A13D27-EA94-4B18-8A6B-213394F6D292} |  | Medium | Agriculture Blocked | Moderate | 27 | CHA | 3 |  |  | 2014-01-15 16:30 | No | Open
North East | Baghlan | Dih Salah | Khwaja Qalat | {7F07DA6B-4DB6-4C17-A0A7-E7969DFB4F33} | c0a8-0057-12c3baf9535-30a6fe78-38442- | MF-HQ-13987 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1313/385/MF003 | 5000 | 69.3387 | 35.6675 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {7F07DA6B-4DB6-4C17-A0A7-E7969DFB4F33} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-12-21 | No | Open
North East | Baghlan | Dih Salah | Saka | {332EB75C-F7BD-439D-B2AE-906F305D713A} | c0a8-0057-12c3b811065-5c0084e7-1a2ee- | MF-HQ-11311 | HT - HALO TRUST | H/2202 | 3493 | 69.3002 | 35.7185 | Open | AP Only | AP Only | MineField |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {332EB75C-F7BD-439D-B2AE-906F305D713A} |  | Low | Agriculture Blocked | Moderate | 99 | CHA | 5 |  |  | 2009-05-13 | No | Open
North East | Baghlan | Dih Salah | Saka | {332EB75C-F7BD-439D-B2AE-906F305D713A} | c0a8-0057-12c3b9d7bdc-13e064b-2d60b-d | MF-HQ-11310 | HT - HALO TRUST | H/2212 | 2467 | 69.3318 | 35.7181 | Open | AP Only | AP Only | MineField |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {332EB75C-F7BD-439D-B2AE-906F305D713A} |  | Low | Agriculture Blocked | Moderate | 12 | CHA | 4 |  |  | 2009-05-13 | No | Open
North East | Baghlan | Dih Salah | Sangboran | {65AC774A-6C85-4974-AB4E-E2F29D191415} | c0a8-0057-12c3b75422d-463c1977-11b6d- | MF-HQ-11388 | HT - HALO TRUST | H/6120 | 20790 | 69.3271 | 35.6868 | Open | AP Only | AP Only | MineField |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {65AC774A-6C85-4974-AB4E-E2F29D191415} |  | Low | Agriculture Blocked | Moderate | 44 | CHA | 4 |  |  | 2009-05-16 | No | Open
North East | Baghlan | Dih Salah | Sangboran | {65AC774A-6C85-4974-AB4E-E2F29D191415} | c0a8-0057-12c3b8088d0-57648fad-19d10- | MF-HQ-11313 | HT - HALO TRUST | H/2245 | 901 | 69.3195 | 35.6657 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {65AC774A-6C85-4974-AB4E-E2F29D191415} |  | Medium | Agriculture Blocked | Moderate | 92 | CHA | 3 |  |  | 2009-05-18 | No | Open
North East | Baghlan | Dih Salah | Sangboran | {65AC774A-6C85-4974-AB4E-E2F29D191415} | c0a8-0057-12c3b8b3597-998fdff6-21531- | MF-HQ-11312 | HT - HALO TRUST | H/2244 | 1218 | 69.3264 | 35.6654 | Open | AP Only | AP Only | MineField |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {65AC774A-6C85-4974-AB4E-E2F29D191415} |  | Low | Agriculture Blocked | Moderate | 26 | CHA | 5 |  |  | 2009-05-18 | No | Open
North East | Baghlan | Dih Salah | Sangboran | {65AC774A-6C85-4974-AB4E-E2F29D191415} | c0a8-0057-12c3bb3a542-8bda4f13-3ab04- | MF-HQ-11298 | HT - HALO TRUST | H/6119 | 29100 | 69.3269 | 35.6839 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {65AC774A-6C85-4974-AB4E-E2F29D191415} |  | Medium | Critical Infrastracture | Moderate | 44 | CHA | 3 |  |  | 2009-05-16 | No | Open
North East | Baghlan | Dih Salah | Sangboran | {65AC774A-6C85-4974-AB4E-E2F29D191415} | c0a8-0057-12c3bb3a8da-158f14e4-3ab27- | MF-HQ-12002 | HT - HALO TRUST | H/6130 | 16500 | 69.3261 | 35.6885 | Open | AP Only | AP Only | MineField |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {65AC774A-6C85-4974-AB4E-E2F29D191415} |  | Low | Agriculture Blocked | Moderate | 44 | CHA | 4 |  |  | 2009-05-17 | No | Open
North East | Baghlan | Dih Salah | Sayade Bala | {7E71E659-9844-48E1-8369-41B28F95591F} | c0a8-0009-1440569e9ed-a4084865-1735-4 | Hz-ID-18474 | HT - HALO TRUST | H/8906 | 6860 | 69.2933 | 35.6883 | Open | AP Only | AP Only | MineField |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {7E71E659-9844-48E1-8369-41B28F95591F} |  | Low | Agriculture Blocked | Moderate | 47 | CHA | 5 |  |  | 2014-01-16 16:30 | No | Open
North East | Baghlan | Dih Salah | Sayade Bala | {7E71E659-9844-48E1-8369-41B28F95591F} | c0a8-0057-12c3b70772d-fc461f86-e1d3-5 | MF-HQ-11299 | HT - HALO TRUST | H/6118 | 1464 | 69.3002 | 35.6935 | Open | AP Only | AP Only | MineField |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {7E71E659-9844-48E1-8369-41B28F95591F} |  | Low | Agriculture Blocked | Moderate | 59 | CHA | 5 |  |  | 2009-05-12 | No | Open
North East | Baghlan | Dih Salah | Sayade Bala | {7E71E659-9844-48E1-8369-41B28F95591F} | c0a8-0057-12c3bb15709-36865b72-394f6- | MF-HQ-11308 | HT - HALO TRUST | H/2248 | 1000 | 69.3047 | 35.6844 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {7E71E659-9844-48E1-8369-41B28F95591F} |  | Medium | Agriculture Blocked | Moderate | 148 | CHA | 3 |  |  | 2009-05-10 | No | Open
North East | Baghlan | Dih Salah | Sayade Payan | {D71A0756-80AD-439A-8AB6-53737860CC1B} | c0a8-0057-12c3b8c45f9-d4e3e392-22128- | MF-HQ-13986 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1313/13639/MF002 | 2850 | 69.2819 | 35.6776 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {D71A0756-80AD-439A-8AB6-53737860CC1B} |  | Low | Agriculture Blocked | Moderate | 8 | SHA | 5 |  |  | 2009-12-21 | No | Open
North East | Baghlan | Dih Salah | Sayade Payan | {D71A0756-80AD-439A-8AB6-53737860CC1B} | c0a8-0057-12c3b9a6d88-5bf9a854-2b718- | MF-HQ-13985 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1313/13639/MF001 | 39600 | 69.291 | 35.688 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {D71A0756-80AD-439A-8AB6-53737860CC1B} |  | Low | Agriculture Blocked | Moderate | 42 | SHA | 5 |  |  | 2009-12-21 | No | Open
North East | Baghlan | Dih Salah | Tale Mirghazi | {0B57230C-4A2E-47DE-9F6A-2B41A39D8BD2} | c0a8-0009-14375c54aa8-106ace4a-26f6-2 | Hz-ID-18356 | HT - HALO TRUST | B/3110 | 64531 | 69.3044 | 35.7587 | Open | UXO Only | UXO Only | BF |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {0B57230C-4A2E-47DE-9F6A-2B41A39D8BD2} |  | Medium | Agriculture Blocked | Moderate | 47 | CHA | 3 |  |  | 2013-12-15 16:30 | No | Open
North East | Baghlan | Dih Salah | Tale Mirghazi | {0B57230C-4A2E-47DE-9F6A-2B41A39D8BD2} | c0a8-0057-12c3b8ae048-42c41631-21181- | MF-HQ-12179 | HT - HALO TRUST | H/2221 | 2640 | 69.3077 | 35.7675 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {0B57230C-4A2E-47DE-9F6A-2B41A39D8BD2} |  | Medium | Agriculture Blocked | Moderate | 92 | CHA | 3 |  |  | 2004-04-18 | No | Open
North East | Baghlan | Dih Salah | Tale Mirghazi | {0B57230C-4A2E-47DE-9F6A-2B41A39D8BD2} | c0a8-0057-12c3b8b7ee5-3b64eb2c-21863- | MF-HQ-12188 | HT - HALO TRUST | H/2222 | 5024 | 69.3 | 35.7521 | Open | AP Only | AP Only | MineField |  | MBT Project-081 | Baghlan Demining Project-20 |  |  |  |  | 1400 |  | {0B57230C-4A2E-47DE-9F6A-2B41A39D8BD2} |  | Low | Agriculture Blocked | Moderate | 126 | CHA | 5 |  |  | 2009-09-09 | No | Open
North East | Baghlan | Dih Salah | Tale Mirghazi | {0B57230C-4A2E-47DE-9F6A-2B41A39D8BD2} | c0a8-0057-12c3bb39135-b3dbb3f1-3aa5c- | MF-HQ-12319 | HT - HALO TRUST | H/2223 | 7320 | 69.3097 | 35.758 | Open | AP Only | AP Only | MineField |  | MBT Project-119 | Baghlan Demining Project-07 |  |  |  |  | 1397 |  | {0B57230C-4A2E-47DE-9F6A-2B41A39D8BD2} |  | Medium | Critical Infrastracture | Moderate | 167 | CHA | 2 |  |  | 2004-09-02 16:30 | No | Open
North East | Baghlan | Dushi | Akhundzadakhel | {DF28DE1E-7CBE-48D4-A099-CAEA86CBDE53} | c0a8-0057-12c3b73980d-c22934f2-10793- | BF-HQ-15018 | HT - HALO TRUST | B/2753 | 374400 | 68.8172 | 35.8673 | Worked on | UXO Only | UXO Only | BF | 1392/1393 | MBT Project-121/F | Baghlan Demining Project-15/F | DOS | Yes | 2012-04-01 | 2014-09-23 | 1393 | HT | {DF28DE1E-7CBE-48D4-A099-CAEA86CBDE53} |  | Medium | Critical Infrastracture | Low | 36 | CHA | 3 |  |  | 2010-09-14 | No | Planned
North East | Baghlan | Dushi | Akhundzadakhel | {DF28DE1E-7CBE-48D4-A099-CAEA86CBDE53} | c0a8-00f6-1352e393d67-e133e63f-e2-836 | BF-15170 | HT - HALO TRUST | B/2793 | 155000 | 68.7787 | 35.8745 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes | 2013-06-03 | 2013-06-05 | 1392-1393 | HT | {DF28DE1E-7CBE-48D4-A099-CAEA86CBDE53} |  |  |  | Low | 38 | CHA | 3 |  |  | 2011-12-21 16:30 | No | Planned
North East | Baghlan | Dushi | Akhundzadakhel | {DF28DE1E-7CBE-48D4-A099-CAEA86CBDE53} | c0a8-00f6-1386aba5119-2593f749-44b5-1 | Hz-ID-17118 | HT - HALO TRUST | B/3102 | 185850 | 68.8086 | 35.8782 | Closed | UXO Only | UXO Only | BF | 1391/1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes | 2012-08-06 | 2014-04-23 | 1392-1393 | HT | {DF28DE1E-7CBE-48D4-A099-CAEA86CBDE53} |  |  |  | Low | 72 | CHA | 3 |  |  | 2012-06-02 16:30 | No | Planned
North East | Baghlan | Dushi | Akhundzadakhel | {DF28DE1E-7CBE-48D4-A099-CAEA86CBDE53} | c0a8-00f6-1386ac120ef-f88b28f-451b-8e | Hz-ID-17117 | HT - HALO TRUST | B/3101 | 127600 | 68.7981 | 35.8818 | Closed | UXO Only | UXO Only | BF | 1391/1392 | MBT Project-121/F | Baghlan Demining Project-15/F | DOS | Yes | 2013-11-01 | 2014-03-23 | 1393 | HT | {DF28DE1E-7CBE-48D4-A099-CAEA86CBDE53} | Rahmuddin s/o Mohammad Din |  |  | Low | 758 | CHA | 3 |  |  | 2012-06-01 16:30 | No | Planned
North East | Baghlan | Dushi | Baghe Qadzi | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} | c0a8-0009-1454b44119c-b591524d-1055-b | Hz-ID-18621 | HT - HALO TRUST | H/8921 | 108100 | 68.8034 | 35.739 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} |  | Low | Agriculture Blocked | Low | 61 | CHA | 5 |  |  | 2014-03-15 16:30 | No | Open
North East | Baghlan | Dushi | Baghe Qadzi | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} | c0a8-0057-12c3b68b347-b5b65665-840e-b | MF-HT-500 | HT - HALO TRUST | H/3137 | 12500 | 68.7601 | 35.733 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-121/F | Baghlan Demining Project-15/F | DOS | Yes | 2014-05-01 |  | 1393 | HT | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} |  | Low | Agriculture Blocked | Low | 14 | CHA | 4 |  |  | 2010-03-07 10:29 | No | Planned
North East | Baghlan | Dushi | Baghe Qadzi | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} | c0a8-0057-12c3b6b0611-383f86de-9f54-f | MF-HT-503 | HT - HALO TRUST | H/3138 | 40573 | 68.7637 | 35.7367 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes | 2014-01-04 | 2014-06-22 | 1392-1393 | None | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} |  |  |  | Low | 4 | CHA | 5 |  |  | 2010-03-06 11:12 | No | Planned
North East | Baghlan | Dushi | Baghe Qadzi | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} | c0a8-0057-12c3b712e98-35c2c53d-ea72-d | MF-HT-514 | HT - HALO TRUST | H/3142 | 13480 | 68.7888 | 35.7547 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes | 2014-01-01 | 2014-03-23 | 1392-1393 | None | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} |  |  |  | Low | 5 | CHA | 4 |  |  | 2010-03-08 11:23 | No | Planned
North East | Baghlan | Dushi | Baghe Qadzi | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} | c0a8-0057-12c3b775422-c835b25c-133bb- | MF-HT-397 | HT - HALO TRUST | H/2306 | 24000 | 68.7668 | 35.7416 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-121/F | Baghlan Demining Project-15/F | DOS | Yes | 2014-04-01 | 2014-06-23 | 1393 | HT | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} |  |  |  | Low | 1 | CHA | 5 |  |  | 2010-03-08 11:12 | No | Planned
North East | Baghlan | Dushi | Baghe Qadzi | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} | c0a8-0057-12c3b7c88da-6ecaf208-17010- | MF-HT-506 | HT - HALO TRUST | H/3140 | 14300 | 68.7798 | 35.7477 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes | 2014-04-01 | 2014-06-23 | 1393 | HT | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} |  |  |  | Low | 7 | CHA | 5 |  |  | 2010-03-08 | No | Planned
North East | Baghlan | Dushi | Baghe Qadzi | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} | c0a8-0057-12c3b7c8b1b-b160a923-1702b- | MF-HT-508 | HT - HALO TRUST | H/3141 | 15340 | 68.7819 | 35.7501 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes | 2014-01-01 | 2014-06-23 | 1392-1393 | HT | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} |  |  |  | Low | 5 | CHA | 5 |  |  | 2007-12-16 11:03 | No | Planned
North East | Baghlan | Dushi | Baghe Qadzi | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} | c0a8-0057-12c3b954915-3feb55fa-280ae- | MF-HT-400 | HT - HALO TRUST | H/2310 | 2860 | 68.7758 | 35.745 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-121/E | Baghlan Demining Project-15/E | B-AAR | Yes |  |  | 1393 | HT | {6E20EDE4-21A3-4738-A558-3CFAA6E21000} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2010-03-07 | No | Planned
North East | Baghlan | Dushi | Belawsang | {D03F24FA-CF6F-4C31-91F7-F0B586F2EF1D} | c0a8-0057-12c3b6a41eb-db2b6223-9623-f | MF-NE-534 | HT - HALO TRUST | H/4723 | 4400 | 68.7726 | 35.6511 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {D03F24FA-CF6F-4C31-91F7-F0B586F2EF1D} |  | Low | Agriculture Blocked | Low | 8 | CHA | 5 |  |  | 2010-04-05 | No | Open
North East | Baghlan | Dushi | Belawsang | {D03F24FA-CF6F-4C31-91F7-F0B586F2EF1D} | c0a8-0057-12c3b8b0525-1704be13-21314- | MF-NE-533 | HT - HALO TRUST | H/4722 | 42000 | 68.7664 | 35.6271 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {D03F24FA-CF6F-4C31-91F7-F0B586F2EF1D} | Based on amendment 37, removed from project list | Low | Agriculture Blocked | Low | 1 | CHA | 4 |  |  | 2008-05-18 | No | Open
North East | Baghlan | Dushi | Belawsang | {D03F24FA-CF6F-4C31-91F7-F0B586F2EF1D} | c0a8-0057-12c3b8e4651-3028e648-23789- | MF-NE-535 | HT - HALO TRUST | H/4724 | 26000 | 68.7869 | 35.6355 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {D03F24FA-CF6F-4C31-91F7-F0B586F2EF1D} | Based on amendment 37, removed from project list | Low | Agriculture Blocked | Low | 2 | CHA | 4 |  |  | 2008-05-18 | No | Open
North East | Baghlan | Dushi | Belawsang | {D03F24FA-CF6F-4C31-91F7-F0B586F2EF1D} | c0a8-0057-12c3badf025-d79be0c8-3748d- | MF-NE-589 | HT - HALO TRUST | H/4726 | 30000 | 68.7546 | 35.6161 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {D03F24FA-CF6F-4C31-91F7-F0B586F2EF1D} | Based on amendment 37, removed from project list | Low | Agriculture Blocked | Low | 7 | CHA | 4 |  |  | 2008-05-18 | No | Open
North East | Baghlan | Dushi | Chehelkapa-i-Larkhaw | {F264F394-876A-4000-8AE0-7487ABFFD6B8} | c0a8-0057-12c3b82cd97-fb83aa31-1b6bf- | MF-NE-516 | HT - HALO TRUST | H/2326 | 100000 | 68.8594 | 35.8541 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-031 | Baghlan Demining Project-14 | VTF-Canada | Yes | 2012-12-10 | 2013-03-23 | 1391 | HT | {F264F394-876A-4000-8AE0-7487ABFFD6B8} | Based on amendment 37, included in 1391 work plan |  |  | Low | 24 |  | 5 |  |  | 2008-09-06 | No | Complete
North East | Baghlan | Dushi | Chehelkapa-i-Larkhaw | {F264F394-876A-4000-8AE0-7487ABFFD6B8} | c0a8-0057-12c3bb4d92a-d42dabcb-3b672- | MF-NE-512 | HT - HALO TRUST | H/4750 | 412261 | 68.8563 | 35.798 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {F264F394-876A-4000-8AE0-7487ABFFD6B8} |  | Low | Agriculture Blocked | Low | 6 | CHA | 5 |  |  | 2008-06-22 | No | Planned
North East | Baghlan | Dushi | Dahane Darrahe Ghori | {8B7BCEA8-BEB9-4E61-90E0-ADC745C8231C} | c0a8-0057-12c3b82e55b-9b0432fb-1b7be- | MF-NE-587 | HT - HALO TRUST | H/4734 | 60 | 68.9219 | 35.7526 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-031 | Baghlan Demining Project-14 | VTF-Canada | Yes | 2012-10-01 | 2012-12-23 | 1391 | HT | {8B7BCEA8-BEB9-4E61-90E0-ADC745C8231C} |  |  |  | Low | 23 |  | 3 |  |  | 2008-06-05 | No | Complete
North East | Baghlan | Dushi | Dahane Darrahe Ghori | {8B7BCEA8-BEB9-4E61-90E0-ADC745C8231C} | c0a8-0057-12c3b82e75e-b02f9684-1b7d2- | MF-NE-585 | HT - HALO TRUST | H/4732 | 7500 | 68.9173 | 35.7544 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {8B7BCEA8-BEB9-4E61-90E0-ADC745C8231C} |  | Low | Agriculture Blocked | Low | 23 | CHA | 5 |  |  | 2008-06-04 | No | Open
North East | Baghlan | Dushi | Dahane Darrahe Ghori | {8B7BCEA8-BEB9-4E61-90E0-ADC745C8231C} | c0a8-0057-12c3b82e903-a3a00c35-1b7eb- | MF-NE-586 | HT - HALO TRUST | H/4733 | 3700 | 68.9228 | 35.7528 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-031 | Baghlan Demining Project-14 | VTF-Canada | Yes | 2012-10-01 | 2012-12-23 | 1391 | HT | {8B7BCEA8-BEB9-4E61-90E0-ADC745C8231C} |  |  |  | Low | 23 |  | 4 |  |  | 2008-06-04 | No | Complete
North East | Baghlan | Dushi | Dahane Darrahe Ghori | {8B7BCEA8-BEB9-4E61-90E0-ADC745C8231C} | c0a8-0057-12c3b82eac7-45e16701-1b7fd- | MF-NE-588 | HT - HALO TRUST | H/4735 | 1100 | 68.9231 | 35.7523 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-031 | Baghlan Demining Project-14 | VTF-Canada | Yes | 2012-10-01 | 2012-12-23 | 1391 | HT | {8B7BCEA8-BEB9-4E61-90E0-ADC745C8231C} |  |  |  | Low | 23 |  | 3 |  |  | 2008-06-05 | No | Complete
North East | Baghlan | Dushi | Dahane Darrahe Ghori | {8B7BCEA8-BEB9-4E61-90E0-ADC745C8231C} | c0a8-0057-12c3b8ec56e-794edb79-23cac- | MF-NE-641 | HT - HALO TRUST | H/5119 | 57000 | 68.9393 | 35.7133 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {8B7BCEA8-BEB9-4E61-90E0-ADC745C8231C} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2008-09-05 | No | Open
North East | Baghlan | Dushi | Dahane Khojasafa | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} | c0a8-0009-145456d2c15-6c46ddf6-38a-47 | Hz-ID-18609 | HT - HALO TRUST | H/8912 | 48737 | 68.8428 | 35.7926 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} |  | Low | Agriculture Blocked | Low | 6 | CHA | 5 |  |  | 2014-02-17 16:30 | No | Open
North East | Baghlan | Dushi | Dahane Khojasafa | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} | c0a8-0009-14545c6d525-af3347b5-3dd-51 | Hz-ID-18611 | HT - HALO TRUST | H/8913 | 32647 | 68.8413 | 35.7976 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} |  | Low | Agriculture Blocked | Low | 7 | CHA | 5 |  |  | 2014-02-19 16:30 | No | Open
North East | Baghlan | Dushi | Dahane Khojasafa | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} | c0a8-0009-14545fabcef-f77e391f-441-be | Hz-ID-18612 | HT - HALO TRUST | H/8914 | 53275 | 68.844 | 35.7956 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} |  | Low | Agriculture Blocked | Low | 7 | CHA | 5 |  |  | 2014-02-21 16:30 | No | Open
North East | Baghlan | Dushi | Dahane Khojasafa | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} | c0a8-0009-14549ea69bd-78203686-548-16 | Hz-ID-18614 | HT - HALO TRUST | H/8915 | 1944 | 68.843 | 35.8 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2014-02-22 16:30 | No | Open
North East | Baghlan | Dushi | Dahane Khojasafa | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} | c0a8-0009-1466b8d2f5b-c26555a-5c2-b8b | Hz-ID-18789 | HT - HALO TRUST | H/8924 | 369961 | 68.865 | 35.7989 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} |  | Low | Agriculture Blocked | Low | 21 | CHA | 5 |  |  | 2014-04-19 16:30 | No | Open
North East | Baghlan | Dushi | Dahane Khojasafa | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} | c0a8-0009-14689831d99-b952d5ff-21e2-5 | Hz-ID-18791 | HT - HALO TRUST | H/8925 | 235840 | 68.8676 | 35.807 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2014-04-20 16:30 | No | Open
North East | Baghlan | Dushi | Dahane Khojasafa | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} | c0a8-0057-12c3bb64cc0-ac3b93f-3c37b-a | MF-NE-483 | HT - HALO TRUST | H/2313 | 48600 | 68.8491 | 35.8011 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/C | Baghlan Demining Project-15/C | CIDA | Yes | 2013-11-03 | 2014-04-23 | 1392-1393 | HT | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} |  |  |  | Low | 14 | CHA | 5 |  |  | 2010-04-08 | No | Complete
North East | Baghlan | Dushi | Dahane Khojasafa | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} | c0a8-0057-12c3bb64f10-3d400fd9-3c394- | MF-NE-486 | HT - HALO TRUST | H/4141 | 37500 | 68.8492 | 35.8009 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/C | Baghlan Demining Project-15/C | CIDA | Yes | 2013-12-01 | 2014-05-23 | 1392-1393 |  | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} |  |  |  | Low | 3 | CHA | 5 |  |  | 2010-04-08 | No | Complete
North East | Baghlan | Dushi | Dahane Khojasafa | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} | c0a8-0057-12c3bb65383-4af1c35f-3c3ad- | MF-HQ-14601 | HT - HALO TRUST | H/6552 | 68500 | 68.847 | 35.8005 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/C | Baghlan Demining Project-15/C | CIDA | Yes | 2014-01-01 | 2014-05-23 | 1392-1393 | HT | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} |  |  |  | Low | 14 | CHA | 5 |  |  | 2010-04-08 | No | Complete
North East | Baghlan | Dushi | Dahane Khojasafa | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} | c0a8-0057-12c3bb65641-13c76582-3c3d4- | MF-HQ-14610 | HT - HALO TRUST | H/6551 | 22100 | 68.8506 | 35.8025 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/C | Baghlan Demining Project-15/C | CIDA | Yes | 2013-12-01 | 2014-03-23 | 1392-1393 | HT | {51B144E2-C621-4E1E-92B7-8BC27134CEBC} |  |  |  | Low | 3 | CHA | 5 |  |  | 2010-04-08 | No | Complete
North East | Baghlan | Dushi | Dahane Khwaja zaid | {F7EF25C8-EC74-4900-82B6-92641C2CF30F} | c0a8-00f6-1353d60c043-e33291a8-174a-b | BF-15198 | HT - HALO TRUST | B/2743 | 0 | 68.7452 | 35.5863 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes |  |  | 1392-1393 | HT | {F7EF25C8-EC74-4900-82B6-92641C2CF30F} |  |  |  | Low | 0 | CHA | 3 |  |  | 2010-02-26 16:30 | Yes | Planned
North East | Baghlan | Dushi | Dahane Kuru | {5E33AF02-313F-4149-B132-393C7E93C3BC} | c0a8-0057-12c3b89cbe0-91df5aba-20571- | MF-NE-565 | HT - HALO TRUST | H/2312 | 100000 | 68.8294 | 35.5526 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {5E33AF02-313F-4149-B132-393C7E93C3BC} | Based on amendment 37, removed from project list | Low | Agriculture Blocked | Low | 2 | CHA | 4 |  |  | 2008-06-02 | No | Open
North East | Baghlan | Dushi | Dahane Kuru | {5E33AF02-313F-4149-B132-393C7E93C3BC} | c0a8-0057-12c3b9423e4-47aede45-274cc- | MF-NE-566 | HT - HALO TRUST | H/4729 | 57000 | 68.8277 | 35.5584 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {5E33AF02-313F-4149-B132-393C7E93C3BC} |  | Low | Agriculture Blocked | Low | 6 | CHA | 5 |  |  | 2008-06-02 | No | Open
North East | Baghlan | Dushi | Dahane Kuru | {5E33AF02-313F-4149-B132-393C7E93C3BC} | c0a8-0057-12c3b99ba14-1aafdc76-2af99- | MF-NE-563 | HT - HALO TRUST | H/4731 | 46000 | 68.8058 | 35.539 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {5E33AF02-313F-4149-B132-393C7E93C3BC} |  | Low | Agriculture Blocked | Low | 5 | CHA | 5 |  |  | 2008-06-03 | No | Open
North East | Baghlan | Dushi | Dahane Kuru | {5E33AF02-313F-4149-B132-393C7E93C3BC} | c0a8-0057-12c3bb01b63-cd4fe354-38912- | MF-NE-584 | HT - HALO TRUST | H/4730 | 59000 | 68.7902 | 35.5584 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {5E33AF02-313F-4149-B132-393C7E93C3BC} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2008-06-02 | No | Open
North East | Baghlan | Dushi | Daragak | {66CFD39E-FF47-4F70-92AF-87CEEB80E099} | c0a8-0057-12c3b9b5a33-afcfcbb6-2c088- | MF-HQ-14598 | HT - HALO TRUST | H/6605 | 51300 | 68.6686 | 35.6075 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {66CFD39E-FF47-4F70-92AF-87CEEB80E099} |  | Low | Agriculture Blocked | Low | 140 | CHA | 5 |  |  | 2010-04-17 | No | Planned
North East | Baghlan | Dushi | Dosti | {4BD5D453-9002-4C34-A2EC-F6F6A6033099} | c0a8-00f6-135b8365d8e-921be277-a1b-84 | MF-NE-594 | HT - HALO TRUST | H/4717 | 23500 | 68.7802 | 35.5809 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes | 2014-02-01 | 2014-03-23 | 1392-1393 | HT | {4BD5D453-9002-4C34-A2EC-F6F6A6033099} |  |  |  | Low | 14 | CHA | 5 |  |  | 2010-04-20 | No | Planned
North East | Baghlan | Dushi | Dosti | {4BD5D453-9002-4C34-A2EC-F6F6A6033099} | c0a8-00f6-135b83be1ee-b6e20313-acc-5b | MF-NE-592 | HT - HALO TRUST | H/2316 | 26500 | 68.7787 | 35.5805 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes |  |  | 1392-1393 | HT | {4BD5D453-9002-4C34-A2EC-F6F6A6033099} |  |  |  | Low | 14 | CHA | 5 |  |  | 2010-04-20 | No | Planned
North East | Baghlan | Dushi | Kaylahgay | {D58D0C4D-E1C9-4798-AD89-9B4C914C8FD5} | c0a8-0009-142e56636cf-ccdfc31e-6969-7 | Hz-ID-18286 | MCPA - Mine Clearance Planning Agency | AF/1304/13307/MF0014 | 101330 | 68.8732 | 35.9549 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-083 | Baghlan Demining Project-16 | VTF | Yes | 2013-11-02 | 2013-12-31 | 1392 | OMAR | {D58D0C4D-E1C9-4798-AD89-9B4C914C8FD5} |  |  |  | Low | 11 | CHA | 1 |  |  | 2013-12-04 16:30 | No | Complete
North East | Baghlan | Dushi | Kaylahgay | {D58D0C4D-E1C9-4798-AD89-9B4C914C8FD5} | c0a8-0057-12c3bae4748-3b1e113e-377bd- | MF-NE-496 | MCPA - Mine Clearance Planning Agency | AF/1304/13307/MF2324 | 75000 | 68.8689 | 35.9635 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes | 2014-01-01 | 2014-04-23 | 1392-1393 | HT | {D58D0C4D-E1C9-4798-AD89-9B4C914C8FD5} | Based on amendment 37, removed from project list |  |  | Low | 22 | CHA | 1 |  |  | 2008-06-08 | No | Planned
North East | Baghlan | Dushi | Kaylahgay | {D58D0C4D-E1C9-4798-AD89-9B4C914C8FD5} | c0a8-00f6-13a3ab73ade-dc72a487-fd71-d | Hz-ID-17219 | HT - HALO TRUST | B/3104 | 259000 | 68.7974 | 35.8736 | Open | UXO Only | UXO Only | BF |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {D58D0C4D-E1C9-4798-AD89-9B4C914C8FD5} |  | High with Victim | High with Victims | Low | 711 | CHA | 1 |  |  | 2012-07-20 16:30 | No | Open
North East | Baghlan | Dushi | Kaylahgay | {D58D0C4D-E1C9-4798-AD89-9B4C914C8FD5} | c0a8-00f6-13a3abb610a-c5e8a746-fe46-b | Hz-ID-17225 | HT - HALO TRUST | B/3105 | 385000 | 68.8009 | 35.8827 | Open | UXO Only | UXO Only | BF |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {D58D0C4D-E1C9-4798-AD89-9B4C914C8FD5} |  | High with Victim | High with Victims | Low | 896 | CHA | 1 |  |  | 2012-07-21 16:30 | No | Open
North East | Baghlan | Dushi | Khwaja Zayd-Olia | {DD18A031-6976-40ED-B9DD-C6E855237D5F} | c0a8-0057-12c3b853900-5442f4e0-1d2bd- | MF-NE-561 | HT - HALO TRUST | H/4714 | 5670 | 68.6921 | 35.5581 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {DD18A031-6976-40ED-B9DD-C6E855237D5F} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-11-02 16:30 | No | Open
North East | Baghlan | Dushi | Khwaja Zayd-Olia | {DD18A031-6976-40ED-B9DD-C6E855237D5F} | c0a8-0057-12c3ba7a59e-1bce2249-33994- | MF-NE-560 | HT - HALO TRUST | H/2323 | 28000 | 68.7113 | 35.5607 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {DD18A031-6976-40ED-B9DD-C6E855237D5F} |  | Low | Agriculture Blocked | Low | 3 | CHA | 5 |  |  | 2008-05-11 | No | Open
North East | Baghlan | Dushi | Myandeh | {5E6E2661-3CC7-4FE4-88B4-84845A88463C} | c0a8-0057-12c3b813459-32f8edd7-1a48f- | MF-NE-531 | HT - HALO TRUST | H/4728 | 50000 | 68.6698 | 35.5222 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {5E6E2661-3CC7-4FE4-88B4-84845A88463C} | Based on amendment 37, removed from project list | Low | Agriculture Blocked | Low | 0 | CHA | 4 |  |  | 2008-05-20 | No | Open
North East | Baghlan | Dushi | Myandeh | {5E6E2661-3CC7-4FE4-88B4-84845A88463C} | c0a8-0057-12c3b86f3a3-ddc34f30-1e5ac- | MF-NE-532 | HT - HALO TRUST | H/4727 | 55000 | 68.6827 | 35.5266 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {5E6E2661-3CC7-4FE4-88B4-84845A88463C} | Based on amendment 37, removed from project list | Low | Agriculture Blocked | Low | 2 | CHA | 4 |  |  | 2008-05-20 | No | Open
North East | Baghlan | Dushi | Petawak | {7D7FE3E6-3C6F-49FA-884A-9460E5B30E5F} | c0a8-0057-12c3b910163-37a648b4-25404- | MF-NE-466 | HT - HALO TRUST | H/4715 | 50000 | 68.8862 | 35.7866 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {7D7FE3E6-3C6F-49FA-884A-9460E5B30E5F} |  | Low | Agriculture Blocked | Low | 3 | CHA | 5 |  |  | 2007-05-12 | No | Open
North East | Baghlan | Dushi | Piaz Qol | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} | c0a8-0057-12c3b697857-3ffc156c-8cb1-8 | MF-HQ-14372 | HT - HALO TRUST | H/6601 | 44500 | 68.8919 | 35.6877 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-04-10 | No | Open
North East | Baghlan | Dushi | Piaz Qol | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} | c0a8-0057-12c3b6d53dd-84e77c5f-bb6b-4 | MF-HQ-14626 | HT - HALO TRUST | H/6602 | 36000 | 68.7737 | 35.6376 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-04-09 | No | Open
North East | Baghlan | Dushi | Piaz Qol | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} | c0a8-0057-12c3b70751b-2e8715c9-e1b4-f | MF-HQ-14370 | HT - HALO TRUST | H/6603 | 19800 | 68.7737 | 35.6376 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2010-04-07 | No | Open
North East | Baghlan | Dushi | Piaz Qol | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} | c0a8-0057-12c3b71ab15-65fffce1-f063-3 | MF-HQ-14392 | HT - HALO TRUST | H/6604 | 33900 | 68.808 | 35.6424 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-04-13 | No | Open
North East | Baghlan | Dushi | Piaz Qol | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} | c0a8-0057-12c3b9a0008-92813ea6-2b27f- | MF-NE-553 | HT - HALO TRUST | H/2327 | 39000 | 68.7542 | 35.6387 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2010-04-14 | No | Open
North East | Baghlan | Dushi | Piaz Qol | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} | c0a8-0057-12c9770e205-9e6cdcf1-ef4-52 | MF-NE-536 | HT - HALO TRUST | H/4725 | 39500 | 68.8064 | 35.6405 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {0A5A99C1-50B2-431E-8AA5-069BA91E2CF0} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-04-13 | No | Open
North East | Baghlan | Dushi | Qal'a-i-Eshan | {56791C16-1435-4136-AF76-510ADE831AC8} | c0a8-008e-1306d4c7381-97376463-7b-52e | MF-NE-500 | HT - HALO TRUST | H/2329 | 46567 | 68.9065 | 35.7524 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {56791C16-1435-4136-AF76-510ADE831AC8} |  | Low | Agriculture Blocked | Low | 8 | CHA | 5 |  |  | 2008-03-19 | No | Open
North East | Baghlan | Dushi | Qala-i-Kayan | {7BC62140-FC9B-4689-AF17-2EEC514F53B2} | c0a8-0057-12c3ba2b267-33e7494c-30938- | MF-NE-590 | HT - HALO TRUST | H/2322 | 2150 | 68.4685 | 35.6412 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {7BC62140-FC9B-4689-AF17-2EEC514F53B2} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2008-04-15 | No | Open
North East | Baghlan | Dushi | Qaramat | {7028CD34-0308-4239-BACC-974E26468F01} | c0a8-0009-14106188878-ce7e4e49-6a3e-2 | Hz-ID-18158 | HT - HALO TRUST | B/3107 |  | 68.7188 | 35.6411 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {7028CD34-0308-4239-BACC-974E26468F01} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2013-04-16 16:30 | No | Open
North East | Baghlan | Dushi | Qaramat | {7028CD34-0308-4239-BACC-974E26468F01} | c0a8-0009-14106d82171-b42a9604-8e30-a | Hz-ID-18151 | HT - HALO TRUST | B/3106 |  | 68.7385 | 35.9653 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {7028CD34-0308-4239-BACC-974E26468F01} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2013-04-15 16:30 | No | Open
North East | Baghlan | Dushi | Qaramat | {7028CD34-0308-4239-BACC-974E26468F01} | c0a8-0057-12c3b8d5754-922270fb-22cc3- | MF-NE-591 | HT - HALO TRUST | H/2335 | 63500 | 68.7248 | 35.6788 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {7028CD34-0308-4239-BACC-974E26468F01} | Based on amendment 37, removed from project list | High with Victim | High with Victims | Low | 3 | CHA | 2 |  |  | 2007-03-06 | No | Open
North East | Baghlan | Dushi | Qaramat | {7028CD34-0308-4239-BACC-974E26468F01} | c0a8-0057-12c3b9bad40-33cc20b2-2c3cb- | MF-HQ-14438 | HT - HALO TRUST | H/6550 | 35000 | 68.7438 | 35.6592 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-031 | Baghlan Demining Project-14 | VTF-Canada | Yes | 2012-09-03 | 2012-12-23 | 1391 | HT | {7028CD34-0308-4239-BACC-974E26468F01} |  |  |  | Low | 3 |  | 2 |  |  | 2010-03-17 | No | Complete
North East | Baghlan | Dushi | Qaramat | {7028CD34-0308-4239-BACC-974E26468F01} | c0a8-0057-12c3b9bb126-ff398e34-2c3eb- | MF-HQ-14482 | HT - HALO TRUST | H/6549 | 35500 | 68.7478 | 35.6599 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-031 | Baghlan Demining Project-14 | VTF-Canada | Yes | 2012-08-14 | 2012-12-23 | 1391 | HT | {7028CD34-0308-4239-BACC-974E26468F01} |  |  |  | Low | 3 |  | 2 |  |  | 2010-03-17 | No | Complete
North East | Baghlan | Dushi | Qaramat | {7028CD34-0308-4239-BACC-974E26468F01} | c0a8-0057-12c3baee4ae-ab0ea320-37dd6- | MF-HT-494 | HT - HALO TRUST | H/3130 | 56250 | 68.7109 | 35.6716 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {7028CD34-0308-4239-BACC-974E26468F01} | Based on amendment 37, removed from project list | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2007-12-16 09:56 | No | Open
North East | Baghlan | Dushi | Qole Masi | {D9D2B813-7541-47A7-B35F-9D25B5776F2A} | c0a8-00f6-134e643d872-53d72d1f-9e0-3f | MF-16085 | HT - HALO TRUST | H/7436 | 28770 | 68.8039 | 35.7995 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-031 | Baghlan Demining Project-14 | VTF-Canada | Yes | 2012-10-01 | 2012-12-23 | 1391 | HT | {D9D2B813-7541-47A7-B35F-9D25B5776F2A} |  |  |  | Low | 8 |  | 5 |  |  | 2011-04-08 16:30 | No | Complete
North East | Baghlan | Dushi | Qole Masi | {D9D2B813-7541-47A7-B35F-9D25B5776F2A} | c0a8-00f6-134ea2ac35a-49e62091-b8c-26 | MF-16086 | HT - HALO TRUST | H/7435 | 36960 | 68.8039 | 35.7695 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-031 | Baghlan Demining Project-14 | VTF-Canada | Yes | 2012-10-01 | 2012-12-23 | 1391 | HT | {D9D2B813-7541-47A7-B35F-9D25B5776F2A} |  |  |  | Low | 8 |  | 5 |  |  | 2011-04-06 16:30 | No | Complete
North East | Baghlan | Dushi | Qole Masi | {D9D2B813-7541-47A7-B35F-9D25B5776F2A} | c0a8-00f6-134ea2d47ad-7a994048-ba3-25 | MF-16087 | HT - HALO TRUST | H/7434 | 30240 | 68.8039 | 35.7695 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-031 | Baghlan Demining Project-14 | VTF-Canada | Yes | 2012-10-01 | 2012-12-23 | 1391 | HT | {D9D2B813-7541-47A7-B35F-9D25B5776F2A} |  |  |  | Low | 9 |  | 5 |  |  | 2011-04-04 16:30 | No | Complete
North East | Baghlan | Dushi | Rama-Dara | {249A1B4D-38EC-421A-B012-59BB148A0DCB} | c0a8-0057-12c3b90133b-5328467-24a99-e | MF-NE-489 | HT - HALO TRUST | H/4711 | 14700 | 68.6788 | 35.5457 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {249A1B4D-38EC-421A-B012-59BB148A0DCB} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-11-01 16:30 | No | Open
North East | Baghlan | Dushi | Rama-Dara | {249A1B4D-38EC-421A-B012-59BB148A0DCB} | c0a8-0057-12c3b9baa15-82e6c7d2-2c3b5- | MF-NE-494 | HT - HALO TRUST | H/4713 | 25100 | 68.7195 | 35.5522 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {249A1B4D-38EC-421A-B012-59BB148A0DCB} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-11-11 16:30 | No | Open
North East | Baghlan | Dushi | Rama-Dara | {249A1B4D-38EC-421A-B012-59BB148A0DCB} | c0a8-0057-12c3ba17b06-2a8b1733-2fd78- | MF-NE-491 | HT - HALO TRUST | H/4712 | 17640 | 68.6778 | 35.559 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {249A1B4D-38EC-421A-B012-59BB148A0DCB} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2010-10-31 16:30 | No | Open
North East | Baghlan | Dushi | Safi Keylagay | {9BD0B1E2-F1A2-4454-A886-D14FC59ECC35} | c0a8-0057-12c3b8a28ae-ffa524d4-209bd- | MF-NE-538 | HT - HALO TRUST | H/4747 | 28000 | 68.8374 | 35.7994 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-121/B | Baghlan Demining Project-15/B | B-AAR | Yes | 2013-04-01 | 2013-08-23 | 1392 | HT | {9BD0B1E2-F1A2-4454-A886-D14FC59ECC35} |  |  |  | Low | 0 | CHA | 5 |  |  | 2010-04-09 | No | Complete
North East | Baghlan | Dushi | Safi Keylagay | {9BD0B1E2-F1A2-4454-A886-D14FC59ECC35} | c0a8-0057-12c3b8a2ab1-2c7c1709-209d4- | MF-NE-541 | HT - HALO TRUST | H/4748 | 34689 | 68.8413 | 35.7976 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/C | Baghlan Demining Project-15/C | CIDA | Yes | 2014-04-01 | 2014-05-23 | 1392-1393 | HT | {9BD0B1E2-F1A2-4454-A886-D14FC59ECC35} |  |  |  | Low | 8 | CHA | 5 |  |  | 2008-06-20 | No | Complete
North East | Baghlan | Dushi | Safi Keylagay | {9BD0B1E2-F1A2-4454-A886-D14FC59ECC35} | c0a8-0057-12c3b8a2ca4-f020618-209ea-9 | MF-NE-539 | HT - HALO TRUST | H/4749 | 7840 | 68.8443 | 35.7987 | Worked on | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes | 2014-01-01 | 2014-06-23 | 1392-1393 | HT | {9BD0B1E2-F1A2-4454-A886-D14FC59ECC35} |  | Low | Agriculture Blocked | Low | 8 | CHA | 5 |  |  | 2008-06-20 | No | Planned
North East | Baghlan | Dushi | Sangsolakh | {21DF1CA3-D7E8-4D21-B433-8469B138186A} | c0a8-0009-13fa2e62f11-ce5a1990-ad9-6c | Hz-ID-17925 | HT - HALO TRUST | H/8429 | 33150 | 68.7822 | 35.7532 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes | 2013-11-11 | 2014-07-11 | 1392-1393 | HT | {21DF1CA3-D7E8-4D21-B433-8469B138186A} |  |  |  | Low | 15 | CHA | 5 |  |  | 2013-04-11 16:30 | No | Planned
North East | Baghlan | Dushi | Sangsolakh | {21DF1CA3-D7E8-4D21-B433-8469B138186A} | c0a8-0057-12c3b6b5394-fc7a099b-a316-e | MF-HQ-14612 | HT - HALO TRUST | H/6554 | 25500 | 68.7682 | 35.7447 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-121/E | Baghlan Demining Project-15/E | B-AAR | Yes | 2014-04-01 |  | 1393 | HT | {21DF1CA3-D7E8-4D21-B433-8469B138186A} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2010-04-11 | No | Planned
North East | Baghlan | Dushi | Sangsolakh | {21DF1CA3-D7E8-4D21-B433-8469B138186A} | c0a8-0057-12c3b74ce75-b63e0fc1-1160f- | MF-HQ-14453 | HT - HALO TRUST | H/6553 | 23500 | 68.7721 | 35.7465 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {21DF1CA3-D7E8-4D21-B433-8469B138186A} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2010-04-11 | No | Open
North East | Baghlan | Dushi | Sangsolakh | {21DF1CA3-D7E8-4D21-B433-8469B138186A} | c0a8-0057-12c3b87ec60-74321e81-1f0d8- | MF-NE-548 | HT - HALO TRUST | H/2333 | 63750 | 68.7947 | 35.7616 | Closed | AP Only | AP Only | MineField | 1391/1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes | 2012-06-11 | 2013-06-23 | 1392-1393 | HT | {21DF1CA3-D7E8-4D21-B433-8469B138186A} |  |  |  | Low | 5 | CHA | 5 |  |  | 2008-05-05 | No | Planned
North East | Baghlan | Dushi | Sangsolakh | {21DF1CA3-D7E8-4D21-B433-8469B138186A} | c0a8-0057-12c3b87ee15-335dbb0b-1f0ec- | MF-NE-546 | HT - HALO TRUST | H/4708 | 65000 | 68.7947 | 35.7616 | Closed | AP Only | AP Only | MineField | 1391/1392 | MBT Project-121/B | Baghlan Demining Project-15/B | B-AAR | Yes | 2012-12-11 | 2013-12-23 | 1392 | HT | {21DF1CA3-D7E8-4D21-B433-8469B138186A} |  |  |  | Low | 5 | CHA | 4 |  |  | 2008-05-05 | No | Complete
North East | Baghlan | Dushi | Tazun | {D87610CF-3E0A-4597-99D6-DE9FCE73B035} | c0a8-0057-12c3bb71fb5-f272c19-3cac6-c | MF-NE-555 | HT - HALO TRUST | H/4719 | 42000 | 68.7736 | 35.5466 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {D87610CF-3E0A-4597-99D6-DE9FCE73B035} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2008-05-21 | No | Open
North East | Baghlan | Dushi | Zard Sang | {A9DAAE9F-B1D1-47BE-91F4-D56464F754CA} | c0a8-0057-12c3b74c12d-ac0526b-11572-a | MF-HQ-14479 | HT - HALO TRUST | H/6548 | 44500 | 68.7852 | 35.6853 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {A9DAAE9F-B1D1-47BE-91F4-D56464F754CA} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2010-03-15 | No | Open
North East | Baghlan | Khinjan | Ab Mazar | {74BDE5AE-C53C-44C0-B0C7-1CD6762A7ECE} | c0a8-0057-12c3b95431c-b411aafd-28077- | MF-HT-390 | HT - HALO TRUST | H/2305 | 38000 | 68.9011 | 35.663 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {74BDE5AE-C53C-44C0-B0C7-1CD6762A7ECE} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2007-12-13 10:34 | No | Open
North East | Baghlan | Khinjan | Aspandak | {97AA9ECC-2914-416A-A5A6-7294EDF235EB} | c0a8-0057-12c3b887472-4fc800e3-1f6b6- | MF-NE-852 | HT - HALO TRUST | H/4066 | 42486 | 68.9238 | 35.5122 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {97AA9ECC-2914-416A-A5A6-7294EDF235EB} |  | Low | Agriculture Blocked | Low | 10 | CHA | 5 |  |  | 2006-08-12 | No | Open
North East | Baghlan | Khinjan | Bajga | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | c0a8-0009-140a4d489e5-a213dfc7-3932-e | Hz-ID-18107 | HT - HALO TRUST | H/8426 | 32600 | 69.0161 | 35.5787 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes | 2014-04-01 | 2014-04-23 | 1393 | HT | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} |  |  |  | Low | 46 | CHA | 3 |  |  | 2013-07-11 16:30 | No | Planned
North East | Baghlan | Khinjan | Bajga | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | c0a8-0057-12c3b6ae76b-56e50d57-9dfe-a | MF-HQ-13166 | HT - HALO TRUST | H/6334 | 22100 | 69.017 | 35.5814 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes |  |  | 1391 | HT | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} |  |  |  | Low | 133 |  | 3 |  |  | 2009-08-31 | No | Complete
North East | Baghlan | Khinjan | Bajga | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | c0a8-0057-12c3b70edf1-f013744f-e764-f | MF-HQ-14983 | HT - HALO TRUST | H/7304 | 64800 | 69.0095 | 35.5776 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes | 2012-09-04 | 2012-12-23 | 1391 | HT | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | Based on amendment 37, included in 1391 work plan |  |  | Low | 32 |  | 5 |  |  | 2010-08-20 | No | Complete
North East | Baghlan | Khinjan | Bajga | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | c0a8-0057-12c3b79ab30-45016994-14f08- | MF-HQ-14988 | HT - HALO TRUST | H/7305 | 67500 | 69.0069 | 35.5752 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-120/A | Baghlan Demining Project-13/A | GAGP | Yes | 2013-11-01 | 2014-06-21 | 1392-1393 | HT | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} |  |  |  | Low | 14 | CHA | 5 |  |  | 2010-08-21 | No | Planned
North East | Baghlan | Khinjan | Bajga | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | c0a8-0057-12c3b918116-73693f75-258ba- | MF-HT-574 | HT - HALO TRUST | H/3950 | 950 | 69.0211 | 35.5838 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | Contingency Plan for North/Northeast German RFP | High | Water Blocked | Low | 45 | CHA | 3 |  |  | 2007-09-26 15:29 | No | Pledged
North East | Baghlan | Khinjan | Bajga | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | c0a8-0057-12c3b9186a1-6405ebc3-258f2- | MF-HT-571 | HT - HALO TRUST | H/3949 | 6650 | 69.0183 | 35.5863 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | Contingency Plan for North/Northeast German RFP | High | Water Blocked | Low | 45 | CHA | 3 |  |  | 2007-09-29 15:07 | No | Pledged
North East | Baghlan | Khinjan | Bajga | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | c0a8-0057-12c3b918a97-4445523e-2590c- | MF-HT-579 | HT - HALO TRUST | H/3951 | 1450 | 69.0206 | 35.5857 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | Contingency Plan for North/Northeast German RFP | High | Water Blocked | Low | 45 | CHA | 3 |  |  | 2007-09-26 15:47 | No | Pledged
North East | Baghlan | Khinjan | Bajga | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | c0a8-0057-12c3ba4791a-b254f2d-31a88-c | MF-HT-1193 | HT - HALO TRUST | H/3999 | 190860 | 69.0112 | 35.5576 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-08-18 | No | Open
North East | Baghlan | Khinjan | Bajga | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} | c0a8-0057-12c3ba4e12e-c4aeb536-31e61- | MF-HT-860 | HT - HALO TRUST | H/2381 | 180000 | 69.0089 | 35.5886 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes |  |  | 1391 | HT | {1C9E67C9-0DCD-4433-8D42-05FE1B87999E} |  |  |  | Low | 32 |  | 3 |  |  | 2006-08-12 | No | Complete
North East | Baghlan | Khinjan | Chandaran | {B5558BD0-3FF9-4A84-BAFD-BF254BBC6E72} | c0a8-0057-12c3b82bd23-2ad8e8e-1b600-7 | MF-NE-809 | HT - HALO TRUST | H/2431 | 20000 | 68.9308 | 35.4326 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {B5558BD0-3FF9-4A84-BAFD-BF254BBC6E72} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2007-12-07 | No | Open
North East | Baghlan | Khinjan | Chandaran | {B5558BD0-3FF9-4A84-BAFD-BF254BBC6E72} | c0a8-0057-12c3b96f15a-58996ed5-2920e- | MF-NE-843 | HT - HALO TRUST | H/2422 | 73741 | 68.9193 | 35.5322 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {B5558BD0-3FF9-4A84-BAFD-BF254BBC6E72} |  | Low | Agriculture Blocked | Low | 93 | CHA | 5 |  |  | 2008-07-03 | No | Open
North East | Baghlan | Khinjan | Chandaran | {B5558BD0-3FF9-4A84-BAFD-BF254BBC6E72} | c0a8-0057-12c3ba0b1d0-726e1534-2f5e6- | MF-NE-807 | HT - HALO TRUST | H/4958 | 67432 | 68.9275 | 35.5295 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {B5558BD0-3FF9-4A84-BAFD-BF254BBC6E72} |  | Low | Agriculture Blocked | Low | 84 | CHA | 4 |  |  | 2008-07-05 | No | Open
North East | Baghlan | Khinjan | Charmaghzak | {9E7EBB26-6939-463E-9D2D-8B74281F3500} | c0a8-0009-13d0ff29cb4-7c14ac2c-3c13-8 | Hz-ID-17577 | MCPA - Mine Clearance Planning Agency | AF/1306/00482/MF0009 | 41224 | 68.9903 | 35.4491 | Open | AP Only | AP Only | MineField |  | MBT Project-028 | Baghlan Demining Project-09 | DOS |  |  |  | 1393 |  | {9E7EBB26-6939-463E-9D2D-8B74281F3500} |  | High with Victim | High with Victims | Low | 1 | CHA | 2 |  |  | 2012-12-17 16:30 | No | Pledged
North East | Baghlan | Khinjan | Charmaghzak | {9E7EBB26-6939-463E-9D2D-8B74281F3500} | c0a8-0057-12c3b876ee9-3d838d83-1eb2a- | MF-NE-768 | HT - HALO TRUST | H/5105 | 60000 | 68.9714 | 35.4425 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {9E7EBB26-6939-463E-9D2D-8B74281F3500} | Contingency plan for North/Northeast German RFP | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2008-08-03 | No | Pledged
North East | Baghlan | Khinjan | Charmaghzak | {9E7EBB26-6939-463E-9D2D-8B74281F3500} | c0a8-0057-12c3b8770eb-5d5b7fd5-1eb42- | MF-NE-763 | HT - HALO TRUST | H/2396 | 60000 | 68.9714 | 35.4425 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {9E7EBB26-6939-463E-9D2D-8B74281F3500} | Contingency Plan for North/Northeast German RFP | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2008-08-03 | No | Pledged
North East | Baghlan | Khinjan | Charmaghzak | {9E7EBB26-6939-463E-9D2D-8B74281F3500} | c0a8-0057-12c3b8772ee-cd3608a2-1eb5b- | MF-NE-767 | HT - HALO TRUST | H/2394 | 75000 | 68.9714 | 35.4425 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {9E7EBB26-6939-463E-9D2D-8B74281F3500} | Contingecy Plan for North/Northeast German RFP | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2008-08-03 | No | Pledged
North East | Baghlan | Khinjan | Charmaghzak | {9E7EBB26-6939-463E-9D2D-8B74281F3500} | c0a8-0057-12c3b8774e1-3ad5af9f-1eb75- | MF-NE-769 | HT - HALO TRUST | H/5106 | 65000 | 68.9714 | 35.4425 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {9E7EBB26-6939-463E-9D2D-8B74281F3500} | Contingency Plan for North/Northeast German RFP | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2008-08-03 | No | Pledged
North East | Baghlan | Khinjan | Chawgani | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} | c0a8-0009-142e1c2ec2e-917951c9-5f69-7 | Hz-ID-18275 | HT - HALO TRUST | H/8868 | 69320 | 68.8918 | 35.5885 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes | 2014-03-11 | 2014-05-23 | 1392-1393 | HT | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} |  |  |  | Low | 75 | CHA | 5 |  |  | 2013-11-01 16:30 | No | Planned
North East | Baghlan | Khinjan | Chawgani | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} | c0a8-0009-142e55a8c04-d8724433-6627-d | Hz-ID-18270 | HT - HALO TRUST | H/8863 | 51140 | 68.889 | 35.5857 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes |  |  | 1392-1393 | HT | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} |  |  |  | Low | 22 | CHA | 5 |  |  | 2013-11-02 16:30 | No | Planned
North East | Baghlan | Khinjan | Chawgani | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} | c0a8-0009-142e55be663-624a7f3f-6679-7 | Hz-ID-18271 | HT - HALO TRUST | H/8864 | 59560 | 68.889 | 35.5857 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes |  |  | 1392-1393 | HT | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} |  |  |  | Low | 22 | CHA | 5 |  |  | 2013-11-03 16:30 | No | Planned
North East | Baghlan | Khinjan | Chawgani | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} | c0a8-0009-142e55ce1e0-2f69bd0c-66d2-c | Hz-ID-18274 | HT - HALO TRUST | H/8867 | 48615 | 68.8918 | 35.5885 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes | 2014-01-11 | 2014-04-24 | 1392-1393 | HT | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} |  |  |  | Low | 51 | CHA | 5 |  |  | 2013-11-02 16:30 | No | Planned
North East | Baghlan | Khinjan | Chawgani | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} | c0a8-0009-142e560993b-1ebb5510-6786-8 | Hz-ID-18273 | HT - HALO TRUST | H/8866 | 44880 | 68.889 | 35.5857 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes | 2014-03-05 | 2014-04-24 | 1392-1393 | HT | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} |  |  |  | Low | 22 | CHA | 5 |  |  | 2013-11-04 16:30 | No | Planned
North East | Baghlan | Khinjan | Chawgani | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} | c0a8-0009-142e560ab16-ed219c5a-67a4-1 | Hz-ID-18269 | HT - HALO TRUST | H/8862 | 55100 | 68.889 | 35.5857 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes |  |  | 1392-1393 | HT | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} |  |  |  | Low | 51 | CHA | 5 |  |  | 2013-11-01 16:30 | No | Planned
North East | Baghlan | Khinjan | Chawgani | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} | c0a8-0009-142e56122c4-608716d0-67c5-3 | Hz-ID-18272 | HT - HALO TRUST | H/8865 | 51213 | 68.889 | 35.5857 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-121/A | Baghlan Demining Project-15/A | Bilateral | Yes | 2014-01-11 | 2014-04-16 | 1392-1393 | HT | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} |  |  |  | Low | 22 | CHA | 5 |  |  | 2013-11-03 16:30 | No | Planned
North East | Baghlan | Khinjan | Chawgani | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} | c0a8-00f6-1356ffbe2b6-ae5744f7-111-34 | BF-15204 | HT - HALO TRUST | B/2726 | 0 | 68.8841 | 35.6011 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes |  |  | 1392-1393 | HT | {BD6219CF-B5C9-421C-B4B7-807A7AA06E49} |  |  |  | Low | 0 | CHA | 2 |  |  | 2009-08-06 16:30 | Yes | Planned
North East | Baghlan | Khinjan | Dahana-e-Mazar | {7D5095E2-E188-4FE4-A8B5-FEF702B50603} | c0a8-0057-12c3b9b8a37-9f01ed8b-2c274- | MF-NE-810 | HT - HALO TRUST | H/5115 | 43000 | 69.0311 | 35.5434 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {7D5095E2-E188-4FE4-A8B5-FEF702B50603} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2008-08-19 | No | Open
North East | Baghlan | Khinjan | Dahane Kawa | {0AD9B4A1-FDAC-4A4A-8A0E-D03D6584981D} | c0a8-0057-12c3bb641d7-66fdd3fc-3c309- | MF-HT-406 | HT - HALO TRUST | H/2388 | 1000 | 68.9395 | 35.6023 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No | 2010-06-17 | 2010-06-21 | 1393 | WRA | {0AD9B4A1-FDAC-4A4A-8A0E-D03D6584981D} | Planned for EOD Teams | High with Victim | High with Victims | Low | 2876 | CHA | 3 |  |  | 2007-12-03 11:51 | No | Pledged
North East | Baghlan | Khinjan | Dahan-e Valian | {BAC0B5FE-9300-40E5-B4F0-B50D31477634} | c0a8-0009-1454b4e1a6a-6f82d937-1112-f | Hz-ID-18622 | HT - HALO TRUST | H/8922 | 13737 | 68.8872 | 35.5763 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {BAC0B5FE-9300-40E5-B4F0-B50D31477634} |  | Low | Agriculture Blocked | Low | 6 | CHA | 5 |  |  | 2014-03-18 16:30 | No | Open
North East | Baghlan | Khinjan | Dargak | {06EA8AA2-7F9D-451F-B3BA-574A4A2819F2} | c0a8-008e-130824da0ee-944dab74-684-ba | MF-HT-992 | HT - HALO TRUST | H/2379 | 5900 | 69.0318 | 35.5377 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {06EA8AA2-7F9D-451F-B3BA-574A4A2819F2} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2006-08-16 11:15 | No | Open
North East | Baghlan | Khinjan | Doawi | {55567BA3-522C-407F-A20A-80C9E5A3D6FC} | c0a8-0009-140a4c061a9-aca3f7a0-36fd-a | Hz-ID-18112 | HT - HALO TRUST | H/8574 | 52130 | 69.0148 | 35.6461 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {55567BA3-522C-407F-A20A-80C9E5A3D6FC} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2013-07-27 16:30 | No | Open
North East | Baghlan | Khinjan | Doawi | {55567BA3-522C-407F-A20A-80C9E5A3D6FC} | c0a8-0009-140a4c335e6-23193b0b-3729-1 | Hz-ID-18111 | HT - HALO TRUST | H/8573 | 74360 | 69.0036 | 35.6491 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {55567BA3-522C-407F-A20A-80C9E5A3D6FC} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2013-07-19 16:30 | No | Open
North East | Baghlan | Khinjan | Doawi | {55567BA3-522C-407F-A20A-80C9E5A3D6FC} | c0a8-0009-140a4c66675-bedb35dc-376b-5 | Hz-ID-18110 | HT - HALO TRUST | H/8572 | 59640 | 68.9978 | 35.6503 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {55567BA3-522C-407F-A20A-80C9E5A3D6FC} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2013-07-18 16:30 | No | Open
North East | Baghlan | Khinjan | Doawi | {55567BA3-522C-407F-A20A-80C9E5A3D6FC} | c0a8-0009-140a4cb4b62-2e85bece-37a0-8 | Hz-ID-18109 | HT - HALO TRUST | H/8571 | 64284 | 68.9858 | 35.6446 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {55567BA3-522C-407F-A20A-80C9E5A3D6FC} |  | Low | Agriculture Blocked | Low | 19 | CHA | 5 |  |  | 2013-07-16 16:30 | No | Open
North East | Baghlan | Khinjan | Doshakh | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | c0a8-0057-12c3b6bcd73-fc189d39-a8e1-b | MF-HQ-15005 | HT - HALO TRUST | H/6639 | 224000 | 69.0032 | 35.3999 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | Removed from HT 1391 plan based on HT revised plan | High with Victim | High with Victims | Low | 36 | CHA | 5 |  |  | 2010-09-14 | No | Open
North East | Baghlan | Khinjan | Doshakh | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | c0a8-0057-12c3b6be40e-d618e966-aa09-c | MF-HT-758 | HT - HALO TRUST | H/2397 | 91600 | 69.0048 | 35.4036 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | Based on HALO Trust e-mail received on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet) the hazard removed from | High with Victim | High with Victims | Low | 36 | CHA | 4 |  |  | 2010-08-04 | No | Open
North East | Baghlan | Khinjan | Doshakh | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | c0a8-0057-12c3b734991-6777e927-103ec- | MF-HQ-15004 | HT - HALO TRUST | H/6638 | 123600 | 69.0048 | 35.4036 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | Based on HALO Trust e-mail received on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet) the hazard removed from | High with Victim | High with Victims | Low | 36 | CHA | 5 |  |  | 2010-09-14 | No | Open
North East | Baghlan | Khinjan | Doshakh | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | c0a8-0057-12c3b7ab3d5-ec9e0703-15b05- | BF-HQ-14940 | HT - HALO TRUST | B/2751 | 43832 | 68.996 | 35.4063 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {E97E8436-4CD9-4153-8C50-7B1A7D493134} |  | High with Victim | High with Victims | Low | 746 | CHA | 3 |  |  | 2010-08-13 | No | Pledged
North East | Baghlan | Khinjan | Doshakh | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | c0a8-0057-12c3b7c705b-65c6c163-16ee2- | MF-HT-1206 | HT - HALO TRUST | H/2393 | 44000 | 68.9893 | 35.4095 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {E97E8436-4CD9-4153-8C50-7B1A7D493134} |  | High with Victim | High with Victims | Low | 16 | CHA | 5 |  |  | 2006-08-03 | No | Open
North East | Baghlan | Khinjan | Doshakh | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | c0a8-0057-12c3b92e936-f1e83298-267a1- | MF-NE-748 | HT - HALO TRUST | H/5112 | 76440 | 68.9918 | 35.4313 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {E97E8436-4CD9-4153-8C50-7B1A7D493134} |  | High with Victim | High with Victims | Low | 1 | CHA | 5 |  |  | 2008-08-11 | No | Open
North East | Baghlan | Khinjan | Doshakh | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | c0a8-0057-12c3b970019-c3cda76-292a4-b | MF-NE-757 | HT - HALO TRUST | H/2441 | 13000 | 68.9356 | 35.4886 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {E97E8436-4CD9-4153-8C50-7B1A7D493134} |  | High with Victim | High with Victims | Low | 103 | CHA | 5 |  |  | 2008-07-04 | No | Open
North East | Baghlan | Khinjan | Doshakh | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | c0a8-0057-12c3b9a04c9-c5f4f808-2b2b1- | MF-NE-846 | HT - HALO TRUST | H/5111 | 110000 | 68.9834 | 35.4348 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {E97E8436-4CD9-4153-8C50-7B1A7D493134} |  | High with Victim | High with Victims | Low | 0 | CHA | 5 |  |  | 2008-08-09 | No | Open
North East | Baghlan | Khinjan | Doshakh | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | c0a8-0057-12c3bae4a35-1a8cf0ef-377d3- | MF-NE-842 | HT - HALO TRUST | H/2392 | 55000 | 68.9879 | 35.4051 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {E97E8436-4CD9-4153-8C50-7B1A7D493134} |  | High with Victim | High with Victims | Low | 10 | CHA | 5 |  |  | 2008-08-12 | No | Open
North East | Baghlan | Khinjan | Doshakh | {E97E8436-4CD9-4153-8C50-7B1A7D493134} | c0a8-0057-12c3bb63144-3df5edab-3c2b3- | MF-NE-755 | HT - HALO TRUST | H/2417 | 44100 | 68.9938 | 35.4337 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {E97E8436-4CD9-4153-8C50-7B1A7D493134} |  | High with Victim | High with Victims | Low | 0 | CHA | 5 |  |  | 2008-08-10 | No | Open
North East | Baghlan | Khinjan | Gardana-i Ghunj | {456579DC-6961-4149-A2A7-661A9E5B7CD3} | c0a8-0057-12c3bb6ad45-fb2aa3f-3c6cf-2 | MF-NE-775 | HT - HALO TRUST | H/4966 | 100000 | 68.951 | 35.5007 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {456579DC-6961-4149-A2A7-661A9E5B7CD3} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2008-07-11 | No | Open
North East | Baghlan | Khinjan | Gaza Gill | {D3CD26CA-4721-4E39-926F-0A93F09B4700} | c0a8-0009-1467f045ad8-9e54e2c9-1c39-4 | Hz-ID-18358 | HT - HALO TRUST | B/3111 | 280531 | 68.8235 | 35.5966 | Open | UXO Only | UXO Only | BF |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {D3CD26CA-4721-4E39-926F-0A93F09B4700} |  | Medium | Critical Infrastracture | Low | 275 | CHA | 3 |  |  | 2013-12-07 16:30 | No | Open
North East | Baghlan | Khinjan | Gaza Gill | {D3CD26CA-4721-4E39-926F-0A93F09B4700} | c0a8-0057-12c3b69a13b-ad6c2eb4-8ea5-b | MF-HQ-14481 | HT - HALO TRUST | H/6546 | 37500 | 68.8331 | 35.5505 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {D3CD26CA-4721-4E39-926F-0A93F09B4700} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2010-03-11 | No | Open
North East | Baghlan | Khinjan | Gaza Gill | {D3CD26CA-4721-4E39-926F-0A93F09B4700} | c0a8-0057-12c3b7712bf-804f4015-130dd- | MF-HQ-14499 | HT - HALO TRUST | H/6547 | 49500 | 68.8327 | 35.548 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {D3CD26CA-4721-4E39-926F-0A93F09B4700} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2010-03-11 | No | Open
North East | Baghlan | Khinjan | Gori Sokhta | {9F00491D-BB39-4484-8BF4-7D2A3E232239} | c0a8-0057-12c3b7a04b4-fe33ee1d-15318- | MF-HT-1142 | HT - HALO TRUST | H/2404 | 12500 | 68.9615 | 35.4684 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {9F00491D-BB39-4484-8BF4-7D2A3E232239} |  | Medium | Critical Infrastracture | Low | 1433 | CHA | 3 |  |  | 2006-08-01 | No | Open
North East | Baghlan | Khinjan | Gori Sokhta | {9F00491D-BB39-4484-8BF4-7D2A3E232239} | c0a8-0057-12c3b8dcc92-bb91ec0b-231be- | MF-NE-835 | HT - HALO TRUST | H/5101 | 60500 | 68.968 | 35.4603 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes |  |  | 1391 | HT | {9F00491D-BB39-4484-8BF4-7D2A3E232239} |  |  |  | Low | 114 |  | 3 |  |  | 2008-08-02 | No | Complete
North East | Baghlan | Khinjan | Gori Sokhta | {9F00491D-BB39-4484-8BF4-7D2A3E232239} | c0a8-0057-12c3b91f8dd-1bf61426-25df5- | MF-NE-837 | HT - HALO TRUST | H/4968 | 45000 | 68.974 | 35.4659 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {9F00491D-BB39-4484-8BF4-7D2A3E232239} |  | Low | Agriculture Blocked | Low | 108 | CHA | 4 |  |  | 2008-08-02 | No | Open
North East | Baghlan | Khinjan | Gori Sokhta | {9F00491D-BB39-4484-8BF4-7D2A3E232239} | c0a8-0057-12c3b91fb4d-8bba8f9d-25e10- | MF-NE-834 | HT - HALO TRUST | H/2434 | 34000 | 68.9697 | 35.465 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes |  |  | 1391 | HT | {9F00491D-BB39-4484-8BF4-7D2A3E232239} |  |  |  | Low | 103 |  | 3 |  |  | 2008-08-02 | No | Complete
North East | Baghlan | Khinjan | Gori Sokhta | {9F00491D-BB39-4484-8BF4-7D2A3E232239} | c0a8-0057-12c3b98510d-d64391c5-2a098- | MF-NE-836 | HT - HALO TRUST | H/4969 | 60000 | 68.9667 | 35.469 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {9F00491D-BB39-4484-8BF4-7D2A3E232239} | Based on amendment 37, removed form project list | Low | Agriculture Blocked | Low | 10 | CHA | 3 |  |  | 2008-08-01 | No | Pledged
North East | Baghlan | Khinjan | Gori Sokhta | {9F00491D-BB39-4484-8BF4-7D2A3E232239} | c0a8-0057-12c3ba311b4-615aca6e-30cd4- | MF-NE-841 | HT - HALO TRUST | H/5108 | 81900 | 68.9901 | 35.4422 | Open | AP Only | AP Only | MineField | Blank | MBT Project-120 | Baghlan Demining Project-13 |  | No |  |  | 1396 | None | {9F00491D-BB39-4484-8BF4-7D2A3E232239} | Contingency Plan for North/Northeast German RFP | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2008-08-07 | No | Open
North East | Baghlan | Khinjan | Gori Sokhta | {9F00491D-BB39-4484-8BF4-7D2A3E232239} | c0a8-008e-13121eeb46d-d8e37560-38f-fb | MF-NE-765 | HT - HALO TRUST | H/2409 | 24480 | 68.9703 | 35.4582 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes |  |  | 1391 | HT | {9F00491D-BB39-4484-8BF4-7D2A3E232239} |  |  |  | Low | 135 |  | 3 |  |  | 2008-08-02 | No | Complete
North East | Baghlan | Khinjan | Gori Sokhta | {9F00491D-BB39-4484-8BF4-7D2A3E232239} | c0a8-00f6-134ea2f0eeb-a60ea90c-bbd-1a | MF-16081 | HT - HALO TRUST | H/7492 | 80100 | 68.968 | 35.4603 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {9F00491D-BB39-4484-8BF4-7D2A3E232239} |  | Low | Agriculture Blocked | Low | 11 | CHA | 5 |  |  | 2011-04-16 16:30 | No | Open
North East | Baghlan | Khinjan | Hesar | {8D4EFD76-2394-4506-A7D9-75FA523CC32B} | c0a8-0009-13bdad993ba-693e95c8-e06-73 | Hz-ID-17512 | HT - HALO TRUST | H/8424 | 45180 | 68.9313 | 35.4933 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {8D4EFD76-2394-4506-A7D9-75FA523CC32B} |  | Low | Agriculture Blocked | Low | 92 | CHA | 5 |  |  | 2012-11-18 16:30 | No | Open
North East | Baghlan | Khinjan | Hesar | {8D4EFD76-2394-4506-A7D9-75FA523CC32B} | c0a8-0009-13bdadfc2ff-b947ff89-e25-46 | Hz-ID-17513 | HT - HALO TRUST | H/8425 | 44640 | 68.9313 | 35.4933 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {8D4EFD76-2394-4506-A7D9-75FA523CC32B} |  | Low | Agriculture Blocked | Low | 10 | CHA | 5 |  |  | 2012-11-19 16:30 | No | Open
North East | Baghlan | Khinjan | Hesar | {8D4EFD76-2394-4506-A7D9-75FA523CC32B} | c0a8-0057-12c3b897d16-6d1ec26c-20242- | MF-HT-733 | HT - HALO TRUST | H/2424 | 40000 | 68.9381 | 35.4976 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes | 2012-07-10 | 2012-10-08 | 1391 | HT | {8D4EFD76-2394-4506-A7D9-75FA523CC32B} |  |  |  | Low | 86 |  | 3 |  |  | 2006-08-17 | No | Complete
North East | Baghlan | Khinjan | Hesar | {8D4EFD76-2394-4506-A7D9-75FA523CC32B} | c0a8-0057-12c3ba3ca76-f9ff1f3d-3138f- | MF-NE-832 | HT - HALO TRUST | H/2405 | 70000 | 68.9233 | 35.4873 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {8D4EFD76-2394-4506-A7D9-75FA523CC32B} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2008-07-04 | No | Open
North East | Baghlan | Khinjan | Khenjan | {9E916876-6B7A-45E3-A558-F755304D1061} | c0a8-0009-13df393baa7-7c893d5b-1478-b | Hz-ID-17793 | HT - HALO TRUST | H/8428 | 17200 | 68.9174 | 35.5829 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes | 2014-04-01 | 2014-05-13 | 1393 | HT | {9E916876-6B7A-45E3-A558-F755304D1061} |  |  |  | Low | 82 | CHA | 2 |  |  | 2013-03-19 16:30 | No | Planned
North East | Baghlan | Khinjan | Khenjan | {9E916876-6B7A-45E3-A558-F755304D1061} | c0a8-0057-12c3bad60f2-94898930-36f02- | MF-HT-485 | HT - HALO TRUST | H/2433 | 35000 | 69.0025 | 35.3666 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {9E916876-6B7A-45E3-A558-F755304D1061} | Contingency Plan for North/Northeast German RFP | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2007-10-07 08:51 | No | Pledged
North East | Baghlan | Khinjan | Khobdara | {78E5DE31-31DC-493E-A129-3CB37B5C78EB} | c0a8-00c9-12fddaeb630-391ae42e-9c5-64 | MF-NE-827 | HT - HALO TRUST | H/2445 | 60000 | 68.892 | 35.5157 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {78E5DE31-31DC-493E-A129-3CB37B5C78EB} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2008-07-02 | No | Open
North East | Baghlan | Khinjan | Khobdara | {78E5DE31-31DC-493E-A129-3CB37B5C78EB} | c0a8-00c9-12fddb0375c-11dc9304-9e0-a9 | MF-NE-826 | HT - HALO TRUST | H/2390 | 40300 | 68.881 | 35.5135 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {78E5DE31-31DC-493E-A129-3CB37B5C78EB} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2007-12-11 | No | Open
North East | Baghlan | Khinjan | Khoja-qalat | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} | c0a8-0009-140a4bcff90-6e99e880-36b4-c | Hz-ID-18113 | HT - HALO TRUST | H/8575 | 6440 | 69.0216 | 35.6072 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-120/B | Baghlan Demining Project-13/B | B-Germany | Yes |  |  | 1392 | HT | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} |  |  |  | Low | 128 | CHA | 4 |  |  | 2013-07-28 16:30 | No | Complete
North East | Baghlan | Khinjan | Khoja-qalat | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} | c0a8-0009-140d83c233b-ecf79f43-1271-5 | Hz-ID-18114 | HT - HALO TRUST | H/8576 | 117000 | 69.018 | 35.6109 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-120/B | Baghlan Demining Project-13/B | B-Germany | Yes | 2013-11-01 | 2013-12-23 | 1392 | HT | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} |  |  |  | Low | 93 | CHA | 5 |  |  | 2013-07-29 16:30 | No | Complete
North East | Baghlan | Khinjan | Khoja-qalat | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} | c0a8-0009-14106a06f97-f26703a9-7d5f-6 | Hz-ID-18157 | HT - HALO TRUST | H/8588 | 66280 | 69.0073 | 35.6129 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-121/D | Baghlan Demining Project-15/D | CIDA | Yes | 2014-02-03 | 2014-04-23 | 1392 | HT | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} |  |  |  | Low | 18 | CHA | 5 |  |  | 2013-08-19 16:30 | No | Complete
North East | Baghlan | Khinjan | Khoja-qalat | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} | c0a8-0009-14106a57cda-e6a15802-7e7e-a | Hz-ID-18156 | HT - HALO TRUST | H/8587 | 42170 | 69.0294 | 35.6169 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} |  | Low | Agriculture Blocked | Low | 44 | CHA | 5 |  |  | 2013-08-20 16:30 | No | Open
North East | Baghlan | Khinjan | Khoja-qalat | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} | c0a8-0009-14106a9ae50-5e4b1966-84b5-7 | Hz-ID-18155 | HT - HALO TRUST | H/8580 | 88100 | 69.0099 | 35.6141 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-121/D | Baghlan Demining Project-15/D | CIDA | Yes | 2014-01-01 | 2014-03-23 | 1392 | HT | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} |  |  |  | Low | 18 | CHA | 5 |  |  | 2013-08-18 16:30 | No | Complete
North East | Baghlan | Khinjan | Khoja-qalat | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} | c0a8-0009-14106c2e71b-5ddf3b6e-8d12-b | Hz-ID-18154 | HT - HALO TRUST | H/8579 | 72950 | 69.0117 | 35.6125 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-121/D | Baghlan Demining Project-15/D | CIDA | Yes | 2013-12-01 | 2014-03-23 | 1392 | HT | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} |  |  |  | Low | 18 | CHA | 5 |  |  | 2013-08-17 16:30 | No | Complete
North East | Baghlan | Khinjan | Khoja-qalat | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} | c0a8-0009-14106cea6b3-aa0894aa-8d7e-e | Hz-ID-18153 | HT - HALO TRUST | H/8578 | 67960 | 69.0131 | 35.6133 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-121/D | Baghlan Demining Project-15/D | CIDA | Yes | 2014-01-01 | 2014-04-23 | 1392 | HT | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} |  |  |  | Low | 19 | CHA | 5 |  |  | 2013-08-15 16:30 | No | Complete
North East | Baghlan | Khinjan | Khoja-qalat | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} | c0a8-0009-1410724e40b-86b5a83b-9ee8-a | Hz-ID-18150 | HT - HALO TRUST | H/8577 | 128720 | 69.014 | 35.6125 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-120/B | Baghlan Demining Project-13/B | B-Germany | Yes | 2013-11-01 | 2013-11-23 | 1392 | HT | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} |  |  |  | Low | 19 | CHA | 5 |  |  | 2013-08-13 16:30 | No | Complete
North East | Baghlan | Khinjan | Khoja-qalat | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} | c0a8-0057-12c3b6ca346-b2cd2e3f-b30f-8 | MF-HT-1166 | HT - HALO TRUST | H/3934 | 5700 | 69.0141 | 35.6022 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} |  | Low | Agriculture Blocked | Low | 116 | CHA | 4 |  |  | 2009-04-09 | No | Open
North East | Baghlan | Khinjan | Khoja-qalat | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} | c0a8-0057-12c3b6f838e-4ea4037b-d629-8 | MF-HT-1250 | HT - HALO TRUST | H/3984 | 405000 | 69.0201 | 35.6081 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes | 2012-10-01 | 2013-03-27 | 1391 | HT | {3D0C68E8-8A50-4B1E-9285-EAA1860867B6} | Based on amendment 37, included in 1391 work plan |  |  | Low | 165 |  | 4 |  |  | 2009-04-09 | No | Complete
North East | Baghlan | Khinjan | Khushkak | {FF78DEE9-1EE7-45BE-9F56-FA549551DE08} | c0a8-0009-141a101559c-c5fbe3c9-3a9c-e | Hz-ID-18189 | HT - HALO TRUST | H/8589 | 145485 | 69.1008 | 35.5204 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {FF78DEE9-1EE7-45BE-9F56-FA549551DE08} |  | Low | Agriculture Blocked | Low | 6 | CHA | 5 |  |  | 2013-09-02 16:30 | No | Open
North East | Baghlan | Khinjan | Khushkak | {FF78DEE9-1EE7-45BE-9F56-FA549551DE08} | c0a8-0009-141a102c0bb-9af6c28b-3ab6-a | Hz-ID-18191 | HT - HALO TRUST | H/8590 | 170112 | 69.1008 | 35.5204 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {FF78DEE9-1EE7-45BE-9F56-FA549551DE08} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2013-09-03 16:30 | No | Open
North East | Baghlan | Khinjan | Khushkak | {FF78DEE9-1EE7-45BE-9F56-FA549551DE08} | c0a8-0057-12c3b93e1d9-a3d50476-271fa- | MF-NE-743 | HT - HALO TRUST | H/2407 | 33200 | 69.0502 | 35.5221 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {FF78DEE9-1EE7-45BE-9F56-FA549551DE08} |  | Low | Agriculture Blocked | Low | 279 | CHA | 4 |  |  | 2010-08-11 | No | Open
North East | Baghlan | Khinjan | Khushkak | {FF78DEE9-1EE7-45BE-9F56-FA549551DE08} | c0a8-00f6-13532710935-dd85ec6e-4ff-95 | MF-16549 | HT - HALO TRUST | H/7485 | 474180 | 69.0143 | 35.506 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {FF78DEE9-1EE7-45BE-9F56-FA549551DE08} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-07-12 16:30 | No | Open
North East | Baghlan | Khinjan | Kohe Sohrab | {EB0DA36C-796A-43DE-9871-B13B5E16BA2C} | c0a8-0057-12c3b7f16b1-c31226b9-18c86- | MF-HT-1241 | HT - HALO TRUST | H/3959 | 32000 | 69.038 | 35.5356 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {EB0DA36C-796A-43DE-9871-B13B5E16BA2C} |  | Low | Agriculture Blocked | Low | 12 | CHA | 5 |  |  | 2007-10-01 | No | Open
North East | Baghlan | Khinjan | Kohe Sohrab | {EB0DA36C-796A-43DE-9871-B13B5E16BA2C} | c0a8-00f6-1353df396db-5bf1178a-1ad4-4 | MF-16529 | HT - HALO TRUST | H/7484 | 577500 | 69.0143 | 35.506 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {EB0DA36C-796A-43DE-9871-B13B5E16BA2C} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-07-12 16:30 | No | Open
North East | Baghlan | Khinjan | Kohi Chilcha | {F1F87BBD-20D6-49E0-AAAD-91F9692C39A1} | c0a8-0057-12c3b706be7-e6fbc286-e14d-1 | MF-HQ-15008 | HT - HALO TRUST | H/6640 | 294000 | 69.009 | 35.5517 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {F1F87BBD-20D6-49E0-AAAD-91F9692C39A1} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2010-09-14 | No | Open
North East | Baghlan | Khinjan | Kohi Chilcha | {F1F87BBD-20D6-49E0-AAAD-91F9692C39A1} | c0a8-0057-12c3b8d26d3-e67d964-22aad-7 | MF-HT-433 | HT - HALO TRUST | H/2399 | 850000 | 68.9837 | 35.5135 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {F1F87BBD-20D6-49E0-AAAD-91F9692C39A1} |  | Low | Agriculture Blocked | Low | 0 | CHA | 4 |  |  | 2010-08-08 | No | Open
North East | Baghlan | Khinjan | Kohi Chilcha | {F1F87BBD-20D6-49E0-AAAD-91F9692C39A1} | c0a8-0057-12c3b910e9b-ba08f37-2548a-2 | MF-HT-1232 | HT - HALO TRUST | H/4000 | 52800 | 68.9937 | 35.5339 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {F1F87BBD-20D6-49E0-AAAD-91F9692C39A1} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-08-08 | No | Open
North East | Baghlan | Khinjan | Kuhnadeh | {0CAA8C3B-B901-4451-B741-E4B2B43BCDD1} | c0a8-0057-12c3b8801a4-66d0f642-1f1c2- | MF-NE-740 | HT - HALO TRUST | H/5114 | 95000 | 69.0892 | 35.5055 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {0CAA8C3B-B901-4451-B741-E4B2B43BCDD1} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2008-08-18 | No | Open
North East | Baghlan | Khinjan | Lalm | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} | c0a8-0009-142e56174f9-103d1eeb-67f9-2 | Hz-ID-18277 | HT - HALO TRUST | H/8870 | 79195 | 68.9482 | 35.5028 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} |  | Low | Agriculture Blocked | Low | 15 | CHA | 5 |  |  | 2013-11-21 16:30 | No | Open
North East | Baghlan | Khinjan | Lalm | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} | c0a8-0057-12c3b7c1320-462680ca-16aa0- | MF-NE-870 | HT - HALO TRUST | H/4065 | 43251 | 68.92 | 35.5075 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} |  | Low | Agriculture Blocked | Low | 8 | CHA | 5 |  |  | 2007-12-03 | No | Open
North East | Baghlan | Khinjan | Lalm | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} | c0a8-0057-12c3b925b51-ddc28f93-261e3- | MF-NE-805 | HT - HALO TRUST | H/2421 | 8140 | 68.9231 | 35.505 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} |  | Low | Agriculture Blocked | Low | 8 | CHA | 5 |  |  | 2007-12-04 | No | Open
North East | Baghlan | Khinjan | Lalm | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} | c0a8-0057-12c3b978165-726ee4f4-2980d- | MF-NE-804 | HT - HALO TRUST | H/4067 | 67540 | 68.9455 | 35.5062 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2007-12-14 | No | Open
North East | Baghlan | Khinjan | Lalm | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} | c0a8-0057-12c3b9783b6-66c4a8dc-29826- | MF-NE-802 | HT - HALO TRUST | H/2427 | 47750 | 68.9455 | 35.5062 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2007-12-13 | No | Open
North East | Baghlan | Khinjan | Lalm | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} | c0a8-0057-12c3baa89ae-96c5fe92-3543e- | MF-NE-774 | HT - HALO TRUST | H/2423 | 44610 | 68.9455 | 35.5063 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {D6E87D48-FC8C-4318-BB0F-D64BCCE466D9} |  | Low | Agriculture Blocked | Low | 840 | CHA | 4 |  |  | 2007-12-12 | No | Open
North East | Baghlan | Khinjan | Lisa | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} | c0a8-0057-12c3b892a47-ceac8aa1-1fee5- | MF-NE-825 | HT - HALO TRUST | H/2430 | 59400 | 68.9556 | 35.4776 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes | 2012-09-03 |  | 1391 | HT | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} | Based on amendment 37, included in 1391 work plan |  |  | Low | 67 |  | 4 |  |  | 2008-08-02 | No | Complete
North East | Baghlan | Khinjan | Lisa | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} | c0a8-0057-12c3b892c1a-9e170a8-1fefe-3 | MF-NE-822 | HT - HALO TRUST | H/5103 | 68670 | 68.9584 | 35.4777 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} | Based on amendment 37, removed from project list | Medium | Critical Infrastracture | Low | 0 | CHA | 3 |  |  | 2008-08-02 | No | Pledged
North East | Baghlan | Khinjan | Lisa | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} | c0a8-008e-13290b78662-bc19df95-552-f3 | MF-16082 | HT - HALO TRUST | H/7491 | 50400 | 68.9606 | 35.4797 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-04-10 16:30 | No | Open
North East | Baghlan | Khinjan | Lisa | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} | c0a8-00c9-12fddb1d93f-7e467fb2-9f8-c3 | MF-NE-823 | HT - HALO TRUST | H/5104 | 41400 | 68.959 | 35.4777 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} | Based on amendment 37, removed from project list | Low | Agriculture Blocked | Low | 0 | CHA | 3 |  |  | 2008-08-02 | No | Pledged
North East | Baghlan | Khinjan | Lisa | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} | c0a8-00f6-134ea27fa3b-c0389444-b60-f5 | MF-16084 | HT - HALO TRUST | H/7479 | 73980 | 68.9585 | 35.4777 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} | Based on HALO Trust statement, the hazard is removed from their plan | Low | Agriculture Blocked | Low | 0 | CHA | 4 |  |  | 2011-04-10 16:30 | No | Open
North East | Baghlan | Khinjan | Lisa | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} | c0a8-00f6-135278d37e4-d88acbff-b07-bd | MF-16083 | HT - HALO TRUST | H/7480 | 73080 | 68.9601 | 35.4786 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {7B01DE89-8DC8-4464-97D9-0B144D4B879A} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-07-17 16:30 | No | Open
North East | Baghlan | Khinjan | Mali Khani | {3C2D44D2-C0C2-4E72-9FCC-6FAE3B9B8D59} | c0a8-0057-12c3ba4f875-bdfaa601-31f3d- | MF-NE-791 | HT - HALO TRUST | H/2384 | 60700 | 69.0214 | 35.5755 | Worked on | AP Only | AP Only | MineField | 1392/1393 | MBT Project-120/A | Baghlan Demining Project-13/A | GAGP | Yes | 2013-12-01 | 2014-09-23 | 1392-1393 | HT | {3C2D44D2-C0C2-4E72-9FCC-6FAE3B9B8D59} |  | Low | Agriculture Blocked | Low | 116 | CHA | 5 |  |  | 2006-08-13 | No | Planned
North East | Baghlan | Khinjan | Mali Khani | {3C2D44D2-C0C2-4E72-9FCC-6FAE3B9B8D59} | c0a8-00f6-1353c91322b-ab005795-1442-9 | MF-16627 | HT - HALO TRUST | H/8242 | 1470 | 69.026 | 35.5857 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes |  |  | 1391 | HT | {3C2D44D2-C0C2-4E72-9FCC-6FAE3B9B8D59} |  |  |  | Low | 41 |  | 3 |  |  | 2011-09-20 16:30 | No | Complete
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-0009-13bdac4172e-32e91b67-db7-9b | Hz-ID-17509 | HT - HALO TRUST | H/8421 | 36200 | 68.9517 | 35.4691 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} |  | High with Victim | High with Victims | Low | 27 | CHA | 2 |  |  | 2012-11-08 16:30 | No | Open
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-0009-13c18dbe77b-c22b8610-10ca-1 | Hz-ID-17511 | HT - HALO TRUST | H/8423 | 110400 | 68.9522 | 35.4656 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} |  | High with Victim | High with Victims | Low | 1 | CHA | 2 |  |  | 2012-11-17 16:30 | No | Open
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-0009-13c1e9abe2f-b51815c3-83ea-2 | Hz-ID-17510 | HT - HALO TRUST | H/8422 | 94960 | 68.9522 | 35.4656 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} |  | High with Victim | High with Victims | Low | 1 | CHA | 2 |  |  | 2012-11-16 16:30 | No | Open
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-0057-12c3b6925e5-ec11b735-8917-5 | MF-HQ-15206 | HT - HALO TRUST | H/7311 | 3500 | 68.9495 | 35.4728 | Open | AP Only | AP Only | MineField |  | MBT Project-028 | Baghlan Demining Project-09 | DOS |  |  |  | 1393 |  | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | , | High with Victim | High with Victims | Low | 4 | CHA | 3 |  |  | 2010-09-25 | No | Pledged
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-0057-12c3b742905-47d1025e-10e70- | MF-HQ-14886 | HT - HALO TRUST | H/6632 | 43300 | 68.9473 | 35.4776 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes | 2012-08-13 | 2012-12-23 | 1391 | HT | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} |  |  |  | Low | 123 |  | 2 |  |  | 2010-07-18 | No | Complete
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-0057-12c3b742ceb-17549cc9-10e99- | MF-HQ-14887 | HT - HALO TRUST | H/6633 | 52500 | 68.9445 | 35.4749 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes |  |  | 1391 | HT | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} |  |  |  | Low | 127 |  | 2 |  |  | 2010-07-19 | No | Complete
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-0057-12c3b7f3ae3-8b705cb2-18e15- | MF-NE-779 | HT - HALO TRUST | H/4963 | 100000 | 68.9461 | 35.4606 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | Based on amendment 37, removed from project list | High with Victim | High with Victims | Low | 1 | CHA | 2 |  |  | 2008-07-08 | No | Pledged
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-0057-12c3b8a6ffa-692e0cc5-20cad- | MF-NE-786 | HT - HALO TRUST | H/4962 | 17955 | 68.9495 | 35.4728 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes |  |  | 1391 | HT | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | a |  |  | Low | 30 |  | 2 |  |  | 2008-07-08 | No | Complete
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-0057-12c3b8a724b-f1a90d6-20cd8-7 | MF-NE-790 | HT - HALO TRUST | H/4959 | 80000 | 68.9519 | 35.4772 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | Based on HALO Trust confirmation, the hazard is removed from their plan | High with Victim | High with Victims | Low | 67 | CHA | 2 |  |  | 2008-07-06 | No | Open
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-0057-12c3ba06a28-a7f9d962-2f324- | MF-NE-777 | HT - HALO TRUST | H/4961 | 75000 | 68.9449 | 35.4652 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | Based on HALO Trust e-mail received on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet) the hazard removed from | High with Victim | High with Victims | Low | 1 | CHA | 2 |  |  | 2008-07-07 | No | Pledged
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-008e-131944c6e8e-d695bc75-f45-81 | MF-NE-789 | HT - HALO TRUST | H/4960 | 60000 | 68.952 | 35.4773 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes | 2012-08-10 |  | 1391 | HT | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} |  |  |  | Low | 93 |  | 2 |  |  | 2008-07-06 | No | Complete
North East | Baghlan | Khinjan | Malkhan | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | c0a8-008e-1329f6006a5-d4544c5-1faf-39 | MF-15354 | HT - HALO TRUST | H/7313 | 10050 | 68.9493 | 35.4736 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {5194FEF8-ED5B-4762-8736-2489EADC5BE6} | Based on HALO Trust e-mail recieved on 31 May 2012, the task removed from HT plan (H/7313 this task selected by AMAC NE for VTF emergency team but due to Rostaq new emergency task our team didn't work in this task, you can remove this task too) | High with Victim | High with Victims | Low | 4 | CHA | 2 |  |  | 2010-10-12 16:30 | No | Pledged
North East | Baghlan | Khinjan | Margha | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} | c0a8-0009-140a4d0b086-3ced1315-38ee-e | Hz-ID-18108 | HT - HALO TRUST | H/8427 | 25080 | 69.0058 | 35.5894 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes | 2014-04-01 | 2014-09-23 | 1393 | HT | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} |  | Medium | Critical Infrastracture | Low | 82 | CHA | 3 |  |  | 2013-07-13 16:30 | No | Planned
North East | Baghlan | Khinjan | Margha | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} | c0a8-0009-14375e6a393-9436f530-29ae-4 | Hz-ID-18361 | HT - HALO TRUST | H/8871 | 51811 | 69.0069 | 35.5752 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} |  | Low | Critical Infrastracture | Low | 2 | CHA | 5 |  |  | 2013-12-09 16:30 | No | Open
North East | Baghlan | Khinjan | Margha | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} | c0a8-0009-14375f330cf-fcde1e16-2b12-9 | Hz-ID-18362 | HT - HALO TRUST | H/8872 | 63930 | 69.0069 | 35.5752 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2013-12-10 16:30 | No | Open
North East | Baghlan | Khinjan | Margha | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} | c0a8-0009-14384aad795-8f8ff345-3b8b-b | Hz-ID-18364 | HT - HALO TRUST | H/8873 | 49793 | 69.0797 | 35.5654 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2013-12-11 16:30 | No | Open
North East | Baghlan | Khinjan | Margha | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} | c0a8-0009-14384b125ff-d25ed85d-3cd2-6 | Hz-ID-18368 | HT - HALO TRUST | H/8875 | 78830 | 69.0065 | 35.5594 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2013-12-13 16:30 | No | Open
North East | Baghlan | Khinjan | Margha | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} | c0a8-0009-14384b2a4af-2282b838-3d07-a | Hz-ID-18366 | HT - HALO TRUST | H/8874 | 45158 | 69.008 | 35.5654 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2013-12-12 16:30 | No | Open
North East | Baghlan | Khinjan | Margha | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} | c0a8-0057-12c3bb78bfd-ffbee876-3ceaf- | MF-HT-728 | HT - HALO TRUST | H/2380 | 25000 | 69.0071 | 35.5917 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes |  |  | 1391 | HT | {BC3A2DA7-2A3F-46F3-BE33-DAF0D9FCD9DC} |  |  |  | Low | 61 |  | 3 |  |  | 2006-08-01 | No | Complete
North East | Baghlan | Khinjan | Pasak | {87921399-9895-4B51-9972-D08EB1AA9B79} | c0a8-008e-13127f55c28-5dc4e702-186-be | MF-NE-818 | HT - HALO TRUST | H/2425 | 19826 | 68.925 | 35.5592 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 |  | {87921399-9895-4B51-9972-D08EB1AA9B79} |  | Low | Agriculture Blocked | Low | 81 | CHA | 4 |  |  | 2007-12-06 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3b68c81e-31826d52-8506-1 | BF-HQ-12255 | HT - HALO TRUST | B/1749 | 20000 | 69.0211 | 35.3242 | Open | UXO Only | UXO Only | BF | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes |  |  | 1392-1393 | HT | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Medium | Critical Infrastracture | Low | 94 | CHA | 3 |  |  | 2009-09-09 | No | Planned
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3b68ff62-5f996c04-8780-9 | MF-HQ-14883 | HT - HALO TRUST | H/6629 | 38400 | 69.0246 | 35.3168 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 | None | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Low | Agriculture Blocked | Low | 25 | CHA | 5 |  |  | 2010-07-02 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3b6a28b0-b927264d-9500-a | MF-HQ-14869 | HT - HALO TRUST | H/6594 | 155900 | 69.0295 | 35.3177 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 | None | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Low | Agriculture Blocked | Low | 8 | CHA | 5 |  |  | 2010-07-06 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3b6ccc38-ff69eb84-b500-3 | MF-HQ-14885 | HT - HALO TRUST | H/6631 | 51000 | 69.0258 | 35.3205 | Open | AP Only | AP Only | MineField |  | MBT Project-030 | Baghlan Demining Project-11 |  |  |  |  | 1395 | None | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Low | Agriculture Blocked | Low | 101 | CHA | 4 |  |  | 2010-07-13 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3b70643a-2cfa93e-e0ec-f4 | MF-HQ-14870 | HT - HALO TRUST | H/6595 | 101000 | 69.0295 | 35.3177 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 | None | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Low | Agriculture Blocked | Low | 22 | CHA | 5 |  |  | 2010-07-07 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3b7097c7-f7456aab-e340-3 | MF-HQ-14866 | HT - HALO TRUST | H/6591 | 77700 | 69.0238 | 35.3138 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 | None | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Low | Agriculture Blocked | Low | 32 | CHA | 5 |  |  | 2010-07-02 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3b71378d-a6c8ad42-eae7-2 | MF-HQ-14882 | HT - HALO TRUST | H/6628 | 55200 | 69.0251 | 35.3186 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 | None | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Low | Agriculture Blocked | Low | 21 | CHA | 5 |  |  | 2010-07-02 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3b7321e6-65ad0fdb-10207- | MF-HQ-14884 | HT - HALO TRUST | H/6630 | 44640 | 69.0231 | 35.316 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | Based on HALO Trust statement, the hazard is removed from their plan | Low | Agriculture Blocked | Low | 25 | CHA | 5 |  |  | 2010-07-03 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3b773c8d-7b01fe73-132ae- | MF-HQ-14881 | HT - HALO TRUST | H/6627 | 72400 | 69.0265 | 35.3202 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | Based on HALO Trust confirmation, the hazard is removed from their plan | Low | Agriculture Blocked | Low | 21 | CHA | 4 |  |  | 2010-07-01 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3b785586-9864756a-13f8a- | MF-HQ-14871 | HT - HALO TRUST | H/6596 | 136500 | 69.0336 | 35.3159 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 | None | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Low | Critical Infrastracture | Low | 1 | CHA | 5 |  |  | 2010-07-08 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3b7a17f5-c0f51c7b-153ea- | MF-HQ-14865 | HT - HALO TRUST | H/6590 | 67650 | 69.0181 | 35.3127 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 | None | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Low | Agriculture Blocked | Low | 11 | CHA | 5 |  |  | 2010-07-01 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-0057-12c3bad63cf-cdfd82be-36f17- | MF-NE-840 | HT - HALO TRUST | H/2435 | 42500 | 69.0042 | 35.3654 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | Based on HALO Trust e-mail received on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet) the hazard removed from | Low | Critical Infrastracture | Low | 0 | CHA | 5 |  |  | 2010-07-14 | No | Open
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-008e-1328f888c01-603579-150a-d3a | MF-15804 | HT - HALO TRUST | H/7472 | 98740 | 69.0271 | 35.3234 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Medium | Critical Infrastracture | Low | 7 | CHA | 3 |  |  | 2011-01-01 16:30 | No | Pledged
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-008e-1328fa08886-1cf89506-1f89-2 | MF-15803 | HT - HALO TRUST | H/7471 | 120700 | 69.0271 | 35.3209 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Medium | Critical Infrastracture | Low | 7 | CHA | 3 |  |  | 2011-01-01 16:30 | No | Pledged
North East | Baghlan | Khinjan | Salange Shamali | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} | c0a8-00f6-1353d195ada-8ecfa2b4-155c-6 | MF-16639 | HT - HALO TRUST | H/6587 | 32000 | 68.9868 | 35.3612 | Open | AP Only | AP Only | MineField |  | MBT Project-082 | Baghlan Demining Project-12 |  |  |  |  | 1395 |  | {C8E2A1C9-6F1D-4E30-B082-89EBDC901458} |  | Low | Agriculture Blocked | Low | 5 | CHA | 5 |  |  | 2010-07-04 16:30 | No | Open
North East | Baghlan | Khinjan | Shawool Salang | {274B96EC-0394-40B6-A267-C654476B8AF4} | c0a8-0057-12c3b6eaaa0-55cba7dd-cbe9-6 | MF-HQ-14880 | HT - HALO TRUST | H/6626 | 158400 | 68.9757 | 35.3582 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 | None | {274B96EC-0394-40B6-A267-C654476B8AF4} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-07-05 | No | Open
North East | Baghlan | Khinjan | Shawool Salang | {274B96EC-0394-40B6-A267-C654476B8AF4} | c0a8-0057-12c3b78f387-cb533398-146c0- | MF-HQ-14863 | HT - HALO TRUST | H/6588 | 27000 | 68.9924 | 35.3693 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 | None | {274B96EC-0394-40B6-A267-C654476B8AF4} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-07-05 | No | Open
North East | Baghlan | Khinjan | Shawool Salang | {274B96EC-0394-40B6-A267-C654476B8AF4} | c0a8-0057-12c3b79e082-10cfb1ca-15166- | MF-HQ-14864 | HT - HALO TRUST | H/6589 | 74000 | 68.9852 | 35.372 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 | None | {274B96EC-0394-40B6-A267-C654476B8AF4} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-07-13 | No | Open
North East | Baghlan | Khinjan | Surkhyan | {6A8AF3CC-5C8D-4009-8C8D-993CBB70A2B1} | c0a8-0057-12c3b7312aa-cccb0925-10154- | MF-HQ-14876 | HT - HALO TRUST | H/6600 | 48100 | 68.9231 | 35.5601 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {6A8AF3CC-5C8D-4009-8C8D-993CBB70A2B1} |  | Low | Agriculture Blocked | Low | 14 | CHA | 5 |  |  | 2010-07-19 | No | Open
North East | Baghlan | Khinjan | Surkhyan | {6A8AF3CC-5C8D-4009-8C8D-993CBB70A2B1} | c0a8-0057-12c3b7a2944-8865bfd0-154b6- | MF-HQ-14875 | HT - HALO TRUST | H/6599 | 49900 | 68.9231 | 35.5601 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {6A8AF3CC-5C8D-4009-8C8D-993CBB70A2B1} |  | Low | Agriculture Blocked | Low | 14 | CHA | 5 |  |  | 2010-07-18 | No | Open
North East | Baghlan | Khinjan | Syahsang | {48A32118-7D32-48D0-8C23-0DA5AE4798A7} | c0a8-00c9-12fddb36c32-488bbc64-a29-55 | MF-NE-830 | HT - HALO TRUST | H/4068 | 4375 | 68.9102 | 35.5168 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {48A32118-7D32-48D0-8C23-0DA5AE4798A7} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2007-12-09 | No | Pledged
North East | Baghlan | Khinjan | Syahsang | {48A32118-7D32-48D0-8C23-0DA5AE4798A7} | c0a8-00c9-12fddb51f41-e802a56b-a9a-c0 | MF-NE-831 | HT - HALO TRUST | H/2437 | 69000 | 68.9102 | 35.52 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {48A32118-7D32-48D0-8C23-0DA5AE4798A7} |  | High with Victim | High with Victims | Low | 4 | CHA | 2 |  |  | 2007-12-08 | No | Pledged
North East | Baghlan | Khinjan | Syahsang | {48A32118-7D32-48D0-8C23-0DA5AE4798A7} | c0a8-00c9-12fddb6266e-5a20302c-abf-d1 | MF-NE-829 | HT - HALO TRUST | H/4965 | 31337 | 68.9349 | 35.5186 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {48A32118-7D32-48D0-8C23-0DA5AE4798A7} |  | High with Victim | High with Victims | Low | 14 | CHA | 2 |  |  | 2008-07-09 | No | Pledged
North East | Baghlan | Khinjan | Syahsang | {48A32118-7D32-48D0-8C23-0DA5AE4798A7} | c0a8-00c9-12fddb77fbf-3bdec334-add-c6 | MF-NE-828 | HT - HALO TRUST | H/4964 | 35000 | 68.9346 | 35.5189 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {48A32118-7D32-48D0-8C23-0DA5AE4798A7} |  | High with Victim | High with Victims | Low | 99 | CHA | 2 |  |  | 2008-07-09 | No | Pledged
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-0009-13bda980b41-a5f3a9d6-cf5-2d | Hz-ID-17503 | HT - HALO TRUST | H/8417 | 44600 | 68.9492 | 35.4906 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} |  | High with Victim | High with Victims | Low | 0 | CHA | 4 |  |  | 2012-11-02 16:30 | No | Open
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-0009-13bdaa74798-9dbaa49c-d1b-99 | Hz-ID-17506 | HT - HALO TRUST | H/8418 | 52920 | 68.9515 | 35.4927 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} |  | High with Victim | High with Victims | Low | 0 | CHA | 4 |  |  | 2012-11-03 16:30 | No | Open
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-0009-13bdabd71a2-fd783085-d60-65 | Hz-ID-17507 | HT - HALO TRUST | H/8419 | 13280 | 68.9493 | 35.4854 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} |  | High with Victim | High with Victims | Low | 97 | CHA | 3 |  |  | 2012-11-04 16:30 | No | Open
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-0009-13bdac080eb-f6c7750d-d86-e5 | Hz-ID-17508 | HT - HALO TRUST | H/8420 | 102 | 68.9432 | 35.4859 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} |  | High with Victim | High with Victims | Low | 97 | CHA | 3 |  |  | 2012-11-05 16:30 | No | Planned
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-0057-12c3b88883f-2a36e09b-1f796- | MF-HT-745 | HT - HALO TRUST | H/2440 | 2000 | 68.9454 | 35.4852 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} |  | High with Victim | High with Victims | Low | 97 | CHA | 3 |  |  | 2006-08-03 | No | Pledged
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-0057-12c3b888a04-9e1d99f7-1f7a8- | MF-HT-746 | HT - HALO TRUST | H/2439 | 40500 | 68.9485 | 35.4866 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes | 2012-08-10 | 2012-12-23 | 1391 | HT | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} |  |  |  | Low | 97 |  | 3 |  |  | 2006-08-04 | No | Complete
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-0057-12c3b9f9b86-573cb06e-2eaed- | MF-NE-838 | HT - HALO TRUST | H/2432 | 1950 | 68.9454 | 35.4859 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | Based on HALO Trust e-mail received on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet) the hazard removed from | High with Victim | High with Victims | Low | 97 | CHA | 3 |  |  | 2008-07-13 | No | Pledged
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-0057-12c3b9f9dd7-ad0a3810-2eb0a- | MF-NE-839 | HT - HALO TRUST | H/2438 | 105000 | 68.9332 | 35.4836 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} |  | High with Victim | High with Victims | Low | 8 | CHA | 5 |  |  | 2008-07-12 | No | Open
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-0057-12c3b9fa0f2-fd081237-2eb24- | MF-HT-744 | HT - HALO TRUST | H/2442 | 68000 | 68.9616 | 35.5028 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} |  | High with Victim | High with Victims | Low | 0 | CHA | 5 |  |  | 2008-07-14 | No | Open
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-008e-1328a3936c6-5030ddac-38e-87 | MF-15689 | HT - HALO TRUST | H/7392 | 15400 | 68.9581 | 35.4856 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} |  | High with Victim | High with Victims | Low | 1 | CHA | 5 |  |  | 2010-12-08 16:30 | No | Open
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-008e-1328f9d530f-c1f17918-1e21-e | MF-15688 | HT - HALO TRUST | H/7391 | 43700 | 68.9485 | 35.4866 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes | 2012-09-03 |  | 1391 | HT | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} |  |  |  | Low | 97 |  | 4 |  |  | 2010-12-01 16:30 | No | Complete
North East | Baghlan | Khinjan | Takhtasang | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | c0a8-008e-1329f213b90-d57c79d2-12ff-a | MF-15683 | HT - HALO TRUST | H/7389 | 5050 | 68.9446 | 35.4858 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-029 | Baghlan Demining Project-10 | VTF-Canada | Yes |  |  | 1391 | HT | {02EC61E5-815A-4FD1-B0E8-D1D0B1183D29} | Based on amendment 37, included in 1391 work plan |  |  | Low | 97 |  | 3 |  |  | 2010-11-26 16:30 | No | Complete
North East | Baghlan | Khinjan | Toughan | {22838E25-F376-41FF-AF16-04ACE51E1C59} | c0a8-0057-12c3b817f3d-eb7a6370-1a7e7- | MF-HT-749 | HT - HALO TRUST | H/2383 | 40600 | 69.0394 | 35.5791 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-120/A | Baghlan Demining Project-13/A | GAGP | Yes | 2013-09-01 | 2013-11-23 | 1392-1393 | HT | {22838E25-F376-41FF-AF16-04ACE51E1C59} |  |  |  | Low | 1 | CHA | 5 |  |  | 2006-08-18 | No | Planned
North East | Baghlan | Khinjan | Toughan | {22838E25-F376-41FF-AF16-04ACE51E1C59} | c0a8-008e-1328a37fd15-1cf7f58e-359-84 | MF-15704 | HT - HALO TRUST | H/7395 | 39300 | 69.0441 | 35.5823 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-120/A | Baghlan Demining Project-13/A | GAGP | Yes | 2013-08-01 | 2013-09-23 | 1392-1393 | HT | {22838E25-F376-41FF-AF16-04ACE51E1C59} |  |  |  | Low | 1 | CHA | 5 |  |  | 2010-12-12 16:30 | No | Planned
North East | Baghlan | Khinjan | Toughan | {22838E25-F376-41FF-AF16-04ACE51E1C59} | c0a8-008e-1328a389491-6069660b-373-aa | MF-15690 | HT - HALO TRUST | H/7394 | 39000 | 69.0441 | 35.5823 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-120/A | Baghlan Demining Project-13/A | GAGP | Yes | 2013-09-03 | 2013-11-23 | 1392-1393 | HT | {22838E25-F376-41FF-AF16-04ACE51E1C59} |  |  |  | Low | 2 | CHA | 5 |  |  | 2010-12-12 16:30 | No | Planned
North East | Baghlan | Khinjan | Toughan | {22838E25-F376-41FF-AF16-04ACE51E1C59} | c0a8-008e-1328a3f8730-b2167d9a-49c-99 | MF-15686 | HT - HALO TRUST | H/7393 | 1810 | 69.0401 | 35.5798 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-120/A | Baghlan Demining Project-13/A | GAGP | Yes |  |  | 1392-1393 | HT | {22838E25-F376-41FF-AF16-04ACE51E1C59} |  |  |  | Low | 1 | CHA | 5 |  |  | 2010-12-13 16:30 | No | Planned
North East | Baghlan | Khinjan | Toughan | {22838E25-F376-41FF-AF16-04ACE51E1C59} | c0a8-008e-132d37bb35f-a028777f-908e-6 | MF-15702 | HT - HALO TRUST | H/7397 | 39700 | 69.0448 | 35.5801 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-120/A | Baghlan Demining Project-13/A | GAGP | Yes | 2013-08-01 | 2013-08-23 | 1392-1393 | HT | {22838E25-F376-41FF-AF16-04ACE51E1C59} |  |  |  | Low | 1 | CHA | 5 |  |  | 2010-12-12 16:30 | No | Planned
North East | Baghlan | Khinjan | Toughan | {22838E25-F376-41FF-AF16-04ACE51E1C59} | c0a8-00f6-1356fdc52c3-b6fa5cdd-67-c5a | MF-15703 | HT - HALO TRUST | H/7396 | 34650 | 69.0442 | 35.5805 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-120/A | Baghlan Demining Project-13/A | GAGP | Yes | 2013-08-01 | 2013-09-23 | 1392-1393 | HT | {22838E25-F376-41FF-AF16-04ACE51E1C59} |  |  |  | Low | 1 | CHA | 5 |  |  | 2010-12-12 16:30 | No | Planned
North East | Baghlan | Khinjan | Turkan | {75E4A141-BD70-44A3-8F75-AAAC9A3F468A} | c0a8-0009-142415d56e9-1537b3e3-392a-c | Hz-ID-18224 | HT - HALO TRUST | H/8598 | 44000 | 68.9173 | 35.6261 | Open | AP Only | AP Only | MineField |  | MBT Project-028 | Baghlan Demining Project-09 | DOS |  |  |  | 1393 |  | {75E4A141-BD70-44A3-8F75-AAAC9A3F468A} |  | High with Victim | High with Victims | Low | 12 | CHA | 2 |  |  | 2013-10-06 16:30 | No | Pledged
North East | Baghlan | Khinjan | Turkan | {75E4A141-BD70-44A3-8F75-AAAC9A3F468A} | c0a8-0009-142e1c28310-d839d2f0-5f3b-b | Hz-ID-18276 | HT - HALO TRUST | H/8869 | 30550 | 68.9231 | 35.6119 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {75E4A141-BD70-44A3-8F75-AAAC9A3F468A} |  | High with Victim | High with Victims | Low | 196 | CHA | 2 |  |  | 2013-11-05 16:30 | No | Planned
North East | Baghlan | Khinjan | Turkan | {75E4A141-BD70-44A3-8F75-AAAC9A3F468A} | c0a8-0057-12c3b80368d-2001b80d-19965- | MF-NE-759 | HT - HALO TRUST | H/3958 | 52450 | 68.9167 | 35.624 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {75E4A141-BD70-44A3-8F75-AAAC9A3F468A} |  | High with Victim | High with Victims | Low | 57 | CHA | 2 |  |  | 2007-10-03 | No | Pledged
North East | Baghlan | Khinjan | Turkan | {75E4A141-BD70-44A3-8F75-AAAC9A3F468A} | c0a8-00c9-12fddbb3edd-e2e1f834-b11-28 | MF-HT-487 | HT - HALO TRUST | H/2443 | 56580 | 68.9178 | 35.6246 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {75E4A141-BD70-44A3-8F75-AAAC9A3F468A} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2007-10-03 09:14 | No | Pledged
North East | Baghlan | Khinjan | Yakawlang | {C79FBAB3-DDA8-4F31-9B9C-87361091663E} | c0a8-0057-12c3b6c5c0a-29bcbd7c-afb6-1 | MF-HQ-14979 | HT - HALO TRUST | H/7302 | 450000 | 68.993 | 35.5045 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {C79FBAB3-DDA8-4F31-9B9C-87361091663E} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2010-08-09 | No | Pledged
North East | Baghlan | Khinjan | Yakawlang | {C79FBAB3-DDA8-4F31-9B9C-87361091663E} | c0a8-0057-12c3b6e361e-81ab4099-c63d-a | MF-HQ-14972 | HT - HALO TRUST | H/7301 | 730000 | 68.993 | 35.5045 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {C79FBAB3-DDA8-4F31-9B9C-87361091663E} |  | High with Victim | High with Victims | Low | 0 | CHA | 2 |  |  | 2010-08-09 | No | Pledged
North East | Baghlan | Khinjan | Yakawlang | {C79FBAB3-DDA8-4F31-9B9C-87361091663E} | c0a8-0057-12c3b7b50cd-4fbb8878-161ec- | MF-HQ-14982 | HT - HALO TRUST | H/7303 | 480000 | 69.0055 | 35.5142 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-028 | Baghlan Demining Project-09 | DOS | No |  |  | 1393 | WRA | {C79FBAB3-DDA8-4F31-9B9C-87361091663E} |  | High with Victim | High with Victims | Low | 2 | CHA | 2 |  |  | 2010-08-08 | No | Pledged
North East | Baghlan | Khinjan | Yoch | {F9F52FAA-EC0A-4290-B038-074220FB97B8} | c0a8-0057-12c3b6a991e-1f8d3370-9a55-7 | MF-HQ-11950 | HT - HALO TRUST | H/6102 | 5000 | 69.0536 | 35.5732 | Open | AP Only | AP Only | MineField |  | MBT Project-120 | Baghlan Demining Project-13 |  |  |  |  | 1396 |  | {F9F52FAA-EC0A-4290-B038-074220FB97B8} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2009-04-17 | No | Open
North East | Baghlan | Khost Wa Firing | Myanshahr | {B56E0280-3963-48AB-A8FE-41DA717181B2} | c0a8-0009-142e56547fe-684464bb-691f-7 | Hz-ID-18285 | HT - HALO TRUST | H/8891 | 42100 | 69.5153 | 36.0125 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {B56E0280-3963-48AB-A8FE-41DA717181B2} |  | Low | Critical Infrastracture | Low | 79 | CHA | 5 |  |  | 2013-11-21 16:30 | No | Open
North East | Baghlan | Khwaja Hijran (Jilga Nahrin) | Chahardeh | {EDF65795-ECB4-4CB6-87A5-AFE8BC2B0232} | c0a8-0057-12c3b7c639f-d64b0ab4-16e56- | MF-NE-747 | HT - HALO TRUST | H/5225 | 28400 | 69.2421 | 35.8771 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {EDF65795-ECB4-4CB6-87A5-AFE8BC2B0232} |  | Low | Agriculture Blocked | Moderate | 70 | CHA | 5 |  |  | 2008-11-09 | No | Open
North East | Baghlan | Khwaja Hijran (Jilga Nahrin) | Chahardeh | {EDF65795-ECB4-4CB6-87A5-AFE8BC2B0232} | c0a8-0057-12c3b812481-ce64c256-1a3d5- | MF-NE-744 | HT - HALO TRUST | H/5226 | 45800 | 69.223 | 35.8736 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {EDF65795-ECB4-4CB6-87A5-AFE8BC2B0232} |  | Low | Agriculture Blocked | Moderate | 58 | CHA | 5 |  |  | 2008-11-10 | No | Open
North East | Baghlan | Khwaja Hijran (Jilga Nahrin) | Chahardeh | {EDF65795-ECB4-4CB6-87A5-AFE8BC2B0232} | c0a8-0057-12c3b8126c2-6515ac61-1a3eb- | MF-NE-745 | HT - HALO TRUST | H/5227 | 48200 | 69.2196 | 35.8732 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {EDF65795-ECB4-4CB6-87A5-AFE8BC2B0232} |  | Low | Agriculture Blocked | Moderate | 58 | CHA | 5 |  |  | 2008-11-10 | No | Open
North East | Baghlan | Khwaja Hijran (Jilga Nahrin) | Khwajeh Jeyran | {A83B170A-8003-40C9-B3D7-47180663635E} | c0a8-0057-12c3b7e0f83-43ab03f7-18199- | MF-NE-733 | HT - HALO TRUST | H/2459 | 44300 | 69.2211 | 36.0338 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {A83B170A-8003-40C9-B3D7-47180663635E} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2008-10-31 | No | Open
North East | Baghlan | Khwaja Hijran (Jilga Nahrin) | Khwajeh Jeyran | {A83B170A-8003-40C9-B3D7-47180663635E} | c0a8-0057-12c3b7f8818-4feea63d-191ac- | MF-NE-734 | HT - HALO TRUST | H/2460 | 46200 | 69.2264 | 36.0561 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {A83B170A-8003-40C9-B3D7-47180663635E} |  | Low | Agriculture Blocked | Moderate | 22 | CHA | 5 |  |  | 2008-10-31 | No | Open
North East | Baghlan | Khwaja Hijran (Jilga Nahrin) | Khwajeh Jeyran | {A83B170A-8003-40C9-B3D7-47180663635E} | c0a8-0057-12c3b993760-60c0fb37-2aa2f- | MF-NE-776 | HT - HALO TRUST | H/5212 | 2910 | 69.206 | 36.0773 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {A83B170A-8003-40C9-B3D7-47180663635E} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2008-10-08 | No | Open
North East | Baghlan | Khwaja Hijran (Jilga Nahrin) | Zardaspan | {7232FF33-1321-4959-8174-AE273DCCBB68} | c0a8-0057-12c3b93dc1f-6049c50-271be-f | MF-NE-806 | HT - HALO TRUST | H/5223 | 9000 | 69.2645 | 35.8888 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {7232FF33-1321-4959-8174-AE273DCCBB68} |  | High with Victim | High with Victims | Moderate | 14 | CHA | 1 |  |  | 2008-11-08 | No | Open
North East | Baghlan | Khwaja Hijran (Jilga Nahrin) | Zardaspan | {7232FF33-1321-4959-8174-AE273DCCBB68} | c0a8-0057-12c3ba20587-583dd842-302d9- | MF-NE-764 | HT - HALO TRUST | H/5224 | 38700 | 69.2723 | 35.8689 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {7232FF33-1321-4959-8174-AE273DCCBB68} |  | High with Victim | High with Victims | Moderate | 89 | CHA | 1 |  |  | 2008-11-09 | No | Open
North East | Baghlan | Nahrin | Abqol | {95121FB8-D91D-4A32-9E82-344B536BD0EF} | c0a8-0057-12c3b7d9314-b83bfa62-17c07- | MF-NE-772 | HT - HALO TRUST | H/2462 | 38700 | 69.0002 | 35.8849 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {95121FB8-D91D-4A32-9E82-344B536BD0EF} |  | Low | Agriculture Blocked | Moderate | 14 | CHA | 4 |  |  | 2008-11-22 | No | Open
North East | Baghlan | Nahrin | Arakash | {254E82A5-D639-4BBB-A912-F96DB6AB660E} | c0a8-0057-12c3b885741-854a1b22-1f560- | MF-NE-800 | HT - HALO TRUST | H/3040 | 22660 | 69.0208 | 36.0622 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {254E82A5-D639-4BBB-A912-F96DB6AB660E} |  | Medium | Agriculture Blocked | Moderate | 63 | CHA | 4 |  |  | 2008-11-02 | No | Open
North East | Baghlan | Nahrin | Baragi | {17647785-6B68-4EAB-98F8-197F1B56EE10} | c0a8-0057-12c3b93b668-8ea22ce1-2701b- | MF-NE-799 | HT - HALO TRUST | H/5228 | 50500 | 68.8847 | 35.9999 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {17647785-6B68-4EAB-98F8-197F1B56EE10} |  | Low | Agriculture Blocked | Moderate | 128 | CHA | 5 |  |  | 2008-11-20 | No | Open
North East | Baghlan | Nahrin | Baragi | {17647785-6B68-4EAB-98F8-197F1B56EE10} | c0a8-0057-12c3b93b82d-c4a7cdb3-27031- | MF-NE-797 | HT - HALO TRUST | H/2447 | 31900 | 68.8856 | 36.0017 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {17647785-6B68-4EAB-98F8-197F1B56EE10} |  | Low | Agriculture Blocked | Moderate | 71 | CHA | 5 |  |  | 2008-11-19 | No | Open
North East | Baghlan | Nahrin | Baragi | {17647785-6B68-4EAB-98F8-197F1B56EE10} | c0a8-0057-12c3b93ba10-9afcc81d-27045- | MF-NE-798 | HT - HALO TRUST | H/5229 | 31500 | 68.8848 | 35.9999 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {17647785-6B68-4EAB-98F8-197F1B56EE10} |  | Low | Agriculture Blocked | Moderate | 62 | CHA | 5 |  |  | 2008-11-21 | No | Open
North East | Baghlan | Nahrin | Chenarak | {2E0C0AE8-9F12-46D8-BFEF-4F48AF39B955} | c0a8-0057-12c3b9025c0-82f76aea-24b70- | MF-NE-741 | HT - HALO TRUST | H/2449 | 24730 | 69.1874 | 36.048 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {2E0C0AE8-9F12-46D8-BFEF-4F48AF39B955} |  | Low | Agriculture Blocked | Moderate | 3 | CHA | 5 |  |  | 2008-10-31 | No | Open
North East | Baghlan | Nahrin | Chenarak | {2E0C0AE8-9F12-46D8-BFEF-4F48AF39B955} | c0a8-0057-12c3bb4bc09-ba37ac98-3b561- | MF-NE-742 | HT - HALO TRUST | H/5214 | 15190 | 69.1712 | 36.0455 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {2E0C0AE8-9F12-46D8-BFEF-4F48AF39B955} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-10-11 | No | Open
North East | Baghlan | Nahrin | Doabi | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} | c0a8-0009-1467f7a7ce8-2a54f0c-221c-54 | Hz-ID-18821 | HT - HALO TRUST | H/8927 | 70390 | 69.132 | 35.9848 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} |  | High with Victim | High with Victims | Moderate | 5 | CHA | 1 |  |  | 2014-05-20 16:30 | No | Open
North East | Baghlan | Nahrin | Doabi | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} | c0a8-0009-1470f13ae11-545f5d74-1778-5 | Hz-ID-18833 | HT - HALO TRUST | H/8926 | 78000 | 69.1291 | 35.9856 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} |  | High with Victim | High with Victims | Moderate | 0 | CHA | 1 |  |  | 2014-05-16 16:30 | No | Open
North East | Baghlan | Nahrin | Doabi | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} | c0a8-0057-12c3b8756b8-d7d4f63c-1ea1e- | MF-HQ-14146 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1309/13477/MF0016 | 50000 | 69.1242 | 36.0085 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} |  | High with Victim | High with Victims | Moderate | 174 | SHA | 2 |  |  | 2010-02-01 | No | Open
North East | Baghlan | Nahrin | Doabi | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} | c0a8-0057-12c3b9fe2e1-42a66cfa-2edb1- | MF-NE-795 | HT - HALO TRUST | H/5220 | 48600 | 69.1439 | 36.0329 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} |  | High with Victim | High with Victims | Moderate | 10 | CHA | 2 |  |  | 2008-11-05 | No | Open
North East | Baghlan | Nahrin | Doabi | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} | c0a8-0057-12c3b9fe496-511a5dcb-2edc5- | MF-NE-792 | HT - HALO TRUST | H/5221 | 60800 | 69.1439 | 36.0329 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} |  | High with Victim | High with Victims | Moderate | 7 | CHA | 2 |  |  | 2008-11-06 | No | Open
North East | Baghlan | Nahrin | Doabi | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} | c0a8-0057-12c3b9fe64a-77f75518-2edd8- | MF-NE-788 | HT - HALO TRUST | H/5222 | 71000 | 69.1439 | 36.0329 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} |  | High with Victim | High with Victims | Moderate | 7 | CHA | 2 |  |  | 2008-11-06 | No | Open
North East | Baghlan | Nahrin | Doabi | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} | c0a8-0057-12c3b9fe82e-72925f62-2edeb- | MF-HQ-11652 | HT - HALO TRUST | H/2465 | 35000 | 69.1445 | 36.0311 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {43C0577E-88EE-4A2E-A0E2-7EE87FB6FDC6} |  | High with Victim | High with Victims | Moderate | 7 | CHA | 2 |  |  | 2008-11-04 | No | Open
North East | Baghlan | Nahrin | Gawi | {C8F6E7CD-E89B-4BA7-B9D9-0FA076A38E8D} | c0a8-0057-12c3b9d6551-4a7f71c4-2d513- | MF-NE-787 | HT - HALO TRUST | H/2456 | 42500 | 69.0915 | 35.8764 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {C8F6E7CD-E89B-4BA7-B9D9-0FA076A38E8D} |  | Low | Agriculture Blocked | Moderate | 15 | CHA | 5 |  |  | 2008-11-12 | No | Open
North East | Baghlan | Nahrin | Hafezbacha | {27761604-C806-49DA-8119-3CA5D90D12D2} | c0a8-0057-12c3b8e9911-27af8194-23ae8- | MF-NE-808 | HT - HALO TRUST | H/2457 | 30770 | 69.0544 | 36.0627 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {27761604-C806-49DA-8119-3CA5D90D12D2} |  | Low | Agriculture Blocked | Moderate | 21 | CHA | 5 |  |  | 2008-10-18 | No | Open
North East | Baghlan | Nahrin | Joye Kalan | {AD796659-B0EE-456C-B26C-6C6F03C53547} | c0a8-0057-12c3b9f0754-a77f73c4-2e544- | MF-NE-803 | HT - HALO TRUST | H/5231 | 990 | 69.1053 | 36.0397 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {AD796659-B0EE-456C-B26C-6C6F03C53547} |  | High | Critical Infrastracture | Moderate | 489 | CHA | 3 |  |  | 2008-11-23 | No | Open
North East | Baghlan | Nahrin | Kaafer Qala | {47BFB4A8-E187-498D-B7E0-FCCDDAC6DF89} | c0a8-0057-12c3b727ffe-46d41323-fa5c-4 | MF-HQ-9981 | HT - HALO TRUST | H/6033 | 9100 | 68.8829 | 35.8552 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {47BFB4A8-E187-498D-B7E0-FCCDDAC6DF89} |  | Low | Agriculture Blocked | Moderate | 106 | CHA | 5 |  |  | 2009-03-30 | No | Open
North East | Baghlan | Nahrin | Kaafer Qala | {47BFB4A8-E187-498D-B7E0-FCCDDAC6DF89} | c0a8-0057-12c3b861c3b-f44f3cd6-1dc86- | MF-NE-570 | HT - HALO TRUST | H/4736 | 120000 | 68.8859 | 35.8877 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {47BFB4A8-E187-498D-B7E0-FCCDDAC6DF89} |  | Low | Agriculture Blocked | Moderate | 16 | CHA | 5 |  |  | 2008-06-06 | No | Open
North East | Baghlan | Nahrin | Khwaja Khedzr | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} | c0a8-0057-12c3b950a05-d5f9881c-27e55- | MF-NE-781 | HT - HALO TRUST | H/5217 | 49411 | 69.1339 | 35.9685 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-10-20 | No | Open
North East | Baghlan | Nahrin | Khwaja Khedzr | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} | c0a8-0057-12c3b950bd9-ef42ffb8-27e6b- | MF-NE-783 | HT - HALO TRUST | H/5216 | 110791 | 69.1209 | 35.96 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2008-10-19 | No | Open
North East | Baghlan | Nahrin | Khwaja Khedzr | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} | c0a8-0057-12c3b950dac-ec07bcc3-27e82- | MF-NE-785 | HT - HALO TRUST | H/2458 | 61706 | 69.1201 | 35.9617 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2008-10-19 | No | Open
North East | Baghlan | Nahrin | Khwaja Khedzr | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} | c0a8-0057-12c3b950f71-4889a215-27e97- | MF-NE-778 | HT - HALO TRUST | H/5219 | 64710 | 69.133 | 35.9505 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-10-22 | No | Open
North East | Baghlan | Nahrin | Khwaja Khedzr | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} | c0a8-0057-12c3b951135-13313e70-27eae- | MF-NE-780 | HT - HALO TRUST | H/5218 | 38900 | 69.1313 | 35.9534 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-10-21 | No | Open
North East | Baghlan | Nahrin | Khwaja Khedzr | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} | c0a8-0057-12c3b98b430-e4b9d49c-2a4b9- | MF-NE-766 | HT - HALO TRUST | H/2454 | 78060 | 69.1275 | 35.9843 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {A15D5FB1-C82E-4007-BFC2-9B47442AC76F} |  | Low | Critical Infrastracture | Moderate | 8 | CHA | 5 |  |  | 2008-10-26 | No | Open
North East | Baghlan | Nahrin | Madrasa | {7DC9E666-388B-487B-85BC-BDB0811DC059} | c0a8-0009-1440565f515-ce43a0aa-15de-9 | Hz-ID-18475 | HT - HALO TRUST | H/8857 | 370 | 68.9873 | 36.0372 | Open | AP Only | AP Only | MineField |  | MBT Project-118 | Baghlan Demining Project-04 |  |  |  |  | 1396 |  | {7DC9E666-388B-487B-85BC-BDB0811DC059} |  | Medium | Agriculture Blocked | Moderate | 0 | CHA | 3 |  |  | 2014-01-17 16:30 | No | Open
North East | Baghlan | Nahrin | Pase Mazar | {0F73DE5A-4F7F-435D-AD00-51765AF8CCE1} | c0a8-0057-12c3b97b36c-54b01fa8-29a07- | MF-HT-384 | HT - HALO TRUST | H/2304 | 55700 | 68.8915 | 35.8239 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {0F73DE5A-4F7F-435D-AD00-51765AF8CCE1} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2007-12-13 09:50 | No | Open
North East | Baghlan | Nahrin | Pase Mazar | {0F73DE5A-4F7F-435D-AD00-51765AF8CCE1} | c0a8-0057-12c3ba9b40a-a44a1d7f-34ca1- | MF-NE-556 | HT - HALO TRUST | H/1164 | 70000 | 68.9182 | 35.8653 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {0F73DE5A-4F7F-435D-AD00-51765AF8CCE1} |  | High Requested | Resettlment/Local Request | Moderate | 25 | CHA | 1 | Yes | Priority of the task is high but Insecure | 2008-06-06 | No | Open
North East | Baghlan | Nahrin | Qoybaghar | {5CEBCC4F-7311-4E33-889D-5F2AFA5B00DE} | c0a8-0009-1467f7aaadb-b6abbeb4-2248-3 | Hz-ID-18822 | HT - HALO TRUST | H/8928 | 83100 | 69.1315 | 35.9533 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {5CEBCC4F-7311-4E33-889D-5F2AFA5B00DE} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2014-05-10 16:30 | No | Open
North East | Baghlan | Nahrin | Senjetak | {5DD09D15-5803-4B2B-9AF3-B38E97A18250} | c0a8-0057-12c3b92a1cf-d93388cc-264c1- | MF-NE-773 | HT - HALO TRUST | H/5232 | 38700 | 68.9317 | 35.8782 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {5DD09D15-5803-4B2B-9AF3-B38E97A18250} |  | Low | Agriculture Blocked | Moderate | 204 | CHA | 5 |  |  | 2008-11-18 | No | Open
North East | Baghlan | Nahrin | Sheen Dara | {D67586C7-DB7A-4DC9-8D0E-6F563D512246} | c0a8-0057-12c3b821fdd-b14968b5-1af11- | MF-NE-736 | HT - HALO TRUST | H/2466 | 1800 | 69.1583 | 36.0075 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {D67586C7-DB7A-4DC9-8D0E-6F563D512246} |  | Low | Agriculture Blocked | Moderate | 3 | CHA | 5 |  |  | 2008-10-16 | No | Open
North East | Baghlan | Nahrin | Tangi Nahrin/ Alachlog | {4463B4B8-E039-47C0-9E12-8613EEB410F5} | c0a8-0057-12c3b9554f7-1133cea8-2810f- | MF-NE-756 | HT - HALO TRUST | H/2446 | 8000 | 69.1789 | 36.0642 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-121/E | Baghlan Demining Project-15/E | B-AAR | Yes | 2014-06-02 | 2014-06-22 | 1393 | HT | {4463B4B8-E039-47C0-9E12-8613EEB410F5} |  |  |  | Moderate | 4 | CHA | 5 |  |  | 2008-10-09 | No | Planned
North East | Baghlan | Nahrin | Tangi Nahrin/ Alachlog | {4463B4B8-E039-47C0-9E12-8613EEB410F5} | c0a8-0057-12c3ba0c051-58c4fc7c-2f67c- | MF-NE-751 | HT - HALO TRUST | H/5211 | 70500 | 69.1911 | 36.0809 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {4463B4B8-E039-47C0-9E12-8613EEB410F5} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-10-07 | No | Open
North East | Baghlan | Nahrin | Tangi Nahrin/ Alachlog | {4463B4B8-E039-47C0-9E12-8613EEB410F5} | c0a8-0057-12c3ba0c235-1380113-2f694-3 | MF-NE-749 | HT - HALO TRUST | H/2468 | 62000 | 69.1946 | 36.0802 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {4463B4B8-E039-47C0-9E12-8613EEB410F5} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-10-06 | No | Open
North East | Baghlan | Nahrin | Tangi Nahrin/ Alachlog | {4463B4B8-E039-47C0-9E12-8613EEB410F5} | c0a8-0057-12c3ba0c418-4ec95006-2f6a6- | MF-NE-750 | HT - HALO TRUST | H/5210 | 80000 | 69.1912 | 36.0774 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {4463B4B8-E039-47C0-9E12-8613EEB410F5} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2008-10-06 | No | Open
North East | Baghlan | Nahrin | Tangi Nahrin/ Alachlog | {4463B4B8-E039-47C0-9E12-8613EEB410F5} | c0a8-00c9-12fddbd2f5d-15911d33-b2a-c1 | MF-NE-754 | HT - HALO TRUST | H/5213 | 7200 | 69.1775 | 36.0748 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {4463B4B8-E039-47C0-9E12-8613EEB410F5} |  | Low | Agriculture Blocked | Moderate | 24 | CHA | 5 |  |  | 2008-10-09 | No | Open
North East | Baghlan | Nahrin | Tarnab | {2824F2F7-0252-4A8E-9BF2-DF263707A1AA} | c0a8-0057-12c3ba38d87-c40971bb-3116c- | MF-NE-739 | HT - HALO TRUST | H/2467 | 22500 | 68.9739 | 35.8839 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {2824F2F7-0252-4A8E-9BF2-DF263707A1AA} |  | Low | Agriculture Blocked | Moderate | 4 | CHA | 5 |  |  | 2008-11-03 | No | Open
North East | Baghlan | Nahrin | Tarnab | {2824F2F7-0252-4A8E-9BF2-DF263707A1AA} | c0a8-0057-12c3baac5c3-9f88eef9-3563e- | MF-NE-738 | HT - HALO TRUST | H/2469 | 36000 | 68.9696 | 35.8699 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {2824F2F7-0252-4A8E-9BF2-DF263707A1AA} |  | Low | Agriculture Blocked | Moderate | 4 | CHA | 5 |  |  | 2008-11-12 | No | Open
North East | Baghlan | Nahrin | Watarchi | {32DEB999-9D9D-4EBE-9D4E-190247B0977D} | c0a8-0009-1468015bd59-87b2dd29-2631-b | Hz-ID-18824 | HT - HALO TRUST | H/8935 | 1100 | 68.9396 | 35.9064 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {32DEB999-9D9D-4EBE-9D4E-190247B0977D} |  | Low | Agriculture Blocked | Moderate | 1 | CHA | 5 |  |  | 2014-05-22 16:30 | No | Open
North East | Baghlan | Nahrin | Watarchi | {32DEB999-9D9D-4EBE-9D4E-190247B0977D} | c0a8-0009-1468017aaf1-dc11016f-2658-a | Hz-ID-18823 | HT - HALO TRUST | H/8933 | 1400 | 68.9377 | 35.9041 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {32DEB999-9D9D-4EBE-9D4E-190247B0977D} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2014-05-21 16:30 | No | Open
North East | Baghlan | Nahrin | Watarchi | {32DEB999-9D9D-4EBE-9D4E-190247B0977D} | c0a8-0057-12c3b86474f-c85acfe-1de48-e | MF-NE-727 | HT - HALO TRUST | H/2473 | 66930 | 68.9438 | 35.9076 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {32DEB999-9D9D-4EBE-9D4E-190247B0977D} |  | Low | Agriculture Blocked | Moderate | 2 | CHA | 5 |  |  | 2008-11-30 | No | Open
North East | Baghlan | Nahrin | Watarchi | {32DEB999-9D9D-4EBE-9D4E-190247B0977D} | c0a8-0057-12c3b9e2d4e-38afdf3f-2dd16- | MF-NE-728 | HT - HALO TRUST | H/2472 | 48200 | 68.9592 | 35.9202 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {32DEB999-9D9D-4EBE-9D4E-190247B0977D} |  | Low | Agriculture Blocked | Moderate | 161 | CHA | 5 |  |  | 2008-11-30 | No | Open
North East | Baghlan | Nahrin | Watarchi | {32DEB999-9D9D-4EBE-9D4E-190247B0977D} | c0a8-0057-12c3bb88d81-2588f2ed-3d797- | MF-NE-729 | HT - HALO TRUST | H/5230 | 36000 | 68.9339 | 35.9172 | Open | AP Only | AP Only | MineField |  | MBT Project-243 | Baghlan Demining Project-06 |  |  |  |  | 1397 |  | {32DEB999-9D9D-4EBE-9D4E-190247B0977D} |  | Low | Agriculture Blocked | Moderate | 11 | CHA | 5 |  |  | 2008-11-30 | No | Open
North East | Baghlan | Puli Hisar | Dahane Arbeshan | {AD1AEA94-FBDB-4699-A9C7-4E757A8A0CEF} | c0a8-0057-12c3b7151ff-8774996d-ec17-f | MF-HQ-11320 | MCPA - Mine Clearance Planning Agency | AF/1307/13627/MF2232 | 36366 | 69.373 | 35.6264 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AD1AEA94-FBDB-4699-A9C7-4E757A8A0CEF} |  | Low | Agriculture Blocked | Low | 8 | CHA | 5 |  |  | 2009-05-02 | No | Open
North East | Baghlan | Puli Hisar | Dahane Arbeshan | {AD1AEA94-FBDB-4699-A9C7-4E757A8A0CEF} | c0a8-0057-12c3baa1912-3871f5b8-35075- | MF-HQ-11305 | MCPA - Mine Clearance Planning Agency | AF/1307/13627/MF2234 | 42600 | 69.3772 | 35.6256 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AD1AEA94-FBDB-4699-A9C7-4E757A8A0CEF} |  | Low | Agriculture Blocked | Low | 7 | CHA | 5 |  |  | 2009-05-02 | No | Open
North East | Baghlan | Puli Hisar | Dahane Arbeshan | {AD1AEA94-FBDB-4699-A9C7-4E757A8A0CEF} | c0a8-0057-12c3baf9dec-4087a2a7-3848b- | MF-HQ-11314 | MCPA - Mine Clearance Planning Agency | AF/1307/13627/MF2235 | 59000 | 69.3815 | 35.6242 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AD1AEA94-FBDB-4699-A9C7-4E757A8A0CEF} |  | Low | Agriculture Blocked | Low | 7 | CHA | 5 |  |  | 2009-05-02 | No | Open
North East | Baghlan | Puli Hisar | Dahane Baghdara | {286C3735-32B6-484C-A48F-D6018E48CC8C} | c0a8-0057-12c3b80ad31-986a9bbb-19eb3- | MF-HQ-12200 | MCPA - Mine Clearance Planning Agency | AF/1307/13615/MF2207 | 60000 | 69.4579 | 35.6106 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {286C3735-32B6-484C-A48F-D6018E48CC8C} |  | Medium | Critical Infrastracture | Low | 306 | CHA | 3 |  |  | 2002-08-20 | No | Open
North East | Baghlan | Puli Hisar | Dahane Baghdara | {286C3735-32B6-484C-A48F-D6018E48CC8C} | c0a8-0057-12c3b923251-a7351031-2605d- | MF-HQ-12192 | MCPA - Mine Clearance Planning Agency | AF/1307/13615/MF2208 | 2942 | 69.4386 | 35.6046 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {286C3735-32B6-484C-A48F-D6018E48CC8C} |  | Medium | Agriculture Blocked | Low | 16 | CHA | 3 |  |  | 2002-08-18 16:30 | No | Open
North East | Baghlan | Puli Hisar | Dashtak | {8D3306F3-35EA-4846-A544-6CDC191E687C} | c0a8-0057-12c3bb3669d-c8de158c-3a8ba- | MF-HQ-12175 | MCPA - Mine Clearance Planning Agency | AF/1307/13599/MF2231 | 19715 | 69.3815 | 35.6615 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {8D3306F3-35EA-4846-A544-6CDC191E687C} |  | Low | Agriculture Blocked | Low | 26 | CHA | 5 |  |  | 2004-10-23 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-008e-1328fad07f6-55bba459-21ff-b | MF-15474 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF7594 | 33650 | 69.7871 | 35.6638 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Medium | Critical Infrastracture | Low | 27 | CHA | 5 |  |  | 2010-11-09 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-008e-1328fad5a78-590a1091-221c-7 | MF-15473 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF7593 | 33620 | 69.7871 | 35.6632 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Critical Infrastracture | Low | 83 | CHA | 5 |  |  | 2010-11-08 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-008e-132908bd77a-a91b68af-cd-ea8 | MF-16161 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8024 | 70450 | 69.7824 | 35.6638 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | Removed from HALO Trust plan based on e-mail received on 16th August 2012 | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-06-17 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-008e-132b4bbe130-8811d932-be5-31 | MF-16255 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF7597 | 87900 | 69.7871 | 35.6632 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Medium | Critical Infrastracture | Low | 56 | CHA | 5 |  |  | 2010-11-11 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-008e-132c94dfdfd-e69a4981-2f66-6 | MF-15475 | MCPA - Mine Clearance Planning Agency | AF/1317/13679/MF7595 | 19120 | 69.7871 | 35.6632 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Medium | Critical Infrastracture | Low | 65 | CHA | 5 |  |  | 2010-11-10 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-008e-132c958309a-1774cba5-30dd-f | MF-15523 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF7590 | 58500 | 69.7871 | 35.6632 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | Removed from HALO Trust plan based on e-mail received on 16th August 2012 | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-11-06 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1349cd82538-c1f819d0-5-8d7a | MF-16484 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8192 | 51000 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2011-10-04 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1349cdefde8-92e0c56b-19-578 | MF-16483 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8191 | 51000 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2011-10-03 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1349ce15970-bd28a97c-2d-338 | MF-16482 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8190 | 47600 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2011-10-02 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1349ce5327c-a7307926-43-86a | MF-16481 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8189 | 57100 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 34 | CHA | 5 |  |  | 2011-10-01 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134a70a9492-a36f94c4-82-866 | MF-16512 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8302 | 48100 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-14 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134a7330015-c5f2f694-d0-23d | MF-16511 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8301 | 91800 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2011-10-13 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134a7612e5b-d9a26f30-2be-13 | MF-16505 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8200 | 52920 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2011-10-12 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134a824fd74-9fa48682-4e7-b4 | MF-16489 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8196 | 58900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-08 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134a84bdcb8-320af096-ce4-65 | MF-16488 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8195 | 45000 | 69.7395 | 35.6647 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-07 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134a84e065f-b4a8f54c-d10-25 | MF-16486 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8194 | 52500 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2011-10-06 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134a84fa90e-575f8fe2-d24-e6 | MF-16485 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8193 | 63600 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2011-10-05 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134a85a5ec1-e9b340de-d82-5c | MF-16490 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8303 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-05 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134a86679e2-4ac300ce-dd6-47 | MF-16493 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8305 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-07 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134a86a5636-d8dcf788-e3f-f6 | MF-16494 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8306 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-08 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134ac06773e-4932cd87-e94-30 | MF-16496 | HT - HALO TRUST | H/8307 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-09 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134c0ca280c-25a883c-ef7-a6b | MF-15524 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF7591 | 66840 | 69.7871 | 35.6632 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | Removed from HALO Trust plan based on e-mail received on 16th August 2012 | Low | Agriculture Blocked | Low | 25 | CHA | 5 |  |  | 2010-11-07 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134c63d10aa-4ed01545-27b9-3 | MF-16504 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8314 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-21 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134c63e238a-769fbd18-27ce-f | MF-16503 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8313 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-20 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134c63eb1b2-cf756946-27e3-7 | MF-16501 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8312 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-17 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134c63f1044-4051f513-27f8-5 | MF-16500 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8311 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-15 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134c641f549-db1e04b1-2844-f | MF-16499 | HT - HALO TRUST | H/8310 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-13 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134c64ab547-936e702-2877-1f | MF-16498 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8309 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-11 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134c64b4e0a-5384ef36-288d-9 | MF-16497 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8308 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-10 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-134c65ebf66-bb4a86fb-2978-3 | MF-16492 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8304 | 39900 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-06 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1350deacc8c-d912fd-91e-23a7 | MF-16423 | HT - HALO TRUST | H/7596 | 68800 | 69.7871 | 35.6632 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Medium | Critical Infrastracture | Low | 56 | CHA | 5 |  |  | 2011-10-18 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-13518719721-9cb7ea03-3d2-5b | MF-16537 | MCPA - Mine Clearance Planning Agency | AF/1317/13679/MF8104 | 37599 | 69.767 | 35.6668 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 87 | CHA | 5 |  |  | 2011-07-14 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-135194f5961-eb60abd7-876-63 | MF-16533 | MCPA - Mine Clearance Planning Agency | AF/1317/13679/MF8105 | 30470 | 69.767 | 35.6668 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 62 | CHA | 5 |  |  | 2011-07-16 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-13528633734-a840b855-580-f9 | MF-16547 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8103 | 42510 | 69.7739 | 35.6647 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 25 | CHA | 5 |  |  | 2011-07-12 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-13533b6e1fa-b1fdc530-283-ee | MF-16502 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8199 | 48110 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2011-10-11 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-13533c0de06-5a387464-2f7-bb | MF-16495 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8198 | 50933 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-10 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-13533c2a62b-c5f7985a-30b-2f | MF-16491 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8197 | 52020 | 69.7861 | 35.6712 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-09 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1353860869d-fb467eb2-2f8-cc | MF-16613 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8099 | 56000 | 69.7791 | 35.6644 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-08-07 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1353c914960-992c4b4c-145f-c | MF-16630 | MCPA - Mine Clearance Planning Agency | AF/1317/13679/MF8138 | 37000 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 25 | CHA | 5 |  |  | 2011-09-08 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1353c916e49-4bd2e1b0-1474-4 | MF-16631 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8134 | 37500 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Medium | Critical Infrastracture | Low | 62 | CHA | 5 |  |  | 2011-09-04 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1353d5eb919-a1aeaf99-1722-b | MF-16506 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8316 | 2888862 | 69.7871 | 35.6634 | Open | AP Only | AP Only | MineField |  | MBT Project-132 | Baghlan Demining Project-022 |  |  |  |  | 1400 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2011-10-17 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1353d7bf192-2e20852c-1812-7 | MF-16566 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8033 | 47100 | 69.7788 | 35.6647 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | Based on HALO Trust confirmation, the hazard is removed from their plan | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2011-07-04 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1353d812c7d-af77c521-1832-4 | MF-16629 | MCPA - Mine Clearance Planning Agency | AF/1317/13679/MF8168 | 108750 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 87 | CHA | 5 |  |  | 2011-09-11 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1353d83ba71-aa55f739-1848-c | MF-16507 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8317 | 989250 | 69.7871 | 35.6634 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 3 | CHA | 5 |  |  | 2011-10-18 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1353df5fdc0-12802ea3-1aed-8 | MF-16608 | MCPA - Mine Clearance Planning Agency | AF/1317/13679/MF8135 | 37500 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 62 | CHA | 5 |  |  | 2011-09-05 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-1353df711d8-bd9b1250-1b06-1 | MF-16605 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8137 | 46000 | 69.7859 | 35.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 87 | CHA | 5 |  |  | 2011-09-07 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-13551e3276b-d7cd014a-336-f3 | MF-16510 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8320 | 3480000 | 69.7871 | 35.6634 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Medium | Critical Infrastracture | Low | 245 | CHA | 5 |  |  | 2011-10-01 16:30 | No | Open
North East | Baghlan | Puli Hisar | Farashkushta | {AA3EDC7E-2893-41D4-881B-1454D4D65098} | c0a8-00f6-135520c3f67-87594a2b-145-3f | MF-16509 | MCPA - Mine Clearance Planning Agency | AF/1307/13679/MF8319 | 2975700 | 69.7871 | 35.6634 | Open | AP Only | AP Only | MineField |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {AA3EDC7E-2893-41D4-881B-1454D4D65098} |  | Low | Agriculture Blocked | Low | 163 | CHA | 5 |  |  | 2011-10-15 16:30 | No | Open
North East | Baghlan | Puli Hisar | Khetyan | {E4DDC82E-1A63-4FF1-A563-7C00754FF04A} | c0a8-0009-14240e5b672-e5cca05f-3293-3 | Hz-ID-18221 | MCPA - Mine Clearance Planning Agency | AF/1317/13611/MF0007 | 51945 | 69.3347 | 35.6546 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {E4DDC82E-1A63-4FF1-A563-7C00754FF04A} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2013-09-25 16:30 | No | Open
North East | Baghlan | Puli Hisar | Khetyan | {E4DDC82E-1A63-4FF1-A563-7C00754FF04A} | c0a8-0009-14240f418a8-80bf999a-3738-7 | Hz-ID-18220 | MCPA - Mine Clearance Planning Agency | AF/1317/13611/MF0003 | 1027 | 69.3469 | 35.6624 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {E4DDC82E-1A63-4FF1-A563-7C00754FF04A} |  | Medium | Agriculture Blocked | Low | 63 | CHA | 3 |  |  | 2013-09-24 16:30 | No | Open
North East | Baghlan | Puli Hisar | Murghabidahan | {F42F5E06-E18B-40AF-B53E-5FD558DDA70E} | c0a8-0057-12c3b9228ef-a2325838-25ff9- | MF-HQ-12344 | HT - HALO TRUST | H/2246 | 5000 | 69.3521 | 35.6755 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {F42F5E06-E18B-40AF-B53E-5FD558DDA70E} |  | Medium | Critical Infrastracture | Low | 916 | CHA | 3 |  |  | 2002-07-08 | No | Open
North East | Baghlan | Puli Hisar | Nawbahar | {F5186D25-B331-4CC6-B003-C480B55BE0B1} | c0a8-0057-12c3b82cba4-97a013cf-1b6ad- | MF-HQ-12204 | HT - HALO TRUST | H/2233 | 6000 | 69.4808 | 35.6755 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {F5186D25-B331-4CC6-B003-C480B55BE0B1} |  | High with Victim | High with Victims | Low | 1 | CHA | 1 |  |  | 2009-09-12 | No | Open
North East | Baghlan | Puli Hisar | Puli Hisar | {7DD47266-73B1-4025-8C57-2E615C556667} | c0a8-0009-14241485bd4-84e3b386-38ac-a | Hz-ID-18222 | MCPA - Mine Clearance Planning Agency | AF/1307/13629/MF0005 | 25947 | 69.465 | 35.6117 | Open | AP Only | AP Only | MineField |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {7DD47266-73B1-4025-8C57-2E615C556667} |  | Low | Agriculture Blocked | Low | 87 | CHA | 5 |  |  | 2013-09-26 16:30 | No | Open
North East | Baghlan | Puli Hisar | Qaza | {BCF3CF84-A141-4712-918A-2AC6C193A06A} | c0a8-0009-142f47ce3e2-6a6953b3-2-60ec | Hz-ID-18214 | MCPA - Mine Clearance Planning Agency | AF/1317/13669/SpotERW0001 | 100 | 69.54 | 35.6169 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {BCF3CF84-A141-4712-918A-2AC6C193A06A} |  | High | Critical Infrastracture | Low | 131 | CHA | 3 |  |  | 2013-10-02 16:30 | No | Open
North East | Baghlan | Puli Hisar | Qaza | {BCF3CF84-A141-4712-918A-2AC6C193A06A} | c0a8-0009-143757fbb32-3f42d9f5-24bf-a | Hz-ID-18349 | MCPA - Mine Clearance Planning Agency | AF/1317/13669/BF0006 | 100 | 69.54 | 35.6169 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-080 | Baghlan Demining Project-19 |  |  |  |  | 1397 |  | {BCF3CF84-A141-4712-918A-2AC6C193A06A} |  | High | Critical Infrastracture | Low | 131 | CHA | 3 |  |  | 2013-10-02 16:30 | No | Open
North East | Baghlan | Puli Hisar | Tele Doab | {3AC2A900-E81C-4570-A165-CC3229E5B11A} | c0a8-0057-12c3b8061d1-b2077f78-19b36- | MF-HQ-13961 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1317/13676/MF001 | 125000 | 69.712 | 35.6158 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-123 | Baghlan Demining Project-18 |  |  |  |  | 1399 |  | {3AC2A900-E81C-4570-A165-CC3229E5B11A} |  | Low | Critical Infrastracture | Low | 1 | SHA | 5 |  |  | 2009-12-21 | No | Open
North East | Baghlan | Puli Khumri | Bala Duri (1) | {309C9057-5FA3-4079-BF48-D027822D96E7} | c0a8-0009-14406be9185-4311056b-2ae4-c | Hz-ID-18490 | MCPA - Mine Clearance Planning Agency | AF/1302/13149/MF0015 | 16240 | 68.7252 | 36.0565 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {309C9057-5FA3-4079-BF48-D027822D96E7} |  | High with Victim | High with Victims | Substantial | 12 | CHA | 2 |  |  | 2014-01-15 16:30 | No | Open
North East | Baghlan | Puli Khumri | Bala Duri (1) | {309C9057-5FA3-4079-BF48-D027822D96E7} | c0a8-0009-144168e7e22-8640d8d0-5076-8 | Hz-ID-18492 | MCPA - Mine Clearance Planning Agency | AF/1302/13149/MF0017 | 2001 | 68.7252 | 36.0565 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {309C9057-5FA3-4079-BF48-D027822D96E7} |  | High with Victim | High with Victims | Substantial | 12 | CHA | 2 |  |  | 2014-01-22 16:30 | No | Open
North East | Baghlan | Puli Khumri | Chashma-i-Sher (2) | {6E18AB00-C1AC-422F-B8D9-B44F151C315A} | c0a8-00f6-1352e3c415e-cc6268bb-fa-1ed | MF-16571 | HT - HALO TRUST | H/8271 | 850 | 68.5622 | 36.0631 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes | 2013-04-01 | 2013-06-23 | 1392-1393 | HT | {6E18AB00-C1AC-422F-B8D9-B44F151C315A} |  |  |  | Substantial | 146 | CHA | 3 |  |  | 2011-12-13 16:30 | No | Planned
North East | Baghlan | Puli Khumri | Dasht-i-Khwaja Alwan | {81533B5D-D17C-49E3-B46E-961129F9CF6F} | c0a8-0057-12c3b6ab4c8-454a6a6f-9b9b-7 | MF-HT-1226 | HT - HALO TRUST | H/3139 | 6100 | 68.5276 | 36.0637 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes | 2013-04-01 | 2013-06-23 | 1392-1393 | HT | {81533B5D-D17C-49E3-B46E-961129F9CF6F} |  |  |  | Substantial | 13 | CHA | 2 |  |  | 2007-12-01 | No | Planned
North East | Baghlan | Puli Khumri | Gurgorak | {B2C48796-E1BF-41EB-934A-2D926F7A3C18} | c0a8-0057-12c3b79fd54-c905f9c6-152b8- | MF-HQ-9933 | HT - HALO TRUST | H/2479 | 104 | 68.5966 | 36.0727 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes | 2013-04-19 | 2013-04-21 | 1392-1393 | HT | {B2C48796-E1BF-41EB-934A-2D926F7A3C18} | Planned for EOD Teams |  |  | Substantial | 162 | CHA | 3 |  |  | 2009-03-30 | No | Planned
North East | Baghlan | Puli Khumri | Khojadelbar Baba | {5D860F9E-A17A-47BE-ABD2-15F9D38B2CDA} | c0a8-0009-14406d26f8c-52c6cff6-2e1b-4 | Hz-ID-18491 | MCPA - Mine Clearance Planning Agency | AF/1302/13100/MF0016 | 230 | 68.6131 | 35.954 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {5D860F9E-A17A-47BE-ABD2-15F9D38B2CDA} |  | High | Critical Infrastracture | Substantial | 792 | CHA | 3 |  |  | 2014-01-19 16:30 | No | Open
North East | Baghlan | Puli Khumri | Mulla Shahzada | {059E6027-E3E6-488D-B665-5B3E8199E1CB} | c0a8-0057-12c3b733872-371bac84-10318- | MF-HQ-9921 | HT - HALO TRUST | H/5851 | 620 | 68.5784 | 36.0064 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes | 2013-05-21 | 2013-05-21 | 1392-1393 | HT | {059E6027-E3E6-488D-B665-5B3E8199E1CB} | , |  |  | Substantial | 510 | CHA | 3 |  |  | 2009-03-30 | No | Planned
North East | Baghlan | Puli Khumri | Mulla Shahzada | {059E6027-E3E6-488D-B665-5B3E8199E1CB} | c0a8-0057-12c3b74cb98-2bad6c-115cc-7b | MF-HQ-9928 | HT - HALO TRUST | H/5241 | 1002 | 68.5789 | 36.0066 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes | 2010-07-07 | 2010-07-11 | 1393 | HT | {059E6027-E3E6-488D-B665-5B3E8199E1CB} | , | High | Water Blocked | Substantial | 510 | CHA | 3 |  |  | 2009-03-30 | No | Planned
North East | Baghlan | Puli Khumri | Puli Hashemkhan | {9C8AE3D4-39EA-4FA6-B6A8-046B74D5CFB8} | c0a8-0057-12c3b9cf8da-b74dfdbb-2d10a- | MF-HT-983 | MCPA - Mine Clearance Planning Agency | AF/1302/00475/MF2484 | 45000 | 68.6114 | 36.1108 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes | 2014-02-11 | 2014-04-23 | 1392-1393 | HT | {9C8AE3D4-39EA-4FA6-B6A8-046B74D5CFB8} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2006-07-01 | No | Planned
North East | Baghlan | Puli Khumri | Qara-i-Faqirbay | {4401ECCA-8892-4DA2-81FB-95BEEA3CC962} | c0a8-0009-14406b6a8b0-fda70837-2a91-e | Hz-ID-18489 | MCPA - Mine Clearance Planning Agency | AF/1302/01310/MF0014 | 2100 | 68.5964 | 35.9802 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {4401ECCA-8892-4DA2-81FB-95BEEA3CC962} |  | High | Critical Infrastracture | Substantial | 1171 | CHA | 3 |  |  | 2014-01-04 16:30 | No | Open
North East | Baghlan | Puli Khumri | Qosh Tapa-Farah | {1DA019E7-1DE8-4C0C-9CB8-E511D43ECF22} | c0a8-0009-145cfe67d7f-82f8473c-296e-c | Hz-ID-18675 | MCPA - Mine Clearance Planning Agency | AF/1302/13120/MF0018 | 3434 | 68.6879 | 35.9463 | Open | AP Only | AP Only | MineField |  | MBT Project-121 | Baghlan Demining Project-15 |  |  |  |  | 1394 |  | {1DA019E7-1DE8-4C0C-9CB8-E511D43ECF22} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2014-03-27 16:30 | No | Open
North East | Baghlan | Puli Khumri | Shamarq | {79AB732D-40E3-46D2-9843-C9A7DE92B875} | c0a8-0057-12c3b86c2c4-1c12ae2a-1e38e- | MF-HQ-13990 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/1302/13132/MF0007 | 87473 | 68.8484 | 35.9248 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-083 | Baghlan Demining Project-16 | VTF | Yes | 2013-07-21 | 2013-08-31 | 1392 | OMAR | {79AB732D-40E3-46D2-9843-C9A7DE92B875} |  |  |  | Substantial | 62 | CHA | 3 |  |  | 2009-12-21 16:30 | No | Complete
North East | Baghlan | Puli Khumri | Shamarq | {79AB732D-40E3-46D2-9843-C9A7DE92B875} | c0a8-0057-12c3b88508d-d06c27ff-1f51c- | MF-HQ-9932 | HT - HALO TRUST | H/6035 | 390000 | 68.8827 | 35.9575 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-083 | Baghlan Demining Project-16 | VTF | Yes |  |  | 1392 | OMAR | {79AB732D-40E3-46D2-9843-C9A7DE92B875} |  |  |  | Substantial | 654 | CHA | 2 |  |  | 2009-03-05 | No | Complete
North East | Baghlan | Puli Khumri | Shamarq | {79AB732D-40E3-46D2-9843-C9A7DE92B875} | c0a8-0057-12c3b8f7911-8156cf6a-24421- | MF-HQ-9951 | HT - HALO TRUST | H/5881 | 35000 | 68.8117 | 35.9635 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-083 | Baghlan Demining Project-16 | VTF | Yes | 2013-05-26 | 2013-06-20 | 1392 | OMAR | {79AB732D-40E3-46D2-9843-C9A7DE92B875} |  |  |  | Substantial | 4 | CHA | 2 |  |  | 2009-03-30 | No | Complete
North East | Baghlan | Puli Khumri | Shamarq | {79AB732D-40E3-46D2-9843-C9A7DE92B875} | c0a8-0057-12c3b8f7c1d-e93ed26e-24439- | MF-HQ-9949 | HT - HALO TRUST | H/5880 | 27720 | 68.8105 | 35.9651 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-083 | Baghlan Demining Project-16 | VTF | Yes | 2013-05-26 | 2013-06-30 | 1392 | OMAR | {79AB732D-40E3-46D2-9843-C9A7DE92B875} |  |  |  | Substantial | 4 | CHA | 2 |  |  | 2009-03-30 | No | Complete
North East | Baghlan | Puli Khumri | Shamarq | {79AB732D-40E3-46D2-9843-C9A7DE92B875} | c0a8-0057-12c3b8f7f48-37cf1853-2445a- | MF-HQ-9955 | HT - HALO TRUST | H/2493 | 22000 | 68.81 | 35.9685 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-083 | Baghlan Demining Project-16 | VTF | Yes | 2013-05-26 | 2013-06-30 | 1392 | OMAR | {79AB732D-40E3-46D2-9843-C9A7DE92B875} |  |  |  | Substantial | 5 | CHA | 2 |  |  | 2009-03-30 | No | Complete
North East | Baghlan | Puli Khumri | Shamarq | {79AB732D-40E3-46D2-9843-C9A7DE92B875} | c0a8-0057-12c3b949102-5d02b747-2792c- | MF-HQ-9923 | HT - HALO TRUST | H/5882 | 29480 | 68.8106 | 35.9726 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-083 | Baghlan Demining Project-16 | VTF | Yes | 2013-05-26 | 2013-06-30 | 1392 | OMAR | {79AB732D-40E3-46D2-9843-C9A7DE92B875} |  |  |  | Substantial | 2 | CHA | 2 |  |  | 2009-03-02 | No | Complete
North East | Baghlan | Puli Khumri | Shamarq | {79AB732D-40E3-46D2-9843-C9A7DE92B875} | c0a8-0057-12c3b9493df-864a2829-27951- | MF-HQ-9927 | HT - HALO TRUST | H/2494 | 17600 | 68.8097 | 35.9707 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-083 | Baghlan Demining Project-16 | VTF | Yes | 2013-06-29 | 2013-07-15 | 1392 | OMAR | {79AB732D-40E3-46D2-9843-C9A7DE92B875} |  |  |  | Substantial | 1 | CHA | 2 |  |  | 2009-03-02 | No | Complete
North East | Baghlan | Puli Khumri | Shamarq | {79AB732D-40E3-46D2-9843-C9A7DE92B875} | c0a8-0057-12c3b94964f-dbcc5800-27973- | MF-HQ-9925 | HT - HALO TRUST | H/5883 | 39000 | 68.8112 | 35.9754 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-083 | Baghlan Demining Project-16 | VTF | Yes | 2013-05-27 | 2013-08-05 | 1392 | OMAR | {79AB732D-40E3-46D2-9843-C9A7DE92B875} |  |  |  | Substantial | 1 | CHA | 2 |  |  | 2009-03-02 | No | Complete
North East | Baghlan | Puli Khumri | Shamarq | {79AB732D-40E3-46D2-9843-C9A7DE92B875} | c0a8-0057-12c3bb46c84-9a565e69-3b214- | MF-HQ-9929 | HT - HALO TRUST | H/2492 | 41000 | 68.8206 | 35.9592 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-083 | Baghlan Demining Project-16 | VTF | Yes | 2013-06-29 | 2013-07-25 | 1392 | OMAR | {79AB732D-40E3-46D2-9843-C9A7DE92B875} |  |  |  | Substantial | 18 | CHA | 2 |  |  | 2009-03-03 | No | Complete
North East | Baghlan | Puli Khumri | Shamarq | {79AB732D-40E3-46D2-9843-C9A7DE92B875} | c0a8-00f6-134eb4a3a65-5fe5fcd5-106e-8 | MF-HQ-9930 | HT - HALO TRUST | H/2495 | 14000 | 68.8263 | 35.9594 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-083 | Baghlan Demining Project-16 | VTF | Yes | 2013-06-29 | 2013-07-15 | 1392 | OMAR | {79AB732D-40E3-46D2-9843-C9A7DE92B875} |  |  |  | Substantial | 11 | CHA | 2 |  |  | 2009-03-03 | No | Complete
North East | Baghlan | Puli Khumri | Wazirabad | {B63D4ED6-DA9F-461B-90FF-930B7C938738} | c0a8-00f6-1357b8d6a02-f2d4719a-3c5b-8 | MF-16694 | MCPA - Mine Clearance Planning Agency | AF/1302/13125/MF8272 | 1840 | 68.6557 | 35.9886 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-043 | Baghlan Demining Project-1 (AT) | DOS | Yes |  |  | 1392-1393 | HT | {B63D4ED6-DA9F-461B-90FF-930B7C938738} |  |  |  | Substantial | 1635 | CHA | 3 |  |  | 2012-01-10 16:30 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3ba7f939-161bfac1-33ca0- | MF-HQ-12317 | HT - HALO TRUST | H/2511 | 60000 | 68.3106 | 35.3921 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  |  |  | Substantial | 43 | CHA | 3 |  |  | 2002-08-04 | Yes | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3ba7fb7a-62106cdc-33cb2- | MF-NE-470 | HT - HALO TRUST | H/4851 | 51250 | 68.3595 | 35.3906 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes | 2014-06-02 | 2014-07-13 | 1393 |  | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  |  |  | Substantial | 30 | CHA | 5 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-01-07 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3ba7fdab-a28380d7-33ccb- | MF-NE-469 | HT - HALO TRUST | H/4852 | 28372 | 68.3594 | 35.3902 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes | 2014-06-01 | 2014-07-23 | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  |  |  | Substantial | 12 | CHA | 1 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-01-07 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3ba7ffdd-7061a13d-33ce2- | MF-NE-474 | HT - HALO TRUST | H/4800 | 19749 | 68.3567 | 35.3877 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes | 2014-07-01 | 2014-07-23 | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  |  |  | Substantial | 30 | CHA | 1 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-01-07 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3ba801e0-c4ff0f7e-33cfa- | MF-NE-476 | HT - HALO TRUST | H/4798 | 55086 | 68.355 | 35.3894 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes | 2014-06-01 | 2014-07-23 | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  |  |  | Substantial | 18 | CHA | 1 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-01-07 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3ba80430-854ef773-33d10- | MF-NE-477 | HT - HALO TRUST | H/4797 | 64450 | 68.3536 | 35.3905 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes | 2014-06-10 | 2014-07-19 | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  |  |  | Substantial | 18 | CHA | 5 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-01-07 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3ba80652-c8b96486-33d27- | MF-NE-472 | HT - HALO TRUST | H/4799 | 54775 | 68.3564 | 35.3864 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes | 2014-06-02 | 2014-07-13 | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  |  |  | Substantial | 31 | CHA | 5 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-01-07 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3bac1833-b3eb5ab9-362a7- | MF-NE-530 | HT - HALO TRUST | H/4791 | 84250 | 68.3239 | 35.4255 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes |  |  | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  | High Requested | Resettlment/Local Request | Substantial | 0 | CHA | 1 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-06-01 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3bac1a16-b9f9faa9-362bd- | MF-NE-527 | HT - HALO TRUST | H/4788 | 110481 | 68.3351 | 35.4318 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes | 2014-08-01 | 2014-09-23 | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  | High Requested | Resettlment/Local Request | Substantial | 3 | CHA | 1 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-06-01 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3bac1bdb-956d0c1b-362d3- | MF-NE-526 | HT - HALO TRUST | H/2503 | 76905 | 68.3363 | 35.4268 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes | 2014-08-01 |  | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  | High Requested | Resettlment/Local Request | Substantial | 7 | CHA | 1 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-06-01 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3bac1dce-ee917e83-362e5- | MF-NE-528 | HT - HALO TRUST | H/4789 | 129160 | 68.3321 | 35.4285 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes | 2014-08-01 | 2014-09-23 | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  | High Requested | Resettlment/Local Request | Substantial | 3 | CHA | 1 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-06-01 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3bac200f-b08413f2-362fb- | MF-NE-529 | HT - HALO TRUST | H/4790 | 78383 | 68.3298 | 35.4297 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes |  |  | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  | High Requested | Resettlment/Local Request | Substantial | 0 | CHA | 1 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-06-01 | No | Planned
North East | Baghlan | Tala Wa Barfak | Angar | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} | c0a8-0057-12c3bb70e38-8531c80a-3ca1f- | MF-NE-554 | HT - HALO TRUST | H/4794 | 9100 | 68.3456 | 35.3933 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {C68B9AD7-62B3-45A9-B0F4-B8BC4B498691} |  | High Requested | Resettlment/Local Request | Substantial | 26 | CHA | 1 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-07-01 | No | Planned
North East | Baghlan | Tala Wa Barfak | Asheqan | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} | c0a8-0057-12c3b821208-87249893-1ae7e- | MF-NE-572 | HT - HALO TRUST | H/4781 | 131931 | 68.1735 | 35.4965 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Asheqan | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} | c0a8-0057-12c3b8303a4-c0d81901-1b915- | MF-NE-574 | HT - HALO TRUST | H/4780 | 251700 | 68.154 | 35.4875 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Asheqan | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} | c0a8-0057-12c3b8b1a79-3186814b-21401- | MF-NE-579 | HT - HALO TRUST | H/4778 | 251000 | 68.1546 | 35.4768 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Asheqan | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} | c0a8-0057-12c3b8ed630-508ff4ab-23d50- | MF-NE-581 | HT - HALO TRUST | H/4783 | 52500 | 68.2587 | 35.3769 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Asheqan | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} | c0a8-0057-12c3bacdf85-a844129b-36a72- | MF-NE-485 | HT - HALO TRUST | H/2505 | 203600 | 68.1769 | 35.4954 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-11-06 | No | Open
North East | Baghlan | Tala Wa Barfak | Asheqan | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} | c0a8-0057-12c3bb1a6ec-1b825aea-39802- | MF-NE-482 | HT - HALO TRUST | H/4777 | 116000 | 68.2269 | 35.4749 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-01-07 | No | Open
North East | Baghlan | Tala Wa Barfak | Asheqan | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} | c0a8-0057-12c3bb1a9d9-cb83e99c-3981a- | MF-NE-484 | HT - HALO TRUST | H/2504 | 177500 | 68.2132 | 35.4712 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {4DD8138A-641F-42B2-BEFD-8D18E994A7E6} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-01-06 | No | Open
North East | Baghlan | Tala Wa Barfak | Dahane Estama | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} | c0a8-0009-14549f7f03f-7b7b32c-7d4-f88 | Hz-ID-18618 | HT - HALO TRUST | H/8918 | 94136 | 68.2117 | 35.427 | Open | AP Only | AP Only | MineField |  | MBT Project-027 | Baghlan Demining Project-01 |  |  |  |  | 1394 |  | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} |  | High with Victim | High with Victims | Substantial | 5 | CHA | 2 |  |  | 2014-03-10 16:30 | No | Open
North East | Baghlan | Tala Wa Barfak | Dahane Estama | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} | c0a8-0009-1454a02dc1a-751c369a-8b5-29 | Hz-ID-18617 | HT - HALO TRUST | H/8917 | 85390 | 68.1978 | 35.4269 | Open | AP Only | AP Only | MineField |  | MBT Project-027 | Baghlan Demining Project-01 |  |  |  |  | 1394 |  | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} |  | High with Victim | High with Victims | Substantial | 5 | CHA | 2 |  |  | 2014-03-07 16:30 | No | Open
North East | Baghlan | Tala Wa Barfak | Dahane Estama | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} | c0a8-0057-12c3bb4c54c-a0138d48-3b5be- | MF-NE-576 | HT - HALO TRUST | H/4793 | 20400 | 68.1881 | 35.4414 | Open | AP Only | AP Only | MineField |  | MBT Project-027 | Baghlan Demining Project-01 |  |  |  |  | 1394 |  | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} |  | High with Victim | High with Victims | Substantial | 16 | CHA | 1 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Dahane Estama | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} | c0a8-0057-12c3bb4c7dc-d34bd097-3b5d2- | MF-NE-577 | HT - HALO TRUST | H/4792 | 91000 | 68.1977 | 35.4346 | Open | AP Only | AP Only | MineField |  | MBT Project-027 | Baghlan Demining Project-01 |  |  |  |  | 1394 |  | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} |  | High with Victim | High with Victims | Substantial | 21 | CHA | 1 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Dahane Estama | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} | c0a8-0057-12c3bb582a0-b26d88ba-3bc4a- | MF-NE-502 | HT - HALO TRUST | H/4787 | 44420 | 68.2366 | 35.4189 | Open | AP Only | AP Only | MineField |  | MBT Project-027 | Baghlan Demining Project-01 |  |  |  |  | 1394 |  | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} |  | High with Victim | High with Victims | Substantial | 61 | CHA | 1 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Dahane Estama | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} | c0a8-00c9-12fddbf6b0e-be429331-b45-fe | MF-NE-503 | HT - HALO TRUST | H/4863 | 7776 | 68.2445 | 35.4143 | Open | AP Only | AP Only | MineField |  | MBT Project-027 | Baghlan Demining Project-01 |  |  |  |  | 1394 |  | {32718E8F-CA22-4B7F-BC9D-6ACB3CCEE93D} |  | High with Victim | High with Victims | Substantial | 989 | CHA | 1 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Dahane Marq | {7F788A0B-F291-444F-916D-D9FC5DF5A540} | c0a8-0009-14563a5e9d2-d80fe528-2bcd-f | Hz-ID-18619 | HT - HALO TRUST | H/8919 | 35720 | 68.2434 | 35.3477 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {7F788A0B-F291-444F-916D-D9FC5DF5A540} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2014-03-08 16:30 | No | Open
North East | Baghlan | Tala Wa Barfak | Dahane Marq | {7F788A0B-F291-444F-916D-D9FC5DF5A540} | c0a8-0057-12c3b968745-a3f729cf-28e09- | MF-NE-479 | HT - HALO TRUST | H/2518 | 27600 | 68.2465 | 35.3478 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {7F788A0B-F291-444F-916D-D9FC5DF5A540} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-01-06 | No | Open
North East | Baghlan | Tala Wa Barfak | Dahane Marq | {7F788A0B-F291-444F-916D-D9FC5DF5A540} | c0a8-0057-12c3b99e91f-deef915c-2b189- | MF-NE-582 | HT - HALO TRUST | H/4768 | 37500 | 68.2608 | 35.3415 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {7F788A0B-F291-444F-916D-D9FC5DF5A540} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Dahane Marq | {7F788A0B-F291-444F-916D-D9FC5DF5A540} | c0a8-0057-12c3bb0bacc-a02d05a4-38f33- | MF-NE-580 | HT - HALO TRUST | H/4779 | 70500 | 68.1358 | 35.4754 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {7F788A0B-F291-444F-916D-D9FC5DF5A540} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Dahane Marq | {7F788A0B-F291-444F-916D-D9FC5DF5A540} | c0a8-0057-12c3bb14389-78a138e1-39454- | MF-NE-578 | HT - HALO TRUST | H/4769 | 31000 | 68.2629 | 35.3484 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {7F788A0B-F291-444F-916D-D9FC5DF5A540} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Dashte Lajam | {A9ED7FF0-5D4D-41A3-A19D-590CEF41607C} | c0a8-0057-12c3b7ef730-2d8bec4f-18af1- | MF-NE-571 | HT - HALO TRUST | H/4796 | 35500 | 68.2506 | 35.3952 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {A9ED7FF0-5D4D-41A3-A19D-590CEF41607C} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Dashte Lajam | {A9ED7FF0-5D4D-41A3-A19D-590CEF41607C} | c0a8-0057-12c3bb55af5-6b793b7d-3bb00- | MF-HQ-11850 | HT - HALO TRUST | H/5244 | 35846 | 68.2397 | 35.3908 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {A9ED7FF0-5D4D-41A3-A19D-590CEF41607C} |  | Low | Critical Infrastracture | Substantial | 107 | CHA | 5 |  |  | 2008-11-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Gosha | {D2029069-7343-4004-AFB6-D2824A95580C} | c0a8-0057-12c3b8d2905-641a9f66-22ac7- | MF-NE-521 | HT - HALO TRUST | H/4864 | 29900 | 68.4181 | 35.3788 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {D2029069-7343-4004-AFB6-D2824A95580C} |  | Low | Agriculture Blocked | Substantial | 93 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Gosha | {D2029069-7343-4004-AFB6-D2824A95580C} | c0a8-0057-12c3b8d2af8-b86169ff-22add- | MF-NE-520 | HT - HALO TRUST | H/2514 | 71500 | 68.4132 | 35.3796 | Open | AP Only | AP Only | MineField |  | MBT Project-152 | Baghlan Demining Project-2 (AT) |  |  |  |  | 1396 |  | {D2029069-7343-4004-AFB6-D2824A95580C} |  | Low | Agriculture Blocked | Substantial | 93 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Kawshandaz | {72F6B436-B13E-4902-A656-E42B34857FBE} | c0a8-00c9-12fddc38f5d-98a3d10e-b61-91 | MF-NE-481 | HT - HALO TRUST | H/2516 | 800 | 68.1374 | 35.3257 | Open | AP Only | AP Only | MineField |  | MBT Project-027 | Baghlan Demining Project-01 |  |  |  |  | 1394 |  | {72F6B436-B13E-4902-A656-E42B34857FBE} |  | Medium | Critical Infrastracture | Substantial | 13 | CHA | 3 |  |  | 2008-01-06 | No | Open
North East | Baghlan | Tala Wa Barfak | Kololasang | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} | c0a8-0057-12c3b9a54ea-d7037b07-2b604- | MF-NE-515 | HT - HALO TRUST | H/4859 | 201200 | 68.4107 | 35.4391 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Kololasang | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} | c0a8-0057-12c3b9a568f-c065174f-2b61a- | MF-NE-517 | HT - HALO TRUST | H/4860 | 102000 | 68.4155 | 35.441 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Kololasang | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} | c0a8-0057-12c3b9a5863-1890d3ed-2b62d- | MF-NE-513 | HT - HALO TRUST | H/2520 | 112500 | 68.4168 | 35.4365 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Kololasang | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} | c0a8-0057-12c3b9a5a27-ddf12e70-2b63f- | MF-NE-514 | HT - HALO TRUST | H/4858 | 127500 | 68.4107 | 35.4391 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Kololasang | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} | c0a8-0057-12c3bb3139f-312a77df-3a59f- | MF-NE-510 | HT - HALO TRUST | H/4856 | 78000 | 68.3832 | 35.3743 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Kololasang | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} | c0a8-0057-12c3bb315b1-bfbac3d1-3a5b5- | MF-NE-508 | HT - HALO TRUST | H/2515 | 84000 | 68.3775 | 35.3812 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Kololasang | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} | c0a8-0057-12c3bb3186f-f5349f99-3a5c9- | MF-NE-505 | HT - HALO TRUST | H/4857 | 90400 | 68.3766 | 35.3768 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Kololasang | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} | c0a8-0057-12c3bb31ac0-3264c0e-3a5e4-7 | MF-NE-511 | HT - HALO TRUST | H/4854 | 75000 | 68.3874 | 35.3703 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Kololasang | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} | c0a8-0057-12c3bb31d01-59064673-3a5fb- | MF-NE-504 | HT - HALO TRUST | H/4855 | 80700 | 68.3855 | 35.3743 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Kololasang | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} | c0a8-0057-12c3bb31f33-7b8fa226-3a614- | MF-NE-507 | HT - HALO TRUST | H/4853 | 34000 | 68.3889 | 35.3837 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A754E047-2233-44E0-BE5C-6BC00ACA4E58} |  | Low | Agriculture Blocked | Substantial | 22 | CHA | 5 |  |  | 2008-07-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Maqsud | {CE5CEC00-7BC6-433F-84CC-DD827509CC9C} | c0a8-0057-12c3b9230bb-e40536c2-2604c- | MF-HQ-14136 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1305/00830/MF0008 | 20000 | 68.5494 | 35.3384 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {CE5CEC00-7BC6-433F-84CC-DD827509CC9C} |  | Low | Agriculture Blocked | Substantial | 0 | SHA | 5 |  |  | 2010-02-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Maqsud | {CE5CEC00-7BC6-433F-84CC-DD827509CC9C} | c0a8-0057-12c3bb25d6c-4be276e3-39ee7- | MF-HQ-14134 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1305/00830/MF0007 | 30000 | 68.5495 | 35.3375 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {CE5CEC00-7BC6-433F-84CC-DD827509CC9C} |  | Low | Agriculture Blocked | Substantial | 0 | SHA | 5 |  |  | 2010-02-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Nagharakhana | {32F8154F-7A92-46DB-B58E-610E325E76CD} | c0a8-0009-1454a1b8f93-4b77a89b-8d9-6c | Hz-ID-18620 | HT - HALO TRUST | H/8920 | 32530 | 68.2671 | 35.3837 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {32F8154F-7A92-46DB-B58E-610E325E76CD} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2014-03-18 16:30 | No | Open
North East | Baghlan | Tala Wa Barfak | Nagharakhana | {32F8154F-7A92-46DB-B58E-610E325E76CD} | c0a8-0057-12c3ba8ffcb-d63bd1cf-34626- | MF-NE-562 | HT - HALO TRUST | H/4784 | 88300 | 68.2759 | 35.3814 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {32F8154F-7A92-46DB-B58E-610E325E76CD} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Nagharakhana | {32F8154F-7A92-46DB-B58E-610E325E76CD} | c0a8-0057-12c3ba9019f-be6d2b3b-3463d- | MF-NE-564 | HT - HALO TRUST | H/2517 | 84300 | 68.2778 | 35.3806 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {32F8154F-7A92-46DB-B58E-610E325E76CD} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Pazhak | {7A918166-599A-41A6-B94A-6BD354700C54} | c0a8-0057-12c3b7be186-d1ac298-16874-b | MF-NE-490 | HT - HALO TRUST | H/4865 | 51500 | 68.2888 | 35.4161 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {7A918166-599A-41A6-B94A-6BD354700C54} |  | Low | Agriculture Blocked | Substantial | 17 | CHA | 4 |  |  | 2008-01-07 | No | Open
North East | Baghlan | Tala Wa Barfak | Pazhak | {7A918166-599A-41A6-B94A-6BD354700C54} | c0a8-0057-12c3b7be33b-a8207cf7-1688a- | MF-NE-487 | HT - HALO TRUST | H/4866 | 62000 | 68.2866 | 35.4101 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {7A918166-599A-41A6-B94A-6BD354700C54} |  | Low | Agriculture Blocked | Substantial | 44 | CHA | 4 |  |  | 2008-01-07 | No | Open
North East | Baghlan | Tala Wa Barfak | Pazhak | {7A918166-599A-41A6-B94A-6BD354700C54} | c0a8-0057-12c3b7be4e0-68f54f44-168a1- | MF-NE-488 | HT - HALO TRUST | H/4867 | 66000 | 68.2923 | 35.4145 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {7A918166-599A-41A6-B94A-6BD354700C54} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2008-01-07 | No | Open
North East | Baghlan | Tala Wa Barfak | Pazhak | {7A918166-599A-41A6-B94A-6BD354700C54} | c0a8-0057-12c3b885b85-3a39df04-1f59b- | MF-NE-492 | HT - HALO TRUST | H/2510 | 85000 | 68.3037 | 35.3811 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {7A918166-599A-41A6-B94A-6BD354700C54} |  | Low | Agriculture Blocked | Substantial | 112 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Pazhak | {7A918166-599A-41A6-B94A-6BD354700C54} | c0a8-0057-12c3b885d2b-b4440197-1f5b2- | MF-NE-495 | HT - HALO TRUST | H/4786 | 65600 | 68.3092 | 35.3771 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {7A918166-599A-41A6-B94A-6BD354700C54} |  | Low | Agriculture Blocked | Substantial | 5 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Qara (1) | {475ECB8C-AC32-4A7F-8D0D-78FD50DE1F87} | c0a8-0057-12c3bb4f1b8-9f5295f6-3b741- | MF-NE-461 | HT - HALO TRUST | H/4861 | 117000 | 68.1732 | 35.3902 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {475ECB8C-AC32-4A7F-8D0D-78FD50DE1F87} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-01-07 | No | Open
North East | Baghlan | Tala Wa Barfak | Qara (1) | {475ECB8C-AC32-4A7F-8D0D-78FD50DE1F87} | c0a8-0057-12c3bb4f419-390cf5dd-3b75a- | MF-NE-462 | HT - HALO TRUST | H/4862 | 160400 | 68.1731 | 35.3902 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {475ECB8C-AC32-4A7F-8D0D-78FD50DE1F87} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-01-07 | No | Open
North East | Baghlan | Tala Wa Barfak | Sarsang | {D8F85A5C-B866-49E6-92CC-18A6B8E29124} | c0a8-0057-12c3bad8bc8-f27e6ea2-37091- | MF-NE-468 | HT - HALO TRUST | H/4871 | 73666 | 68.3645 | 35.4361 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes |  |  | 1393 | HT | {D8F85A5C-B866-49E6-92CC-18A6B8E29124} |  | High Requested | Resettlment/Local Request | Substantial | 1 | CHA | 5 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-01-07 | No | Planned
North East | Baghlan | Tala Wa Barfak | Sarsang | {D8F85A5C-B866-49E6-92CC-18A6B8E29124} | c0a8-0057-12c3bad8d8d-55cc6acc-370a7- | MF-NE-465 | HT - HALO TRUST | H/4869 | 65980 | 68.358 | 35.4373 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes |  |  | 1393 | HT | {D8F85A5C-B866-49E6-92CC-18A6B8E29124} |  | High Requested | Resettlment/Local Request | Substantial | 1 | CHA | 1 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-01-07 | No | Planned
North East | Baghlan | Tala Wa Barfak | Sarsang | {D8F85A5C-B866-49E6-92CC-18A6B8E29124} | c0a8-0057-12c3bad91d1-5736c196-370d7- | MF-NE-464 | HT - HALO TRUST | H/4868 | 80409 | 68.3567 | 35.4345 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes |  |  | 1393 | HT | {D8F85A5C-B866-49E6-92CC-18A6B8E29124} |  | High Requested | Resettlment/Local Request | Substantial | 0 | CHA | 1 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-01-07 | No | Planned
North East | Baghlan | Tala Wa Barfak | Sarsang | {D8F85A5C-B866-49E6-92CC-18A6B8E29124} | c0a8-0057-12c3bad93a5-68e0004a-370ef- | MF-NE-463 | HT - HALO TRUST | H/4872 | 87599 | 68.3692 | 35.4363 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-079 | Baghlan Demining Project-02 | VTF-Japan | Yes |  |  | 1393 | HT | {D8F85A5C-B866-49E6-92CC-18A6B8E29124} |  | High Requested | Resettlment/Local Request | Substantial | 1 | CHA | 5 | Yes | Priority of the tasks are high but these tasks are very remote and sometimes security problem | 2008-01-07 | No | Planned
North East | Baghlan | Tala Wa Barfak | Sarsang | {D8F85A5C-B866-49E6-92CC-18A6B8E29124} | c0a8-00c9-12fddcf386e-766e3c4e-4-70c1 | MF-NE-467 | HT - HALO TRUST | H/4870 | 64000 | 68.3611 | 35.4367 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-027/A | Baghlan Demining Project-01/A | Bilateral | Yes |  |  | 1393 | HT | {D8F85A5C-B866-49E6-92CC-18A6B8E29124} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-01-07 | No | Planned
North East | Baghlan | Tala Wa Barfak | Sayelan | {B1B1CAC7-793F-4679-BDF6-71CC30491F58} | c0a8-0009-1453fb578e0-78bb8a7f-a92-32 | Hz-ID-18579 | HT - HALO TRUST | H/8909 | 51480 | 68.2321 | 35.4154 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {B1B1CAC7-793F-4679-BDF6-71CC30491F58} |  | Low | Agriculture Blocked | Substantial | 446 | CHA | 4 |  |  | 2014-03-03 16:30 | No | Open
North East | Baghlan | Tala Wa Barfak | Sayelan | {B1B1CAC7-793F-4679-BDF6-71CC30491F58} | c0a8-0009-145452c8241-6892e3e0-23d-2b | Hz-ID-18606 | HT - HALO TRUST | H/8910 | 84762 | 68.2311 | 35.412 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {B1B1CAC7-793F-4679-BDF6-71CC30491F58} |  | Low | Agriculture Blocked | Substantial | 325 | CHA | 4 |  |  | 2014-03-04 16:30 | No | Open
North East | Baghlan | Tala Wa Barfak | Sayelan | {B1B1CAC7-793F-4679-BDF6-71CC30491F58} | c0a8-0009-145453c81d0-2d1a4766-2d6-b5 | Hz-ID-18607 | HT - HALO TRUST | H/8911 | 72424 | 68.231 | 35.4097 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {B1B1CAC7-793F-4679-BDF6-71CC30491F58} |  | Low | Agriculture Blocked | Substantial | 121 | CHA | 4 |  |  | 2014-03-02 16:30 | No | Open
North East | Baghlan | Tala Wa Barfak | Sayelan | {B1B1CAC7-793F-4679-BDF6-71CC30491F58} | c0a8-0057-12c3bb7ece1-31536b84-3d229- | MF-HQ-12322 | HT - HALO TRUST | H/2508 | 57419 | 68.2442 | 35.4212 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {B1B1CAC7-793F-4679-BDF6-71CC30491F58} |  | Low | Agriculture Blocked | Substantial | 54 | CHA | 5 |  |  | 2002-08-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Shahidan | {A9AF703B-1AE9-486B-B1F7-DD8A2D11755D} | c0a8-0057-12c3bb55450-fde1fc79-3bace- | MF-NE-551 | HT - HALO TRUST | H/4782 | 17800 | 68.2534 | 35.3839 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A9AF703B-1AE9-486B-B1F7-DD8A2D11755D} |  | Low | Agriculture Blocked | Substantial | 18 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Shahidan | {A9AF703B-1AE9-486B-B1F7-DD8A2D11755D} | c0a8-0057-12c3bb556d0-a3a161f9-3bae8- | MF-NE-550 | HT - HALO TRUST | H/2519 | 15000 | 68.2463 | 35.3814 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {A9AF703B-1AE9-486B-B1F7-DD8A2D11755D} |  | Low | Agriculture Blocked | Substantial | 20 | CHA | 5 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Shahre Sagan | {17A68B9E-8109-48F8-9E23-821DBEC71953} | c0a8-0009-14563ad048d-b818a405-2e85-8 | Hz-ID-18616 | HT - HALO TRUST | H/8916 | 10200 | 68.2332 | 35.4329 | Open | AP Only | AP Only | MineField |  | MBT Project-242 | Baghlan Demining Project-03 |  |  |  |  | 1395 |  | {17A68B9E-8109-48F8-9E23-821DBEC71953} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2014-03-04 16:30 | No | Open
North East | Baghlan | Tala Wa Barfak | Tala Wa Barfak | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} | c0a8-0057-12c3b87200f-bcf477d2-1e7ba- | MF-NE-497 | HT - HALO TRUST | H/2509 | 60500 | 68.1973 | 35.4004 | Open | AP Only | AP Only | MineField |  | MBT Project-027 | Baghlan Demining Project-01 |  |  |  |  | 1394 |  | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} |  | High with Victim | High with Victims | Substantial | 1 | CHA | 2 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Tala Wa Barfak | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} | c0a8-0057-12c3b8721d3-bf046a07-1e7ce- | MF-NE-499 | HT - HALO TRUST | H/4770 | 63600 | 68.1988 | 35.4019 | Open | AP Only | AP Only | MineField |  | MBT Project-027 | Baghlan Demining Project-01 |  |  |  |  | 1394 |  | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} |  | High with Victim | High with Victims | Substantial | 13 | CHA | 2 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Tala Wa Barfak | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} | c0a8-0057-12c3b872398-5af72163-1e7e5- | MF-NE-498 | HT - HALO TRUST | H/4771 | 49700 | 68.2003 | 35.4036 | Open | AP Only | AP Only | MineField |  | MBT Project-027 | Baghlan Demining Project-01 |  |  |  |  | 1394 |  | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} |  | High with Victim | High with Victims | Substantial | 13 | CHA | 2 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Tala Wa Barfak | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} | c0a8-0057-12c3b8d77bf-da2096b5-22e1d- | MF-NE-568 | HT - HALO TRUST | H/4774 | 91200 | 68.195 | 35.4072 | Open | AP Only | AP Only | MineField |  | MBT Project-027 | Baghlan Demining Project-01 |  |  |  |  | 1394 |  | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} |  | High with Victim | High with Victims | Substantial | 4 | CHA | 2 |  |  | 2008-06-01 | No | Open
North East | Baghlan | Tala Wa Barfak | Tala Wa Barfak | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} | c0a8-0057-12c3b8d7983-6ea027fc-22e31- | MF-NE-569 | HT - HALO TRUST | H/4773 | 72800 | 68.1969 | 35.4067 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-027/B | Baghlan Demining Project-01/B | GAGP | Yes |  |  | 1393 | HT | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} |  | High with Victim | High with Victims | Substantial | 4 | CHA | 2 |  |  | 2008-06-01 | No | Planned
North East | Baghlan | Tala Wa Barfak | Tala Wa Barfak | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} | c0a8-0057-12c3b8d7b57-5f2333d-22e45-4 | MF-NE-567 | HT - HALO TRUST | H/4775 | 68000 | 68.1929 | 35.4073 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-027/B | Baghlan Demining Project-01/B | GAGP | Yes |  |  | 1393 | HT | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} |  | High with Victim | High with Victims | Substantial | 10 | CHA | 2 |  |  | 2008-06-01 | No | Planned
North East | Baghlan | Tala Wa Barfak | Tala Wa Barfak | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} | c0a8-0057-12c3b8d7d4b-268e2233-22e5b- | MF-NE-583 | HT - HALO TRUST | H/4772 | 90000 | 68.1941 | 35.405 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-027/B | Baghlan Demining Project-01/B | GAGP | Yes |  |  | 1393 | HT | {A6185A21-6625-4B36-A4D5-1D75B98B5B5C} |  | High with Victim | High with Victims | Substantial | 4 | CHA | 2 |  |  | 2008-06-01 | No | Planned
North East | Kunduz | Aliabad | Airport | {ABD6AC6B-9B7B-46B1-BCD2-CC851B3BE5AB} | c0a8-00f6-135e26acea9-a0f900f9-e456-4 | BF-15216 | MCPA - Mine Clearance Planning Agency | AF/1405/00001/BF0001 | 36294 | 68.9055 | 36.6518 | Open | UXO Only | UXO Only | BF |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {ABD6AC6B-9B7B-46B1-BCD2-CC851B3BE5AB} |  | Medium | Critical Infrastracture | Moderate | 122 | CHA | 3 |  |  | 2012-01-21 16:30 | No | Open
North East | Kunduz | Chahar Dara | Durman (1) | {8572271C-2FE8-40D3-A673-53EC2A597FED} | c0a8-0009-13d0a8d8bcd-d658712f-3423-4 | Hz-ID-17633 | MDC - Mine Detection and Dog Center | AF/1404/14117/MF0024 | 6730 | 68.8 | 36.6621 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {8572271C-2FE8-40D3-A673-53EC2A597FED} |  | Low | Infrastructure | Substantial | 40 | CHA | 5 |  |  | 2013-01-28 16:30 | No | Open
North East | Kunduz | Chahar Dara | Haji Amanulla | {11155D64-5331-481A-A494-ECA4B5E2FF85} | c0a8-0009-14106aa568f-a5e022ea-852b-9 | Hz-ID-18166 | MDC - Mine Detection and Dog Center | AF/1401/13780/SpotERW0002 |  | 68.8007 | 36.7016 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {11155D64-5331-481A-A494-ECA4B5E2FF85} |  | Medium | Agriculture Blocked | Substantial | 150 | CHA | 3 |  |  | 2012-12-09 16:30 | No | Open
North East | Kunduz | Chahar Dara | Kharu Ti | {F3F45359-C1F4-418A-90F9-4EC6ED436E9D} | c0a8-00c9-12fddef792a-a689ac56-7-50ff | MF-HQ-11052 | MCPA - Mine Clearance Planning Agency | AF/1404/14131/MF0022 | 5268 | 68.8154 | 36.6829 | Open | AP Only | AP Only | MineField |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {F3F45359-C1F4-418A-90F9-4EC6ED436E9D} |  | Medium | Critical Infrastracture | Substantial | 553 | CHA | 3 |  |  | 2009-07-01 | No | Open
North East | Kunduz | Chahar Dara | Nawabad (1) | {D6A4212D-AF85-428C-B299-13B008ABEE28} | c0a8-00c9-12fddf1c92e-5cbed5a1-22-2b7 | MF-HQ-11007 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1404/14112/MF0020 | 32336 | 68.6503 | 36.6234 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {D6A4212D-AF85-428C-B299-13B008ABEE28} |  | High with Victim | High with Victims | Substantial | 21 | SHA | 2 |  |  | 2009-07-01 | No | Open
North East | Kunduz | Chahar Dara | Nawabad (1) | {D6A4212D-AF85-428C-B299-13B008ABEE28} | c0a8-00c9-12fddf2d4ac-593358be-33-bb6 | MF-HQ-11008 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1404/14112/MF0021 | 9114 | 68.5471 | 36.6303 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {D6A4212D-AF85-428C-B299-13B008ABEE28} |  | High with Victim | High with Victims | Substantial | 24 | SHA | 2 |  |  | 2009-07-01 | No | Open
North East | Kunduz | Chahar Dara | Nawabad (1) | {D6A4212D-AF85-428C-B299-13B008ABEE28} | c0a8-00c9-12fddf3eeae-7f332792-47-c6a | MF-NE-991 | MDC - Mine Detection and Dog Center | AF/1404/14112/MF0019 | 290500 | 68.6642 | 36.6583 | Open | AT Only | AT Only | MineField |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {D6A4212D-AF85-428C-B299-13B008ABEE28} |  | High with Victim | High with Victims | Substantial | 40 | CHA | 2 |  |  | 2008-03-20 | No | Open
North East | Kunduz | Chahar Dara | Nawabad (1) | {D6A4212D-AF85-428C-B299-13B008ABEE28} | c0a8-00c9-12fddf654b0-82b57b4a-67-5a3 | MF-NE-992 | MDC - Mine Detection and Dog Center | AF/1404/14112/MF0023 | 61656 | 68.6614 | 36.6617 | Open | AP Only | AP Only | MineField |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {D6A4212D-AF85-428C-B299-13B008ABEE28} |  | High with Victim | High with Victims | Substantial | 43 | CHA | 2 |  |  | 2008-03-24 | No | Open
North East | Kunduz | Chahar Dara | Palaw Kamar | {F3EC19C8-79AB-4CBA-B680-69DB999EB8E1} | c0a8-0009-14106baf0f4-7246b9a8-8ba3-3 | Hz-ID-18159 | MDC - Mine Detection and Dog Center | AF/1404/14116/Spot ERW0001 | 132 | 68.7636 | 36.687 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {F3EC19C8-79AB-4CBA-B680-69DB999EB8E1} |  | High | Critical Infrastracture | Substantial | 82 | CHA | 3 |  |  | 2013-02-11 16:30 | No | Open
North East | Kunduz | Dashte Archi | Ab-i-Shor | {8475ABE5-1C44-4D16-9C1B-E67CA7BA8D08} | c0a8-0057-12c3b6c15f6-20246dfc-ac61-e | MF-HQ-10273 | HT - HALO TRUST | H/6024 | 2800 | 69.3097 | 36.9564 | Open | AT Only | AT Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {8475ABE5-1C44-4D16-9C1B-E67CA7BA8D08} |  | Low | Agriculture Blocked | Substantial | 29 | CHA | 5 |  |  | 2009-04-05 | No | Open
North East | Kunduz | Dashte Archi | Ab-i-Shor | {8475ABE5-1C44-4D16-9C1B-E67CA7BA8D08} | c0a8-0057-12c3b7383c3-7da19525-1069f- | MF-HQ-10271 | HT - HALO TRUST | H/6027 | 616 | 69.3175 | 36.9436 | Open | AP Only | AP Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {8475ABE5-1C44-4D16-9C1B-E67CA7BA8D08} |  | Medium | Agriculture Blocked | Substantial | 17 | CHA | 3 |  |  | 2009-04-03 | No | Open
North East | Kunduz | Dashte Archi | Ab-i-Shor | {8475ABE5-1C44-4D16-9C1B-E67CA7BA8D08} | c0a8-0057-12c3b7af141-8d8db08d-15db8- | MF-HQ-10272 | HT - HALO TRUST | H/6025 | 4800 | 69.3097 | 36.9565 | Open | AT Only | AT Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {8475ABE5-1C44-4D16-9C1B-E67CA7BA8D08} |  | Low | Small Hazards | Substantial | 28 | CHA | 5 |  |  | 2009-04-05 | No | Open
North East | Kunduz | Dashte Archi | Ab-i-Shor | {8475ABE5-1C44-4D16-9C1B-E67CA7BA8D08} | c0a8-0057-12c3b867d7b-41ee1118-1e0b0- | MF-HQ-10237 | HT - HALO TRUST | H/6026 | 29800 | 69.2999 | 36.9661 | Open | AP Only | AP Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {8475ABE5-1C44-4D16-9C1B-E67CA7BA8D08} |  | Low | Agriculture Blocked | Substantial | 21 | CHA | 5 |  |  | 2009-04-03 | No | Open
North East | Kunduz | Dashte Archi | Ab-i-Shor | {8475ABE5-1C44-4D16-9C1B-E67CA7BA8D08} | c0a8-0057-12c3ba8685e-d799fe22-340e6- | MF-HQ-11009 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1407/14071/MF0020 | 232200 | 69.3282 | 36.9263 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {8475ABE5-1C44-4D16-9C1B-E67CA7BA8D08} |  | Low | Agriculture Blocked | Substantial | 17 | SHA | 5 |  |  | 2009-07-01 | No | Open
North East | Kunduz | Dashte Archi | Archi | {6FA4BD82-08E7-4ECE-A696-9A01025C3D1B} | c0a8-0057-12c3b92caa1-c4e69f65-2666b- | MF-HQ-12330 | HT - HALO TRUST | H/2640 | 110000 | 69.3183 | 37.0497 | Open | AT Only | AT Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {6FA4BD82-08E7-4ECE-A696-9A01025C3D1B} |  | High with Victim | High with Victims | Substantial | 88 | CHA | 2 |  |  | 2002-01-30 | No | Open
North East | Kunduz | Dashte Archi | Galam Taba | {1E3CA8A4-4E64-414E-A18F-B933ADEB58D4} | c0a8-0057-12c3ba78810-25787ec2-3386d- | MF-HQ-12163 | HT - HALO TRUST | H/2638 | 6000 | 69.038 | 36.9869 | Open | AT Only | AT Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {1E3CA8A4-4E64-414E-A18F-B933ADEB58D4} |  | Low | Other | Substantial | 25 | CHA | 5 |  |  | 2005-09-12 | No | Open
North East | Kunduz | Dashte Archi | Galam Taba | {1E3CA8A4-4E64-414E-A18F-B933ADEB58D4} | c0a8-0057-12c3ba78aed-7fcdf566-33881- | MF-NE-996 | MDC - Mine Detection and Dog Center | AF/1407/14080/MF0017 | 1885 | 69.0165 | 36.9778 | Open | AT Only | AT Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {1E3CA8A4-4E64-414E-A18F-B933ADEB58D4} |  | Low | Agriculture Blocked | Substantial | 47 | CHA | 5 |  |  | 2009-02-25 | No | Open
North East | Kunduz | Dashte Archi | Gul Bulaq | {DF81A52E-1BC6-41BF-BEC8-03562E9BCCC3} | c0a8-0009-13f190500f5-e9c94066-5064-6 | Hz-ID-17956 | HT - HALO TRUST | H/8477 | 2800 | 69.2206 | 36.8265 | Open | AP Only | AP Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {DF81A52E-1BC6-41BF-BEC8-03562E9BCCC3} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2013-05-02 16:30 | No | Open
North East | Kunduz | Dashte Archi | Gul Bulaq | {DF81A52E-1BC6-41BF-BEC8-03562E9BCCC3} | c0a8-0009-13f2cba2b31-3da5dae2-575f-4 | Hz-ID-17964 | HT - HALO TRUST | H/8493 | 1950 | 69.2241 | 36.8233 | Open | AP Only | AP Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {DF81A52E-1BC6-41BF-BEC8-03562E9BCCC3} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2013-05-02 16:30 | No | Open
North East | Kunduz | Dashte Archi | Mulla Abdul Ghani | {EA4F4A4D-1F25-46A2-AEB5-7E59AED98140} | c0a8-0057-12c3b978970-ac41e5e4-29863- | MF-HQ-11006 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1407/00730/MF0021 | 18360 | 69.2596 | 36.9805 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {EA4F4A4D-1F25-46A2-AEB5-7E59AED98140} |  | Low | Agriculture Blocked | Substantial | 5 | SHA | 5 |  |  | 2009-07-01 | No | Open
North East | Kunduz | Dashte Archi | Mulla Abdul Ghani | {EA4F4A4D-1F25-46A2-AEB5-7E59AED98140} | c0a8-0057-12c3bb809b3-7f73a6d2-3d339- | MF-HQ-11005 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1407/00730/MF0022 | 24426 | 69.2555 | 36.9805 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {EA4F4A4D-1F25-46A2-AEB5-7E59AED98140} |  | Low | Agriculture Blocked | Substantial | 9 | SHA | 5 |  |  | 2009-07-01 | No | Open
North East | Kunduz | Dashte Archi | Qara Ghushi (1) | {3F3FBCDB-CC96-4657-A40A-452CE52BD5E0} | c0a8-0057-12c3b6a1d1d-7c90c0c8-9494-b | MF-HQ-10249 | HT - HALO TRUST | H/6089 | 58400 | 69.306 | 36.8991 | Open | AP Only | AP Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {3F3FBCDB-CC96-4657-A40A-452CE52BD5E0} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-04-22 | No | Open
North East | Kunduz | Dashte Archi | Qara Ghushi (1) | {3F3FBCDB-CC96-4657-A40A-452CE52BD5E0} | c0a8-0057-12c3b746d44-5c31ee1b-11189- | MF-HQ-10248 | HT - HALO TRUST | H/6090 | 57350 | 69.3056 | 36.8971 | Open | AP Only | AP Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {3F3FBCDB-CC96-4657-A40A-452CE52BD5E0} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-04-23 | No | Open
North East | Kunduz | Dashte Archi | Qara Ghushi (1) | {3F3FBCDB-CC96-4657-A40A-452CE52BD5E0} | c0a8-0057-12c3b75f43a-db15cd5d-1239a- | MF-HQ-10285 | HT - HALO TRUST | H/6087 | 74800 | 69.306 | 36.8991 | Open | AP Only | AP Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {3F3FBCDB-CC96-4657-A40A-452CE52BD5E0} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2009-04-21 | No | Open
North East | Kunduz | Dashte Archi | Qara Ghushi (1) | {3F3FBCDB-CC96-4657-A40A-452CE52BD5E0} | c0a8-0057-12c3b7a97cd-89bbd3d6-159c1- | MF-HQ-10252 | HT - HALO TRUST | H/6088 | 77200 | 69.306 | 36.8991 | Open | AP Only | AP Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {3F3FBCDB-CC96-4657-A40A-452CE52BD5E0} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2009-04-22 | No | Open
North East | Kunduz | Dashte Archi | Qara Ghushi (2) | {4B610B1D-6235-4CD5-B83E-F0D4C95A76DB} | c0a8-00f6-1356fffb5c0-6cdd4c15-139-9d | MF-16688 | HT - HALO TRUST | H/2637 | 160000 | 69.2672 | 36.9268 | Open | AP Only | AP Only | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {4B610B1D-6235-4CD5-B83E-F0D4C95A76DB} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2004-09-06 16:30 | No | Open
North East | Kunduz | Imam Sahib | Turkman Qudoq, Shour Qudoq | {FAF9C935-4A65-43DB-88AB-F503269E393C} | c0a8-00f6-137547a9333-25f518b1-ea8-8e | MF-16765 | MDC - Mine Detection and Dog Center | AF/1407/00793/MF0024 | 63705 | 68.9753 | 36.9021 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-153 | Kunduz Demining Project-04 |  |  |  |  | 1394 |  | {FAF9C935-4A65-43DB-88AB-F503269E393C} |  | Low | Agriculture Blocked | Substantial | 41 | CHA | 5 |  |  | 2012-04-14 16:30 | No | Open
North East | Kunduz | Khanabad | Ajal | {B08311D2-2579-4894-A363-7D8A51659808} | c0a8-008e-132c97d7159-b15dd431-35a9-e | MF-15962 | MCPA - Mine Clearance Planning Agency | AF/1406/14056/MF0042 | 5765 | 69.14 | 36.7662 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {B08311D2-2579-4894-A363-7D8A51659808} |  | High with Victim | High with Victims | Substantial | 10 | CHA | 5 |  |  | 2011-04-19 16:30 | No | Open
North East | Kunduz | Khanabad | Amirabad | {8701030F-7ADD-4747-93CB-C48815F892C3} | c0a8-008e-1306d56a4f5-165366c-18a-b7b | MF-HQ-11634 | HT - HALO TRUST | H/4032 | 750 | 69.1817 | 36.7208 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {8701030F-7ADD-4747-93CB-C48815F892C3} | , | Low | Agriculture Blocked | Substantial | 16 | CHA | 4 |  |  | 2007-11-15 | No | Open
North East | Kunduz | Khanabad | Amirabad | {8701030F-7ADD-4747-93CB-C48815F892C3} | c0a8-008e-1306d5c8cb8-3b13cd74-1b0-da | MF-HQ-11618 | MCPA - Mine Clearance Planning Agency | AF/1406/32113/MF4034 | 11808 | 69.181 | 36.723 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {8701030F-7ADD-4747-93CB-C48815F892C3} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 16 | CHA | 4 |  |  | 2007-11-15 | No | Open
North East | Kunduz | Khanabad | Chahar Tut | {63CFBB51-4EB5-4210-A7F8-97A3BDC07D17} | c0a8-0009-140383c0cdd-80d261f7-c2-917 | Hz-ID-17581 | MCPA - Mine Clearance Planning Agency | AF/1406/13980/MF0047 | 17277 | 69.1257 | 36.6381 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {63CFBB51-4EB5-4210-A7F8-97A3BDC07D17} |  | Low | Agriculture Blocked | Substantial | 26 | CHA | 5 |  |  | 2012-12-17 16:30 | No | Open
North East | Kunduz | Khanabad | Chahar Tut | {63CFBB51-4EB5-4210-A7F8-97A3BDC07D17} | c0a8-0009-14106c689f9-94c8d28e-8d47-2 | Hz-ID-18171 | MCPA - Mine Clearance Planning Agency | AF/1406/13980/SpotERW0001 |  | 69.1031 | 36.6453 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {63CFBB51-4EB5-4210-A7F8-97A3BDC07D17} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2013-01-20 16:30 | No | Open
North East | Kunduz | Khanabad | Chahar Tut | {63CFBB51-4EB5-4210-A7F8-97A3BDC07D17} | c0a8-0057-12c3b9ed2be-83d4c758-2e34e- | MF-HQ-11864 | MCPA - Mine Clearance Planning Agency | AF/1406/13980/MF5076 | 10000 | 69.1261 | 36.6357 | Open | AP Only | AP Only | MineField | Blank | MBT Project-084 | Kunduz Demining Project-02 |  | No |  |  | 1395 | None | {63CFBB51-4EB5-4210-A7F8-97A3BDC07D17} | Removed from HT Plan for 1391 based on HT revised plan | Low | Agriculture Blocked | Substantial | 5 | CHA | 5 |  |  | 2008-08-15 | No | Open
North East | Kunduz | Khanabad | Chawni | {6004D930-D98B-4C26-8E99-F07DFA367237} | c0a8-004c-1302a79754a-17bb63e8-11b2-9 | MF-HT-205 | MCPA - Mine Clearance Planning Agency | AF/1406/00732/MF3600 | 1370 | 69.1176 | 36.4986 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {6004D930-D98B-4C26-8E99-F07DFA367237} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2007-07-31 | No | Open
North East | Kunduz | Khanabad | Chawni | {6004D930-D98B-4C26-8E99-F07DFA367237} | c0a8-004c-1302a7a5e6d-b7752a86-11ca-d | MF-HQ-11870 | MCPA - Mine Clearance Planning Agency | AF/1406/00732/MF5264 | 2400 | 69.1272 | 36.4717 | Open | AP Only | AP Only | MineField |  | MBT Project-032 | Kunduz Demining Project-01 |  |  |  |  | 1394 |  | {6004D930-D98B-4C26-8E99-F07DFA367237} |  | Medium | Agriculture Blocked | Substantial | 29 | CHA | 3 |  |  | 2008-09-16 | No | Open
North East | Kunduz | Khanabad | Chawni | {6004D930-D98B-4C26-8E99-F07DFA367237} | c0a8-0057-12c3b7d9160-c0b83d67-17be5- | MF-NE-437 | MCPA - Mine Clearance Planning Agency | AF/1406/00732/MF2621 | 16200 | 69.1305 | 36.4667 | Open | AP Only | AP Only | MineField | Blank | MBT Project-084 | Kunduz Demining Project-02 |  | No |  |  | 1395 | None | {6004D930-D98B-4C26-8E99-F07DFA367237} |  | Low | Agriculture Blocked | Substantial | 36 | CHA | 5 |  |  | 2008-02-04 | No | Open
North East | Kunduz | Khanabad | Chogha Sufla (1) | {3E0F769A-5FC2-4F1C-9644-4801EF5E745F} | c0a8-0057-12c3b6d717a-86a8ab18-bce5-2 | MF-HQ-11895 | MCPA - Mine Clearance Planning Agency | AF/1406/14044/MF6305 | 35566 | 69.1959 | 36.6992 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {3E0F769A-5FC2-4F1C-9644-4801EF5E745F} | Removed from HT plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 125 | CHA | 5 |  |  | 2009-07-03 | No | Open
North East | Kunduz | Khanabad | Chogha Sufla (1) | {3E0F769A-5FC2-4F1C-9644-4801EF5E745F} | c0a8-0057-12c3b7a2d59-8e58d866-154df- | MF-HQ-11906 | HT - HALO TRUST | H/6304 | 57200 | 69.1974 | 36.6983 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {3E0F769A-5FC2-4F1C-9644-4801EF5E745F} | , | Low | Agriculture Blocked | Substantial | 125 | CHA | 5 |  |  | 2009-07-03 | No | Open
North East | Kunduz | Khanabad | Chogha-i-Sufla (2) | {1426978E-467E-461F-AF80-96C033BC086A} | c0a8-0057-12c3b6b4ace-1276bb96-a2aa-d | MF-HQ-14896 | MCPA - Mine Clearance Planning Agency | AF/1406/14045/MF6660 | 35500 | 69.2064 | 36.6911 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1426978E-467E-461F-AF80-96C033BC086A} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 35 | CHA | 5 |  |  | 2010-07-17 | No | Open
North East | Kunduz | Khanabad | Chogha-i-Sufla (2) | {1426978E-467E-461F-AF80-96C033BC086A} | c0a8-0057-12c3b70fbf4-49e109f0-e806-3 | MF-HQ-14894 | MCPA - Mine Clearance Planning Agency | AF/1406/14045/MF6658 | 11350 | 69.2039 | 36.6894 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1426978E-467E-461F-AF80-96C033BC086A} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 22 | CHA | 5 |  |  | 2010-07-19 | No | Open
North East | Kunduz | Khanabad | Chogha-i-Sufla (2) | {1426978E-467E-461F-AF80-96C033BC086A} | c0a8-0057-12c3b75bf66-237d596e-1211f- | MF-HQ-14897 | MCPA - Mine Clearance Planning Agency | AF/1406/14045/MF6661 | 25000 | 69.2094 | 36.692 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1426978E-467E-461F-AF80-96C033BC086A} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 29 | CHA | 5 |  |  | 2010-07-18 | No | Open
North East | Kunduz | Khanabad | Chogha-i-Sufla (2) | {1426978E-467E-461F-AF80-96C033BC086A} | c0a8-0057-12c3b78dfba-cd3c546b-145d1- | MF-HQ-14895 | MCPA - Mine Clearance Planning Agency | AF/1406/14045/MF6659 | 33100 | 69.2037 | 36.6897 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1426978E-467E-461F-AF80-96C033BC086A} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 22 | CHA | 5 |  |  | 2010-07-17 | No | Open
North East | Kunduz | Khanabad | Chugha-i-Ulya(2) | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} | c0a8-0009-13f2ceb821e-589f000e-589d-b | Hz-ID-17963 | HT - HALO TRUST | H/8483 | 6863 | 69.2083 | 36.6887 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} |  | Low | Agriculture Blocked | Substantial | 22 | CHA | 5 |  |  | 2013-05-15 16:30 | No | Open
North East | Kunduz | Khanabad | Chugha-i-Ulya(2) | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} | c0a8-0009-13f2cedc7d2-c044a152-5946-6 | Hz-ID-17962 | HT - HALO TRUST | H/8482 | 2340 | 69.221 | 36.6915 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} |  | Low | Agriculture Blocked | Substantial | 79 | CHA | 5 |  |  | 2013-05-13 16:30 | No | Open
North East | Kunduz | Khanabad | Chugha-i-Ulya(2) | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} | c0a8-0009-13f9e160889-f630abca-1990-a | Hz-ID-17982 | HT - HALO TRUST | H/8480 | 21114 | 69.2117 | 36.7021 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} |  | Low | Agriculture Blocked | Substantial | 126 | CHA | 4 |  |  | 2013-05-14 16:30 | No | Open
North East | Kunduz | Khanabad | Chugha-i-Ulya(2) | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} | c0a8-0009-13fa7f0354d-151faf56-2a62-2 | Hz-ID-17959 | HT - HALO TRUST | H/8481 | 18041 | 69.2138 | 36.703 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} |  | Low | Agriculture Blocked | Substantial | 117 | CHA | 4 |  |  | 2013-05-16 16:30 | No | Open
North East | Kunduz | Khanabad | Chugha-i-Ulya(2) | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} | c0a8-0009-1417cd25f19-574ae57b-58d-a9 | Hz-ID-18176 | MCPA - Mine Clearance Planning Agency | AF/1406/14051/MF0052 | 19349 | 69.224 | 36.7087 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} |  | Low | Agriculture Blocked | Substantial | 84 | CHA | 5 |  |  | 2013-06-20 16:30 | No | Open
North East | Kunduz | Khanabad | Chugha-i-Ulya(2) | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} | c0a8-0057-12c3b8f071e-9529ba5d-23f35- | MF-HQ-11358 | MCPA - Mine Clearance Planning Agency | AF/1406/14051/MF4971 | 21697 | 69.2127 | 36.7093 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} | , | Low | Agriculture Blocked | Substantial | 157 | CHA | 4 |  |  | 2008-07-18 | No | Open
North East | Kunduz | Khanabad | Chugha-i-Ulya(2) | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} | c0a8-0057-12c3ba62980-d46be455-32ae2- | MF-HQ-10743 | HT - HALO TRUST | H/4030 | 32000 | 69.2157 | 36.7041 | Open | AP Only | AP Only | MineField | Blank | MBT Project-084 | Kunduz Demining Project-02 |  | No |  |  | 1395 | None | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} | Removed from HT Plan for 1391 based on HT revised plan | Low | Agriculture Blocked | Substantial | 146 | CHA | 4 |  |  | 2007-11-13 | No | Open
North East | Kunduz | Khanabad | Chugha-i-Ulya(2) | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} | c0a8-0057-12c3ba6316c-d052b81b-32b33- | MF-HQ-10748 | HT - HALO TRUST | H/4027 | 30000 | 69.2104 | 36.7038 | Open | AP Only | AP Only | MineField | Blank | MBT Project-084 | Kunduz Demining Project-02 |  | No |  |  | 1395 | None | {1D794BBA-C6F6-4DBC-9C9E-315E3DCDF201} | Removed from HT Plan for 1391 based on HT revised plan | Low | Agriculture Blocked | Substantial | 115 | CHA | 5 |  |  | 2007-11-13 | No | Open
North East | Kunduz | Khanabad | Dara-I-zangi | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | c0a8-004c-13006869918-ada46954-929-d3 | MF-HQ-11657 | MCPA - Mine Clearance Planning Agency | AF/1406/00076/MF4174 | 31200 | 69.04 | 36.4189 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 | None | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} |  | High Requested | Resettlment/Local Request | Substantial | 0 | CHA | 5 | Yes | Dear ORIAKHIL sahib, Mine clearance request approved by Kunduz governor, Ali Abad district governor and provincial advisor of environment forwarded for your information and inclusion into any of the potential funding demining projects would be highly app | 2008-04-06 | No | Open
North East | Kunduz | Khanabad | Dara-I-zangi | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | c0a8-004c-13006878b5f-2cff8249-950-5a | MF-HQ-11654 | MCPA - Mine Clearance Planning Agency | AF/1406/00076/MF4176 | 27870 | 69.0385 | 36.4197 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 | None | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} |  | High Requested | Resettlment/Local Request | Substantial | 0 | CHA | 5 | Yes | Dear ORIAKHIL sahib, Mine clearance request approved by Kunduz governor, Ali Abad district governor and provincial advisor of environment forwarded for your information and inclusion into any of the potential funding demining projects would be highly app | 2008-04-06 | No | Open
North East | Kunduz | Khanabad | Dara-I-zangi | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | c0a8-004c-1300688928c-cbd25ec9-966-97 | MF-NE-430 | MCPA - Mine Clearance Planning Agency | AF/1406/00076/MF4757 | 18000 | 69.0723 | 36.4454 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 | None | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} |  | High Requested | Resettlment/Local Request | Substantial | 6 | CHA | 5 | Yes | Dear ORIAKHIL sahib, Mine clearance request approved by Kunduz governor, Ali Abad district governor and provincial advisor of environment forwarded for your information and inclusion into any of the potential funding demining projects would be highly app | 2008-01-05 | No | Open
North East | Kunduz | Khanabad | Dara-I-zangi | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | c0a8-004c-1300689c412-641986d3-98a-3d | MF-NE-443 | MCPA - Mine Clearance Planning Agency | AF/1406/00076/MF4758 | 13500 | 69.0743 | 36.4422 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 | None | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} |  | High Requested | Resettlment/Local Request | Substantial | 4 | CHA | 5 | Yes | Dear ORIAKHIL sahib, Mine clearance request approved by Kunduz governor, Ali Abad district governor and provincial advisor of environment forwarded for your information and inclusion into any of the potential funding demining projects would be highly app | 2008-05-31 | No | Open
North East | Kunduz | Khanabad | Dara-I-zangi | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | c0a8-004c-1302a7b8c4b-b18698f0-11e1-6 | MF-HQ-11661 | MCPA - Mine Clearance Planning Agency | AF/1406/00076/MF4186 | 3600 | 69.0666 | 36.463 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} |  | High Requested | Resettlment/Local Request | Substantial | 5 | CHA | 5 | Yes | Dear ORIAKHIL sahib, Mine clearance request approved by Kunduz governor, Ali Abad district governor and provincial advisor of environment forwarded for your information and inclusion into any of the potential funding demining projects would be highly app | 2008-04-14 | No | Open
North East | Kunduz | Khanabad | Dara-I-zangi | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | c0a8-004c-1302a7d01f1-b02a61bf-11f5-d | MF-HQ-11580 | MCPA - Mine Clearance Planning Agency | AF/1406/00076/MF4179 | 2440 | 69.0809 | 36.4528 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} |  | High Requested | Resettlment/Local Request | Substantial | 19 | CHA | 5 | Yes | Dear ORIAKHIL sahib, Mine clearance request approved by Kunduz governor, Ali Abad district governor and provincial advisor of environment forwarded for your information and inclusion into any of the potential funding demining projects would be highly app | 2008-04-11 | No | Open
North East | Kunduz | Khanabad | Dara-I-zangi | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | c0a8-0057-12c3b720f53-3788deff-f512-b | MF-HQ-11660 | MCPA - Mine Clearance Planning Agency | AF/1406/00059/MF4178 | 6850 | 69.0843 | 36.4517 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 | None | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} |  | High Requested | Resettlment/Local Request | Substantial | 17 | CHA | 5 | Yes | Dear ORIAKHIL sahib, Mine clearance request approved by Kunduz governor, Ali Abad district governor and provincial advisor of environment forwarded for your information and inclusion into any of the potential funding demining projects would be highly app | 2008-04-11 | No | Open
North East | Kunduz | Khanabad | Dara-I-zangi | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | c0a8-0057-12c3b7a58bc-aef802c5-156de- | MF-HQ-11658 | MCPA - Mine Clearance Planning Agency | AF/1406/00076/MF4180 | 240 | 69.0817 | 36.453 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | , | High Requested | Resettlment/Local Request | Substantial | 19 | CHA | 5 | Yes | Dear ORIAKHIL sahib, Mine clearance request approved by Kunduz governor, Ali Abad district governor and provincial advisor of environment forwarded for your information and inclusion into any of the potential funding demining projects would be highly app | 2008-04-11 | No | Open
North East | Kunduz | Khanabad | Dara-I-zangi | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | c0a8-0057-12c3b7aa43b-d21cbe9b-15a46- | MF-HQ-11663 | MCPA - Mine Clearance Planning Agency | AF/1406/00076/MF4185 | 6070 | 69.064 | 36.5843 | Open | AP Only | AP Only | MineField | Blank | MBT Project-084 | Kunduz Demining Project-02 |  | No |  |  | 1395 | None | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | Contingency Plan for North/Northeast German RFP | High Requested | Resettlment/Local Request | Substantial | 548 | CHA | 2 | Yes | Dear ORIAKHIL sahib, Mine clearance request approved by Kunduz governor, Ali Abad district governor and provincial advisor of environment forwarded for your information and inclusion into any of the potential funding demining projects would be highly app | 2008-04-14 | No | Open
North East | Kunduz | Khanabad | Dara-I-zangi | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} | c0a8-0057-12c3b9db2e2-248ea64f-2d839- | MF-HQ-11659 | HT - HALO TRUST | H/2635 | 6880 | 69.0822 | 36.4462 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 | None | {1CA681EE-8937-49F4-90FD-D4E80156DCF1} |  | High Requested | Resettlment/Local Request | Substantial | 15 | CHA | 5 | Yes | Dear ORIAKHIL sahib, Mine clearance request approved by Kunduz governor, Ali Abad district governor and provincial advisor of environment forwarded for your information and inclusion into any of the potential funding demining projects would be highly app | 2008-04-10 | No | Open
North East | Kunduz | Khanabad | Dashte Gunjeshkan | {C16F99FC-712C-4936-AC90-70999C6E480C} | c0a8-0009-13ec5725fb3-61c8dcf-2895-eb | Hz-ID-17919 | HT - HALO TRUST | H/8471 | 28000 | 69.2396 | 36.7419 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {C16F99FC-712C-4936-AC90-70999C6E480C} |  | Low | Agriculture Blocked | Substantial | 100 | CHA | 5 |  |  | 2013-04-18 16:30 | No | Open
North East | Kunduz | Khanabad | Dashte Gunjeshkan | {C16F99FC-712C-4936-AC90-70999C6E480C} | c0a8-0009-13ec5763a22-a3b6f9ea-28b3-c | Hz-ID-17918 | HT - HALO TRUST | H/8472 | 54600 | 69.2396 | 36.7419 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {C16F99FC-712C-4936-AC90-70999C6E480C} |  | Low | Agriculture Blocked | Substantial | 25 | CHA | 5 |  |  | 2013-04-18 16:30 | No | Open
North East | Kunduz | Khanabad | Deh-i-Kalan (2) | {8D4D4670-98C2-40CD-8126-4FAD979CFAE4} | c0a8-0057-12c3b7b9f88-ff36574c-1655e- | MF-HQ-11611 | MCPA - Mine Clearance Planning Agency | AF/1406/14024/MF5079 | 8000 | 69.1543 | 36.6334 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {8D4D4670-98C2-40CD-8126-4FAD979CFAE4} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 21 | CHA | 5 |  |  | 2008-08-17 | No | Open
North East | Kunduz | Khanabad | Ghajer Khana (2) | {6E939659-CA9E-4207-B902-601A6B4A7DB5} | c0a8-008e-1308de2bbc1-c13aad92-5fe-f5 | MF-HQ-14142 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1406/14055/MF0031 | 18750 | 69.1286 | 36.8149 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {6E939659-CA9E-4207-B902-601A6B4A7DB5} |  | Low | Other | Substantial | 60 | SHA | 5 |  |  | 2010-02-01 | No | Open
North East | Kunduz | Khanabad | Husayn Khel | {10379C8C-5F50-4207-96CA-DC9A84D3A04F} | c0a8-0009-1410693d53c-e0a708a6-7a39-5 | Hz-ID-18164 | MCPA - Mine Clearance Planning Agency | AF/1406/13981/SpotERW0007 |  | 69.0748 | 36.6545 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {10379C8C-5F50-4207-96CA-DC9A84D3A04F} |  | Medium | Comunity Centers | Substantial | 316 | CHA | 4 |  |  | 2013-01-20 16:30 | No | Open
North East | Kunduz | Khanabad | Husayn Khel | {10379C8C-5F50-4207-96CA-DC9A84D3A04F} | c0a8-0009-1410697cc42-7d762a93-7a76-b | Hz-ID-18163 | MCPA - Mine Clearance Planning Agency | AF/1406/13981/SoptERW0008 |  | 69.0751 | 36.6544 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {10379C8C-5F50-4207-96CA-DC9A84D3A04F} |  | Medium | Comunity Centers | Substantial | 316 | CHA | 4 |  |  | 2013-01-20 16:30 | No | Open
North East | Kunduz | Khanabad | Jamaanchi | {17ECFD14-9365-40EF-B7E1-0463F1AF08F4} | c0a8-0009-13fdc6eb3f6-a7fb4414-2748-2 | Hz-ID-18032 | MCPA - Mine Clearance Planning Agency | AF/1406/0063/MF0051 | 2127 | 69.101 | 36.5069 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {17ECFD14-9365-40EF-B7E1-0463F1AF08F4} |  | Low | Small Hazards | Substantial | 257 | CHA | 4 |  |  | 2013-06-04 16:30 | No | Open
North East | Kunduz | Khanabad | Jamaanchi | {17ECFD14-9365-40EF-B7E1-0463F1AF08F4} | c0a8-0009-13fdc6f4a98-ed0f9058-2764-d | Hz-ID-18029 | MCPA - Mine Clearance Planning Agency | AF/1406/0063/MF0050 | 5701 | 69.1011 | 36.5275 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {17ECFD14-9365-40EF-B7E1-0463F1AF08F4} |  | Low | Agriculture Blocked | Substantial | 10 | CHA | 5 |  |  | 2013-06-03 16:30 | No | Open
North East | Kunduz | Khanabad | Jamaanchi | {17ECFD14-9365-40EF-B7E1-0463F1AF08F4} | c0a8-0009-13fdc6fb50d-f5855d63-2780-a | Hz-ID-18028 | MCPA - Mine Clearance Planning Agency | AF/1406/0063/MF0049 | 1659 | 69.1026 | 36.5253 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {17ECFD14-9365-40EF-B7E1-0463F1AF08F4} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2013-06-03 16:30 | No | Open
North East | Kunduz | Khanabad | Jawlancha | {C0142932-DDC7-4150-B58E-8A188C60FF95} | c0a8-004c-130069095aa-88bc1ce9-a22-ec | MF-HQ-14474 | MCPA - Mine Clearance Planning Agency | AF/1406/14052/MF0034 | 5104 | 69.2077 | 36.7742 | Open | AP Only | AP Only | MineField |  | MBT Project-032 | Kunduz Demining Project-01 |  |  |  |  | 1394 | None | {C0142932-DDC7-4150-B58E-8A188C60FF95} |  | High | Water Blocked | Substantial | 118 | CHA | 3 |  |  | 2010-06-20 | No | Open
North East | Kunduz | Khanabad | Jawlancha | {C0142932-DDC7-4150-B58E-8A188C60FF95} | c0a8-004c-1300691ad11-9b77327-a35-8ce | MF-HQ-11699 | HT - HALO TRUST | H/5054 | 28000 | 69.2363 | 36.7672 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 | None | {C0142932-DDC7-4150-B58E-8A188C60FF95} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-09-20 | No | Open
North East | Kunduz | Khanabad | Jawlancha | {C0142932-DDC7-4150-B58E-8A188C60FF95} | c0a8-008e-132c97166bd-a873711e-3374-4 | MF-15752 | MCPA - Mine Clearance Planning Agency | AF/1406/14052/MF0037 | 7894 | 69.0971 | 36.4756 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {C0142932-DDC7-4150-B58E-8A188C60FF95} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2011-01-30 16:30 | No | Open
North East | Kunduz | Khanabad | Kabuli Qeshlaq | {7753893D-A0F7-4B20-A4A2-8C97A6310217} | c0a8-0009-141068737d5-813ced26-7789-a | Hz-ID-18169 | MCPA - Mine Clearance Planning Agency | AF/1406/14018/SpotERW0005 |  | 69.0896 | 36.7229 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-032 | Kunduz Demining Project-01 |  |  |  |  | 1394 |  | {7753893D-A0F7-4B20-A4A2-8C97A6310217} |  | Medium | Comunity Centers | Substantial | 2271 | CHA | 3 |  |  | 2013-01-20 16:30 | No | Open
North East | Kunduz | Khanabad | Khvajeh Pesta | {933E67FE-F852-4D06-A65B-54586A1A1277} | c0a8-0009-141068eea58-aca1795c-793d-4 | Hz-ID-18167 | MCPA - Mine Clearance Planning Agency | AF/1406/13963/SpotERW0006 |  | 69.0342 | 36.6944 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {933E67FE-F852-4D06-A65B-54586A1A1277} |  | Medium | Comunity Centers | Substantial | 513 | CHA | 4 |  |  | 2013-01-20 16:30 | No | Open
North East | Kunduz | Khanabad | Kohna Qal'a (2) | {241BBCD5-B338-4B88-B925-A43FCA8898C7} | c0a8-0009-14106a1f5f3-29627474-7da9-6 | Hz-ID-18172 | MCPA - Mine Clearance Planning Agency | AF/1406/14043/SpotERW0002 |  | 69.1144 | 36.7052 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-032 | Kunduz Demining Project-01 |  |  |  |  | 1394 |  | {241BBCD5-B338-4B88-B925-A43FCA8898C7} |  | Medium | Agriculture Blocked | Substantial | 279 | CHA | 3 |  |  | 2013-01-20 16:30 | No | Open
North East | Kunduz | Khanabad | Kuhna Qeshlaq | {17454566-4F06-4933-9A1F-09AC8C48AC96} | c0a8-0057-12c3b75c53f-dd057362-12168- | MF-HQ-11596 | MCPA - Mine Clearance Planning Agency | AF/1406/00059/MF4182 | 3400 | 69.0849 | 36.4535 | Open | AP Only | AP Only | MineField | Blank | MBT Project-084 | Kunduz Demining Project-02 |  | No |  |  | 1395 | Blank | {17454566-4F06-4933-9A1F-09AC8C48AC96} |  | Low | Agriculture Blocked | Substantial | 8 | CHA | 5 |  |  | 2008-04-12 | No | Open
North East | Kunduz | Khanabad | Kuhna Qeshlaq | {17454566-4F06-4933-9A1F-09AC8C48AC96} | c0a8-0057-12c3b83d5ce-6329c88a-1c279- | MF-NE-434 | MCPA - Mine Clearance Planning Agency | AF/1406/00059/MF2634 | 5360 | 69.0861 | 36.4579 | Open | AP Only | AP Only | MineField | Blank | MBT Project-084 | Kunduz Demining Project-02 |  | No |  |  | 1395 | Blank | {17454566-4F06-4933-9A1F-09AC8C48AC96} | , | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2008-01-05 | No | Open
North East | Kunduz | Khanabad | Kuhna Qeshlaq | {17454566-4F06-4933-9A1F-09AC8C48AC96} | c0a8-0057-12c3ba04efa-fb709b3f-2f21d- | MF-NE-441 | MCPA - Mine Clearance Planning Agency | AF/1406/00059/MF4752 | 3540 | 69.0834 | 36.4593 | Open | AP Only | AP Only | MineField | Blank | MBT Project-084 | Kunduz Demining Project-02 |  | No |  |  | 1395 | Blank | {17454566-4F06-4933-9A1F-09AC8C48AC96} | , | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-05-31 | No | Open
North East | Kunduz | Khanabad | Kuhna Qeshlaq | {17454566-4F06-4933-9A1F-09AC8C48AC96} | c0a8-0057-12c3bad6758-4fe67571-36f32- | MF-NE-433 | MCPA - Mine Clearance Planning Agency | AF/1406/00059/MF4181 | 14720 | 69.0842 | 36.4529 | Open | AP Only | AP Only | MineField | Blank | MBT Project-084 | Kunduz Demining Project-02 |  | No |  |  | 1395 | Blank | {17454566-4F06-4933-9A1F-09AC8C48AC96} |  | Low | Agriculture Blocked | Substantial | 27 | CHA | 5 |  |  | 2008-04-01 | No | Open
North East | Kunduz | Khanabad | Paitawak | {0969411F-5157-43E8-8797-E8688089644E} | c0a8-008e-1328f9bdf3c-8a01f96a-1d26-c | MF-15615 | MCPA - Mine Clearance Planning Agency | AF/1406/00021/MF7349 | 28780 | 69.2052 | 36.6568 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {0969411F-5157-43E8-8797-E8688089644E} |  | Low | Agriculture Blocked | Substantial | 98 | CHA | 5 |  |  | 2010-12-02 16:30 | No | Open
North East | Kunduz | Khanabad | Paitawak | {0969411F-5157-43E8-8797-E8688089644E} | c0a8-008e-132c95ea54e-ff02f352-328b-e | MF-15673 | MCPA - Mine Clearance Planning Agency | AF/1406/00021/MF7350 | 10000 | 69.2187 | 36.6683 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {0969411F-5157-43E8-8797-E8688089644E} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2010-12-03 16:30 | No | Open
North East | Kunduz | Khanabad | Sahak | {D71E08C9-7C24-467B-9E03-420ED1A7F26C} | c0a8-008e-1306d624704-b6a49b7e-2b4-df | MF-HT-162 | HT - HALO TRUST | H/3521 | 2600 | 69.183 | 36.7186 | Open | AP Only | AP Only | MineField |  | MBT Project-032 | Kunduz Demining Project-01 |  |  |  |  | 1394 |  | {D71E08C9-7C24-467B-9E03-420ED1A7F26C} | , | Medium | Critical Infrastracture | Substantial | 16 | CHA | 3 |  |  | 2007-06-30 | No | Open
North East | Kunduz | Khanabad | Sanduq Say (1) | {76CF824B-9F74-40C3-B7E9-592CAA293AF1} | c0a8-0009-13f9e152a8a-608e3e49-1946-4 | Hz-ID-17983 | HT - HALO TRUST | H/8488 | 28235 | 69.1148 | 36.5664 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {76CF824B-9F74-40C3-B7E9-592CAA293AF1} |  | Low | Agriculture Blocked | Substantial | 39 | CHA | 5 |  |  | 2013-05-18 16:30 | No | Open
North East | Kunduz | Khanabad | Sanduq Say (1) | {76CF824B-9F74-40C3-B7E9-592CAA293AF1} | c0a8-0009-13fa3fe616b-e9258f7a-283f-f | Hz-ID-17957 | HT - HALO TRUST | H/8491 | 1765 | 69.1154 | 36.5635 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {76CF824B-9F74-40C3-B7E9-592CAA293AF1} |  | Low | Agriculture Blocked | Substantial | 18 | CHA | 5 |  |  | 2013-05-19 16:30 | No | Open
North East | Kunduz | Khanabad | Sanduq Say (2) | {DEEE4DC4-3307-4495-B91C-3AEFCCE8ED5D} | c0a8-0009-1403804b3fb-bf17dc56-2f00-7 | Hz-ID-17579 | MCPA - Mine Clearance Planning Agency | AF/1406/13973/MF0046 | 6669 | 69.1001 | 36.5724 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {DEEE4DC4-3307-4495-B91C-3AEFCCE8ED5D} |  | Low | Agriculture Blocked | Substantial | 35 | CHA | 5 |  |  | 2012-12-04 16:30 | No | Open
North East | Kunduz | Khanabad | Sang Gosh | {104D9ABF-F325-4755-8B5A-763FB74D37C2} | c0a8-0009-14106807902-63beca31-773d-e | Hz-ID-18170 | MCPA - Mine Clearance Planning Agency | AF/1406/14015/SpotERW0004 |  | 69.0459 | 36.7774 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-032 | Kunduz Demining Project-01 |  |  |  |  | 1394 |  | {104D9ABF-F325-4755-8B5A-763FB74D37C2} |  | Medium | Agriculture Blocked | Substantial | 39 | CHA | 3 |  |  | 2013-01-20 16:30 | No | Open
North East | Kunduz | Khanabad | Sang Gosh | {104D9ABF-F325-4755-8B5A-763FB74D37C2} | c0a8-0009-14106bff8da-3628261-8cea-97 | Hz-ID-18173 | MCPA - Mine Clearance Planning Agency | AF/1406/14015/SpotERW0003 |  | 69.0487 | 36.7756 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-032 | Kunduz Demining Project-01 |  |  |  |  | 1394 |  | {104D9ABF-F325-4755-8B5A-763FB74D37C2} |  | Medium | Agriculture Blocked | Substantial | 39 | CHA | 3 |  |  | 2013-01-20 16:30 | No | Open
North East | Kunduz | Khanabad | Shor Dara | {B2D9E63B-0DFB-4FE5-8D67-B7949E349D65} | c0a8-0057-12c3b77eb21-f05e391-13aa1-d | MF-HQ-11364 | MCPA - Mine Clearance Planning Agency | AF/1406/00547/MF6005 | 1843 | 69.2005 | 36.5831 | Open | AT Only | AT Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {B2D9E63B-0DFB-4FE5-8D67-B7949E349D65} | , | Low | Small Hazards | Substantial | 3 | CHA | 5 |  |  | 2009-03-05 | No | Open
North East | Kunduz | Khanabad | Shorak Ab | {E15F3CE2-C105-4875-BA47-0530C959C96E} | c0a8-0009-13c1f04166b-4cded119-614-72 | Hz-ID-17583 | MCPA - Mine Clearance Planning Agency | AF/1406/13970/MF0048 | 1888 | 69.0914 | 36.5597 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {E15F3CE2-C105-4875-BA47-0530C959C96E} |  | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2012-12-08 16:30 | No | Open
North East | Kunduz | Khanabad | Shorak Ab | {E15F3CE2-C105-4875-BA47-0530C959C96E} | c0a8-0057-12c3b72960d-53be00d8-fb6b-4 | MF-HQ-10409 | MCPA - Mine Clearance Planning Agency | AF/4061/13970/MF6040 | 60 | 69.1092 | 36.5527 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {E15F3CE2-C105-4875-BA47-0530C959C96E} | Removed from HT Plan for 1391 based on HT revised plan | Medium | Comunity Centers | Substantial | 175 | CHA | 5 |  |  | 2009-04-01 | No | Open
North East | Kunduz | Khanabad | Shorak Ab | {E15F3CE2-C105-4875-BA47-0530C959C96E} | c0a8-0057-12c3b83f012-e09c3bd5-1c3b7- | MF-NE-962 | HT - HALO TRUST | H/2705 | 33877 | 69.1026 | 36.5527 | Open | AT Only | AT Only | MineField |  | MBT Project-032 | Kunduz Demining Project-01 |  |  |  |  | 1394 |  | {E15F3CE2-C105-4875-BA47-0530C959C96E} | It was planned for 1388, as per security problem the task has been suspended, mentioned hazard is re-planned for 1391 but it has removed from HT plan due to security issue and based on HT revised plan | Medium | Critical Infrastracture | Substantial | 204 | CHA | 3 |  |  | 2006-10-04 | No | Open
North East | Kunduz | Khanabad | Shorak Ab | {E15F3CE2-C105-4875-BA47-0530C959C96E} | c0a8-0057-12c3b89b3de-5639708e-2044b- | MF-HQ-11590 | MCPA - Mine Clearance Planning Agency | AF/1406/13970/MF6003 | 19529 | 69.0929 | 36.5552 | Worked on | AP Only | AP Only | MineField | 1390 | MBT Project-084 | Kunduz Demining Project-02 |  | Yes |  |  | 1395 | HT | {E15F3CE2-C105-4875-BA47-0530C959C96E} | Removed from HT plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 15 | CHA | 5 |  |  | 2009-03-03 | No | Open
North East | Kunduz | Khanabad | Shorak Ab | {E15F3CE2-C105-4875-BA47-0530C959C96E} | c0a8-0057-12c3b89b96a-8af680ed-20493- | MF-HQ-14007 | MCPA - Mine Clearance Planning Agency | AF/1406/13970/MF6001 | 10509 | 69.0916 | 36.5581 | Open | AP Only | AP Only | MineField | Blank | MBT Project-084 | Kunduz Demining Project-02 |  | No |  |  | 1395 | None | {E15F3CE2-C105-4875-BA47-0530C959C96E} | It has suspended due to the security problem and removed from HT 1391 plan which was re-planned for 1391 | Low | Agriculture Blocked | Substantial | 4 | CHA | 5 |  |  | 2009-03-06 | No | Open
North East | Kunduz | Khanabad | Shorak Ab | {E15F3CE2-C105-4875-BA47-0530C959C96E} | c0a8-0057-12c3b9c6f63-633f40e2-2cbd1- | MF-HQ-14013 | MCPA - Mine Clearance Planning Agency | AF/1406/13970/MF0027 | 49600 | 69.1119 | 36.5513 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-032 | Kunduz Demining Project-01 |  |  |  |  | 1394 |  | {E15F3CE2-C105-4875-BA47-0530C959C96E} |  | Medium | Critical Infrastracture | Substantial | 238 | CHA | 3 |  |  | 2010-01-17 | No | Open
North East | Kunduz | Khanabad | Shorak Ab | {E15F3CE2-C105-4875-BA47-0530C959C96E} | c0a8-008e-1313ce251a3-be280a90-8ef-c8 | MF-HQ-10415 | MCPA - Mine Clearance Planning Agency | AF/4061/13970/MF6051 | 1630 | 69.0961 | 36.5592 | Open | AP Only | AP Only | MineField |  | MBT Project-032 | Kunduz Demining Project-01 |  |  |  |  | 1394 |  | {E15F3CE2-C105-4875-BA47-0530C959C96E} | , | Medium | Critical Infrastracture | Substantial | 78 | CHA | 3 |  |  | 2009-04-12 | No | Open
North East | Kunduz | Khanabad | Taghak Ab | {7061D4E8-6370-4C97-B6D6-3F106C0DDCA9} | c0a8-0057-12c3b7b0148-8de208d4-15e53- | MF-HQ-11656 | MCPA - Mine Clearance Planning Agency | AF/1406/13947/MF4177 | 6850 | 69.0823 | 36.4475 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {7061D4E8-6370-4C97-B6D6-3F106C0DDCA9} |  | Low | Agriculture Blocked | Substantial | 25 | CHA | 5 |  |  | 2008-04-10 | No | Open
North East | Kunduz | Khanabad | Ta'usabad | {B19459E0-4760-4DFD-9822-48A9252B1DD2} | c0a8-0057-12c3b7aae0b-61fdf88d-15ab8- | MF-HQ-11958 | MCPA - Mine Clearance Planning Agency | AF/1406/13958/MF6317 | 800 | 69.0071 | 36.6429 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {B19459E0-4760-4DFD-9822-48A9252B1DD2} | Removed from HT 1391 plan based on HT revised plan | Medium | Agriculture Blocked | Substantial | 199 | CHA | 5 |  |  | 2009-07-13 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3b6ca9ac-832972ca-b365-1 | MF-HQ-14993 | MCPA - Mine Clearance Planning Agency | AF/1406/00021/MF7322 | 40600 | 69.24 | 36.6508 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 | None | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2010-08-19 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3b74537d-10167715-1104f- | MF-HQ-14989 | MCPA - Mine Clearance Planning Agency | AF/1406/00021/MF7321 | 20400 | 69.24 | 36.6508 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 | None | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} |  | Low | Agriculture Blocked | Substantial | 18 | CHA | 5 |  |  | 2010-08-18 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3b75b29a-d2fc025e-1208f- | MF-HQ-14891 | MCPA - Mine Clearance Planning Agency | AF/1406/14042/MF6655 | 5630 | 69.1981 | 36.6209 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 5 | CHA | 5 |  |  | 2010-07-11 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3b77bb7a-8205652c-13861- | MF-HQ-14892 | MCPA - Mine Clearance Planning Agency | AF/1406/14042/MF6656 | 27200 | 69.202 | 36.6186 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 10 | CHA | 5 |  |  | 2010-07-09 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3b976204-2795aafa-296bb- | MF-HT-818 | HT - HALO TRUST | H/2719 | 11290 | 69.2004 | 36.6296 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 10 | CHA | 5 |  |  | 2010-07-12 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3b976484-2168f214-296d5- | MF-HT-808 | MCPA - Mine Clearance Planning Agency | AF/1406/14042/MF2717 | 10640 | 69.2043 | 36.6194 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 10 | CHA | 5 |  |  | 2010-07-08 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3ba4fdd2-e5958f9e-31f78- | MF-HQ-11707 | MCPA - Mine Clearance Planning Agency | AF/1406/14042/MF5800 | 4755 | 69.2389 | 36.645 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 17 | CHA | 5 |  |  | 2008-10-18 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3ba501e7-78fe00bb-31f96- | MF-HQ-11694 | MCPA - Mine Clearance Planning Agency | AF/1406/14042/MF5805 | 32870 | 69.24 | 36.6455 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 18 | CHA | 5 |  |  | 2008-10-23 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3ba50522-202e3c33-31fb9- | MF-HQ-11667 | MCPA - Mine Clearance Planning Agency | AF/1406/14042/MF5802 | 14850 | 69.2425 | 36.6464 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-20 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3ba50fad-902be22f-32017- | MF-HQ-11668 | MCPA - Mine Clearance Planning Agency | AF/1406/14042/MF5803 | 24750 | 69.2448 | 36.6467 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-21 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3ba51307-c22bd1df-32036- | MF-HQ-11666 | MCPA - Mine Clearance Planning Agency | AF/1406/14042/MF5801 | 20790 | 69.2408 | 36.6457 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 18 | CHA | 5 |  |  | 2008-10-19 | No | Open
North East | Kunduz | Khanabad | Zahed | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | c0a8-0057-12c3ba516fd-cbb9a887-32053- | MF-HQ-11669 | MCPA - Mine Clearance Planning Agency | AF/1406/14042/MF5804 | 21780 | 69.2464 | 36.646 | Open | AP Only | AP Only | MineField |  | MBT Project-084 | Kunduz Demining Project-02 |  |  |  |  | 1395 |  | {FA86A09B-4A1D-4F0A-8AE7-563DD9B8127C} | Removed from HT 1391 plan based on HT revised plan | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-22 | No | Open
North East | Kunduz | Kunduz | Gharaw Shakh | {5ED6552D-FECB-43BD-AFEB-3F8D6641DEB4} | c0a8-0009-14106adb981-e5d477f6-864f-6 | Hz-ID-18162 | MCPA - Mine Clearance Planning Agency | AF/1401/13838/SpotERW0003 |  | 68.7511 | 36.783 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {5ED6552D-FECB-43BD-AFEB-3F8D6641DEB4} |  | Medium | Agriculture Blocked | Substantial | 96 | CHA | 3 |  |  | 2013-02-02 16:30 | No | Open
North East | Kunduz | Kunduz | Hadzarat-i-Sultan | {7BF65DC7-4DC4-4FF5-BE04-78A8396BBDE1} | c0a8-0009-141d544784c-19d0b9a1-37f-74 | Hz-ID-18161 | MCPA - Mine Clearance Planning Agency | AF/1401/13824/SpotERW0002 |  | 68.9107 | 36.7749 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {7BF65DC7-4DC4-4FF5-BE04-78A8396BBDE1} |  | High with Victim | High with Victims | Substantial | 682 | CHA | 2 |  |  | 2013-02-03 16:30 | No | Open
North East | Kunduz | Kunduz | Jar Tapa | {6373D38B-3DBD-49BD-8B8F-A9726C430033} | c0a8-0009-14106c8cd3d-9adc811f-8d63-8 | Hz-ID-18165 | MCPA - Mine Clearance Planning Agency | AF/1401/14121/SpotERW0004 |  | 68.7015 | 36.7757 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {6373D38B-3DBD-49BD-8B8F-A9726C430033} |  | Medium | Agriculture Blocked | Substantial | 38 | CHA | 3 |  |  | 2013-03-18 16:30 | No | Open
North East | Kunduz | Kunduz | Tagha'i | {402771AD-BDA8-4679-A08C-D394F179AE52} | c0a8-0009-14106b78d28-ad59c198-8a4f-5 | Hz-ID-18160 | MCPA - Mine Clearance Planning Agency | AF/1401/13828/SoptERW0001 |  | 68.9297 | 36.6977 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {402771AD-BDA8-4679-A08C-D394F179AE52} |  | Medium | Comunity Centers | Substantial | 10280 | CHA | 3 |  |  | 2013-02-06 16:30 | No | Open
North East | Kunduz | Kunduz | Za Khel (2) | {597A96B3-13A6-46A7-9DF7-FAB67FD31853} | c0a8-0009-14106a72fa2-35e30c3e-7fd9-9 | Hz-ID-18168 | MCPA - Mine Clearance Planning Agency | AF/1401/13813/SpotERW0005 |  | 68.8492 | 36.7318 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-124 | Kunduz Demining Project-03 |  |  |  |  | 1394 |  | {597A96B3-13A6-46A7-9DF7-FAB67FD31853} |  | Medium | Comunity Centers | Substantial | 1312 | CHA | 4 |  |  | 2013-03-12 16:30 | No | Open
North East | Takhar | Baharak | Quduq Qeshlaq | {8802CED7-651E-4E68-A478-AF83EFF2BA10} | c0a8-0057-12c3b69ee21-be699b65-9256-1 | MF-HQ-11938 | HT - HALO TRUST | H/6099 | 46640 | 69.2939 | 36.8606 | Open | AP Only | AP Only | MineField | Blank | MBT Project-085/A | Takhar Demining Project-03 |  | No |  |  | 1395 | Blank | {8802CED7-651E-4E68-A478-AF83EFF2BA10} |  | Low | Agriculture Blocked | Minimal | 9 | CHA | 5 |  |  | 2009-05-15 | No | Open
North East | Takhar | Baharak | Quduq Qeshlaq | {8802CED7-651E-4E68-A478-AF83EFF2BA10} | c0a8-0057-12c3b6a7f28-b250e095-991a-c | MF-HQ-11935 | HT - HALO TRUST | H/6098 | 36960 | 69.2895 | 36.8602 | Open | AP Only | AP Only | MineField | Blank | MBT Project-085/A | Takhar Demining Project-03 |  | No |  |  | 1395 | Blank | {8802CED7-651E-4E68-A478-AF83EFF2BA10} |  | Low | Agriculture Blocked | Minimal | 10 | CHA | 5 |  |  | 2009-05-15 | No | Open
North East | Takhar | Baharak | Quduq Qeshlaq | {8802CED7-651E-4E68-A478-AF83EFF2BA10} | c0a8-0057-12c3b732fcb-810462e8-102b1- | MF-HQ-11960 | HT - HALO TRUST | H/6097 | 30200 | 69.2948 | 36.8687 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes |  |  | 1393 | MDC | {8802CED7-651E-4E68-A478-AF83EFF2BA10} |  | Low | Agriculture Blocked | Minimal | 21 | CHA | 5 |  |  | 2009-05-14 | No | Planned
North East | Takhar | Baharak | Shash Tepa (1) | {F422B0EF-B3DC-4BCC-AAD1-746178EB545F} | c0a8-0009-13df333ea75-196b54cf-c63-4c | Hz-ID-17799 | HT - HALO TRUST | H/8461 | 690 | 69.4299 | 36.772 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-06-11 | 2014-06-12 | 1393 | MDC | {F422B0EF-B3DC-4BCC-AAD1-746178EB545F} |  | Medium | Water Blocked | Minimal | 169 | CHA | 3 |  |  | 2013-03-07 16:30 | No | Planned
North East | Takhar | Baharak | Shash Tepa (1) | {F422B0EF-B3DC-4BCC-AAD1-746178EB545F} | c0a8-0009-13df36f2912-588e7d0f-100c-5 | Hz-ID-17796 | HT - HALO TRUST | H/8460 | 440 | 69.4315 | 36.7719 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-06-13 | 2014-06-17 | 1393 | MDC | {F422B0EF-B3DC-4BCC-AAD1-746178EB545F} |  | Medium | Water Blocked | Minimal | 338 | CHA | 3 |  |  | 2013-03-05 16:30 | No | Planned
North East | Takhar | Baharak | Shash Tepa (1) | {F422B0EF-B3DC-4BCC-AAD1-746178EB545F} | c0a8-0009-13df39801d5-734ff83e-14c7-7 | Hz-ID-17806 | HT - HALO TRUST | H/8459 | 192 | 69.4354 | 36.7736 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-06-16 | 2014-06-20 | 1393 | MDC | {F422B0EF-B3DC-4BCC-AAD1-746178EB545F} |  |  |  | Minimal | 169 | CHA | 3 |  |  | 2013-03-02 16:30 | No | Planned
North East | Takhar | Baharak | Teya Boin | {D70CEF4F-5EDC-4EE7-9539-83797897D876} | c0a8-0057-12c3b6a20c4-17041bd-94c4-13 | MF-HQ-11296 | HT - HALO TRUST | H/6096 | 26500 | 69.3304 | 36.7977 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-05-21 | 2014-06-10 | 1393 | MDC | {D70CEF4F-5EDC-4EE7-9539-83797897D876} |  |  |  | Minimal | 1 | CHA | 5 |  |  | 2009-05-09 | No | Planned
North East | Takhar | Baharak | Teya Boin | {D70CEF4F-5EDC-4EE7-9539-83797897D876} | c0a8-0057-12c3b6aa963-1e0b1c8f-9b19-b | MF-HQ-11291 | HT - HALO TRUST | H/6095 | 30700 | 69.3312 | 36.7985 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-07-03 | 2014-08-15 | 1393 | MDC | {D70CEF4F-5EDC-4EE7-9539-83797897D876} |  | Low | Agriculture Blocked | Minimal | 1 | CHA | 5 |  |  | 2009-05-08 | No | Planned
North East | Takhar | Baharak | Teya Boin | {D70CEF4F-5EDC-4EE7-9539-83797897D876} | c0a8-0057-12c3bb381ea-c3bcfe65-3a9bd- | MF-HQ-11289 | HT - HALO TRUST | H/6093 | 62580 | 69.3222 | 36.8109 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-07-03 | 2014-08-25 | 1393 | MDC | {D70CEF4F-5EDC-4EE7-9539-83797897D876} |  | Low | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2009-05-05 | No | Planned
North East | Takhar | Baharak | Teya Boin | {D70CEF4F-5EDC-4EE7-9539-83797897D876} | c0a8-0057-12c3bb38727-b9e152c9-3a9ee- | MF-HQ-10242 | HT - HALO TRUST | H/6091 | 26400 | 69.3247 | 36.8109 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-06-28 | 2014-07-31 | 1393 | MDC | {D70CEF4F-5EDC-4EE7-9539-83797897D876} |  |  |  | Minimal | 6 | CHA | 5 |  |  | 2009-04-20 | No | Planned
North East | Takhar | Baharak | Teya Boin | {D70CEF4F-5EDC-4EE7-9539-83797897D876} | c0a8-0057-12c3bb38949-3fe6b950-3aa0c- | MF-HQ-10257 | HT - HALO TRUST | H/6092 | 24600 | 69.3245 | 36.8111 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-05-30 | 2014-06-16 | 1393 | MDC | {D70CEF4F-5EDC-4EE7-9539-83797897D876} |  |  |  | Minimal | 0 | CHA | 5 |  |  | 2009-04-20 | No | Planned
North East | Takhar | Baharak | Wochareq | {69CD57F2-EA2B-4D0E-922E-14A6A48F22D6} | c0a8-008e-1328f915b81-12755888-1a60-a | MF-15860 | HT - HALO TRUST | H/7460 | 2230 | 69.4301 | 36.8155 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-06-21 | 2014-06-30 | 1393 | MDC | {69CD57F2-EA2B-4D0E-922E-14A6A48F22D6} |  |  |  | Minimal | 192 | CHA | 3 |  |  | 2011-01-10 16:30 | No | Planned
North East | Takhar | Bangi | Chahar Chenar (4) | {0C1E3022-460A-4925-AB75-2975FC4D7002} | c0a8-0057-12c3b78c74a-c8f9f47b-14480- | MF-HQ-11967 | MCPA - Mine Clearance Planning Agency | AF/1202/12679/MF6321 | 6708 | 69.3771 | 36.5999 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {0C1E3022-460A-4925-AB75-2975FC4D7002} |  |  |  | Minimal | 46 | CHA | 5 | Yes |  | 2009-07-18 | No | Complete
North East | Takhar | Bangi | Ganjala | {9DC46AE7-3BB9-489C-A402-7F5A61AF9FC3} | c0a8-008e-131a7a2f85b-7284b774-2ff4-5 | MF-HT-370 | MCPA - Mine Clearance Planning Agency | AF/1202/00477/MF2894 | 1427 | 69.3556 | 36.6139 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {9DC46AE7-3BB9-489C-A402-7F5A61AF9FC3} | , |  |  | Minimal | 16 | CHA | 5 | Yes |  | 2010-09-30 | No | Complete
North East | Takhar | Bangi | Hazara Qolugh (1) | {80852EB4-A905-49DA-A1BF-D888568029D8} | c0a8-0009-13b7e5265c6-e077117c-4e70-f | Hz-ID-17437 | MCPA - Mine Clearance Planning Agency | AF/1202/12302/MF0014 | 7751 | 69.2568 | 36.768 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {80852EB4-A905-49DA-A1BF-D888568029D8} |  |  |  | Minimal | 7 | SHA | 5 | Yes |  | 2012-11-08 16:30 | No | Complete
North East | Takhar | Bangi | Murch Ali (1) | {C59FFB05-FDED-49B3-94A0-730B57A391E9} | c0a8-0009-13adeb39533-7c0b8b22-b6e-8a | Hz-ID-17321 | MCPA - Mine Clearance Planning Agency | AF/1202/12677/MF0013 | 356 | 69.3556 | 36.6138 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {C59FFB05-FDED-49B3-94A0-730B57A391E9} |  |  |  | Minimal | 0 | CHA | 5 | Yes |  | 2012-10-03 16:30 | No | Complete
North East | Takhar | Bangi | Murch Ali (1) | {C59FFB05-FDED-49B3-94A0-730B57A391E9} | c0a8-0009-13b830fd86d-fd95bee2-e5-e9a | Hz-ID-17454 | MCPA - Mine Clearance Planning Agency | AF/1202/12677/MF0012 | 134 | 69.3556 | 36.6138 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {C59FFB05-FDED-49B3-94A0-730B57A391E9} |  |  |  | Minimal | 16 | CHA | 5 | Yes |  | 2012-10-02 16:30 | No | Complete
North East | Takhar | Bangi | Saqab | {FA992319-A390-49C7-A547-F9C17BE84CFF} | c0a8-0057-12c3b9a6b94-ac2e9bd8-2b702- | MF-HQ-11818 | HT - HALO TRUST | H/6197 | 62400 | 69.2508 | 36.7243 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-03-01 | 2013-04-20 | 1392 | MDC | {FA992319-A390-49C7-A547-F9C17BE84CFF} | Removed from HT plan |  |  | Minimal | 138 | CHA | 4 | Yes |  | 2009-07-01 | No | Complete
North East | Takhar | Bangi | Shah Ali | {433828D6-7290-4148-A370-09019F820B57} | c0a8-0009-13b7e5927dc-996e958e-4ed0-f | Hz-ID-17438 | MCPA - Mine Clearance Planning Agency | AF/1202/12648/MF0015 | 3359 | 69.2253 | 36.7031 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {433828D6-7290-4148-A370-09019F820B57} |  |  |  | Minimal | 31 | SHA | 5 | Yes |  | 2012-11-11 16:30 | No | Complete
North East | Takhar | Bangi | Shah Ali | {433828D6-7290-4148-A370-09019F820B57} | c0a8-0057-12c3b6d8642-f6e34191-bdfc-e | MF-HQ-11827 | HT - HALO TRUST | H/6316 | 47500 | 69.2528 | 36.7 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-03-01 | 2013-05-11 | 1392 | MDC | {433828D6-7290-4148-A370-09019F820B57} |  |  |  | Minimal | 22 | CHA | 5 | Yes |  | 2009-07-10 | No | Complete
North East | Takhar | Bangi | Shah Ali | {433828D6-7290-4148-A370-09019F820B57} | c0a8-0057-12c3b6e2472-7afcff26-c567-b | MF-HQ-11825 | HT - HALO TRUST | H/6315 | 26900 | 69.2502 | 36.6987 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-03-01 | 2013-05-11 | 1392 | MDC | {433828D6-7290-4148-A370-09019F820B57} |  |  |  | Minimal | 22 | CHA | 5 | Yes |  | 2009-07-10 | No | Complete
North East | Takhar | Bangi | Shah Ali | {433828D6-7290-4148-A370-09019F820B57} | c0a8-0057-12c3b6f5629-27cb6de1-d3f1-1 | MF-HQ-11888 | MCPA - Mine Clearance Planning Agency | AF/1202/12648/MF6310 | 3901 | 69.2347 | 36.694 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-03-26 | 2013-04-24 | 1392 | MDC | {433828D6-7290-4148-A370-09019F820B57} |  |  |  | Minimal | 82 | CHA | 5 | Yes |  | 2009-07-07 | No | Complete
North East | Takhar | Bangi | Shah Ali | {433828D6-7290-4148-A370-09019F820B57} | c0a8-0057-12c3ba96d2c-b018c7b7-34a20- | MF-HQ-11866 | MCPA - Mine Clearance Planning Agency | AF/1202/12648/MF6312 | 1763 | 69.2311 | 36.6968 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-04-21 | 2013-04-22 | 1392 | MDC | {433828D6-7290-4148-A370-09019F820B57} |  |  |  | Minimal | 73 | CHA | 5 | Yes |  | 2009-07-07 | No | Complete
North East | Takhar | Bangi | Shah Ali | {433828D6-7290-4148-A370-09019F820B57} | c0a8-0057-12c3bb6e3cf-68b9124e-3c8a3- | MF-HQ-11823 | MCPA - Mine Clearance Planning Agency | AF/1202/12648/MF6314 | 10800 | 69.2395 | 36.6863 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-05-12 | 2013-05-31 | 1392 | MDC | {433828D6-7290-4148-A370-09019F820B57} |  |  |  | Minimal | 3 | CHA | 5 | Yes |  | 2009-07-08 | No | Complete
North East | Takhar | Bangi | Shah Ali | {433828D6-7290-4148-A370-09019F820B57} | c0a8-0057-12c3bb81ad3-c470ba8f-3d3aa- | MF-HQ-11876 | MCPA - Mine Clearance Planning Agency | AF/1202/12648/MF6307 | 23796 | 69.238 | 36.6949 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-03-01 | 2013-03-20 | 1392 | MDC | {433828D6-7290-4148-A370-09019F820B57} |  |  |  | Minimal | 9 | CHA | 5 | Yes |  | 2009-07-05 | No | Complete
North East | Takhar | Bangi | Shah Ali | {433828D6-7290-4148-A370-09019F820B57} | c0a8-0057-12c3bb82261-b890e306-3d3d7- | MF-HQ-11872 | MCPA - Mine Clearance Planning Agency | AF/1202/12648/MF6306 | 10518 | 69.247 | 36.6944 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-03-01 | 2013-03-25 | 1392 | MDC | {433828D6-7290-4148-A370-09019F820B57} |  |  |  | Minimal | 3 | CHA | 5 | Yes |  | 2009-07-05 | No | Complete
North East | Takhar | Chal | Badam Darrah | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} | c0a8-0009-13f2c91c88b-301b1b7d-5557-9 | Hz-ID-17969 | HT - HALO TRUST | H/8484 | 47720 | 69.501 | 36.4722 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2013-07-01 | 2013-09-23 | 1392 | HT | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} |  |  |  | Minimal | 18 | CHA | 5 |  |  | 2013-05-20 16:30 | No | Complete
North East | Takhar | Chal | Badam Darrah | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} | c0a8-0009-13f2c9a4ffb-b456cebb-55ff-b | Hz-ID-17968 | HT - HALO TRUST | H/8485 | 12540 | 69.501 | 36.4722 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2013-07-01 | 2013-08-23 | 1392 | HT | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} |  |  |  | Minimal | 18 | CHA | 5 |  |  | 2013-05-22 16:30 | No | Complete
North East | Takhar | Chal | Badam Darrah | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} | c0a8-0057-12c3b890b33-ed2faee3-1fd7d- | MF-HQ-13838 | HT - HALO TRUST | H/6414 | 29600 | 69.5027 | 36.4725 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2010-06-01 | 2013-07-23 | 1392 | HT | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} | Based on HALO Trust and MDC agreement, the hazard excluded from MDC plan and allocated to HALO Trust |  |  | Minimal | 21 | CHA | 5 |  |  | 2009-12-15 | No | Complete
North East | Takhar | Chal | Badam Darrah | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} | c0a8-0057-12c3b994fc0-b966bdb3-2ab05- | MF-HT-825 | HT - HALO TRUST | H/3944 | 32000 | 69.5109 | 36.4659 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2013-05-18 | 2013-06-06 | 1392 | HT | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} |  |  |  | Minimal | 6 | CHA | 5 |  |  | 2009-11-02 | No | Complete
North East | Takhar | Chal | Badam Darrah | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} | c0a8-0057-12c3b995452-34983d55-2ab38- | MF-HT-246 | HT - HALO TRUST | H/3926 | 51600 | 69.5134 | 36.4658 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2013-05-19 | 2013-06-22 | 1392 | HT | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} |  |  |  | Minimal | 6 | CHA | 5 |  |  | 2009-12-15 | No | Complete
North East | Takhar | Chal | Badam Darrah | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} | c0a8-0057-12c3b995683-26f9376d-2ab51- | MF-HT-383 | HT - HALO TRUST | H/2906 | 46000 | 69.5118 | 36.4636 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2013-06-01 | 2013-10-23 | 1392 | HT | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} |  |  |  | Minimal | 6 | CHA | 5 |  |  | 2009-12-15 | No | Complete
North East | Takhar | Chal | Badam Darrah | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} | c0a8-0057-12c3b995886-a83e32-2ab68-c7 | MF-HT-640 | HT - HALO TRUST | H/3943 | 30000 | 69.5097 | 36.4642 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2013-05-01 | 2013-06-02 | 1392 | HT | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} |  |  |  | Minimal | 6 | CHA | 5 |  |  | 2009-12-15 | No | Complete
North East | Takhar | Chal | Badam Darrah | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} | c0a8-008e-131944da21b-abb17fb5-fcf-76 | MF-HQ-13836 | HT - HALO TRUST | H/6415 | 49800 | 69.4989 | 36.4732 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2013-04-01 | 2013-08-13 | 1392 | HT | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} |  |  |  | Minimal | 21 | CHA | 5 |  |  | 2009-12-15 | No | Complete
North East | Takhar | Chal | Badam Darrah | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} | c0a8-008e-131944e2f4c-2905b3a5-1029-4 | MF-HQ-13820 | HT - HALO TRUST | H/6412 | 32100 | 69.5097 | 36.4642 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2013-04-19 | 2013-06-08 | 1392 | HT | {210F3B0F-72F5-41FD-9606-25CD34BAD0B4} |  |  |  | Minimal | 6 | CHA | 5 |  |  | 2009-12-15 | No | Complete
North East | Takhar | Chal | Hazara Say | {526187EB-678B-4145-B3D3-BB9E98D85A7F} | c0a8-0009-13e2b6034dd-cbea5aa0-561-e8 | MF-HQ-13846 | HT - HALO TRUST | H/6469 | 63050 | 69.5872 | 36.5911 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/C | Takhar Demining Project-02/C | GAGP | Yes | 2014-03-18 | 2014-05-18 | 1392-1393 | HT | {526187EB-678B-4145-B3D3-BB9E98D85A7F} |  |  |  | Minimal | 15 | CHA | 5 |  |  | 2009-12-15 | No | Complete
North East | Takhar | Chal | Hazara Say | {526187EB-678B-4145-B3D3-BB9E98D85A7F} | c0a8-0057-12c3b85a059-bc4a0663-1d74f- | MF-HQ-13849 | HT - HALO TRUST | H/6468 | 47230 | 69.5951 | 36.5843 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/C | Takhar Demining Project-02/C | GAGP | Yes | 2014-01-15 | 2014-05-23 | 1392-1393 | HT | {526187EB-678B-4145-B3D3-BB9E98D85A7F} |  |  |  | Minimal | 56 | CHA | 4 |  |  | 2009-12-15 | No | Complete
North East | Takhar | Chal | Hazara Say | {526187EB-678B-4145-B3D3-BB9E98D85A7F} | c0a8-0057-12c3b85a25c-ef6aa5a2-1d765- | MF-HT-250 | HT - HALO TRUST | H/3907 | 55680 | 69.5952 | 36.585 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/C | Takhar Demining Project-02/C | GAGP | Yes | 2014-02-16 | 2014-05-21 | 1392-1393 | HT | {526187EB-678B-4145-B3D3-BB9E98D85A7F} |  |  |  | Minimal | 14 | CHA | 5 |  |  | 2009-12-15 | No | Complete
North East | Takhar | Chal | Hazara Say | {526187EB-678B-4145-B3D3-BB9E98D85A7F} | c0a8-0057-12c3b85a8a2-86aaaf99-1d7a1- | MF-HT-264 | HT - HALO TRUST | H/2907 | 52870 | 69.5952 | 36.585 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/C | Takhar Demining Project-02/C | GAGP | Yes | 2014-03-05 |  | 1392-1393 | HT | {526187EB-678B-4145-B3D3-BB9E98D85A7F} |  |  |  | Minimal | 14 | CHA | 4 |  |  | 2009-12-15 | No | Complete
North East | Takhar | Chal | Jar Tiba | {4AC6DAC4-E939-4C3E-818A-2C1F695A3BA4} | c0a8-0057-12c3b861567-cff24652-1dc31- | MF-HT-260 | HT - HALO TRUST | H/2910 | 22032 | 69.5071 | 36.5593 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/C | Takhar Demining Project-02/C | GAGP | Yes | 2014-05-14 | 2014-06-21 | 1392-1393 | HT | {4AC6DAC4-E939-4C3E-818A-2C1F695A3BA4} |  |  |  | Minimal | 1 | CHA | 5 |  |  | 2007-09-30 | No | Complete
North East | Takhar | Chal | Kham-i-Kalan | {D1AA142F-7501-42F1-BABF-FF5DAB80F2D0} | c0a8-0009-13fdc6d04d5-bc5cd86b-26d1-e | Hz-ID-18036 | HT - HALO TRUST | H/8554 | 34975 | 69.4845 | 36.4492 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2013-12-01 | 2014-01-23 | 1392 | HT | {D1AA142F-7501-42F1-BABF-FF5DAB80F2D0} |  |  |  | Minimal | 4 | CHA | 5 |  |  | 2013-06-15 16:30 | No | Complete
North East | Takhar | Chal | Kham-i-Kalan | {D1AA142F-7501-42F1-BABF-FF5DAB80F2D0} | c0a8-0057-12c3b700a0a-594a8207-dc9d-c | MF-HQ-14813 | MCPA - Mine Clearance Planning Agency | AF/1204/12636/MF0006 | 53960 | 69.4849 | 36.4385 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/C | Takhar Demining Project-02/C | GAGP | Yes | 2014-06-01 |  | 1392-1393 | HT | {D1AA142F-7501-42F1-BABF-FF5DAB80F2D0} |  |  |  | Minimal | 25 | CHA | 4 |  |  | 2010-04-25 | No | Complete
North East | Takhar | Chal | Maan Dara | {7EA04FEE-C064-48FA-9964-B7D548315215} | c0a8-0057-12c3b70c108-c7d20074-e546-e | MF-HT-1147 | HT - HALO TRUST | H/2912 | 91850 | 69.5121 | 36.4422 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2013-06-03 |  | 1392 | HT | {7EA04FEE-C064-48FA-9964-B7D548315215} |  |  |  | Minimal | 120 | CHA | 5 |  |  | 2007-09-01 | No | Complete
North East | Takhar | Chal | Pil Kha | {A2853DAE-5078-4F02-A0D6-872391303A1C} | c0a8-0009-13fdc6d71c9-363910e-2707-90 | Hz-ID-18035 | HT - HALO TRUST | H/8497 | 290 | 69.4614 | 36.4996 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {A2853DAE-5078-4F02-A0D6-872391303A1C} |  | Medium | Agriculture Blocked | Minimal | 22 | CHA | 3 |  |  | 2013-06-05 16:30 | No | Planned
North East | Takhar | Chal | Pil Kha | {A2853DAE-5078-4F02-A0D6-872391303A1C} | c0a8-0009-13fdc6dfd65-8ccac70e-2725-a | Hz-ID-18034 | HT - HALO TRUST | H/8496 | 655 | 69.4636 | 36.5009 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {A2853DAE-5078-4F02-A0D6-872391303A1C} |  | Medium | Agriculture Blocked | Minimal | 22 | CHA | 3 |  |  | 2013-06-06 16:30 | No | Planned
North East | Takhar | Chal | Sag Khurda | {BC63AFB5-2705-4A9D-99E0-93BE67B4ADB3} | c0a8-0057-12c3bb37f4b-8ae151cd-3a9a8- | MF-HT-388 | HT - HALO TRUST | H/2916 | 6800 | 69.6009 | 36.502 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {BC63AFB5-2705-4A9D-99E0-93BE67B4ADB3} |  | Low | Critical Infrastracture | Minimal | 35 | CHA | 5 |  |  | 2007-09-01 | No | Planned
North East | Takhar | Chal | Sangoj | {482F46A7-C4D1-4D49-A354-612E0DAEBEC9} | c0a8-0057-12c3ba481d1-64360600-31adc- | MF-HT-254 | HT - HALO TRUST | H/3901 | 10153 | 69.555 | 36.5043 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/C | Takhar Demining Project-02/C | GAGP | Yes | 2014-05-07 | 2014-06-05 | 1392-1393 | HT | {482F46A7-C4D1-4D49-A354-612E0DAEBEC9} |  |  |  | Minimal | 20 | CHA | 5 |  |  | 2007-09-30 | No | Complete
North East | Takhar | Farkhar | Chashmai Garmak | {38BABBEE-D265-4D4D-B29F-EE247BE24406} | c0a8-0057-12c3b6b0a84-f21866d2-9f95-6 | MF-HQ-11737 | HT - HALO TRUST | H/6063 | 35175 | 69.8016 | 36.5661 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {38BABBEE-D265-4D4D-B29F-EE247BE24406} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2009-06-10 | No | Open
North East | Takhar | Farkhar | Chashmai Garmak | {38BABBEE-D265-4D4D-B29F-EE247BE24406} | c0a8-00c9-12fde3f6e1b-41c1bb72-c8-b54 | MF-HQ-11754 | HT - HALO TRUST | H/6062 | 65210 | 69.812 | 36.5762 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {38BABBEE-D265-4D4D-B29F-EE247BE24406} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2009-06-09 | No | Open
North East | Takhar | Farkhar | Chashmai Garmak | {38BABBEE-D265-4D4D-B29F-EE247BE24406} | c0a8-00c9-12fde409fb3-ba4d8deb-dd-262 | MF-HQ-11752 | HT - HALO TRUST | H/6061 | 63100 | 69.8112 | 36.5752 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {38BABBEE-D265-4D4D-B29F-EE247BE24406} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2009-06-08 | No | Open
North East | Takhar | Farkhar | Chashmai Garmak | {38BABBEE-D265-4D4D-B29F-EE247BE24406} | c0a8-00c9-12fde41dea3-eec62ece-f2-c3b | MF-HQ-11750 | HT - HALO TRUST | H/6060 | 59379 | 69.8112 | 36.5752 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {38BABBEE-D265-4D4D-B29F-EE247BE24406} |  | Low | Agriculture Blocked | Low | 7 | CHA | 5 |  |  | 2009-06-07 | No | Open
North East | Takhar | Farkhar | Chashmai Garmak | {38BABBEE-D265-4D4D-B29F-EE247BE24406} | c0a8-00c9-12fde482fa2-8053f2b4-106-3c | MF-HQ-11747 | HT - HALO TRUST | H/2917 | 68400 | 69.8102 | 36.5723 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {38BABBEE-D265-4D4D-B29F-EE247BE24406} |  | Low | Agriculture Blocked | Low | 3 | CHA | 5 |  |  | 2009-06-11 | No | Open
North East | Takhar | Farkhar | Chashmai Garmak | {38BABBEE-D265-4D4D-B29F-EE247BE24406} | c0a8-00c9-12fde499d30-dfd9bc92-11b-9c | MF-HQ-11756 | HT - HALO TRUST | H/6059 | 49140 | 69.8077 | 36.5839 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {38BABBEE-D265-4D4D-B29F-EE247BE24406} |  | Low | Agriculture Blocked | Low | 5 | CHA | 5 |  |  | 2009-06-06 | No | Open
North East | Takhar | Farkhar | Farkhar | {2214612C-C47F-4D85-91EB-2846675C0B6C} | c0a8-0057-12c3b8b0747-f495328a-21330- | MF-HQ-13681 | MCPA - Mine Clearance Planning Agency | AF/1206/12848/MF0028 | 12000 | 69.8584 | 36.5817 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-034 | Takhar Demining Project-05 | DOS | Yes | 2013-05-08 | 2013-06-14 | 1392-1393 | MDC | {2214612C-C47F-4D85-91EB-2846675C0B6C} |  |  |  | Low | 409 | CHA | 2 |  |  | 2009-11-10 | No | Planned
North East | Takhar | Farkhar | Kashan | {C8D7C2B4-56BA-4971-B666-893F6952D829} | c0a8-0057-12c3b6a6a03-3f160978-980f-b | MF-HQ-15211 | HT - HALO TRUST | H/7340 | 19300 | 69.9518 | 36.6126 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {C8D7C2B4-56BA-4971-B666-893F6952D829} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2010-09-24 | No | Open
North East | Takhar | Farkhar | Kashan | {C8D7C2B4-56BA-4971-B666-893F6952D829} | c0a8-0057-12c3b6d1567-ecbfb0a7-b88b-6 | MF-HQ-15209 | HT - HALO TRUST | H/7338 | 42400 | 69.9597 | 36.6023 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {C8D7C2B4-56BA-4971-B666-893F6952D829} |  | Low | Agriculture Blocked | Low | 14 | CHA | 5 |  |  | 2010-09-23 | No | Open
North East | Takhar | Farkhar | Khas Deh | {495229C3-9EFE-4773-8222-A6284F02A327} | c0a8-0057-12c3b6a2c78-edddfe0c-9527-d | MF-HQ-13553 | HT - HALO TRUST | H/6444 | 42570 | 69.7915 | 36.4995 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {495229C3-9EFE-4773-8222-A6284F02A327} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2009-10-04 | No | Open
North East | Takhar | Farkhar | Khas Deh | {495229C3-9EFE-4773-8222-A6284F02A327} | c0a8-0057-12c3b6f364a-973f6def-d27c-e | MF-HQ-13503 | HT - HALO TRUST | H/6445 | 40240 | 69.7915 | 36.4995 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {495229C3-9EFE-4773-8222-A6284F02A327} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2009-10-05 | No | Open
North East | Takhar | Farkhar | Khas Deh | {495229C3-9EFE-4773-8222-A6284F02A327} | c0a8-0057-12c3b75aee2-d25e5815-12068- | MF-HQ-15217 | HT - HALO TRUST | H/7361 | 4400 | 69.7959 | 36.48 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {495229C3-9EFE-4773-8222-A6284F02A327} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-09-25 | No | Open
North East | Takhar | Farkhar | Khas Deh | {495229C3-9EFE-4773-8222-A6284F02A327} | c0a8-0057-12c3b77fa9b-b10f1531-13b4f- | MF-HQ-13505 | HT - HALO TRUST | H/6446 | 9560 | 69.7882 | 36.4969 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {495229C3-9EFE-4773-8222-A6284F02A327} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2009-10-06 | No | Open
North East | Takhar | Farkhar | Khawaki | {85F7B8F1-E951-4FEA-A0A0-045EF0A0A83C} | c0a8-0057-12cba73e5b3-a9e8618d-6b8-a7 | MF-HQ-11735 | HT - HALO TRUST | H/2922 | 50800 | 69.8255 | 36.5373 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {85F7B8F1-E951-4FEA-A0A0-045EF0A0A83C} |  | Low | Agriculture Blocked | Low | 13 | CHA | 5 |  |  | 2009-06-17 | No | Open
North East | Takhar | Farkhar | Khawaki | {85F7B8F1-E951-4FEA-A0A0-045EF0A0A83C} | c0a8-0057-12cbb252e5d-5ec3f3dd-128f-5 | MF-HQ-11759 | HT - HALO TRUST | H/6068 | 40400 | 69.8415 | 36.5498 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {85F7B8F1-E951-4FEA-A0A0-045EF0A0A83C} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2009-06-16 | No | Open
North East | Takhar | Farkhar | Khawaki | {85F7B8F1-E951-4FEA-A0A0-045EF0A0A83C} | c0a8-0057-12cbb2a5b1a-748ae05a-12ed-4 | MF-HQ-11745 | HT - HALO TRUST | H/6065 | 72800 | 69.8042 | 36.5364 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {85F7B8F1-E951-4FEA-A0A0-045EF0A0A83C} |  | Low | Agriculture Blocked | Low | 1 | CHA | 5 |  |  | 2009-06-13 | No | Open
North East | Takhar | Farkhar | Khawaki | {85F7B8F1-E951-4FEA-A0A0-045EF0A0A83C} | c0a8-0057-12cbb2e63c7-5150912d-1338-3 | MF-HQ-11743 | HT - HALO TRUST | H/6064 | 65600 | 69.8174 | 36.5366 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {85F7B8F1-E951-4FEA-A0A0-045EF0A0A83C} |  | Low | Agriculture Blocked | Low | 9 | CHA | 5 |  |  | 2009-06-12 | No | Open
North East | Takhar | Farkhar | Khurmab(1) | {83F2D014-033D-45D2-A5B7-01B60EEC1A99} | c0a8-008e-1328f989e23-ae490219-1b75-e | MF-15356 | HT - HALO TRUST | H/7364 | 22200 | 70.0528 | 36.5804 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {83F2D014-033D-45D2-A5B7-01B60EEC1A99} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-10-04 16:30 | No | Open
North East | Takhar | Farkhar | Khurmab(1) | {83F2D014-033D-45D2-A5B7-01B60EEC1A99} | c0a8-008e-1328f9acb43-af982adf-1c83-e | MF-15358 | HT - HALO TRUST | H/7362 | 29400 | 70.0535 | 36.5537 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {83F2D014-033D-45D2-A5B7-01B60EEC1A99} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-10-02 16:30 | No | Open
North East | Takhar | Farkhar | Khurmab(1) | {83F2D014-033D-45D2-A5B7-01B60EEC1A99} | c0a8-008e-1328fb5055c-49ed33c9-23c5-a | MF-15359 | HT - HALO TRUST | H/7363 | 32400 | 70.0278 | 36.5461 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {83F2D014-033D-45D2-A5B7-01B60EEC1A99} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2010-10-02 16:30 | No | Open
North East | Takhar | Farkhar | Khurmab(2) | {245D65B2-514C-4DB4-A0E4-6C4BDD0F3A8B} | c0a8-0057-12c3b7b81db-cf80563d-163fe- | MF-HQ-15210 | HT - HALO TRUST | H/7339 | 26500 | 69.9743 | 36.6097 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {245D65B2-514C-4DB4-A0E4-6C4BDD0F3A8B} |  | Low | Critical Infrastracture | Low | 4 | CHA | 5 |  |  | 2010-09-23 | No | Open
North East | Takhar | Farkhar | Kishaktan | {295DCDD1-EEC2-4319-8811-A30E23C12388} | c0a8-0009-13ec19de1f1-cf078c87-2173-4 | Hz-ID-17920 | HT - HALO TRUST | H/8467 | 15120 | 69.7346 | 36.6254 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes |  |  | 1393 | MDC | {295DCDD1-EEC2-4319-8811-A30E23C12388} |  | High with Victim | High with Victims | Low | 572 | CHA | 1 |  |  | 2013-04-10 16:30 | No | Planned
North East | Takhar | Farkhar | Kishaktan | {295DCDD1-EEC2-4319-8811-A30E23C12388} | c0a8-0057-12c3bb213c1-ed8ff894-39c3f- | MF-HQ-11882 | HT - HALO TRUST | H/5896 | 31328 | 69.7381 | 36.6297 | Closed | AP Only | AP Only | MineField | 1391/1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2012-04-01 | 2013-06-23 | 1392 | HT | {295DCDD1-EEC2-4319-8811-A30E23C12388} |  |  |  | Low | 581 | CHA | 5 |  |  | 2008-12-01 | No | Complete
North East | Takhar | Farkhar | Kishaktan | {295DCDD1-EEC2-4319-8811-A30E23C12388} | c0a8-00c9-12fde4c4e9e-797305a7-14b-65 | MF-NE-973 | HT - HALO TRUST | H/5891 | 25000 | 69.7363 | 36.6313 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes |  |  | 1393 | MDC | {295DCDD1-EEC2-4319-8811-A30E23C12388} |  | High with Victim | High with Victims | Low | 581 | CHA | 5 |  |  | 2010-09-02 | No | Planned
North East | Takhar | Farkhar | Sang-i-Atas | {D082D1D5-F285-40BF-8773-6BFA50B0196E} | c0a8-0057-12c3b6a43bf-16b5f34f-963e-6 | MF-HQ-13508 | HT - HALO TRUST | H/6448 | 64830 | 69.7869 | 36.5141 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {D082D1D5-F285-40BF-8773-6BFA50B0196E} |  | Low | Agriculture Blocked | Low | 36 | CHA | 5 |  |  | 2009-10-08 | No | Planned
North East | Takhar | Farkhar | Sang-i-Atas | {D082D1D5-F285-40BF-8773-6BFA50B0196E} | c0a8-0057-12c3b6ed335-758cc3c8-cde0-7 | MF-HQ-13510 | HT - HALO TRUST | H/6450 | 39700 | 69.7827 | 36.5188 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {D082D1D5-F285-40BF-8773-6BFA50B0196E} | , | Medium | Critical Infrastracture | Low | 16 | CHA | 3 |  |  | 2009-10-05 | No | Open
North East | Takhar | Farkhar | Sang-i-Atas | {D082D1D5-F285-40BF-8773-6BFA50B0196E} | c0a8-0057-12c3b7608f2-93d1ffb3-12495- | MF-HQ-13509 | HT - HALO TRUST | H/6449 | 54910 | 69.7888 | 36.5149 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {D082D1D5-F285-40BF-8773-6BFA50B0196E} |  | Low | Agriculture Blocked | Low | 36 | CHA | 5 |  |  | 2009-10-09 | No | Planned
North East | Takhar | Farkhar | Sang-i-Atas | {D082D1D5-F285-40BF-8773-6BFA50B0196E} | c0a8-0057-12c3b77f82b-58b635b-13b35-5 | MF-HQ-13507 | HT - HALO TRUST | H/6447 | 70130 | 69.7869 | 36.5141 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {D082D1D5-F285-40BF-8773-6BFA50B0196E} |  | Low | Agriculture Blocked | Low | 36 | CHA | 5 |  |  | 2009-10-07 | No | Planned
North East | Takhar | Farkhar | Sang-i-Atas | {D082D1D5-F285-40BF-8773-6BFA50B0196E} | c0a8-0057-12c3ba9dfab-6c96b5c4-34e61- | MF-HQ-11721 | HT - HALO TRUST | H/6066 | 38100 | 69.8281 | 36.5356 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {D082D1D5-F285-40BF-8773-6BFA50B0196E} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2009-06-14 | No | Planned
North East | Takhar | Farkhar | Sang-i-Atas | {D082D1D5-F285-40BF-8773-6BFA50B0196E} | c0a8-00c9-12fde4da330-1cd00aca-167-1f | MF-HQ-11766 | HT - HALO TRUST | H/6067 | 28870 | 69.8273 | 36.5375 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {D082D1D5-F285-40BF-8773-6BFA50B0196E} |  | Low | Agriculture Blocked | Low | 13 | CHA | 5 |  |  | 2009-06-15 | No | Planned
North East | Takhar | Farkhar | Sar-i-Kham | {8A9C5BD2-4482-46F2-A933-F6BD6759AC23} | c0a8-008e-1328f97bdb7-9868518c-1b1e-5 | MF-15355 | HT - HALO TRUST | H/7365 | 20200 | 69.9685 | 36.635 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {8A9C5BD2-4482-46F2-A933-F6BD6759AC23} |  | Low | Agriculture Blocked | Low | 4 | CHA | 5 |  |  | 2010-10-05 16:30 | No | Planned
North East | Takhar | Hazar Sumuch | Gharab Darrah(1) | {E85BBDB8-2BB3-4CE2-96DA-92C4116F28ED} | c0a8-0057-12c3b6ede5c-90ab9e3d-ce54-8 | MF-HQ-14961 | HT - HALO TRUST | H/6683 | 25000 | 69.6155 | 36.9471 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-034 | Takhar Demining Project-05 | DOS | Yes | 2014-04-30 | 2014-05-13 | 1392-1393 | MDC | {E85BBDB8-2BB3-4CE2-96DA-92C4116F28ED} |  |  |  | Minimal | 95 | CHA | 3 | Yes |  | 2010-08-09 | No | Planned
North East | Takhar | Hazar Sumuch | Gul Mesh | {96B08B41-3DC7-4F28-A8C2-6CA217690A3D} | c0a8-008e-1328f90b7b6-f270d8a6-19de-9 | MF-15854 | HT - HALO TRUST | H/7458 | 6850 | 69.5124 | 36.9443 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {96B08B41-3DC7-4F28-A8C2-6CA217690A3D} |  |  |  | Minimal | 9 | CHA | 5 | Yes |  | 2011-01-06 16:30 | No | Complete
North East | Takhar | Hazar Sumuch | Hazar samooch | {5F2D6825-1509-42B7-9FA6-DA20E878186B} | c0a8-0057-12c3b697c9b-d4a36592-8cea-4 | MF-HQ-13821 | HT - HALO TRUST | H/6419 | 10800 | 69.592 | 36.8727 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {5F2D6825-1509-42B7-9FA6-DA20E878186B} |  |  |  | Minimal | 3 | CHA | 5 | Yes |  | 2009-12-15 | No | Complete
North East | Takhar | Hazar Sumuch | Hazar samooch | {5F2D6825-1509-42B7-9FA6-DA20E878186B} | c0a8-0057-12c3b69a36c-8f9f2b6d-8ec1-b | MF-HQ-11931 | HT - HALO TRUST | H/6358 | 21370 | 69.5702 | 36.8874 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {5F2D6825-1509-42B7-9FA6-DA20E878186B} |  |  |  | Minimal | 2 | CHA | 5 | Yes |  | 2009-07-17 | No | Complete
North East | Takhar | Hazar Sumuch | Hazar samooch | {5F2D6825-1509-42B7-9FA6-DA20E878186B} | c0a8-0057-12c3b6c3845-57286094-ae07-c | MF-HQ-11860 | HT - HALO TRUST | H/6357 | 31100 | 69.571 | 36.8854 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {5F2D6825-1509-42B7-9FA6-DA20E878186B} |  |  |  | Minimal | 2 | CHA | 5 | Yes |  | 2009-07-16 | No | Complete
North East | Takhar | Hazar Sumuch | Hazar samooch | {5F2D6825-1509-42B7-9FA6-DA20E878186B} | c0a8-0057-12c3b6f585a-304612c1-d40e-b | MF-HQ-11948 | HT - HALO TRUST | H/6352 | 9610 | 69.603 | 36.8727 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {5F2D6825-1509-42B7-9FA6-DA20E878186B} |  |  |  | Minimal | 3 | CHA | 5 | Yes |  | 2009-07-10 | No | Complete
North East | Takhar | Hazar Sumuch | Hazar samooch | {5F2D6825-1509-42B7-9FA6-DA20E878186B} | c0a8-008e-1328fa14fe6-9bd4a80-1ff0-16 | MF-16058 | HT - HALO TRUST | H/7467 | 4600 | 69.5642 | 36.8514 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {5F2D6825-1509-42B7-9FA6-DA20E878186B} |  |  |  | Minimal | 10 | CHA | 5 | Yes |  | 2011-05-04 16:30 | No | Complete
North East | Takhar | Hazar Sumuch | Hazar samooch | {5F2D6825-1509-42B7-9FA6-DA20E878186B} | c0a8-008e-132908b5005-cbe77dc0-ad-7d8 | MF-16060 | HT - HALO TRUST | H/7466 | 17482 | 69.5636 | 36.8539 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {5F2D6825-1509-42B7-9FA6-DA20E878186B} |  |  |  | Minimal | 22 | CHA | 5 | Yes |  | 2011-05-03 16:30 | No | Complete
North East | Takhar | Hazar Sumuch | Petaw | {21D334B1-8ED5-4695-8D6E-3E3A4DD0C04A} | c0a8-003c-1306379318d-fe9eb656-17-89a | BF-HQ-15020 | HT - HALO TRUST | B/2748 | 15.7 | 69.5164 | 36.889 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-034 | Takhar Demining Project-05 | DOS | Yes |  |  | 1392-1393 | MDC | {21D334B1-8ED5-4695-8D6E-3E3A4DD0C04A} |  | Medium | Agriculture Blocked | Minimal | 0 | CHA | 5 |  |  | 2010-09-14 | No | Planned
North East | Takhar | Hazar Sumuch | Qal'a-i-Mamay | {9334DE19-7674-4E5A-85DF-D97912DE4978} | c0a8-0057-12c3b76dce1-6950b3a0-12e67- | MF-HQ-15027 | HT - HALO TRUST | H/6681 | 5720 | 69.5995 | 36.9646 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-034 | Takhar Demining Project-05 | DOS | Yes |  |  | 1392-1393 | MDC | {9334DE19-7674-4E5A-85DF-D97912DE4978} |  |  |  | Minimal | 11 | CHA | 5 | Yes |  | 2010-08-05 | No | Planned
North East | Takhar | Hazar Sumuch | Qotan Bulaq | {5FE5C004-5AA3-4065-93EB-D1E999A4E44C} | c0a8-008e-1328f90e876-5f8a6a39-19fd-1 | MF-15855 | HT - HALO TRUST | H/7459 | 5800 | 69.5146 | 36.952 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {5FE5C004-5AA3-4065-93EB-D1E999A4E44C} |  |  |  | Minimal | 5 | CHA | 5 | Yes |  | 2011-01-07 16:30 | No | Complete
North East | Takhar | Hazar Sumuch | Qotan Bulaq | {5FE5C004-5AA3-4065-93EB-D1E999A4E44C} | c0a8-00f6-1351859e461-910e122e-307-56 | MF-16531 | HT - HALO TRUST | H/7490 | 7014 | 69.5518 | 36.9137 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-034 | Takhar Demining Project-05 | DOS | Yes | 2014-05-14 | 2014-05-17 | 1392-1393 | MDC | {5FE5C004-5AA3-4065-93EB-D1E999A4E44C} |  |  |  | Minimal | 10 | CHA | 4 | Yes |  | 2011-07-15 16:30 | No | Planned
North East | Takhar | Hazar Sumuch | Qotan Bulaq | {5FE5C004-5AA3-4065-93EB-D1E999A4E44C} | c0a8-00f6-135185e9a26-3c48b7a4-335-58 | MF-16532 | HT - HALO TRUST | H/7440 | 28380 | 69.5536 | 36.9161 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-034 | Takhar Demining Project-05 | DOS | Yes | 2014-05-19 | 2014-06-04 | 1392-1393 | MDC | {5FE5C004-5AA3-4065-93EB-D1E999A4E44C} |  |  |  | Minimal | 21 | CHA | 4 | Yes |  | 2011-07-16 16:30 | No | Planned
North East | Takhar | Hazar Sumuch | Qotum Bolaq | {F6399874-D5F4-4A15-9751-338D9EE778BB} | c0a8-0057-12c3ba56e3f-bfe58fcd-323d0- | MF-NE-658 | HT - HALO TRUST | H/3962 | 21900 | 69.5273 | 36.9151 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {F6399874-D5F4-4A15-9751-338D9EE778BB} | Removed from HT 1390 plan |  |  | Minimal | 34 | CHA | 5 | Yes |  | 2008-09-01 | No | Complete
North East | Takhar | Hazar Sumuch | Qotum Bolaq | {F6399874-D5F4-4A15-9751-338D9EE778BB} | c0a8-008e-1306d67fa71-d6f911a5-3b3-16 | MF-NE-623 | HT - HALO TRUST | H/2958 | 2600 | 69.5554 | 36.9101 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-034 | Takhar Demining Project-05 | DOS | Yes | 2014-06-05 | 2014-06-07 | 1392-1393 | MDC | {F6399874-D5F4-4A15-9751-338D9EE778BB} |  |  |  | Minimal | 10 | CHA | 3 | Yes |  | 2007-09-01 | No | Planned
North East | Takhar | Hazar Sumuch | Shor Quduq | {643D04BF-F57C-43AA-8E1F-75677B1E74B5} | c0a8-0057-12c3ba577c1-829493a5-32407- | MF-HQ-14963 | HT - HALO TRUST | H/6685 | 2850 | 69.5257 | 36.9147 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {643D04BF-F57C-43AA-8E1F-75677B1E74B5} |  |  |  | Minimal | 34 | CHA | 5 | Yes |  | 2010-08-14 | No | Complete
North East | Takhar | Hazar Sumuch | Shor Quduq | {643D04BF-F57C-43AA-8E1F-75677B1E74B5} | c0a8-0057-12c3ba57a02-b0259903-3241e- | MF-HQ-14999 | HT - HALO TRUST | H/7331 | 1500 | 69.5302 | 36.913 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {643D04BF-F57C-43AA-8E1F-75677B1E74B5} | , |  |  | Minimal | 34 | CHA | 5 | Yes |  | 2010-08-15 | No | Complete
North East | Takhar | Hazar Sumuch | Shor Quduq | {643D04BF-F57C-43AA-8E1F-75677B1E74B5} | c0a8-0057-12c3ba57cdf-6e543d49-32434- | MF-HQ-15000 | HT - HALO TRUST | H/7332 | 3200 | 69.5267 | 36.9152 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {643D04BF-F57C-43AA-8E1F-75677B1E74B5} |  |  |  | Minimal | 34 | CHA | 5 | Yes |  | 2010-08-15 | No | Complete
North East | Takhar | Ishkamish | Chagha | {23C59A3E-E31E-4F9C-B91D-B2006F6E254E} | c0a8-0009-141066df532-269137e3-7548-e | Hz-ID-18120 | MCPA - Mine Clearance Planning Agency | AF/1203/12604/SpotERW0002 | 72 | 69.2661 | 36.3563 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {23C59A3E-E31E-4F9C-B91D-B2006F6E254E} |  | High | Critical Infrastracture | Low | 147 | CHA | 3 |  |  | 2013-07-25 16:30 | No | Open
North East | Takhar | Ishkamish | Shera Chi | {3EB840BB-BAA9-4BE8-96B4-561505CF81DE} | c0a8-0009-140d8594460-c0f6ac5c-155a-d | Hz-ID-18117 | MCPA - Mine Clearance Planning Agency | AF/1203/12618/SpotERW0001 | 9 | 69.3103 | 36.4443 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {3EB840BB-BAA9-4BE8-96B4-561505CF81DE} |  | Medium | Agriculture Blocked | Low | 41 | CHA | 3 |  |  | 2013-07-21 16:30 | No | Open
North East | Takhar | Kalfagan | Aq Bulaq | {60331221-602D-4932-A9AD-0354F6F546B4} | c0a8-0009-13fdc6aa5d7-602406b1-2626-a | Hz-ID-18042 | HT - HALO TRUST | H/8559 | 9000 | 69.8676 | 36.7723 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {60331221-602D-4932-A9AD-0354F6F546B4} |  |  |  | Minimal | 3 | CHA | 5 |  |  | 2013-06-08 16:30 | Yes | Complete
North East | Takhar | Kalfagan | Kalafgan | {B8D668BA-51C6-44E5-88EC-3420E6EEB0E5} | c0a8-0009-13f2ca1afdf-f009ce55-5672-d | Hz-ID-17967 | HT - HALO TRUST | H/8489 | 3230 | 69.9485 | 36.7764 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-11 | 2013-07-11 | 1392 | MDC | {B8D668BA-51C6-44E5-88EC-3420E6EEB0E5} |  |  |  | Minimal | 201 | CHA | 2 |  |  | 2013-05-19 16:30 | No | Complete
North East | Takhar | Kalfagan | Kalafgan | {B8D668BA-51C6-44E5-88EC-3420E6EEB0E5} | c0a8-0009-13f2ca6333d-19792825-56b9-6 | Hz-ID-17966 | HT - HALO TRUST | H/8490 | 930 | 69.9485 | 36.7764 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-30 | 2013-07-30 | 1392 | MDC | {B8D668BA-51C6-44E5-88EC-3420E6EEB0E5} |  |  |  | Minimal | 201 | CHA | 2 |  |  | 2013-05-20 16:30 | No | Complete
North East | Takhar | Kalfagan | Kalafgan (3) | {E2274031-B222-413B-8266-9D23BA888269} | c0a8-0009-13bea637025-8281f1b-355-18d | Hz-ID-17520 | HT - HALO TRUST | H/8442 | 255 | 69.9619 | 36.7821 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-10 | 2013-07-10 | 1392 | MDC | {E2274031-B222-413B-8266-9D23BA888269} |  |  |  | Minimal | 300 | CHA | 3 |  |  | 2012-11-16 16:30 | No | Complete
North East | Takhar | Kalfagan | Kalafgan (3) | {E2274031-B222-413B-8266-9D23BA888269} | c0a8-0009-13bea6e3950-507fae2d-3dd-97 | Hz-ID-17521 | HT - HALO TRUST | H/8443 | 300 | 69.9619 | 36.7821 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-10 | 2013-07-10 | 1392 | MDC | {E2274031-B222-413B-8266-9D23BA888269} |  |  |  | Minimal | 300 | CHA | 3 |  |  | 2012-11-16 16:30 | No | Complete
North East | Takhar | Kalfagan | Kalafgan (3) | {E2274031-B222-413B-8266-9D23BA888269} | c0a8-0009-13c0e3c09b2-85bca394-97a-61 | Hz-ID-17523 | HT - HALO TRUST | H/8444 | 1110 | 69.9619 | 36.7821 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-08 | 2013-07-09 | 1392 | MDC | {E2274031-B222-413B-8266-9D23BA888269} |  |  |  | Minimal | 300 | CHA | 3 |  |  | 2012-11-16 16:30 | No | Complete
North East | Takhar | Kalfagan | Kalafgan (3) | {E2274031-B222-413B-8266-9D23BA888269} | c0a8-0009-13c0e429606-56f22b03-9cc-85 | Hz-ID-17524 | HT - HALO TRUST | H/8445 | 370 | 69.9619 | 36.7821 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-07 | 2013-07-07 | 1392 | MDC | {E2274031-B222-413B-8266-9D23BA888269} |  |  |  | Minimal | 300 | CHA | 3 |  |  | 2012-11-16 16:30 | No | Complete
North East | Takhar | Kalfagan | Kalafgan (3) | {E2274031-B222-413B-8266-9D23BA888269} | c0a8-0009-13c0e4aafaa-aa3ae78d-9ed-d4 | Hz-ID-17525 | HT - HALO TRUST | H/8446 | 800 | 69.9594 | 36.779 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-04 | 2013-07-06 | 1392 | MDC | {E2274031-B222-413B-8266-9D23BA888269} |  |  |  | Minimal | 612 | CHA | 4 |  |  | 2012-11-17 16:30 | No | Complete
North East | Takhar | Kalfagan | Kalafgan (3) | {E2274031-B222-413B-8266-9D23BA888269} | c0a8-0009-13c0e4efc80-bda23792-a51-f1 | Hz-ID-17526 | HT - HALO TRUST | H/8447 | 1300 | 69.9594 | 36.779 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {E2274031-B222-413B-8266-9D23BA888269} |  |  |  | Minimal | 300 | CHA | 3 |  |  | 2012-11-18 16:30 | No | Complete
North East | Takhar | Kalfagan | Kalafgan (3) | {E2274031-B222-413B-8266-9D23BA888269} | c0a8-0009-13c0e5d0fdc-dc5f199-afe-b44 | Hz-ID-17527 | HT - HALO TRUST | H/8448 | 1170 | 69.9636 | 36.7776 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-03 | 2013-07-03 | 1392 | MDC | {E2274031-B222-413B-8266-9D23BA888269} |  |  |  | Minimal | 300 | CHA | 3 |  |  | 2012-11-19 16:30 | No | Complete
North East | Takhar | Kalfagan | Kalafgan (3) | {E2274031-B222-413B-8266-9D23BA888269} | c0a8-0009-13c0e7c7e8b-366f3b42-b82-cf | Hz-ID-17528 | HT - HALO TRUST | H/8449 | 205 | 69.9636 | 36.7776 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-02 | 2013-07-02 | 1392 | MDC | {E2274031-B222-413B-8266-9D23BA888269} |  |  |  | Minimal | 300 | CHA | 3 |  |  | 2012-11-20 16:30 | No | Complete
North East | Takhar | Kalfagan | Kalafgan (3) | {E2274031-B222-413B-8266-9D23BA888269} | c0a8-0009-13c0e8169e0-375c2a78-ba3-48 | Hz-ID-17529 | HT - HALO TRUST | H/8450 | 300 | 69.9657 | 36.7783 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-01 | 2013-07-01 | 1392 | MDC | {E2274031-B222-413B-8266-9D23BA888269} |  |  |  | Minimal | 537 | CHA | 4 |  |  | 2012-11-21 16:30 | No | Complete
North East | Takhar | Khwaja Ghar | Bahar Law | {DB1546BB-B43A-4DA0-AE32-E96C369D831F} | c0a8-0057-12c3b770c4a-719d5c5b-1308d- | BF-HQ-12132 | HT - HALO TRUST | BLU/2496 | 170368 | 69.3859 | 37.0819 | Open | UXO Only | UXO Only | BF |  | MBT Project-085/A | Takhar Demining Project-03 |  |  |  |  | 1395 |  | {DB1546BB-B43A-4DA0-AE32-E96C369D831F} | Based on HALO Trust confirmation, the hazard is removed from their plan | High Requested | Resettlment/Local Request | Low | 213 | CHA | 4 | Yes |  | 2009-03-08 | No | Open
North East | Takhar | Khwaja Ghar | Chaghatay | {714DC00E-C99F-42BB-8938-C5AC85712B23} | c0a8-008e-1328fc8d360-45344d07-280d-e | AIF-15008 | MCPA - Mine Clearance Planning Agency | AF/1212/12585/AIF0010 | 129659 | 69.3949 | 37.119 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-097 | Takhar Demining Project-2 (AT) | DOS | Yes |  |  | 1392 | MDC | {714DC00E-C99F-42BB-8938-C5AC85712B23} |  |  |  | Low | 811 | CHA | 3 | Yes |  | 2010-07-04 16:30 | No | Complete
North East | Takhar | Khwaja Ghar | Hawar Say | {B1653483-9FF4-4A28-BEA3-611B7F4D3AAD} | c0a8-0057-12c3b9e9246-20e88870-2e0fe- | MF-HQ-13168 | HT - HALO TRUST | H/6401 | 2035 | 69.3779 | 36.8946 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-097 | Takhar Demining Project-2 (AT) | DOS | Yes | 2014-03-17 | 2014-03-18 | 1392 | MDC | {B1653483-9FF4-4A28-BEA3-611B7F4D3AAD} |  |  |  | Low | 42 | CHA | 3 | Yes |  | 2009-09-04 | No | Complete
North East | Takhar | Khwaja Ghar | Hawar Say | {B1653483-9FF4-4A28-BEA3-611B7F4D3AAD} | c0a8-00f6-1353dbe57cf-1b399f55-1949-6 | MF-16636 | HT - HALO TRUST | H/6675 | 6100 | 69.3807 | 36.8997 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-08-25 | 2013-09-13 | 1392 | MDC | {B1653483-9FF4-4A28-BEA3-611B7F4D3AAD} |  |  |  | Low | 42 | CHA | 5 | Yes |  | 2010-07-20 16:30 | No | Complete
North East | Takhar | Khwaja Ghar | Hazar Bagh | {BE1D51F9-244F-4225-82EE-F0DAEBDF77CC} | c0a8-0009-13b405770ff-63e85342-4c1c-7 | Hz-ID-17410 | HT - HALO TRUST | H/8281 | 54300 | 69.4256 | 36.973 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {BE1D51F9-244F-4225-82EE-F0DAEBDF77CC} |  |  |  | Low | 27 | CHA | 2 |  |  | 2012-08-11 16:30 | No | Complete
North East | Takhar | Khwaja Ghar | Hazar Bagh | {BE1D51F9-244F-4225-82EE-F0DAEBDF77CC} | c0a8-0057-12c3b6f24fc-43256941-d1a3-7 | MF-HQ-10000 | HT - HALO TRUST | H/6021 | 6200 | 69.4017 | 36.9589 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2014-01-26 | 2014-01-28 | 1392 | MDC | {BE1D51F9-244F-4225-82EE-F0DAEBDF77CC} |  |  |  | Low | 5 | CHA | 2 |  |  | 2009-03-20 | No | Complete
North East | Takhar | Khwaja Ghar | Hazar Bagh | {BE1D51F9-244F-4225-82EE-F0DAEBDF77CC} | c0a8-0057-12c3b7b867c-daa16f7a-1643a- | MF-HQ-9999 | HT - HALO TRUST | H/6020 | 27720 | 69.4143 | 36.9611 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2013-12-07 | 2014-12-21 | 1392 | MDC | {BE1D51F9-244F-4225-82EE-F0DAEBDF77CC} |  |  |  | Low | 8 | CHA | 2 |  |  | 2009-03-19 | No | Complete
North East | Takhar | Khwaja Ghar | Hazar Bagh | {BE1D51F9-244F-4225-82EE-F0DAEBDF77CC} | c0a8-008e-1306d695d62-e2860232-3e7-9d | MF-HQ-10270 | HT - HALO TRUST | H/6028 | 9950 | 69.3308 | 37.0033 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-097 | Takhar Demining Project-2 (AT) | DOS | Yes | 2014-01-02 | 2014-06-07 | 1392 | MDC | {BE1D51F9-244F-4225-82EE-F0DAEBDF77CC} |  |  |  | Low | 65 | CHA | 2 |  |  | 2009-04-09 | No | Complete
North East | Takhar | Khwaja Ghar | Hazar Bagh | {BE1D51F9-244F-4225-82EE-F0DAEBDF77CC} | c0a8-008e-1306d6aa101-1f960d34-41d-df | MF-HQ-10269 | HT - HALO TRUST | H/6029 | 10000 | 69.3175 | 37.0094 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-097 | Takhar Demining Project-2 (AT) | DOS | Yes | 2014-01-08 | 2014-01-13 | 1392 | MDC | {BE1D51F9-244F-4225-82EE-F0DAEBDF77CC} |  |  |  | Low | 140 | CHA | 2 |  |  | 2009-04-10 | No | Complete
North East | Takhar | Khwaja Ghar | Hazar Bagh (1) | {B3BDECC2-C66F-4754-8022-625D9968320E} | c0a8-008e-1306d6bc827-ed742b33-463-f1 | MF-HQ-10274 | HT - HALO TRUST | H/6023 | 7700 | 69.3401 | 37.0043 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-097 | Takhar Demining Project-2 (AT) | DOS | Yes | 2014-01-14 | 2014-01-16 | 1392 | MDC | {B3BDECC2-C66F-4754-8022-625D9968320E} |  |  |  | Low | 59 | CHA | 5 | Yes |  | 2009-04-08 | No | Complete
North East | Takhar | Khwaja Ghar | Men Chuqar Ulya | {C2A297D1-8A7A-4DA4-9532-2020A8F19E30} | c0a8-0057-12c3b97c315-630b104c-29acd- | BF-NE-632 | HT - HALO TRUST | BLU2487 | 306000 | 69.3547 | 37.0922 | Open | UXO Only | UXO Only | BF |  | MBT Project-085/A | Takhar Demining Project-03 |  |  |  |  | 1395 |  | {C2A297D1-8A7A-4DA4-9532-2020A8F19E30} | Based on HALO Trust confirmation, the hazard is removed from their plan | High with Victim | High with Victims | Low | 253 | CHA | 2 |  |  | 2008-09-01 | No | Open
North East | Takhar | Khwaja Ghar | Men Chuqur | {D3A2FD93-E8F4-4772-B5D9-01364B950BF8} | c0a8-008e-132c924cc61-89e8b07a-29b8-8 | AIF-15006 | MCPA - Mine Clearance Planning Agency | AF/1212/14078/AIF0012 | 24080 | 69.3479 | 37.0872 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-097 | Takhar Demining Project-2 (AT) | DOS | Yes | 2014-01-30 | 2014-02-11 | 1392 | MDC | {D3A2FD93-E8F4-4772-B5D9-01364B950BF8} |  |  |  | Low | 59 | CHA | 3 | Yes |  | 2011-01-26 16:30 | No | Complete
North East | Takhar | Khwaja Ghar | Men Chuqur | {D3A2FD93-E8F4-4772-B5D9-01364B950BF8} | c0a8-008e-132c955efca-b2b40cd3-2fde-d | BF-HQ-13847 | HT - HALO TRUST | BLU/2740 | 6300 | 69.3259 | 37.1064 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-097 | Takhar Demining Project-2 (AT) | DOS | Yes |  |  | 1392 | MDC | {D3A2FD93-E8F4-4772-B5D9-01364B950BF8} |  |  |  | Low | 826 | CHA | 3 |  |  | 2009-12-15 | No | Complete
North East | Takhar | Khwaja Ghar | Qezel Say (1) | {667B2E5B-9C89-4608-86FC-CF7A0B6ED2B2} | c0a8-0009-13b40255a99-cff4a150-4a1d-3 | Hz-ID-17415 | HT - HALO TRUST | H/8287 | 55000 | 69.4427 | 36.9255 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-15 | 2013-08-15 | 1392 | MDC | {667B2E5B-9C89-4608-86FC-CF7A0B6ED2B2} |  |  |  | Low | 27 | CHA | 5 | Yes |  | 2012-08-03 16:30 | No | Complete
North East | Takhar | Khwaja Ghar | Qezel Say (1) | {667B2E5B-9C89-4608-86FC-CF7A0B6ED2B2} | c0a8-0009-13b403d40c9-cfca05b2-4aa9-6 | Hz-ID-17414 | HT - HALO TRUST | H/8286 | 51000 | 69.4466 | 36.928 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-24 | 2013-08-30 | 1392 | MDC | {667B2E5B-9C89-4608-86FC-CF7A0B6ED2B2} |  |  |  | Low | 29 | CHA | 5 | Yes |  | 2012-08-02 16:30 | No | Complete
North East | Takhar | Khwaja Ghar | Qezel Say (1) | {667B2E5B-9C89-4608-86FC-CF7A0B6ED2B2} | c0a8-0057-12c3b71806e-7d3d1f7f-ee56-1 | MF-HQ-10275 | HT - HALO TRUST | H/6022 | 60100 | 69.4223 | 36.9341 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-01 | 2013-08-19 | 1392 | MDC | {667B2E5B-9C89-4608-86FC-CF7A0B6ED2B2} |  |  |  | Low | 28 | CHA | 5 | Yes |  | 2009-04-04 | No | Complete
North East | Takhar | Khwaja Ghar | Qezel Say (1) | {667B2E5B-9C89-4608-86FC-CF7A0B6ED2B2} | c0a8-0057-12c3b78128e-c74134c4-13c67- | MF-HQ-10349 | HT - HALO TRUST | H/5886 | 33520 | 69.4188 | 36.9357 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-08-20 | 2013-09-08 | 1392 | MDC | {667B2E5B-9C89-4608-86FC-CF7A0B6ED2B2} |  |  |  | Low | 22 | CHA | 5 | Yes |  | 2009-04-04 | No | Complete
North East | Takhar | Khwaja Ghar | Qezel Say (2) | {A9F5E1FB-2E5D-493E-B3C4-093A3736AFF8} | c0a8-0057-12c3ba59677-e6615c0c-32530- | MF-NE-667 | HT - HALO TRUST | H/5099 | 3100 | 69.4062 | 36.9549 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2014-01-18 | 2014-01-19 | 1392 | MDC | {A9F5E1FB-2E5D-493E-B3C4-093A3736AFF8} |  |  |  | Low | 5 | CHA | 3 | Yes |  | 2008-09-01 | No | Complete
North East | Takhar | Khwaja Ghar | Qorq | {441031CD-31EA-49CB-B4A1-7A0E2B56B25E} | c0a8-008e-132c924efa9-e55db2b7-29ec-f | AIF-15007 | MCPA - Mine Clearance Planning Agency | AF/1212/00032/AIF0011 | 4220 | 69.3885 | 37.1454 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-097 | Takhar Demining Project-2 (AT) | DOS | Yes | 2014-01-20 | 2014-01-21 | 1392 | MDC | {441031CD-31EA-49CB-B4A1-7A0E2B56B25E} |  |  |  | Low | 47 | CHA | 3 |  |  | 2011-02-08 16:30 | Yes | Complete
North East | Takhar | Khwaja Ghar | Wraz Bacha | {9C75FFA3-3071-49B9-9E2D-D0F9C064DB9D} | c0a8-0057-12c3b7dba24-21caad12-17dbd- | MF-HT-674 | HT - HALO TRUST | H/3928 | 7300 | 69.3994 | 37.0854 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-01 | 2013-07-22 | 1392 | MDC | {9C75FFA3-3071-49B9-9E2D-D0F9C064DB9D} |  |  |  | Low | 4554 | CHA | 4 | Yes |  | 2007-09-01 | No | Complete
North East | Takhar | Khwaja Ghar | Yakka Shor | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} | c0a8-0009-13b4048071f-538b7c26-4b2f-c | Hz-ID-17411 | HT - HALO TRUST | H/8282 | 17784 | 69.4597 | 37.0022 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-01 | 2013-07-15 | 1392 | MDC | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} |  |  |  | Low | 14 | CHA | 5 | Yes |  | 2012-08-13 16:30 | No | Complete
North East | Takhar | Khwaja Ghar | Yakka Shor | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} | c0a8-0009-13b40d7cf8f-81d87e8b-4e24-c | Hz-ID-17413 | HT - HALO TRUST | H/8284 | 16400 | 69.4763 | 36.972 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-06-08 | 2013-06-21 | 1392 | MDC | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} |  |  |  | Low | 37 | CHA | 5 | Yes |  | 2012-08-15 16:30 | No | Complete
North East | Takhar | Khwaja Ghar | Yakka Shor | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} | c0a8-0009-13b7e4c7335-1e949e25-4d81-6 | Hz-ID-17412 | HT - HALO TRUST | H/8283 | 48040 | 69.489 | 36.989 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-04-18 | 2013-06-20 | 1392 | MDC | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} |  |  |  | Low | 80 | CHA | 5 | Yes |  | 2012-08-15 16:30 | No | Complete
North East | Takhar | Khwaja Ghar | Yakka Shor | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} | c0a8-0057-12c3b69b2b8-e50f7c65-8f84-2 | MF-HQ-14723 | HT - HALO TRUST | H/6620 | 4400 | 69.5059 | 36.9934 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} |  |  |  | Low | 36 | CHA | 5 | Yes |  | 2010-06-12 | No | Complete
North East | Takhar | Khwaja Ghar | Yakka Shor | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} | c0a8-0057-12c3b6af494-b1675494-9e7a-7 | MF-HQ-10226 | HT - HALO TRUST | H/6030 | 46200 | 69.4767 | 36.9941 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-05-20 | 2013-07-15 | 1392 | MDC | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} |  |  |  | Low | 77 | CHA | 4 | Yes |  | 2009-04-11 | No | Complete
North East | Takhar | Khwaja Ghar | Yakka Shor | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} | c0a8-0057-12c3b711213-740eb270-e914-a | MF-HQ-14702 | HT - HALO TRUST | H/6619 | 34000 | 69.5024 | 36.9936 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {C087DC2C-8A2D-48A6-817C-F2BD27126E93} |  |  |  | Low | 11 | CHA | 5 | Yes |  | 2010-06-12 | No | Complete
North East | Takhar | Khwaja Ghar | Zaghcha Guzar | {E2531549-D8AF-4B81-B2D7-5C98B131BFE8} | c0a8-008e-13358d558c1-e849693d-fd4-bf | MF-16336 | HT - HALO TRUST | H/8221 | 14800 | 69.4238 | 36.9828 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-27 | 2013-08-24 | 1392 | MDC | {E2531549-D8AF-4B81-B2D7-5C98B131BFE8} |  |  |  | Low | 72 | CHA | 5 | Yes |  | 2011-09-04 16:30 | No | Complete
North East | Takhar | Khwaja Ghar | Zard Kamar | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | c0a8-0009-13b7e4bfaa0-ae6631f8-4d5c-5 | Hz-ID-17416 | HT - HALO TRUST | H/8288 | 41900 | 69.3568 | 37.1247 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-03-30 | 2014-04-19 | 1393 | MDC | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} |  |  |  | Low | 23 | CHA | 2 |  |  | 2012-08-01 16:30 | No | Planned
North East | Takhar | Khwaja Ghar | Zard Kamar | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | c0a8-0009-13e1c71b1af-364b2994-69eb-a | Hz-ID-17821 | MCPA - Mine Clearance Planning Agency | AF/1212/12586/BF0013 | 160655 | 69.3717 | 37.1063 | Open | UXO Only | UXO Only | BF |  | MBT Project-085/A | Takhar Demining Project-03 |  |  |  |  | 1395 |  | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} |  | High with Victim | High with Victims | Low | 195 | CHA | 2 |  |  | 2013-03-28 16:30 | No | Open
North East | Takhar | Khwaja Ghar | Zard Kamar | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | c0a8-0009-1455fe2dbd9-62f66ec4-2b4f-6 | Hz-ID-18624 | MDC - Mine Detection and Dog Center | AF/1212/12586/MF0014 | 30033 | 69.3564 | 37.1207 | Worked on | Mixed | Mixed AP AT UXO | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes |  |  | 1393 | MDC | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} |  | High with Victim | High with Victims | Low | 16 | CHA | 2 |  |  | 2014-04-02 16:30 | No | Planned
North East | Takhar | Khwaja Ghar | Zard Kamar | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | c0a8-0057-12c3b69298d-38df09f3-8950-d | BF-HQ-13563 | HT - HALO TRUST | BLU/2728 | 307650 | 69.3704 | 37.1011 | Open | UXO Only | UXO Only | BF |  | MBT Project-085/A | Takhar Demining Project-03 |  |  |  |  | 1395 |  | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | Based on HALO Trust confirmation, the hazard is removed from their plan | High with Victim | High with Victims | Low | 357 | CHA | 2 |  |  | 2009-10-18 | No | Open
North East | Takhar | Khwaja Ghar | Zard Kamar | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | c0a8-0057-12c3b6b7804-21bbd44a-a4d6-d | MF-HQ-10286 | HT - HALO TRUST | H/5841 | 610 | 69.3529 | 37.1474 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2014-01-22 | 2014-01-15 | 1392 | MDC | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} |  |  |  | Low | 34 | CHA | 2 |  |  | 2009-04-01 | No | Complete
North East | Takhar | Khwaja Ghar | Zard Kamar | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | c0a8-0057-12c3b6c1210-846f782c-ac2d-c | BF-HQ-13576 | HT - HALO TRUST | BLU/2733 | 372750 | 69.3693 | 37.1128 | Open | UXO Only | UXO Only | BF |  | MBT Project-085/A | Takhar Demining Project-03 |  |  |  |  | 1395 |  | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | Based on HALO Trust confirmation, the hazard is removed from their plan | High with Victim | High with Victims | Low | 149 | CHA | 2 |  |  | 2009-10-18 | No | Open
North East | Takhar | Khwaja Ghar | Zard Kamar | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | c0a8-0057-12c3b6c7cd2-e390693e-b153-5 | BF-HQ-13573 | HT - HALO TRUST | BLU/2732 | 479850 | 69.3532 | 37.1032 | Open | UXO Only | UXO Only | BF |  | MBT Project-085/A | Takhar Demining Project-03 |  |  |  |  | 1395 |  | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | Based on HALO Trust confirmation, the hazard is removed from their plan | High with Victim | High with Victims | Low | 80 | CHA | 2 |  |  | 2009-10-17 | No | Open
North East | Takhar | Khwaja Ghar | Zard Kamar | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | c0a8-0057-12c3b716be5-2f8fa84e-ed55-d | BF-HQ-13565 | HT - HALO TRUST | BLU/2729 | 254625 | 69.3672 | 37.097 | Open | UXO Only | UXO Only | BF |  | MBT Project-085/A | Takhar Demining Project-03 |  |  |  |  | 1395 |  | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | Based on HALO Trust confirmation, the hazard is removed from their plan | High with Victim | High with Victims | Low | 193 | CHA | 2 |  |  | 2009-10-18 | No | Open
North East | Takhar | Khwaja Ghar | Zard Kamar | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | c0a8-0057-12c3b719d21-85e1b29-efb9-81 | BF-HQ-13568 | HT - HALO TRUST | BLU/2730 | 315000 | 69.3604 | 37.0924 | Open | UXO Only | UXO Only | BF |  | MBT Project-085/A | Takhar Demining Project-03 |  |  |  |  | 1395 |  | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | Based on HALO Trust confirmation, the hazard is removed from their plan | High with Victim | High with Victims | Low | 221 | CHA | 2 |  |  | 2009-10-18 | No | Open
North East | Takhar | Khwaja Ghar | Zard Kamar | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | c0a8-0057-12c3b7210f8-ce0785eb-f52f-7 | MF-HQ-10284 | HT - HALO TRUST | H/5842 | 2470 | 69.3546 | 37.1495 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2014-01-23 | 2014-01-25 | 1392 | MDC | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} |  |  |  | Low | 34 | CHA | 2 |  |  | 2009-04-02 | No | Complete
North East | Takhar | Khwaja Ghar | Zard Kamar | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | c0a8-0057-12c3b775837-3a7ee2da-133f0- | BF-HQ-13571 | HT - HALO TRUST | BLU/2731 | 341250 | 69.3542 | 37.0967 | Open | UXO Only | UXO Only | BF |  | MBT Project-085/A | Takhar Demining Project-03 |  |  |  |  | 1395 |  | {DFB9A801-3EBD-47D3-A6C9-3229D7F0064E} | Based on HALO Trust confirmation, the hazard is removed from their plan | High with Victim | High with Victims | Low | 101 | CHA | 2 |  |  | 2009-10-17 | No | Open
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-142e561f32c-9509089c-6815-4 | Hz-ID-18280 | HT - HALO TRUST | H/8878 | 20283 | 69.7322 | 36.5731 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Critical Infrastracture | Minimal | 17 | CHA | 5 |  |  | 2013-11-20 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-142e5621efd-6fbc41c2-684c-f | Hz-ID-18278 | HT - HALO TRUST | H/8876 | 3170 | 69.7301 | 36.5775 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Agriculture Blocked | Minimal | 17 | CHA | 5 |  |  | 2013-11-17 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-142e5630ce3-aa990a3e-6873-d | Hz-ID-18279 | HT - HALO TRUST | H/8877 | 17582 | 69.7331 | 36.5756 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Critical Infrastracture | Minimal | 17 | CHA | 5 |  |  | 2013-11-18 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-142e563bf02-3d782f24-68aa-5 | Hz-ID-18283 | HT - HALO TRUST | H/8885 | 6221 | 69.733 | 36.5717 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Agriculture Blocked | Minimal | 17 | CHA | 5 |  |  | 2013-11-18 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-142e563df7d-d928d044-68c8-c | Hz-ID-18281 | HT - HALO TRUST | H/8879 | 1758 | 69.7321 | 36.5717 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Agriculture Blocked | Minimal | 17 | CHA | 5 |  |  | 2013-11-22 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-142e56493fc-2e678d6-68ee-d9 | Hz-ID-18282 | HT - HALO TRUST | H/8884 | 33932 | 69.7342 | 36.5757 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Critical Infrastracture | Minimal | 17 | CHA | 5 |  |  | 2013-11-20 16:30 | No | Open
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-142e5656e24-bae6d631-6943-c | Hz-ID-18284 | HT - HALO TRUST | H/8886 | 33900 | 69.6884 | 36.5778 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Agriculture Blocked | Minimal | 56 | CHA | 5 |  |  | 2013-11-21 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-142e568288c-7b8d93fe-6998-9 | Hz-ID-18287 | HT - HALO TRUST | H/8883 | 5635 | 69.7385 | 36.5756 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Agriculture Blocked | Minimal | 17 | CHA | 5 |  |  | 2013-11-19 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-14384ac9d14-b6e1c01d-3bb0-b | Hz-ID-18374 | HT - HALO TRUST | H/8887 | 54732 | 69.7333 | 36.5703 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes | 2014-08-01 |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Critical Infrastracture | Minimal | 27 | CHA | 5 |  |  | 2013-12-02 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-14384ad243d-7b388bda-3bde-c | Hz-ID-18377 | HT - HALO TRUST | H/8889 | 47110 | 69.7336 | 36.5683 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes | 2014-08-01 |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Critical Infrastracture | Minimal | 10 | CHA | 5 |  |  | 2013-12-07 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-14384afd274-2ff9d0d5-3caa-a | Hz-ID-18369 | HT - HALO TRUST | H/8880 | 3440 | 69.7322 | 36.571 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Agriculture Blocked | Minimal | 27 | CHA | 5 |  |  | 2013-12-02 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-14384d4c09a-9a943e69-3e75-1 | Hz-ID-18379 | HT - HALO TRUST | H/8892 | 22018 | 69.7194 | 36.5701 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Agriculture Blocked | Minimal | 74 | CHA | 5 |  |  | 2013-12-14 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-14384dfb418-5a990b5f-3f1c-d | Hz-ID-18381 | HT - HALO TRUST | H/8893 | 63934 | 69.6848 | 36.5775 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Critical Infrastracture | Minimal | 44 | CHA | 5 |  |  | 2013-12-15 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-14384dff848-79ac7fa9-3f3d-b | Hz-ID-18382 | HT - HALO TRUST | H/8897 | 12178 | 69.6938 | 36.5862 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Critical Infrastracture | Minimal | 57 | CHA | 5 |  |  | 2013-12-11 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-14384e77975-3bf3ae6-3fc8-33 | Hz-ID-18375 | HT - HALO TRUST | H/8888 | 6205 | 69.7354 | 36.5726 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Critical Infrastracture | Minimal | 17 | CHA | 5 |  |  | 2013-12-04 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-14384e7fa86-f3286305-3fe6-c | Hz-ID-18373 | HT - HALO TRUST | H/8882 | 8202 | 69.7271 | 36.5704 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Agriculture Blocked | Minimal | 17 | CHA | 5 |  |  | 2013-12-05 16:30 | No | Planned
North East | Takhar | Namak Ab | Bagh-i-Khwaja | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} | c0a8-0009-144b4666130-76137d6d-703b-e | Hz-ID-18378 | HT - HALO TRUST | H/8890 | 33252 | 69.6949 | 36.561 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-126/A | Takhar Demining Project-07/A | GAGP | Yes |  |  | 1393 | HT | {D71548A4-BEF3-4052-B05F-8B1DDE87DE21} |  | Low | Critical Infrastracture | Minimal | 29 | CHA | 5 |  |  | 2013-12-09 16:30 | No | Planned
North East | Takhar | Namak Ab | Jaw Roz | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | c0a8-0057-12c3b69bd04-23d85e64-8ff4-7 | MF-HQ-13845 | HT - HALO TRUST | H/6467 | 25120 | 69.6537 | 36.5502 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {6F27D580-8BE6-4B74-83E6-52CBEF493833} |  | High Requested | Resettlment/Local Request | Minimal | 24 | CHA | 5 |  |  | 2009-12-15 | No | Open
North East | Takhar | Namak Ab | Jaw Roz | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | c0a8-0057-12c3b745919-69fe1387-11099- | MF-HQ-13848 | HT - HALO TRUST | H/6466 | 9200 | 69.6492 | 36.5398 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | , | High Requested | Resettlment/Local Request | Minimal | 32 | CHA | 3 |  |  | 2009-12-15 | No | Open
North East | Takhar | Namak Ab | Jaw Roz | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | c0a8-0057-12c3b7860db-35628cfa-13ffe- | MF-HQ-13844 | HT - HALO TRUST | H/6465 | 1120 | 69.6531 | 36.5318 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | , | High Requested | Resettlment/Local Request | Minimal | 11 | CHA | 3 |  |  | 2009-12-15 | No | Open
North East | Takhar | Namak Ab | Jaw Roz | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | c0a8-0057-12c3b79828b-1f3ba435-14d37- | MF-HQ-13850 | HT - HALO TRUST | H/6464 | 18115 | 69.6513 | 36.537 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {6F27D580-8BE6-4B74-83E6-52CBEF493833} |  | High Requested | Resettlment/Local Request | Minimal | 29 | CHA | 4 |  |  | 2009-12-15 | No | Open
North East | Takhar | Namak Ab | Jaw Roz | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | c0a8-0057-12c3bb7961b-a0db7d01-3cefe- | MF-HT-255 | HT - HALO TRUST | H/3905 | 1060 | 69.6478 | 36.538 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | , | High Requested | Resettlment/Local Request | Minimal | 3 | CHA | 6 |  |  | 2010-09-30 | No | Open
North East | Takhar | Namak Ab | Jaw Roz | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | c0a8-0057-12c3bb798c9-dc12c02e-3cf1e- | MF-HT-253 | HT - HALO TRUST | H/3906 | 5320 | 69.6535 | 36.5309 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | , | High Requested | Resettlment/Local Request | Minimal | 11 | CHA | 3 |  |  | 2009-12-15 | No | Open
North East | Takhar | Namak Ab | Jaw Roz | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | c0a8-0057-12c3bb79b0b-10e852fb-3cf37- | MF-HT-261 | HT - HALO TRUST | H/2908 | 31200 | 69.6344 | 36.5337 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {6F27D580-8BE6-4B74-83E6-52CBEF493833} |  | High Requested | Resettlment/Local Request | Minimal | 29 | CHA | 5 |  |  | 2007-09-30 | No | Open
North East | Takhar | Namak Ab | Jaw Roz | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | c0a8-0057-12c3bb79e74-4a48492e-3cf4d- | MF-HT-252 | HT - HALO TRUST | H/3904 | 2250 | 69.6519 | 36.538 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {6F27D580-8BE6-4B74-83E6-52CBEF493833} |  | High Requested | Resettlment/Local Request | Minimal | 29 | CHA | 6 |  |  | 2007-09-30 | No | Open
North East | Takhar | Namak Ab | Jaw Roz | {6F27D580-8BE6-4B74-83E6-52CBEF493833} | c0a8-0057-12c3bb7a151-19654cd2-3cf6b- | MF-HT-251 | HT - HALO TRUST | H/3903 | 19700 | 69.6488 | 36.5433 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {6F27D580-8BE6-4B74-83E6-52CBEF493833} |  | High Requested | Resettlment/Local Request | Minimal | 14 | CHA | 5 |  |  | 2007-09-30 | No | Open
North East | Takhar | Namak Ab | Khami Khairan | {F315A7B7-AAF3-4EE7-B718-9C8477C03B95} | c0a8-0057-12c3b73f2f8-a7740028-10bd7- | MF-HQ-13552 | HT - HALO TRUST | H/6443 | 6470 | 69.6513 | 36.6221 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-10-17 | 2013-10-29 | 1392 | MDC | {F315A7B7-AAF3-4EE7-B718-9C8477C03B95} |  |  |  | Minimal | 3 | CHA | 5 |  |  | 2009-10-02 | No | Complete
North East | Takhar | Namak Ab | Khami Khairan | {F315A7B7-AAF3-4EE7-B718-9C8477C03B95} | c0a8-0057-12c3b96dbe7-9a528430-29138- | MF-HQ-11930 | HT - HALO TRUST | H/6071 | 2215 | 69.663 | 36.6054 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-08-01 | 2013-08-02 | 1392 | MDC | {F315A7B7-AAF3-4EE7-B718-9C8477C03B95} |  |  |  | Minimal | 37 | CHA | 3 |  |  | 2009-07-03 | No | Complete
North East | Takhar | Namak Ab | Khami Khairan | {F315A7B7-AAF3-4EE7-B718-9C8477C03B95} | c0a8-0057-12c3ba43d24-8d37af3b-3181f- | MF-HQ-11790 | HT - HALO TRUST | H/6069 | 1130 | 69.6504 | 36.6228 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-10-30 | 2013-10-31 | 1392 | MDC | {F315A7B7-AAF3-4EE7-B718-9C8477C03B95} | , |  |  | Minimal | 3 | CHA | 5 |  |  | 2009-07-01 | No | Complete
North East | Takhar | Namak Ab | Khami Khairan | {F315A7B7-AAF3-4EE7-B718-9C8477C03B95} | c0a8-0057-12c3ba44159-14064b1b-3183e- | MF-HQ-11848 | HT - HALO TRUST | H/6070 | 2800 | 69.6487 | 36.6227 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-07-28 | 2013-07-31 | 1392 | MDC | {F315A7B7-AAF3-4EE7-B718-9C8477C03B95} |  |  |  | Minimal | 3 | CHA | 3 |  |  | 2009-07-02 | No | Complete
North East | Takhar | Namak Ab | Nahr Ab | {C3ECC4BB-D9FD-48BA-BD68-D9711A86AFAF} | c0a8-0057-12c3b6da047-37fd3225-bf3a-1 | MF-HQ-12398 | HT - HALO TRUST | H/6389 | 49800 | 69.738 | 36.5612 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-07-29 | 2013-09-05 | 1392 | MDC | {C3ECC4BB-D9FD-48BA-BD68-D9711A86AFAF} |  |  |  | Minimal | 29 | CHA | 3 |  |  | 2009-08-10 | No | Complete
North East | Takhar | Namak Ab | Nahr Ab | {C3ECC4BB-D9FD-48BA-BD68-D9711A86AFAF} | c0a8-0057-12c3b749f1c-201391e6-113c7- | MF-HQ-12401 | HT - HALO TRUST | H/6390 | 60885 | 69.7372 | 36.5586 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-09-22 | 2013-10-16 | 1392 | MDC | {C3ECC4BB-D9FD-48BA-BD68-D9711A86AFAF} |  |  |  | Minimal | 29 | CHA | 5 |  |  | 2009-08-11 | No | Complete
North East | Takhar | Namak Ab | Nahr Ab | {C3ECC4BB-D9FD-48BA-BD68-D9711A86AFAF} | c0a8-0057-12c3b7a23b8-11ff249-15474-5 | MF-HQ-12379 | HT - HALO TRUST | H/6396 | 36490 | 69.741 | 36.5614 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-06-21 | 2013-07-27 | 1392 | MDC | {C3ECC4BB-D9FD-48BA-BD68-D9711A86AFAF} |  |  |  | Minimal | 4 | CHA | 3 |  |  | 2009-08-17 | No | Complete
North East | Takhar | Namak Ab | Nahr Ab | {C3ECC4BB-D9FD-48BA-BD68-D9711A86AFAF} | c0a8-008e-1328fb60d35-7053b3cb-2430-a | MF-15423 | HT - HALO TRUST | H/7367 | 31600 | 69.7629 | 36.5765 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-05-28 | 2013-07-27 | 1392 | MDC | {C3ECC4BB-D9FD-48BA-BD68-D9711A86AFAF} |  |  |  | Minimal | 168 | CHA | 3 |  |  | 2010-10-19 16:30 | No | Complete
North East | Takhar | Namak Ab | Nahr Ab | {C3ECC4BB-D9FD-48BA-BD68-D9711A86AFAF} | c0a8-008e-132c94ad6bb-ab9aa6db-2e94-5 | MF-15422 | HT - HALO TRUST | H/7366 | 35200 | 69.7644 | 36.5823 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-05-08 | 2013-06-06 | 1392 | MDC | {C3ECC4BB-D9FD-48BA-BD68-D9711A86AFAF} |  |  |  | Minimal | 44 | CHA | 3 |  |  | 2010-10-18 16:30 | No | Complete
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-004c-130069b5d66-9cc7c399-b13-32 | MF-HQ-13519 | HT - HALO TRUST | H/6456 | 1650 | 69.6936 | 36.5099 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 15 | CHA | 2 |  |  | 2009-10-15 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b68f2e5-b487e66f-86f8-c | MF-HQ-13523 | HT - HALO TRUST | H/6459 | 2110 | 69.6829 | 36.5149 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 20 | CHA | 2 |  |  | 2009-10-18 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b6973d5-1f7d9b54-8c8d-c | MF-HQ-13521 | HT - HALO TRUST | H/6458 | 1020 | 69.6898 | 36.5134 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 16 | CHA | 2 |  |  | 2009-10-17 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b69c158-fd4aa49d-9030-c | MF-HQ-13200 | HT - HALO TRUST | H/6072 | 7100 | 69.7465 | 36.5424 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes |  |  | 1392 | MDC | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} |  |  |  | Minimal | 22 | CHA | 2 |  |  | 2009-09-12 | No | Complete
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b69f217-1259b1ac-9281-b | MF-HQ-13526 | HT - HALO TRUST | H/6461 | 2900 | 69.6694 | 36.5219 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 16 | CHA | 2 |  |  | 2009-10-27 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b6c70d1-5bc14b6a-b0c1-f | MF-HQ-13515 | HT - HALO TRUST | H/6453 | 31350 | 69.6932 | 36.5134 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 31 | CHA | 2 |  |  | 2009-10-12 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b6db405-4feeea4e-c021-2 | MF-HQ-13520 | HT - HALO TRUST | H/6457 | 850 | 69.6993 | 36.5128 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 26 | CHA | 2 |  |  | 2009-10-16 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b727600-6892f3ee-f9f4-c | MF-HQ-13524 | HT - HALO TRUST | H/6460 | 1540 | 69.6825 | 36.5162 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 0 | CHA | 2 |  |  | 2009-10-19 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b761966-cb2cbe72-12554- | MF-HQ-13512 | HT - HALO TRUST | H/6451 | 28600 | 69.7796 | 36.5211 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 16 | CHA | 2 |  |  | 2009-10-10 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b768956-b47c85f5-12a7e- | MF-HQ-13513 | HT - HALO TRUST | H/6452 | 39300 | 69.7842 | 36.5243 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 25 | CHA | 2 |  |  | 2009-10-11 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b7887bc-40ff1333-141be- | MF-HQ-13529 | HT - HALO TRUST | H/6463 | 4290 | 69.6659 | 36.5241 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 6 | CHA | 2 |  |  | 2009-10-20 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b7933d1-7e6f465-14998-7 | MF-HQ-13527 | HT - HALO TRUST | H/6462 | 11440 | 69.6592 | 36.5265 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 16 | CHA | 2 |  |  | 2009-10-22 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b7aa055-e0bc5b74-15a1a- | MF-HQ-13518 | HT - HALO TRUST | H/6455 | 7830 | 69.6937 | 36.5099 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 15 | CHA | 2 |  |  | 2009-10-14 | No | Open
North East | Takhar | Namak Ab | Namak Ab | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | c0a8-0057-12c3b9eca84-dd76d99b-2e30a- | MF-HQ-13516 | HT - HALO TRUST | H/6454 | 1920 | 69.6917 | 36.5079 | Open | AP Only | AP Only | MineField |  | MBT Project-126 | Takhar Demining Project-07 |  |  |  |  | 1395 |  | {77A885AD-7DC9-4F8E-983F-581DFC678B4C} | , | High with Victim | High with Victims | Minimal | 0 | CHA | 2 |  |  | 2009-10-13 | No | Open
North East | Takhar | Namak Ab | Shak Darah | {4C8C7C06-636D-44F4-9CF9-CBB9ADC5007C} | c0a8-0057-12c3bb2a563-df96c412-3a147- | MF-HQ-12399 | HT - HALO TRUST | H/6398 | 33800 | 69.6572 | 36.5452 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes |  |  | 1393 | MDC | {4C8C7C06-636D-44F4-9CF9-CBB9ADC5007C} | , | High Requested | Resettlment/Local Request | Minimal | 27 | CHA | 3 |  |  | 2009-08-15 | No | Planned
North East | Takhar | Namak Ab | Shak Darah | {4C8C7C06-636D-44F4-9CF9-CBB9ADC5007C} | c0a8-0057-12c3bb2a86f-c1ea179b-3a165- | MF-HQ-12346 | HT - HALO TRUST | H/2924 | 44240 | 69.6588 | 36.5427 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes |  |  | 1393 | MDC | {4C8C7C06-636D-44F4-9CF9-CBB9ADC5007C} | , | High Requested | Resettlment/Local Request | Minimal | 8 | CHA | 3 |  |  | 2009-08-15 | No | Planned
North East | Takhar | Namak Ab | Shak Darah | {4C8C7C06-636D-44F4-9CF9-CBB9ADC5007C} | c0a8-0057-12c3bb2aadf-fbce23d2-3a183- | MF-HQ-12395 | HT - HALO TRUST | H/6397 | 17120 | 69.6572 | 36.55 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes |  |  | 1393 | MDC | {4C8C7C06-636D-44F4-9CF9-CBB9ADC5007C} | , | High Requested | Resettlment/Local Request | Minimal | 8 | CHA | 3 |  |  | 2009-08-14 | No | Planned
North East | Takhar | Namak Ab | Shulesh Darrah | {0B47CD4F-ACA7-47C7-8A0C-B600CEDC7A61} | c0a8-0057-12c3bb59130-15dcdffe-3bcb9- | MF-HT-441 | HT - HALO TRUST | H/2986 | 26000 | 69.5784 | 36.623 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes |  |  | 1393 | MDC | {0B47CD4F-ACA7-47C7-8A0C-B600CEDC7A61} |  | High Requested | Resettlment/Local Request | Minimal | 1 | CHA | 5 | Yes |  | 2007-06-01 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0009-13b405d0a1d-9d966f67-4c4b-6 | Hz-ID-17408 | HT - HALO TRUST | H/8274 | 16160 | 69.7013 | 36.5962 | Worked on | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-12-01 | 2014-04-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  | High Requested | Resettlment/Local Request | Minimal | 67 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2012-08-16 16:30 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0009-13b409f55ae-9a90683e-4cfd-a | Hz-ID-17407 | HT - HALO TRUST | H/8273 | 7320 | 69.7012 | 36.5962 | Worked on | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-12-01 | 2014-09-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  | High Requested | Resettlment/Local Request | Minimal | 20 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2012-08-10 16:30 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0009-13b459bae20-c90ad98-5466-79 | Hz-ID-17409 | HT - HALO TRUST | H/8275 | 65400 | 69.698 | 36.5625 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-06-03 | 2014-06-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 26 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2012-08-15 16:30 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0009-13bdbbf0245-8491e26d-14e9-b | Hz-ID-17517 | HT - HALO TRUST | H/8436 | 22100 | 69.7134 | 36.5941 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-125/E | Takhar Demining Project-02/E | B-Germany | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 25 | CHA | 5 |  |  | 2012-11-11 16:30 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0009-13bea3dcb30-85ed3711-af-fcc | Hz-ID-17518 | HT - HALO TRUST | H/8437 | 50347 | 69.7077 | 36.5955 | Closed | Mixed | Mixed AP UXO | MineField | 1392/1393 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-07-01 | 2014-06-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 50 | CHA | 5 |  |  | 2012-11-14 16:30 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0009-13c1e35f2f7-4899d471-8208-2 | Hz-ID-17519 | HT - HALO TRUST | H/8438 | 31150 | 69.7011 | 36.6021 | Worked on | Mixed | Mixed AP UXO | MineField | 1392/1393 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-12-01 | 2014-07-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  | Low | Agriculture Blocked | Minimal | 25 | CHA | 5 |  |  | 2012-11-15 16:30 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0009-13c1ee0450d-6ee99c34-375-4d | Hz-ID-17516 | HT - HALO TRUST | H/8435 | 31600 | 69.7162 | 36.5896 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/E | Takhar Demining Project-02/E | B-Germany | Yes | 2013-10-01 | 2013-11-23 | 1392 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 29 | CHA | 5 |  |  | 2012-11-09 16:30 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0009-13f2caf9f41-8ba0a680-5711-4 | Hz-ID-17965 | HT - HALO TRUST | H/8492 | 2320 | 69.7074 | 36.591 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  | Low | Agriculture Blocked | Minimal | 119 | CHA | 4 |  |  | 2013-05-09 16:30 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0009-14384e6c5d1-11850689-3f9c-3 | Hz-ID-18384 | HT - HALO TRUST | H/8899 | 8376 | 69.7095 | 36.6202 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes |  |  | 1393 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  | Low | Critical Infrastracture | Minimal | 0 | CHA | 5 |  |  | 2013-12-13 16:30 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b68f91c-e490c4b2-8733-7 | MF-HQ-13148 | HT - HALO TRUST | H/6433 | 7330 | 69.6935 | 36.5715 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-05-03 | 2013-06-08 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 59 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-09-05 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b69420c-eb2db88a-8a6a-e | MF-HQ-12382 | HT - HALO TRUST | H/6384 | 58070 | 69.7353 | 36.5621 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-10-25 | 2013-12-06 | 1392 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 4 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-05 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b6aa58c-6aa874bd-9ae5-8 | MF-HQ-13550 | HT - HALO TRUST | H/6441 | 18000 | 69.7299 | 36.5681 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-10-01 | 2013-11-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 12 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-10-01 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b6b2e59-c2ff19d4-a14b-d | MF-HQ-13198 | HT - HALO TRUST | H/6439 | 28500 | 69.7328 | 36.5727 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-12-01 | 2014-05-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 28 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-09-11 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b6bc8f1-b1f786d5-a8b2-e | MF-HQ-13193 | HT - HALO TRUST | H/6437 | 135 | 69.6901 | 36.5776 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-06-16 | 2014-07-17 | 1393 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | , | High Requested | Resettlment/Local Request | Minimal | 31 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-09-09 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b6cfd27-a63bb520-b76f-f | MF-HQ-12392 | HT - HALO TRUST | H/6386 | 62080 | 69.7388 | 36.5553 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-06-09 | 2013-07-28 | 1392 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 29 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-07 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b6ecf4f-e228ba5a-cda9-a | MF-HQ-12375 | HT - HALO TRUST | H/6382 | 63360 | 69.7288 | 36.558 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes | 2014-06-01 | 2014-07-19 | 1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  | High Requested | Resettlment/Local Request | Minimal | 18 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-03 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b6f66cb-6f5c4324-d4ba-1 | MF-HQ-12409 | HT - HALO TRUST | H/6395 | 7340 | 69.739 | 36.5718 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes |  |  | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 16 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-16 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b6fc020-9185ccc1-d900-c | MF-HQ-11975 | HT - HALO TRUST | H/6079 | 760 | 69.7173 | 36.5973 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-06-11 | 2013-06-11 | 1392 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | , |  |  | Minimal | 45 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-10 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b6fc638-affae618-d94e-a | MF-HQ-13551 | HT - HALO TRUST | H/6442 | 4100 | 69.7304 | 36.5692 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-12-01 | 2013-12-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 12 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-10-03 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b6fdd02-2b8cf5ee-da77-2 | MF-HQ-13146 | HT - HALO TRUST | H/6432 | 2015 | 69.698 | 36.5694 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-05-08 | 2013-06-12 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 59 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-09-04 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b701698-6a30c136-dd2e-e | MF-HQ-11986 | HT - HALO TRUST | H/6374 | 22490 | 69.7318 | 36.5758 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-11-01 | 2014-05-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 18 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-15 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b710f94-a8619c68-e8f2-9 | MF-HQ-11927 | HT - HALO TRUST | H/6075 | 25360 | 69.7076 | 36.6166 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-06-10 | 2013-11-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 50 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-06 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b711eb0-ca2db632-e9a8-1 | MF-HQ-13549 | HT - HALO TRUST | H/6440 | 5000 | 69.7294 | 36.568 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-06-05 | 2013-06-10 | 1392 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 12 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-09-30 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b7158d2-6a680ed4-ec67-2 | MF-HQ-12402 | HT - HALO TRUST | H/6391 | 2560 | 69.7354 | 36.5802 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-11-01 | 2013-11-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 16 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-12 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b725ae2-2cf52b49-f8a7-5 | MF-HQ-12394 | HT - HALO TRUST | H/6388 | 53560 | 69.7288 | 36.558 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-06-08 | 2014-07-31 | 1393 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  | High Requested | Resettlment/Local Request | Minimal | 18 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-09 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b72bbd5-f26c2ac7-fd3f-9 | MF-HQ-11922 | HT - HALO TRUST | H/6074 | 35840 | 69.7082 | 36.6155 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-07-01 | 2013-07-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 22 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-05 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b738690-91c04050-106b9- | MF-HQ-13144 | HT - HALO TRUST | H/6399 | 3070 | 69.7112 | 36.5833 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  | High Requested | Resettlment/Local Request | Minimal | 99 | CHA | 4 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-09-01 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b73e6d8-b7687c5e-10b4e- | MF-HQ-12380 | HT - HALO TRUST | H/6381 | 415 | 69.6977 | 36.5662 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-06-02 | 2013-06-21 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 26 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-01 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b743f04-50cd02a5-10f6a- | MF-HQ-13195 | HT - HALO TRUST | H/6438 | 4950 | 69.7291 | 36.571 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes |  |  | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 12 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-09-10 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b747d99-33910623-11245- | MF-HQ-12405 | HT - HALO TRUST | H/6392 | 6220 | 69.7368 | 36.5789 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-11-01 | 2013-11-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 16 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-13 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b74f9a9-7ca6b341-11815- | MF-HQ-11992 | HT - HALO TRUST | H/6376 | 11700 | 69.7222 | 36.5762 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-10-01 | 2013-10-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 6 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-17 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b75e79d-39770d54-12304- | MF-HQ-11988 | HT - HALO TRUST | H/6375 | 5780 | 69.7217 | 36.5764 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-10-01 | 2013-10-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 6 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-16 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b762058-455db4ad-1259e- | MF-HQ-11994 | HT - HALO TRUST | H/6073 | 8600 | 69.7067 | 36.6192 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-09-01 | 2013-12-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 50 | CHA | 5 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-04 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b76381c-b0706aff-126bc- | MF-HQ-13145 | HT - HALO TRUST | H/6431 | 2440 | 69.7002 | 36.5703 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-05-03 | 2013-05-19 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 561 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-09-03 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b768b98-48a14120-12a9f- | MF-HQ-12388 | HT - HALO TRUST | H/6387 | 65340 | 69.7388 | 36.5553 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | Based on HALO Trust e-mail recieved on 28 June 2012, as per the ee-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet) the hazard removed from | High Requested | Resettlment/Local Request | Minimal | 29 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-08 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b76b297-1d90b608-12c6a- | MF-HQ-11909 | HT - HALO TRUST | H/6078 | 1680 | 69.7189 | 36.5975 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-06-19 | 2013-07-20 | 1392 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | , |  |  | Minimal | 45 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-09 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b778619-2cff6971-135f9- | MF-HQ-11998 | HT - HALO TRUST | H/6371 | 3690 | 69.7248 | 36.5823 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-10-01 | 2013-10-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 6 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-12 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b77a2ec-219a5c78-13752- | MF-HQ-12385 | HT - HALO TRUST | H/6385 | 43560 | 69.7353 | 36.5621 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-09-22 | 2013-10-24 | 1392 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 4 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-06 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b77a81a-425a037c-1378c- | MF-HQ-12407 | HT - HALO TRUST | H/6393 | 2120 | 69.7332 | 36.577 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-10-01 | 2013-10-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 16 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-14 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b77e8f0-a8b53973-13a77- | MF-HQ-12413 | HT - HALO TRUST | H/6394 | 23600 | 69.7391 | 36.5726 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-10-01 | 2013-11-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 18 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-15 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b782f9f-2ccc47e2-13db3- | MF-HQ-11919 | HT - HALO TRUST | H/6076 | 10175 | 69.7174 | 36.5981 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-06-09 | 2013-07-18 | 1392 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 55 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-07 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b7975ee-7c4af8e8-14ca4- | MF-HQ-12383 | HT - HALO TRUST | H/6380 | 7460 | 69.6972 | 36.5658 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-06-03 | 2013-07-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 26 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-08-02 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b79b731-4d92856f-14f7f- | MF-HQ-11985 | HT - HALO TRUST | H/6372 | 29600 | 69.7239 | 36.5796 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-12-01 | 2013-12-01 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 12 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-13 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b79d165-b074e6d9-150b8- | MF-HQ-13191 | HT - HALO TRUST | H/6400 | 16130 | 69.7189 | 36.5724 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-05-08 | 2013-05-23 | 1392 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 11 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-09-02 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b7a011c-34524819-152d9- | MF-HQ-11915 | HT - HALO TRUST | H/6377 | 34230 | 69.7151 | 36.5734 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2013-05-08 | 2013-05-24 | 1392 | MDC | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 47 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-18 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b7a2158-1bc12e66-15456- | MF-HQ-13163 | HT - HALO TRUST | H/6436 | 12230 | 69.6848 | 36.5775 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-12-01 | 2013-12-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 31 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-09-08 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-0057-12c3b7a8d71-abf88ec3-1593a- | MF-HQ-11984 | HT - HALO TRUST | H/6373 | 4930 | 69.7301 | 36.5772 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-10-01 | 2013-10-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 6 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-14 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-008e-1306d6e323d-75637c64-523-ea | MF-HQ-13151 | HT - HALO TRUST | H/6434 | 2410 | 69.6944 | 36.571 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-05-03 | 2013-05-22 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 59 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-09-06 | No | Planned
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-008e-1306d6ef132-eb499b3c-53c-ee | MF-HQ-11980 | HT - HALO TRUST | H/6378 | 17560 | 69.7226 | 36.5687 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-10-01 | 2013-11-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 11 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-19 | No | Complete
North East | Takhar | Namak Ab | Tutak | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} | c0a8-008e-1306d7c0847-4d0080a4-5d6-f5 | MF-HT-186 | HT - HALO TRUST | H/3582 | 6770 | 69.7108 | 36.5968 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-06-01 | 2013-11-23 | 1392-1393 | HT | {BC1ABFE0-4627-4EBD-AAA3-D47ABCF94BDF} |  |  |  | Minimal | 25 | CHA | 1 | Yes | Priority of the tasks are high and local pepeople requested always but some tasks of these lest are very remote. | 2009-07-09 | No | Planned
North East | Takhar | Rustaq | Dasht-I-Amani | {7AFF013F-FE97-4D75-96FB-4E4EACC21CAC} | c0a8-0009-13dc44b75c0-c3e11aeb-1053-8 | MF-HT-353 | HT - HALO TRUST | H/2182 | 34000 | 70.1249 | 37.0524 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-08-25 | 2013-09-17 | 1392 | MDC | {7AFF013F-FE97-4D75-96FB-4E4EACC21CAC} |  |  |  | Minimal | 73 | CHA | 5 | Yes |  | 2010-10-02 16:30 | No | Complete
North East | Takhar | Rustaq | Dasht-I-Amani | {7AFF013F-FE97-4D75-96FB-4E4EACC21CAC} | c0a8-008e-132c92c316e-69275c5b-2b6a-e | MF-15375 | HT - HALO TRUST | H/7347 | 50160 | 70.1249 | 37.0524 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-08-24 | 2013-09-12 | 1392 | MDC | {7AFF013F-FE97-4D75-96FB-4E4EACC21CAC} |  |  |  | Minimal | 76 | CHA | 4 | Yes |  | 2010-10-04 16:30 | No | Complete
North East | Takhar | Rustaq | Dasht-I-Amani | {7AFF013F-FE97-4D75-96FB-4E4EACC21CAC} | c0a8-008e-132c94a70aa-eae33dbe-2e64-8 | MF-15425 | HT - HALO TRUST | H/7346 | 31370 | 70.1299 | 37.0524 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-09-14 | 2013-10-05 | 1392 | MDC | {7AFF013F-FE97-4D75-96FB-4E4EACC21CAC} |  |  |  | Minimal | 138 | CHA | 5 | Yes |  | 2010-10-03 16:30 | No | Complete
North East | Takhar | Rustaq | Dasht-i-Chenar(1) | {61B64B22-C4CC-4177-B337-A6E8F22793AD} | c0a8-0057-12c3b7df85b-6c565c2a-18089- | MF-HQ-13927 | MCPA - Mine Clearance Planning Agency | AF/1208/12494/MF0015 | 76189 | 69.9812 | 37.0376 | Closed | AP Only | AP Only | MineField | 1391/1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2012-08-01 | 2013-07-23 | 1392-1393 | HT | {61B64B22-C4CC-4177-B337-A6E8F22793AD} |  |  |  | Minimal | 2 | CHA | 2 | Yes | Priority of the tasks are high and also these tasks have located between two villages (Dashte Chenar and Khwaja Khayrab)and local people have requested several times for clearance of the MFs for us because more accident happened on there but the clearanc | 2009-12-26 | No | Planned
North East | Takhar | Rustaq | Dasht-i-Chenar(1) | {61B64B22-C4CC-4177-B337-A6E8F22793AD} | c0a8-0057-12c3b949842-c3b00090-27992- | MF-HQ-10395 | HT - HALO TRUST | AF/1208/12494/MF6049 | 84500 | 69.964 | 37.028 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2013-09-17 | 2013-11-19 | 1392 | MDC | {61B64B22-C4CC-4177-B337-A6E8F22793AD} |  |  |  | Minimal | 0 | CHA | 1 | Yes | Priority of the tasks are high and also these tasks have located between two villages (Dashte Chenar and Khwaja Khayrab)and local people have requested several times for clearance of the MFs for us because more accident happened on there but the clearanc | 2009-04-18 | No | Complete
North East | Takhar | Rustaq | Dasht-i-Chenar(1) | {61B64B22-C4CC-4177-B337-A6E8F22793AD} | c0a8-0057-12c3b949bfa-7a832f49-279c7- | MF-HQ-10394 | HT - HALO TRUST | H/6050 | 71280 | 69.964 | 37.028 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2013-11-20 | 2014-01-13 | 1392 | MDC | {61B64B22-C4CC-4177-B337-A6E8F22793AD} |  |  |  | Minimal | 4 | CHA | 1 | Yes | Priority of the tasks are high and also these tasks have located between two villages (Dashte Chenar and Khwaja Khayrab)and local people have requested several times for clearance of the MFs for us because more accident happened on there but the clearanc | 2009-04-19 | No | Complete
North East | Takhar | Rustaq | Dasht-i-Chenar(1) | {61B64B22-C4CC-4177-B337-A6E8F22793AD} | c0a8-00f6-13538494d56-dd605db0-1ed-ca | MF-16621 | HT - HALO TRUST | H/8216 | 58500 | 69.9763 | 37.0311 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2013-06-04 | 2013-07-27 | 1392 | MDC | {61B64B22-C4CC-4177-B337-A6E8F22793AD} |  |  |  | Minimal | 1 | CHA | 1 | Yes | Priority of the tasks are high and also these tasks have located between two villages (Dashte Chenar and Khwaja Khayrab)and local people have requested several times for clearance of the MFs for us because more accident happened on there but the clearanc | 2011-08-14 16:30 | No | Complete
North East | Takhar | Rustaq | Dasht-i-Chenar(1) | {61B64B22-C4CC-4177-B337-A6E8F22793AD} | c0a8-00f6-1353c9118a6-8a5021c3-142d-f | MF-16622 | HT - HALO TRUST | H/8217 | 45320 | 69.9814 | 37.0304 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2013-09-03 | 2013-11-15 | 1392 | MDC | {61B64B22-C4CC-4177-B337-A6E8F22793AD} |  |  |  | Minimal | 1 | CHA | 1 | Yes | Priority of the tasks are high and also these tasks have located between two villages (Dashte Chenar and Khwaja Khayrab)and local people have requested several times for clearance of the MFs for us because more accident happened on there but the clearanc | 2011-08-15 16:30 | No | Complete
North East | Takhar | Rustaq | Dasht-i-Chenar(1) | {61B64B22-C4CC-4177-B337-A6E8F22793AD} | c0a8-00f6-1357b87644c-90709e96-3c44-9 | MF-16693 | HT - HALO TRUST | H/8219 | 2035 | 69.9828 | 37.0332 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2013-07-25 | 2013-07-26 | 1392 | MDC | {61B64B22-C4CC-4177-B337-A6E8F22793AD} |  |  |  | Minimal | 0 | CHA | 2 |  |  | 2011-08-16 16:30 | No | Complete
North East | Takhar | Rustaq | Dasht-i-Chenar(1) | {61B64B22-C4CC-4177-B337-A6E8F22793AD} | c0a8-00f6-137fdec6de6-20f3ec7b-a2-6a1 | Hz-ID-17014 | HT - HALO TRUST | H/8218 | 42460 | 69.9691 | 37.033 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2013-06-13 | 2013-07-24 | 1392 | MDC | {61B64B22-C4CC-4177-B337-A6E8F22793AD} |  |  |  | Minimal | 0 | CHA | 1 | Yes | Priority of the tasks are high and also these tasks have located between two villages (Dashte Chenar and Khwaja Khayrab)and local people have requested several times for clearance of the MFs for us because more accident happened on there but the clearanc | 2011-08-15 16:30 | No | Complete
North East | Takhar | Rustaq | Ganj | {797323E4-969C-4902-BF25-6A7173684C04} | c0a8-0057-12c3bafab35-4ec2069-38506-4 | MF-HT-428 | HT - HALO TRUST | H/2964 | 104257 | 69.9744 | 37.0577 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes |  |  | 1392 | MDC | {797323E4-969C-4902-BF25-6A7173684C04} |  |  |  | Minimal | 0 | CHA | 2 |  |  | 2010-11-09 16:30 | No | Complete
North East | Takhar | Rustaq | Kezer | {EDF212E5-73BF-44B4-927A-D07748882D5E} | c0a8-0057-12c3bafaf98-62b3e866-3852c- | MF-HQ-10264 | HT - HALO TRUST | H/6041 | 84580 | 69.9712 | 37.1164 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-08-02 | 2013-08-30 | 1392 | MDC | {EDF212E5-73BF-44B4-927A-D07748882D5E} |  |  |  | Minimal | 10 | CHA | 5 | Yes |  | 2009-04-10 | No | Complete
North East | Takhar | Rustaq | Kezer | {EDF212E5-73BF-44B4-927A-D07748882D5E} | c0a8-0057-12c3bafb1ba-c40860be-38548- | MF-HQ-10407 | HT - HALO TRUST | H/6042 | 97400 | 69.9706 | 37.1174 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {EDF212E5-73BF-44B4-927A-D07748882D5E} |  |  |  | Minimal | 6 | CHA | 5 | Yes |  | 2009-04-09 | Yes | Complete
North East | Takhar | Rustaq | Kezer | {EDF212E5-73BF-44B4-927A-D07748882D5E} | c0a8-0057-12c3bafb3cc-e54074e9-38563- | MF-HQ-10405 | HT - HALO TRUST | H/6043 | 95340 | 69.9694 | 37.1193 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {EDF212E5-73BF-44B4-927A-D07748882D5E} |  |  |  | Minimal | 6 | CHA | 5 | Yes |  | 2009-04-11 | Yes | Complete
North East | Takhar | Rustaq | Khvajeh Khayr Ab | {2239F8A5-F64A-46F5-B87B-7FBB8F55AE54} | c0a8-0057-12c3b949a16-818600ee-279ac- | MF-HQ-10401 | HT - HALO TRUST | H/6045 | 41492 | 69.9544 | 37.0396 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-09 | 2013-09-02 | 1392 | MDC | {2239F8A5-F64A-46F5-B87B-7FBB8F55AE54} |  |  |  | Minimal | 1 | CHA | 1 | Yes | Priority of the tasks are high and also these tasks have located between two villages (Dashte Chenar and Khwaja Khayrab)and local people have requested several times for clearance of the MFs for us because more accident happened on there but the clearanc | 2009-04-14 | No | Complete
North East | Takhar | Rustaq | Khvajeh Khayr Ab | {2239F8A5-F64A-46F5-B87B-7FBB8F55AE54} | c0a8-0057-12c3b949ded-f03385b2-279e2- | MF-HQ-10397 | HT - HALO TRUST | H/6047 | 39600 | 69.9544 | 37.0396 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-08-18 | 2013-09-18 | 1392 | MDC | {2239F8A5-F64A-46F5-B87B-7FBB8F55AE54} |  |  |  | Minimal | 0 | CHA | 1 | Yes | Priority of the tasks are high and also these tasks have located between two villages (Dashte Chenar and Khwaja Khayrab)and local people have requested several times for clearance of the MFs for us because more accident happened on there but the clearanc | 2009-04-16 | No | Complete
North East | Takhar | Rustaq | Khvajeh Khayr Ab | {2239F8A5-F64A-46F5-B87B-7FBB8F55AE54} | c0a8-0057-12c3b949fd0-c1db96dd-279fc- | MF-HQ-10244 | HT - HALO TRUST | H/6046 | 43000 | 69.9544 | 37.0396 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-01 | 2013-07-30 | 1392 | MDC | {2239F8A5-F64A-46F5-B87B-7FBB8F55AE54} |  |  |  | Minimal | 0 | CHA | 1 | Yes | Priority of the tasks are high and also these tasks have located between two villages (Dashte Chenar and Khwaja Khayrab)and local people have requested several times for clearance of the MFs for us because more accident happened on there but the clearanc | 2009-04-15 | No | Complete
North East | Takhar | Rustaq | Khvajeh Khayr Ab | {2239F8A5-F64A-46F5-B87B-7FBB8F55AE54} | c0a8-0057-12c3b94a3b7-49c832bc-27a17- | MF-HQ-10245 | HT - HALO TRUST | H/6048 | 76690 | 69.9544 | 37.0396 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-09-03 | 2013-10-31 | 1392 | MDC | {2239F8A5-F64A-46F5-B87B-7FBB8F55AE54} |  |  |  | Minimal | 4 | CHA | 1 | Yes | Priority of the tasks are high and also these tasks have located between two villages (Dashte Chenar and Khwaja Khayrab)and local people have requested several times for clearance of the MFs for us because more accident happened on there but the clearanc | 2009-04-17 | No | Complete
North East | Takhar | Rustaq | Khvajeh Khayr Ab | {2239F8A5-F64A-46F5-B87B-7FBB8F55AE54} | c0a8-0057-12c3b94a6b3-506eed01-27a33- | MF-HQ-10402 | HT - HALO TRUST | H/6044 | 46200 | 69.9544 | 37.0396 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-07-08 | 2013-07-13 | 1392 | MDC | {2239F8A5-F64A-46F5-B87B-7FBB8F55AE54} |  |  |  | Minimal | 1 | CHA | 1 | Yes | Priority of the tasks are high and also these tasks have located between two villages (Dashte Chenar and Khwaja Khayrab)and local people have requested several times for clearance of the MFs for us because more accident happened on there but the clearanc | 2009-04-13 | No | Complete
North East | Takhar | Rustaq | Marghak | {4A64CA17-06A0-467B-BE00-C14F610865E4} | c0a8-0009-14222b15361-f7051e53-19d4-c | Hz-ID-18186 | HT - HALO TRUST | B/3103 | 38 | 69.6681 | 37.0059 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes |  |  | 1392-1393 | HT | {4A64CA17-06A0-467B-BE00-C14F610865E4} |  |  |  | Minimal | 172 | CHA | 4 |  |  | 2013-09-10 16:30 | No | Planned
North East | Takhar | Rustaq | Marghak | {4A64CA17-06A0-467B-BE00-C14F610865E4} | c0a8-0009-14222b20f7e-236bb864-19f0-e | Hz-ID-18187 | HT - HALO TRUST | B/3108 | 70 | 69.6681 | 37.0057 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes |  |  | 1392-1393 | HT | {4A64CA17-06A0-467B-BE00-C14F610865E4} |  |  |  | Minimal | 172 | CHA | 5 |  |  | 2013-09-11 16:30 | No | Planned
North East | Takhar | Rustaq | Shakh Salman | {BC82D6E1-B465-4295-92ED-D7E472E84DB4} | c0a8-0009-14222b249bf-f045ff2e-1a08-c | Hz-ID-18188 | HT - HALO TRUST | B/3109 | 65 | 69.6682 | 37.0054 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes |  |  | 1392-1393 | HT | {BC82D6E1-B465-4295-92ED-D7E472E84DB4} |  |  |  | Minimal | 172 | CHA | 4 |  |  | 2013-09-10 16:30 | No | Planned
North East | Takhar | Rustaq | Tuti | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} | c0a8-0057-12c3b7ba4d5-7930dee1-165a2- | MF-HQ-11571 | HT - HALO TRUST | H/5848 | 105100 | 70.0625 | 37.0005 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2013-11-26 | 2014-02-08 | 1392 | MDC | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} |  |  |  | Minimal | 15 | CHA | 3 | Yes |  | 2009-03-06 | No | Complete
North East | Takhar | Rustaq | Tuti | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} | c0a8-0057-12c3b7ba716-67d11399-165b7- | MF-HQ-11626 | HT - HALO TRUST | H/5844 | 105000 | 70.0726 | 36.9926 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes |  |  | 1392 | MDC | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} |  |  |  | Minimal | 22 | CHA | 5 | Yes |  | 2009-03-10 | No | Complete
North East | Takhar | Rustaq | Tuti | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} | c0a8-0057-12c3b7ba8bb-5bc2bcc1-165cd- | MF-HQ-11573 | HT - HALO TRUST | H/5846 | 120750 | 70.0646 | 36.993 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-09-01 | 2013-12-12 | 1392 | MDC | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} |  |  |  | Minimal | 17 | CHA | 5 | Yes |  | 2009-03-08 | No | Complete
North East | Takhar | Rustaq | Tuti | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} | c0a8-0057-12c3b7baa80-2d89d769-165e3- | MF-HQ-11577 | HT - HALO TRUST | H/5845 | 129150 | 70.0646 | 36.993 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-09-01 | 2013-11-30 | 1392 | MDC | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} |  |  |  | Minimal | 17 | CHA | 5 | Yes |  | 2009-03-09 | No | Complete
North East | Takhar | Rustaq | Tuti | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} | c0a8-0057-12c3b7bac54-79a70c48-165f9- | MF-HQ-11568 | HT - HALO TRUST | H/5849 | 131250 | 70.0726 | 36.9926 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-10-06 | 2013-12-25 | 1392 | MDC | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} |  |  |  | Minimal | 49 | CHA | 5 | Yes |  | 2009-03-05 | No | Complete
North East | Takhar | Rustaq | Tuti | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} | c0a8-0057-12c3b7badda-7898fcdd-16610- | MF-HQ-11578 | HT - HALO TRUST | H/5847 | 120620 | 70.0625 | 37.0005 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-035 | Takhar Demining Project-06 | DOS | Yes | 2013-11-12 | 2014-02-25 | 1392 | MDC | {ACA8F093-2452-4D05-B5DD-AF9CECB09A95} |  |  |  | Minimal | 3 | CHA | 3 | Yes |  | 2009-03-07 | No | Complete
North East | Takhar | Rustaq | Yal Ka Shan | {1D340EF5-77E4-4207-9209-57B0F83683C7} | c0a8-0009-13fdc6b125f-6b6ed47d-264c-9 | Hz-ID-18041 | HT - HALO TRUST | H/8558 | 65206 | 69.9829 | 37.0513 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-06-08 | 2014-07-15 | 1393 | MDC | {1D340EF5-77E4-4207-9209-57B0F83683C7} |  |  |  | Minimal | 8 | CHA | 5 |  |  | 2013-06-17 16:30 | No | Planned
North East | Takhar | Rustaq | Yal Ka Shan | {1D340EF5-77E4-4207-9209-57B0F83683C7} | c0a8-0009-13fdc6b8d76-21bf72e0-2668-b | Hz-ID-18040 | HT - HALO TRUST | H/8557 | 39869 | 69.9829 | 37.0513 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-05-01 | 2014-05-20 | 1393 | MDC | {1D340EF5-77E4-4207-9209-57B0F83683C7} |  |  |  | Minimal | 17 | CHA | 5 |  |  | 2013-06-17 16:30 | No | Planned
North East | Takhar | Rustaq | Yal Ka Shan | {1D340EF5-77E4-4207-9209-57B0F83683C7} | c0a8-0009-13fdc6c19bd-28f93ec3-2689-6 | Hz-ID-18039 | HT - HALO TRUST | H/8556 | 46965 | 69.9829 | 37.0513 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-03-16 | 2014-04-19 | 1393 | MDC | {1D340EF5-77E4-4207-9209-57B0F83683C7} |  |  |  | Minimal | 17 | CHA | 5 |  |  | 2013-06-16 16:30 | No | Planned
North East | Takhar | Rustaq | Zaribay | {A3F8A101-3402-4DAD-A4E1-34A0A98A7863} | c0a8-0009-13f99d6cace-961e56bd-14dd-1 | Hz-ID-17917 | HT - HALO TRUST | H/8474 | 9220 | 69.9763 | 37.0359 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/A | Takhar Demining Project-02/A | Bilateral | Yes | 2013-07-01 | 2013-07-23 | 1392-1393 | HT | {A3F8A101-3402-4DAD-A4E1-34A0A98A7863} |  |  |  | Minimal | 0 | CHA | 5 |  |  | 2013-04-19 16:30 | No | Planned
North East | Takhar | Taluqan | Abdul | {28D37D31-D4BE-4FBD-8E01-7BFA6D870FCA} | c0a8-008e-132c476e76f-e6d0af46-127b-d | MF-15899 | HT - HALO TRUST | H/7320 | 2060 | 69.465 | 36.7486 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-097 | Takhar Demining Project-2 (AT) | DOS | Yes | 2014-02-25 | 2014-02-28 | 1392 | MDC | {28D37D31-D4BE-4FBD-8E01-7BFA6D870FCA} |  |  |  | Low | 2497 | CHA | 3 | Yes |  | 2011-05-04 16:30 | No | Complete
North East | Takhar | Taluqan | Aqjar (Qorghez) | {69B118C7-9A23-4600-A363-6BE07FA9119E} | c0a8-00c9-12fde4b322b-3530b429-136-ce | MF-NE-972 | HT - HALO TRUST | H/5897 | 11812 | 69.7892 | 36.6674 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-03-12 | 2014-03-26 | 1393 | MDC | {69B118C7-9A23-4600-A363-6BE07FA9119E} |  |  |  | Low | 4 | CHA | 5 |  |  | 2008-11-29 | No | Planned
North East | Takhar | Taluqan | Aqjar (Qorghez) | {69B118C7-9A23-4600-A363-6BE07FA9119E} | c0a8-00c9-12fde6773c8-fcf502c8-211-54 | MF-HT-399 | HT - HALO TRUST | H/2938 | 8450 | 69.7852 | 36.6842 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {69B118C7-9A23-4600-A363-6BE07FA9119E} |  | High Requested | Resettlment/Local Request | Low | 2 | CHA | 5 | Yes |  | 2007-03-01 | No | Planned
North East | Takhar | Taluqan | Aqmasjed (1) | {8E111E52-D921-43DE-B94D-18FA99D8EF4F} | c0a8-0009-13c18e0d9e2-88abe0f7-1161-6 | Hz-ID-17565 | MDC - Mine Detection and Dog Center | AF/1201/12321/MF8439 | 42043 | 69.4524 | 36.7044 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-05-12 | 2013-06-30 | 1392 | MDC | {8E111E52-D921-43DE-B94D-18FA99D8EF4F} |  |  |  | Low | 30 | CHA | 1 |  |  | 2012-12-10 16:30 | No | Complete
North East | Takhar | Taluqan | Aqmasjed (2) | {5800EBCA-A731-4A73-8D6B-1484C95268D4} | c0a8-00f6-13532535ef5-ebff0fee-458-13 | MF-16575 | HT - HALO TRUST | H/8226 | 5964 | 69.4324 | 36.7121 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {5800EBCA-A731-4A73-8D6B-1484C95268D4} |  | High Requested | Resettlment/Local Request | Low | 111 | CHA | 5 | Yes |  | 2011-12-17 16:30 | No | Planned
North East | Takhar | Taluqan | Chashma Sher (2) | {626877E2-5328-491E-B59C-8AE04C21AC38} | c0a8-0009-13ec17a704e-2b3655b2-204e-9 | Hz-ID-17923 | HT - HALO TRUST | H/8463 | 553 | 69.4409 | 36.7175 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes | 2014-08-01 | 2014-08-23 | 1393 | HT | {626877E2-5328-491E-B59C-8AE04C21AC38} |  | Medium | Agriculture Blocked | Low | 421 | CHA | 3 |  |  | 2013-04-02 16:30 | No | Planned
North East | Takhar | Taluqan | Chashma Sher (2) | {626877E2-5328-491E-B59C-8AE04C21AC38} | c0a8-0009-13ec192b78a-73f7bc7a-2068-a | Hz-ID-17922 | HT - HALO TRUST | H/8464 | 573 | 69.4434 | 36.7208 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes | 2014-07-01 | 2014-07-23 | 1393 | HT | {626877E2-5328-491E-B59C-8AE04C21AC38} |  | Medium | Critical Infrastracture | Low | 281 | CHA | 3 |  |  | 2013-04-04 16:30 | No | Planned
North East | Takhar | Taluqan | Chin Za'i (1) | {F059C31C-5E59-45CD-8078-E1E2F436D642} | c0a8-0057-12c3b7241e6-7078cf1c-f76f-f | MF-HQ-11589 | HT - HALO TRUST | H/5823 | 25200 | 69.2602 | 36.7232 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-04-21 | 2013-05-12 | 1392 | MDC | {F059C31C-5E59-45CD-8078-E1E2F436D642} | Removed from HT 1390 plan |  |  | Low | 92 | CHA | 4 | Yes |  | 2008-12-04 | No | Complete
North East | Takhar | Taluqan | Chin Za'i (1) | {F059C31C-5E59-45CD-8078-E1E2F436D642} | c0a8-0057-12c3ba320b2-d7a70c9f-30d65- | MF-HT-207 | HT - HALO TRUST | H/3602 | 11500 | 69.269 | 36.7321 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-04-16 | 2013-04-28 | 1392 | MDC | {F059C31C-5E59-45CD-8078-E1E2F436D642} |  |  |  | Low | 322 | CHA | 1 | Yes | Priority of the tasks are high and local People requested many times but the area is insecure | 2007-07-31 | No | Complete
North East | Takhar | Taluqan | Chin Za'i (1) | {F059C31C-5E59-45CD-8078-E1E2F436D642} | c0a8-0057-12c3ba3239f-1d6c519d-30d8e- | MF-HT-209 | HT - HALO TRUST | H/3604 | 40500 | 69.269 | 36.7321 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-036 | Takhar Demining Project-08 | B-Germany | Yes | 2013-03-01 | 2013-04-15 | 1392 | MDC | {F059C31C-5E59-45CD-8078-E1E2F436D642} |  |  |  | Low | 325 | CHA | 4 | Yes |  | 2007-07-01 | No | Complete
North East | Takhar | Taluqan | Darina (2) | {0B415D79-411B-4F60-9DDA-BB8C3417ADD3} | c0a8-0009-13c18b62ddd-99733b99-d0c-d2 | Hz-ID-17562 | HT - HALO TRUST | H/8416 | 50550 | 69.698 | 36.8452 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {0B415D79-411B-4F60-9DDA-BB8C3417ADD3} |  | High Requested | Resettlment/Local Request | Low | 73 | CHA | 4 | Yes |  | 2012-12-02 16:30 | No | Planned
North East | Takhar | Taluqan | Darina (2) | {0B415D79-411B-4F60-9DDA-BB8C3417ADD3} | c0a8-0009-13c18bba107-6a15360a-d67-9d | Hz-ID-17561 | HT - HALO TRUST | H/8285 | 21200 | 69.6934 | 36.8448 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {0B415D79-411B-4F60-9DDA-BB8C3417ADD3} |  | High Requested | Resettlment/Local Request | Low | 57 | CHA | 5 | Yes |  | 2012-12-02 16:30 | No | Planned
North East | Takhar | Taluqan | Gazestan (2) | {F41090F7-ED23-428A-A0EC-0A16E6B91753} | c0a8-0009-13df3969ad6-c3ef8f80-14a1-d | Hz-ID-17801 | HT - HALO TRUST | H/8462 | 30370 | 69.7484 | 36.6563 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {F41090F7-ED23-428A-A0EC-0A16E6B91753} |  | Low | Agriculture Blocked | Low | 7 | CHA | 5 |  |  | 2013-03-13 16:30 | No | Planned
North East | Takhar | Taluqan | Gazestan (2) | {F41090F7-ED23-428A-A0EC-0A16E6B91753} | c0a8-0009-13f2d02052e-c7e24872-5aa0-c | Hz-ID-17924 | HT - HALO TRUST | H/8452 | 2300 | 69.7749 | 36.6869 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {F41090F7-ED23-428A-A0EC-0A16E6B91753} |  | Low | Agriculture Blocked | Low | 2 | CHA | 5 |  |  | 2013-04-05 16:30 | No | Planned
North East | Takhar | Taluqan | Gazestan (2) | {F41090F7-ED23-428A-A0EC-0A16E6B91753} | c0a8-008e-132c95e5638-9bcc3ffa-3260-d | MF-15576 | HT - HALO TRUST | H/7348 | 2500 | 69.766 | 36.6669 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {F41090F7-ED23-428A-A0EC-0A16E6B91753} |  | High Requested | Resettlment/Local Request | Low | 2 | CHA | 5 | Yes |  | 2010-10-21 16:30 | No | Planned
North East | Takhar | Taluqan | Jar Qeshlaq (1) | {572AD9E3-5DCC-41A1-85C4-83913DAF33EB} | c0a8-0009-13c18c9b9ed-97f66e14-f93-15 | Hz-ID-17563 | HT - HALO TRUST | H/8433 | 11100 | 69.6377 | 36.8554 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {572AD9E3-5DCC-41A1-85C4-83913DAF33EB} |  | High Requested | Resettlment/Local Request | Low | 4 | CHA | 5 | Yes |  | 2012-12-07 16:30 | No | Planned
North East | Takhar | Taluqan | Jar Qeshlaq (1) | {572AD9E3-5DCC-41A1-85C4-83913DAF33EB} | c0a8-0009-13c18dc072b-f8a126d-10ec-b0 | Hz-ID-17564 | HT - HALO TRUST | H/8434 | 2600 | 69.6346 | 36.8568 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {572AD9E3-5DCC-41A1-85C4-83913DAF33EB} |  | High Requested | Resettlment/Local Request | Low | 21 | CHA | 5 | Yes |  | 2012-12-08 16:30 | No | Planned
North East | Takhar | Taluqan | Jar Qeshlaq (2) | {DC3BEA91-13B6-4B90-88ED-5A25295E3C1E} | c0a8-0009-13c19b7778f-4cea670-6890-fe | Hz-ID-17567 | HT - HALO TRUST | H/8440 | 6200 | 69.6105 | 36.846 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {DC3BEA91-13B6-4B90-88ED-5A25295E3C1E} |  | High Requested | Resettlment/Local Request | Low | 13 | CHA | 5 | Yes |  | 2012-12-12 16:30 | No | Planned
North East | Takhar | Taluqan | Jar Qeshlaq (2) | {DC3BEA91-13B6-4B90-88ED-5A25295E3C1E} | c0a8-0009-13c1dc245e0-6d2249cc-7722-c | Hz-ID-17568 | HT - HALO TRUST | H/8441 | 4000 | 69.6105 | 36.846 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {DC3BEA91-13B6-4B90-88ED-5A25295E3C1E} |  | High Requested | Resettlment/Local Request | Low | 13 | CHA | 5 | Yes |  | 2012-12-12 16:30 | No | Planned
North East | Takhar | Taluqan | Khatayan | {2EF8AE20-E0EB-4599-A746-556A14375BE2} | c0a8-0057-12c3b855862-ec17beb9-1d42f- | MF-HT-352 | HT - HALO TRUST | H/2295 | 61696 | 69.7005 | 36.6723 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {2EF8AE20-E0EB-4599-A746-556A14375BE2} |  | High Requested | Resettlment/Local Request | Low | 14 | CHA | 5 | Yes |  | 2002-08-01 | No | Planned
North East | Takhar | Taluqan | Khoja Felankha | {FA0C4567-D53A-4FA0-B2AD-D5573D2E0398} | c0a8-008e-1320f3efd00-367aada9-bb-da4 | MF-HT-517 | HT - HALO TRUST | H/3632 | 42000 | 69.7445 | 36.7876 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {FA0C4567-D53A-4FA0-B2AD-D5573D2E0398} |  | High Requested | Resettlment/Local Request | Low | 4 | CHA | 5 | Yes |  | 2007-08-31 16:30 | No | Planned
North East | Takhar | Taluqan | Khwaja Khalil | {C9E25930-A9F4-4E83-9B8C-84C1004F34C9} | c0a8-0057-12c3ba8e153-cfe6791f-344f8- | MF-NE-856 | HT - HALO TRUST | H/4037 | 12500 | 69.7129 | 36.8172 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-085 | Takhar Demining Project-03 | DOS | Yes | 2014-05-01 | 2014-05-09 | 1393 | MDC | {C9E25930-A9F4-4E83-9B8C-84C1004F34C9} | Based on HALO Trust e-mail recieved on 28 June 2012, as per the statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet) the hazard removed from their pl |  |  | Low | 26 | CHA | 2 |  |  | 2007-11-18 | No | Planned
North East | Takhar | Taluqan | Khwaja Khalil | {C9E25930-A9F4-4E83-9B8C-84C1004F34C9} | c0a8-0057-12c3ba8ea29-c97b047a-34556- | MF-NE-857 | HT - HALO TRUST | H/4038 | 38000 | 69.7137 | 36.8137 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2014-03-18 | 2014-04-18 | 1392 | MDC | {C9E25930-A9F4-4E83-9B8C-84C1004F34C9} | Based on HALO Trust e-mail recieved on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet.) the hazard removed from |  |  | Low | 12 | CHA | 2 |  |  | 2007-11-18 | No | Complete
North East | Takhar | Taluqan | Lataband (1) | {12F39174-84C3-4F14-B7E8-82152D543061} | c0a8-0009-13c1dd6b21f-1b1f0d6c-77e6-6 | Hz-ID-17569 | HT - HALO TRUST | H/8451 | 31500 | 69.7485 | 36.7254 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {12F39174-84C3-4F14-B7E8-82152D543061} |  | High Requested | Resettlment/Local Request | Low | 2 | CHA | 5 | Yes |  | 2012-12-15 16:30 | No | Planned
North East | Takhar | Taluqan | Lataband (1) | {12F39174-84C3-4F14-B7E8-82152D543061} | c0a8-004c-1302a808e0c-b00fad59-122e-1 | MF-HT-583 | HT - HALO TRUST | H/3683 | 35294 | 69.7535 | 36.7069 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {12F39174-84C3-4F14-B7E8-82152D543061} |  | High Requested | Resettlment/Local Request | Low | 6 | CHA | 5 | Yes |  | 2009-10-16 | No | Planned
North East | Takhar | Taluqan | Qara Tash | {5C775FB1-0BB7-4FF5-9FD6-D215078A89F2} | c0a8-008e-1328a420730-f4b7824b-530-a7 | MF-15619 | HT - HALO TRUST | H/7421 | 54700 | 69.6901 | 36.8303 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {5C775FB1-0BB7-4FF5-9FD6-D215078A89F2} | Based on HALO Trust e-mail recieved on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet.) the hazard removed fro | High Requested | Resettlment/Local Request | Low | 43 | CHA | 5 | Yes |  | 2010-12-07 16:30 | No | Planned
North East | Takhar | Taluqan | Sah Mardan Beg | {CB460514-856B-4626-A916-508968DEE669} | c0a8-0009-1470a6c8018-ca9abe27-1417-a | Hz-ID-18794 | HT - HALO TRUST | H/8938 | 5786 | 69.5064 | 36.7392 | Open | AP Only | AP Only | MineField |  | MBT Project-085/A | Takhar Demining Project-03 |  |  |  |  | 1395 |  | {CB460514-856B-4626-A916-508968DEE669} |  | Medium | Critical Infrastracture | Low | 0 | CHA | 5 |  |  | 2014-04-13 16:30 | No | Open
North East | Takhar | Taluqan | Saray Zargar | {220A9D8F-D466-4E53-BE37-3E31EDE4F613} | c0a8-0009-13f0e7ed8af-1c56cf04-10bb-1 | Hz-ID-17949 | MCPA - Mine Clearance Planning Agency | AF/1201/12393/BF0031 | 12128 | 69.5627 | 36.73 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-125/B | Takhar Demining Project-02/B | DOS | Yes | 2013-07-01 | 2013-09-23 | 1392 | HT | {220A9D8F-D466-4E53-BE37-3E31EDE4F613} |  |  |  | Low | 1174 | CHA | 3 |  |  | 2013-05-28 16:30 | No | Complete
North East | Takhar | Taluqan | Shor Cha (3) | {9B4A6743-59BD-4D6C-BAE9-D379313C5D56} | c0a8-0009-13ec196410e-c90a74d4-20dd-c | Hz-ID-17921 | HT - HALO TRUST | H/8465 | 1940 | 69.4511 | 36.6588 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125 | Takhar Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {9B4A6743-59BD-4D6C-BAE9-D379313C5D56} |  | Low | Agriculture Blocked | Low | 0 | CHA | 5 |  |  | 2013-04-07 16:30 | No | Planned
North East | Takhar | Taluqan | Shor Cha (3) | {9B4A6743-59BD-4D6C-BAE9-D379313C5D56} | c0a8-0057-12c3ba134f2-63d41746-2fad2- | MF-HT-212 | HT - HALO TRUST | H/2905 | 33350 | 69.4537 | 36.6646 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-11-01 | 2013-12-23 | 1392-1393 | HT | {9B4A6743-59BD-4D6C-BAE9-D379313C5D56} |  |  |  | Low | 9 | CHA | 5 | Yes |  | 2007-07-31 | No | Complete
North East | Takhar | Taluqan | Shor Cha (3) | {9B4A6743-59BD-4D6C-BAE9-D379313C5D56} | c0a8-0057-12cbf09b743-9df166da-1ec8-6 | MF-HT-220 | HT - HALO TRUST | H/2904 | 10200 | 69.4614 | 36.6481 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-11-01 | 2013-11-23 | 1392-1393 | HT | {9B4A6743-59BD-4D6C-BAE9-D379313C5D56} |  |  |  | Low | 36 | CHA | 5 | Yes |  | 2010-10-10 16:30 | No | Complete
North East | Takhar | Taluqan | Shor Cha (3) | {9B4A6743-59BD-4D6C-BAE9-D379313C5D56} | c0a8-008e-1328fb7cf46-118eb36c-2536-6 | MF-15463 | HT - HALO TRUST | H/7410 | 4800 | 69.4455 | 36.6656 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-11-01 | 2013-11-23 | 1392-1393 | HT | {9B4A6743-59BD-4D6C-BAE9-D379313C5D56} |  |  |  | Low | 7 | CHA | 5 | Yes |  | 2010-11-12 16:30 | No | Complete
North East | Takhar | Taluqan | Taluk | {26AF6115-CEEC-4540-B651-61CE84E72F03} | c0a8-0057-12c3b70cb83-204365fb-e5c8-e | MF-HQ-14966 | HT - HALO TRUST | H/6692 | 10950 | 69.7639 | 36.7339 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-10-01 | 2013-10-23 | 1392-1393 | HT | {26AF6115-CEEC-4540-B651-61CE84E72F03} |  |  |  | Low | 34 | CHA | 5 | Yes |  | 2010-08-10 | No | Complete
North East | Takhar | Taluqan | Taluk | {26AF6115-CEEC-4540-B651-61CE84E72F03} | c0a8-008e-1328f8e4db6-45df8c2e-185a-7 | MF-15840 | HT - HALO TRUST | H/7463 | 54400 | 69.7545 | 36.7106 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-125/D | Takhar Demining Project-02/D | CIDA | Yes | 2013-10-01 | 2014-01-23 | 1392-1393 | HT | {26AF6115-CEEC-4540-B651-61CE84E72F03} |  |  |  | Low | 11 | CHA | 5 | Yes |  | 2011-01-05 16:30 | No | Complete
North East | Takhar | Taluqan | Taluk | {26AF6115-CEEC-4540-B651-61CE84E72F03} | c0a8-008e-1328f8e7947-2480a96c-1887-1 | MF-15841 | HT - HALO TRUST | H/7464 | 51700 | 69.7599 | 36.722 | Closed | AP Only | AP Only | MineField | 1392/1393 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2014-03-27 | 2014-05-20 | 1392 | MDC | {26AF6115-CEEC-4540-B651-61CE84E72F03} |  |  |  | Low | 18 | CHA | 3 | Yes |  | 2011-01-06 16:30 | No | Complete
North East | Takhar | Taluqan | Taluk | {26AF6115-CEEC-4540-B651-61CE84E72F03} | c0a8-008e-1328f91138a-c92a1b76-1a1a-7 | MF-15857 | HT - HALO TRUST | H/7430 | 33400 | 69.8028 | 36.7439 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125/F | Takhar Demining Project-02 /F | B-Germany | Yes |  |  | 1393 | HT | {26AF6115-CEEC-4540-B651-61CE84E72F03} | Based on HALO Trust e-mail recieved on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet) hazard removed from their | High Requested | Resettlment/Local Request | Low | 21 | CHA | 5 | Yes |  | 2011-01-01 16:30 | No | Planned
North East | Takhar | Taluqan | Taluk | {26AF6115-CEEC-4540-B651-61CE84E72F03} | c0a8-008e-1328f91461e-a85198fb-1a41-5 | MF-15858 | HT - HALO TRUST | H/7461 | 32700 | 69.804 | 36.7406 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-125/F | Takhar Demining Project-02 /F | B-Germany | Yes | 2014-09-01 |  | 1393 | HT | {26AF6115-CEEC-4540-B651-61CE84E72F03} | Based on HALO Trust e-mail recieved on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet.) the hazard removed from | High Requested | Resettlment/Local Request | Low | 15 | CHA | 5 | Yes |  | 2011-01-02 16:30 | No | Planned
North East | Takhar | Taluqan | Taluk | {26AF6115-CEEC-4540-B651-61CE84E72F03} | c0a8-008e-1328f917528-1ef54d16-1a77-a | MF-15859 | HT - HALO TRUST | H/7462 | 16800 | 69.8075 | 36.7475 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-125/F | Takhar Demining Project-02 /F | B-Germany | Yes |  |  | 1393 | HT | {26AF6115-CEEC-4540-B651-61CE84E72F03} | Based on HALO Trust e-mail recieved on 28 June 2012, as per the e-mail statement (Attached you can find a list of tasks to be added to HALO 1391 WP on 1st sheet and a list of tasks to be removed from HALO 1391 WP on second sheet.) the hazard removed form | High Requested | Resettlment/Local Request | Low | 6 | CHA | 5 | Yes |  | 2011-01-02 16:30 | No | Planned
North East | Takhar | Taluqan | Taluk | {26AF6115-CEEC-4540-B651-61CE84E72F03} | c0a8-00f6-1353c50b801-1fdda328-f60-31 | MF-16626 | HT - HALO TRUST | H/8244 | 38200 | 69.7579 | 36.7045 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-125/F | Takhar Demining Project-02 /F | B-Germany | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {26AF6115-CEEC-4540-B651-61CE84E72F03} |  | High Requested | Resettlment/Local Request | Low | 2 | CHA | 5 | Yes |  | 2011-09-11 16:30 | No | Planned
North East | Takhar | Taluqan | Taluk | {26AF6115-CEEC-4540-B651-61CE84E72F03} | c0a8-00f6-13552216d71-a04746ca-2f9-39 | MF-16658 | HT - HALO TRUST | H/8233 | 10800 | 69.7579 | 36.7045 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-125/F | Takhar Demining Project-02 /F | B-Germany | Yes | 2014-07-01 | 2014-08-23 | 1393 | HT | {26AF6115-CEEC-4540-B651-61CE84E72F03} |  | High Requested | Resettlment/Local Request | Low | 3 | CHA | 5 | Yes |  | 2011-09-13 16:30 | No | Planned
North East | Takhar | Taluqan | Taluk | {26AF6115-CEEC-4540-B651-61CE84E72F03} | c0a8-00f6-1355226baa2-7143e408-36e-c4 | MF-16655 | HT - HALO TRUST | H/8231 | 44900 | 69.7591 | 36.7067 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-125/F | Takhar Demining Project-02 /F | B-Germany | Yes | 2014-07-01 | 2014-08-23 | 1393 | HT | {26AF6115-CEEC-4540-B651-61CE84E72F03} |  | High Requested | Resettlment/Local Request | Low | 0 | CHA | 5 | Yes |  | 2011-09-11 16:30 | No | Planned
North East | Takhar | Taluqan | Taluk | {26AF6115-CEEC-4540-B651-61CE84E72F03} | c0a8-00f6-13552449c6c-c77e2ce7-573-e4 | MF-16656 | HT - HALO TRUST | H/8232 | 63100 | 69.7579 | 36.7088 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-125/F | Takhar Demining Project-02 /F | B-Germany | Yes |  |  | 1393 | HT | {26AF6115-CEEC-4540-B651-61CE84E72F03} |  | High Requested | Resettlment/Local Request | Low | 9 | CHA | 5 | Yes |  | 2011-09-12 16:30 | No | Planned
North East | Takhar | Taluqan | Taluqan | {174DFD63-F4D3-41AB-9503-0C22D7AACD48} | c0a8-008e-132c958984f-be1e6565-3107-3 | MF-15644 | HT - HALO TRUST | H/7424 | 1890 | 69.5003 | 36.7383 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-033 | Takhar Demining Project-01 | DOS | Yes | 2014-03-15 | 2014-03-17 | 1392 | MDC | {174DFD63-F4D3-41AB-9503-0C22D7AACD48} | , |  |  | Low | 1324 | CHA | 1 |  |  | 2010-12-12 16:30 | No | Complete
South | Hilmand | Garmser | Hazar Joft | {F7C577A6-4170-4D53-8C21-05CC9D523A33} | c0a8-0057-12c3b8e3542-831b1112-236d8- | MF-HQ-10572 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2312/20862/MF009 | 90000 | 64.2041 | 31.1575 | Open | Mixed | Mixed AT UXO | Converted From SHA |  | MBT Project-285 | Hilmand Demining Project-08 |  |  |  |  | 1398 |  | {F7C577A6-4170-4D53-8C21-05CC9D523A33} |  | High with Victim | High with Victims | High | 4 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Garmser | Hazar Joft | {F7C577A6-4170-4D53-8C21-05CC9D523A33} | c0a8-0057-12c3b992eb9-ea21a3a2-2a9d1- | MF-HQ-10573 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2312/20862/MF008 | 160000 | 64.2041 | 31.1575 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-285 | Hilmand Demining Project-08 |  |  |  |  | 1398 |  | {F7C577A6-4170-4D53-8C21-05CC9D523A33} |  | High with Victim | High with Victims | High | 4 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Garmser | Hazrat Jufti-I-Iulya | {5027063A-451A-435F-BCF7-30A5C16DE5E8} | c0a8-0057-12c3b9400cc-bb5408a8-27355- | MF-HQ-10542 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2312/00238/MF012 | 60000 | 64.2014 | 31.1679 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-285 | Hilmand Demining Project-08 |  |  |  |  | 1398 |  | {5027063A-451A-435F-BCF7-30A5C16DE5E8} |  | Low | Water Blocked | High | 6 | SHA | 5 |  |  | 2009-05-25 | No | Open
South | Hilmand | Garmser | Hazrat Jufti-I-Iulya | {5027063A-451A-435F-BCF7-30A5C16DE5E8} | c0a8-0057-12c3b9c7185-971fd8d-2cbf9-6 | MF-HQ-10543 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2312/00238/MF011 | 416000 | 64.2001 | 31.1872 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-285 | Hilmand Demining Project-08 |  |  |  |  | 1398 |  | {5027063A-451A-435F-BCF7-30A5C16DE5E8} |  | Low | Other | High | 74 | SHA | 4 |  |  | 2009-05-25 | No | Open
South | Hilmand | Garmser | Kertakah | {F4606184-0935-4C99-83CF-1F3077C57E6E} | c0a8-0057-12c3b93f529-bf72100c-272da- | MF-HQ-10584 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2312/20779/MF010 | 480000 | 64.09 | 30.8863 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-285 | Hilmand Demining Project-08 |  |  |  |  | 1398 |  | {F4606184-0935-4C99-83CF-1F3077C57E6E} |  | Low | Agriculture Blocked | High | 263 | SHA | 4 |  |  | 2009-05-25 | No | Open
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-13fc2d113d3-b35eac8a-9d-fa8 | Hz-ID-18007 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0073 | 97301 | 65.1038 | 32.3156 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2013-11-30 | 2014-04-30 | 1392-1393 | DAFA | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  |  |  | High | 24 | CHA | 2 |  |  | 2013-06-23 16:30 | No | Planned
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-13fc2d3ab8b-e99d58ac-c1-283 | Hz-ID-18008 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0074 | 97047 | 65.0987 | 32.3182 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2014-01-01 | 2014-03-31 | 1392-1393 | DAFA | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  |  |  | High | 25 | CHA | 2 |  |  | 2013-06-23 16:30 | No | Planned
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-13fc2d557b0-c1895377-e2-d11 | Hz-ID-18009 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0075 | 36432 | 65.1011 | 32.3115 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2013-06-22 | 2013-11-28 | 1392-1393 | DAFA | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  |  |  | High | 36 | CHA | 2 |  |  | 2013-06-23 16:30 | No | Planned
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-13fc2d78a14-d3ec247c-104-97 | Hz-ID-18010 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0076 | 87687 | 65.1011 | 32.3115 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2013-06-22 | 2013-12-31 | 1392-1393 | DAFA | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  |  |  | High | 25 | CHA | 2 |  |  | 2013-06-23 16:30 | No | Planned
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-13fc2d8df44-e34853c6-126-9d | Hz-ID-18011 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0077 | 68514 | 65.0937 | 32.3132 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2013-06-22 | 2014-01-31 | 1392-1393 | DAFA | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  |  |  | High | 25 | CHA | 2 |  |  | 2013-06-23 16:30 | No | Planned
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-13fc2da7d31-a774d3a0-15c-cd | Hz-ID-18012 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0078 | 92034 | 65.0941 | 32.318 | Closed | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2014-02-01 | 2014-05-31 | 1392-1393 | DAFA | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  |  |  | High | 42 | CHA | 2 |  |  | 2013-06-23 16:30 | No | Planned
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-14400d7cfc9-4abd3d0c-8cdf-a | Hz-ID-18421 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0086 | 137407 | 65.0987 | 32.317 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-164 | Hilmand Demining Project-05 |  |  |  |  | 1394 |  | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  | High with Victim | High with Victims | High | 52 | CHA | 2 |  |  | 2014-01-12 16:30 | No | Open
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-14400d99a63-cbf630d3-8cfb-d | Hz-ID-18422 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0087 | 153906 | 65.0987 | 32.317 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-164 | Hilmand Demining Project-05 |  |  |  |  | 1394 |  | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  | High with Victim | High with Victims | High | 21 | CHA | 2 |  |  | 2014-01-12 16:30 | No | Open
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-14400dc1fe3-2566d24d-8d1b-8 | Hz-ID-18423 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0088 | 184208 | 65.0976 | 32.3106 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-164 | Hilmand Demining Project-05 |  |  |  |  | 1394 |  | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  | High with Victim | High with Victims | High | 36 | CHA | 2 |  |  | 2014-01-15 16:30 | No | Open
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-14400de46c1-f8ad981a-8d38-8 | Hz-ID-18424 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0089 | 243236 | 65.0976 | 32.3106 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-164 | Hilmand Demining Project-05 |  |  |  |  | 1394 |  | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  | High with Victim | High with Victims | High | 18 | CHA | 2 |  |  | 2014-01-15 16:30 | No | Open
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-14400dfe8a7-ca025df7-8d54-b | Hz-ID-18425 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0084 | 344483 | 65.1095 | 32.317 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-164 | Hilmand Demining Project-05 |  |  |  |  | 1394 |  | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  | High with Victim | High with Victims | High | 33 | CHA | 2 |  |  | 2014-01-23 16:30 | No | Open
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0009-14400e1a148-af2f328c-8d72-e | Hz-ID-18427 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0085 | 197381 | 65.1095 | 32.317 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-164 | Hilmand Demining Project-05 |  |  |  |  | 1394 |  | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  | High with Victim | High with Victims | High | 17 | CHA | 2 |  |  | 2014-01-22 16:30 | No | Open
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0057-12c3b99e336-77d48a89-2b146- | MF-HQ-10558 | DAFA - Demining Agency for Afghanistan | AF/2303/20475/MF0056 | 89721 | 65.0937 | 32.3132 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2013-06-22 | 2014-01-31 | 1392-1393 | DAFA | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  |  |  | High | 25 | CHA | 2 |  |  | 2009-05-25 | No | Planned
South | Hilmand | Kajaki | Kajaki | {AA1F4E50-8434-4858-B23E-D4AC73303C44} | c0a8-0057-12c3b9d8cdd-83cb734-2d6d3-8 | MF-HQ-10557 | DAFA - Demining Agency for Afghanistan | AF/2303/00536/AIF0065 | 61116 | 65.0899 | 32.3196 | Closed | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2014-04-08 | 2014-05-31 | 1392-1393 | DAFA | {AA1F4E50-8434-4858-B23E-D4AC73303C44} |  |  |  | High | 26 | CHA | 2 |  |  | 2012-07-16 16:30 | No | Planned
South | Hilmand | Kajaki | Kajaki Sufla | {73F19058-A256-4818-B8BC-1E7437680283} | c0a8-0057-12c3b8aa5a9-eb452ca0-20ef4- | MF-HQ-10560 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2303/20473/MF059 | 4000000 | 65.056 | 32.2619 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-267 | Hilmand Demining Project-08 AT |  |  |  |  | 1397 |  | {73F19058-A256-4818-B8BC-1E7437680283} |  | High with Victim | High with Victims | High | 582 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Kajaki | Khake Jahannum | {C0DC80FA-27F4-4BC8-91BB-EAF2E0A5036C} | c0a8-0057-12c3b8a378d-6e7d7cdb-20a58- | MF-HQ-10555 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2303/20572/MF058 | 16250 | 65.1172 | 32.3515 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-284 | Hilmand Demining Project-07 |  |  |  |  | 1401 |  | {C0DC80FA-27F4-4BC8-91BB-EAF2E0A5036C} |  | Low | Agriculture Blocked | High | 136 | SHA | 5 |  |  | 2009-05-25 | No | Open
South | Hilmand | Kajaki | Qal'a-i-Gul | {19FF18CA-230D-473A-B5DB-B8728164FF0C} | c0a8-0009-14400b0c07e-6c40f22b-8c07-7 | Hz-ID-18415 | DAFA - Demining Agency for Afghanistan | AF/2303/20483/MF0079 | 219453 | 65.0998 | 32.3268 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-164 | Hilmand Demining Project-05 |  |  |  |  | 1394 |  | {19FF18CA-230D-473A-B5DB-B8728164FF0C} |  | Medium | Critical Infrastracture | High | 62 | CHA | 3 |  |  | 2014-01-02 16:30 | No | Open
South | Hilmand | Kajaki | Qal'a-i-Gul | {19FF18CA-230D-473A-B5DB-B8728164FF0C} | c0a8-0009-14400b78a04-7d907588-8c43-7 | Hz-ID-18416 | DAFA - Demining Agency for Afghanistan | AF/2303/20483/MF0080 | 294729 | 65.1102 | 32.3345 | Worked on | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2014-06-01 | 2014-09-30 | 1392-1393 | DAFA | {19FF18CA-230D-473A-B5DB-B8728164FF0C} |  | Low | Agriculture Blocked | High | 25 | CHA | 5 |  |  | 2014-01-04 16:30 | No | Planned
South | Hilmand | Kajaki | Qal'a-i-Gul | {19FF18CA-230D-473A-B5DB-B8728164FF0C} | c0a8-0009-14400bac94c-8e59c26b-8c65-f | Hz-ID-18417 | DAFA - Demining Agency for Afghanistan | AF/2303/20483/MF0081 | 282137 | 65.1102 | 32.3345 | Worked on | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2014-06-01 | 2014-07-20 | 1392-1393 | DAFA | {19FF18CA-230D-473A-B5DB-B8728164FF0C} |  | Low | Agriculture Blocked | High | 28 | CHA | 5 |  |  | 2014-01-04 16:30 | No | Planned
South | Hilmand | Kajaki | Qal'a-i-Gul | {19FF18CA-230D-473A-B5DB-B8728164FF0C} | c0a8-0009-14400be8a2e-19d7800f-8c8e-8 | Hz-ID-18418 | DAFA - Demining Agency for Afghanistan | AF/2303/20483/MF0082 | 307428 | 65.12 | 32.3326 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes |  |  | 1392-1393 | DAFA | {19FF18CA-230D-473A-B5DB-B8728164FF0C} |  | Low | Agriculture Blocked | High | 3 | CHA | 5 |  |  | 2014-01-05 16:30 | No | Planned
South | Hilmand | Kajaki | Qal'a-i-Gul | {19FF18CA-230D-473A-B5DB-B8728164FF0C} | c0a8-0009-14400c365b9-10a49a9e-8cb2-3 | Hz-ID-18419 | DAFA - Demining Agency for Afghanistan | AF/2303/20483/MF0083 | 242226 | 65.12 | 32.3326 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-284 | Hilmand Demining Project-07 |  |  |  |  | 1401 |  | {19FF18CA-230D-473A-B5DB-B8728164FF0C} |  | Low | Agriculture Blocked | High | 2 | CHA | 5 |  |  | 2014-01-05 16:30 | No | Open
South | Hilmand | Kajaki | Qarya-I-Khanan | {B00CEA44-EF32-483F-820E-38E8FF034563} | c0a8-0057-12c3b9da339-f0bbc770-2d7af- | MF-HQ-10559 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2303/536/MF060 | 90000 | 65.1209 | 32.3321 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {B00CEA44-EF32-483F-820E-38E8FF034563} |  | High with Victim | High with Victims | High | 0 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Kajaki | Qarya-I-Khanan | {B00CEA44-EF32-483F-820E-38E8FF034563} | c0a8-00f6-1392381d8bb-6028a55-34c9-8e | Hz-ID-17175 | DAFA - Demining Agency for Afghanistan | AF/2303/00536/AIF0069 | 57709 | 65.084 | 32.3105 | Closed | UXO Only | UXO Only | MineField | 1393 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2014-05-01 | 2014-05-31 | 1392-1393 | DAFA | {B00CEA44-EF32-483F-820E-38E8FF034563} |  |  |  | High | 134 | CHA | 2 |  |  | 2012-07-16 16:30 | No | Planned
South | Hilmand | Kajaki | Qarya-I-Khanan | {B00CEA44-EF32-483F-820E-38E8FF034563} | c0a8-00f6-13923ffd637-9c44fe64-3d10-e | Hz-ID-17171 | DAFA - Demining Agency for Afghanistan | AF/2303/00536/AIF0066 | 59642 | 65.0825 | 32.3196 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2013-08-10 | 2013-11-22 | 1392-1393 | DAFA | {B00CEA44-EF32-483F-820E-38E8FF034563} |  |  |  | High | 39 | CHA | 2 |  |  | 2012-07-16 16:30 | No | Planned
South | Hilmand | Kajaki | Qarya-I-Khanan | {B00CEA44-EF32-483F-820E-38E8FF034563} | c0a8-00f6-13924089183-fbe7886e-3d68-e | Hz-ID-17176 | DAFA - Demining Agency for Afghanistan | AF/2303/00536/AIF0068 | 64309 | 65.0903 | 32.3187 | Closed | UXO Only | UXO Only | MineField | 1393 | MBT Project-161 | Hilmand Demining Project-01 | DOS | Yes | 2014-04-01 | 2014-05-31 | 1392-1393 | DAFA | {B00CEA44-EF32-483F-820E-38E8FF034563} |  |  |  | High | 23 | CHA | 2 |  |  | 2012-07-16 16:30 | No | Planned
South | Hilmand | Lashkar Gah | Basharan | {DCFC636F-A5B7-4E4E-9CA8-FD2D8C2F1EAF} | c0a8-0057-12c3ba1923d-4a39efbe-2fe64- | MF-HQ-10601 | DAFA - Demining Agency for Afghanistan | AF/2301/20066/MF0117 | 91976 | 64.3287 | 31.6722 | Open | AT Only | AT Only | MineField |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {DCFC636F-A5B7-4E4E-9CA8-FD2D8C2F1EAF} |  | High with Victim | High with Victims | High | 446 | CHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Lashkar Gah | Bost | {0EDC8956-025A-4229-A637-5F776628AA95} | c0a8-0057-12c3b964d05-25816edc-28bc1- | MF-HQ-10609 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2301/00037/MF118 | 40000 | 64.3781 | 31.4715 | Closed | AT Only | AT Only | Converted From SHA |  | MBT Project-289 | Hilmand Demining Project-07 AT | [6 empty] | {0EDC8956-025A-4229-A637-5F776628AA95} |  |  |  | High | 0 | SHA | 5 |  |  | 2009-05-25 | Yes | Complete
South | Hilmand | Musa Qala | Deh Zore Sufla | {C26B4D4A-7D01-4C26-8FAF-C5FA44C8FBD3} | c0a8-0057-12c3b84dfca-2c76b8e1-1ceae- | MF-HQ-10603 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20344/MF035 | 480000 | 64.7455 | 32.3011 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {C26B4D4A-7D01-4C26-8FAF-C5FA44C8FBD3} |  | High with Victim | High with Victims | Extreme | 339 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Deh Zore Sufla | {C26B4D4A-7D01-4C26-8FAF-C5FA44C8FBD3} | c0a8-0057-12c3bb7348c-e3817b24-3cb90- | MF-HQ-10606 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20344/MF034 | 62500 | 64.7455 | 32.3011 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {C26B4D4A-7D01-4C26-8FAF-C5FA44C8FBD3} |  | High with Victim | High with Victims | Extreme | 44 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Deh Zuhre Ulya | {072CEE06-BA07-4B13-84F0-106EE847D6A5} | c0a8-0009-144910ab8c3-99fd02a-7f3-bda | Hz-ID-18524 | DAFA - Demining Agency for Afghanistan | AF/2304/20352/MF0007 | 102108 | 64.7425 | 32.3489 | Open | UXO Only | UXO Only | MineField | 1393 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2014-07-17 | 2015-03-14 | 1392-1393 | DAFA | {072CEE06-BA07-4B13-84F0-106EE847D6A5} |  | High with Victim | High with Victims | Extreme | 156 | CHA | 2 |  |  | 2014-02-25 16:30 | No | Planned
South | Hilmand | Musa Qala | Deh Zuhre Ulya | {072CEE06-BA07-4B13-84F0-106EE847D6A5} | c0a8-0009-1449112a6df-e1f09f0d-87a-4a | Hz-ID-18526 | DAFA - Demining Agency for Afghanistan | AF/2304/20352/MF0008 | 154276 | 64.7425 | 32.3489 | Open | UXO Only | UXO Only | MineField | 1393 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2014-07-17 | 2015-07-15 | 1392-1393 | DAFA | {072CEE06-BA07-4B13-84F0-106EE847D6A5} |  | High with Victim | High with Victims | Extreme | 52 | CHA | 2 |  |  | 2014-02-25 16:30 | No | Planned
South | Hilmand | Musa Qala | Deh Zuhre Ulya | {072CEE06-BA07-4B13-84F0-106EE847D6A5} | c0a8-0009-1449114df27-f08cbd3a-8f2-ae | Hz-ID-18529 | DAFA - Demining Agency for Afghanistan | AF/2304/20352/MF0009 | 166928 | 64.7425 | 32.3489 | Open | UXO Only | UXO Only | MineField | 1393 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2014-07-17 | 2015-07-15 | 1392-1393 | DAFA | {072CEE06-BA07-4B13-84F0-106EE847D6A5} |  | High with Victim | High with Victims | Extreme | 52 | CHA | 2 |  |  | 2014-02-25 16:30 | No | Planned
South | Hilmand | Musa Qala | Deh Zuhre Ulya | {072CEE06-BA07-4B13-84F0-106EE847D6A5} | c0a8-0009-144919a7e25-c86520e2-a82-14 | Hz-ID-18530 | DAFA - Demining Agency for Afghanistan | AF/2304/20352/MF0010 | 94023 | 64.7425 | 32.3489 | Open | UXO Only | UXO Only | MineField | 1393 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2014-07-17 | 2015-07-15 | 1392-1393 | DAFA | {072CEE06-BA07-4B13-84F0-106EE847D6A5} |  | High with Victim | High with Victims | Extreme | 52 | CHA | 2 |  |  | 2014-02-25 16:30 | No | Planned
South | Hilmand | Musa Qala | Deh Zuhre Ulya | {072CEE06-BA07-4B13-84F0-106EE847D6A5} | c0a8-0009-144919f625f-b781a132-aa0-49 | Hz-ID-18532 | DAFA - Demining Agency for Afghanistan | AF/2304/20352/MF0011 | 113207 | 64.7425 | 32.3489 | Open | UXO Only | UXO Only | MineField | 1393 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2014-07-17 | 2015-04-09 | 1392-1393 | DAFA | {072CEE06-BA07-4B13-84F0-106EE847D6A5} |  | High with Victim | High with Victims | Extreme | 61 | CHA | 2 |  |  | 2014-02-25 16:30 | No | Planned
South | Hilmand | Musa Qala | Deh Zuhre Ulya | {072CEE06-BA07-4B13-84F0-106EE847D6A5} | c0a8-0009-14491aba374-21f1ce46-aea-c9 | Hz-ID-18534 | DAFA - Demining Agency for Afghanistan | AF/2304/20352/MF0012 | 128116 | 64.7447 | 32.3397 | Open | UXO Only | UXO Only | MineField |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {072CEE06-BA07-4B13-84F0-106EE847D6A5} |  | High with Victim | High with Victims | Extreme | 33 | CHA | 2 |  |  | 2014-02-25 16:30 | No | Open
South | Hilmand | Musa Qala | Deh Zuhre Ulya | {072CEE06-BA07-4B13-84F0-106EE847D6A5} | c0a8-0009-14495afc66d-e70d9fd-c74-fbf | Hz-ID-18535 | DAFA - Demining Agency for Afghanistan | AF/2304/20352/MF0013 | 107530 | 64.7447 | 32.3397 | Open | UXO Only | UXO Only | MineField |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {072CEE06-BA07-4B13-84F0-106EE847D6A5} |  | High with Victim | High with Victims | Extreme | 33 | CHA | 2 |  |  | 2014-02-25 16:30 | No | Open
South | Hilmand | Musa Qala | Deh Zuhre Ulya | {072CEE06-BA07-4B13-84F0-106EE847D6A5} | c0a8-0009-14495b47bea-a2c8344b-c9e-b4 | Hz-ID-18536 | DAFA - Demining Agency for Afghanistan | AF/2304/20352/MF0014 | 129888 | 64.7538 | 32.3485 | Open | UXO Only | UXO Only | MineField |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {072CEE06-BA07-4B13-84F0-106EE847D6A5} |  | High with Victim | High with Victims | Extreme | 24 | CHA | 2 |  |  | 2014-02-25 16:30 | No | Open
South | Hilmand | Musa Qala | Deh Zuhre Ulya | {072CEE06-BA07-4B13-84F0-106EE847D6A5} | c0a8-0057-12c3b865238-ec01209d-1decf- | MF-HQ-10566 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20352/MF025 | 120000 | 64.721 | 32.3361 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {072CEE06-BA07-4B13-84F0-106EE847D6A5} |  | High with Victim | High with Victims | Extreme | 0 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Deh Zuhre Ulya | {072CEE06-BA07-4B13-84F0-106EE847D6A5} | c0a8-0057-12c3b8b2478-a4595f17-2146f- | MF-HQ-10565 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20352/MF024 | 120000 | 64.7279 | 32.3576 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {072CEE06-BA07-4B13-84F0-106EE847D6A5} |  | High with Victim | High with Victims | Extreme | 7 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Ghund Kalay | {0087AD20-4BF5-4B40-A4B7-9063486B2333} | c0a8-0057-12c3b7cff5f-9317b402-1757b- | MF-HQ-10599 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20345/MF032 | 87500 | 64.7487 | 32.3145 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {0087AD20-4BF5-4B40-A4B7-9063486B2333} |  | High with Victim | High with Victims | Extreme | 19 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Ghund Kalay | {0087AD20-4BF5-4B40-A4B7-9063486B2333} | c0a8-0057-12c3b983850-6f982ba5-29fab- | MF-HQ-10597 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20345/MF031 | 2500 | 64.756 | 32.3201 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {0087AD20-4BF5-4B40-A4B7-9063486B2333} |  | High with Victim | High with Victims | Extreme | 1503 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Ghund Kalay | {0087AD20-4BF5-4B40-A4B7-9063486B2333} | c0a8-0057-12c3bae0b71-ec04f1b6-3756c- | MF-HQ-10598 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20345/MF030 | 15000 | 64.754 | 32.3145 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {0087AD20-4BF5-4B40-A4B7-9063486B2333} |  | High with Victim | High with Victims | Extreme | 25 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Kareze Deh | {C71FED02-D6DD-4147-884D-B8FBD1ED957A} | c0a8-0057-12c3bb0bf10-ea556e90-38f5c- | MF-HQ-10562 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20355/MF033 | 100000 | 64.8122 | 32.3366 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-284 | Hilmand Demining Project-07 |  |  |  |  | 1401 |  | {C71FED02-D6DD-4147-884D-B8FBD1ED957A} |  | Low | Agriculture Blocked | Extreme | 19 | SHA | 5 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Qarya-i-Kunjak | {25A80858-BADC-499D-82DE-6CBEC16D73AF} | c0a8-0009-13fc2de2550-387c8a29-17d-65 | Hz-ID-18013 | DAFA - Demining Agency for Afghanistan | AF/2304/20357/AIF0001 | 149700 | 64.7943 | 32.3573 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2013-08-20 | 2014-05-12 | 1392-1393 | DAFA | {25A80858-BADC-499D-82DE-6CBEC16D73AF} |  |  |  | Extreme | 1277 | CHA | 3 |  |  | 2013-06-24 16:30 | No | Planned
South | Hilmand | Musa Qala | Qarya-i-Kunjak | {25A80858-BADC-499D-82DE-6CBEC16D73AF} | c0a8-0009-13fdc7032d3-b6ad9344-279b-1 | Hz-ID-18015 | DAFA - Demining Agency for Afghanistan | AF/2304/20357/AIF0003 | 164989 | 64.7943 | 32.3573 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2014-05-13 | 2014-07-31 | 1392-1393 | DAFA | {25A80858-BADC-499D-82DE-6CBEC16D73AF} |  |  |  | Extreme | 1277 | CHA | 3 |  |  | 2013-06-24 16:30 | No | Planned
South | Hilmand | Musa Qala | Qarya-i-Kunjak | {25A80858-BADC-499D-82DE-6CBEC16D73AF} | c0a8-0009-13fdc709656-9848d8de-27bb-f | Hz-ID-18014 | DAFA - Demining Agency for Afghanistan | AF/2304/20357/AIF0002 | 128649 | 64.803 | 32.3578 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2013-08-20 | 2014-01-14 | 1392-1393 | DAFA | {25A80858-BADC-499D-82DE-6CBEC16D73AF} |  |  |  | Extreme | 133 | CHA | 3 |  |  | 2013-06-24 16:30 | No | Planned
South | Hilmand | Musa Qala | Qarya-i-Kunjak | {25A80858-BADC-499D-82DE-6CBEC16D73AF} | c0a8-0009-13fe0e2b9a4-f8d590c6-30da-3 | Hz-ID-18016 | DAFA - Demining Agency for Afghanistan | AF/2304/20357/AIF0004 | 128649 | 64.803 | 32.3578 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2014-01-15 | 2014-05-22 | 1392-1393 | DAFA | {25A80858-BADC-499D-82DE-6CBEC16D73AF} |  |  |  | Extreme | 133 | CHA | 3 |  |  | 2013-06-24 16:30 | No | Planned
South | Hilmand | Musa Qala | Qarya-i-Kunjak | {25A80858-BADC-499D-82DE-6CBEC16D73AF} | c0a8-0009-142e568f942-8def7891-69c6-a | Hz-ID-18288 | DAFA - Demining Agency for Afghanistan | AF/2304/20357/AIF0005 | 109708 | 64.8017 | 32.3552 | Worked on | UXO Only | UXO Only | MineField | 1393 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2014-01-25 | 2014-08-10 | 1392-1393 | DAFA | {25A80858-BADC-499D-82DE-6CBEC16D73AF} |  | Medium | Comunity Centers | Extreme | 39 | CHA | 5 |  |  | 2013-11-04 16:30 | No | Planned
South | Hilmand | Musa Qala | Qarya-i-Kunjak | {25A80858-BADC-499D-82DE-6CBEC16D73AF} | c0a8-0009-142e569bb96-539925cb-69ff-7 | Hz-ID-18289 | DAFA - Demining Agency for Afghanistan | AF/2304/20357/MF0006 | 132504 | 64.7977 | 32.36 | Worked on | UXO Only | UXO Only | MineField | 1393 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2014-02-22 | 2014-07-16 | 1392-1393 | DAFA | {25A80858-BADC-499D-82DE-6CBEC16D73AF} |  | Medium | Comunity Centers | Extreme | 92 | CHA | 5 |  |  | 2013-11-04 16:30 | No | Planned
South | Hilmand | Musa Qala | Qarya-i-Kunjak | {25A80858-BADC-499D-82DE-6CBEC16D73AF} | c0a8-0009-145f4674217-fbaad648-8b4-c6 | Hz-ID-18701 | DAFA - Demining Agency for Afghanistan | AF/2304/20357/MF0015 | 223792 | 64.7984 | 32.365 | Worked on | UXO Only | UXO Only | MineField | 1393 | MBT Project-216/A | Hilmand Demining Project-06/A | DOS | Yes | 2014-05-17 | 2014-10-17 | 1392-1393 | DAFA | {25A80858-BADC-499D-82DE-6CBEC16D73AF} |  | Medium | Critical Infrastracture | Extreme | 483 | CHA | 3 |  |  | 2014-05-07 16:30 | No | Planned
South | Hilmand | Musa Qala | Qarya-i-Kunjak | {25A80858-BADC-499D-82DE-6CBEC16D73AF} | c0a8-0057-12c3bad41af-1a7c7b0-36dfa-b | MF-HQ-10564 | DAFA - Demining Agency for Afghanistan | AF/2304/20357/AIF0026 | 134554 | 64.803 | 32.3578 | Open | UXO Only | UXO Only | MineField |  | MBT Project-216 | Hilmand Demining Project-06 |  |  |  |  | 1398 |  | {25A80858-BADC-499D-82DE-6CBEC16D73AF} |  | Medium | Agriculture Blocked | Extreme | 35 | CHA | 4 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Sangin Gadr | {0CDD1F4E-ADB7-4E46-81E9-9E41E012D713} | c0a8-0057-12c3b93cac2-b2aae7a0-270f5- | MF-HQ-10563 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/00032/MF023 | 100000 | 64.7861 | 32.3731 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {0CDD1F4E-ADB7-4E46-81E9-9E41E012D713} |  | High with Victim | High with Victims | Extreme | 34 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Shir Ghazay | {3D72A0E4-5943-4F64-A435-8AD4AE18E341} | c0a8-0057-12c3b801632-fc2888d5-197ff- | MF-HQ-10616 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20307/MF029 | 80000 | 64.6752 | 32.213 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {3D72A0E4-5943-4F64-A435-8AD4AE18E341} |  | High with Victim | High with Victims | Extreme | 0 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Shir Ghazay | {3D72A0E4-5943-4F64-A435-8AD4AE18E341} | c0a8-0057-12c3b9b8029-68c603-2c202-b2 | MF-HQ-10614 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20307/MF027 | 90000 | 64.7147 | 32.2032 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {3D72A0E4-5943-4F64-A435-8AD4AE18E341} |  | High with Victim | High with Victims | Extreme | 37 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Shir Ghazay | {3D72A0E4-5943-4F64-A435-8AD4AE18E341} | c0a8-0057-12c3ba4fa78-259e30ce-31f5d- | MF-HQ-10613 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20307/MF028 | 80000 | 64.6942 | 32.2216 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-161/A | Hilmand Demining Project-01/A |  |  |  |  | 1394 |  | {3D72A0E4-5943-4F64-A435-8AD4AE18E341} |  | High with Victim | High with Victims | Extreme | 181 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Takhtapul Keli | {1ACA7E98-D2A9-4C76-87F9-548E5DA381D2} | c0a8-0057-12c3b7de587-51954e23-17fae- | MF-SA-190 | MCPA - Mine Clearance Planning Agency | AF/2304/20367/027 | 74694 | 64.797 | 32.3736 | Open | AT Only | AT Only | MineField |  | MBT Project-216 | Hilmand Demining Project-06 |  |  |  |  | 1398 |  | {1ACA7E98-D2A9-4C76-87F9-548E5DA381D2} |  | Low | Infrastructure | Extreme | 3 | CHA | 5 |  |  | 2003-09-30 | No | Open
South | Hilmand | Musa Qala | Takhtapul Keli | {1ACA7E98-D2A9-4C76-87F9-548E5DA381D2} | c0a8-0057-12c3b9aa874-bc053b11-2b98d- | MF-HQ-10608 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20367/MF036 | 62500 | 64.784 | 32.3672 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-216 | Hilmand Demining Project-06 |  |  |  |  | 1398 |  | {1ACA7E98-D2A9-4C76-87F9-548E5DA381D2} |  | Medium | Critical Infrastracture | Extreme | 0 | SHA | 3 |  |  | 2009-05-25 | No | Open
South | Hilmand | Musa Qala | Takhtapul Keli | {1ACA7E98-D2A9-4C76-87F9-548E5DA381D2} | c0a8-0057-12c3b9fea31-708fb1e7-2edfd- | MF-HQ-10610 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2304/20367/MF037 | 90000 | 64.784 | 32.3672 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-216 | Hilmand Demining Project-06 |  |  |  |  | 1398 |  | {1ACA7E98-D2A9-4C76-87F9-548E5DA381D2} |  | Medium | Critical Infrastracture | Extreme | 0 | SHA | 3 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nad Ali | Block 9_B | {0F1D21D9-4C35-4CA8-870A-F07FD5691E8A} | c0a8-0057-12c3b92f70b-92021c8d-26838- | MF-HQ-10581 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2309/00038/MF008 | 43200 | 64.0734 | 31.361 | Closed | AT Only | AT Only | Converted From SHA |  | MBT Project-289 | Hilmand Demining Project-07 AT | [6 empty] | {0F1D21D9-4C35-4CA8-870A-F07FD5691E8A} |  |  |  | High | 6 | SHA | 5 |  |  | 2009-05-25 | Yes | Complete
South | Hilmand | Nad Ali | Haji abdurahman Kalay,sharshorak kalay | {C938F486-8B98-4D0B-A371-740BA3E88907} | c0a8-0057-12c3b886c18-d67a53e-1f655-f | MF-HQ-10553 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2308/00622/MF0011 | 60000 | 64.0243 | 31.4216 | Closed | AT Only | AT Only | Converted From SHA |  | MBT Project-289 | Hilmand Demining Project-07 AT | [6 empty] | {C938F486-8B98-4D0B-A371-740BA3E88907} |  |  |  | High | 0 | SHA | 5 |  |  | 2009-05-25 | Yes | Complete
South | Hilmand | Nad Ali | Haji abdurahman Kalay,sharshorak kalay | {C938F486-8B98-4D0B-A371-740BA3E88907} | c0a8-0057-12c3b9a2d7d-83ed638e-2b44c- | MF-HQ-10554 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2308/00622/MF0010 | 100000 | 64.0243 | 31.4216 | Closed | AT Only | AT Only | Converted From SHA |  | MBT Project-289 | Hilmand Demining Project-07 AT | [6 empty] | {C938F486-8B98-4D0B-A371-740BA3E88907} |  |  |  | High | 0 | SHA | 5 |  |  | 2009-05-25 | Yes | Complete
South | Hilmand | Nad Ali | Mula Yahya-Hadira | {305FFF3C-8127-4FB9-AD8C-05748C40A109} | c0a8-0057-12c3b9378d0-4fd9214-26da2-3 | MF-HQ-10617 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2308/00140/MF008 | 57000 | 64.3527 | 31.7427 | Open | Mixed | Mixed AT UXO | Converted From SHA |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {305FFF3C-8127-4FB9-AD8C-05748C40A109} |  | High with Victim | High with Victims | High | 25 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nahri Sarraj | Aue pashak, Dasht Kalay | {ADB132B1-FB06-423B-B5D7-59D68F2A4B62} | c0a8-0057-12c3b893c31-dc8543bb-1ffa6- | MF-HQ-15302 | DAFA - Demining Agency for Afghanistan | AF/2302/00527/MF0135 | 97116 | 64.514 | 31.8011 | Open | AT Only | AT Only | MineField |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {ADB132B1-FB06-423B-B5D7-59D68F2A4B62} |  | High with Victim | High with Victims | High | 39 | CHA | 2 |  |  | 2010-11-05 | No | Open
South | Hilmand | Nahri Sarraj | Aue pashak, Dasht Kalay | {ADB132B1-FB06-423B-B5D7-59D68F2A4B62} | c0a8-0057-12c3b894140-9a17eb6a-1ffd9- | MF-HQ-15297 | DAFA - Demining Agency for Afghanistan | AF/2302/00527/MF0130 | 78601 | 64.5234 | 31.8046 | Open | AT Only | AT Only | MineField |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {ADB132B1-FB06-423B-B5D7-59D68F2A4B62} | Funding Status updated | High with Victim | High with Victims | High | 332 | CHA | 2 |  |  | 2010-11-05 | No | Open
South | Hilmand | Nahri Sarraj | Aue pashak, Dasht Kalay | {ADB132B1-FB06-423B-B5D7-59D68F2A4B62} | c0a8-0057-12c3b89440d-97518584-1ffea- | MF-HQ-15300 | DAFA - Demining Agency for Afghanistan | AF/2302/00527/MF0133 | 82251 | 64.5179 | 31.8025 | Open | AT Only | AT Only | MineField |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {ADB132B1-FB06-423B-B5D7-59D68F2A4B62} | Planned year and Agecny removed | High with Victim | High with Victims | High | 371 | CHA | 2 |  |  | 2010-11-05 | No | Open
South | Hilmand | Nahri Sarraj | Aue pashak, Dasht Kalay | {ADB132B1-FB06-423B-B5D7-59D68F2A4B62} | c0a8-0057-12c3b894b5d-631096e7-20036- | MF-HQ-15299 | DAFA - Demining Agency for Afghanistan | AF/2302/00527/MF0132 | 76960 | 64.5197 | 31.8031 | Open | AT Only | AT Only | MineField |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {ADB132B1-FB06-423B-B5D7-59D68F2A4B62} |  | High with Victim | High with Victims | High | 332 | CHA | 2 |  |  | 2010-11-05 | No | Open
South | Hilmand | Nahri Sarraj | Haidar Kajak, Haidar abad | {F2382CDC-98CF-4389-8165-2BF64BEC537C} | c0a8-0057-12c3b919540-341e3a4d-2598f- | MF-HQ-10549 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2302/00755/MF115 | 120000 | 64.7726 | 31.9278 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-162 | Hilmand Demining Project-03 |  |  |  |  | 1395 |  | {F2382CDC-98CF-4389-8165-2BF64BEC537C} |  | Low | Agriculture Blocked | High | 123 | SHA | 4 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nahri Sarraj | Haidar Kajak, Haidar abad | {F2382CDC-98CF-4389-8165-2BF64BEC537C} | c0a8-0057-12c3ba2b988-36be32db-30988- | MF-HQ-10550 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2302/00755/MF116 | 90000 | 64.7756 | 31.9272 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-162 | Hilmand Demining Project-03 |  |  |  |  | 1395 |  | {F2382CDC-98CF-4389-8165-2BF64BEC537C} |  | Medium | Agriculture Blocked | High | 78 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Hilmand | Nahri Sarraj | Haidar Kajak, Haidar abad | {F2382CDC-98CF-4389-8165-2BF64BEC537C} | c0a8-0057-12c3ba8745f-137b9c4e-34153- | MF-HQ-10551 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2302/755/MF117 | 142500 | 64.7724 | 31.9273 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-162 | Hilmand Demining Project-03 |  |  |  |  | 1395 |  | {F2382CDC-98CF-4389-8165-2BF64BEC537C} |  | Low | Agriculture Blocked | High | 189 | SHA | 4 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nahri Sarraj | Khushkyar | {8C1AB982-DBE9-44C8-A8C7-0CBDF44714BD} | c0a8-0057-12c3b93ea03-5c44af82-2725c- | MF-HQ-10602 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2301/00424/MF120 | 120000 | 64.3756 | 31.7031 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-162 | Hilmand Demining Project-03 |  |  |  |  | 1395 |  | {8C1AB982-DBE9-44C8-A8C7-0CBDF44714BD} |  | High | Water Blocked | High | 1420 | SHA | 3 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nahri Sarraj | Liwa | {EF377A94-3F80-4451-B46B-1BE0DB4DEBC4} | c0a8-0057-12c3bb49596-6f1d235a-3b3c1- | MF-HQ-10607 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2302/00741/MF120 | 80000 | 64.6248 | 31.813 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {EF377A94-3F80-4451-B46B-1BE0DB4DEBC4} |  | Medium | Agriculture Blocked | High | 533 | SHA | 4 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nahri Sarraj | Mirmandaw | {1226ACF7-BD09-407A-8347-96100F43E50D} | c0a8-0057-12c3b7fc065-b3ddd19f-1943b- | MF-HQ-10578 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2302/20230/MF122 | 100000 | 64.7639 | 31.8769 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {1226ACF7-BD09-407A-8347-96100F43E50D} |  | High with Victim | High with Victims | High | 105 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nahri Sarraj | Mirmandaw | {1226ACF7-BD09-407A-8347-96100F43E50D} | c0a8-0057-12c3b93443c-108d6b5f-26b2a- | MF-HQ-10579 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2302/20230/MF123 | 70000 | 64.7756 | 31.8758 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {1226ACF7-BD09-407A-8347-96100F43E50D} |  | High with Victim | High with Victims | High | 121 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nahri Sarraj | Noorzai | {C9D4AFC8-804C-4FB0-866C-23ADD1129688} | c0a8-0057-12c3bb3bbcd-15d5aa3a-3abdd- | MF-HQ-10575 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2302/00625/MF114 | 1200000 | 64.6061 | 31.7912 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {C9D4AFC8-804C-4FB0-866C-23ADD1129688} |  | High with Victim | High with Victims | High | 32 | SHA | 1 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nahri Sarraj | Safi | {90525C23-043C-4964-A0DD-87A645BB0DEA} | c0a8-0057-12c3b8b47c0-e36a1123-2160b- | MF-HQ-10556 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2302/435/MF121 | 562500 | 64.7048 | 31.7857 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-162 | Hilmand Demining Project-03 |  |  |  |  | 1395 |  | {90525C23-043C-4964-A0DD-87A645BB0DEA} |  | Low | Agriculture Blocked | High | 360 | SHA | 4 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nahri Sarraj | Saidan (1) | {1350EF57-342F-4956-B0B1-B4FC7B278132} | c0a8-0057-12c3ba103b6-6a3f318d-2f8e9- | MF-SA-601 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2302/20159/MF0115 | 277663 | 64.6366 | 31.8172 | Open | AT Only | AT Only | MineField |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {1350EF57-342F-4956-B0B1-B4FC7B278132} |  | High with Victim | High with Victims | High | 553 | CHA | 2 |  |  | 2008-11-04 | No | Open
South | Hilmand | Nahri Sarraj | Torma | {91F82AE7-1F18-4FF6-B3BF-35136129A72A} | c0a8-008e-132340658a6-212e770d-1763-7 | MF-HQ-10580 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2302/20245/MF118 | 60000 | 64.8203 | 31.9972 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-271 | Hilmand Demining Project-05 AT |  |  |  |  | 1394 |  | {91F82AE7-1F18-4FF6-B3BF-35136129A72A} |  | High with Victim | High with Victims | High | 43 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Naw Zad | Ali Za`i | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | c0a8-0009-13d3f20645f-1a82e91-6e0-cb4 | Hz-ID-17693 | MDC - Mine Detection and Dog Center | AF/2306/20662/AIF0082 | 172933 | 64.4639 | 32.4183 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-166 | Hilmand Demining Project-10 | DOS | Yes | 2013-02-04 | 2013-09-30 | 1392 | MDC | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} |  |  |  | Extreme | 2320 | CHA | 2 |  |  | 2013-02-07 16:30 | No | Planned
South | Hilmand | Naw Zad | Ali Za`i | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | c0a8-0009-13e73037d92-2efc93e6-226-e6 | Hz-ID-17831 | MDC - Mine Detection and Dog Center | AF/2306/20662/AIF0086 | 30383 | 64.4617 | 32.413 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | , | High with Victim | High with Victims | Extreme | 2079 | CHA | 2 |  |  | 2013-04-08 16:30 | No | Open
South | Hilmand | Naw Zad | Ali Za`i | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | c0a8-0009-13e7308f8d9-6be7824d-257-db | Hz-ID-17834 | MDC - Mine Detection and Dog Center | AF/2306/20662/AIF0083 | 34591 | 64.4665 | 32.4169 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | , | High with Victim | High with Victims | Extreme | 2320 | CHA | 2 |  |  | 2013-04-05 16:30 | No | Open
South | Hilmand | Naw Zad | Ali Za`i | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | c0a8-0009-13e730a7592-30991bc8-271-3a | Hz-ID-17833 | MDC - Mine Detection and Dog Center | AF/2306/20662/AIF0084 | 28592 | 64.4702 | 32.4167 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | , | High with Victim | High with Victims | Extreme | 2214 | CHA | 2 |  |  | 2013-04-06 16:30 | No | Open
South | Hilmand | Naw Zad | Ali Za`i | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | c0a8-0009-13e730b2f8b-c8cf9ba9-28c-39 | Hz-ID-17832 | MDC - Mine Detection and Dog Center | AF/2306/20662/AIF0085 | 52072 | 64.4652 | 32.416 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | , | High with Victim | High with Victims | Extreme | 2185 | CHA | 2 |  |  | 2013-04-07 16:30 | No | Open
South | Hilmand | Naw Zad | Ali Za`i | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | c0a8-008e-131db19b694-172018eb-2fb-ce | AIF-HQ-14029 | MDC - Mine Detection and Dog Center | AF/2306/20662/AIF0024 | 12345 | 64.4702 | 32.4167 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-166 | Hilmand Demining Project-10 | DOS | Yes |  |  | 1392 | MDC | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} |  |  |  | Extreme | 2214 | CHA | 2 |  |  | 2010-01-13 | No | Planned
South | Hilmand | Naw Zad | Ali Za`i | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | c0a8-008e-1328fca0380-b06dabfc-285b-7 | AIF-15001 | MDC - Mine Detection and Dog Center | AF/2306/20662/AIF0053 | 11950 | 64.4669 | 32.4162 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-166 | Hilmand Demining Project-10 | DOS | Yes |  |  | 1392 | MDC | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} |  |  |  | Extreme | 2320 | CHA | 2 |  |  | 2010-08-22 16:30 | No | Planned
South | Hilmand | Naw Zad | Ali Za`i | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | c0a8-00f6-135186e6267-e32dd0e5-3ae-c7 | AIF-15015 | MCPA - Mine Clearance Planning Agency | AF/2306/20662/AIF0069 | 52906 | 64.4647 | 32.4138 | Closed | UXO Only | UXO Only | MineField | 1392 | MBT Project-166 | Hilmand Demining Project-10 | DOS | Yes | 2012-09-06 | 2012-10-14 | 1392 | MDC | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} |  |  |  | Extreme | 2140 | CHA | 1 |  |  | 2010-12-30 16:30 | No | Planned
South | Hilmand | Naw Zad | Ali Za`i | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | c0a8-00f6-13923fdfae8-f68ae27f-3cf4-4 | Hz-ID-17123 | MDC - Mine Detection and Dog Center | AF/2306/20662/AIF0064 | 24429 | 64.4707 | 32.4197 | Worked on | UXO Only | UXO Only | MineField | 1392 | MBT Project-166 | Hilmand Demining Project-10 | DOS | Yes |  |  | 1392 | MDC | {5AA9AB7A-B2F2-47FF-BF49-28AE096EE27C} | Contact person of the mentioned area is Haji Abdul Baqi residential of Alizai village | High with Victim | High with Victims | Extreme | 2214 | CHA | 2 |  |  | 2012-05-01 16:30 | No | Planned
South | Hilmand | Naw Zad | Da`ud Zai | {0565E411-0DC0-44CE-810D-D112DA01B3BE} | c0a8-008e-131db10ec88-9d022eba-20c-83 | AIF-HQ-14039 | MCPA - Mine Clearance Planning Agency | AF/2306/20664/AIF0026 | 468765 | 64.4626 | 32.398 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {0565E411-0DC0-44CE-810D-D112DA01B3BE} |  | High | Critical Infrastracture | Extreme | 2446 | CHA | 3 |  |  | 2010-01-09 | No | Open
South | Hilmand | Naw Zad | Da`ud Zai | {0565E411-0DC0-44CE-810D-D112DA01B3BE} | c0a8-008e-131db113309-c22f839f-21b-59 | AIF-HQ-14037 | MCPA - Mine Clearance Planning Agency | AF/2306/20664/AIF0027 | 506520 | 64.4866 | 32.4186 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 | None | {0565E411-0DC0-44CE-810D-D112DA01B3BE} |  | High | Critical Infrastracture | Extreme | 2544 | CHA | 3 |  |  | 2010-01-24 | No | Open
South | Hilmand | Naw Zad | Dehe Baluch | {59262864-2223-4380-8352-4F6107BA960B} | c0a8-0057-12c3b80430b-d987c27c-199f2- | MF-HQ-10547 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2306/20636/MF003 | 30000 | 64.4635 | 32.3932 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-163 | Hilmand Demining Project-04 |  |  |  |  | 1399 | None | {59262864-2223-4380-8352-4F6107BA960B} |  | Low | Critical Infrastracture | Extreme | 406 | SHA | 4 |  |  | 2009-05-25 | No | Open
South | Hilmand | Naw Zad | Dehe Baluch | {59262864-2223-4380-8352-4F6107BA960B} | c0a8-0057-12c3b8144dc-bcff88ce-1a54f- | MF-HQ-10548 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2306/20636/MF004 | 40000 | 64.4828 | 32.3673 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-163 | Hilmand Demining Project-04 |  |  |  |  | 1399 | None | {59262864-2223-4380-8352-4F6107BA960B} |  | Low | Agriculture Blocked | Extreme | 9 | SHA | 5 |  |  | 2009-05-25 | No | Open
South | Hilmand | Naw Zad | Dehe Baluch | {59262864-2223-4380-8352-4F6107BA960B} | c0a8-0057-12c3b821d8c-1f26d8b6-1aefe- | MF-HQ-10545 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2306/20636/MF001 | 45000 | 64.4635 | 32.3907 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-163 | Hilmand Demining Project-04 |  |  |  |  | 1399 | None | {59262864-2223-4380-8352-4F6107BA960B} |  | Low | Agriculture Blocked | Extreme | 406 | SHA | 4 |  |  | 2009-05-25 | No | Open
South | Hilmand | Naw Zad | Dehe Baluch | {59262864-2223-4380-8352-4F6107BA960B} | c0a8-0057-12c3ba28c51-ab6b8f64-307be- | MF-HQ-10546 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2306/20636/MF002 | 12500 | 64.5001 | 32.369 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-163 | Hilmand Demining Project-04 |  |  |  |  | 1399 | None | {59262864-2223-4380-8352-4F6107BA960B} |  | Low | Agriculture Blocked | Extreme | 0 | SHA | 5 |  |  | 2009-05-25 | No | Open
South | Hilmand | Naw Zad | Kareze Afghan | {4848BCF6-CE1C-43E1-8878-7F736F44AD8D} | c0a8-008e-131db1266c2-9193e90f-267-b5 | AIF-HQ-14017 | MCPA - Mine Clearance Planning Agency | AF/2306/20647/AIF0016 | 398287 | 64.4866 | 32.4186 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {4848BCF6-CE1C-43E1-8878-7F736F44AD8D} | , | High with Victim | High with Victims | Extreme | 179 | CHA | 3 |  |  | 2010-01-04 | No | Open
South | Hilmand | Naw Zad | Kareze Afghan | {4848BCF6-CE1C-43E1-8878-7F736F44AD8D} | c0a8-008e-131db12ad05-fc705010-278-c9 | AIF-HQ-14016 | MCPA - Mine Clearance Planning Agency | AF/2306/20647/AIF0015 | 410400 | 64.5003 | 32.3877 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {4848BCF6-CE1C-43E1-8878-7F736F44AD8D} |  | High with Victim | High with Victims | Extreme | 56 | CHA | 3 |  |  | 2010-01-04 | No | Open
South | Hilmand | Naw Zad | Khwaja Jamal | {95E77437-C8E0-4FF3-AF19-EAB0DB43D0AB} | c0a8-0057-12c3b89efc4-7c9fdc7f-206fe- | MF-HQ-10561 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2306/20648/MF005 | 21000 | 64.4496 | 32.3685 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-163 | Hilmand Demining Project-04 |  |  |  |  | 1399 | None | {95E77437-C8E0-4FF3-AF19-EAB0DB43D0AB} |  | Low | Critical Infrastracture | Extreme | 0 | SHA | 5 |  |  | 2009-05-25 | No | Open
South | Hilmand | Naw Zad | Naw Zad | {07375AF5-EF9F-4328-9193-EC1D77D4C692} | c0a8-00f6-13518770a67-74d8fa9d-3ec-1f | AIF-15013 | MCPA - Mine Clearance Planning Agency | AF/2306/31829/AIF0063 | 6060 | 64.4827 | 32.3924 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {07375AF5-EF9F-4328-9193-EC1D77D4C692} |  | High with Victim | High with Victims | Extreme | 27 | CHA | 2 |  |  | 2010-12-05 16:30 | No | Open
South | Hilmand | Naw Zad | Shaykh Za'i | {B0E706A8-0ABB-4A27-A224-ED3D178A2FA2} | c0a8-008e-131db106409-bc4753a3-1ec-c6 | AIF-HQ-14040 | MCPA - Mine Clearance Planning Agency | AF/2306/20661/AIF0028 | 378352 | 64.4626 | 32.398 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {B0E706A8-0ABB-4A27-A224-ED3D178A2FA2} |  | High with Victim | High with Victims | Extreme | 879 | CHA | 2 |  |  | 2010-01-08 | No | Open
South | Hilmand | Naw Zad | Shaykh Za'i | {B0E706A8-0ABB-4A27-A224-ED3D178A2FA2} | c0a8-008e-131db118e80-720c1838-22e-69 | AIF-HQ-14042 | MCPA - Mine Clearance Planning Agency | AF/2306/20661/AIF0030 | 424164 | 64.4626 | 32.398 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {B0E706A8-0ABB-4A27-A224-ED3D178A2FA2} |  | High with Victim | High with Victims | Extreme | 681 | CHA | 2 |  |  | 2010-01-08 | No | Open
South | Hilmand | Naw Zad | Shaykh Za'i | {B0E706A8-0ABB-4A27-A224-ED3D178A2FA2} | c0a8-008e-131db11d407-e7b8197c-23f-8f | AIF-HQ-14041 | MCPA - Mine Clearance Planning Agency | AF/2306/20661/AIF0029 | 427064 | 64.4866 | 32.4186 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {B0E706A8-0ABB-4A27-A224-ED3D178A2FA2} |  | High with Victim | High with Victims | Extreme | 353 | CHA | 2 |  |  | 2010-01-09 | No | Open
South | Hilmand | Naw Zad | Shaykh Za'i | {B0E706A8-0ABB-4A27-A224-ED3D178A2FA2} | c0a8-008e-131db12f7e8-6fc2bb5a-28b-eb | AIF-HQ-14043 | MCPA - Mine Clearance Planning Agency | AF/2306/20661/AIF0031 | 479685 | 64.4866 | 32.4186 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {B0E706A8-0ABB-4A27-A224-ED3D178A2FA2} |  | High with Victim | High with Victims | Extreme | 589 | CHA | 2 |  |  | 2010-01-08 | No | Open
South | Hilmand | Naw Zad | Tangi Sufla | {62B07428-85D3-4352-9A57-10F811D08957} | c0a8-008e-131db10a78e-985b80af-1fb-3a | AIF-HQ-14024 | MCPA - Mine Clearance Planning Agency | AF/2306/20638/AIF0014 | 409050 | 64.4626 | 32.398 | Open | UXO Only | UXO Only | MineField |  | MBT Project-167 | Hilmand Demining Project-11 |  |  |  |  | 1397 |  | {62B07428-85D3-4352-9A57-10F811D08957} |  | High with Victim | High with Victims | Extreme | 33 | CHA | 2 |  |  | 2010-01-05 | No | Open
South | Hilmand | Nawa-I- Barak Zayi | Gawhargin | {AFEEC3D1-679F-4738-B3DF-19BF50E5B854} | c0a8-0057-12c3bae4e98-477263bf-377ee- | MF-HQ-10605 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2309/00535/MF002 | 14750 | 64.3378 | 31.4608 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-285 | Hilmand Demining Project-08 |  |  |  |  | 1398 |  | {AFEEC3D1-679F-4738-B3DF-19BF50E5B854} |  | Medium | Critical Infrastracture | High | 676 | SHA | 3 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nawa-I- Barak Zayi | Korkori | {9E1E625E-B37A-4E02-9BDC-A99D718D9A07} | c0a8-0057-12c3b80e80e-6e16f889-1a111- | MF-HQ-10574 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2301/00479/MF121 | 100000 | 64.286 | 31.2802 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-285 | Hilmand Demining Project-08 |  |  |  |  | 1398 |  | {9E1E625E-B37A-4E02-9BDC-A99D718D9A07} |  | Low | Other | High | 0 | SHA | 5 |  |  | 2009-05-25 | No | Open
South | Hilmand | Nawa-I- Barak Zayi | Lawar-gawhargin | {759B0DD6-113C-4CB2-8950-F97FCE3A3ADC} | c0a8-0057-12c3b9fa4e8-6abe805c-2eb52- | MF-HQ-10582 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2309/00356/MF004 | 40000 | 64.3253 | 31.4614 | Open | Mixed | Mixed AT UXO | Converted From SHA |  | MBT Project-285 | Hilmand Demining Project-08 |  |  |  |  | 1398 |  | {759B0DD6-113C-4CB2-8950-F97FCE3A3ADC} |  | Low | Agriculture Blocked | High | 714 | SHA | 4 |  |  | 2009-05-25 | No | Open
South | Hilmand | Reg(Khanshin) | Zamankhan Kalay | {B3056BCC-49CE-42C3-9DF1-9EA951DF277F} | c0a8-0057-12c3b8eda07-94dc412-23d7b-1 | MF-HQ-10570 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2314/20089/MF002 | 120000 | 63.8093 | 30.5591 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-285 | Hilmand Demining Project-08 |  |  |  |  | 1398 |  | {B3056BCC-49CE-42C3-9DF1-9EA951DF277F} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-05-25 | No | Open
South | Hilmand | Reg(Khanshin) | Zamankhan Kalay | {B3056BCC-49CE-42C3-9DF1-9EA951DF277F} | c0a8-0057-12c3bb5e355-fbcc7d83-3bfdf- | MF-HQ-10571 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2314/20089/MF001 | 150000 | 63.8552 | 30.5492 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-285 | Hilmand Demining Project-08 |  |  |  |  | 1398 |  | {B3056BCC-49CE-42C3-9DF1-9EA951DF277F} |  | Medium | Critical Infrastracture | High | 292 | SHA | 3 |  |  | 2009-05-25 | No | Open
South | Hilmand | Sangin | Chaka Kata Zai | {EFF6E9B4-D5A8-4917-94E6-02449F6ACAA0} | c0a8-0057-12c3ba109ce-4f633e3b-2f926- | MF-HQ-10587 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2313/00746/MF029 | 70000 | 64.9214 | 32.1146 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-270 | Hilmand Demining Project-04 AT |  |  |  |  | 1399 |  | {EFF6E9B4-D5A8-4917-94E6-02449F6ACAA0} |  | Low | Agriculture Blocked | Extreme | 68 | SHA | 4 |  |  | 2009-05-25 | No | Open
South | Hilmand | Sangin | Garmab | {95D11C71-49CC-4BF2-96F0-A20CCAE7609B} | c0a8-0009-140384a02a7-f0399487-162-8f | Hz-ID-18087 | MDC - Mine Detection and Dog Center | AF/2313/20295/MF0031 | 6479 | 65.0128 | 32.2308 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-102/A | Hilmand Demining Project-02 AT/A | DOS | Yes |  |  | 1393 | MDC | {95D11C71-49CC-4BF2-96F0-A20CCAE7609B} |  | High with Victim | High with Victims | Extreme | 71 | CHA | 2 |  |  | 2013-07-16 16:30 | No | Planned
South | Hilmand | Sangin | Kaj Gerd | {517293B8-2F85-4E45-8C75-FE97BDDF60F5} | c0a8-0057-12c3b852ffb-5d91c96b-1d268- | MF-HQ-10569 | MDC - Mine Detection and Dog Center | AF/2313/20287/MF0021 | 84579 | 64.9777 | 32.1689 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-102 | Hilmand Demining Project-02 AT | DOS | Yes | 2013-09-28 | 2013-12-19 | 1392-1393 | MDC | {517293B8-2F85-4E45-8C75-FE97BDDF60F5} |  |  |  | Extreme | 380 | CHA | 1 |  |  | 2009-05-25 | No | Planned
South | Hilmand | Sangin | Kaj Gerd | {517293B8-2F85-4E45-8C75-FE97BDDF60F5} | c0a8-0057-12c3b994342-ef1d75a-2aab0-e | MF-HQ-10567 | MDC - Mine Detection and Dog Center | AF/2313/20287/MF0020 | 76340 | 64.9637 | 32.1569 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-102 | Hilmand Demining Project-02 AT | DOS | Yes | 2013-06-29 | 2014-08-29 | 1392-1393 | MDC | {517293B8-2F85-4E45-8C75-FE97BDDF60F5} |  |  |  | Extreme | 151 | CHA | 2 |  |  | 2009-05-25 | No | Planned
South | Hilmand | Sangin | Kaj Gerd | {517293B8-2F85-4E45-8C75-FE97BDDF60F5} | c0a8-0057-12c3bb1acc5-7584fd2b-39832- | MF-HQ-10568 | MDC - Mine Detection and Dog Center | AF/2313/20287/MF0019 | 68928 | 64.9674 | 32.1602 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-102 | Hilmand Demining Project-02 AT | DOS | Yes | 2013-06-29 | 2013-10-10 | 1392-1393 | MDC | {517293B8-2F85-4E45-8C75-FE97BDDF60F5} |  |  |  | Extreme | 101 | CHA | 2 |  |  | 2009-05-25 | No | Planned
South | Hilmand | Sangin | Pan Kelah Janubi | {6B5B939E-085B-47A5-BF5F-4770D892C1C9} | c0a8-0057-12c3b8ed833-632d28ce-23d67- | MF-HQ-10590 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2313/00804/MF024 | 20000000 | 64.835 | 32.0368 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-270 | Hilmand Demining Project-04 AT |  |  |  |  | 1399 |  | {6B5B939E-085B-47A5-BF5F-4770D892C1C9} |  | Medium | Critical Infrastracture | Extreme | 7392 | SHA | 3 |  |  | 2009-05-25 | No | Open
South | Hilmand | Sangin | Qarya-I-Hirati | {FDA35691-661A-42C4-8B7E-014DF60FDB9B} | c0a8-0057-12c3b83c1c2-86336181-1c1a3- | MF-HQ-10611 | MDC - Mine Detection and Dog Center | AF/2313/00804/MF0026 | 115468 | 64.9721 | 32.1653 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-102/A | Hilmand Demining Project-02 AT/A | DOS | Yes | 2013-12-22 | 2014-08-30 | 1393 | MDC | {FDA35691-661A-42C4-8B7E-014DF60FDB9B} |  | Medium | Critical Infrastracture | Extreme | 151 | CHA | 3 |  |  | 2009-05-25 | No | Planned
South | Hilmand | Sangin | Qarya-I-Hirati | {FDA35691-661A-42C4-8B7E-014DF60FDB9B} | c0a8-0057-12c3b8687d7-33e9306b-1e12d- | MF-HQ-10615 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2313/00804/MF028 | 120000 | 64.9543 | 32.1399 | Open | Mixed Mine | Mixed Mine | Converted From SHA | 1393 | MBT Project-102/A | Hilmand Demining Project-02 AT/A | DOS | Yes |  |  | 1393 | MDC | {FDA35691-661A-42C4-8B7E-014DF60FDB9B} |  | Low | Critical Infrastracture | Extreme | 119 | SHA | 5 |  |  | 2009-05-25 | No | Planned
South | Hilmand | Sangin | Qarya-I-Hirati | {FDA35691-661A-42C4-8B7E-014DF60FDB9B} | c0a8-0057-12c3bae1688-3037f2bc-375d5- | MF-HQ-10612 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2313/00804/MF027 | 160000 | 64.9543 | 32.1399 | Open | Mixed Mine | Mixed Mine | Converted From SHA | 1393 | MBT Project-102/A | Hilmand Demining Project-02 AT/A | DOS | Yes |  |  | 1393 | MDC | {FDA35691-661A-42C4-8B7E-014DF60FDB9B} |  | Low | Critical Infrastracture | Extreme | 292 | SHA | 4 |  |  | 2009-05-25 | No | Planned
South | Hilmand | Sangin | Sangin | {73FF8FF8-9809-47A9-8C2A-0F39C31D6520} | c0a8-0057-12c3bb6b13b-e8900e15-3c6f6- | MF-HQ-10588 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2313/20266/MF0030 | 25000000 | 64.8419 | 32.0648 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-237 | Hilmand Demining Project-01 AT |  |  |  |  | 1398 |  | {73FF8FF8-9809-47A9-8C2A-0F39C31D6520} | , | High with Victim | High with Victims | Extreme | 11155 | SHA | 2 |  |  | 2009-05-25 | No | Open
South | Hilmand | Sangin | Sarpuza | {DA37B7E4-7C39-4874-B43E-6D7AFFE6AD71} | c0a8-0009-142e557fdbb-44c36aea-65b8-7 | Hz-ID-18257 | MDC - Mine Detection and Dog Center | AF/2313/20255/MF0032 | 192609 | 64.9869 | 32.193 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-102 | Hilmand Demining Project-02 AT | DOS | Yes | 2014-02-24 | 2014-08-25 | 1392-1393 | MDC | {DA37B7E4-7C39-4874-B43E-6D7AFFE6AD71} |  | Medium | Critical Infrastracture | Extreme | 2137 | CHA | 3 |  |  | 2013-11-15 16:30 | No | Planned
South | Hilmand | Sangin | Sarpuza | {DA37B7E4-7C39-4874-B43E-6D7AFFE6AD71} | c0a8-0009-142e55886d7-a4e49fa-65ea-5b | Hz-ID-18258 | MDC - Mine Detection and Dog Center | AF/2313/20255/MF0033 | 82105 | 64.9852 | 32.1876 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-102/A | Hilmand Demining Project-02 AT/A | DOS | Yes | 2014-04-25 | 2014-06-30 | 1393 | MDC | {DA37B7E4-7C39-4874-B43E-6D7AFFE6AD71} |  | Medium | Critical Infrastracture | Extreme | 203 | CHA | 3 |  |  | 2013-11-12 16:30 | No | Planned
South | Hilmand | Sangin | Sarpuza | {DA37B7E4-7C39-4874-B43E-6D7AFFE6AD71} | c0a8-0009-14665748270-59002531-80b0-c | Hz-ID-18756 | MDC - Mine Detection and Dog Center | AF/2313/20255/MF0035 | 37397 | 64.9883 | 32.1995 | Open | AT Only | AT Only | MineField |  | MBT Project-270 | Hilmand Demining Project-04 AT |  |  |  |  | 1399 |  | {DA37B7E4-7C39-4874-B43E-6D7AFFE6AD71} |  | Medium | Critical Infrastracture | Extreme | 2093 | CHA | 3 |  |  | 2014-04-24 16:30 | No | Open
South | Hilmand | Sangin | Sarpuza | {DA37B7E4-7C39-4874-B43E-6D7AFFE6AD71} | c0a8-0057-12c3bb0afb5-2b5412bc-38eca- | MF-HQ-10592 | MDC - Mine Detection and Dog Center | AF/2313/20255/MF0023 | 113332 | 64.9879 | 32.1996 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-102 | Hilmand Demining Project-02 AT | DOS | Yes | 2013-10-09 | 2014-01-22 | 1392-1393 | MDC | {DA37B7E4-7C39-4874-B43E-6D7AFFE6AD71} |  |  |  | Extreme | 2658 | CHA | 3 |  |  | 2009-05-25 | No | Planned
South | Hilmand | Sangin | Sarpuza | {DA37B7E4-7C39-4874-B43E-6D7AFFE6AD71} | c0a8-0057-12c3bb25f8e-2c94bbb1-39ef8- | MF-HQ-10594 | MDC - Mine Detection and Dog Center | AF/2313/20255/MF0022 | 58412 | 64.9931 | 32.2044 | Closed | AT Only | AT Only | MineField | 1392/1393 | MBT Project-102 | Hilmand Demining Project-02 AT | DOS | Yes | 2014-01-01 | 2014-04-25 | 1392-1393 | MDC | {DA37B7E4-7C39-4874-B43E-6D7AFFE6AD71} |  |  |  | Extreme | 85 | CHA | 4 |  |  | 2009-05-25 | No | Planned
South | Kandahar | Arghandab | Babur | {33DB2BD3-D79A-4337-84DE-0C67CDEA355A} | c0a8-0009-13b5f504e33-1e99c969-29e9-c | Hz-ID-17431 | EODT- TECHNOLOGEY,INC | AF/2404/22182/MF0063 | 147445 | 65.6814 | 31.7332 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-04-01 | 2013-04-23 | 1392 | EODT | {33DB2BD3-D79A-4337-84DE-0C67CDEA355A} |  |  |  | Substantial | 15 | CHA | 2 |  |  | 2012-10-18 16:30 | No | Complete
South | Kandahar | Arghandab | Babur | {33DB2BD3-D79A-4337-84DE-0C67CDEA355A} | c0a8-0009-13c19a7001f-5c2a98af-5eb1-f | Hz-ID-17554 | EODT- TECHNOLOGEY,INC | AF/2404/22182/MF0062 | 126808 | 65.6814 | 31.7332 | Closed | AT Only | AT Only | MineField | 1391 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-03-05 | 2013-03-30 | 1392 | EODT | {33DB2BD3-D79A-4337-84DE-0C67CDEA355A} |  |  |  | Substantial | 28 | CHA | 2 |  |  | 2012-10-15 16:30 | No | Complete
South | Kandahar | Arghandab | Babur | {33DB2BD3-D79A-4337-84DE-0C67CDEA355A} | c0a8-0009-14028cd7b0b-34838360-86d-b0 | Hz-ID-18070 | DAFA - Demining Agency for Afghanistan | AF/2404/22182/MF0072 | 33119 | 65.6689 | 31.7481 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {33DB2BD3-D79A-4337-84DE-0C67CDEA355A} |  | High with Victim | High with Victims | Substantial | 1 | CHA | 2 |  |  | 2013-06-15 16:30 | No | Open
South | Kandahar | Arghandab | Babur | {33DB2BD3-D79A-4337-84DE-0C67CDEA355A} | c0a8-0009-1402966189e-70edfe44-34-b6e | Hz-ID-18072 | DAFA - Demining Agency for Afghanistan | AF/2404/22182/MF0074 | 35141 | 65.6685 | 31.7484 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {33DB2BD3-D79A-4337-84DE-0C67CDEA355A} |  | High with Victim | High with Victims | Substantial | 2 | CHA | 2 |  |  | 2013-06-16 16:30 | No | Open
South | Kandahar | Arghandab | Babur | {33DB2BD3-D79A-4337-84DE-0C67CDEA355A} | c0a8-0009-140296ad9c9-4770b756-4f-ed5 | Hz-ID-18071 | DAFA - Demining Agency for Afghanistan | AF/2404/22182/MF0073 | 63650 | 65.6682 | 31.752 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {33DB2BD3-D79A-4337-84DE-0C67CDEA355A} |  | High with Victim | High with Victims | Substantial | 1 | CHA | 2 |  |  | 2013-06-15 16:30 | No | Open
South | Kandahar | Arghandab | Hajikhodayrahm Kalacha | {F6D4CBE9-3E5E-47B1-B047-645366D8BB52} | c0a8-0009-1402960cbcb-75ac511d-2-7c40 | Hz-ID-18073 | DAFA - Demining Agency for Afghanistan | AF/2404/22178/MF0075 | 7074 | 65.6226 | 31.6933 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {F6D4CBE9-3E5E-47B1-B047-645366D8BB52} |  | Low | Agriculture Blocked | Substantial | 324 | CHA | 5 |  |  | 2013-06-25 16:30 | No | Open
South | Kandahar | Arghandab | Jelawur | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} | c0a8-0009-14037eca550-f6b9160-2c3a-1c | Hz-ID-18078 | DAFA - Demining Agency for Afghanistan | AF/2404/22181/MF0065 | 181680 | 65.6513 | 31.7224 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} |  | High with Victim | High with Victims | Substantial | 5 | CHA | 1 |  |  | 2013-06-19 16:30 | No | Open
South | Kandahar | Arghandab | Jelawur | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} | c0a8-0009-14037ee4258-8103ef28-2c77-a | Hz-ID-18079 | DAFA - Demining Agency for Afghanistan | AF/2404/22181/MF0064 | 41657 | 65.6524 | 31.7179 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} |  | High with Victim | High with Victims | Substantial | 32 | CHA | 1 |  |  | 2013-06-19 16:30 | No | Open
South | Kandahar | Arghandab | Jelawur | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} | c0a8-0009-14037ef0fa4-895e686b-2c9a-7 | Hz-ID-18080 | DAFA - Demining Agency for Afghanistan | AF/2404/22181/MF0066 | 18695 | 65.6566 | 31.7259 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} |  | High with Victim | High with Victims | Substantial | 8 | CHA | 1 |  |  | 2013-06-19 16:30 | No | Open
South | Kandahar | Arghandab | Jelawur | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} | c0a8-0009-14037efd236-f5a426b1-2cb9-2 | Hz-ID-18081 | DAFA - Demining Agency for Afghanistan | AF/2404/22181/MF0067 | 7083 | 65.6512 | 31.723 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} |  | High with Victim | High with Victims | Substantial | 5 | CHA | 1 |  |  | 2013-06-20 16:30 | No | Open
South | Kandahar | Arghandab | Jelawur | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} | c0a8-0009-14037f0683d-7608115a-2cd5-c | Hz-ID-18082 | DAFA - Demining Agency for Afghanistan | AF/2404/22181/MF0068 | 10657 | 65.6519 | 31.7256 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} |  | High with Victim | High with Victims | Substantial | 13 | CHA | 1 |  |  | 2013-07-30 16:30 | No | Open
South | Kandahar | Arghandab | Jelawur | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} | c0a8-0009-14037f0e133-4e47f4e6-2cf0-8 | Hz-ID-18083 | DAFA - Demining Agency for Afghanistan | AF/2404/22181/MF0069 | 34861 | 65.6666 | 31.7189 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} |  | High with Victim | High with Victims | Substantial | 858 | CHA | 1 |  |  | 2013-06-19 16:30 | No | Open
South | Kandahar | Arghandab | Jelawur | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} | c0a8-0009-14037f1748c-b6d44d8e-2d0d-8 | Hz-ID-18084 | DAFA - Demining Agency for Afghanistan | AF/2404/22181/MF0070 | 149491 | 65.6486 | 31.7224 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} |  | High with Victim | High with Victims | Substantial | 34 | CHA | 1 |  |  | 2013-06-22 16:30 | No | Open
South | Kandahar | Arghandab | Jelawur | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} | c0a8-0009-14038340ad7-e45c3585-96-1bd | Hz-ID-18085 | DAFA - Demining Agency for Afghanistan | AF/2404/22181/MF0071 | 158942 | 65.6468 | 31.7176 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} |  | High with Victim | High with Victims | Substantial | 317 | CHA | 1 |  |  | 2013-06-22 16:30 | No | Open
South | Kandahar | Arghandab | Jelawur | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} | c0a8-0057-12c3bafad38-2306fcb4-3851a- | MF-HQ-10878 | EODT- TECHNOLOGEY,INC | AF/2404/22181/MF0058 | 25475 | 65.6325 | 31.7131 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-04-17 | 2013-04-23 | 1392 | EODT | {53B3C3F4-A296-43FE-B7A7-A3A0EE2F8CA5} |  |  |  | Substantial | 11 | CHA | 2 |  |  | 2009-06-03 | No | Complete
South | Kandahar | Arghandab | Petaway | {C1D4FB98-DBE2-4E4E-A7CF-8A99D7F2BD69} | c0a8-00f6-13904607d6c-82d1c036-113-10 | Hz-ID-17145 | EODT- TECHNOLOGEY,INC | AF/2404/22157/MF0060 | 56018 | 65.5457 | 31.6394 | Closed | AT Only | AT Only | MineField | 1391 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-01-09 | 2013-02-04 | 1392 | EODT | {C1D4FB98-DBE2-4E4E-A7CF-8A99D7F2BD69} |  |  |  | Substantial | 67 | CHA | 5 |  |  | 2012-07-14 16:30 | No | Complete
South | Kandahar | Arghandab | Petaway | {C1D4FB98-DBE2-4E4E-A7CF-8A99D7F2BD69} | c0a8-00f6-139047dc8f1-4a353b6d-245-5d | Hz-ID-17147 | EODT- TECHNOLOGEY,INC | AF/2404/22157/MF0061 | 59046 | 65.5456 | 31.6338 | Closed | AT Only | AT Only | MineField | 1391 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-01-31 | 2013-02-18 | 1392 | EODT | {C1D4FB98-DBE2-4E4E-A7CF-8A99D7F2BD69} |  |  |  | Substantial | 352 | CHA | 4 |  |  | 2012-07-21 16:30 | No | Complete
South | Kandahar | Arghandab | Petaway | {C1D4FB98-DBE2-4E4E-A7CF-8A99D7F2BD69} | c0a8-00f6-13904876d6f-6b280868-2ca-8d | Hz-ID-17144 | EODT- TECHNOLOGEY,INC | AF/2404/22157/MF0059 | 50087 | 65.5416 | 31.6372 | Closed | AT Only | AT Only | MineField | 1391 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-01-02 | 2013-01-26 | 1392 | EODT | {C1D4FB98-DBE2-4E4E-A7CF-8A99D7F2BD69} |  |  |  | Substantial | 16 | CHA | 3 |  |  | 2012-07-14 16:30 | No | Complete
South | Kandahar | Arghandab | Sa'idano Kalacha | {05FFDDC9-BFE6-4120-A26B-74E1D96A699F} | c0a8-0009-1402936cb97-40ee4b3d-df8-9c | Hz-ID-18074 | DAFA - Demining Agency for Afghanistan | AF/2404/22179/MF0076 | 26898 | 65.6351 | 31.7003 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {05FFDDC9-BFE6-4120-A26B-74E1D96A699F} |  | Medium | Critical Infrastracture | Substantial | 42 | CHA | 5 |  |  | 2013-06-23 16:30 | No | Open
South | Kandahar | Arghandab | Sa'idano Kalacha | {05FFDDC9-BFE6-4120-A26B-74E1D96A699F} | c0a8-0009-140293a8973-f0df4938-e6f-98 | Hz-ID-18075 | DAFA - Demining Agency for Afghanistan | AF/2404/22179/MF0077 | 192878 | 65.628 | 31.707 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {05FFDDC9-BFE6-4120-A26B-74E1D96A699F} |  | Low | Agriculture Blocked | Substantial | 78 | CHA | 5 |  |  | 2013-06-24 16:30 | No | Open
South | Kandahar | Arghandab | Shuyene Wusta | {92FFB578-AF82-46C8-AF92-9153CDF3A21F} | c0a8-0009-14029dcda51-b2a4d40e-55a-d9 | Hz-ID-18077 | DAFA - Demining Agency for Afghanistan | AF/2404/22191/MF0080 | 107481 | 65.6893 | 31.7351 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {92FFB578-AF82-46C8-AF92-9153CDF3A21F} |  | Medium | Critical Infrastracture | Substantial | 219 | CHA | 3 |  |  | 2013-06-10 16:30 | No | Open
South | Kandahar | Arghandab | Shuyene Wusta | {92FFB578-AF82-46C8-AF92-9153CDF3A21F} | c0a8-0009-14037eb32a2-759d5fdd-2c1d-5 | Hz-ID-18076 | DAFA - Demining Agency for Afghanistan | AF/2404/22191/MF0078 | 102355 | 65.6893 | 31.7351 | Open | AT Only | AT Only | MineField |  | MBT Project-184 | Kandahar Demining Project-04 AT |  |  |  |  | 1394 |  | {92FFB578-AF82-46C8-AF92-9153CDF3A21F} |  | Medium | Critical Infrastracture | Substantial | 243 | CHA | 3 |  |  | 2013-06-10 16:30 | No | Open
South | Kandahar | Arghistan | Akizay | {4C23AFF3-B707-4720-9315-1144ACB84A75} | c0a8-0009-1455fee63e3-687e92cc-2cf2-2 | Hz-ID-18578 | DAFA - Demining Agency for Afghanistan | AF/2412/21613/MF0133 | 600000 | 66.8066 | 31.6336 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {4C23AFF3-B707-4720-9315-1144ACB84A75} |  | Low | Agriculture Blocked | High | 41 | SHA | 5 |  |  | 2013-10-09 16:30 | No | Open
South | Kandahar | Arghistan | Alghamchi | {B450C773-8B81-4D0E-AAF6-D9AD5C421B76} | c0a8-0009-1453fa6bdfa-a519dca0-7e3-70 | Hz-ID-18575 | DAFA - Demining Agency for Afghanistan | AF/2412/21830/MF0130 | 1000000 | 66.7535 | 31.6356 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {B450C773-8B81-4D0E-AAF6-D9AD5C421B76} |  | Low | Agriculture Blocked | High | 13 | SHA | 5 |  |  | 2013-10-05 16:30 | No | Open
South | Kandahar | Arghistan | Bakalzai | {83F1B2FE-0C97-49E4-A217-0D402B03301B} | c0a8-0009-13c1de90751-ac5012fc-789a-b | Hz-ID-17570 | EODT- TECHNOLOGEY,INC | AF/2412/21657/MF0108 | 14595 | 66.517 | 31.5352 | Open | AT Only | AT Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No | 2013-07-01 | 2013-07-04 | 1396 |  | {83F1B2FE-0C97-49E4-A217-0D402B03301B} |  | High Requested | Resettlment/Local Request | High | 75 | CHA | 5 | Yes |  | 2012-11-25 16:30 | No | Open
South | Kandahar | Arghistan | Bakalzai | {83F1B2FE-0C97-49E4-A217-0D402B03301B} | c0a8-0009-13c1e044511-a3408b26-7a45-8 | Hz-ID-17571 | EODT- TECHNOLOGEY,INC | AF/2412/21657/MF0109 | 35794 | 66.517 | 31.5352 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-07-06 | 2013-07-14 | 1392 | EODT | {83F1B2FE-0C97-49E4-A217-0D402B03301B} |  |  |  | High | 0 | CHA | 5 | Yes |  | 2012-11-25 16:30 | No | Complete
South | Kandahar | Arghistan | Bakalzai | {83F1B2FE-0C97-49E4-A217-0D402B03301B} | c0a8-0009-13c1e1df957-ace66a00-7e24-1 | Hz-ID-17572 | EODT- TECHNOLOGEY,INC | AF/2412/21657/MF0110 | 15403 | 66.521 | 31.5319 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-07-15 | 2013-07-18 | 1392 | EODT | {83F1B2FE-0C97-49E4-A217-0D402B03301B} |  |  |  | High | 0 | CHA | 5 | Yes |  | 2012-11-26 16:30 | No | Complete
South | Kandahar | Arghistan | Bakalzai | {83F1B2FE-0C97-49E4-A217-0D402B03301B} | c0a8-0009-13c1ea6f6e6-3b8e0d36-8417-e | Hz-ID-17575 | EODT- TECHNOLOGEY,INC | AF/2412/21657/MF0111 | 66332 | 66.5236 | 31.5306 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-07-20 | 2013-08-05 | 1392 | EODT | {83F1B2FE-0C97-49E4-A217-0D402B03301B} |  |  |  | High | 0 | CHA | 5 | Yes |  | 2012-11-26 16:30 | No | Complete
South | Kandahar | Arghistan | Bakalzai | {83F1B2FE-0C97-49E4-A217-0D402B03301B} | c0a8-0009-13c1f08d84d-d61a0733-635-a5 | Hz-ID-17582 | EODT- TECHNOLOGEY,INC | AF/2412/21657/MF0112 | 48314 | 66.537 | 31.5275 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-07-23 | 2013-08-13 | 1392 | EODT | {83F1B2FE-0C97-49E4-A217-0D402B03301B} |  |  |  | High | 0 | CHA | 5 | Yes |  | 2012-11-28 16:30 | No | Complete
South | Kandahar | Arghistan | Bakalzai | {83F1B2FE-0C97-49E4-A217-0D402B03301B} | c0a8-0009-13c1f0cc4cb-ea7296f3-67e-38 | Hz-ID-17584 | EODT- TECHNOLOGEY,INC | AF/2412/21657/MF0113 | 49962 | 66.5407 | 31.5234 | Open | AT Only | AT Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {83F1B2FE-0C97-49E4-A217-0D402B03301B} |  | High Requested | Resettlment/Local Request | High | 0 | CHA | 5 | Yes |  | 2012-11-29 16:30 | No | Open
South | Kandahar | Arghistan | Bandaki | {11E10620-917C-48E7-993E-4015F56222D1} | c0a8-0009-1453fa465d2-70e25e67-77d-26 | Hz-ID-18574 | DAFA - Demining Agency for Afghanistan | AF/2412/21809/BF0129 | 120000 | 66.4511 | 31.757 | Open | UXO Only | UXO Only | BF |  | MBT Project-305 | Kandahar Demining Project-06 AT |  |  |  |  | 1394 |  | {11E10620-917C-48E7-993E-4015F56222D1} |  | Medium | Agriculture Blocked | High | 0 | SHA | 3 |  |  | 2013-10-06 16:30 | No | Open
South | Kandahar | Arghistan | Bolan (1) | {A607DB02-B724-4181-B69B-6122FFC6540C} | c0a8-0057-12c3b809483-61feebcf-19d9d- | MF-HQ-10887 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21807/MF051 | 180000 | 66.4161 | 31.6625 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-305 | Kandahar Demining Project-06 AT |  | No |  |  | 1394 | Blank | {A607DB02-B724-4181-B69B-6122FFC6540C} |  | High with Victim | High with Victims | High | 156 | SHA | 2 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Bolan (1) | {A607DB02-B724-4181-B69B-6122FFC6540C} | c0a8-0057-12c3ba47fce-c937f14-31acb-9 | MF-HQ-10888 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21807/MF052 | 180000 | 66.5345 | 31.76 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-305 | Kandahar Demining Project-06 AT |  | No |  |  | 1394 | Blank | {A607DB02-B724-4181-B69B-6122FFC6540C} |  | High with Victim | High with Victims | High | 192 | SHA | 2 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Chawday | {0964B7DF-E89D-4070-A53F-CB4EE1183F7A} | c0a8-0009-142e54dbde2-57f076e2-63ce-b | Hz-ID-18242 | DAFA - Demining Agency for Afghanistan | AF/2412/21751/MF0124 | 680838 | 66.7217 | 31.4557 | Open | AT Only | AT Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {0964B7DF-E89D-4070-A53F-CB4EE1183F7A} |  | Low | Agriculture Blocked | High | 11 | CHA | 5 |  |  | 2013-09-03 16:30 | No | Open
South | Kandahar | Arghistan | Chawday | {0964B7DF-E89D-4070-A53F-CB4EE1183F7A} | c0a8-0009-142e54e82c6-5bf7b8f2-6417-a | Hz-ID-18243 | DAFA - Demining Agency for Afghanistan | AF/2412/21751/MF0125 | 787024 | 66.717 | 31.4405 | Open | AT Only | AT Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {0964B7DF-E89D-4070-A53F-CB4EE1183F7A} |  | Low | Critical Infrastracture | High | 0 | CHA | 5 |  |  | 2013-09-04 16:30 | No | Open
South | Kandahar | Arghistan | De Ghreh Kalay Makayan | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} | c0a8-0057-12c3b7c68ec-8bb324d-16e90-9 | MF-HQ-10835 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21632/MF0065 | 445312 | 66.381 | 31.413 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-133 | Kandahar Demining Project-03 |  |  |  |  | 1400 | None | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} |  | Low | Agriculture Blocked | High | 58 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | De Ghreh Kalay Makayan | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} | c0a8-0057-12c3b85b205-c212bd96-1d80f- | MF-HQ-10841 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21632/MF0062 | 245000 | 66.381 | 31.413 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-133 | Kandahar Demining Project-03 |  |  |  |  | 1400 | None | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | De Ghreh Kalay Makayan | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} | c0a8-0057-12c3b89de19-602a845b-2063c- | MF-HQ-10845 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21632/MF0063 | 131250 | 66.371 | 31.42 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-133 | Kandahar Demining Project-03 |  |  |  |  | 1400 | None | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} |  | Low | Agriculture Blocked | High | 27 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | De Ghreh Kalay Makayan | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} | c0a8-0057-12c3b99be58-e62ccce9-2afcc- | MF-HQ-10853 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21632/MF0067 | 560000 | 66.3826 | 31.4221 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-133 | Kandahar Demining Project-03 |  |  |  |  | 1400 | None | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} |  | Low | Agriculture Blocked | High | 111 | SHA | 4 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | De Ghreh Kalay Makayan | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} | c0a8-0057-12c3ba8bb0f-37a873c4-343a0- | MF-HQ-10849 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21632/MF0066 | 272000 | 66.3825 | 31.4221 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-133 | Kandahar Demining Project-03 |  |  |  |  | 1400 | None | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} |  | Low | Agriculture Blocked | High | 122 | SHA | 4 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | De Ghreh Kalay Makayan | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} | c0a8-0057-12c3bab1cc7-cc7fbe6d-35983- | MF-HQ-10837 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21632/MF0064 | 255937 | 66.381 | 31.413 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-133 | Kandahar Demining Project-03 |  |  |  |  | 1400 |  | {8A7AF269-A14D-4A1E-B304-7A4B16C345C4} | , | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Derga | {31AC6B26-1ED9-4752-8FB7-E4E6A42A671B} | c0a8-0057-12c3ba562ea-e4b0d13b-3236e- | MF-HQ-10806 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21639/MF061 | 243750 | 66.2559 | 31.5358 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No | 2012-08-11 | 2012-10-30 | 1396 |  | {31AC6B26-1ED9-4752-8FB7-E4E6A42A671B} |  | Low | Agriculture Blocked | High | 10 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Garet | {5EF53E7C-9E2B-4CA2-AD79-E57CBBE97E59} | c0a8-0057-12c3b8ceed3-a25650db-22866- | MF-HQ-10808 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21741/MF0073 | 50000 | 66.7425 | 31.298 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-305 | Kandahar Demining Project-06 AT |  | No |  |  | 1394 |  | {5EF53E7C-9E2B-4CA2-AD79-E57CBBE97E59} |  | Medium | Water Blocked | High | 72 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Garet | {5EF53E7C-9E2B-4CA2-AD79-E57CBBE97E59} | c0a8-0057-12c3bad3f9d-1b8bddce-36de7- | MF-HQ-10811 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21741/MF0074 | 136000 | 66.7425 | 31.298 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-305 | Kandahar Demining Project-06 AT |  | No |  |  | 1394 |  | {5EF53E7C-9E2B-4CA2-AD79-E57CBBE97E59} |  | Medium | Critical Infrastracture | High | 0 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Kac | {D794D5A1-88D9-428E-A69B-B44F95EBC81B} | c0a8-00f6-1384180b3bc-278f7093-16e1-f | Hz-ID-17079 | EODT- TECHNOLOGEY,INC | AF/2412/21867/MF0091 | 97343 | 66.3667 | 31.5865 | Open | AT Only | AT Only | MineField | Blank | MBT Project-305 | Kandahar Demining Project-06 AT |  | No | 2013-01-13 | 2013-02-11 | 1394 | Blank | {D794D5A1-88D9-428E-A69B-B44F95EBC81B} |  | Medium | Critical Infrastracture | High | 144 | CHA | 3 |  |  | 2012-03-26 16:30 | No | Open
South | Kandahar | Arghistan | Kalacha | {E7581E18-C389-4A3F-A3A9-73C164EFE479} | c0a8-0057-12c3bb84d57-5c131ee7-3d54d- | MF-HQ-10824 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21655/MF0071 | 53125 | 66.3772 | 31.6008 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-305 | Kandahar Demining Project-06 AT |  | No | 2012-08-11 | 2012-09-03 | 1394 |  | {E7581E18-C389-4A3F-A3A9-73C164EFE479} |  | Medium | Agriculture Blocked | High | 11 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Karmalay | {9D9A36F2-DC44-4108-B5F8-551A6B527B1C} | c0a8-0057-12c3b97c4e9-a8a23a11-29ae3- | MF-HQ-10778 | DAFA - Demining Agency for Afghanistan | AF/2412/21641/MF0059 | 104409 | 66.3248 | 31.5052 | Open | AT Only | AT Only | MineField |  | MBT Project-133 | Kandahar Demining Project-03 |  |  |  |  | 1400 | None | {9D9A36F2-DC44-4108-B5F8-551A6B527B1C} |  | High Requested | Resettlment/Local Request | High | 0 | CHA | 5 | Yes |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Khun Darrah | {10716818-32A9-4D9E-B94B-C9A881B839E1} | c0a8-0009-1453faaa3ed-da8ac2de-8b7-52 | Hz-ID-18576 | DAFA - Demining Agency for Afghanistan | AF/2412/21853/MF0131 | 500000 | 66.9422 | 31.6524 | Open | Mixed | Mixed AP AT UXO | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {10716818-32A9-4D9E-B94B-C9A881B839E1} |  | Low | Other | High | 0 | SHA | 5 |  |  | 2013-10-08 16:30 | No | Open
South | Kandahar | Arghistan | Laday | {BFDFFD03-1161-4AA8-A7D5-63D0F1AEA81C} | c0a8-0009-142e54d1342-1a44bc33-63b1-6 | Hz-ID-18241 | DAFA - Demining Agency for Afghanistan | AF/2412/21779/MF0128 | 8512 | 66.8492 | 31.5222 | Open | AP Only | AP Only | MineField |  | MBT Project-305 | Kandahar Demining Project-06 AT |  |  |  |  | 1394 |  | {BFDFFD03-1161-4AA8-A7D5-63D0F1AEA81C} |  | Medium | Critical Infrastracture | High | 0 | CHA | 3 |  |  | 2013-07-14 16:30 | No | Open
South | Kandahar | Arghistan | Lwar Sherzay | {9EA10DCF-C90A-4558-9986-BADD04FF893D} | c0a8-0057-12c3b9f5cb3-9cfecab5-2e8a2- | MF-HQ-10802 | DAFA - Demining Agency for Afghanistan | AF/2412/21703/MF0058 | 309492 | 66.7391 | 31.4546 | Open | AP Only | AP Only | MineField |  | MBT Project-133 | Kandahar Demining Project-03 |  | No |  |  | 1400 |  | {9EA10DCF-C90A-4558-9986-BADD04FF893D} |  | High Requested | Resettlment/Local Request | High | 0 | CHA | 5 | Yes |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Mayu | {5C134813-34DE-4DBC-A51A-3874AF9A49C7} | c0a8-0009-1453fa1dd95-d1dcfe15-748-26 | Hz-ID-18573 | DAFA - Demining Agency for Afghanistan | AF/2412/21810/MF0128 | 500000 | 66.4152 | 31.745 | Open | AT Only | AT Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {5C134813-34DE-4DBC-A51A-3874AF9A49C7} |  | Low | Comunity Centers | High | 21 | SHA | 5 |  |  | 2013-10-07 16:30 | No | Open
South | Kandahar | Arghistan | Mohammadah | {A3BE073F-8AEE-4F71-9386-7326724F6CBE} | c0a8-0009-142e550707d-367575d5-6489-9 | Hz-ID-18246 | DAFA - Demining Agency for Afghanistan | AF/2412/21723/MF0123 | 186215 | 66.7073 | 31.4759 | Open | AT Only | AT Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {A3BE073F-8AEE-4F71-9386-7326724F6CBE} |  | Low | Critical Infrastracture | High | 3 | CHA | 5 |  |  | 2013-09-01 16:30 | No | Open
South | Kandahar | Arghistan | Ngande | {DF16EE1F-A198-4E07-BB53-7A5F08EC0630} | c0a8-0057-12c3b82a6e5-c8d88a22-1b4eb- | MF-HQ-10891 | DAFA - Demining Agency for Afghanistan | AF/2412/21650/MF0081 | 400380 | 66.2733 | 31.5633 | Open | AT Only | AT Only | MineField |  | MBT Project-133 | Kandahar Demining Project-03 |  | No |  |  | 1400 |  | {DF16EE1F-A198-4E07-BB53-7A5F08EC0630} |  | High Requested | Resettlment/Local Request | High | 4 | CHA | 5 | Yes |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Obezhan | {BF57D1F2-37C6-4B42-9C51-9AAAEDAE9498} | c0a8-0057-12c3b92fae1-8225aa1e-26869- | MF-HQ-10783 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21698/MF042 | 8750 | 66.7047 | 31.2896 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-305 | Kandahar Demining Project-06 AT |  | No |  |  | 1394 |  | {BF57D1F2-37C6-4B42-9C51-9AAAEDAE9498} |  | Medium | Water Blocked | High | 7 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Pay Kariz | {7AB04F34-1135-46F6-A0C2-424E84709693} | c0a8-0057-12c3b8edbbb-31347263-23d94- | MF-HQ-10762 | DAFA - Demining Agency for Afghanistan | AF/2412/21645/MF0045 | 195539 | 66.3432 | 31.4845 | Open | AT Only | AT Only | MineField |  | MBT Project-133 | Kandahar Demining Project-03 |  | No |  |  | 1400 |  | {7AB04F34-1135-46F6-A0C2-424E84709693} | , | High Requested | Resettlment/Local Request | High | 0 | CHA | 5 | Yes |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Potey | {CADB9EF8-CFF7-4D5C-96DF-DF34C8DCDE41} | c0a8-0009-1453facd8cd-b2ff12fd-99b-60 | Hz-ID-18577 | DAFA - Demining Agency for Afghanistan | AF/2412/21707/BF0132 | 600000 | 66.5131 | 31.4524 | Open | UXO Only | UXO Only | BF |  | MBT Project-305 | Kandahar Demining Project-06 AT |  |  |  |  | 1394 |  | {CADB9EF8-CFF7-4D5C-96DF-DF34C8DCDE41} |  | Medium | Agriculture Blocked | High | 105 | SHA | 3 |  |  | 2013-10-08 16:30 | No | Open
South | Kandahar | Arghistan | Qaderkhel | {702E8F53-9C04-43F4-92BA-3D8F5A3BA692} | c0a8-0057-12c3b9f5acf-bb1e3649-2e891- | MF-HQ-10774 | DAFA - Demining Agency for Afghanistan | AF/2412/21712/MF0043 | 24555 | 66.5182 | 31.5775 | Open | AT Only | AT Only | MineField |  | MBT Project-133 | Kandahar Demining Project-03 |  | No |  |  | 1400 |  | {702E8F53-9C04-43F4-92BA-3D8F5A3BA692} |  | High Requested | Resettlment/Local Request | High | 25 | CHA | 4 | Yes |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Qal'a-i-Amin | {A77CE0D4-3DD6-4165-A587-C5A888183191} | c0a8-0057-12c3b7dead4-3ce973dc-17ff0- | MF-HQ-10798 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21653/MF0082 | 60000 | 66.3908 | 31.6172 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-133 | Kandahar Demining Project-03 |  | No |  |  | 1400 |  | {A77CE0D4-3DD6-4165-A587-C5A888183191} | , | High with Victim | High with Victims | High | 0 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Salamjan Kalay | {3B98F8D6-FC21-4DB2-9C80-42D1517971F1} | c0a8-0009-142e557618c-49cbad7c-658a-9 | Hz-ID-18255 | DAFA - Demining Agency for Afghanistan | AF/2412/21681/MF0127 | 145859 | 66.5828 | 31.292 | Open | AT Only | AT Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {3B98F8D6-FC21-4DB2-9C80-42D1517971F1} |  | Low | Other | High | 54 | CHA | 5 |  |  | 2013-09-09 16:30 | No | Open
South | Kandahar | Arghistan | Salamjan Kalay | {3B98F8D6-FC21-4DB2-9C80-42D1517971F1} | c0a8-0009-142e559923c-8c8166e3-6603-2 | Hz-ID-18259 | DAFA - Demining Agency for Afghanistan | AF/2412/21681/MF0126 | 62957 | 66.5803 | 31.2951 | Open | AP Only | AP Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {3B98F8D6-FC21-4DB2-9C80-42D1517971F1} |  | Low | Agriculture Blocked | High | 50 | CHA | 5 |  |  | 2013-09-09 16:30 | No | Open
South | Kandahar | Arghistan | Samakay(Habib Sahibzada) | {AF7F6786-D153-4913-9B99-DC66B0D89B3A} | c0a8-0057-12c3bb63f0a-1451c73c-3c2f7- | MF-HQ-10759 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21742/MF072 | 10800 | 66.7934 | 31.2607 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-305 | Kandahar Demining Project-06 AT |  | No |  |  | 1394 |  | {AF7F6786-D153-4913-9B99-DC66B0D89B3A} |  | Medium | Critical Infrastracture | High | 40 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Sar Darrah | {82D95A3D-F878-42FB-BC71-97383B40B6F9} | c0a8-0057-12c3bac1620-beaad582-36295- | MF-HQ-10751 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21840/MF049 | 80000 | 66.776 | 31.6458 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {82D95A3D-F878-42FB-BC71-97383B40B6F9} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Sar Darrah | {82D95A3D-F878-42FB-BC71-97383B40B6F9} | c0a8-0057-12c3baf2fd0-c187deeb-3808f- | MF-HQ-10753 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21840/MF048 | 60000 | 66.776 | 31.6458 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-305 | Kandahar Demining Project-06 AT |  | No |  |  | 1394 |  | {82D95A3D-F878-42FB-BC71-97383B40B6F9} |  | Medium | Agriculture Blocked | High | 4 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Shamali Cheghnay | {1F313B6A-9C35-4634-8A6D-4EEAA841BC77} | c0a8-0057-12c3b84bc34-4b2b3a5f-1cd2b- | MF-HQ-10794 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21821/MF076 | 500000 | 66.5348 | 31.7615 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {1F313B6A-9C35-4634-8A6D-4EEAA841BC77} |  | Low | Agriculture Blocked | High | 1 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Shamali Cheghnay | {1F313B6A-9C35-4634-8A6D-4EEAA841BC77} | c0a8-0057-12c3b8ea090-e49dfb04-23b3c- | MF-HQ-10796 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21821/MF078 | 3000000 | 66.5348 | 31.7615 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-133 | Kandahar Demining Project-03 |  | No |  |  | 1400 |  | {1F313B6A-9C35-4634-8A6D-4EEAA841BC77} | a | Low | Agriculture Blocked | High | 15 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Shamali Cheghnay | {1F313B6A-9C35-4634-8A6D-4EEAA841BC77} | c0a8-0057-12c3b917c26-915f1a17-25891- | MF-HQ-10787 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21821/MF079 | 270000 | 66.5348 | 31.7615 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {1F313B6A-9C35-4634-8A6D-4EEAA841BC77} |  | Low | Agriculture Blocked | High | 24 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Shamali Cheghnay | {1F313B6A-9C35-4634-8A6D-4EEAA841BC77} | c0a8-0057-12c3b974ed2-26cb08d5-29606- | MF-HQ-10791 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21821/MF077 | 480000 | 66.5348 | 31.7615 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {1F313B6A-9C35-4634-8A6D-4EEAA841BC77} |  | Low | Agriculture Blocked | High | 36 | SHA | 4 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13aded1b359-fa84e704-ef2-38 | Hz-ID-17325 | EODT- TECHNOLOGEY,INC | AF/2412/ 21726/MF0106 | 22329 | 66.6188 | 31.539 | Open | AP Only | AP Only | MineField | Blank | MBT Project-305 | Kandahar Demining Project-06 AT |  | No |  |  | 1394 |  | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  | High with Victim | High with Victims | High | 147 | CHA | 3 | Yes |  | 2012-08-30 16:30 | No | Open
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13aded4cf89-ef717089-f08-30 | Hz-ID-17326 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0105 | 107268 | 66.6102 | 31.5346 | Open | AP Only | AP Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  | High with Victim | High with Victims | High | 75 | CHA | 4 | Yes |  | 2012-08-28 16:30 | No | Open
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13aded6b64c-36342037-f56-68 | Hz-ID-17327 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0104 | 56224 | 66.6102 | 31.5346 | Open | AP Only | AP Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  | High with Victim | High with Victims | High | 75 | CHA | 5 | Yes |  | 2012-08-29 16:30 | No | Open
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13aded9d1a5-30c7d2a6-fca-47 | Hz-ID-17328 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0094 | 22922 | 66.624 | 31.5243 | Open | AP Only | AP Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  | High with Victim | High with Victims | High | 9 | CHA | 5 | Yes |  | 2012-08-09 16:30 | No | Open
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13adee2ee4f-26b7870b-1086-9 | Hz-ID-17329 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0095 | 263006 | 66.5864 | 31.5372 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-05-12 | 2013-07-16 | 1392 | EODT | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  |  |  | High | 21 | CHA | 4 | Yes |  | 2012-08-11 16:30 | No | Complete
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13adee4f9dd-7f144639-10df-4 | Hz-ID-17330 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0096 | 306504 | 66.5898 | 31.537 | Open | AP Only | AP Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  | High with Victim | High with Victims | High | 37 | CHA | 5 | Yes |  | 2012-08-11 16:30 | No | Open
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13adee8fc00-b9535c4a-117f-6 | Hz-ID-17331 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0097 | 194107 | 66.596 | 31.5379 | Open | AP Only | AP Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  | High with Victim | High with Victims | High | 16 | CHA | 5 | Yes |  | 2012-08-12 16:30 | No | Open
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13adeea74b6-4e9662-11ec-88c | Hz-ID-17332 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0098 | 160112 | 66.5983 | 31.5382 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-06-15 | 2013-07-30 | 1392 | EODT | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  |  |  | High | 28 | CHA | 5 | Yes |  | 2012-08-14 16:30 | No | Complete
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13adeeb92a1-7a6deece-1221-4 | Hz-ID-17333 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0099 | 59954 | 66.6004 | 31.5386 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-07-15 | 2013-08-08 | 1392 | EODT | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  |  |  | High | 29 | CHA | 5 | Yes |  | 2012-08-15 16:30 | No | Complete
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13adeefdefa-7c2825ec-12c8-e | Hz-ID-17334 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0100 | 51162 | 66.6025 | 31.5376 | Open | AP Only | AP Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  | High with Victim | High with Victims | High | 13 | CHA | 5 | Yes |  | 2012-08-17 16:30 | No | Open
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13adef0c90a-2906cf25-12fc-d | Hz-ID-17335 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0101 | 49336 | 66.6025 | 31.5376 | Open | AP Only | AP Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  | High with Victim | High with Victims | High | 13 | CHA | 5 | Yes |  | 2012-08-25 16:30 | No | Open
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13adef35e17-bd035db8-1356-8 | Hz-ID-17336 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0102 | 59751 | 66.6072 | 31.5358 | Open | AP Only | AP Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  | High with Victim | High with Victims | High | 88 | CHA | 5 | Yes |  | 2012-08-26 16:30 | No | Open
South | Kandahar | Arghistan | Shaykhan Kalay | {F6794EB1-56B9-4F08-8949-614B4046A34A} | c0a8-0009-13adef450ab-64fd4ba5-1374-8 | Hz-ID-17337 | EODT- TECHNOLOGEY,INC | AF/2412/21726/MF0103 | 57899 | 66.6072 | 31.5358 | Open | AP Only | AP Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {F6794EB1-56B9-4F08-8949-614B4046A34A} |  | High with Victim | High with Victims | High | 88 | CHA | 5 | Yes |  | 2012-08-27 16:30 | No | Open
South | Kandahar | Arghistan | Sherabolak | {BA97A754-2350-47AF-9FD5-9B8D2A6303AC} | c0a8-0057-12c3ba63e77-c2b0b23-32bc0-4 | MF-HQ-10814 | DAFA - Demining Agency for Afghanistan | AF/2112/21701/MF0046 | 78528 | 66.6979 | 31.3716 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-249 | Kandahar Demining Project-025 |  | No |  |  | 1400 |  | {BA97A754-2350-47AF-9FD5-9B8D2A6303AC} |  | High Requested | Resettlment/Local Request | High | 4 | CHA | 5 | Yes |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Shin Ca | {B5683D19-FB8E-4D46-9272-73F0D87DF3BC} | c0a8-0057-12c3baf3b16-ee680afb-380fe- | MF-HQ-10795 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21874/MF0052 | 315000 | 66.4992 | 31.6729 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {B5683D19-FB8E-4D46-9272-73F0D87DF3BC} |  | Low | Water Blocked | High | 14 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Shir Ali Kalay | {F261B8E4-85C2-4935-B068-0FCDCDB5FAB8} | c0a8-0009-13ee041da0a-af0c210b-1b24-2 | Hz-ID-17909 | DAFA - Demining Agency for Afghanistan | AF/2412/00756/MF0118 | 87360 | 66.3346 | 31.5749 | Open | AT Only | AT Only | MineField |  | MBT Project-249 | Kandahar Demining Project-025 |  |  |  |  | 1400 |  | {F261B8E4-85C2-4935-B068-0FCDCDB5FAB8} |  | Low | Agriculture Blocked | High | 9 | CHA | 5 |  |  | 2013-03-28 16:30 | No | Open
South | Kandahar | Arghistan | Shir Ali Kalay | {F261B8E4-85C2-4935-B068-0FCDCDB5FAB8} | c0a8-0009-13f1901d849-78865101-501c-7 | Hz-ID-17908 | DAFA - Demining Agency for Afghanistan | AF/2412/00756/MF0117 | 201396 | 66.3344 | 31.5877 | Open | AT Only | AT Only | MineField |  | MBT Project-249 | Kandahar Demining Project-025 |  |  |  |  | 1400 |  | {F261B8E4-85C2-4935-B068-0FCDCDB5FAB8} |  | Low | Agriculture Blocked | High | 6 | CHA | 5 |  |  | 2013-03-31 16:30 | No | Open
South | Kandahar | Arghistan | Surpan | {4043ABA9-0DA9-40EA-9C05-8DB1B6178E7D} | c0a8-0009-1417ccdfa24-db73c04-53f-dad | Hz-ID-18178 | DAFA - Demining Agency for Afghanistan | AF/2412/21660/MF0120 | 377322 | 66.3971 | 31.4768 | Open | AT Only | AT Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {4043ABA9-0DA9-40EA-9C05-8DB1B6178E7D} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2013-07-13 16:30 | No | Open
South | Kandahar | Arghistan | Surpan | {4043ABA9-0DA9-40EA-9C05-8DB1B6178E7D} | c0a8-0009-1417ce3a818-8a4803a8-5ea-88 | Hz-ID-18179 | DAFA - Demining Agency for Afghanistan | AF/2412/21660/MF0121 | 408990 | 66.3971 | 31.4768 | Open | AT Only | AT Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {4043ABA9-0DA9-40EA-9C05-8DB1B6178E7D} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2013-07-14 16:30 | No | Open
South | Kandahar | Arghistan | Tajawu | {7264A980-FAE5-4DAF-A0F7-C08A374BEBDC} | c0a8-0057-12c3baa635a-3e73d853-352c1- | MF-HQ-10827 | DAFA - Demining Agency for Afghanistan | AF/2412/21649/MF0054 | 197398 | 66.3322 | 31.5357 | Open | AT Only | AT Only | MineField |  | MBT Project-249 | Kandahar Demining Project-025 |  |  |  |  | 1400 |  | {7264A980-FAE5-4DAF-A0F7-C08A374BEBDC} |  | High Requested | Resettlment/Local Request | High | 0 | CHA | 5 | Yes |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Tarakay | {E0A01EF4-1926-4D10-BAFA-68FCF632692E} | c0a8-0009-145639e8655-76ee6f8c-2351-a | Hz-ID-18260 | DAFA - Demining Agency for Afghanistan | AF/2412/21753/MF0122 | 424275 | 66.7222 | 31.472 | Open | AT Only | AT Only | MineField |  | MBT Project-305 | Kandahar Demining Project-06 AT |  |  |  |  | 1394 |  | {E0A01EF4-1926-4D10-BAFA-68FCF632692E} |  | Medium | Critical Infrastracture | High | 0 | CHA | 3 |  |  | 2013-08-29 16:30 | No | Open
South | Kandahar | Arghistan | Tarakay | {E0A01EF4-1926-4D10-BAFA-68FCF632692E} | c0a8-0057-12c3bb7327a-e30e3987-3cb7e- | MF-HQ-10869 | DAFA - Demining Agency for Afghanistan | AF/2412/21753/MF0080 | 562851 | 66.7246 | 31.463 | Open | AT Only | AT Only | MineField |  | MBT Project-306 | Kandahar Demining Project-09 AT |  |  |  |  | 1396 |  | {E0A01EF4-1926-4D10-BAFA-68FCF632692E} |  | High Requested | Resettlment/Local Request | High | 315 | CHA | 4 | Yes |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Tozhna | {C2C2FFBC-B030-4BC5-873B-5344024A4FCA} | c0a8-0057-12c3baee05a-97f5cee5-37db0- | MF-HQ-10823 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2412/21743/MF0070 | 750000 | 66.8123 | 31.2358 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-306 | Kandahar Demining Project-09 AT |  | No |  |  | 1396 |  | {C2C2FFBC-B030-4BC5-873B-5344024A4FCA} |  | Medium | Agriculture Blocked | High | 32 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Tughay Qobod Kalay | {60EE8933-4221-413A-932C-3E0788C60F24} | c0a8-0057-12c3ba84a53-ead8bc4f-33fbb- | MF-HQ-10809 | DAFA - Demining Agency for Afghanistan | AF/2412/21750/MF0047 | 1676312 | 66.7402 | 31.4623 | Open | AT Only | AT Only | MineField |  | MBT Project-249 | Kandahar Demining Project-025 |  |  |  |  | 1400 | None | {60EE8933-4221-413A-932C-3E0788C60F24} |  | High Requested | Resettlment/Local Request | High | 106 | CHA | 4 | Yes |  | 2009-06-03 | No | Open
South | Kandahar | Arghistan | Zarinzayi | {09734A31-F197-4E26-9022-872214B00DAB} | c0a8-0009-13dcf548fe1-51fa5092-48d-5d | Hz-ID-17755 | MCPA - Mine Clearance Planning Agency | AF/2412/21873/BF0115 | 896 | 66.5797 | 31.5716 | Open | UXO Only | UXO Only | BF |  | MBT Project-305 | Kandahar Demining Project-06 AT |  | No |  |  | 1394 |  | {09734A31-F197-4E26-9022-872214B00DAB} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-03-24 16:30 | No | Open
South | Kandahar | Arghistan | Zarinzayi | {09734A31-F197-4E26-9022-872214B00DAB} | c0a8-0009-13dcf56ee45-ab2a53bb-4aa-fb | Hz-ID-17756 | MCPA - Mine Clearance Planning Agency | AF/2412/21873/BF0116 | 46504 | 66.5834 | 31.5754 | Open | UXO Only | UXO Only | BF |  | MBT Project-305 | Kandahar Demining Project-06 AT |  | No |  |  | 1394 |  | {09734A31-F197-4E26-9022-872214B00DAB} |  | High with Victim | High with Victims | High | 4 | CHA | 1 |  |  | 2013-03-26 16:30 | No | Open
South | Kandahar | Arghistan | Zarinzayi | {09734A31-F197-4E26-9022-872214B00DAB} | c0a8-00f6-138414a3244-e8b5615b-1164-5 | Hz-ID-17078 | EODT- TECHNOLOGEY,INC | AF/2412/21873/MF0084 | 324138 | 66.5454 | 31.5697 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-305 | Kandahar Demining Project-06 AT |  | No |  |  | 1394 |  | {09734A31-F197-4E26-9022-872214B00DAB} |  | High with Victim | High with Victims | High | 11 | CHA | 3 | Yes |  | 2012-03-24 16:30 | No | Open
South | Kandahar | Daman | Byaban Darrah | {CDC9C9F9-C846-402C-8088-2C8B808EF95C} | c0a8-0009-13d38fb0dd8-6833122a-10ab-e | Hz-ID-17686 | MACCA | AF/2402/21537/MF0583 | 14500 | 65.9597 | 31.4545 | Open | AP Only | AP Only | MineField |  | MBT Project-186 | Kandahar Demining Project-03 |  | No | 2013-06-30 | 2013-07-17 | 1393 |  | {CDC9C9F9-C846-402C-8088-2C8B808EF95C} |  | Medium | Water Blocked | Substantial | 26 | CHA | 3 |  |  | 2012-12-09 16:30 | No | Open
South | Kandahar | Daman | Da'i Kalay | {8C05C2B3-0EB8-45FD-A89A-30F3AF40B519} | c0a8-0009-13d38d5ab76-a7f278dd-fff-a1 | Hz-ID-17684 | MACCA | AF/2402/21538/BF0581 | 1000000 | 65.8317 | 31.457 | Open | UXO Only | UXO Only | BF |  | MBT Project-186 | Kandahar Demining Project-03 |  |  |  |  | 1393 |  | {8C05C2B3-0EB8-45FD-A89A-30F3AF40B519} |  | Medium | Critical Infrastracture | Substantial | 186 | CHA | 3 |  |  | 2012-12-20 16:30 | No | Open
South | Kandahar | Daman | Da'i Kalay | {8C05C2B3-0EB8-45FD-A89A-30F3AF40B519} | c0a8-0009-13d38da3bc4-90b974d3-101c-6 | Hz-ID-17685 | MACCA | AF/2402/21538/BF0582 | 1000000 | 65.8704 | 31.4552 | Open | UXO Only | UXO Only | BF |  | MBT Project-186 | Kandahar Demining Project-03 |  |  |  |  | 1393 |  | {8C05C2B3-0EB8-45FD-A89A-30F3AF40B519} |  | Medium | Critical Infrastracture | Substantial | 33 | CHA | 3 |  |  | 2012-12-20 16:30 | No | Open
South | Kandahar | Daman | Haji Basheer | {AC942DFD-431B-4A1E-90AE-C717F8924307} | c0a8-00f6-13754764dcf-63055a97-c23-7e | MF-16755 | MCPA - Mine Clearance Planning Agency | AF/2402/00521/MF0423 | 151296 | 65.9198 | 31.3682 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-06-22 | 2013-07-25 | 1392 | EODT | {AC942DFD-431B-4A1E-90AE-C717F8924307} |  |  |  | Substantial | 0 | CHA | 1 |  |  | 2012-03-15 16:30 | No | Complete
South | Kandahar | Daman | Haji Deh | {F5103402-EBD2-43F4-8839-F1C654D7F51A} | c0a8-00f6-138418e0a8d-ba80a39a-1843-6 | Hz-ID-17082 | EODT- TECHNOLOGEY,INC | AF/2402/21535/MF0426 | 280139 | 65.8947 | 31.3885 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-05-13 | 2013-08-14 | 1392 | EODT | {F5103402-EBD2-43F4-8839-F1C654D7F51A} |  |  |  | Substantial | 1 | CHA | 2 |  |  | 2012-03-15 16:30 | No | Complete
South | Kandahar | Daman | Mandi Sar | {5FC0115D-7D3C-4CC8-81E4-DC35E26E9A45} | c0a8-0057-12c3b8c038d-c64a5394-21e9b- | MF-HQ-10880 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2402/21544/MF0337 | 80000 | 65.7866 | 31.5572 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-186 | Kandahar Demining Project-03 |  | No | 2013-07-08 | 2013-07-30 | 1393 |  | {5FC0115D-7D3C-4CC8-81E4-DC35E26E9A45} |  | High with Victim | High with Victims | Substantial | 4 | SHA | 2 |  |  | 2009-06-03 | No | Open
South | Kandahar | Daman | Manji Kalay | {B91A7843-2289-487D-8685-59B886FA79F6} | c0a8-00f6-13923963f13-85c9228b-3612-1 | Hz-ID-17179 | EODT- TECHNOLOGEY,INC | AF/2402/21573/MF0431 | 136640 | 66.0839 | 31.6957 | Closed | AT Only | AT Only | MineField | 1391 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-03-10 | 2013-04-09 | 1392 | EODT | {B91A7843-2289-487D-8685-59B886FA79F6} |  |  |  | Substantial | 10 | CHA | 5 |  |  | 2012-07-04 16:30 | No | Complete
South | Kandahar | Daman | Morghan Kechah | {A1DB4439-00FF-4621-96BC-5FA2502842A7} | c0a8-0009-141074ee242-9b0910a5-aeca-8 | Hz-ID-18142 | DAFA - Demining Agency for Afghanistan | AF/2402/21548/MF0444 | 2598 | 65.9621 | 31.5188 | Open | AP Only | AP Only | MineField |  | MBT Project-186 | Kandahar Demining Project-03 |  |  |  |  | 1393 |  | {A1DB4439-00FF-4621-96BC-5FA2502842A7} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 2 |  |  | 2013-01-15 16:30 | No | Open
South | Kandahar | Daman | Nevay Deh | {24464312-E181-4C25-B264-2DDF316ED57A} | c0a8-00f6-13904f35a68-50d3066f-7eb-15 | Hz-ID-17137 | EODT- TECHNOLOGEY,INC | AF/2402/21188/MF0433 | 211578 | 65.9777 | 31.4672 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-04-14 | 2013-07-04 | 1392 | EODT | {24464312-E181-4C25-B264-2DDF316ED57A} |  |  |  | Substantial | 6 | CHA | 2 |  |  | 2012-07-12 16:30 | No | Complete
South | Kandahar | Daman | Safdar Kalay | {479EEE9D-CED8-4640-95D0-1FCACE721FBB} | c0a8-0057-12c3b7aeb29-b6d5a432-15d83- | BF-HQ-14741 | MCPA - Mine Clearance Planning Agency | AF/2402/21521/BF0393 | 10279 | 65.7842 | 31.6275 | Open | UXO Only | UXO Only | BF |  | MBT Project-186 | Kandahar Demining Project-03 |  |  |  |  | 1393 |  | {479EEE9D-CED8-4640-95D0-1FCACE721FBB} | , | High with Victim | High with Victims | Substantial | 6 | CHA | 2 |  |  | 2010-10-26 | No | Open
South | Kandahar | Daman | Safdar Kalay | {479EEE9D-CED8-4640-95D0-1FCACE721FBB} | c0a8-00f6-139aa92b590-8a4399e8-1baa-4 | Hz-ID-17267 | DAFA - Demining Agency for Afghanistan | AF/2402/21521/BF0442 | 4178 | 65.7919 | 31.6275 | Open | UXO Only | UXO Only | BF |  | MBT Project-186 | Kandahar Demining Project-03 |  |  |  |  | 1393 |  | {479EEE9D-CED8-4640-95D0-1FCACE721FBB} |  | High with Victim | High with Victims | Substantial | 12 | CHA | 2 |  |  | 2012-09-02 16:30 | No | Open
South | Kandahar | Daman | Safdar Kalay | {479EEE9D-CED8-4640-95D0-1FCACE721FBB} | c0a8-00f6-139aa98264a-e7afb7be-1bc9-2 | Hz-ID-17268 | DAFA - Demining Agency for Afghanistan | AF/2402/21521/BF0443 | 42428 | 65.7894 | 31.6293 | Open | UXO Only | UXO Only | BF |  | MBT Project-186 | Kandahar Demining Project-03 |  |  |  |  | 1393 |  | {479EEE9D-CED8-4640-95D0-1FCACE721FBB} | As the area is contaminated by different sensitivity munitions manual clearance team have to work under the direct support/supervision of EOD team who will control the clearance operation as well as providing necessary consultation for the unsafe to move | High with Victim | High with Victims | Substantial | 6 | CHA | 2 |  |  | 2012-09-02 16:30 | No | Open
South | Kandahar | Daman | Sar Jakan Kalay | {5E8728E8-08AA-4486-B39D-58978FD7B1BB} | c0a8-00f6-13904b22fe6-91987f-54a-32f4 | Hz-ID-17151 | EODT- TECHNOLOGEY,INC | AF/2402/21591/MF0440 | 223889 | 66.1611 | 31.7031 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-04-08 | 2013-05-15 | 1392 | EODT | {5E8728E8-08AA-4486-B39D-58978FD7B1BB} |  |  |  | Substantial | 211 | CHA | 4 |  |  | 2012-07-18 16:30 | No | Complete
South | Kandahar | Ghorak | Lewanay Dara | {46CADE94-EC3D-4DB9-9091-0239CC0FA135} | c0a8-0057-12c3b8c8e1f-bb393870-2245a- | MF-HQ-10904 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2406/00211/MF0002 | 200000 | 65.2916 | 31.9801 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-268 | Kandahar Demining Project-08 |  | No |  |  | 1395 |  | {46CADE94-EC3D-4DB9-9091-0239CC0FA135} |  | Low | Agriculture Blocked | Extreme | 0 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Ghorak | Lewanay Dara | {46CADE94-EC3D-4DB9-9091-0239CC0FA135} | c0a8-0057-12c3b99dd2d-133dd427-2b10b- | MF-HQ-10898 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2406/00211/MF0001 | 54000 | 65.2916 | 31.9801 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-268 | Kandahar Demining Project-08 |  | No |  |  | 1395 |  | {46CADE94-EC3D-4DB9-9091-0239CC0FA135} |  | Low | Agriculture Blocked | Extreme | 0 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Ghorak | Wanay | {BBE52BD9-C50F-4F1A-93FB-E7503852DB87} | c0a8-0057-12c3bb1a4ba-aea5df8e-397ef- | MF-HQ-10840 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2406/00580MF003 | 1400 | 65.2712 | 32.132 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-268 | Kandahar Demining Project-08 |  | No |  |  | 1395 |  | {BBE52BD9-C50F-4F1A-93FB-E7503852DB87} |  | High with Victim | High with Victims | Extreme | 0 | SHA | 2 |  |  | 2009-06-03 | No | Open
South | Kandahar | Kandahar | Khvosh Ab | {3984DB47-2934-438B-95FD-43B5183D4364} | c0a8-0009-13bef9ae30a-79d337da-2c07-7 | MF-16753 | DAFA - Demining Agency for Afghanistan | AF/2401/21529/MF0653 | 11689 | 65.8236 | 31.4992 | Open | AP Only | AP Only | MineField |  | MBT Project-186 | Kandahar Demining Project-03 |  | No | 2013-07-25 | 2013-08-05 | 1393 |  | {3984DB47-2934-438B-95FD-43B5183D4364} |  | High with Victim | High with Victims | Substantial | 10 | CHA | 1 |  |  | 2012-03-25 16:30 | No | Open
South | Kandahar | Kandahar | Khvosh Ab | {3984DB47-2934-438B-95FD-43B5183D4364} | c0a8-00f6-137e46b9550-1b59dcb0-216-11 | MF-16752 | DAFA - Demining Agency for Afghanistan | AF/2401/21529/MF0652 | 5141 | 65.8261 | 31.4834 | Open | Mixed | Mixed AP AT UXO | MineField |  | MBT Project-186 | Kandahar Demining Project-03 |  | No | 2013-06-30 | 2013-07-10 | 1393 |  | {3984DB47-2934-438B-95FD-43B5183D4364} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 1 |  |  | 2012-03-25 16:30 | No | Open
South | Kandahar | Kandahar | Monar | {5D91AB05-E5F9-472C-A351-2408FED994E3} | c0a8-0009-13b7e46ae4b-d28e7691-4c88-2 | Hz-ID-17430 | MCPA - Mine Clearance Planning Agency | AF/2401/21459/MF0662 | 13245 | 65.6727 | 31.5418 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-03-13 | 2013-04-16 | 1392 | EODT | {5D91AB05-E5F9-472C-A351-2408FED994E3} |  |  |  | Substantial | 29 | CHA | 3 |  |  | 2012-10-04 16:30 | No | Complete
South | Kandahar | Kandahar | Qadzi Kariz | {F46EEF9A-E874-4F15-A786-5C2EB3A14E83} | c0a8-0009-13cfb6ed761-a2578e51-31d4-d | Hz-ID-17649 | EODT- TECHNOLOGEY,INC | AF/2401/21545/MF0663 | 23752 | 65.8821 | 31.4857 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-05-13 | 2013-07-01 | 1392 | EODT | {F46EEF9A-E874-4F15-A786-5C2EB3A14E83} |  |  |  | Substantial | 0 | CHA | 2 |  |  | 2013-02-07 16:30 | No | Complete
South | Kandahar | Kandahar | Qadzi Kariz | {F46EEF9A-E874-4F15-A786-5C2EB3A14E83} | c0a8-0009-13d1a77c1d7-3a232f83-323-79 | Hz-ID-17682 | MACCA | AF/2401/21545/MF0664 | 62300 | 65.8636 | 31.5224 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-06-03 | 2013-07-24 | 1392 | EODT | {F46EEF9A-E874-4F15-A786-5C2EB3A14E83} |  |  |  | Substantial | 6 | CHA | 2 |  |  | 2013-01-30 16:30 | No | Complete
South | Kandahar | Kandahar | Qadzi Kariz | {F46EEF9A-E874-4F15-A786-5C2EB3A14E83} | c0a8-008e-1328fcb6366-cd43bbba-288e-d | BF-15092 | EODT- TECHNOLOGEY,INC | AF/2401/21545/BF0645 | 5381 | 65.8829 | 31.4856 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-01-11 | 2013-01-13 | 1392 | EODT | {F46EEF9A-E874-4F15-A786-5C2EB3A14E83} |  |  |  | Substantial | 0 | CHA | 2 |  |  | 2011-06-29 16:30 | No | Complete
South | Kandahar | Kandahar | Ruhabad | {7784FFBB-AC75-49B4-AE2C-7232BAF592C4} | c0a8-0009-13d52c4f4b7-fa96e750-1478-f | Hz-ID-17683 | MACCA | AF/2401/21421/MF0666 | 381 | 65.7107 | 31.4262 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-05-26 | 2013-05-27 | 1392 | EODT | {7784FFBB-AC75-49B4-AE2C-7232BAF592C4} |  |  |  | Substantial | 4 | CHA | 3 |  |  | 2013-01-03 16:30 | No | Complete
South | Kandahar | Kandahar | Sakzey Kalay | {524E3B34-396F-4E93-ACB9-755474E22BAA} | c0a8-0009-13e3bae96d5-fc7ce10b-cfc-ee | Hz-ID-17741 | MACCA | AF/2401/21468/MF0667 | 16680 | 65.7589 | 31.4258 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-04-17 | 2013-05-12 | 1392 | EODT | {524E3B34-396F-4E93-ACB9-755474E22BAA} |  |  |  | Substantial | 45 | CHA | 5 |  |  | 2013-03-17 16:30 | No | Complete
South | Kandahar | Kandahar | Spin Kalacha | {8362CE7A-B52F-4B12-9A45-B1F333AD76D8} | c0a8-00f6-1386576f2fb-4ed8ec54-81-962 | Hz-ID-17109 | EODT- TECHNOLOGEY,INC | AF/2401/21483/MF0658 | 43086 | 65.64 | 31.5879 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-04-01 | 2013-04-11 | 1392 | EODT | {8362CE7A-B52F-4B12-9A45-B1F333AD76D8} |  |  |  | Substantial | 136 | CHA | 2 |  |  | 2012-06-27 16:30 | No | Complete
South | Kandahar | Kandahar | Spin Kalacha | {8362CE7A-B52F-4B12-9A45-B1F333AD76D8} | c0a8-00f6-139047a27bf-703bd381-20d-34 | Hz-ID-17111 | EODT- TECHNOLOGEY,INC | AF/2401/21483/MF0657 | 5696 | 65.6468 | 31.5863 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-04-07 | 2013-04-10 | 1392 | EODT | {8362CE7A-B52F-4B12-9A45-B1F333AD76D8} |  |  |  | Substantial | 554 | CHA | 2 |  |  | 2012-06-26 16:30 | No | Complete
South | Kandahar | Khakrez | Baghe Khalil | {9495B32B-B20D-4B2D-9FD0-DB71181541B8} | c0a8-0009-1437066423b-85f5be03-f290-a | Hz-ID-18324 | DAFA - Demining Agency for Afghanistan | AF/2405/21903/MF0020 | 382895 | 65.4786 | 31.9693 | Open | AT Only | AT Only | MineField |  | MBT Project-268 | Kandahar Demining Project-08 |  |  |  |  | 1395 |  | {9495B32B-B20D-4B2D-9FD0-DB71181541B8} |  | Medium | Critical Infrastracture | High | 412 | CHA | 3 |  |  | 2013-11-14 16:30 | No | Open
South | Kandahar | Khakrez | Baghe Khalil | {9495B32B-B20D-4B2D-9FD0-DB71181541B8} | c0a8-0009-143706cb4b9-591361f8-f932-3 | Hz-ID-18325 | DAFA - Demining Agency for Afghanistan | AF/2405/21903/MF0021 | 204041 | 65.475 | 31.951 | Open | AT Only | AT Only | MineField |  | MBT Project-268 | Kandahar Demining Project-08 |  |  |  |  | 1395 |  | {9495B32B-B20D-4B2D-9FD0-DB71181541B8} |  | Medium | Critical Infrastracture | High | 48 | CHA | 3 |  |  | 2013-11-14 16:30 | No | Open
South | Kandahar | Khakrez | Baghe Khalil | {9495B32B-B20D-4B2D-9FD0-DB71181541B8} | c0a8-0009-143708411fb-ef075ab3-110b8- | Hz-ID-18326 | DAFA - Demining Agency for Afghanistan | AF/2405/21903/MF0022 | 96445 | 65.475 | 31.9601 | Open | AT Only | AT Only | MineField |  | MBT Project-268 | Kandahar Demining Project-08 |  |  |  |  | 1395 |  | {9495B32B-B20D-4B2D-9FD0-DB71181541B8} |  | Medium | Critical Infrastracture | High | 0 | CHA | 3 |  |  | 2013-11-14 16:30 | No | Open
South | Kandahar | Khakrez | Chenar (2) | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} | c0a8-0009-13b84b60471-e9b8c95e-3f-51f | Hz-ID-17446 | EODT- TECHNOLOGEY,INC | AF/2405/21900/MF0010 | 60692 | 65.4731 | 31.9688 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-06-12 | 2013-06-25 | 1392 | EODT | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} |  |  |  | High | 21 | CHA | 3 |  |  | 2012-11-11 16:30 | No | Complete
South | Kandahar | Khakrez | Chenar (2) | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} | c0a8-0009-13b84b6358f-c0bb8ee1-87-40c | Hz-ID-17443 | EODT- TECHNOLOGEY,INC | AF/2405/21900/MF0014 | 140219 | 65.4734 | 31.9755 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-04-01 | 2013-05-11 | 1392 | EODT | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} |  |  |  | High | 99 | CHA | 3 |  |  | 2012-11-12 16:30 | No | Complete
South | Kandahar | Khakrez | Chenar (2) | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} | c0a8-0009-13b84b65733-7addacd8-a7-f79 | Hz-ID-17444 | EODT- TECHNOLOGEY,INC | AF/2405/21900/MF0015 | 103445 | 65.4797 | 31.9737 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-04-13 | 2013-05-12 | 1392 | EODT | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} |  |  |  | High | 348 | CHA | 3 |  |  | 2012-11-12 16:30 | No | Complete
South | Kandahar | Khakrez | Chenar (2) | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} | c0a8-0009-13b84b67954-d8575b98-c1-cc8 | Hz-ID-17442 | EODT- TECHNOLOGEY,INC | AF/2405/21900/MF0013 | 15674 | 65.4731 | 31.9746 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-06-30 | 2013-07-04 | 1392 | EODT | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} |  |  |  | High | 21 | CHA | 3 |  |  | 2012-11-12 16:30 | No | Complete
South | Kandahar | Khakrez | Chenar (2) | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} | c0a8-0009-13b84b69195-e950f07-db-1ed8 | Hz-ID-17440 | EODT- TECHNOLOGEY,INC | AF/2405/21900/MF0011 | 28909 | 65.474 | 31.97 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-06-30 | 2013-07-08 | 1392 | EODT | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} |  |  |  | High | 21 | CHA | 3 |  |  | 2012-11-11 16:30 | No | Complete
South | Kandahar | Khakrez | Chenar (2) | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} | c0a8-0009-13b84b6aa53-50f6758b-fa-1ab | Hz-ID-17441 | EODT- TECHNOLOGEY,INC | AF/2405/21900/MF0012 | 54214 | 65.4741 | 31.9761 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-07-05 | 2013-07-20 | 1392 | EODT | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} |  |  |  | High | 270 | CHA | 3 |  |  | 2012-11-12 16:30 | No | Complete
South | Kandahar | Khakrez | Chenar (2) | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} | c0a8-0009-13e3bb1f587-8af050e1-e20-75 | Hz-ID-17791 | EODT- TECHNOLOGEY,INC | AF/2405/21900/MF0019 | 13726 | 65.4605 | 31.9784 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2012-09-05 | 2012-09-08 | 1392 | EODT | {150E0FD1-14E5-45D2-B1CC-B7C6E08C3F02} |  |  |  | High | 8 | CHA | 5 |  |  | 2012-03-07 16:30 | No | Complete
South | Kandahar | Khakrez | China | {20ABB67B-42E8-4F60-B2B3-BE3C3EA8C871} | c0a8-0057-12c3b7c6c56-c7facca9-16eb5- | MF-HQ-10881 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2405/21921/MF005 | 375000 | 65.477 | 32.0534 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-268 | Kandahar Demining Project-08 |  | No |  |  | 1395 |  | {20ABB67B-42E8-4F60-B2B3-BE3C3EA8C871} |  | High with Victim | High with Victims | High | 112 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Khakrez | China | {20ABB67B-42E8-4F60-B2B3-BE3C3EA8C871} | c0a8-0057-12c3b7f3d53-46177ba9-18e2f- | MF-HQ-10883 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2405/21921/MF006 | 375000 | 65.4799 | 32.0568 | Open | AT Only | AT Only | Converted From SHA | Blank | MBT Project-268 | Kandahar Demining Project-08 |  | No |  |  | 1395 | Blank | {20ABB67B-42E8-4F60-B2B3-BE3C3EA8C871} |  | High with Victim | High with Victims | High | 94 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Khakrez | Chingay | {D028DD57-1149-4C16-9F93-7B090B6F8352} | c0a8-0009-143704f96f2-98857ecc-b1db-6 | Hz-ID-18323 | DAFA - Demining Agency for Afghanistan | AF/2405/21902/BF0024 | 60381 | 65.4746 | 31.9686 | Open | UXO Only | UXO Only | BF |  | MBT Project-268 | Kandahar Demining Project-08 |  |  |  |  | 1395 |  | {D028DD57-1149-4C16-9F93-7B090B6F8352} |  | Medium | Critical Infrastracture | High | 380 | CHA | 3 |  |  | 2013-11-27 16:30 | No | Open
South | Kandahar | Khakrez | Chingay | {D028DD57-1149-4C16-9F93-7B090B6F8352} | c0a8-0009-14370814b73-c3d85fae-10f68- | Hz-ID-18327 | DAFA - Demining Agency for Afghanistan | AF/2405/21902/MF0023 | 260134 | 65.4737 | 31.9686 | Open | AT Only | AT Only | MineField |  | MBT Project-268 | Kandahar Demining Project-08 |  |  |  |  | 1395 |  | {D028DD57-1149-4C16-9F93-7B090B6F8352} |  | Medium | Critical Infrastracture | High | 407 | CHA | 3 |  |  | 2013-11-27 16:30 | No | Open
South | Kandahar | Khakrez | Darvishan | {4F36ED9D-7112-48D5-B4E8-6D03F39383B2} | c0a8-0009-1437085edb8-a117f8d0-113a6- | Hz-ID-18328 | DAFA - Demining Agency for Afghanistan | AF/2405/21918/MF0025 | 123868 | 65.4747 | 31.9953 | Open | AP Only | AP Only | MineField |  | MBT Project-268 | Kandahar Demining Project-08 |  |  |  |  | 1395 |  | {4F36ED9D-7112-48D5-B4E8-6D03F39383B2} |  | Low | Agriculture Blocked | High | 16 | CHA | 5 |  |  | 2013-11-30 16:30 | No | Open
South | Kandahar | Khakrez | Sarposh | {AE5AEFB6-AC25-4C7B-8FD0-22E85582AAD7} | c0a8-0057-12c3b87c57f-da08759b-1ef29- | MF-HQ-10756 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2405/21901/MF004 | 120000 | 65.4634 | 31.9371 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-268 | Kandahar Demining Project-08 |  | No |  |  | 1395 |  | {AE5AEFB6-AC25-4C7B-8FD0-22E85582AAD7} |  | Medium | Critical Infrastracture | High | 22 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Khakrez | Sarposh | {AE5AEFB6-AC25-4C7B-8FD0-22E85582AAD7} | c0a8-0057-12c3b98dcb5-3bf28616-2a674- | MF-HQ-10757 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2405/21901/MF003 | 140000 | 65.4634 | 31.9371 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-268 | Kandahar Demining Project-08 |  | No |  |  | 1395 |  | {AE5AEFB6-AC25-4C7B-8FD0-22E85582AAD7} |  | Medium | Critical Infrastracture | High | 18 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maruf | Abo Kala | {89B68DAD-2552-4FD2-9704-7C10027D0C40} | c0a8-0057-12c3b8c9530-d58d5f0d-224a3- | MF-HQ-10879 | EODT- TECHNOLOGEY,INC | AF/2413/22893/MF0031 | 39648 | 67.2258 | 31.6209 | Open | AP Only | AP Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  | No | 2013-07-10 | 2013-07-23 | 1395 |  | {89B68DAD-2552-4FD2-9704-7C10027D0C40} |  | Low | Agriculture Blocked | High | 93 | CHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maruf | Abo Kala | {89B68DAD-2552-4FD2-9704-7C10027D0C40} | c0a8-0057-12c3b94e537-9c811175-27cbe- | MF-HQ-10876 | EODT- TECHNOLOGEY,INC | AF/2413/22893/MF0036 | 36158 | 67.2226 | 31.6102 | Open | AP Only | AP Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  | No | 2013-07-17 | 2013-07-26 | 1395 |  | {89B68DAD-2552-4FD2-9704-7C10027D0C40} |  | Low | Water Blocked | High | 0 | CHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maruf | Abo Kala | {89B68DAD-2552-4FD2-9704-7C10027D0C40} | c0a8-0057-12c3b97b169-11a34c74-299f5- | MF-HQ-10861 | EODT- TECHNOLOGEY,INC | AF/2413/22893/MF0034 | 24305 | 67.2251 | 31.6154 | Open | AP Only | AP Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  | No | 2013-07-17 | 2013-07-23 | 1395 |  | {89B68DAD-2552-4FD2-9704-7C10027D0C40} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maruf | Abo Kala | {89B68DAD-2552-4FD2-9704-7C10027D0C40} | c0a8-0057-12c3b9af27d-2ade51af-2bcaf- | MF-HQ-10843 | EODT- TECHNOLOGEY,INC | AF/2413/22893/MF0035 | 43438 | 67.2452 | 31.628 | Open | AP Only | AP Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  | No | 2013-07-24 | 2013-07-31 | 1395 |  | {89B68DAD-2552-4FD2-9704-7C10027D0C40} |  | Medium | Water Blocked | High | 23 | CHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maruf | Abo Kala | {89B68DAD-2552-4FD2-9704-7C10027D0C40} | c0a8-0057-12c3ba1a273-52412566-2ff1a- | MF-HQ-10855 | EODT- TECHNOLOGEY,INC | AF/2413/22893/MF0030 | 12000 | 67.2345 | 31.6158 | Open | AP Only | AP Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  | No | 2013-07-27 | 2013-07-29 | 1395 |  | {89B68DAD-2552-4FD2-9704-7C10027D0C40} |  | Medium | Water Blocked | High | 24 | CHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maruf | Ahu China kalay | {462C579A-F43B-4138-89E2-89035B874BB6} | c0a8-0057-12c3bb22a8b-6da0c900-39d1b- | MF-HQ-10874 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2413/24132/MF028 | 240000 | 67.3298 | 31.7099 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-308 | Kandahar Demining Project-08 AT |  | No |  |  | 1395 |  | {462C579A-F43B-4138-89E2-89035B874BB6} |  | Low | Agriculture Blocked | High | 254 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maruf | Ahu China kalay | {462C579A-F43B-4138-89E2-89035B874BB6} | c0a8-0057-12c3bb6f433-2deb584b-3c945- | MF-HQ-10873 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2413/24132/MF029 | 200000 | 67.3299 | 31.7099 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-308 | Kandahar Demining Project-08 AT |  | No |  |  | 1395 |  | {462C579A-F43B-4138-89E2-89035B874BB6} |  | Medium | Agriculture Blocked | High | 119 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maruf | Ali Sher Kalay | {3BC050A8-8E3A-458A-A0BE-6481B3BF37A4} | c0a8-0009-142e550f823-594c0f6c-64b3-9 | Hz-ID-18249 | DAFA - Demining Agency for Afghanistan | AF/2413/22855/MF0044 | 102083 | 67.1992 | 31.4621 | Open | AP Only | AP Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  |  |  |  | 1395 |  | {3BC050A8-8E3A-458A-A0BE-6481B3BF37A4} |  | Low | Critical Infrastracture | High | 0 | CHA | 5 |  |  | 2013-09-21 16:30 | No | Open
South | Kandahar | Maruf | Ali Sher Kalay | {3BC050A8-8E3A-458A-A0BE-6481B3BF37A4} | c0a8-0009-142e551ba48-d384e571-64cc-4 | Hz-ID-18250 | DAFA - Demining Agency for Afghanistan | AF/2413/22855/MF0045 | 51009 | 67.2434 | 31.4723 | Open | AP Only | AP Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  |  |  |  | 1395 |  | {3BC050A8-8E3A-458A-A0BE-6481B3BF37A4} |  | Low | Critical Infrastracture | High | 0 | CHA | 5 |  |  | 2013-09-19 16:30 | No | Open
South | Kandahar | Maruf | Chormay | {1949AD54-3839-4381-93F1-5B302DC57242} | c0a8-0009-142e54f3a9f-51393d6b-642f-f | Hz-ID-18244 | DAFA - Demining Agency for Afghanistan | AF/2413/23020/MF0042 | 3681 | 67.1379 | 31.6023 | Open | AP Only | AP Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  |  |  |  | 1395 |  | {1949AD54-3839-4381-93F1-5B302DC57242} |  | High | Critical Infrastracture | High | 144 | CHA | 3 |  |  | 2013-07-13 16:30 | No | Open
South | Kandahar | Maruf | Chormay | {1949AD54-3839-4381-93F1-5B302DC57242} | c0a8-0009-142e54fbd84-e3020368-644a-8 | Hz-ID-18245 | DAFA - Demining Agency for Afghanistan | AF/2413/23020/MF0043 | 10317 | 67.1358 | 31.5903 | Open | AP Only | AP Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  |  |  |  | 1395 |  | {1949AD54-3839-4381-93F1-5B302DC57242} |  | Medium | Critical Infrastracture | High | 285 | CHA | 3 |  |  | 2013-07-11 16:30 | No | Open
South | Kandahar | Maruf | Ezghumay | {CA197615-CDEC-4C8F-BBB2-74C654E062AB} | c0a8-0009-142e556ead8-d4ec70cf-656e-f | Hz-ID-18251 | DAFA - Demining Agency for Afghanistan | AF/2413/22783/MF0046 | 64695 | 67.0692 | 31.4871 | Open | AT Only | AT Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  |  |  |  | 1395 |  | {CA197615-CDEC-4C8F-BBB2-74C654E062AB} |  | Low | Critical Infrastracture | High | 0 | CHA | 5 |  |  | 2013-09-18 16:30 | No | Open
South | Kandahar | Maruf | Madezay | {736770E0-D7A5-4349-97F6-6D7B4483E677} | c0a8-0057-12c3b7d06a0-52e516e6-175d2- | MF-HQ-10895 | EODT- TECHNOLOGEY,INC | AF/2413/22907/MF0038 | 223403 | 67.2185 | 31.6255 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-04-06 | 2013-07-16 | 1392 | EODT | {736770E0-D7A5-4349-97F6-6D7B4483E677} |  |  |  | High | 23 | CHA | 5 |  |  | 2009-06-03 | No | Complete
South | Kandahar | Maruf | Mohammadzay | {C0D92785-575D-4750-8B33-5EB1B8DA3FEF} | c0a8-0009-14037f30036-237e6241-2d68-d | Hz-ID-18086 | DAFA - Demining Agency for Afghanistan | AF/2413/22903/MF0040 | 111936 | 67.1742 | 31.6478 | Open | AP Only | AP Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  |  |  |  | 1395 |  | {C0D92785-575D-4750-8B33-5EB1B8DA3FEF} |  | Medium | Critical Infrastracture | High | 12 | CHA | 3 |  |  | 2013-06-15 16:30 | No | Open
South | Kandahar | Maruf | Mohammadzay | {C0D92785-575D-4750-8B33-5EB1B8DA3FEF} | c0a8-0009-142e55417c2-155a2c61-6509-d | Hz-ID-18252 | DAFA - Demining Agency for Afghanistan | AF/2413/22903/MF0047 | 80208 | 67.1713 | 31.6527 | Open | AP Only | AP Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  |  |  |  | 1395 |  | {C0D92785-575D-4750-8B33-5EB1B8DA3FEF} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2013-10-31 16:30 | No | Open
South | Kandahar | Maruf | Psha-I-Kalay | {E7416327-37DF-4978-8366-B3A90D03B0DC} | c0a8-0057-12c3bb8a287-c2a01544-3d85c- | MF-HQ-10767 | EODT- TECHNOLOGEY,INC | AF/2413/00717/MF0027 | 99579 | 67.2009 | 31.6243 | Open | AT Only | AT Only | MineField |  | MBT Project-308 | Kandahar Demining Project-08 AT |  | No |  |  | 1395 |  | {E7416327-37DF-4978-8366-B3A90D03B0DC} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Baizai-2 | {3E239D9B-11AB-44D6-BA75-53F0BE4CECE9} | c0a8-0057-12c3bab675d-96c704a-35c49-6 | MF-HQ-10862 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/00182/MF199 | 6000 | 65.0689 | 31.5234 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {3E239D9B-11AB-44D6-BA75-53F0BE4CECE9} |  | Medium | Water Blocked | Extreme | 323 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Barizi | {4CDC8F3A-974E-4BE8-A2F9-52514E0FDA44} | c0a8-0057-12c3b8d9656-153ddb9a-22f77- | MF-HQ-10899 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/00232/MF204 | 60000 | 65.0909 | 31.5205 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {4CDC8F3A-974E-4BE8-A2F9-52514E0FDA44} |  | Medium | Water Blocked | Extreme | 36 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Barizi | {4CDC8F3A-974E-4BE8-A2F9-52514E0FDA44} | c0a8-0057-12c3ba10c00-208bceab-2f938- | MF-HQ-10901 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/00232/MF201 | 40000 | 65.0909 | 31.5205 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {4CDC8F3A-974E-4BE8-A2F9-52514E0FDA44} |  | Medium | Water Blocked | Extreme | 101 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Barizi | {4CDC8F3A-974E-4BE8-A2F9-52514E0FDA44} | c0a8-0057-12c3bacfe4a-9baa6418-36b9b- | MF-HQ-10897 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/00232/MF0202 | 40000 | 65.0917 | 31.5215 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {4CDC8F3A-974E-4BE8-A2F9-52514E0FDA44} |  | Medium | Water Blocked | Extreme | 39 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Barizi | {4CDC8F3A-974E-4BE8-A2F9-52514E0FDA44} | c0a8-0057-12c3bad5906-4f81dfc6-36eee- | MF-HQ-10894 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/00232/MF0203 | 90000 | 65.0918 | 31.5212 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {4CDC8F3A-974E-4BE8-A2F9-52514E0FDA44} |  | Medium | Water Blocked | Extreme | 13 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Chashma-I-Haji Mohd Rasool | {BE1C6377-2773-4357-AA7F-423BDA8E469B} | c0a8-0057-12c3baede76-8b72f3ae-37d9b- | MF-HQ-10856 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/00584/MF0211 | 90000 | 65.0041 | 31.551 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {BE1C6377-2773-4357-AA7F-423BDA8E469B} |  | Medium | Water Blocked | Extreme | 9 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Chehel Gazi | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} | c0a8-0009-13e3ba627a3-cdf47bb0-9d0-cc | Hz-ID-17809 | EODT- TECHNOLOGEY,INC | AF/2407/22462/MF0218 | 316603 | 65.0232 | 31.5765 | Open | AT Only | AT Only | MineField |  | MBT Project-183 | Kandahar Demining Project-02 |  | No | 2013-05-26 | 2013-05-30 | 1397 |  | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} |  | High with Victim | High with Victims | Extreme | 3 | CHA | 2 |  |  | 2013-02-10 16:30 | No | Open
South | Kandahar | Maywand | Chehel Gazi | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} | c0a8-0009-13e3baf3239-ec318d3e-d29-2e | Hz-ID-17807 | EODT- TECHNOLOGEY,INC | AF/2407/22462/MF0217 | 120939 | 65.0202 | 31.578 | Open | AT Only | AT Only | MineField |  | MBT Project-183 | Kandahar Demining Project-02 |  |  |  |  | 1397 |  | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} |  | High with Victim | High with Victims | Extreme | 2 | CHA | 2 |  |  | 2013-02-10 16:30 | No | Open
South | Kandahar | Maywand | Chehel Gazi | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} | c0a8-0009-13e3baf600d-73a05058-d44-c1 | Hz-ID-17803 | EODT- TECHNOLOGEY,INC | AF/2406/22462/MF0214 | 66904 | 65.2394 | 31.5765 | Open | AT Only | AT Only | MineField |  | MBT Project-183 | Kandahar Demining Project-02 |  |  |  |  | 1397 |  | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} |  | High with Victim | High with Victims | Extreme | 11 | CHA | 2 |  |  | 2013-01-05 16:30 | No | Open
South | Kandahar | Maywand | Chehel Gazi | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} | c0a8-0009-13e3baf8049-278d2962-d6d-a2 | Hz-ID-17800 | EODT- TECHNOLOGEY,INC | AF/2406/22462/MF0213 | 128174 | 65.2382 | 31.5799 | Open | AT Only | AT Only | MineField |  | MBT Project-183 | Kandahar Demining Project-02 |  |  |  |  | 1397 |  | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} |  | High with Victim | High with Victims | Extreme | 13 | CHA | 2 |  |  | 2013-01-06 16:30 | No | Open
South | Kandahar | Maywand | Chehel Gazi | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} | c0a8-0009-13e3bb0320a-c108521e-e08-65 | Hz-ID-17794 | EODT- TECHNOLOGEY,INC | AF/2406/22462/MF0212 | 115787 | 65.2452 | 31.603 | Open | AT Only | AT Only | MineField |  | MBT Project-183 | Kandahar Demining Project-02 |  |  |  |  | 1397 |  | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} |  | High with Victim | High with Victims | Extreme | 0 | CHA | 2 |  |  | 2013-01-03 16:30 | No | Open
South | Kandahar | Maywand | Chehel Gazi | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} | c0a8-0057-12c3b879b83-150bf2c8-1ed2a- | MF-HQ-10867 | EODT- TECHNOLOGEY,INC | AF/2407/22416/MF0210 | 250000 | 65.0169 | 31.5761 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-183 | Kandahar Demining Project-02 |  | No | 2013-05-25 | 2013-07-14 | 1397 |  | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} |  | High with Victim | High with Victims | Extreme | 3 | CHA | 2 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Chehel Gazi | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} | c0a8-0057-12c3b93fee9-be2e79dc-27340- | MF-HQ-10870 | EODT- TECHNOLOGEY,INC | AF/2407/22416/MF0209 | 250000 | 65.0169 | 31.5761 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-183 | Kandahar Demining Project-02 |  | No | 2013-04-09 | 2013-05-29 | 1397 |  | {E62EAF72-71C5-4CDF-A9D4-4AE676F65C09} |  | High with Victim | High with Victims | Extreme | 3 | CHA | 2 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | De Maywnd | {5A3AF6EF-698D-4DFE-981B-A8BDB035F73D} | c0a8-0057-12c3b83c72f-467531e3-1c1de- | MF-HQ-10854 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2403/22468/MF185 | 10000 | 65.1302 | 31.7519 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {5A3AF6EF-698D-4DFE-981B-A8BDB035F73D} |  | Medium | Critical Infrastracture | Extreme | 514 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Eran | {2406E869-1C44-4FCB-8E08-1C83ABF0EE9A} | c0a8-0057-12c3b8612c9-9b4afa5c-1dc1c- | MF-HQ-10896 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22484/MF184 | 800000 | 65.059 | 31.8402 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 | Blank | {2406E869-1C44-4FCB-8E08-1C83ABF0EE9A} |  | Low | Agriculture Blocked | Extreme | 16 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Eran | {2406E869-1C44-4FCB-8E08-1C83ABF0EE9A} | c0a8-0057-12c3ba5ad70-44130b89-32617- | MF-HQ-10902 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22484/MF183 | 100000 | 65.059 | 31.8402 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {2406E869-1C44-4FCB-8E08-1C83ABF0EE9A} |  | Low | Agriculture Blocked | Extreme | 3 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Gach Karez Kalay | {43770F1A-3BDE-4B47-B123-7FB12D2BFCDE} | c0a8-0057-12c3ba7468f-323f5ac5-3360d- | MF-HQ-10893 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22416/MF197 | 90000 | 64.9813 | 31.647 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {43770F1A-3BDE-4B47-B123-7FB12D2BFCDE} |  | High with Victim | High with Victims | Extreme | 5 | SHA | 2 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Gach Karez Kalay | {43770F1A-3BDE-4B47-B123-7FB12D2BFCDE} | c0a8-0057-12c3bb79022-a173002b-3ced3- | MF-HQ-10890 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22416/MF196 | 120000 | 64.9685 | 31.6313 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {43770F1A-3BDE-4B47-B123-7FB12D2BFCDE} |  | High with Victim | High with Victims | Extreme | 4 | SHA | 2 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Hajimohammadkhan Kalay | {BB94E6AC-F073-4498-8540-BC209CFABCC3} | c0a8-0057-12c3b9aced7-54ac6-2bb35-f0a | MF-SA-611 | UNMACA - United Nation Mine Action Center for Afghanistan | Af/2407/22385/MF 182 | 143596 | 65.0823 | 31.5203 | Open | AT Only | AT Only | MineField |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {BB94E6AC-F073-4498-8540-BC209CFABCC3} |  | Low | Agriculture Blocked | Extreme | 101 | CHA | 5 |  |  | 2008-11-05 | No | Open
South | Kandahar | Maywand | Hajimohammadkhan Kalay | {BB94E6AC-F073-4498-8540-BC209CFABCC3} | c0a8-0057-12c3bb58040-5ad02e62-3bc38- | MF-SA-610 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22385/MF 181 | 103880 | 65.0689 | 31.5349 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {BB94E6AC-F073-4498-8540-BC209CFABCC3} |  | Low | Water Blocked | Extreme | 1 | CHA | 4 |  |  | 2008-11-05 | No | Open
South | Kandahar | Maywand | Hajimohammadkhan Kalay | {BB94E6AC-F073-4498-8540-BC209CFABCC3} | c0a8-0057-12c3bb82bc3-9ac02415-3d447- | MF-HQ-10737 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22442/MF208 | 90000 | 65.0812 | 31.5219 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {BB94E6AC-F073-4498-8540-BC209CFABCC3} |  | Medium | Comunity Centers | Extreme | 75 | SHA | 4 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Hajimohammadshah Kalay | {D9165DF7-171D-4075-983F-70083782A0E8} | c0a8-0057-12c3bb78e3f-49338ccd-3cec2- | MF-HQ-10739 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22442/MF198 | 1800 | 65.1008 | 31.5244 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {D9165DF7-171D-4075-983F-70083782A0E8} |  | High | Water Blocked | Extreme | 9 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Jawkari(Mohammadna'im Kalay) | {D54E0522-2C66-4660-A7C4-754895111EF0} | c0a8-0057-12c3ba58548-b785e395-32497- | MF-HQ-10858 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22448/MF207 | 250000 | 65.125 | 31.5337 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {D54E0522-2C66-4660-A7C4-754895111EF0} |  | Low | Agriculture Blocked | Extreme | 9 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Khodaydad Akhundzadah Kariz | {78A7F420-0F07-46C8-B2EB-BBDCC020DA40} | c0a8-0057-12c3b98e0ab-9e8cfc13-2a6a0- | MF-HQ-10859 | UNMACA - United Nation Mine Action Center for Afghanistan | Af/2704/22397/MF187 | 120000 | 65.0068 | 31.589 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {78A7F420-0F07-46C8-B2EB-BBDCC020DA40} |  | Low | Agriculture Blocked | Extreme | 18 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Loy Kariz | {0FB2881D-56B7-426E-8FDD-6A101CDBD06C} | c0a8-0057-12c3b83bfee-2cf4e96e-1c18e- | MF-HQ-10832 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22459/MF205 | 200000 | 65.0325 | 31.5687 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {0FB2881D-56B7-426E-8FDD-6A101CDBD06C} |  | High with Victim | High with Victims | Extreme | 13 | SHA | 2 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Moshak | {3827F423-2712-4601-8CCF-B976DE2B8890} | c0a8-0057-12c3b7dfe06-26e244df-180c7- | MF-HQ-10907 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22471/MF0190 | 90000 | 65.0581 | 31.6836 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {3827F423-2712-4601-8CCF-B976DE2B8890} |  | High with Victim | High with Victims | Extreme | 195 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Moshak | {3827F423-2712-4601-8CCF-B976DE2B8890} | c0a8-0057-12c3b9fc8ad-b8698c64-2ecba- | MF-HQ-10911 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22471/MF188 | 160000 | 65.0495 | 31.6845 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {3827F423-2712-4601-8CCF-B976DE2B8890} |  | High with Victim | High with Victims | Extreme | 112 | SHA | 4 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Moshak | {3827F423-2712-4601-8CCF-B976DE2B8890} | c0a8-0057-12c3ba3042d-b960f4ea-30c58- | MF-HQ-10905 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22471/MF189 | 7500 | 65.0613 | 31.6895 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {3827F423-2712-4601-8CCF-B976DE2B8890} |  | High with Victim | High with Victims | Extreme | 10 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Moshak | {3827F423-2712-4601-8CCF-B976DE2B8890} | c0a8-0057-12c3ba8f060-96145b6b-345a2- | MF-HQ-10910 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22471/MF191 | 120000 | 65.0495 | 31.6845 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {3827F423-2712-4601-8CCF-B976DE2B8890} |  | High with Victim | High with Victims | Extreme | 9 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Pacha kelay | {F4D5D9F8-3D8A-486B-B2BD-EAAA22C8C67B} | c0a8-0057-12c3b9a0dfc-51bceec8-2b310- | MF-HQ-10770 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/00768/MF192 | 90000 | 65.0765 | 31.5254 | Open | Mixed Mine | Mixed Mine | Converted From SHA | Blank | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 | Blank | {F4D5D9F8-3D8A-486B-B2BD-EAAA22C8C67B} |  | High | Water Blocked | Extreme | 23 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Pacha kelay | {F4D5D9F8-3D8A-486B-B2BD-EAAA22C8C67B} | c0a8-0057-12c3b9beb0a-60d00f86-2c63c- | MF-HQ-10769 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/00768/MF0193 | 10000 | 65.0765 | 31.5254 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {F4D5D9F8-3D8A-486B-B2BD-EAAA22C8C67B} |  | High | Water Blocked | Extreme | 86 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Shukor Kalay | {A6A4F6F3-C126-4D3F-B226-659251F5D642} | c0a8-0057-12c3b985c63-97fe730e-2a117- | MF-HQ-10746 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22395/MF194 | 80000 | 64.9868 | 31.6006 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {A6A4F6F3-C126-4D3F-B226-659251F5D642} |  | Low | Agriculture Blocked | Extreme | 21 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Shukor Kalay | {A6A4F6F3-C126-4D3F-B226-659251F5D642} | c0a8-0057-12c3b99307e-b5a6bebe-2a9ed- | MF-HQ-10744 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22395/MF195 | 80000 | 64.9868 | 31.6006 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {A6A4F6F3-C126-4D3F-B226-659251F5D642} |  | Low | Agriculture Blocked | Extreme | 12 | SHA | 5 |  |  | 2009-06-03 | No | Open
South | Kandahar | Maywand | Usmankhel | {5C26FE8B-C638-4E39-B5D2-B9FB557C36E9} | c0a8-0057-12c3b934ae0-cb91436a-26b77- | MF-HQ-10850 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/22392/MF186 | 20000 | 64.8885 | 31.5727 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-183 | Kandahar Demining Project-02 |  | No |  |  | 1397 |  | {5C26FE8B-C638-4E39-B5D2-B9FB557C36E9} |  | Medium | Water Blocked | Extreme | 2 | SHA | 3 |  |  | 2009-06-03 | No | Open
South | Kandahar | Panjwayi | Panjwayi | {44CEAF80-BC90-428D-88F8-FE216803EBB8} | c0a8-0009-13d390d02f8-a4da94f5-1103-b | Hz-ID-17688 | MACCA | AF/2408/31838/MF0141 | 26995 | 65.4622 | 31.5506 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-04-04 | 2013-04-10 | 1392 | EODT | {44CEAF80-BC90-428D-88F8-FE216803EBB8} |  |  |  | High | 142 | CHA | 2 |  |  | 2012-12-20 16:30 | No | Complete
South | Kandahar | Panjwayi | Panjwayi | {44CEAF80-BC90-428D-88F8-FE216803EBB8} | c0a8-0009-13d52d0585b-1cd1764a-14e9-5 | Hz-ID-17689 | MACCA | AF/2408/31838/MF0142 | 59032 | 65.4723 | 31.5492 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-04-08 | 2013-04-18 | 1392 | EODT | {44CEAF80-BC90-428D-88F8-FE216803EBB8} |  |  |  | High | 45 | CHA | 2 |  |  | 2012-12-20 16:30 | No | Complete
South | Kandahar | Panjwayi | Panjwayi | {44CEAF80-BC90-428D-88F8-FE216803EBB8} | c0a8-0009-13dbfc53d50-31c406dd-590b-b | Hz-ID-17691 | MACCA | AF/2408/31838/MF0144 | 60798 | 65.4752 | 31.5504 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-08-03 | 2013-08-11 | 1392 | EODT | {44CEAF80-BC90-428D-88F8-FE216803EBB8} |  |  |  | High | 45 | CHA | 2 |  |  | 2012-12-20 16:30 | No | Complete
South | Kandahar | Panjwayi | Panjwayi | {44CEAF80-BC90-428D-88F8-FE216803EBB8} | c0a8-00f6-13856dedbfe-fdcd17e8-157e-4 | Hz-ID-17112 | EODT- TECHNOLOGEY,INC | AF/2408/31838/MF0123 | 14515 | 65.473 | 31.5399 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-01-01 | 2013-01-05 | 1392 | EODT | {44CEAF80-BC90-428D-88F8-FE216803EBB8} |  |  |  | High | 465 | CHA | 1 |  |  | 2012-04-01 16:30 | No | Complete
South | Kandahar | Panjwayi | Salawat | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} | c0a8-0009-13dbfd8dd9c-bca40ce2-5bc0-8 | Hz-ID-17699 | MACCA | AF/2408/22296/MF0147 | 13453 | 65.5384 | 31.5245 | Open | AT Only | AT Only | MineField |  | MBT Project-165 | Kandahar Demining Project-09 |  |  |  |  | 1394 |  | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} |  | Low | Agriculture Blocked | High | 344 | CHA | 4 |  |  | 2012-12-20 16:30 | No | Open
South | Kandahar | Panjwayi | Salawat | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} | c0a8-0009-13dbfded9a4-7dd844c4-5bec-9 | Hz-ID-17700 | MACCA | AF/2408/22296/MF0148 | 36647 | 65.5419 | 31.5249 | Open | AT Only | AT Only | MineField |  | MBT Project-165 | Kandahar Demining Project-09 |  |  |  |  | 1394 |  | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} |  | Low | Agriculture Blocked | High | 1303 | CHA | 4 |  |  | 2012-12-30 16:30 | No | Open
South | Kandahar | Panjwayi | Salawat | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} | c0a8-0009-13dbfe42dca-8c2b15-5ca0-815 | Hz-ID-17701 | MACCA | AF/2408/22296/MF0149 | 429339 | 65.5419 | 31.5105 | Open | AT Only | AT Only | MineField |  | MBT Project-165 | Kandahar Demining Project-09 |  |  |  |  | 1394 |  | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} |  | Low | Agriculture Blocked | High | 489 | CHA | 4 |  |  | 2012-12-20 16:30 | No | Open
South | Kandahar | Panjwayi | Salawat | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} | c0a8-0009-13dbfeb5d8d-54427189-5ce5-4 | Hz-ID-17702 | MACCA | AF/2408/22296/MF0150 | 19606 | 65.5419 | 31.5249 | Open | AT Only | AT Only | MineField |  | MBT Project-165 | Kandahar Demining Project-09 |  |  |  |  | 1394 |  | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} |  | Low | Agriculture Blocked | High | 1279 | CHA | 4 |  |  | 2012-12-20 16:30 | No | Open
South | Kandahar | Panjwayi | Salawat | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} | c0a8-0009-1432e9ae49a-23f33642-38b9-2 | Hz-ID-18238 | DAFA - Demining Agency for Afghanistan | AF/2408/22296/MF0154 | 62725 | 65.5199 | 31.5287 | Open | AT Only | AT Only | MineField |  | MBT Project-165 | Kandahar Demining Project-09 |  |  |  |  | 1394 |  | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} |  | Medium | Critical Infrastracture | High | 472 | CHA | 5 |  |  | 2013-09-19 16:30 | No | Open
South | Kandahar | Panjwayi | Salawat | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} | c0a8-0009-14375cabb33-26444ada-275a-e | Hz-ID-18237 | DAFA - Demining Agency for Afghanistan | AF/2408/22296/MF0153 | 210625 | 65.5086 | 31.5049 | Open | AT Only | AT Only | MineField |  | MBT Project-165 | Kandahar Demining Project-09 |  |  |  |  | 1394 |  | {094790D3-8B4C-44F5-8B99-D4BE169E2B11} |  | Medium | Critical Infrastracture | High | 886 | CHA | 3 |  |  | 2013-09-19 16:30 | No | Open
South | Kandahar | Panjwayi | Salehan | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} | c0a8-0009-13d585c9d30-7ebf8921-849-de | Hz-ID-17697 | DAFA - Demining Agency for Afghanistan | AF/2408/22354/MF0152 | 65158 | 65.5232 | 31.5592 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-05-01 | 2013-05-16 | 1392 | EODT | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} |  |  |  | High | 81 | CHA | 2 |  |  | 2013-03-10 16:30 | No | Complete
South | Kandahar | Panjwayi | Salehan | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} | c0a8-0009-13dab198e13-4020b34f-4d2-41 | Hz-ID-17696 | DAFA - Demining Agency for Afghanistan | AF/2408/22354/MF0151 | 80750 | 65.519 | 31.5611 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-04-01 | 2013-04-17 | 1392 | EODT | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} |  |  |  | High | 150 | CHA | 2 |  |  | 2013-03-10 16:30 | No | Complete
South | Kandahar | Panjwayi | Salehan | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} | c0a8-0009-13dbfd126df-d8697d1d-5b2b-5 | Hz-ID-17698 | MACCA | AF/2408/22354/MF0146 | 182182 | 65.5456 | 31.5838 | Open | AT Only | AT Only | MineField |  | MBT Project-165 | Kandahar Demining Project-09 |  |  |  |  | 1394 |  | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} |  | High with Victim | High with Victims | High | 226 | CHA | 2 |  |  | 2012-12-20 16:30 | No | Open
South | Kandahar | Panjwayi | Salehan | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} | c0a8-0009-13dc9a7d9ed-6792bf85-2297-9 | Hz-ID-17694 | MACCA | AF/2408/22354/MF0145 | 540223 | 65.5456 | 31.5838 | Open | AT Only | AT Only | MineField |  | MBT Project-165 | Kandahar Demining Project-09 |  |  |  |  | 1394 |  | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} |  | High with Victim | High with Victims | High | 427 | CHA | 2 |  |  | 2012-12-20 16:30 | No | Open
South | Kandahar | Panjwayi | Salehan | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} | c0a8-0057-12c3b99189b-7fa4d075-2a8ed- | MF-SA-697 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2408/22354/MF0111 | 24540 | 65.5588 | 31.5777 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-05-12 | 2013-05-16 | 1392 | EODT | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} |  |  |  | High | 36 | CHA | 2 |  |  | 2009-03-22 | No | Complete
South | Kandahar | Panjwayi | Salehan | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} | c0a8-0057-12c3b991adc-efea0b11-2a8fe- | MF-SA-532 | DAFA - Demining Agency for Afghanistan | AF/2408/22354/MF0099 | 132898 | 65.5634 | 31.5833 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-04-21 | 2013-05-18 | 1392 | EODT | {CAD1638F-C99A-413F-86C3-8D897CECCFD9} | , |  |  | High | 91 | CHA | 2 |  |  | 2007-07-28 | No | Complete
South | Kandahar | Panjwayi | Seperwan | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} | c0a8-0009-13c13eba18e-14472ca6-656-a3 | Hz-ID-17555 | DAFA - Demining Agency for Afghanistan | AF/2408/22274/MF0133 | 1416328 | 65.4167 | 31.4675 | Open | AT Only | AT Only | MineField |  | MBT Project-165 | Kandahar Demining Project-09 |  | No | 2013-07-27 | 2013-08-29 | 1394 |  | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} |  | High with Victim | High with Victims | High | 23 | CHA | 2 |  |  | 2012-12-11 16:30 | No | Open
South | Kandahar | Panjwayi | Seperwan | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} | c0a8-0009-13c1498587c-e1ed974a-874-b2 | Hz-ID-17557 | EODT- TECHNOLOGEY,INC | AF/2408/22274/MF0135 | 226913 | 65.4307 | 31.4789 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-06-10 | 2013-07-15 | 1392 | EODT | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} |  |  |  | High | 175 | CHA | 2 |  |  | 2012-12-19 16:30 | No | Complete
South | Kandahar | Panjwayi | Seperwan | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} | c0a8-0009-13c14d5f96d-4cf50dc2-932-5b | Hz-ID-17558 | EODT- TECHNOLOGEY,INC | AF/2408/22274/MF0136 | 189244 | 65.4362 | 31.4812 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-06-12 | 2013-07-07 | 1392 | EODT | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} |  |  |  | High | 0 | CHA | 2 |  |  | 2012-12-20 16:30 | No | Complete
South | Kandahar | Panjwayi | Seperwan | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} | c0a8-0009-13c1f218cee-6f4c0096-6bb-a6 | Hz-ID-17586 | EODT- TECHNOLOGEY,INC | AF/2408/22274/MF0138 | 193188 | 65.4454 | 31.4822 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-07-10 | 2013-07-29 | 1392 | EODT | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} |  |  |  | High | 0 | CHA | 2 |  | Accordant to contract depth for clearance is 20cm | 2012-12-23 16:30 | No | Complete
South | Kandahar | Panjwayi | Seperwan | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} | c0a8-0009-13c22f987cb-51ffff60-819-e1 | Hz-ID-17591 | EODT- TECHNOLOGEY,INC | AF/2408/22274/MF0139 | 191179 | 65.4497 | 31.4819 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-07-10 | 2013-07-29 | 1392 | EODT | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} |  |  |  | High | 5 | CHA | 2 |  |  | 2012-12-24 16:30 | No | Complete
South | Kandahar | Panjwayi | Seperwan | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} | c0a8-0009-13c230ca3c4-fc018db1-990-a6 | Hz-ID-17602 | EODT- TECHNOLOGEY,INC | AF/2408/22274/MF0140 | 165235 | 65.4521 | 31.4853 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-06-26 | 2013-07-12 | 1392 | EODT | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} |  |  |  | High | 5 | CHA | 2 |  |  | 2012-12-25 16:30 | No | Complete
South | Kandahar | Panjwayi | Seperwan | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} | c0a8-0009-13c236bf133-a0d5c4b1-1079-6 | Hz-ID-17566 | EODT- TECHNOLOGEY,INC | AF/2408/22274/MF0137 | 160767 | 65.4386 | 31.4805 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-06-29 | 2013-07-15 | 1392 | EODT | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} |  |  |  | High | 0 | CHA | 2 |  |  | 2012-12-22 16:30 | No | Complete
South | Kandahar | Panjwayi | Seperwan | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} | c0a8-0009-13cc3216d5b-962b01d4-483-fd | Hz-ID-17556 | EODT- TECHNOLOGEY,INC | AF/2408/22274/MF0134 | 308523 | 65.4219 | 31.479 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-05-18 | 2013-07-17 | 1392 | EODT | {69D81ADE-CE58-4BD6-B6B3-60E87F2B47E3} |  |  |  | High | 180 | CHA | 2 |  |  | 2012-12-18 16:30 | No | Complete
South | Kandahar | Spin Boldak | Kacey | {160C9D74-D2B0-404C-BCD2-376D6A5275E5} | c0a8-0009-13adef84ab4-b1da2edb-13db-1 | Hz-ID-17340 | EODT- TECHNOLOGEY,INC | AF/2411/21317/MF0156 | 89243 | 66.567 | 31.1362 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-03-10 | 2013-04-04 | 1392 | EODT | {160C9D74-D2B0-404C-BCD2-376D6A5275E5} |  |  |  | High | 0 | CHA | 2 |  |  | 2012-08-12 16:30 | No | Complete
South | Kandahar | Spin Boldak | Kacey | {160C9D74-D2B0-404C-BCD2-376D6A5275E5} | c0a8-0009-13adef950da-90589afb-13f9-f | Hz-ID-17342 | EODT- TECHNOLOGEY,INC | AF/2411/21317/MF0157 | 137600 | 66.5828 | 31.1448 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-04-01 | 2013-05-26 | 1392 | EODT | {160C9D74-D2B0-404C-BCD2-376D6A5275E5} |  |  |  | High | 0 | CHA | 2 |  |  | 2012-08-14 16:30 | No | Complete
South | Kandahar | Spin Boldak | Kacey | {160C9D74-D2B0-404C-BCD2-376D6A5275E5} | c0a8-0009-13adefa1be5-5e7d11cd-1415-d | Hz-ID-17343 | EODT- TECHNOLOGEY,INC | AF/2411/21317/MF0158 | 140369 | 66.5828 | 31.1448 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-05-25 | 2013-07-21 | 1392 | EODT | {160C9D74-D2B0-404C-BCD2-376D6A5275E5} |  |  |  | High | 0 | CHA | 2 |  |  | 2012-08-29 16:30 | No | Complete
South | Kandahar | Spin Boldak | Robat Mil | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} | c0a8-0009-13c22fe9e34-bf01521e-85b-b3 | Hz-ID-17596 | EODT- TECHNOLOGEY,INC | AF/2411/21171/MF0159 | 46617 | 66.112 | 31.0552 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-07-09 | 2013-07-13 | 1392 | EODT | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} |  |  |  | High | 0 | CHA | 2 |  |  | 2012-12-19 16:30 | No | Complete
South | Kandahar | Spin Boldak | Robat Mil | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} | c0a8-0009-13c23030961-1001ffa6-8a9-b9 | Hz-ID-17598 | EODT- TECHNOLOGEY,INC | AF/2411/21171/MF0160 | 266814 | 66.0975 | 31.0693 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-04-30 | 2013-06-13 | 1392 | EODT | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} |  |  |  | High | 4 | CHA | 2 |  |  | 2012-12-24 16:30 | No | Complete
South | Kandahar | Spin Boldak | Robat Mil | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} | c0a8-0009-13cc315ba11-6b7a3d1c-301-d0 | Hz-ID-17647 | EODT- TECHNOLOGEY,INC | AF/2411/21171/MF0163 | 481500 | 66.1221 | 31.0483 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-05-30 | 2013-08-18 | 1392 | EODT | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} |  |  |  | High | 18 | CHA | 2 |  |  | 2013-01-08 16:30 | No | Complete
South | Kandahar | Spin Boldak | Robat Mil | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} | c0a8-0009-13cc35d62a8-bd586849-7ca-f0 | Hz-ID-17638 | EODT- TECHNOLOGEY,INC | AF/2411/21171/MF0166 | 277761 | 66.1221 | 31.0483 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-06-13 | 2013-07-30 | 1392 | EODT | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} |  |  |  | High | 10 | CHA | 2 |  |  | 2013-01-10 16:30 | No | Complete
South | Kandahar | Spin Boldak | Robat Mil | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} | c0a8-0009-13cc35d865e-e39bfdfc-7e1-4f | Hz-ID-17635 | EODT- TECHNOLOGEY,INC | AF/2411/21171/MF0167 | 224765 | 66.1221 | 31.0483 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-06-11 | 2013-07-03 | 1392 | EODT | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} |  |  |  | High | 10 | CHA | 2 |  |  | 2013-01-12 16:30 | No | Complete
South | Kandahar | Spin Boldak | Robat Mil | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} | c0a8-0009-13cc35ea13d-cc94db97-816-dd | Hz-ID-17640 | EODT- TECHNOLOGEY,INC | AF/2411/21171/MF0165 | 113798 | 66.1114 | 31.048 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-06-29 | 2013-07-10 | 1392 | EODT | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} |  |  |  | High | 10 | CHA | 2 |  |  | 2013-01-10 16:30 | No | Complete
South | Kandahar | Spin Boldak | Robat Mil | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} | c0a8-0009-13cc35ef39e-9765135d-84f-ad | Hz-ID-17646 | EODT- TECHNOLOGEY,INC | AF/2411/21171/MF0164 | 247246 | 66.1221 | 31.0483 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-05-28 | 2013-07-01 | 1392 | EODT | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} |  |  |  | High | 18 | CHA | 2 |  |  | 2013-01-08 16:30 | No | Complete
South | Kandahar | Spin Boldak | Robat Mil | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} | c0a8-0009-13d0aa8ea7b-1acf563f-347d-b | Hz-ID-17648 | EODT- TECHNOLOGEY,INC | AF/2411/21171/MF0162 | 174223 | 66.1141 | 31.0455 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-06-28 | 2013-07-16 | 1392 | EODT | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} |  |  |  | High | 8 | CHA | 2 |  |  | 2013-01-06 16:30 | No | Complete
South | Kandahar | Spin Boldak | Robat Mil | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} | c0a8-0057-12c3b992067-5c64511a-2a936- | MF-HQ-10776 | EODT- TECHNOLOGEY,INC | AF/2411/21171/MF0068 | 119484 | 66.1401 | 31.0688 | Closed | AT Only | AT Only | MineField | 1391 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-03-19 | 2013-04-10 | 1392 | EODT | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} |  |  |  | High | 0 | CHA | 2 |  |  | 2009-06-03 | No | Complete
South | Kandahar | Spin Boldak | Robat Mil | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} | c0a8-0057-12c3bb395c7-41efa366-3aa88- | MF-SA-606 | EODT- TECHNOLOGEY,INC | AF/2411/21171/MF0054 | 130205 | 66.1154 | 31.0527 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-053 | EODT Kandahar East EMCPA Project | UAE | Yes | 2013-04-11 | 2013-05-02 | 1392 | EODT | {0A295814-5BC4-47D7-96EC-4FE85B2ECB96} |  |  |  | High | 0 | CHA | 2 |  |  | 2008-11-04 | No | Complete
South | Kandahar | Zhari | Ashoqa | {AD124CC5-B3B1-4AAB-9CDD-0B76129D0ED9} | c0a8-0057-12c3b80bab8-ff7076a1-19f36- | MF-SA-128 | EODT- TECHNOLOGEY,INC | AF/2408/22155/MF0041 | 97302 | 65.486 | 31.6047 | Closed | AP Only | AP Only | MineField | 1391 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-02-24 | 2013-03-17 | 1392 | EODT | {AD124CC5-B3B1-4AAB-9CDD-0B76129D0ED9} | Haji Salih Mohammad -- Sadiq Agha –Jana – Jan Mohammad |  |  | High | 26 | CHA | 2 |  |  | 2003-05-31 | No | Complete
South | Kandahar | Zhari | Ashoqa | {AD124CC5-B3B1-4AAB-9CDD-0B76129D0ED9} | c0a8-0057-12c3b8621f5-7ab1590a-1dcc6- | MF-HQ-10728 | DAFA - Demining Agency for Afghanistan | AF/2408/22155/MF0190 | 150400 | 65.4472 | 31.5846 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-286 | Kandahar Demining Project-05 AT | VTF-Japan | Yes | 2013-05-15 | 2013-08-31 | 1392 | DAFA | {AD124CC5-B3B1-4AAB-9CDD-0B76129D0ED9} | Part of MF 0187 Zhari Project |  |  | High | 2 | CHA | 2 |  |  | 2009-06-03 | No | Complete
South | Kandahar | Zhari | Ashoqa | {AD124CC5-B3B1-4AAB-9CDD-0B76129D0ED9} | c0a8-0057-12c3b8e4e6c-50682686-237e5- | MF-HQ-10725 | DAFA - Demining Agency for Afghanistan | AF/2416/22155/MF0191 | 198000 | 65.4498 | 31.599 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-286 | Kandahar Demining Project-05 AT | VTF-Japan | Yes | 2013-05-15 | 2013-07-31 | 1392 | DAFA | {AD124CC5-B3B1-4AAB-9CDD-0B76129D0ED9} | Part of MF 0187 Zhari Project |  |  | High | 2 | CHA | 2 |  |  | 2009-06-03 | No | Complete
South | Kandahar | Zhari | Ashoqa | {AD124CC5-B3B1-4AAB-9CDD-0B76129D0ED9} | c0a8-0057-12c3b96ed16-f45347d2-291e7- | MF-SA-120 | DAFA - Demining Agency for Afghanistan | AF/2416/22155/MF0038 | 105600 | 65.3754 | 31.6003 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-286 | Kandahar Demining Project-05 AT | VTF-Japan | Yes | 2013-08-01 | 2013-09-10 | 1392 | DAFA | {AD124CC5-B3B1-4AAB-9CDD-0B76129D0ED9} |  |  |  | High | 108 | CHA | 2 |  |  | 2003-04-30 | No | Complete
South | Kandahar | Zhari | Ashoqa | {AD124CC5-B3B1-4AAB-9CDD-0B76129D0ED9} | c0a8-008e-13213d9ad29-56c533ae-fdb-6a | MF-SA-129 | DAFA - Demining Agency for Afghanistan | AF/2416/22155/MF0039 | 98300 | 65.4806 | 31.5959 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-286 | Kandahar Demining Project-05 AT | VTF-Japan | Yes | 2013-05-15 | 2013-07-30 | 1392 | DAFA | {AD124CC5-B3B1-4AAB-9CDD-0B76129D0ED9} |  |  |  | High | 213 | CHA | 2 |  |  | 2003-05-31 | No | Complete
South | Kandahar | Zhari | Kariz-e Salim | {26A470EB-BB10-4E59-B236-C8180280CCE3} | c0a8-0057-12c3b828ee3-5ca75fda-1b3f1- | MF-SA-168 | MCPA - Mine Clearance Planning Agency | AF/2408/22329/MF0050 | 151905 | 65.3551 | 31.6356 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-05-22 | 2013-06-22 | 1392 | EODT | {26A470EB-BB10-4E59-B236-C8180280CCE3} |  |  |  | High | 0 | CHA | 1 |  |  | 2003-08-31 | No | Complete
South | Kandahar | Zhari | Kariz-e Salim | {26A470EB-BB10-4E59-B236-C8180280CCE3} | c0a8-0057-12c3b9bcd7c-c8ac074a-2c51d- | MF-SA-183 | MCPA - Mine Clearance Planning Agency | AF/2408/22329/054 | 121458 | 65.356 | 31.6388 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-304 | EODT Kandahar West EMCPA Project | UAE | Yes | 2013-06-17 | 2013-07-17 | 1392 | EODT | {26A470EB-BB10-4E59-B236-C8180280CCE3} |  |  |  | High | 0 | CHA | 1 |  |  | 2003-09-01 | No | Complete
South | Kandahar | Zhari | Makuan | {B5FC2ABC-49C9-403F-8749-49891925959E} | c0a8-0009-14371336e84-62e0a1a1-13f43- | Hz-ID-18334 | DAFA - Demining Agency for Afghanistan | AF/2416/22349/MF0227 | 288310 | 65.46 | 31.6053 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {B5FC2ABC-49C9-403F-8749-49891925959E} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2013-07-14 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13c84adfa62-6a12f7a-598-5d1 | Hz-ID-17609 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0204 | 113755 | 65.4193 | 31.6065 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-168 | Kandahar Demining Project-01 AT | DOS | Yes | 2013-04-09 | 2013-10-31 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2012-12-29 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13cc29d2912-9aa13a2d-1b7-da | Hz-ID-17634 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0213 | 212622 | 65.4034 | 31.5869 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-182 | Kandahar Demining Project-03 AT | DOS | Yes | 2013-05-11 | 2013-12-22 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-07-22 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13cc2a54caf-63e5dddf-290-84 | Hz-ID-17637 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0214 | 188198 | 65.3918 | 31.5899 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-182 | Kandahar Demining Project-03 AT | DOS | Yes | 2013-05-11 | 2013-12-12 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-01-13 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13cc2b04c4e-b0297c39-533-85 | Hz-ID-17641 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0215 | 210149 | 65.4016 | 31.5935 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-182 | Kandahar Demining Project-03 AT | DOS | Yes | 2013-05-11 | 2013-12-18 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-01-12 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13cc2b646b5-ca8c9836-5be-bd | Hz-ID-17643 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0217 | 166786 | 65.401 | 31.6004 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-182 | Kandahar Demining Project-03 AT | DOS | Yes | 2013-05-11 | 2013-11-30 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-01-12 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13ce6697565-975e0613-17bb-b | Hz-ID-17618 | DAFA - Demining Agency for Afghanistan | AF/2416/22343/MF0209 | 153478 | 65.4017 | 31.6037 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-168 | Kandahar Demining Project-01 AT | DOS | Yes | 2013-11-19 | 2014-02-13 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2012-12-29 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13ce690c4dc-5d52de23-17e3-4 | Hz-ID-17639 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0216 | 183916 | 65.4026 | 31.5991 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-182 | Kandahar Demining Project-03 AT | DOS | Yes | 2013-05-11 | 2013-12-10 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-01-12 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13ce6a11e88-6322f752-18c3-f | Hz-ID-17645 | DAFA - Demining Agency for Afghanistan | AF/2416/22343/MF0219 | 128703 | 65.3939 | 31.5976 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-182 | Kandahar Demining Project-03 AT | DOS | Yes | 2013-12-11 | 2014-02-13 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-01-12 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13d0a93077d-2ca64c28-3443-b | Hz-ID-17614 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0205 | 100751 | 65.4193 | 31.6065 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-168 | Kandahar Demining Project-01 AT | DOS | Yes | 2013-04-09 | 2013-08-22 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2012-12-29 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13d0ab535a4-2356fe8a-3497-1 | Hz-ID-17615 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0206 | 110476 | 65.4119 | 31.6061 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-168 | Kandahar Demining Project-01 AT | DOS | Yes | 2013-04-09 | 2013-11-04 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2012-12-29 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13d0ac3466c-f84831b9-34b9-c | Hz-ID-17617 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0208 | 113550 | 65.4067 | 31.6027 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-168 | Kandahar Demining Project-01 AT | DOS | Yes | 2013-10-21 | 2013-12-19 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2012-12-29 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13d0ac7d75c-f4d12396-34d8-4 | Hz-ID-17619 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0210 | 176990 | 65.3953 | 31.6061 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-168 | Kandahar Demining Project-01 AT | DOS | Yes | 2013-11-05 | 2014-02-13 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2012-12-29 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13d43ba41fa-f95ab8f7-c8a-d1 | Hz-ID-17616 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0207 | 149528 | 65.4122 | 31.6038 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-168 | Kandahar Demining Project-01 AT | DOS | Yes | 2013-04-09 | 2013-11-18 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2012-12-29 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13dab1b1e89-8f5bd4e2-4f7-18 | Hz-ID-17629 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0211 | 229437 | 65.3953 | 31.606 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-168 | Kandahar Demining Project-01 AT | DOS | Yes | 2013-11-02 | 2014-02-13 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2012-12-29 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13dc43f5941-3ea914dc-e8e-e5 | Hz-ID-17644 | DAFA - Demining Agency for Afghanistan | AF/2416/22343/MF0218 | 113775 | 65.4067 | 31.6027 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-182 | Kandahar Demining Project-03 AT | DOS | Yes |  |  | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-01-12 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13dc4451bcc-34e87205-ede-7a | Hz-ID-17630 | DAFA - Demining Agency for Afghanistan | AF/2416/22343/MF0222 | 491415 | 65.3761 | 31.6213 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-286 | Kandahar Demining Project-05 AT | VTF-Japan | Yes | 2013-09-29 | 2013-12-31 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-09-05 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13dc4533171-86142667-1144-1 | Hz-ID-17636 | DAFA - Demining Agency for Afghanistan | AF/2416/22343/MF0221 | 149484 | 65.3877 | 31.5971 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-182 | Kandahar Demining Project-03 AT | DOS | Yes | 2013-12-14 | 2014-02-13 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 2 |  |  | 2013-01-12 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13dc4567e14-16880aca-11a6-6 | Hz-ID-17642 | DAFA - Demining Agency for Afghanistan | AF/2416/22343/MF0220 | 169586 | 65.3939 | 31.5976 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-182 | Kandahar Demining Project-03 AT | DOS | Yes | 2013-12-01 | 2014-02-13 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-01-12 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-13dc4699230-4b1a2bd9-1393-4 | Hz-ID-17608 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0203 | 95565 | 65.4179 | 31.602 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-168 | Kandahar Demining Project-01 AT | DOS | Yes | 2013-04-09 | 2013-07-17 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2012-12-29 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-140ed88493e-3fe517c-30c7-58 | Hz-ID-18126 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0223 | 237235 | 65.4193 | 31.6065 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-286 | Kandahar Demining Project-05 AT | VTF-Japan | Yes | 2013-09-02 | 2013-11-30 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-08-28 16:30 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-143712e3000-67dab8b8-13f17- | Hz-ID-18335 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0228 | 635121 | 65.4307 | 31.6064 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-10-20 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-1437153d929-c160e5f2-141aa- | Hz-ID-18337 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0230 | 296075 | 65.4342 | 31.619 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-11-02 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-14371573ae5-e3932d4d-14204- | Hz-ID-18338 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0231 | 273709 | 65.4146 | 31.6153 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-11-10 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-143715a3788-532528ed-1427c- | Hz-ID-18336 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0229 | 376599 | 65.4348 | 31.6141 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-11-02 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-143715cf920-809074d9-14322- | Hz-ID-18333 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0226 | 41090 | 65.4268 | 31.6128 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-08-20 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-143715e3c18-e5496028-1439f- | Hz-ID-18339 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0233 | 72086 | 65.4516 | 31.6264 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-11-23 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-143717ed398-5a36fbde-145d1- | Hz-ID-18340 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0235 | 106855 | 65.4316 | 31.6335 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-10-20 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-1437533450e-fc66023f-888-34 | Hz-ID-18341 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0236 | 210132 | 65.4276 | 31.6308 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-12-03 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-1437535e2c3-3e74723a-ce9-6b | Hz-ID-18342 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0237 | 61009 | 65.4272 | 31.628 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-12-02 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-14375384b4b-388da16c-1117-2 | Hz-ID-18343 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0238 | 250528 | 65.4205 | 31.6247 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-12-07 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-143753aff37-749c18f0-12f3-6 | Hz-ID-18344 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0239 | 366831 | 65.4205 | 31.6347 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-12-09 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-143754484ef-6c3c0097-18d6-7 | Hz-ID-18345 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0240 | 227931 | 65.407 | 31.6309 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-12-11 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-143754952e5-c3b93144-1ad4-4 | Hz-ID-18346 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0241 | 318442 | 65.407 | 31.6309 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-12-17 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-143755ea687-8d1f777-2019-bd | Hz-ID-18347 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0242 | 301311 | 65.4205 | 31.6347 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-12-16 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-1437560859e-e76240e6-2033-3 | Hz-ID-18348 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0243 | 317010 | 65.4097 | 31.6429 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2013-12-16 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-1448bb7139b-581dc91d-203-f4 | Hz-ID-18495 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0248 | 287327 | 65.3967 | 31.6179 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2014-02-12 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-1448bc94c96-b1a8d2fc-222-1b | Hz-ID-18496 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0249 | 261103 | 65.3967 | 31.6179 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2014-02-12 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-1448bcb1453-55271af3-23b-5b | Hz-ID-18497 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0250 | 326131 | 65.3819 | 31.6192 | Open | AT Only | AT Only | MineField |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2014-02-12 16:30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-14495d528b8-9ef7a932-db5-61 | Hz-ID-18547 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0244 | 221670 | 65.4386 | 31.6135 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-169 | Kandahar Demining Project-02 AT | DOS | Yes | 2014-03-01 | 2014-09-27 | 1393 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2014-03-04 16:30 | No | Planned
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-14495e21f53-4569cee9-e30-77 | Hz-ID-18548 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0245 | 209414 | 65.3864 | 31.6135 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-169 | Kandahar Demining Project-02 AT | DOS | Yes | 2014-03-01 | 2014-09-18 | 1393 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2014-03-04 16:30 | No | Planned
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-14495e46211-69e96fbe-e4b-a3 | Hz-ID-18549 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0246 | 242710 | 65.3929 | 31.6133 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-169 | Kandahar Demining Project-02 AT | DOS | Yes | 2014-03-01 | 2014-09-26 | 1393 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2014-03-04 16:30 | No | Planned
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0009-14495e5b05e-67db4854-e63-1e | Hz-ID-18550 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0247 | 255772 | 65.4032 | 31.6147 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-169 | Kandahar Demining Project-02 AT | DOS | Yes | 2014-03-01 | 2014-09-30 | 1393 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2014-03-04 16:30 | No | Planned
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0057-12c3b83446a-94916406-1bbe8- | MF-SA-141 | MCPA - Mine Clearance Planning Agency | AF/2414/045/MF 151 | 91101 | 65.3372 | 31.6607 | Open | AT Only | AT Only | MineField | Blank | MBT Project-136 | Kandahar Demining Project-01 |  | No |  |  | 1394 | Blank | {9810099B-F29B-4218-8D75-920F941469B8} | Removed from DAFA Contingincy plan | High with Victim | High with Victims | High | 23 | CHA | 1 |  |  | 2003-06-30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0057-12c3b860f21-6b616829-1dbf8- | MF-HQ-10717 | DAFA - Demining Agency for Afghanistan | AF/2416/22343/MF0186 | 188569 | 65.4003 | 31.6109 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-168 | Kandahar Demining Project-01 AT | DOS | Yes | 2013-10-01 | 2014-02-13 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2009-06-03 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0057-12c3b86899c-4cba95fa-1e140- | MF-HQ-10719 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0185 | 280766 | 65.3819 | 31.6192 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-169 | Kandahar Demining Project-02 AT | DOS | Yes | 2014-03-01 | 2014-10-29 | 1393 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2009-06-03 | No | Planned
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0057-12c3b96eefa-4b47ab2c-291fd- | MF-SA-593 | DAFA - Demining Agency for Afghanistan | AF/2408/22343/MF0107 | 115211 | 65.3859 | 31.5966 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-182 | Kandahar Demining Project-03 AT | DOS | Yes |  |  | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2008-11-04 | No | Complete
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0057-12c3baa4bb5-6d1545d3-351f6- | MF-SA-193 | MCPA - Mine Clearance Planning Agency | AF/2416/22343/MF0123 | 27254 | 65.3987 | 31.6555 | Open | AT Only | AT Only | MineField | Blank | MBT Project-136 | Kandahar Demining Project-01 |  | No |  |  | 1394 | Blank | {9810099B-F29B-4218-8D75-920F941469B8} | Contingency task for DAFA Zhari DOS demining Project 1390 | High with Victim | High with Victims | High | 0 | CHA | 1 |  |  | 2003-06-30 | No | Open
South | Kandahar | Zhari | Pasab | {9810099B-F29B-4218-8D75-920F941469B8} | c0a8-0057-12c3baf5901-db319bd2-3820e- | MF-HQ-10718 | DAFA - Demining Agency for Afghanistan | AF/2416/22343/MF0183 | 512536 | 65.3822 | 31.6168 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-286 | Kandahar Demining Project-05 AT | VTF-Japan | Yes | 2013-09-01 | 2013-12-30 | 1392 | DAFA | {9810099B-F29B-4218-8D75-920F941469B8} |  |  |  | High | 0 | CHA | 1 |  |  | 2009-06-03 | No | Complete
South | Kandahar | Zhari | Pashmol | {80154717-720C-4735-AF44-92AD180A0E26} | c0a8-0057-12c3b7d0d82-3bb51387-17619- | MF-HQ-10724 | DAFA - Demining Agency for Afghanistan | AF/2416/00388/MF0188 | 61700 | 65.4274 | 31.5813 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-286 | Kandahar Demining Project-05 AT | VTF-Japan | Yes | 2013-09-28 | 2013-11-26 | 1392 | DAFA | {80154717-720C-4735-AF44-92AD180A0E26} |  |  |  | High | 1 | SHA | 1 |  |  | 2009-06-03 | No | Complete
South | Kandahar | Zhari | Pashmol | {80154717-720C-4735-AF44-92AD180A0E26} | c0a8-0057-12c3b869494-959eb68d-1e1b8- | MF-SA-602 | DAFA - Demining Agency for Afghanistan | AF/2408/00388/MF0106 | 150352 | 65.421 | 31.6121 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-286 | Kandahar Demining Project-05 AT | VTF-Japan | Yes | 2013-07-30 | 2013-09-26 | 1392 | DAFA | {80154717-720C-4735-AF44-92AD180A0E26} |  |  |  | High | 0 | CHA | 2 |  |  | 2008-11-05 | No | Complete
South | Kandahar | Zhari | Sangi Hisar | {1D9B0F41-D44F-4144-9C11-08857CBCC357} | c0a8-0057-12c3b9c193a-dfca2dfd-2c811- | MF-HQ-10863 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2416/32179/MF0182 | 80000 | 65.3095 | 31.5475 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-136 | Kandahar Demining Project-01 |  |  |  |  | 1394 |  | {1D9B0F41-D44F-4144-9C11-08857CBCC357} |  | High with Victim | High with Victims | High | 256 | SHA | 2 |  |  | 2009-06-03 | No | Open
South | Kandahar | Zhari | Sangi Hisar | {1D9B0F41-D44F-4144-9C11-08857CBCC357} | c0a8-0057-12c3bb54266-3b2e273d-3ba37- | MF-SA-605 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2407/32179/MF 179 | 14622500 | 65.3048 | 31.5635 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-135 | Kandahar Demining Project-10 |  |  |  |  | 1394 |  | {1D9B0F41-D44F-4144-9C11-08857CBCC357} |  | High with Victim | High with Victims | High | 97 | CHA | 2 |  |  | 2008-11-05 | No | Open
South | Nimroz | Chahar Burjak | Ashkinak (1) | {4DF7FB8C-2764-44F0-BF2A-4BF9E184A003} | c0a8-0009-14416923f5c-abdd0118-50b7-1 | Hz-ID-18399 | DAFA - Demining Agency for Afghanistan | AF/2203/20002/MF0048 | 112930 | 62.2233 | 30.2028 | Open | AP Only | AP Only | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {4DF7FB8C-2764-44F0-BF2A-4BF9E184A003} |  | High with Victim | High with Victims | High | 0 | CHA | 3 |  |  | 2013-12-21 16:30 | No | Open
South | Nimroz | Chahar Burjak | Bandare Janubi | {90B7F542-EE21-468B-AB22-ABA8F4BA5528} | c0a8-0009-143718a02ce-3fa3edda-146e2- | Hz-ID-18330 | DAFA - Demining Agency for Afghanistan | AF/2203/19983/MF0043 | 775880 | 60.9538 | 29.8846 | Open | Mixed | Mixed AP AT UXO | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {90B7F542-EE21-468B-AB22-ABA8F4BA5528} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2013-12-07 16:30 | No | Open
South | Nimroz | Chahar Burjak | Bandare Shamali | {062F0623-135D-4985-8935-11076A5140BB} | c0a8-0009-1433cd08809-3f3c6417-3b9c-b | Hz-ID-18297 | DAFA - Demining Agency for Afghanistan | AF/2203/19984/MF0041 | 412220 | 61.9127 | 30.2842 | Open | AP Only | AP Only | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {062F0623-135D-4985-8935-11076A5140BB} |  | Medium | Critical Infrastracture | High | 25 | CHA | 5 |  |  | 2013-11-14 16:30 | No | Open
South | Nimroz | Chahar Burjak | Chahar Borjak | {308CC219-B853-4966-A868-95D16FCF66C7} | c0a8-0057-12c3b7c6e87-977c4a14-16ec8- | MF-HQ-10470 | DAFA - Demining Agency for Afghanistan | AF/2203/20010/MF0027 | 25315 | 62.0454 | 30.2843 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-101 | Nimroz Demining Project-01 | VTF-Japan | Yes | 2014-06-15 | 2014-12-27 | 1393 | DAFA | {308CC219-B853-4966-A868-95D16FCF66C7} |  | High with Victim | High with Victims | High | 5 | CHA | 1 |  |  | 2009-05-20 | No | Planned
South | Nimroz | Chahar Burjak | Chahar Borjak | {308CC219-B853-4966-A868-95D16FCF66C7} | c0a8-0057-12c3b854234-d730ed93-1d32b- | MF-HQ-10472 | DAFA - Demining Agency for Afghanistan | AF/2203/20010/MF0026 | 318 | 62.0472 | 30.2841 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-101 | Nimroz Demining Project-01 | VTF-Japan | Yes | 2014-07-01 | 2014-07-17 | 1393 | DAFA | {308CC219-B853-4966-A868-95D16FCF66C7} |  | High with Victim | High with Victims | High | 96 | CHA | 1 |  |  | 2009-05-20 | No | Planned
South | Nimroz | Chahar Burjak | Chahar Borjak | {308CC219-B853-4966-A868-95D16FCF66C7} | c0a8-0057-12c3b96f8f8-bf745538-2925c- | MF-HQ-10468 | DAFA - Demining Agency for Afghanistan | AF/2203/20010/MF0028 | 952 | 61.9897 | 30.3329 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-101 | Nimroz Demining Project-01 | VTF-Japan | Yes | 2014-12-02 | 2014-12-19 | 1393 | DAFA | {308CC219-B853-4966-A868-95D16FCF66C7} |  | High with Victim | High with Victims | High | 98 | CHA | 1 |  |  | 2009-05-20 | No | Planned
South | Nimroz | Chahar Burjak | Chahar Borjak | {308CC219-B853-4966-A868-95D16FCF66C7} | c0a8-008e-132c99a83c0-3ea6b248-37f5-8 | MF-16212 | DAFA - Demining Agency for Afghanistan | AF/2203/20010/MF0030 | 330 | 62.0517 | 30.2933 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-101 | Nimroz Demining Project-01 | VTF-Japan | Yes | 2014-12-20 | 2014-12-26 | 1393 | DAFA | {308CC219-B853-4966-A868-95D16FCF66C7} |  | High with Victim | High with Victims | High | 558 | CHA | 1 |  |  | 2011-04-17 16:30 | No | Planned
South | Nimroz | Chahar Burjak | Chigini | {7D586D62-B66F-4147-9DB4-ADC73B7D3AC5} | c0a8-0009-144169134c2-d23a3af5-508d-9 | Hz-ID-18398 | DAFA - Demining Agency for Afghanistan | AF/2203/19968/MF0047 | 66660 | 61.8566 | 30.464 | Open | AT Only | AT Only | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {7D586D62-B66F-4147-9DB4-ADC73B7D3AC5} |  | Low | Critical Infrastracture | High | 585 | CHA | 4 |  |  | 2013-12-11 16:30 | No | Open
South | Nimroz | Chahar Burjak | Chigini | {7D586D62-B66F-4147-9DB4-ADC73B7D3AC5} | c0a8-0009-144959f09af-f3653482-b95-81 | Hz-ID-18397 | DAFA - Demining Agency for Afghanistan | AF/2203/19968/MF0046 | 113111 | 61.8409 | 30.4284 | Open | AT Only | AT Only | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {7D586D62-B66F-4147-9DB4-ADC73B7D3AC5} |  | Low | Critical Infrastracture | High | 726 | CHA | 4 |  |  | 2013-12-10 16:30 | No | Open
South | Nimroz | Chahar Burjak | Chigini | {7D586D62-B66F-4147-9DB4-ADC73B7D3AC5} | c0a8-0009-14495a8cdaf-353319a9-be7-64 | Hz-ID-18400 | DAFA - Demining Agency for Afghanistan | AF/2203/19968/MF0049 | 59251 | 61.8471 | 30.3891 | Open | AT Only | AT Only | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {7D586D62-B66F-4147-9DB4-ADC73B7D3AC5} |  | Low | Critical Infrastracture | High | 773 | CHA | 4 |  |  | 2013-12-09 16:30 | No | Open
South | Nimroz | Chahar Burjak | Mashi | {8925927D-F168-460F-81F0-1677591F8E65} | c0a8-0009-1433d35cd80-a07baf59-3d35-f | Hz-ID-18299 | DAFA - Demining Agency for Afghanistan | AF/2203/20009/MF0033 | 473060 | 61.7383 | 30.7447 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {8925927D-F168-460F-81F0-1677591F8E65} |  | Medium | Critical Infrastracture | High | 11 | CHA | 5 |  |  | 2013-11-28 16:30 | No | Open
South | Nimroz | Chahar Burjak | Mashi | {8925927D-F168-460F-81F0-1677591F8E65} | c0a8-0009-1433d380fc9-79fbe91b-3d66-f | Hz-ID-18301 | DAFA - Demining Agency for Afghanistan | AF/2203/20009/MF0034 | 532200 | 61.7534 | 30.7347 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {8925927D-F168-460F-81F0-1677591F8E65} |  | Low | Agriculture Blocked | High | 10 | CHA | 5 |  |  | 2013-11-28 16:30 | No | Open
South | Nimroz | Chahar Burjak | Mula Hossian | {1F4CA4CA-090A-4A5C-B1AD-5C18F4F6DBF7} | c0a8-0057-12c3badd027-d0d2093a-37365- | MF-HQ-10477 | DAFA - Demining Agency for Afghanistan | AF/2203/00085/MF0018 | 152385 | 61.8178 | 30.776 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {1F4CA4CA-090A-4A5C-B1AD-5C18F4F6DBF7} |  | High Requested | Resettlment/Local Request | High | 15 | CHA | 4 |  |  | 2009-05-20 | No | Open
South | Nimroz | Chahar Burjak | Nasir Bala | {B58F8F4E-7096-4743-897D-9CB519BD5DD8} | c0a8-0009-1433d3cfbf3-975ef643-3d80-3 | Hz-ID-18303 | DAFA - Demining Agency for Afghanistan | AF/2203/19990/MF0035 | 377000 | 61.9828 | 30.2665 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-101 | Nimroz Demining Project-01 | VTF-Japan | Yes | 2014-06-15 | 2014-12-27 | 1393 | DAFA | {B58F8F4E-7096-4743-897D-9CB519BD5DD8} |  | Medium | Critical Infrastracture | High | 26 | CHA | 5 |  |  | 2013-11-25 16:30 | No | Planned
South | Nimroz | Chahar Burjak | Nasir Bala | {B58F8F4E-7096-4743-897D-9CB519BD5DD8} | c0a8-0057-12c3baf8cbd-dde9f7a8-383e7- | MF-HQ-10479 | DAFA - Demining Agency for Afghanistan | AF/2203/19990/MF0025 | 438981 | 61.9637 | 30.2708 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-101 | Nimroz Demining Project-01 | VTF-Japan | Yes | 2014-06-15 | 2014-12-27 | 1393 | DAFA | {B58F8F4E-7096-4743-897D-9CB519BD5DD8} |  | High Requested | Resettlment/Local Request | High | 13 | CHA | 5 |  |  | 2009-05-20 | No | Planned
South | Nimroz | Chahar Burjak | Qal'eh-ye Fath | {2A3BDD86-831D-4927-8FEA-A4B38095B23D} | c0a8-0009-1433d53d268-477f4aa0-3dc2-1 | Hz-ID-18298 | DAFA - Demining Agency for Afghanistan | AF/2203/19975/MF0040 | 176873 | 61.8492 | 30.5625 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {2A3BDD86-831D-4927-8FEA-A4B38095B23D} |  | High with Victim | High with Victims | High | 33 | CHA | 1 |  |  | 2013-11-05 16:30 | No | Open
South | Nimroz | Chahar Burjak | Qal'eh-ye Fath | {2A3BDD86-831D-4927-8FEA-A4B38095B23D} | c0a8-0057-12c3b871804-541943b6-1e766- | MF-HQ-10467 | DAFA - Demining Agency for Afghanistan | AF/2203/19975/MF0029 | 101720 | 61.8563 | 30.5519 | Open | AP Only | AP Only | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {2A3BDD86-831D-4927-8FEA-A4B38095B23D} |  | High with Victim | High with Victims | High | 11 | CHA | 1 |  |  | 2009-05-20 | No | Open
South | Nimroz | Chahar Burjak | Qr Haji Mohd Afzalkhan | {ED742AF0-8437-40D6-BDCC-86737209F74F} | c0a8-0009-1437184f3b3-51b1d722-14663- | Hz-ID-18332 | DAFA - Demining Agency for Afghanistan | AF/2203/19998/MF0045 | 2000000 | 60.9562 | 29.8889 | Open | Mixed | Mixed AP AT UXO | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {ED742AF0-8437-40D6-BDCC-86737209F74F} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2013-11-19 16:30 | No | Open
South | Nimroz | Chahar Burjak | Qr Haji Mohd Afzalkhan | {ED742AF0-8437-40D6-BDCC-86737209F74F} | c0a8-0009-143752e6f13-63db9189-42c-5b | Hz-ID-18329 | DAFA - Demining Agency for Afghanistan | AF/2203/19998/MF0042 | 176850 | 61.0663 | 30.0202 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {ED742AF0-8437-40D6-BDCC-86737209F74F} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2013-12-07 16:30 | No | Open
South | Nimroz | Chahar Burjak | Qr Haji Mohd Afzalkhan | {ED742AF0-8437-40D6-BDCC-86737209F74F} | c0a8-0009-143d2483441-faf85ef0-33b0-c | Hz-ID-18331 | DAFA - Demining Agency for Afghanistan | AF/2203/19998/MF0044 | 92070 | 60.9038 | 29.8706 | Open | Mixed | Mixed AP AT UXO | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {ED742AF0-8437-40D6-BDCC-86737209F74F} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2013-12-08 16:30 | No | Open
South | Nimroz | Chahar Burjak | Tofangcha | {D48F68B1-B802-4FA5-BA18-0127F17135DF} | c0a8-0009-1433da5a90f-ede18c4b-3de3-b | Hz-ID-18300 | DAFA - Demining Agency for Afghanistan | AF/2203/19966/MF0037 | 17220 | 61.8692 | 30.3114 | Open | AP Only | AP Only | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {D48F68B1-B802-4FA5-BA18-0127F17135DF} |  | Medium | Water Blocked | High | 1 | CHA | 5 |  |  | 2013-11-09 16:30 | No | Open
South | Nimroz | Chahar Burjak | Tofangcha | {D48F68B1-B802-4FA5-BA18-0127F17135DF} | c0a8-0009-1433da92171-5188518-3e1e-89 | Hz-ID-18302 | DAFA - Demining Agency for Afghanistan | AF/2203/19966/MF0038 | 5257 | 61.8692 | 30.3114 | Open | AP Only | AP Only | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {D48F68B1-B802-4FA5-BA18-0127F17135DF} |  | Medium | Agriculture Blocked | High | 1 | CHA | 5 |  |  | 2013-11-07 16:30 | No | Open
South | Nimroz | Chahar Burjak | Tofangcha | {D48F68B1-B802-4FA5-BA18-0127F17135DF} | c0a8-0009-144a646f438-efb0ae91-258-a8 | Hz-ID-18304 | DAFA - Demining Agency for Afghanistan | AF/2203/19966/MF0039 | 5937 | 61.8692 | 30.3114 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {D48F68B1-B802-4FA5-BA18-0127F17135DF} |  | Medium | Critical Infrastracture | High | 0 | CHA | 3 |  |  | 2013-11-10 16:30 | No | Open
South | Nimroz | Chahar Burjak | Yar Mohd Khan | {17C81113-DB6D-4EDB-B66B-4D9460BF0A98} | c0a8-0057-12c3b99adc5-3b4488fc-2af17- | MF-HQ-10457 | DAFA - Demining Agency for Afghanistan | AF/2203/00062/MF0021 | 2847 | 61.8896 | 30.3342 | Open | AP Only | AP Only | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {17C81113-DB6D-4EDB-B66B-4D9460BF0A98} |  | High Requested | Resettlment/Local Request | High | 257 | CHA | 5 |  |  | 2009-05-20 | No | Open
South | Nimroz | Chahar Burjak | Yar Mohd Khan | {17C81113-DB6D-4EDB-B66B-4D9460BF0A98} | c0a8-0057-12c3bb2bf78-59973e79-3a244- | MF-HQ-10456 | DAFA - Demining Agency for Afghanistan | AF/2203/00062/MF0022 | 23200 | 61.9225 | 30.3651 | Open | AP Only | AP Only | MineField |  | MBT Project-236 | Nimroz Demining Project-02 |  |  |  |  | 1394 |  | {17C81113-DB6D-4EDB-B66B-4D9460BF0A98} |  | High Requested | Resettlment/Local Request | High | 0 | CHA | 5 |  |  | 2009-05-20 | No | Open
South | Nimroz | Kang | Aydo | {7F38E04A-C656-42E1-9A24-82247864C580} | c0a8-0009-1424164b10f-a92a1312-397d-6 | Hz-ID-18217 | DAFA - Demining Agency for Afghanistan | AF/2202/19762/MF0053 | 762560 | 61.8324 | 31.1673 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-272 | Nimroz Demining Project-01 AT |  |  |  |  | 1395 |  | {7F38E04A-C656-42E1-9A24-82247864C580} |  | Low | Critical Infrastracture | Substantial | 158 | CHA | 4 |  |  | 2013-06-05 16:30 | No | Open
South | Nimroz | Kang | Aydo | {7F38E04A-C656-42E1-9A24-82247864C580} | c0a8-00f6-135521a07c6-2f35d328-269-a8 | MF-15949 | MCPA - Mine Clearance Planning Agency | AF/2202/19762/MF0048 | 32803 | 61.838 | 31.1801 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-272 | Nimroz Demining Project-01 AT |  |  |  |  | 1395 |  | {7F38E04A-C656-42E1-9A24-82247864C580} |  | Low | Water Blocked | Substantial | 19 | CHA | 5 |  |  | 2011-05-22 16:30 | No | Open
South | Nimroz | Kang | Haji Aqakhan | {F672B1C4-4E65-42A9-A25D-118ABF157BBB} | c0a8-0009-14240d8dca1-8de8923c-31da-b | Hz-ID-18216 | DAFA - Demining Agency for Afghanistan | AF/2202/19797/MF0052 | 280651 | 61.8247 | 31.1762 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-272 | Nimroz Demining Project-01 AT |  |  |  |  | 1395 |  | {F672B1C4-4E65-42A9-A25D-118ABF157BBB} |  | Medium | Critical Infrastracture | Substantial | 182 | CHA | 3 |  |  | 2013-06-05 16:30 | No | Open
South | Nimroz | Kang | Haji Habibullah | {524B0F5A-E3E7-43FE-B94B-4E97D4831690} | c0a8-0009-14240dbf79c-fd8b556b-322b-2 | Hz-ID-18219 | DAFA - Demining Agency for Afghanistan | AF/2202/19773/MF0056 | 2824 | 61.7999 | 31.1851 | Open | AT Only | AT Only | MineField |  | MBT Project-272 | Nimroz Demining Project-01 AT |  |  |  |  | 1395 |  | {524B0F5A-E3E7-43FE-B94B-4E97D4831690} |  | Medium | Critical Infrastracture | Substantial | 10 | CHA | 3 |  |  | 2013-06-03 16:30 | No | Open
South | Nimroz | Kang | Haji Habibullah | {524B0F5A-E3E7-43FE-B94B-4E97D4831690} | c0a8-0009-14241700441-f25f7f7e-3a22-a | Hz-ID-18215 | DAFA - Demining Agency for Afghanistan | AF/2202/19773/MF0051 | 55228 | 61.8283 | 31.1604 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-272 | Nimroz Demining Project-01 AT |  |  |  |  | 1395 |  | {524B0F5A-E3E7-43FE-B94B-4E97D4831690} |  | Low | Water Blocked | Substantial | 89 | CHA | 5 |  |  | 2013-06-02 16:30 | No | Open
South | Nimroz | Kang | Haji Habibullah | {524B0F5A-E3E7-43FE-B94B-4E97D4831690} | c0a8-0009-143cd1b7a19-3bf5607f-2716-7 | Hz-ID-18218 | DAFA - Demining Agency for Afghanistan | AF/2202/19773/MF0054 | 14966 | 61.8011 | 31.1885 | Open | AT Only | AT Only | MineField |  | MBT Project-272 | Nimroz Demining Project-01 AT |  |  |  |  | 1395 |  | {524B0F5A-E3E7-43FE-B94B-4E97D4831690} |  | Medium | Critical Infrastracture | Substantial | 15 | CHA | 3 |  |  | 2013-06-13 16:30 | No | Open
South | Nimroz | Kang | Haji Habibullah | {524B0F5A-E3E7-43FE-B94B-4E97D4831690} | c0a8-0009-143ce305f8c-a9d636f3-31fd-1 | Hz-ID-18413 | DAFA - Demining Agency for Afghanistan | AF/2202/19773/MF0055 | 14965 | 61.7974 | 31.189 | Open | AT Only | AT Only | MineField |  | MBT Project-272 | Nimroz Demining Project-01 AT |  |  |  |  | 1395 |  | {524B0F5A-E3E7-43FE-B94B-4E97D4831690} |  | Medium | Critical Infrastracture | Substantial | 0 | CHA | 3 |  |  | 2013-06-13 16:30 | No | Open
South | Nimroz | Kang | Mohammad Sadiq | {05DBF126-AFCD-4704-8328-BD9A2EA99E9F} | c0a8-0057-12c3baf1c9e-1d959f3-37fcf-3 | MF-HQ-15273 | DAFA - Demining Agency for Afghanistan | AF/2202/19771/MF0047 | 80000 | 61.8337 | 31.1816 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-272 | Nimroz Demining Project-01 AT |  |  |  |  | 1395 |  | {05DBF126-AFCD-4704-8328-BD9A2EA99E9F} |  | Medium | Water Blocked | Substantial | 9 | CHA | 3 |  |  | 2010-05-20 | No | Open
South | Nimroz | Khash Rod | Pir Gaz Agha | {E3C2740B-3EBF-4F23-ACFA-FAA3574C2A4F} | c0a8-0057-12c3bb1f7f7-9ca4ca03-39b32- | MF-HQ-10454 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2205/19905/MF036 | 332800 | 62.9876 | 31.8038 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-272 | Nimroz Demining Project-01 AT |  |  |  |  | 1395 |  | {E3C2740B-3EBF-4F23-ACFA-FAA3574C2A4F} |  | Low | Agriculture Blocked | Extreme | 0 | SHA | 5 |  |  | 2009-05-20 | No | Open
South | Nimroz | Khash Rod | Shash Abah | {1377294B-06CC-47B2-866B-B5A1FFFD9CED} | c0a8-0057-12c3b9b46d2-ad4291e1-2bfcd- | MF-SA-599 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2205/19944/MF -038 | 55617 | 62.6446 | 31.4836 | Open | AT Only | AT Only | MineField |  | MBT Project-272 | Nimroz Demining Project-01 AT |  |  |  |  | 1395 |  | {1377294B-06CC-47B2-866B-B5A1FFFD9CED} |  | Medium | Critical Infrastracture | Extreme | 295 | CHA | 3 |  |  | 2008-11-04 | No | Open
South | Nimroz | Khash Rod | Shash Abah | {1377294B-06CC-47B2-866B-B5A1FFFD9CED} | c0a8-0057-12c3b9c0424-9541cddc-2c732- | MF-HQ-10453 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2205/19905/MF035 | 490000 | 62.6445 | 31.4835 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-272 | Nimroz Demining Project-01 AT |  |  |  |  | 1395 |  | {1377294B-06CC-47B2-866B-B5A1FFFD9CED} |  | Medium | Critical Infrastracture | Extreme | 303 | SHA | 3 |  |  | 2009-05-20 | No | Open
South | Nimroz | Zaranj | Lakari | {B2B5A32F-9727-4282-9F9C-407741D2ED13} | c0a8-0057-12c3b86f586-dd7f06b2-1e5c1- | MF-HQ-10450 | DAFA - Demining Agency for Afghanistan | AF/2201/19595/MF0004 | 208691 | 61.8096 | 30.8331 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-101 | Nimroz Demining Project-01 | VTF-Japan | Yes | 2014-06-15 | 2014-12-26 | 1393 | DAFA | {B2B5A32F-9727-4282-9F9C-407741D2ED13} | Planned Year and Planned Agency Removed | High with Victim | High with Victims | High | 11 | CHA | 3 |  |  | 2009-05-20 | No | Planned
South | Uruzgan | Chora | Adin Kalay | {13188382-9C19-4DFA-ABE8-B64231B19BD4} | c0a8-008e-130cb8cdb72-e502922d-1079-3 | BF-HQ-12086 | MDC - Mine Detection and Dog Center | AF/2606/26197/BF0012 | 51500 | 66.0524 | 32.8718 | Open | UXO Only | UXO Only | BF |  | MBT Project-187 | Uruzgan Demining Project-01 ERW |  |  |  |  | 1398 |  | {13188382-9C19-4DFA-ABE8-B64231B19BD4} |  | Medium | Critical Infrastracture | Substantial | 137 | CHA | 3 |  |  | 2009-06-02 | No | Open
South | Uruzgan | Chora | Deenar Khel | {200DA259-26D0-4FD3-B893-146531D6F03A} | c0a8-008e-130cb901038-89ce8057-1128-2 | BF-HQ-12089 | MDC - Mine Detection and Dog Center | AF/2606/32021/BF0015 | 16850 | 66.0358 | 32.8687 | Open | UXO Only | UXO Only | BF |  | MBT Project-187 | Uruzgan Demining Project-01 ERW |  |  |  |  | 1398 |  | {200DA259-26D0-4FD3-B893-146531D6F03A} |  | Low | Agriculture Blocked | Substantial | 20 | CHA | 5 |  |  | 2009-06-04 | No | Open
South | Uruzgan | Chora | Gurjiza'i(Nawa) | {B0795A99-31F3-40E8-83EF-019311447ED1} | c0a8-008e-130cb8dc34f-aa4116ab-10a7-8 | BF-HQ-12088 | MDC - Mine Detection and Dog Center | AF/2606/26195/BF0014 | 8550 | 66.0503 | 32.8522 | Open | UXO Only | UXO Only | BF |  | MBT Project-187 | Uruzgan Demining Project-01 ERW |  |  |  |  | 1398 |  | {B0795A99-31F3-40E8-83EF-019311447ED1} |  | Medium | Critical Infrastracture | Substantial | 182 | CHA | 3 |  |  | 2009-06-03 | No | Open
South | Uruzgan | Chora | Sari | {DD3D2F7E-06BE-4C22-BC6C-ACB6898407C4} | c0a8-008e-130cb8bfe17-63ec4110-1063-6 | BF-HQ-12085 | MDC - Mine Detection and Dog Center | AF/2606/26279/BF0011 | 51200 | 66.0561 | 32.8694 | Open | UXO Only | UXO Only | BF |  | MBT Project-187 | Uruzgan Demining Project-01 ERW |  |  |  |  | 1398 |  | {DD3D2F7E-06BE-4C22-BC6C-ACB6898407C4} |  | High with Victim | High with Victims | Substantial | 65 | CHA | 2 |  |  | 2009-06-02 | No | Open
South | Zabul | Atghar | Kari Kalay | {98E6ED21-42F0-476E-8837-39680EC1763E} | c0a8-0057-12c3bb183e2-2acd0a07-396a9- | MF-HQ-10337 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2508/24138/MF0007 | 2500 | 67.3397 | 31.7587 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {98E6ED21-42F0-476E-8837-39680EC1763E} |  | Medium | Water Blocked | High | 0 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Mizan | De Mulla Bostan Kalay | {0C5639C7-CD61-43D0-B04A-584095C55A1E} | c0a8-0057-12c3b8a462d-3c55c55b-20aff- | MF-HQ-10325 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2505/23324/MF008 | 40000 | 66.5453 | 32.1992 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {0C5639C7-CD61-43D0-B04A-584095C55A1E} |  | Low | Agriculture Blocked | High | 85 | SHA | 4 |  |  | 2009-05-11 | No | Open
South | Zabul | Mizan | De Mulla Bostan Kalay | {0C5639C7-CD61-43D0-B04A-584095C55A1E} | c0a8-0057-12c3ba8ab17-e4a2943e-3430a- | MF-HQ-10327 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2505/23324/MF0009 | 30000 | 66.5453 | 32.1992 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {0C5639C7-CD61-43D0-B04A-584095C55A1E} |  | Low | Agriculture Blocked | High | 13 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Mizan | lkir | {883F8705-0150-407D-B627-CA9525F2A2EC} | c0a8-0057-12c3b985e56-85bf3f80-2a12a- | MF-HQ-10336 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2505/23289/MF010 | 96000 | 66.4762 | 32.1419 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-287 | Zabul Demining Project-04 |  |  |  |  | 1401 |  | {883F8705-0150-407D-B627-CA9525F2A2EC} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Qalat | Kakarkhan Kalacha | {A2520A8D-118F-4938-B613-DAD565FCBF87} | c0a8-0057-12c3b87e233-4090a58d-1f063- | MF-HQ-10344 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2501/23070/MF0176 | 210000 | 66.8416 | 32.1 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-287 | Zabul Demining Project-04 |  |  |  |  | 1401 |  | {A2520A8D-118F-4938-B613-DAD565FCBF87} |  | Low | Agriculture Blocked | High | 4 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Qalat | Kakarkhan Kalacha | {A2520A8D-118F-4938-B613-DAD565FCBF87} | c0a8-0057-12c3b884854-25a18d32-1f4be- | MF-HQ-10295 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2501/23095/MF0165 | 80000 | 66.8541 | 32.0707 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-287 | Zabul Demining Project-04 |  |  |  |  | 1401 |  | {A2520A8D-118F-4938-B613-DAD565FCBF87} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Qalat | Mirza Faydzullah | {C6A20215-0AE4-48BE-B07D-2E0098593ADC} | c0a8-0009-1471e8b80bb-eac919f7-96a-7d | Hz-ID-18846 | DAFA - Demining Agency for Afghanistan | AF/2501/23081/MF0180 | 55903 | 66.9132 | 32.0831 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {C6A20215-0AE4-48BE-B07D-2E0098593ADC} |  | High with Victim | High with Victims | High | 0 | CHA | 3 |  |  | 2014-06-03 16:30 | No | Open
South | Zabul | Qalat | Mirza Faydzullah | {C6A20215-0AE4-48BE-B07D-2E0098593ADC} | c0a8-0009-1471ec85e5a-544af537-ad3-76 | Hz-ID-18847 | DAFA - Demining Agency for Afghanistan | AF/2501/23081/MF0181 | 5931 | 66.9074 | 32.0839 | Open | AP Only | AP Only | MineField |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {C6A20215-0AE4-48BE-B07D-2E0098593ADC} |  | High with Victim | High with Victims | High | 0 | CHA | 5 |  |  | 2014-06-04 16:30 | No | Open
South | Zabul | Qalat | Mirza Faydzullah | {C6A20215-0AE4-48BE-B07D-2E0098593ADC} | c0a8-0057-12c3b8f1a60-7ac40378-24019- | MF-SA-595 | DAFA - Demining Agency for Afghanistan | AF/2501/23081/MF0162 | 61336 | 66.9182 | 32.0852 | Open | AP Only | AP Only | MineField |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {C6A20215-0AE4-48BE-B07D-2E0098593ADC} |  | High with Victim | High with Victims | High | 357 | CHA | 3 |  |  | 2008-11-04 | No | Open
South | Zabul | Qalat | Moladin | {05E5B620-3687-4BA6-AAE4-1D098F448311} | c0a8-0057-12c3b8c7024-5ff2ee05-22307- | MF-HQ-10306 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2501/23095/MF164 | 468750 | 66.9565 | 32.1204 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {05E5B620-3687-4BA6-AAE4-1D098F448311} |  | Low | Agriculture Blocked | High | 189 | SHA | 4 |  |  | 2009-05-11 | No | Open
South | Zabul | Qalat | Moladin | {05E5B620-3687-4BA6-AAE4-1D098F448311} | c0a8-0057-12c3ba094cf-913aadc-2f4bd-1 | MF-HQ-10308 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2501/23095/MF0163 | 800 | 66.9544 | 32.126 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {05E5B620-3687-4BA6-AAE4-1D098F448311} |  | High | Critical Infrastracture | High | 11 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Qalat | Qalat | {ECF755B6-F31F-44F7-8169-95A106AF3419} | c0a8-0009-13dc9af2339-fd7ba17a-22de-d | Hz-ID-17695 | DAFA - Demining Agency for Afghanistan | AF/2501/23154/BF0177 | 1361022 | 66.9277 | 32.098 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-269 | Zabul Demining Project-01 |  | Yes | 2013-09-22 | 2014-01-21 | 1392 | DAFA | {ECF755B6-F31F-44F7-8169-95A106AF3419} |  |  |  | High | 30 | CHA | 2 |  |  | 2013-02-19 16:30 | No | Complete
South | Zabul | Qalat | Qalat | {ECF755B6-F31F-44F7-8169-95A106AF3419} | c0a8-0009-14405aef501-4a5055c5-355-c1 | Hz-ID-18430 | DAFA - Demining Agency for Afghanistan | AF/2501/23154/BF0178 | 1028568 | 66.9273 | 32.0988 | Open | UXO Only | UXO Only | BF |  | MBT Project-269/A | Zabul Demining Project-01/A |  |  |  |  | 1393 |  | {ECF755B6-F31F-44F7-8169-95A106AF3419} |  | High with Victim | High with Victims | High | 456 | CHA | 2 |  |  | 2014-01-23 16:30 | No | Open
South | Zabul | Qalat | Qalat | {ECF755B6-F31F-44F7-8169-95A106AF3419} | c0a8-0009-14405b0ca72-fb88e04f-398-f9 | Hz-ID-18432 | DAFA - Demining Agency for Afghanistan | AF/2501/23154/BF0179 | 258807 | 66.9278 | 32.098 | Open | UXO Only | UXO Only | BF |  | MBT Project-269/A | Zabul Demining Project-01/A |  |  |  |  | 1393 |  | {ECF755B6-F31F-44F7-8169-95A106AF3419} |  | High with Victim | High with Victims | High | 37 | CHA | 2 |  |  | 2014-01-23 16:30 | No | Open
South | Zabul | Qalat | Qalat | {ECF755B6-F31F-44F7-8169-95A106AF3419} | c0a8-0057-12c3b8f18ab-a65124f8-24007- | MF-SA-253 | MCPA - Mine Clearance Planning Agency | AF/2501/23154/MF 158 | 6236 | 66.9014 | 32.1051 | Open | AT Only | AT Only | MineField |  | MBT Project-269/A | Zabul Demining Project-01/A |  |  |  |  | 1393 |  | {ECF755B6-F31F-44F7-8169-95A106AF3419} |  | High with Victim | High with Victims | High | 320 | CHA | 2 |  |  | 2004-04-30 | No | Open
South | Zabul | Shamulzayi | Darwazagey | {BA8EF8FA-3A33-49AF-A9CE-A95CCFD8FEAA} | c0a8-0057-12c3b7c5933-52086891-16ddd- | MF-HQ-10321 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2509/24276/MF0002 | 200000 | 67.7396 | 31.8076 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-218 | Zabul Demining Project-03 |  |  |  |  | 1399 |  | {BA8EF8FA-3A33-49AF-A9CE-A95CCFD8FEAA} |  | Medium | Agriculture Blocked | High | 56 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Shamulzayi | Darwazagey | {BA8EF8FA-3A33-49AF-A9CE-A95CCFD8FEAA} | c0a8-0057-12c3ba42f8e-6f02c21f-317ac- | MF-HQ-10323 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2509/24276/MF0003 | 82500 | 67.7421 | 31.8036 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-218 | Zabul Demining Project-03 |  |  |  |  | 1399 |  | {BA8EF8FA-3A33-49AF-A9CE-A95CCFD8FEAA} |  | High | Water Blocked | High | 11 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Shamulzayi | Darwazagey | {BA8EF8FA-3A33-49AF-A9CE-A95CCFD8FEAA} | c0a8-0057-12c3bac3238-6c943935-363c1- | MF-HQ-10319 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2509/24276/MF0004 | 100000 | 67.7365 | 31.8088 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-218 | Zabul Demining Project-03 |  |  |  |  | 1399 |  | {BA8EF8FA-3A33-49AF-A9CE-A95CCFD8FEAA} |  | Low | Agriculture Blocked | High | 51 | SHA | 4 |  |  | 2009-05-11 | No | Open
South | Zabul | Shamulzayi | Haji Abdul Wahab kalay | {3642D639-9A15-4F3A-ACAF-67F8072E21C7} | c0a8-0057-12c3b98b1ef-31c79b7-2a4a8-d | MF-HQ-10318 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2509/00157/MF005 | 50000 | 67.7284 | 31.8321 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-218 | Zabul Demining Project-03 |  |  |  |  | 1399 |  | {3642D639-9A15-4F3A-ACAF-67F8072E21C7} |  | Low | Critical Infrastracture | High | 0 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Shamulzayi | Haji Abdul Wahab kalay | {3642D639-9A15-4F3A-ACAF-67F8072E21C7} | c0a8-0057-12c3baa3dd1-4dc07980-3518a- | MF-HQ-10320 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2509/00157/MF007 | 60000 | 67.7284 | 31.8321 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-218 | Zabul Demining Project-03 |  |  |  |  | 1399 |  | {3642D639-9A15-4F3A-ACAF-67F8072E21C7} |  | Low | Critical Infrastracture | High | 0 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Shamulzayi | Khan Kala | {28598D73-4A96-45CA-B01A-2293DD24BF0E} | c0a8-0057-12c3bb08a4b-1c259de4-38d55- | MF-HQ-10317 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2509/24265/MF001 | 2500 | 67.7246 | 31.7459 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {28598D73-4A96-45CA-B01A-2293DD24BF0E} |  | High | Water Blocked | High | 0 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Shinkay | Dab | {2713FBE6-1ABE-4955-B90D-116FAB4D7832} | c0a8-0057-12c3b7f8624-9892c598-1919a- | MF-HQ-10294 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2507/24072/MF003 | 3000 | 67.2066 | 32.0618 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-287 | Zabul Demining Project-04 |  |  |  |  | 1401 |  | {2713FBE6-1ABE-4955-B90D-116FAB4D7832} |  | Low | Agriculture Blocked | High | 2 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Shinkay | Dab | {2713FBE6-1ABE-4955-B90D-116FAB4D7832} | c0a8-0057-12c3baeb67d-5b4e11b4-37c0c- | MF-HQ-10297 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2507/24072/MF004 | 240000 | 67.2455 | 32.0705 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-287 | Zabul Demining Project-04 |  |  |  |  | 1401 |  | {2713FBE6-1ABE-4955-B90D-116FAB4D7832} |  | Low | Critical Infrastracture | High | 4 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Shinkay | Dab | {2713FBE6-1ABE-4955-B90D-116FAB4D7832} | c0a8-0057-12c3bb7d471-f51c48f8-3d139- | MF-HQ-10293 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2507/24072/MF002 | 9375 | 67.2055 | 32.0614 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-287 | Zabul Demining Project-04 |  |  |  |  | 1401 |  | {2713FBE6-1ABE-4955-B90D-116FAB4D7832} |  | Low | Agriculture Blocked | High | 2 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Dangar Khel | {8669DBFB-18CB-4CC1-AD28-1AD1C28E152C} | c0a8-0057-12c3b9f3259-86d4473e-2e710- | MF-HQ-10292 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23253/MF037 | 750000 | 66.6842 | 32.055 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-269/A | Zabul Demining Project-01/A |  |  |  |  | 1393 |  | {8669DBFB-18CB-4CC1-AD28-1AD1C28E152C} |  | High with Victim | High with Victims | High | 8 | SHA | 1 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Dangar Khel | {8669DBFB-18CB-4CC1-AD28-1AD1C28E152C} | c0a8-0057-12c3ba20384-272cb7e-302c8-d | MF-HQ-10291 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23253/MF036 | 512500 | 66.6732 | 32.058 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-269/A | Zabul Demining Project-01/A |  |  |  |  | 1393 |  | {8669DBFB-18CB-4CC1-AD28-1AD1C28E152C} |  | High with Victim | High with Victims | High | 4 | SHA | 1 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Da'udshah Kalay | {051044C7-3B2B-4972-A4B0-30D6B91FA3C5} | c0a8-0057-12c3bafd35d-30405165-386b9- | MF-HQ-10313 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/161/MF 0038 | 150000 | 66.7523 | 31.9945 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {051044C7-3B2B-4972-A4B0-30D6B91FA3C5} |  | Low | Critical Infrastracture | High | 25 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Dolagay | {68854FAE-5A25-4366-AE25-074CF73C956D} | c0a8-0057-12c3b8b092b-1a9fe908-21345- | MF-HQ-10310 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23189/MF032 | 60000 | 66.4092 | 31.8551 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-288 | Zabul Demining Project-05 |  |  |  |  | 1401 |  | {68854FAE-5A25-4366-AE25-074CF73C956D} |  | Medium | Agriculture Blocked | High | 98 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Foladgay | {13FF6746-4C2B-424B-8BC2-B741B45B5806} | c0a8-0057-12c3b8b92c3-420ac6a6-21931- | MF-HQ-10290 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23210/MF026 | 22500 | 66.5225 | 31.8938 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {13FF6746-4C2B-424B-8BC2-B741B45B5806} |  | Low | Agriculture Blocked | High | 304 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Foladgay | {13FF6746-4C2B-424B-8BC2-B741B45B5806} | c0a8-0057-12c3b97dccb-2b67c238-29bab- | MF-HQ-10289 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23210/MF028 | 10000 | 66.5193 | 31.8946 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {13FF6746-4C2B-424B-8BC2-B741B45B5806} |  | Low | Agriculture Blocked | High | 304 | SHA | 4 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Foladgay | {13FF6746-4C2B-424B-8BC2-B741B45B5806} | c0a8-0057-12c3bb2c5ce-f2799104-3a285- | MF-HQ-10288 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23210/MF027 | 490000 | 66.5265 | 31.8912 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {13FF6746-4C2B-424B-8BC2-B741B45B5806} |  | Low | Agriculture Blocked | High | 40 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Gedargu | {24ED61C6-665E-4CD5-8226-72E8F1E4E5A9} | c0a8-0057-12c3b86ed0e-3bfe1b3e-1e561- | MF-HQ-10334 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23228/MF044 | 180000 | 66.6445 | 31.9385 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {24ED61C6-665E-4CD5-8226-72E8F1E4E5A9} |  | Medium | Critical Infrastracture | High | 21 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Ghashay | {0D71AA23-AC54-4F32-870C-56297B1D5037} | c0a8-0057-12c3b86912a-a1baf360-1e192- | MF-HQ-10322 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/00034/MF016 | 180000 | 66.5739 | 31.9091 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-288 | Zabul Demining Project-05 |  |  |  |  | 1401 |  | {0D71AA23-AC54-4F32-870C-56297B1D5037} |  | Low | Critical Infrastracture | High | 49 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Ghashay | {0D71AA23-AC54-4F32-870C-56297B1D5037} | c0a8-0057-12c3b878fc1-7be24e3e-1eca1- | MF-HQ-10330 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/00034/MF015 | 20000 | 66.6095 | 31.9266 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {0D71AA23-AC54-4F32-870C-56297B1D5037} |  | Medium | Critical Infrastracture | High | 53 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Ghashay | {0D71AA23-AC54-4F32-870C-56297B1D5037} | c0a8-0057-12c3b8c96f5-cb5ba445-224b5- | MF-HQ-10328 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/00034/MF013 | 80000 | 66.6084 | 31.9287 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-288 | Zabul Demining Project-05 |  |  |  |  | 1401 |  | {0D71AA23-AC54-4F32-870C-56297B1D5037} |  | Low | Agriculture Blocked | High | 91 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Ghashay | {0D71AA23-AC54-4F32-870C-56297B1D5037} | c0a8-0057-12c3b9c0222-e1f8a2b-2c720-f | MF-HQ-10324 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/00034/MF014 | 240000 | 66.5867 | 31.9169 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {0D71AA23-AC54-4F32-870C-56297B1D5037} |  | Medium | Critical Infrastracture | High | 28 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Ghashay | {0D71AA23-AC54-4F32-870C-56297B1D5037} | c0a8-0057-12c3ba17d08-d0ce835d-2fd8d- | MF-HQ-10326 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/00034/MF017 | 120000 | 66.627 | 31.936 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {0D71AA23-AC54-4F32-870C-56297B1D5037} |  | Medium | Critical Infrastracture | High | 11 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Ghashay | {0D71AA23-AC54-4F32-870C-56297B1D5037} | c0a8-0057-12c3ba1e00e-527e72a4-30180- | MF-HQ-10332 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/00034/MF018 | 2500 | 66.6014 | 31.938 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {0D71AA23-AC54-4F32-870C-56297B1D5037} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Ghulam Dastagir | {3ACAF72E-16C2-40D1-AF6C-94C38ACACB7F} | c0a8-0057-12c3b86b59a-5e9200dc-1e2fd- | MF-HQ-10331 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/172/MF0029 | 160000 | 66.5524 | 31.9006 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {3ACAF72E-16C2-40D1-AF6C-94C38ACACB7F} |  | Medium | Critical Infrastracture | High | 32 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Ghulam Dastagir | {3ACAF72E-16C2-40D1-AF6C-94C38ACACB7F} | c0a8-0057-12c3b98697c-f0645a1f-2a193- | MF-HQ-10329 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/172/MF0030 | 200000 | 66.5399 | 31.9017 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {3ACAF72E-16C2-40D1-AF6C-94C38ACACB7F} |  | High | Water Blocked | High | 129 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Hamidullah | {5930C73F-112A-4A9D-AEA8-113D41301DF8} | c0a8-0057-12c3b98581f-f93ac85e-2a0ed- | MF-HQ-10302 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2500/00266/MF031 | 60000 | 66.7857 | 32.0161 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-288 | Zabul Demining Project-05 |  |  |  |  | 1401 |  | {5930C73F-112A-4A9D-AEA8-113D41301DF8} |  | Low | Water Blocked | High | 12 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Jalalkhan | {EB6C5663-1FAF-43AF-BF88-BB74D4680A0F} | c0a8-0057-12c3bafa201-62940efe-384b5- | MF-HQ-10311 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23174/MF0039 | 200000 | 66.3422 | 31.9352 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {EB6C5663-1FAF-43AF-BF88-BB74D4680A0F} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Jalalkhan | {EB6C5663-1FAF-43AF-BF88-BB74D4680A0F} | c0a8-0057-12c3bb300cb-6640a41c-3a4e4- | MF-HQ-10309 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23174/MF 0040 | 240000 | 66.3347 | 31.9246 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {EB6C5663-1FAF-43AF-BF88-BB74D4680A0F} |  | Low | Critical Infrastracture | High | 0 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Laghar | {9636A184-8671-4335-A23E-EA70F3C61F74} | c0a8-0057-12c3b8172fd-4b235552-1a761- | MF-HQ-10338 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23173/MF 0020 | 20000 | 66.3809 | 31.922 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {9636A184-8671-4335-A23E-EA70F3C61F74} |  | Low | Water Blocked | High | 0 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | M.Zai | {A1C34BAC-E4F5-44CE-9870-5AB1C3D288E0} | c0a8-0057-12c3b7d4110-d9d22084-1787d- | MF-HQ-10316 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/00492/MF045 | 40000 | 66.5183 | 31.8869 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {A1C34BAC-E4F5-44CE-9870-5AB1C3D288E0} |  | Medium | Critical Infrastracture | High | 75 | SHA | 3 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Puti Kalay | {B52889B5-1EFA-49BC-8B9D-D35C1B8E5786} | c0a8-0057-12c3bac10f2-1c724c02-36260- | MF-HQ-10335 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/172/MF0019 | 300000 | 66.2236 | 31.7872 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {B52889B5-1EFA-49BC-8B9D-D35C1B8E5786} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Qalandar Kalay | {2BB965D8-B258-420D-AFFF-9E37CDFDA722} | c0a8-0057-12c3b9ab179-743846b8-2b9e3- | MF-HQ-10300 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/121/MF0021 | 80000 | 66.424 | 31.8434 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-312 | Zabul Demining Project-03 AT |  |  |  |  | 1395 |  | {2BB965D8-B258-420D-AFFF-9E37CDFDA722} |  | Low | Critical Infrastracture | High | 41 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Saidano Kalay | {5F24A301-F3CB-4CCB-B7AD-B7EE6281C712} | c0a8-0057-12c3ba98a3d-2acdfdf5-34b43- | MF-HQ-10299 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/00283/MF024 | 15000 | 66.2896 | 31.799 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-217 | Zabul Demining Project-02 |  |  |  |  | 1395 |  | {5F24A301-F3CB-4CCB-B7AD-B7EE6281C712} |  | Low | Agriculture Blocked | High | 129 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Saidano Kalay | {5F24A301-F3CB-4CCB-B7AD-B7EE6281C712} | c0a8-0057-12c3bb4ef87-949a700a-3b72f- | MF-HQ-10301 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/00283/MF025 | 40000 | 66.285 | 31.7886 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-288 | Zabul Demining Project-05 |  |  |  |  | 1401 |  | {5F24A301-F3CB-4CCB-B7AD-B7EE6281C712} |  | Low | Agriculture Blocked | High | 12 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Salam Jan Agha | {69DA9EEA-BE2E-4DF2-BEA9-570F96638C6F} | c0a8-0057-12c3ba7d4d8-65591ae0-33b50- | MF-HQ-10315 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/00322/MF043 | 160000 | 66.6347 | 31.9414 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-288 | Zabul Demining Project-05 |  |  |  |  | 1401 |  | {69DA9EEA-BE2E-4DF2-BEA9-570F96638C6F} |  | Low | Agriculture Blocked | High | 21 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Senjed | {BBD1029B-24F7-4B6C-98C8-EFA434EC65E0} | c0a8-0057-12c3b7c6728-4f7314-16e7e-38 | MF-HQ-10307 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23216/MF0033 | 1000000 | 66.4995 | 32.0045 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-311 | Zabul Demining Project-02 AT |  |  |  |  | 1396 |  | {BBD1029B-24F7-4B6C-98C8-EFA434EC65E0} |  | Low | Agriculture Blocked | High | 6 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Senjed | {BBD1029B-24F7-4B6C-98C8-EFA434EC65E0} | c0a8-0057-12c3b8409e8-20ed25b2-1c4ed- | MF-HQ-10305 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23216/MF0034 | 320000 | 66.4535 | 31.9622 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-311 | Zabul Demining Project-02 AT |  |  |  |  | 1396 |  | {BBD1029B-24F7-4B6C-98C8-EFA434EC65E0} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Senjed | {BBD1029B-24F7-4B6C-98C8-EFA434EC65E0} | c0a8-0057-12c3b867715-47f4c6af-1e076- | MF-HQ-10303 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23216/MF035 | 1750000 | 66.4445 | 31.9706 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-310 | Zabul Demining Project-06 |  |  |  |  | 1396 |  | {BBD1029B-24F7-4B6C-98C8-EFA434EC65E0} |  | Low | Agriculture Blocked | High | 3 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Tora | {EF14BC73-D520-4E3A-A2A9-4595CE1306F2} | c0a8-0057-12c3ba02971-c559d4b3-2f0a4- | MF-HQ-10298 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23169/MF0023 | 37500 | 66.4195 | 31.7782 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-288 | Zabul Demining Project-05 |  |  |  |  | 1401 |  | {EF14BC73-D520-4E3A-A2A9-4595CE1306F2} |  | Low | Agriculture Blocked | High | 15 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Tora | {EF14BC73-D520-4E3A-A2A9-4595CE1306F2} | c0a8-0057-12c3bb59ded-b6efd95d-3bd44- | MF-HQ-10296 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23169/MF022 | 80000 | 66.4145 | 31.7866 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-288 | Zabul Demining Project-05 |  |  |  |  | 1401 |  | {EF14BC73-D520-4E3A-A2A9-4595CE1306F2} |  | Low | Agriculture Blocked | High | 21 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Zyarat | {FF58497C-7ABF-4321-BF99-6A495624323B} | c0a8-0057-12c3b93c4f8-aa6fcc07-270b9- | MF-HQ-10314 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23195/MF041 | 1000000 | 66.3951 | 31.9634 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-288 | Zabul Demining Project-05 |  |  |  |  | 1401 |  | {FF58497C-7ABF-4321-BF99-6A495624323B} |  | Low | Agriculture Blocked | High | 5 | SHA | 5 |  |  | 2009-05-11 | No | Open
South | Zabul | Tarnak Wa Jaldak | Zyarat | {FF58497C-7ABF-4321-BF99-6A495624323B} | c0a8-0057-12c3ba31405-2ccec038-30cee- | MF-HQ-10312 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2506/23195/MF042 | 40000 | 66.4363 | 31.9435 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-288 | Zabul Demining Project-05 |  |  |  |  | 1401 |  | {FF58497C-7ABF-4321-BF99-6A495624323B} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-05-11 | No | Open
South East | Ghazni | Ab Band | Abreshminkhel | {65766A14-9FD2-463E-AE93-7288D874D453} | c0a8-008e-13213d8273f-b482a2d5-fb2-27 | MF-HQ-24 | MCPA - Mine Clearance Planning Agency | AF/0612/06206/MF0005 | 15840 | 68.1285 | 32.8776 | Open | AT Only | AT Only | MineField |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {65766A14-9FD2-463E-AE93-7288D874D453} |  | Low | Comunity Centers | Substantial | 179 | CHA | 5 |  |  | 1990-10-14 | No | Open
South East | Ghazni | Ab Band | Almarkhel | {E7DC2FE3-F084-408D-A2D5-36B197E968CF} | c0a8-0057-12c3b91ef1d-d677bfe1-25d9a- | MF-HQ-12786 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0611/06199/MF0009 | 700000 | 67.9536 | 32.8516 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-208 | Ghazni Demining Project-04 AT |  |  |  |  | 1397 |  | {E7DC2FE3-F084-408D-A2D5-36B197E968CF} |  | High with Victim | High with Victims | Substantial | 18 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Ab Band | Almarkhel | {E7DC2FE3-F084-408D-A2D5-36B197E968CF} | c0a8-0057-12c3ba813da-63593baa-33da8- | MF-HQ-12798 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0611/06199/MF0006 | 235000 | 68.088 | 32.8478 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-208 | Ghazni Demining Project-04 AT |  |  |  |  | 1397 |  | {E7DC2FE3-F084-408D-A2D5-36B197E968CF} |  | High with Victim | High with Victims | Substantial | 142 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Ab Band | Asghari Kalay | {21DD51E9-FA7F-437A-9006-B1E468F65A43} | c0a8-0057-12c3bb1af16-5c95a3bc-3984c- | MF-HQ-12790 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0611/06184/MF010 | 750000 | 67.9721 | 32.8621 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {21DD51E9-FA7F-437A-9006-B1E468F65A43} |  | Low | Agriculture Blocked | Substantial | 31 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Ab Band | Chowni | {5505289B-806F-4D1B-B33D-9A47720CA657} | c0a8-0057-12c3bb6d05f-a753d58f-3c80b- | MF-HQ-12781 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0611/00255/MF008 | 120000 | 68.1128 | 32.8243 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-209 | Ghazni Demining Project-04 |  |  |  |  | 1398 |  | {5505289B-806F-4D1B-B33D-9A47720CA657} |  | Medium | Critical Infrastracture | Substantial | 0 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Ab Band | Dokohay | {964FD9E2-AE8D-48D8-B60E-AAD9C8A73BFE} | c0a8-0057-12c3ba914f0-2fea005b-346fb- | MF-SE-314 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0611/06205/MF(R005) | 116015 | 68.0958 | 32.8527 | Open | AT Only | AT Only | MineField |  | MBT Project-214 | Ghazni Demining Project-07 |  |  |  |  | 1398 |  | {964FD9E2-AE8D-48D8-B60E-AAD9C8A73BFE} |  | Low | Agriculture Blocked | Substantial | 233 | CHA | 4 |  |  | 2008-10-27 16:30 | No | Open
South East | Ghazni | Ab Band | Dokohay | {964FD9E2-AE8D-48D8-B60E-AAD9C8A73BFE} | c0a8-008e-13213fac7ae-7dcbe7e5-123c-a | MF-HQ-22 | MCPA - Mine Clearance Planning Agency | AF/0612/06205/MF0004 | 5645 | 68.0602 | 32.8915 | Open | AT Only | AT Only | MineField |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {964FD9E2-AE8D-48D8-B60E-AAD9C8A73BFE} |  | Low | Critical Infrastracture | Substantial | 0 | CHA | 5 |  |  | 1990-10-13 | No | Open
South East | Ghazni | Ab Band | Gandaw(Gandab) | {3873AE93-E502-4638-A902-F8FA164D7B7D} | c0a8-0057-12c3b8022ee-d20194ec-19884- | MF-SE-315 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0611/06189/MF(R003) | 94352 | 68.0963 | 32.8902 | Open | AT Only | AT Only | MineField |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {3873AE93-E502-4638-A902-F8FA164D7B7D} |  | Low | Agriculture Blocked | Substantial | 143 | CHA | 5 |  |  | 2008-10-27 16:30 | No | Open
South East | Ghazni | Ab Band | Gandaw(Gandab) | {3873AE93-E502-4638-A902-F8FA164D7B7D} | c0a8-0057-12f0533c1b9-c1357a1f-12c5-4 | MF-HQ-218 | MCPA - Mine Clearance Planning Agency | AF/0612/06189/MF0003 | 5648 | 68.0534 | 32.9017 | Open | AP Only | AP Only | MineField |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {3873AE93-E502-4638-A902-F8FA164D7B7D} |  | Low | Flat and AP | Substantial | 0 | CHA | 5 |  |  | 2003-02-09 | No | Open
South East | Ghazni | Ab Band | Salahkhel | {48E953E5-0F2E-4AD6-9909-93FD03DFB4BB} | c0a8-0057-12c3b9348be-ffcd0612-26b64- | MF-HQ-12782 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0611/06200/MF007 | 102000 | 68.0679 | 32.843 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-209 | Ghazni Demining Project-04 |  |  |  |  | 1398 |  | {48E953E5-0F2E-4AD6-9909-93FD03DFB4BB} |  | Medium | Critical Infrastracture | Substantial | 123 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Ab Band | Tawda China | {84D94A2B-FAE6-43B3-9955-41647FEAAF38} | c0a8-0057-12c3b97d665-29f2a7ec-29b88- | MF-HQ-12785 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0611/00406/MF0011 | 40000 | 67.9357 | 33.02 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {84D94A2B-FAE6-43B3-9955-41647FEAAF38} |  | Low | Critical Infrastracture | Substantial | 2 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Ab Band | Tawda China | {84D94A2B-FAE6-43B3-9955-41647FEAAF38} | c0a8-0057-12c3ba6c560-4d1805ef-3310b- | MF-SE-322 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0611/00406/MF(R001) | 69064 | 67.9286 | 33.0188 | Open | AP Only | AP Only | MineField |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {84D94A2B-FAE6-43B3-9955-41647FEAAF38} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-10-27 16:30 | No | Open
South East | Ghazni | Ab Band | Tawda China | {84D94A2B-FAE6-43B3-9955-41647FEAAF38} | c0a8-008e-1329f159ef0-fbdea4a6-ffb-79 | MF-HQ-16 | MCPA - Mine Clearance Planning Agency | AF/0612/00406/MF0001 | 12936 | 67.9347 | 33.0198 | Open | AP Only | AP Only | MineField |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {84D94A2B-FAE6-43B3-9955-41647FEAAF38} |  | Low | Critical Infrastracture | Substantial | 2 | CHA | 5 |  |  | 2003-02-09 | No | Open
South East | Ghazni | Andar | Bar Khadokhel | {0DA290B9-85DB-405C-82C6-5646CE239DC0} | c0a8-0057-12c3b7c111d-8247e0b3-16a8e- | MF-HQ-12689 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06355/MF0024 | 97750 | 68.3709 | 33.3408 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {0DA290B9-85DB-405C-82C6-5646CE239DC0} |  | Medium | Critical Infrastracture | High | 187 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Bar Khadokhel | {0DA290B9-85DB-405C-82C6-5646CE239DC0} | c0a8-0057-12c3b911c70-58bb7e57-25510- | MF-HQ-12687 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06355/MF0026 | 80000 | 68.3709 | 33.3408 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {0DA290B9-85DB-405C-82C6-5646CE239DC0} |  | Medium | Critical Infrastracture | High | 187 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Bar Khadokhel | {0DA290B9-85DB-405C-82C6-5646CE239DC0} | c0a8-0057-12c3b9a4e36-80ea8833-2b5c0- | MF-HQ-12677 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06355/MF0027 | 2500 | 68.3687 | 33.3427 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {0DA290B9-85DB-405C-82C6-5646CE239DC0} |  | Medium | Critical Infrastracture | High | 149 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Bar Khadokhel | {0DA290B9-85DB-405C-82C6-5646CE239DC0} | c0a8-0057-12c3baee25d-d451b00d-37dc4- | MF-HQ-12681 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06355/MF0025 | 2812 | 68.3687 | 33.3427 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {0DA290B9-85DB-405C-82C6-5646CE239DC0} |  | Medium | Critical Infrastracture | High | 149 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Bashi | {EFCEDCBC-9BF9-4512-84C8-BB89EB1CA915} | c0a8-0057-12c3b8f97c7-9cd252a7-24565- | MF-HQ-12702 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06409/MF0031 | 250800 | 68.4428 | 33.386 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {EFCEDCBC-9BF9-4512-84C8-BB89EB1CA915} |  | Medium | Critical Infrastracture | High | 648 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Bashi | {EFCEDCBC-9BF9-4512-84C8-BB89EB1CA915} | c0a8-0057-12c3b901167-185c6306-24a86- | MF-HQ-12701 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06409/MF0030 | 142987 | 68.4428 | 33.386 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {EFCEDCBC-9BF9-4512-84C8-BB89EB1CA915} |  | Medium | Critical Infrastracture | High | 665 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Bashi | {EFCEDCBC-9BF9-4512-84C8-BB89EB1CA915} | c0a8-0057-12c3b9472f8-8ec9f3ca-277ff- | MF-HQ-12705 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06409/MF0032 | 65550 | 68.4351 | 33.381 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {EFCEDCBC-9BF9-4512-84C8-BB89EB1CA915} |  | Low | Agriculture Blocked | High | 45 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Bashi | {EFCEDCBC-9BF9-4512-84C8-BB89EB1CA915} | c0a8-0057-12c3b97792b-48d2802b-297b4- | MF-HQ-12711 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06409/MF0029 | 225000 | 68.4441 | 33.3764 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {EFCEDCBC-9BF9-4512-84C8-BB89EB1CA915} |  | Medium | Critical Infrastracture | High | 422 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Bashi | {EFCEDCBC-9BF9-4512-84C8-BB89EB1CA915} | c0a8-0057-12c3ba84e78-7146e58b-33fe1- | MF-HQ-12707 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06409/MF0028 | 120000 | 68.4351 | 33.381 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {EFCEDCBC-9BF9-4512-84C8-BB89EB1CA915} |  | Low | Agriculture Blocked | High | 410 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Bata | {DE1B9D1A-4F3C-4DFC-A3F1-2F77A7CD848E} | c0a8-0057-12c3b82c32c-cafc4ab7-1b64e- | MF-HQ-12581 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06392/MF0033 | 108800 | 68.4456 | 33.357 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {DE1B9D1A-4F3C-4DFC-A3F1-2F77A7CD848E} |  | Low | Agriculture Blocked | High | 577 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Bata | {DE1B9D1A-4F3C-4DFC-A3F1-2F77A7CD848E} | c0a8-0057-12c3b9c003e-b62f1119-2c70d- | MF-HQ-12578 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06392/MF0034 | 106950 | 68.4373 | 33.3571 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {DE1B9D1A-4F3C-4DFC-A3F1-2F77A7CD848E} |  | Medium | Critical Infrastracture | High | 267 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Chambare Mawladad | {2BE9C3C6-4110-44D5-A199-B989D1747A76} | c0a8-0057-12c3b83463e-510e705-1bbfb-2 | MF-HQ-12693 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06358/MF0037 | 400 | 68.3812 | 33.361 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {2BE9C3C6-4110-44D5-A199-B989D1747A76} |  | Medium | Agriculture Blocked | High | 224 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Chambare Mawladad | {2BE9C3C6-4110-44D5-A199-B989D1747A76} | c0a8-0057-12c3b9787cb-78fb7323-29852- | MF-HQ-12695 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06358/MF0035 | 2500 | 68.3812 | 33.361 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {2BE9C3C6-4110-44D5-A199-B989D1747A76} |  | Medium | Agriculture Blocked | High | 224 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Chambare Mawladad | {2BE9C3C6-4110-44D5-A199-B989D1747A76} | c0a8-0057-12c3baaa7b9-4f6bfc60-3556a- | MF-HQ-12696 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06358/MF0036 | 50000 | 68.3697 | 33.3554 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {2BE9C3C6-4110-44D5-A199-B989D1747A76} |  | Medium | Critical Infrastracture | High | 654 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Chambare Mawladad | {2BE9C3C6-4110-44D5-A199-B989D1747A76} | c0a8-0057-12c3bb3c5bc-817ef07c-3ac41- | MF-HQ-12692 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06358/MF0038 | 1600 | 68.3697 | 33.3554 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {2BE9C3C6-4110-44D5-A199-B989D1747A76} |  | Medium | Critical Infrastracture | High | 654 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Gadoli Zamin | {DC667C62-98D6-4F4C-8863-A8FFC33F6E04} | c0a8-0057-12c3b9a9c06-8344fae6-2b90d- | MF-HQ-12609 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/00681/MF0039 | 195800 | 68.4123 | 33.3726 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {DC667C62-98D6-4F4C-8863-A8FFC33F6E04} |  | Low | Agriculture Blocked | High | 1291 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Hayatkhel | {E867C28A-E221-4139-A2FB-1ECDB963A9A7} | c0a8-0057-12c3b7fc22a-b3f90eee-19456- | MF-HQ-12656 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06356/MF0040 | 160000 | 68.3726 | 33.3641 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {E867C28A-E221-4139-A2FB-1ECDB963A9A7} |  | Medium | Critical Infrastracture | High | 149 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Hayatkhel | {E867C28A-E221-4139-A2FB-1ECDB963A9A7} | c0a8-0057-12c3b8eb586-e90cfd84-23c0a- | MF-HQ-12669 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06356/MF0043 | 115000 | 68.3581 | 33.3626 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {E867C28A-E221-4139-A2FB-1ECDB963A9A7} |  | Medium | Critical Infrastracture | High | 925 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Hayatkhel | {E867C28A-E221-4139-A2FB-1ECDB963A9A7} | c0a8-0057-12c3b993f8a-fcdcb651-2aa8c- | MF-HQ-12661 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06356/MF0041 | 75000 | 68.3586 | 33.3571 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {E867C28A-E221-4139-A2FB-1ECDB963A9A7} |  | Medium | Critical Infrastracture | High | 232 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Hayatkhel | {E867C28A-E221-4139-A2FB-1ECDB963A9A7} | c0a8-0057-12c3ba02b83-941847a8-2f0bf- | MF-HQ-12665 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06356/MF0042 | 100000 | 68.3586 | 33.3571 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-281 | Ghazni Demining Project-12 AT |  |  |  |  | 1398 |  | {E867C28A-E221-4139-A2FB-1ECDB963A9A7} |  | Medium | Critical Infrastracture | High | 352 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Kaboli | {C65D8618-8311-440A-94F6-311BA1FBB662} | c0a8-0057-12c3b7d8a5e-7db22233-17baa- | MF-HQ-12602 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06421/MF0044 | 80950 | 68.4548 | 33.3421 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-206 | Ghazni Demining Project-03 AT |  |  |  |  | 1397 |  | {C65D8618-8311-440A-94F6-311BA1FBB662} |  | High with Victim | High with Victims | High | 191 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Kamalkhel | {867945DC-6B4D-49A7-8E02-6569C3102923} | c0a8-0057-12c3bb76684-680c47b8-3cd23- | MF-HQ-12573 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06352/MF0045 | 171550 | 68.3607 | 33.3373 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {867945DC-6B4D-49A7-8E02-6569C3102923} |  | High with Victim | High with Victims | High | 316 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Khudza'i | {82EAAF41-7150-4EEB-8BD6-3CA94FC8FFA3} | c0a8-0057-12c3b7d88b9-218f23f8-17b97- | MF-HQ-12614 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06371/MF0046 | 100300 | 68.3803 | 33.4002 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {82EAAF41-7150-4EEB-8BD6-3CA94FC8FFA3} |  | Medium | Critical Infrastracture | High | 426 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Khudza'i | {82EAAF41-7150-4EEB-8BD6-3CA94FC8FFA3} | c0a8-0057-12c3b8b2294-23dce65d-2145d- | MF-HQ-12617 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06371/MF0048 | 130000 | 68.3797 | 33.3869 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {82EAAF41-7150-4EEB-8BD6-3CA94FC8FFA3} |  | Medium | Critical Infrastracture | High | 149 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Khudza'i | {82EAAF41-7150-4EEB-8BD6-3CA94FC8FFA3} | c0a8-0057-12c3ba969d2-fa3055b4-34a0e- | MF-HQ-12615 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06371/MF0047 | 180000 | 68.3797 | 33.3869 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {82EAAF41-7150-4EEB-8BD6-3CA94FC8FFA3} |  | Medium | Critical Infrastracture | High | 353 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Kunsaf | {7CF36808-96A9-4F8D-ADA0-12F0C25E26E0} | c0a8-0057-12c3b7bb578-ccba778a-1665f- | MF-HQ-12541 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06275/MF0050 | 100000 | 68.3933 | 33.2485 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {7CF36808-96A9-4F8D-ADA0-12F0C25E26E0} |  | Low | Agriculture Blocked | High | 733 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Kunsaf | {7CF36808-96A9-4F8D-ADA0-12F0C25E26E0} | c0a8-0057-12c3b7d00f5-95c778c7-1758f- | MF-HQ-12539 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06275/MF0049 | 210937 | 68.3975 | 33.2508 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {7CF36808-96A9-4F8D-ADA0-12F0C25E26E0} |  | Low | Agriculture Blocked | High | 128 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Kunsaf | {7CF36808-96A9-4F8D-ADA0-12F0C25E26E0} | c0a8-0057-12c3b927b1f-888e90b1-26331- | MF-HQ-12544 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06275/MF0051 | 60000 | 68.3931 | 33.2467 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {7CF36808-96A9-4F8D-ADA0-12F0C25E26E0} |  | Low | Comunity Centers | High | 643 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Meryani (1) | {A93D4A55-6DE7-4E0E-9D0A-D4FB1FA627DD} | c0a8-0057-12c3b90b403-f880c1ee-250ca- | MF-HQ-12597 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06271/MF0052 | 80000 | 68.3769 | 33.3169 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {A93D4A55-6DE7-4E0E-9D0A-D4FB1FA627DD} |  | Low | Agriculture Blocked | High | 152 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Nazarkhan Kalay | {5C740F63-C13D-4788-973A-900D29A0017E} | c0a8-0057-12c3b832ef7-e4202f66-1baf2- | MF-HQ-12640 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/04176/MF0056 | 90000 | 68.5331 | 33.3998 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-206 | Ghazni Demining Project-03 AT |  |  |  |  | 1397 |  | {5C740F63-C13D-4788-973A-900D29A0017E} |  | High with Victim | High with Victims | High | 283 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Nazarkhan Kalay | {5C740F63-C13D-4788-973A-900D29A0017E} | c0a8-0057-12c3b8ac5d6-5f38d51e-2106b- | MF-HQ-12644 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/04176/MF0054 | 50000 | 68.5066 | 33.3932 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-206 | Ghazni Demining Project-03 AT |  |  |  |  | 1397 |  | {5C740F63-C13D-4788-973A-900D29A0017E} |  | High with Victim | High with Victims | High | 129 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Nazarkhan Kalay | {5C740F63-C13D-4788-973A-900D29A0017E} | c0a8-0057-12c3b9af460-84b7f845-2bcc1- | MF-HQ-12648 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/04176/MF0053 | 90000 | 68.5066 | 33.3932 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-206 | Ghazni Demining Project-03 AT |  |  |  |  | 1397 |  | {5C740F63-C13D-4788-973A-900D29A0017E} |  | High with Victim | High with Victims | High | 129 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Nazarkhan Kalay | {5C740F63-C13D-4788-973A-900D29A0017E} | c0a8-0057-12c3bae1467-e210eaf6-375c1- | MF-HQ-12637 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/04176/MF0055 | 75000 | 68.5331 | 33.3998 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-206 | Ghazni Demining Project-03 AT |  |  |  |  | 1397 |  | {5C740F63-C13D-4788-973A-900D29A0017E} |  | High with Victim | High with Victims | High | 313 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Nyazi (2) | {1D865DC9-F426-4B35-A8A2-1B0A54DD35D6} | c0a8-0057-12c3b91f0d2-ec34122b-25db0- | MF-HQ-12632 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06391/MF0059 | 89250 | 68.4265 | 33.3749 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {1D865DC9-F426-4B35-A8A2-1B0A54DD35D6} |  | Medium | Critical Infrastracture | High | 420 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Nyazi (2) | {1D865DC9-F426-4B35-A8A2-1B0A54DD35D6} | c0a8-0057-12c3b9840d8-7936b066-29ffb- | MF-HQ-12622 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06391/MF0060 | 232900 | 68.43 | 33.3724 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {1D865DC9-F426-4B35-A8A2-1B0A54DD35D6} |  | Medium | Critical Infrastracture | High | 934 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Nyazi (2) | {1D865DC9-F426-4B35-A8A2-1B0A54DD35D6} | c0a8-0057-12c3ba74863-14d7ef3c-33622- | MF-HQ-12624 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06391/MF0057 | 108500 | 68.425 | 33.3704 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {1D865DC9-F426-4B35-A8A2-1B0A54DD35D6} |  | Medium | Critical Infrastracture | High | 453 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Nyazi (2) | {1D865DC9-F426-4B35-A8A2-1B0A54DD35D6} | c0a8-0057-12c3badfe96-d47929c-37507-2 | MF-HQ-12629 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06391/MF0058 | 55650 | 68.4235 | 33.3735 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {1D865DC9-F426-4B35-A8A2-1B0A54DD35D6} |  | Medium | Critical Infrastracture | High | 89 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Qala-i-Haji | {B405EB88-515B-45E9-8B24-291243B7A383} | c0a8-0057-12c3b984edc-5c17a326-2a085- | MF-HQ-12549 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06406/MF0062 | 108000 | 68.4125 | 33.3965 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {B405EB88-515B-45E9-8B24-291243B7A383} |  | Medium | Critical Infrastracture | High | 186 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Qala-i-Haji | {B405EB88-515B-45E9-8B24-291243B7A383} | c0a8-0057-12c3bafa720-cde15056-384e3- | MF-HQ-12551 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06406/MF0061 | 122400 | 68.4202 | 33.3986 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {B405EB88-515B-45E9-8B24-291243B7A383} |  | Medium | Critical Infrastracture | High | 38 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Sahebkhan | {1725F53A-B2AC-4BE5-A7F8-4C52C7737D99} | c0a8-0057-12c3ba6e85a-d62ca5d1-33273- | MF-HQ-12592 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06305/MF0063 | 21000 | 68.4101 | 33.3176 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {1725F53A-B2AC-4BE5-A7F8-4C52C7737D99} |  | Low | Comunity Centers | High | 187 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Sardeh Band(Bande Sardeh) | {2A7EA1C1-FA75-4D89-90A9-500BBB1487D9} | c0a8-0057-12c3b7dc200-b65cdd22-17e18- | MF-HQ-12556 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06449/MF0064 | 139400 | 68.6226 | 33.2921 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {2A7EA1C1-FA75-4D89-90A9-500BBB1487D9} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Sardeh Band(Bande Sardeh) | {2A7EA1C1-FA75-4D89-90A9-500BBB1487D9} | c0a8-0057-12c3ba3f1a5-ca9b6fd2-31545- | MF-HQ-12561 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06449/MF0065 | 102300 | 68.6226 | 33.2921 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {2A7EA1C1-FA75-4D89-90A9-500BBB1487D9} |  | Low | Agriculture Blocked | High | 149 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Sardeh Band(Bande Sardeh) | {2A7EA1C1-FA75-4D89-90A9-500BBB1487D9} | c0a8-0057-12c3ba8b120-64638c5b-34343- | MF-HQ-12565 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06449/MF0063 | 119700 | 68.622 | 33.3113 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {2A7EA1C1-FA75-4D89-90A9-500BBB1487D9} |  | Low | Critical Infrastracture | High | 2 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Sardeh Band(Bande Sardeh) | {2A7EA1C1-FA75-4D89-90A9-500BBB1487D9} | c0a8-0057-12c3baeb278-ebb4476d-37be7- | MF-HQ-12569 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06449/MF0066 | 120600 | 68.622 | 33.3113 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {2A7EA1C1-FA75-4D89-90A9-500BBB1487D9} |  | Low | Critical Infrastracture | High | 2 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Shado | {C983225A-CD32-46FA-B93D-DE542DD297D2} | c0a8-0057-12c3b7eecd4-57c3322c-18a82- | MF-HQ-12710 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06354/MF070 | 60000 | 68.3787 | 33.3317 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-206 | Ghazni Demining Project-03 AT |  |  |  |  | 1397 |  | {C983225A-CD32-46FA-B93D-DE542DD297D2} |  | High with Victim | High with Victims | High | 382 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Shado | {C983225A-CD32-46FA-B93D-DE542DD297D2} | c0a8-0057-12c3b80590a-209551da-19ad2- | MF-HQ-12715 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06354/MF067 | 52500 | 68.3868 | 33.3357 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-206 | Ghazni Demining Project-03 AT |  |  |  |  | 1397 |  | {C983225A-CD32-46FA-B93D-DE542DD297D2} |  | High with Victim | High with Victims | High | 76 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Shado | {C983225A-CD32-46FA-B93D-DE542DD297D2} | c0a8-0057-12c3b901d29-bc699ca6-24b13- | MF-HQ-12718 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06354/MF069 | 96850 | 68.3813 | 33.3402 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-206 | Ghazni Demining Project-03 AT |  |  |  |  | 1397 |  | {C983225A-CD32-46FA-B93D-DE542DD297D2} |  | High with Victim | High with Victims | High | 420 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Shado | {C983225A-CD32-46FA-B93D-DE542DD297D2} | c0a8-0057-12c3baf043e-16140a5e-37f0a- | MF-HQ-12706 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06354/MF068 | 30000 | 68.3722 | 33.3359 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-206 | Ghazni Demining Project-03 AT |  |  |  |  | 1397 |  | {C983225A-CD32-46FA-B93D-DE542DD297D2} |  | High with Victim | High with Victims | High | 38 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Sini (1) | {0B388758-80CC-4D9A-9BDC-F427FC59872C} | c0a8-0057-12c3b85b3d9-2f21095b-1d821- | MF-HQ-12547 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06438/MF0071 | 131250 | 68.5027 | 33.3854 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {0B388758-80CC-4D9A-9BDC-F427FC59872C} |  | Medium | Critical Infrastracture | High | 28 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Ya'qub | {420AF069-3E86-45F5-AF66-B9382C1D6310} | c0a8-0057-12c3b7c9633-40cfc9ab-170b2- | MF-HQ-12537 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06382/MF0073 | 100000 | 68.3859 | 33.3751 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {420AF069-3E86-45F5-AF66-B9382C1D6310} |  | Low | Critical Infrastracture | High | 283 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Ya'qub | {420AF069-3E86-45F5-AF66-B9382C1D6310} | c0a8-0057-12c3b921966-fe4c8eab-25f59- | MF-HQ-12092 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06382/MF072 | 30000 | 68.4018 | 33.3683 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {420AF069-3E86-45F5-AF66-B9382C1D6310} |  | Medium | Critical Infrastracture | High | 89 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Ya'qub | {420AF069-3E86-45F5-AF66-B9382C1D6310} | c0a8-0057-12c3b9c1b9a-2a9dd992-2c825- | MF-HQ-12535 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06382/MF0074 | 234500 | 68.4018 | 33.3683 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {420AF069-3E86-45F5-AF66-B9382C1D6310} |  | Medium | Critical Infrastracture | High | 1193 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Zakuri | {9E3B8CCB-7D59-456C-8B33-8E3306E6F67C} | c0a8-0057-12c3b856da6-e1e1b8fb-1d524- | MF-HQ-12588 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06398/MF0076 | 116950 | 68.3912 | 33.385 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {9E3B8CCB-7D59-456C-8B33-8E3306E6F67C} |  | Medium | Critical Infrastracture | High | 209 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Andar | Zakuri | {9E3B8CCB-7D59-456C-8B33-8E3306E6F67C} | c0a8-0057-12c3bb80ba6-cb21dd46-3d349- | MF-HQ-12586 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06398/MF075 | 94500 | 68.3912 | 33.385 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-300 | Ghazni Demining Project-13 AT |  |  |  |  | 1398 |  | {9E3B8CCB-7D59-456C-8B33-8E3306E6F67C} |  | Medium | Critical Infrastracture | High | 209 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Bahrami Shahid (Jaghatu) | Sar bed | {111B3F46-D4B6-4A5E-B051-204192BD5F3B} | c0a8-0057-12c3b84f389-2fee5d09-1cfb3- | MF-HQ-12777 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0602/00042/MF001 | 108000 | 68.2213 | 33.624 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-205 | Ghazni Demining Project-03 |  |  |  |  | 1397 |  | {111B3F46-D4B6-4A5E-B051-204192BD5F3B} |  | High with Victim | High with Victims | Substantial | 333 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Balay | {C521171D-AC8D-4A6F-8F29-214E9B9CEEBB} | c0a8-0057-12c3baf1e82-e0d8e7bd-37fe1- | MF-HQ-12506 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04211/MF0054 | 320000 | 68.6545 | 33.4275 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-301 | Ghazni Demining Project-14 AT |  |  |  |  | 1400 |  | {C521171D-AC8D-4A6F-8F29-214E9B9CEEBB} |  | Low | Agriculture Blocked | Substantial | 222 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Pajak | {946BBC84-7108-406C-A6AC-235249093AD0} | c0a8-0057-12c3ba36704-b7b03c50-31003- | BF-SE-107 | MCPA - Mine Clearance Planning Agency | AF/0615/04200/BF046 | 292500 | 68.5503 | 33.5039 | Open | UXO Only | UXO Only | BF |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {946BBC84-7108-406C-A6AC-235249093AD0} |  | High with Victim | High with Victims | Substantial | 1319 | CHA | 2 |  |  | 2006-06-30 | No | Open
South East | Ghazni | Dih Yak | Rabat | {6EFE05FA-5A2B-47E0-B04E-C0AD85892046} | c0a8-0057-12c3b7e06ad-e63fc670-18134- | MF-HQ-12509 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04225/MF0059 | 45000 | 68.7014 | 33.52 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {6EFE05FA-5A2B-47E0-B04E-C0AD85892046} |  | High with Victim | High with Victims | Substantial | 117 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Rabat | {6EFE05FA-5A2B-47E0-B04E-C0AD85892046} | c0a8-0057-12c3b87d9f9-193900b-1f00f-e | MF-HQ-12508 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04225/MF0058 | 6000000 | 68.6976 | 33.5537 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-158 | Ghazni Demining Project-01 AT |  |  |  |  | 1397 |  | {6EFE05FA-5A2B-47E0-B04E-C0AD85892046} |  | High with Victim | High with Victims | Substantial | 208 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Rabat | {6EFE05FA-5A2B-47E0-B04E-C0AD85892046} | c0a8-0057-12c3ba28a20-7c80e589-307ad- | MF-HQ-12507 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04225/MF0057 | 4000000 | 68.6924 | 33.5891 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-204 | Ghazni Demining Project-02 AT |  |  |  |  | 1397 |  | {6EFE05FA-5A2B-47E0-B04E-C0AD85892046} |  | High with Victim | High with Victims | Substantial | 1360 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Ramak | {84BA0F41-F7DD-46E0-915C-6A89EB14364A} | c0a8-0057-12c3b7d9dde-36684965-17c7b- | MF-SE-110 | MCPA - Mine Clearance Planning Agency | AF/0615/04217/0047 | 140695 | 68.6386 | 33.5264 | Open | AT Only | AT Only | MineField |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {84BA0F41-F7DD-46E0-915C-6A89EB14364A} |  | High with Victim | High with Victims | Substantial | 131 | CHA | 2 |  |  | 2006-07-31 | No | Open
South East | Ghazni | Dih Yak | Ramak | {84BA0F41-F7DD-46E0-915C-6A89EB14364A} | c0a8-0057-12c3b9d4cd2-e0a3dbb-2d43a-8 | MF-SE-319 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04217/MF(R049) | 33516 | 68.625 | 33.5007 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {84BA0F41-F7DD-46E0-915C-6A89EB14364A} |  | High with Victim | High with Victims | Substantial | 209 | CHA | 2 |  |  | 2008-10-27 16:30 | No | Open
South East | Ghazni | Dih Yak | Ramak | {84BA0F41-F7DD-46E0-915C-6A89EB14364A} | c0a8-0057-12c3b9d50c8-2e815a3c-2d44d- | MF-SE-118 | MCPA - Mine Clearance Planning Agency | AF/0615/04217/049 | 111484 | 68.6207 | 33.5034 | Open | AT Only | AT Only | MineField |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {84BA0F41-F7DD-46E0-915C-6A89EB14364A} |  | High with Victim | High with Victims | Substantial | 151 | CHA | 2 |  |  | 2006-09-30 | No | Open
South East | Ghazni | Dih Yak | Sar Tasan | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} | c0a8-0057-12c3b7fa92e-a2561c20-19325- | MF-HQ-12530 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04205/MF0061 | 132000 | 68.5891 | 33.5025 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} |  | High with Victim | High with Victims | Substantial | 268 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Sar Tasan | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} | c0a8-0057-12c3b81ef6b-818d769b-1ace4- | MF-HQ-12526 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04205/MF0063 | 112500 | 68.5891 | 33.5025 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} |  | High with Victim | High with Victims | Substantial | 12 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Sar Tasan | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} | c0a8-0057-12c3b84d1e6-7e37ab66-1ce1d- | MF-HQ-12517 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04205/MF0062 | 2500 | 68.5991 | 33.5012 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} |  | High with Victim | High with Victims | Substantial | 477 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Sar Tasan | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} | c0a8-0057-12c3b9811af-b425936a-29e12- | MF-HQ-12522 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04205/MF0065 | 120000 | 68.6109 | 33.4982 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} |  | High with Victim | High with Victims | Substantial | 105 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Sar Tasan | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} | c0a8-0057-12c3b9ead35-45fc74b3-2e1f4- | MF-HQ-12514 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04205/MF0060 | 18000 | 68.593 | 33.4678 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} |  | High with Victim | High with Victims | Substantial | 38 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Sar Tasan | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} | c0a8-0057-12c3ba08f05-5fe2627a-2f483- | MF-HQ-12520 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04205/MF0064 | 73500 | 68.6032 | 33.5026 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {CED1CB39-401C-499D-A0B7-1C8AA5D319F6} |  | High with Victim | High with Victims | Substantial | 106 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Shotan | {993DCC6D-B418-4054-B6DC-B1A9A4621AD3} | c0a8-0057-12c3b871e2b-61d9d9ac-1e7a8- | MF-HQ-12492 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/615/4208/MF0051 | 294000 | 68.6666 | 33.583 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {993DCC6D-B418-4054-B6DC-B1A9A4621AD3} |  | High with Victim | High with Victims | Substantial | 414 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Dih Yak | Shotan | {993DCC6D-B418-4054-B6DC-B1A9A4621AD3} | c0a8-0057-12c3bb0a614-cd8b531-38e72-2 | MF-HQ-12490 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0615/04208/MF0050 | 308200 | 68.6666 | 33.583 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-159 | Ghazni Demining Project-02 |  |  |  |  | 1397 |  | {993DCC6D-B418-4054-B6DC-B1A9A4621AD3} |  | High with Victim | High with Victims | Substantial | 130 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Ghazni | Gili Surkh | {4FB2BAA6-DB17-4CCD-91FE-8311377710FF} | c0a8-0057-12c3bb4fa31-6d1848ef-3b79b- | MF-HQ-12893 | MCPA - Mine Clearance Planning Agency | AF/0601/00237/MF0130 | 81605 | 68.354 | 33.5933 | Open | AT Only | AT Only | MineField |  | MBT Project-302 | Ghazni Demining Project-15 AT |  |  |  |  | 1398 |  | {4FB2BAA6-DB17-4CCD-91FE-8311377710FF} | Planned Year Removed | High Requested | Resettlment/Local Request | Moderate | 563 | CHA | 4 |  |  | 2009-10-05 | No | Open
South East | Ghazni | Ghazni | Gili Surkh | {4FB2BAA6-DB17-4CCD-91FE-8311377710FF} | c0a8-00f6-1360588163f-163dd2bf-876-87 | MF-HQ-12892 | MCPA - Mine Clearance Planning Agency | AF/0661/00237/MF0129 | 42107 | 68.3574 | 33.5856 | Open | AT Only | AT Only | MineField |  | MBT Project-302 | Ghazni Demining Project-15 AT |  |  |  |  | 1398 |  | {4FB2BAA6-DB17-4CCD-91FE-8311377710FF} | Planned Agency and plan year removed | Low | Critical Infrastracture | Moderate | 318 | CHA | 5 |  |  | 2009-10-05 | No | Open
South East | Ghazni | Ghazni | Qala-I-Amoo | {44593D77-5634-4D35-B1BB-495B447B7F31} | c0a8-008e-1329f288c28-d15da145-14b3-8 | MF-15766 | MCPA - Mine Clearance Planning Agency | AF/0601/00205/MF0147 | 13807 | 68.3765 | 33.5502 | Open | AT Only | AT Only | MineField |  | MBT Project-302 | Ghazni Demining Project-15 AT |  |  |  |  | 1398 |  | {44593D77-5634-4D35-B1BB-495B447B7F31} | Planned Year Removed | Medium | Critical Infrastracture | Moderate | 143 | CHA | 3 |  |  | 2011-02-07 16:30 | No | Open
South East | Ghazni | Ghazni | Qanate Atakhan | {C0B3E947-B914-4D18-988D-B48512A9DD0B} | c0a8-0057-12f431fbad3-6663fd27-1725-c | MF-SE-283 | MCPA - Mine Clearance Planning Agency | AF/0601/04061/MF0096R | 65015 | 68.3635 | 33.5515 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-302 | Ghazni Demining Project-15 AT |  |  |  |  | 1398 |  | {C0B3E947-B914-4D18-988D-B48512A9DD0B} | Planned Year Removed | Low | Agriculture Blocked | Moderate | 311 | CHA | 4 |  |  | 2000-11-11 16:30 | No | Open
South East | Ghazni | Ghazni | Rawza | {1714C594-76BB-478C-A211-F630A54FFDAF} | c0a8-0009-14227c89a0e-1058334d-4654-9 | Hz-ID-18206 | MCPA - Mine Clearance Planning Agency | AF/0601/04115/BF0179 | 5823 | 68.4862 | 33.6185 | Open | UXO Only | UXO Only | BF |  | MBT Project-302 | Ghazni Demining Project-15 AT |  |  |  |  | 1398 |  | {1714C594-76BB-478C-A211-F630A54FFDAF} |  | High with Victim | High with Victims | Moderate | 14 | CHA | 2 |  |  | 2013-09-21 16:30 | No | Open
South East | Ghazni | Giro | Bar Metakhan | {4B0D81F5-7AA8-4B0A-B3CD-0FCB94E72738} | c0a8-0057-12c3b7d812a-714e56eb-17b43- | MF-HQ-12764 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0612/06512/0014 | 101250 | 68.4317 | 33.0912 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-208 | Ghazni Demining Project-04 AT |  |  |  |  | 1397 |  | {4B0D81F5-7AA8-4B0A-B3CD-0FCB94E72738} |  | High with Victim | High with Victims | High | 21 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Giro | Bar Metakhan | {4B0D81F5-7AA8-4B0A-B3CD-0FCB94E72738} | c0a8-0057-12c3b80ebd5-cfbb3ff8-1a144- | MF-HQ-12758 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0612/06512/MF0013 | 45000 | 68.4267 | 33.1161 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-208 | Ghazni Demining Project-04 AT |  |  |  |  | 1397 |  | {4B0D81F5-7AA8-4B0A-B3CD-0FCB94E72738} |  | High with Victim | High with Victims | High | 0 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Giro | Disi | {F017F77F-EF7C-4A38-A6AA-DE633785D53B} | c0a8-0057-12c3b99fb47-9511318e-2b25b- | MF-HQ-12753 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0612/06497/MF008 | 80000 | 68.4648 | 33.0182 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {F017F77F-EF7C-4A38-A6AA-DE633785D53B} |  | Low | Agriculture Blocked | High | 48 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Giro | Disi | {F017F77F-EF7C-4A38-A6AA-DE633785D53B} | c0a8-0057-12c3ba9ac2e-abc556d2-34c5d- | MF-HQ-12751 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0612/06497/MF007 | 110000 | 68.4792 | 33.0148 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {F017F77F-EF7C-4A38-A6AA-DE633785D53B} |  | Low | Agriculture Blocked | High | 1 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Giro | Musakhel | {40002B1B-F02F-46E3-A8E8-29656C0291C1} | c0a8-0057-12c3b86dae5-b888b338-1e4aa- | MF-HQ-12746 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0612/06509/MF011 | 225000 | 68.38 | 33.1155 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-214 | Ghazni Demining Project-07 |  |  |  |  | 1398 |  | {40002B1B-F02F-46E3-A8E8-29656C0291C1} |  | Low | Agriculture Blocked | High | 300 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Giro | Musakhel | {40002B1B-F02F-46E3-A8E8-29656C0291C1} | c0a8-0057-12c3b887636-8965e43f-1f6d6- | MF-HQ-12739 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0612/06509/MF009 | 5000 | 68.3627 | 33.1195 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-209 | Ghazni Demining Project-04 |  |  |  |  | 1398 |  | {40002B1B-F02F-46E3-A8E8-29656C0291C1} |  | Medium | Critical Infrastracture | High | 277 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Giro | Musakhel | {40002B1B-F02F-46E3-A8E8-29656C0291C1} | c0a8-0057-12c3ba2884c-7bc08b2a-3079c- | MF-HQ-12744 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0612/06509/MF012 | 1250 | 68.3562 | 33.1212 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-209 | Ghazni Demining Project-04 |  |  |  |  | 1398 |  | {40002B1B-F02F-46E3-A8E8-29656C0291C1} |  | Medium | Critical Infrastracture | High | 69 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Giro | Musakhel | {40002B1B-F02F-46E3-A8E8-29656C0291C1} | c0a8-0057-12c3baf289f-e3bfd0e8-3804f- | MF-HQ-12734 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0612/06509/MF010 | 1875 | 68.3628 | 33.1196 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-209 | Ghazni Demining Project-04 |  |  |  |  | 1398 |  | {40002B1B-F02F-46E3-A8E8-29656C0291C1} |  | Medium | Critical Infrastracture | High | 277 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Giro | Parcha | {52F8758B-5A37-4057-B314-65D0684D18FC} | c0a8-0057-12c3b8c10c6-842867ee-21f26- | MF-HQ-12771 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0612/06515/0016 | 7500 | 68.4297 | 33.1459 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {52F8758B-5A37-4057-B314-65D0684D18FC} |  | Low | Agriculture Blocked | High | 10 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Giro | Parcha | {52F8758B-5A37-4057-B314-65D0684D18FC} | c0a8-0057-12c3b9cdf52-41509efd-2d039- | MF-HQ-12770 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0612/06515/MF0015 | 50000 | 68.4233 | 33.1338 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {52F8758B-5A37-4057-B314-65D0684D18FC} |  | Low | Agriculture Blocked | High | 10 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Giro | Sra Kala | {C5481B97-7DEA-46C4-9C89-E77E4F0C525E} | c0a8-008e-13237c748a3-f04b5894-344-d7 | MF-HQ-12756 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0612/06510/MF006 | 100000 | 68.3809 | 33.1192 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-214 | Ghazni Demining Project-07 |  |  |  |  | 1398 |  | {C5481B97-7DEA-46C4-9C89-E77E4F0C525E} |  | Low | Agriculture Blocked | High | 16 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Jaghuri | Bayan (Qarya-I-Bayan) | {C8FCB7AC-BF15-44BC-B8FE-5660F705B3A5} | c0a8-0057-12c3b7d857e-8f8e8ff1-17b71- | MF-HQ-12485 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0607/00621/MF011 | 84150 | 67.597 | 33.1636 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-209 | Ghazni Demining Project-04 |  |  |  |  | 1398 |  | {C8FCB7AC-BF15-44BC-B8FE-5660F705B3A5} |  | Medium | Critical Infrastracture | Minimal | 425 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Jaghuri | Lodah | {AC4D94E5-10FE-4F27-A4EF-4C0A432D04F4} | c0a8-0057-12c3bb5b1bb-cd83e6b8-3be23- | MF-HQ-12488 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0607/00519/MF010 | 108900 | 67.6021 | 33.1626 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-214 | Ghazni Demining Project-07 |  |  |  |  | 1398 |  | {AC4D94E5-10FE-4F27-A4EF-4C0A432D04F4} |  | Low | Agriculture Blocked | Minimal | 22 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Jaghuri | Luman | {5D5537F9-CE62-4F47-B354-F1AC371F7192} | c0a8-0057-12c3b93ddf3-69fca6c1-271d2- | MF-HQ-12487 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0607/05428/MF006 | 96600 | 67.6039 | 33.1284 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-209 | Ghazni Demining Project-04 |  |  |  |  | 1398 |  | {5D5537F9-CE62-4F47-B354-F1AC371F7192} |  | Medium | Critical Infrastracture | Minimal | 238 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Jaghuri | Sare Luman | {B23031F7-4112-4F75-A55B-E1317C4B018B} | c0a8-0057-12c3b80f46d-7bcff651-1a18f- | MF-SE-323 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0607/05428/MF(R005) | 742179 | 67.6651 | 33.1251 | Open | AP Only | AP Only | MineField |  | MBT Project-209 | Ghazni Demining Project-04 |  |  |  |  | 1398 |  | {B23031F7-4112-4F75-A55B-E1317C4B018B} |  | High with Victim | High with Victims | Minimal | 3266 | CHA | 3 |  |  | 2008-10-27 16:30 | No | Open
South East | Ghazni | Jaghuri | Sare Luman | {B23031F7-4112-4F75-A55B-E1317C4B018B} | c0a8-0057-12c3b895175-f60b4f24-20074- | MF-HQ-12479 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0607/05703/MF009 | 62400 | 67.6825 | 33.1296 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {B23031F7-4112-4F75-A55B-E1317C4B018B} |  | High with Victim | High with Victims | Minimal | 229 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Jaghuri | Sare Luman | {B23031F7-4112-4F75-A55B-E1317C4B018B} | c0a8-0057-12c3b8fff10-4c477345-249c1- | MF-HQ-12482 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0607/05703/MF007 | 155800 | 67.6825 | 33.1296 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-214 | Ghazni Demining Project-07 |  |  |  |  | 1398 |  | {B23031F7-4112-4F75-A55B-E1317C4B018B} |  | High with Victim | High with Victims | Minimal | 204 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Jaghuri | Sare Luman | {B23031F7-4112-4F75-A55B-E1317C4B018B} | c0a8-0057-12c3bb0a1a1-e958d00e-38e4e- | MF-HQ-12477 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0607/05703/MF008 | 21000 | 67.6668 | 33.1217 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-214 | Ghazni Demining Project-07 |  |  |  |  | 1398 |  | {B23031F7-4112-4F75-A55B-E1317C4B018B} |  | High with Victim | High with Victims | Minimal | 73 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Jaghuri | Sare Luman | {B23031F7-4112-4F75-A55B-E1317C4B018B} | c0a8-0057-12f0531ff0b-cc7aaac3-1298-5 | MF-HQ-3497 | MCPA - Mine Clearance Planning Agency | AF/0607/05703/MF0005 | 69923 | 67.658 | 33.1206 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-209 | Ghazni Demining Project-04 |  |  |  |  | 1398 |  | {B23031F7-4112-4F75-A55B-E1317C4B018B} |  | High with Victim | High with Victims | Minimal | 1263 | CHA | 3 |  |  | 1996-09-23 | No | Open
South East | Ghazni | Jaghuri | Sare Luman | {B23031F7-4112-4F75-A55B-E1317C4B018B} | c0a8-0057-12f05355f89-9b7738d7-12fd-a | MF-HQ-3496 | MCPA - Mine Clearance Planning Agency | AF/0607/05703/MF0004 | 88213 | 67.6591 | 33.1251 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-209 | Ghazni Demining Project-04 |  |  |  |  | 1398 |  | {B23031F7-4112-4F75-A55B-E1317C4B018B} |  | High with Victim | High with Victims | Minimal | 1263 | CHA | 3 |  |  | 1996-09-16 | No | Open
South East | Ghazni | Khwaja Umari | Dehe Darat | {58D5DD21-9127-46D2-9FDB-ABFD4A07A8F7} | c0a8-0057-12c3b89d62d-2e1c8c83-205e7- | MF-HQ-12546 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0617/04255/MF006 | 240000 | 68.4009 | 33.7078 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-210 | Ghazni Demining Project-05 |  |  |  |  | 1398 |  | {58D5DD21-9127-46D2-9FDB-ABFD4A07A8F7} |  | Medium | Critical Infrastracture | Moderate | 198 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Khwaja Umari | Karez (2) | {41715C5A-609B-4F1D-9013-0D3B9C6A2E30} | c0a8-0057-12c3bb368bf-1ec09b91-3a8cc- | MF-HQ-12548 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0617/04258/MF008 | 75000 | 68.407 | 33.7188 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-210 | Ghazni Demining Project-05 |  |  |  |  | 1398 |  | {41715C5A-609B-4F1D-9013-0D3B9C6A2E30} |  | Medium | Agriculture Blocked | Moderate | 0 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Khwaja Umari | Pay Mast'ali | {32FDE111-AA26-4992-A37D-77CD51BFD626} | c0a8-0057-12c3b855ff0-3f3180f9-1d484- | MF-HQ-12489 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0617/04230/MF007 | 100000 | 68.3774 | 33.7117 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-210 | Ghazni Demining Project-05 |  |  |  |  | 1398 |  | {32FDE111-AA26-4992-A37D-77CD51BFD626} |  | Medium | Critical Infrastracture | Moderate | 264 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Khwaja Umari | Qal'a-i Naw | {01663CB8-DD08-43F6-BA4A-5862D1313AE6} | c0a8-0057-12c3b7b9165-13de518f-164bd- | MF-HQ-12593 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0617/00583/MF005 | 350000 | 68.4433 | 33.6409 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {01663CB8-DD08-43F6-BA4A-5862D1313AE6} |  | Low | Agriculture Blocked | Moderate | 1 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Khwaja Umari | Qal'a-i-Mulla Ghazi | {8B3BA6AD-DE2D-418A-8C93-56B7B7DB0A73} | c0a8-0057-12c3b8c5979-743b12ff-221fd- | MF-HQ-12499 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0617/03363/MF002 | 60000 | 68.4853 | 33.6683 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {8B3BA6AD-DE2D-418A-8C93-56B7B7DB0A73} |  | Low | Critical Infrastracture | Moderate | 91 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Khwaja Umari | Qal'a-i-Mulla Ghazi | {8B3BA6AD-DE2D-418A-8C93-56B7B7DB0A73} | c0a8-0057-12c3bae094f-f4ca2d98-3755a- | MF-HQ-12498 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0617/03363/MF001 | 107100 | 68.4853 | 33.6683 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {8B3BA6AD-DE2D-418A-8C93-56B7B7DB0A73} |  | Low | Critical Infrastracture | Moderate | 91 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Khwaja Umari | Taquduz | {9CB53F46-313E-4307-9937-3FBE422FAA6E} | c0a8-0057-12c3b97262e-fd806434-29454- | MF-HQ-12495 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0617/04234/MF004 | 33900 | 68.3496 | 33.6613 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-205 | Ghazni Demining Project-03 |  |  |  |  | 1397 |  | {9CB53F46-313E-4307-9937-3FBE422FAA6E} |  | High with Victim | High with Victims | Moderate | 39 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Khwaja Umari | Taquduz | {9CB53F46-313E-4307-9937-3FBE422FAA6E} | c0a8-0057-12c3b9d3ba3-afb2e800-2d38d- | MF-HQ-12493 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0617/04234/MF003 | 70000 | 68.3565 | 33.6683 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-205 | Ghazni Demining Project-03 |  |  |  |  | 1397 |  | {9CB53F46-313E-4307-9937-3FBE422FAA6E} |  | High with Victim | High with Victims | Moderate | 41 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Nawa | Nawa | {7C43A8CD-889B-4B18-93C2-4F2428FBD332} | c0a8-0057-12f052d0d89-18ffe026-1238-4 | MF-HQ-9535 | MCPA - Mine Clearance Planning Agency | AF/0604/06651/MF0002 | 143643 | 67.8818 | 32.3231 | Open | AT Only | AT Only | MineField |  | MBT Project-261 | Ghazni Demining Project-11 AT |  |  |  |  | 1400 |  | {7C43A8CD-889B-4B18-93C2-4F2428FBD332} |  | Low | Comunity Centers | Extreme | 15 | CHA | 5 |  |  | 2003-04-30 | No | Open
South East | Ghazni | Nawa | Nawa | {7C43A8CD-889B-4B18-93C2-4F2428FBD332} | c0a8-0057-12f053635ba-2d667ea8-1316-7 | MF-HQ-9534 | MCPA - Mine Clearance Planning Agency | AF/0604/06651/MF0001 | 136631 | 67.8818 | 32.3225 | Open | AT Only | AT Only | MineField |  | MBT Project-261 | Ghazni Demining Project-11 AT |  |  |  |  | 1400 |  | {7C43A8CD-889B-4B18-93C2-4F2428FBD332} |  | Low | Comunity Centers | Extreme | 35 | CHA | 5 |  |  | 2003-04-30 | No | Open
South East | Ghazni | Nawa | Nawa | {7C43A8CD-889B-4B18-93C2-4F2428FBD332} | c0a8-0057-12f0539b05c-d995a1-13c4-49e | MF-HQ-9533 | MCPA - Mine Clearance Planning Agency | AF/0604/06651/MF0003 | 72977 | 67.8818 | 32.3223 | Open | AT Only | AT Only | MineField |  | MBT Project-261 | Ghazni Demining Project-11 AT |  |  |  |  | 1400 |  | {7C43A8CD-889B-4B18-93C2-4F2428FBD332} |  | Low | Comunity Centers | Extreme | 15 | CHA | 5 |  |  | 2003-04-30 | No | Open
South East | Ghazni | Nawur | Qutu | {B437A47A-5FB4-4153-B07E-310EAED296A7} | c0a8-0009-147a4f9fc9b-9c7d969c-1459-6 | Hz-ID-18877 | MCPA - Mine Clearance Planning Agency | AF/0604/04443/SERW0002 | 193 | 67.6476 | 33.9945 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-205 | Ghazni Demining Project-03 |  |  |  |  | 1397 |  | {B437A47A-5FB4-4153-B07E-310EAED296A7} |  | Medium | Agriculture Blocked | Minimal | 0 | CHA | 3 |  |  | 2014-06-24 16:30 | No | Open
South East | Ghazni | Qarabagh | Iday | {40BD68F4-8E3F-4F15-91AE-146BD8195175} | c0a8-0057-12c3b9ee728-6ebd245e-2e427- | MF-HQ-12631 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/05888/MF037 | 500000 | 68.0532 | 33.1985 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-209 | Ghazni Demining Project-04 |  |  |  |  | 1398 |  | {40BD68F4-8E3F-4F15-91AE-146BD8195175} |  | Medium | Critical Infrastracture | High | 1221 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Qarabagh | Kahkash | {E2419A4F-977F-4EC4-B5B8-72BED95C4F04} | c0a8-0057-12c3bb20f7d-996c85-39c17-7d | MF-HQ-12643 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/05842/MF044 | 52500 | 68.0365 | 33.1365 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {E2419A4F-977F-4EC4-B5B8-72BED95C4F04} |  | Low | Agriculture Blocked | High | 577 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Qarabagh | Kashi | {49CEECAE-895F-4AFB-A74A-2D6F1BA8F511} | c0a8-0057-12c3bb2a1ea-b1b856c6-3a133- | MF-HQ-12634 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/05844/MF036 | 80000 | 68.0478 | 33.1287 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-214 | Ghazni Demining Project-07 |  |  |  |  | 1398 |  | {49CEECAE-895F-4AFB-A74A-2D6F1BA8F511} |  | Low | Critical Infrastracture | High | 172 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Qarabagh | Mushakay | {1FD1F802-FE3B-4CB9-8D72-E6088FDBF27C} | c0a8-0057-12c3bafb66b-bc0e7a83-3857f- | MF-HQ-12626 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/05927/MF043 | 81000 | 68.2113 | 33.2427 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-208 | Ghazni Demining Project-04 AT |  |  |  |  | 1397 |  | {1FD1F802-FE3B-4CB9-8D72-E6088FDBF27C} |  | High with Victim | High with Victims | High | 33 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Qarabagh | Nawaz | {3B438D8E-5F86-42FE-99ED-54569E47BD27} | c0a8-0057-12c3ba2bb7b-4c1cc4ed-3099a- | MF-HQ-12638 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/05920/MF038 | 150000 | 68.1902 | 33.114 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-214 | Ghazni Demining Project-07 |  |  |  |  | 1398 |  | {3B438D8E-5F86-42FE-99ED-54569E47BD27} |  | Low | Agriculture Blocked | High | 202 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Qarabagh | Qal`a-i-Bara | {16E0D1CA-3F75-4AD2-B377-1D52E9C25BEE} | c0a8-0057-12c3b968b89-cf05b1b8-28e3a- | MF-HQ-13799 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/05932/MF0046 | 99400 | 68.2484 | 33.2761 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {16E0D1CA-3F75-4AD2-B377-1D52E9C25BEE} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-12-13 | No | Open
South East | Ghazni | Qarabagh | Qal`a-i-Bara | {16E0D1CA-3F75-4AD2-B377-1D52E9C25BEE} | c0a8-0057-12c3ba7bb21-84633e0b-33a56- | MF-HQ-13808 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/05932/MF047 | 152300 | 68.2514 | 33.2809 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-258 | Ghazni Demining Project-08 |  |  |  |  | 1400 |  | {16E0D1CA-3F75-4AD2-B377-1D52E9C25BEE} |  | Low | Agriculture Blocked | High | 20 | SHA | 5 |  |  | 2009-12-13 | No | Open
South East | Ghazni | Qarabagh | Qarya-i-Deh Kushk | {F940D91D-0CC0-4F48-8A86-C541DDE4AA89} | c0a8-0057-12c3bb22685-b0562cf7-39cf9- | MF-HQ-13809 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/05790/MF048 | 132600 | 67.7733 | 33.2734 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-214 | Ghazni Demining Project-07 |  |  |  |  | 1398 |  | {F940D91D-0CC0-4F48-8A86-C541DDE4AA89} |  | Low | Agriculture Blocked | High | 369 | SHA | 4 |  |  | 2009-12-13 | No | Open
South East | Ghazni | Qarabagh | Sher Khan Qala | {B93F8050-6C96-4B1F-82F3-173B52D10809} | c0a8-0057-12c3bb696b9-261cfda-3c60c-9 | MF-HQ-12623 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/00570/MF045 | 63750 | 68.0787 | 33.1942 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-208 | Ghazni Demining Project-04 AT |  |  |  |  | 1397 |  | {B93F8050-6C96-4B1F-82F3-173B52D10809} |  | High with Victim | High with Victims | High | 2034 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Qarabagh | Tamaki | {2F795B8F-75B7-4820-984C-E608126664E8} | c0a8-0057-12c3b7f6b16-e43fb5e8-19067- | MF-HQ-12660 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/00137/MF040 | 111550 | 67.7659 | 33.1889 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-098 | Ghazni Demining Project-01 |  |  |  |  | 1396 |  | {2F795B8F-75B7-4820-984C-E608126664E8} |  | High with Victim | High with Victims | High | 1104 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Qarabagh | Tamaki | {2F795B8F-75B7-4820-984C-E608126664E8} | c0a8-0057-12c3b7fe7d2-40ecd487-19605- | MF-HQ-12654 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/00137/MF041 | 90000 | 67.7659 | 33.1889 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-098 | Ghazni Demining Project-01 |  |  |  |  | 1396 |  | {2F795B8F-75B7-4820-984C-E608126664E8} |  | High with Victim | High with Victims | High | 141 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Qarabagh | Tamaki | {2F795B8F-75B7-4820-984C-E608126664E8} | c0a8-0057-12c3b913413-edf7e8ae-255fe- | MF-HQ-12649 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/00137/MF039 | 97200 | 67.7659 | 33.1889 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-098 | Ghazni Demining Project-01 |  |  |  |  | 1396 |  | {2F795B8F-75B7-4820-984C-E608126664E8} |  | High with Victim | High with Victims | High | 1204 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Qarabagh | Tamaki | {2F795B8F-75B7-4820-984C-E608126664E8} | c0a8-0057-12c3bb510ad-8df0f897-3b865- | MF-HQ-12663 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0613/00137/MF042 | 80000 | 67.7753 | 33.2016 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-098 | Ghazni Demining Project-01 |  |  |  |  | 1396 |  | {2F795B8F-75B7-4820-984C-E608126664E8} |  | High with Victim | High with Victims | High | 62 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Adro Kala | {2A6FCEFF-CACE-44AD-8150-523F09668B10} | c0a8-0057-12c3ba811c7-14df3af6-33d95- | MF-HQ-12532 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/06416/MF003 | 124250 | 68.3004 | 33.4559 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {2A6FCEFF-CACE-44AD-8150-523F09668B10} |  | Low | Agriculture Blocked | Substantial | 50 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Ayin | {20829B48-D9C3-418B-9352-435B77FF31DD} | c0a8-0057-12c3ba1cb08-e32c6601-300a5- | MF-HQ-12583 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/04916/MF002 | 210600 | 68.2906 | 33.4935 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-215 | Ghazni Demining Project-07 AT |  |  |  |  | 1399 |  | {20829B48-D9C3-418B-9352-435B77FF31DD} |  | Low | Agriculture Blocked | Substantial | 312 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Ayin | {20829B48-D9C3-418B-9352-435B77FF31DD} | c0a8-0057-12c3ba96fcb-4d86722e-34a38- | MF-HQ-12589 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/04916/MF001 | 105000 | 68.2906 | 33.4935 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-215 | Ghazni Demining Project-07 AT |  |  |  |  | 1399 |  | {20829B48-D9C3-418B-9352-435B77FF31DD} |  | Low | Agriculture Blocked | Substantial | 294 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Bagay | {943D23A6-590F-498E-93DA-2CF6B25FABF0} | c0a8-0057-12c3b9c85cf-f316252d-2cccb- | MF-HQ-12515 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/04875/MF016 | 147650 | 68.235 | 33.4058 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {943D23A6-590F-498E-93DA-2CF6B25FABF0} |  | Low | Agriculture Blocked | Substantial | 47 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Bazmohammad Kala | {A4B21C2D-59F6-40E8-9B83-F54D60DAC5B7} | c0a8-0057-12c3b9772d5-9664a434-2977b- | MF-SE-316 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0614/06366/MF(R020) | 80936 | 68.3028 | 33.4102 | Open | AT Only | AT Only | MineField |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {A4B21C2D-59F6-40E8-9B83-F54D60DAC5B7} |  | Low | Agriculture Blocked | Substantial | 49 | CHA | 5 |  |  | 2008-10-27 16:30 | No | Open
South East | Ghazni | Waghaz | Bazmohammad Kala | {A4B21C2D-59F6-40E8-9B83-F54D60DAC5B7} | c0a8-0057-12f0537b2b2-df50f6b1-136a-8 | MF-HQ-4145 | MCPA - Mine Clearance Planning Agency | AF/0613/06366/MF0020 | 20838.5 | 68.3006 | 33.4103 | Open | AT Only | AT Only | MineField |  | MBT Project-210 | Ghazni Demining Project-05 |  |  |  |  | 1398 |  | {A4B21C2D-59F6-40E8-9B83-F54D60DAC5B7} |  | Medium | Critical Infrastracture | Substantial | 49 | CHA | 3 |  |  | 1997-06-09 | No | Open
South East | Ghazni | Waghaz | Chahar Diwal | {E8F79EE7-0453-453F-9059-E70A4B9684D4} | c0a8-0057-12c3b98b633-423ca37f-2a4d3- | MF-HQ-12557 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/00724/MF021 | 240000 | 68.323 | 33.4208 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-210 | Ghazni Demining Project-05 |  |  |  |  | 1398 |  | {E8F79EE7-0453-453F-9059-E70A4B9684D4} |  | Medium | Critical Infrastracture | Substantial | 209 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Faizu Wal | {D61F55A6-CFBE-4583-8A5D-58702586F5B5} | c0a8-0057-12c3b85e92a-6afd21e0-1da58- | MF-HQ-12534 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/00662/MF019 | 136800 | 68.2692 | 33.3808 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {D61F55A6-CFBE-4583-8A5D-58702586F5B5} |  | Low | Agriculture Blocked | Substantial | 242 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Gholaman | {CE7DE3BC-A2BF-4C8C-9B39-C3BC492E1EE6} | c0a8-0057-12c3b805e48-b8bae2fa-19b0d- | MF-HQ-12543 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/04878/MF017 | 234800 | 68.2297 | 33.4274 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-215 | Ghazni Demining Project-07 AT |  |  |  |  | 1399 |  | {CE7DE3BC-A2BF-4C8C-9B39-C3BC492E1EE6} |  | Low | Agriculture Blocked | Substantial | 1113 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Godale Shamsher | {62B0E559-0FBE-4824-9A67-1544E80C5053} | c0a8-0057-12c3bb7039e-2bca82ee-3c9cd- | MF-HQ-12579 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/04925/MF011 | 252250 | 68.2748 | 33.4635 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-205 | Ghazni Demining Project-03 |  |  |  |  | 1397 |  | {62B0E559-0FBE-4824-9A67-1544E80C5053} |  | High with Victim | High with Victims | Substantial | 777 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Kabuli | {87D61993-5866-49E8-ADBD-8AD6C6D43E5C} | c0a8-0057-12c3baaee87-96585fff-357af- | MF-HQ-12528 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/06414/MF015 | 69000 | 68.3342 | 33.4301 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {87D61993-5866-49E8-ADBD-8AD6C6D43E5C} |  | Low | Agriculture Blocked | Substantial | 69 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Khadarwal | {8314F181-4F73-452B-A69D-FB69D2ABE60A} | c0a8-0057-12c3b7d4b8b-392ae61-178f8-7 | MF-HQ-12559 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/06363/MF006 | 90000 | 68.2848 | 33.3911 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {8314F181-4F73-452B-A69D-FB69D2ABE60A} |  | Low | Agriculture Blocked | Substantial | 47 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Khadarwal | {8314F181-4F73-452B-A69D-FB69D2ABE60A} | c0a8-0057-12c3b843ba1-3659e83d-1c72d- | MF-HQ-12563 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/06363/MF007 | 5000 | 68.2908 | 33.3925 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-210 | Ghazni Demining Project-05 |  |  |  |  | 1398 |  | {8314F181-4F73-452B-A69D-FB69D2ABE60A} |  | Medium | Agriculture Blocked | Substantial | 0 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Khadarwal | {8314F181-4F73-452B-A69D-FB69D2ABE60A} | c0a8-0057-12c3ba3fbe1-8fbd61cc-315a8- | MF-HQ-12567 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/06363/MF010 | 60000 | 68.2943 | 33.3946 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-210 | Ghazni Demining Project-05 |  |  |  |  | 1398 |  | {8314F181-4F73-452B-A69D-FB69D2ABE60A} |  | Medium | Critical Infrastracture | Substantial | 491 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Khadarwal | {8314F181-4F73-452B-A69D-FB69D2ABE60A} | c0a8-0057-12c3bb15c94-3647a0d4-3952d- | MF-HQ-12570 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/06363/MF009 | 140000 | 68.2943 | 33.3946 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-210 | Ghazni Demining Project-05 |  |  |  |  | 1398 |  | {8314F181-4F73-452B-A69D-FB69D2ABE60A} |  | Medium | Critical Infrastracture | Substantial | 569 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Khadarwal | {8314F181-4F73-452B-A69D-FB69D2ABE60A} | c0a8-0057-12c3bb70581-a4b232cb-3c9e3- | MF-HQ-12558 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/06363/MF008 | 2500 | 68.2811 | 33.3922 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {8314F181-4F73-452B-A69D-FB69D2ABE60A} |  | Low | Agriculture Blocked | Substantial | 32 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Mirzawal | {29204533-B60A-4634-8EBD-9CB0D9B69812} | c0a8-0057-12c3bad71a4-aefaff77-36f97- | MF-HQ-12524 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/06350/MF004 | 107250 | 68.2987 | 33.3744 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-210 | Ghazni Demining Project-05 |  |  |  |  | 1398 |  | {29204533-B60A-4634-8EBD-9CB0D9B69812} |  | Medium | Critical Infrastracture | Substantial | 134 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Myadad Kala | {BF2FF64B-2F6B-470C-AB66-9407794F0EBB} | c0a8-0057-12c3b9306a4-79f6f1a-268ea-f | MF-HQ-12575 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/06363/MF013 | 120000 | 68.2502 | 33.3715 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {BF2FF64B-2F6B-470C-AB66-9407794F0EBB} |  | Low | Agriculture Blocked | Substantial | 11 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Nazarkhan Kala | {C97CB14A-FD77-447D-8679-ABC4755A3700} | c0a8-0057-12c3b9e378a-b627ea90-2dd74- | MF-HQ-12521 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/06343/MF018 | 52500 | 68.2683 | 33.4177 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-260 | Ghazni Demining Project-10 |  |  |  |  | 1401 |  | {C97CB14A-FD77-447D-8679-ABC4755A3700} |  | Low | Other | Substantial | 12 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Omarwal | {9544A0B3-AC62-4D9A-8E43-3EB6F408D4E9} | c0a8-0057-12c3b89332c-5ce2dfa3-1ff4e- | MF-HQ-12518 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/06334/MF012 | 74550 | 68.288 | 33.4058 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-210 | Ghazni Demining Project-05 |  |  |  |  | 1398 |  | {9544A0B3-AC62-4D9A-8E43-3EB6F408D4E9} |  | Medium | Agriculture Blocked | Substantial | 157 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Qala-i-Mohammad Khan | {A8D9CAA2-8BB9-4FFA-97EA-57C011EECC0F} | c0a8-0057-12c3b975cc7-d9af4f8c-2968c- | MF-HQ-12540 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/04922/MF014 | 198000 | 68.2533 | 33.4653 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-098 | Ghazni Demining Project-01 |  |  |  |  | 1396 |  | {A8D9CAA2-8BB9-4FFA-97EA-57C011EECC0F} |  | High with Victim | High with Victims | Substantial | 772 | SHA | 1 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Waghaz | Sa'adat Kala | {7B33B2BB-4A50-4BF8-8018-AA169FB14A39} | c0a8-0057-12c3b85372c-14dd3922-1d2aa- | MF-HQ-12512 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0619/04880/MF005 | 116000 | 68.2629 | 33.4365 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-210 | Ghazni Demining Project-05 |  |  |  |  | 1398 |  | {7B33B2BB-4A50-4BF8-8018-AA169FB14A39} |  | Medium | Critical Infrastracture | Substantial | 730 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Alikhankhel | {49D94754-6137-48E9-A62F-CCFB29ADEEAB} | c0a8-0057-12c3b9b959c-4f14bf38-2c2f0- | MF-SE-313 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0602/05034/MF(R007) | 42409 | 68.3225 | 33.5611 | Open | AT Only | AT Only | MineField |  | MBT Project-211 | Ghazni Demining Project-05 AT |  |  |  |  | 1398 |  | {49D94754-6137-48E9-A62F-CCFB29ADEEAB} |  | Medium | Critical Infrastracture | Substantial | 887 | CHA | 3 |  |  | 2008-10-27 16:30 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Alikhankhel | {49D94754-6137-48E9-A62F-CCFB29ADEEAB} | c0a8-0057-12f052e887e-5da56dcd-1273-e | MF-HQ-6602 | MCPA - Mine Clearance Planning Agency | AF/0606/05034/MF0005 | 79007 | 68.3279 | 33.5677 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-215 | Ghazni Demining Project-07 AT |  |  |  |  | 1399 |  | {49D94754-6137-48E9-A62F-CCFB29ADEEAB} |  | Low | Agriculture Blocked | Substantial | 48 | CHA | 4 |  |  | 1999-10-16 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Alikhankhel | {49D94754-6137-48E9-A62F-CCFB29ADEEAB} | c0a8-0057-12f05386942-f1849985-138e-6 | MF-HQ-6603 | MCPA - Mine Clearance Planning Agency | AF/0606/05034/MF0006 | 85911 | 68.3258 | 33.5689 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-215 | Ghazni Demining Project-07 AT |  |  |  |  | 1399 |  | {49D94754-6137-48E9-A62F-CCFB29ADEEAB} |  | Low | Agriculture Blocked | Substantial | 85 | CHA | 4 |  |  | 1999-10-24 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Alikhankhel | {49D94754-6137-48E9-A62F-CCFB29ADEEAB} | c0a8-0057-12f053913b2-6e62ba8d-13a9-c | MF-HQ-6604 | MCPA - Mine Clearance Planning Agency | AF/0606/05034/MF0007 | 36735 | 68.3309 | 33.5658 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-211 | Ghazni Demining Project-05 AT |  |  |  |  | 1398 |  | {49D94754-6137-48E9-A62F-CCFB29ADEEAB} |  | Medium | Agriculture Blocked | Substantial | 143 | CHA | 3 |  |  | 1999-10-28 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Ashraf Khel | {03B320D0-D1A2-4BA6-AF60-C5AEE7D8F990} | c0a8-0057-12c3b973866-36367e4a-2951c- | MF-HQ-12714 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00004/MF028 | 121500 | 68.2512 | 33.5606 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-215 | Ghazni Demining Project-07 AT |  |  |  |  | 1399 |  | {03B320D0-D1A2-4BA6-AF60-C5AEE7D8F990} |  | Low | Agriculture Blocked | Substantial | 1067 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Bakhshay | {9BF527A2-BFBB-4C92-9FBB-1A868121102C} | c0a8-0057-12c3bb3a15b-23de5464-3aaf1- | MF-HQ-12727 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/04939/MF013 | 94600 | 68.277 | 33.5029 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {9BF527A2-BFBB-4C92-9FBB-1A868121102C} |  | Low | Agriculture Blocked | Substantial | 225 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Barik | {655683C8-FFA7-455B-8D9B-99B30415C73E} | c0a8-0057-12c3ba9a480-984b4e06-34c1d- | MF-HQ-12694 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00305/MF048 | 145200 | 68.302 | 33.5887 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {655683C8-FFA7-455B-8D9B-99B30415C73E} |  | Low | Agriculture Blocked | Substantial | 76 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Baryam | {A718F45F-0CBE-477D-A9A8-E62054785AF7} | c0a8-0057-12c3ba8ee8c-bf4ef0bf-3458f- | MF-HQ-12752 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00502/MF001 | 212625 | 68.3087 | 33.5079 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-211 | Ghazni Demining Project-05 AT |  |  |  |  | 1398 |  | {A718F45F-0CBE-477D-A9A8-E62054785AF7} |  | Medium | Critical Infrastracture | Substantial | 841 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Chaharqal'a | {641F7217-CD8D-4253-8D7C-B7E1A9168708} | c0a8-0057-12c3b913606-a823b123-25612- | MF-HQ-12722 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05030/MF049 | 131500 | 68.3011 | 33.5592 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-205 | Ghazni Demining Project-03 |  |  |  |  | 1397 |  | {641F7217-CD8D-4253-8D7C-B7E1A9168708} |  | High with Victim | High with Victims | Substantial | 168 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Chobtrash | {8344BD13-B3C4-4A80-A66C-72F19FD39F99} | c0a8-0057-12c3b7dacbc-4180c1e0-17d28- | MF-HQ-12750 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00399/MF035 | 222862 | 68.2892 | 33.5023 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-211 | Ghazni Demining Project-05 AT |  |  |  |  | 1398 |  | {8344BD13-B3C4-4A80-A66C-72F19FD39F99} |  | Medium | Critical Infrastracture | Substantial | 81 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Chobtrash | {8344BD13-B3C4-4A80-A66C-72F19FD39F99} | c0a8-0057-12c3b96d5d0-ab378af7-29101- | MF-HQ-12745 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00399/MF036 | 210000 | 68.2867 | 33.5021 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {8344BD13-B3C4-4A80-A66C-72F19FD39F99} |  | Low | Agriculture Blocked | Substantial | 304 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Deh Essa | {EF5EEBBB-EFCA-4EDA-B408-0566D4FD9C60} | c0a8-0057-12c3bb736be-251658c5-3cba2- | MF-HQ-12730 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00744/MF020 | 210000 | 68.21 | 33.5661 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-211 | Ghazni Demining Project-05 AT |  |  |  |  | 1398 |  | {EF5EEBBB-EFCA-4EDA-B408-0566D4FD9C60} |  | Medium | Critical Infrastracture | Substantial | 215 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Dehe Mulla | {F64AD571-DFA2-4A0A-B1E9-5FC5F91E8F3D} | c0a8-0057-12c3b7f6edd-e25116aa-1908e- | MF-HQ-12577 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05031/MF027 | 325181 | 68.32 | 33.5425 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {F64AD571-DFA2-4A0A-B1E9-5FC5F91E8F3D} |  | Low | Agriculture Blocked | Substantial | 232 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Dehe Mulla | {F64AD571-DFA2-4A0A-B1E9-5FC5F91E8F3D} | c0a8-0057-12c3ba24a43-f9f0e3dd-3054f- | MF-HQ-12574 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05031/MF026 | 281136 | 68.32 | 33.5425 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-215 | Ghazni Demining Project-07 AT |  |  |  |  | 1399 |  | {F64AD571-DFA2-4A0A-B1E9-5FC5F91E8F3D} |  | Low | Agriculture Blocked | Substantial | 169 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Dehe Mulla | {F64AD571-DFA2-4A0A-B1E9-5FC5F91E8F3D} | c0a8-0057-12c3baff435-3cb994f7-387c0- | MF-HQ-12582 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05031/MF025 | 200000 | 68.326 | 33.536 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {F64AD571-DFA2-4A0A-B1E9-5FC5F91E8F3D} |  | Low | Agriculture Blocked | Substantial | 95 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Dehe Mulla | {F64AD571-DFA2-4A0A-B1E9-5FC5F91E8F3D} | c0a8-0057-12c3bb2f862-3b737e55-3a495- | MF-HQ-12587 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05031/MF024 | 65100 | 68.313 | 33.5488 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-215 | Ghazni Demining Project-07 AT |  |  |  |  | 1399 |  | {F64AD571-DFA2-4A0A-B1E9-5FC5F91E8F3D} |  | Low | Agriculture Blocked | Substantial | 976 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Dehe Mulla | {F64AD571-DFA2-4A0A-B1E9-5FC5F91E8F3D} | c0a8-0057-12c3bb426de-b27bbbc2-3afdb- | MF-HQ-12585 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05031/MF023 | 310500 | 68.3129 | 33.5451 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-211 | Ghazni Demining Project-05 AT |  |  |  |  | 1398 |  | {F64AD571-DFA2-4A0A-B1E9-5FC5F91E8F3D} |  | Medium | Critical Infrastracture | Substantial | 1107 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Gulistan | {4F6692A2-3812-4CDD-870C-FDE9BA44E857} | c0a8-0057-12c3b97c6bc-70a3ed92-29af5- | MF-HQ-12766 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00236/MF0051 | 225000 | 68.2838 | 33.5053 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-212 | Ghazni Demining Project-06 |  |  |  |  | 1398 |  | {4F6692A2-3812-4CDD-870C-FDE9BA44E857} |  | Medium | Critical Infrastracture | Substantial | 320 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Gulzar Khel | {B643D7C5-B623-442C-B4BF-B327EC031EBD} | c0a8-0057-12c3ba4438a-62a8c7c1-31862- | MF-HQ-12668 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00558/MF007 | 160000 | 68.3233 | 33.5507 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-253 | Ghazni Demining Project-08 AT |  |  |  |  | 1400 |  | {B643D7C5-B623-442C-B4BF-B327EC031EBD} |  | Low | Agriculture Blocked | Substantial | 397 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Kajikhel | {E91B32E0-AFBC-479E-AC58-E15137D1BF16} | c0a8-0057-12c3ba13bc6-c6c190e4-2fb13- | MF-HQ-12682 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/04100/MF019 | 419750 | 68.3467 | 33.5515 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {E91B32E0-AFBC-479E-AC58-E15137D1BF16} |  | High with Victim | High with Victims | Substantial | 1240 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Kalakhel (2) | {BEAFE38C-7962-446E-AD5D-96396500CA4E} | c0a8-0057-12c3b89641a-5df80648-20139- | MF-HQ-12768 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05008/MF008 | 180000 | 68.2422 | 33.5609 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-212 | Ghazni Demining Project-06 |  |  |  |  | 1398 |  | {BEAFE38C-7962-446E-AD5D-96396500CA4E} |  | Medium | Critical Infrastracture | Substantial | 32 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Karak | {2F3857B8-C0DF-482D-B2C6-CB8B4A725379} | c0a8-0057-12c3bb6be46-cefc590a-3c763- | MF-HQ-12724 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00135/MF030 | 102400 | 68.2937 | 33.5448 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-212 | Ghazni Demining Project-06 |  |  |  |  | 1398 |  | {2F3857B8-C0DF-482D-B2C6-CB8B4A725379} |  | Medium | Critical Infrastracture | Substantial | 23 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Khaki Sharbat | {2B38A81D-9AC9-4C3E-9DD0-AA493D82408A} | c0a8-0057-12c3b857c36-1857165-1d5bf-3 | MF-HQ-12761 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05035/MF031 | 207000 | 68.2912 | 33.5671 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-253 | Ghazni Demining Project-08 AT |  |  |  |  | 1400 |  | {2B38A81D-9AC9-4C3E-9DD0-AA493D82408A} |  | Low | Agriculture Blocked | Substantial | 295 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Khaki Sharbat | {2B38A81D-9AC9-4C3E-9DD0-AA493D82408A} | c0a8-0057-12c3b90b615-29de58eb-250de- | MF-HQ-12759 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05035/MF032 | 345100 | 68.2931 | 33.5676 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-212 | Ghazni Demining Project-06 |  |  |  |  | 1398 |  | {2B38A81D-9AC9-4C3E-9DD0-AA493D82408A} |  | Medium | Critical Infrastracture | Substantial | 542 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Khwajakhel | {2C47EBD5-4CED-4A90-930C-25746870AA96} | c0a8-0057-12c3b87dbbd-d4d3bc97-1f020- | MF-HQ-12673 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/04940/MF034 | 113100 | 68.2662 | 33.5121 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-253 | Ghazni Demining Project-08 AT |  |  |  |  | 1400 |  | {2C47EBD5-4CED-4A90-930C-25746870AA96} |  | Low | Agriculture Blocked | Substantial | 367 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Khwajakhel | {2C47EBD5-4CED-4A90-930C-25746870AA96} | c0a8-0057-12c3b9404a3-47cd40fb-27384- | MF-HQ-12676 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/04940/MF033 | 327037 | 68.2786 | 33.5096 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-253 | Ghazni Demining Project-08 AT |  |  |  |  | 1400 |  | {2C47EBD5-4CED-4A90-930C-25746870AA96} |  | Low | Agriculture Blocked | Substantial | 360 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Pir Aka | {CEEA0204-111E-4AA9-8808-45145F8515CE} | c0a8-0057-12c3b8d7446-9c9a512f-22df7- | MF-HQ-12731 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05033/MF018 | 190600 | 68.3184 | 33.613 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-253 | Ghazni Demining Project-08 AT |  |  |  |  | 1400 |  | {CEEA0204-111E-4AA9-8808-45145F8515CE} |  | Low | Agriculture Blocked | Substantial | 1107 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qal'a-i Khasha | {6D1E8829-EABA-4B97-A61A-93A11D9B9741} | c0a8-0057-12c3b8e4ad4-6f012e0b-237c0- | MF-HQ-12763 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05037/MF0043 | 104200 | 68.3114 | 33.5989 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-253 | Ghazni Demining Project-08 AT |  |  |  |  | 1400 |  | {6D1E8829-EABA-4B97-A61A-93A11D9B9741} |  | Low | Agriculture Blocked | Substantial | 252 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qal'a-i Khasha | {6D1E8829-EABA-4B97-A61A-93A11D9B9741} | c0a8-0057-12c3b9267ee-fae3522c-26265- | MF-HQ-12760 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05037/MF0040 | 72800 | 68.3114 | 33.5989 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {6D1E8829-EABA-4B97-A61A-93A11D9B9741} |  | Low | Agriculture Blocked | Substantial | 96 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qal'a-i Khasha | {6D1E8829-EABA-4B97-A61A-93A11D9B9741} | c0a8-0057-12c3bb221f3-3f16d2fd-39cd2- | MF-HQ-12755 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05037/MF0042 | 81500 | 68.3038 | 33.5955 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-257 | Ghazni Demining Project-09 AT |  |  |  |  | 1400 |  | {6D1E8829-EABA-4B97-A61A-93A11D9B9741} |  | Low | Agriculture Blocked | Substantial | 293 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qal'a-i Khasha | {6D1E8829-EABA-4B97-A61A-93A11D9B9741} | c0a8-0057-12c3bb2db60-81f28e5f-3a34c- | MF-HQ-12754 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05037/MF0044 | 91500 | 68.3082 | 33.6013 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-257 | Ghazni Demining Project-09 AT |  |  |  |  | 1400 |  | {6D1E8829-EABA-4B97-A61A-93A11D9B9741} |  | Low | Agriculture Blocked | Substantial | 77 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qal'a-i Kuhna | {965131A0-0423-417B-AB21-1CE1D8CE8E76} | c0a8-0057-12c3b81fd6f-66acf105-1ad83- | MF-HQ-12726 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05038/MF009 | 117250 | 68.3367 | 33.5542 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-212 | Ghazni Demining Project-06 |  |  |  |  | 1398 |  | {965131A0-0423-417B-AB21-1CE1D8CE8E76} |  | Medium | Critical Infrastracture | Substantial | 239 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qalai Nazar | {F52D0EE6-B499-416F-A0B9-089509AFEB31} | c0a8-0057-12c3b83f9b3-e6c2b963-1c444- | MF-HQ-12743 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00769/MF022 | 93750 | 68.3008 | 33.6155 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-213 | Ghazni Demining Project-06 AT |  |  |  |  | 1398 |  | {F52D0EE6-B499-416F-A0B9-089509AFEB31} |  | Medium | Critical Infrastracture | Substantial | 1030 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qalai Nazar | {F52D0EE6-B499-416F-A0B9-089509AFEB31} | c0a8-0057-12c3b924929-2c6eef03-26139- | MF-HQ-12736 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00769/MF021 | 103500 | 68.3004 | 33.614 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-213 | Ghazni Demining Project-06 AT |  |  |  |  | 1398 |  | {F52D0EE6-B499-416F-A0B9-089509AFEB31} |  | Medium | Critical Infrastracture | Substantial | 1030 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qal'a-i Surkh | {603AE98C-3F0D-4910-86EA-84B5C525C807} | c0a8-0057-12c3baa7f14-2b66bd3-353e5-d | MF-HQ-12698 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/04099/MF050 | 162250 | 68.3599 | 33.5682 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-257 | Ghazni Demining Project-09 AT |  |  |  |  | 1400 |  | {603AE98C-3F0D-4910-86EA-84B5C525C807} |  | Low | Agriculture Blocked | Substantial | 3579 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qala-I-Karim | {73FAD44D-388C-44BE-BDF0-FF2EBE22A7A1} | c0a8-0057-12c3b98f498-cfd317eb-2a76a- | MF-HQ-12729 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00351/MF0046 | 114700 | 68.3306 | 33.5896 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {73FAD44D-388C-44BE-BDF0-FF2EBE22A7A1} |  | Low | Agriculture Blocked | Substantial | 71 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qal'a-i-Sayd Alem | {AD07E845-E828-4C15-B01F-3388133DA585} | c0a8-0057-12c3b8090fb-f19a0e81-19d76- | MF-HQ-12733 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05039/MF002 | 103800 | 68.3526 | 33.5871 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {AD07E845-E828-4C15-B01F-3388133DA585} |  | Low | Critical Infrastracture | Substantial | 318 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qal'a-i-Sayd Alem | {AD07E845-E828-4C15-B01F-3388133DA585} | c0a8-0057-12c3b8b809a-89d509da-21874- | MF-HQ-12742 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05039/MF005 | 73200 | 68.3399 | 33.5838 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-257 | Ghazni Demining Project-09 AT |  |  |  |  | 1400 |  | {AD07E845-E828-4C15-B01F-3388133DA585} |  | Low | Agriculture Blocked | Substantial | 66 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qal'a-i-Sayd Alem | {AD07E845-E828-4C15-B01F-3388133DA585} | c0a8-0057-12c3b8c3611-809bd9d-22088-e | MF-HQ-12738 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05039/MF004 | 107100 | 68.3526 | 33.5871 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {AD07E845-E828-4C15-B01F-3388133DA585} |  | Low | Critical Infrastracture | Substantial | 318 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qal'a-i-Sayd Alem | {AD07E845-E828-4C15-B01F-3388133DA585} | c0a8-0057-12c3b9fbe61-ae86a03-2ec57-8 | MF-HQ-12749 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05039/MF006 | 110500 | 68.3268 | 33.574 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {AD07E845-E828-4C15-B01F-3388133DA585} |  | Low | Agriculture Blocked | Substantial | 85 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qal'a-i-Sayd Alem | {AD07E845-E828-4C15-B01F-3388133DA585} | c0a8-0057-12c3ba21e73-2171ff6d-303bd- | MF-HQ-12747 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05039/MF003 | 75600 | 68.3385 | 33.5833 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-257 | Ghazni Demining Project-09 AT |  |  |  |  | 1400 |  | {AD07E845-E828-4C15-B01F-3388133DA585} |  | Low | Agriculture Blocked | Substantial | 566 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qalandarkhel | {8AE69683-BF63-4F9D-AE83-F0EF326828A7} | c0a8-0057-12c3b7f390f-ad7175cf-18e02- | MF-HQ-12568 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05011/MF011 | 337500 | 68.2388 | 33.5664 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-257 | Ghazni Demining Project-09 AT |  |  |  |  | 1400 |  | {8AE69683-BF63-4F9D-AE83-F0EF326828A7} |  | Low | Comunity Centers | Substantial | 1077 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qalandarkhel | {8AE69683-BF63-4F9D-AE83-F0EF326828A7} | c0a8-0057-12c3baa9023-c47b470b-3547f- | MF-HQ-12564 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05011/MF010 | 110000 | 68.2388 | 33.5664 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-257 | Ghazni Demining Project-09 AT |  |  |  |  | 1400 |  | {8AE69683-BF63-4F9D-AE83-F0EF326828A7} |  | Low | Comunity Centers | Substantial | 1849 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qala-Wali | {50C3C0B3-FEB2-4173-8024-2E0705368A7E} | c0a8-0057-12c3ba52ff8-6b36be7b-32161- | MF-HQ-12740 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00240/MF052 | 155950 | 68.3462 | 33.5664 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-257 | Ghazni Demining Project-09 AT |  |  |  |  | 1400 |  | {50C3C0B3-FEB2-4173-8024-2E0705368A7E} |  | Low | Agriculture Blocked | Substantial | 175 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qarya-i-Hamada | {750CC8BE-52D9-4D77-A8F5-9BCC07667096} | c0a8-0057-12c3bb0e15e-3115f557-3907b- | MF-HQ-12719 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/04942/MF0047 | 171000 | 68.2681 | 33.5608 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {750CC8BE-52D9-4D77-A8F5-9BCC07667096} |  | Low | Agriculture Blocked | Substantial | 151 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qazi | {731522C7-90F0-4F2D-A869-21C4A4B86AB3} | c0a8-0057-12c3b9a1250-aef81d47-2b337- | MF-HQ-12703 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00349/MF045 | 128100 | 68.2241 | 33.5685 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-213 | Ghazni Demining Project-06 AT |  |  |  |  | 1398 |  | {731522C7-90F0-4F2D-A869-21C4A4B86AB3} |  | Medium | Critical Infrastracture | Substantial | 388 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qoli chirek | {D8D4A7EE-3949-4B88-93AE-CFB4449CB1EB} | c0a8-0057-12c3b7c0f68-46912c61-16a7c- | MF-HQ-12612 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00670/MF016 | 66700 | 68.2741 | 33.5491 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {D8D4A7EE-3949-4B88-93AE-CFB4449CB1EB} |  | Low | Agriculture Blocked | Substantial | 39 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qoli chirek | {D8D4A7EE-3949-4B88-93AE-CFB4449CB1EB} | c0a8-0057-12c3b80c3ec-cb233007-19f99- | MF-HQ-12607 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00670/MF017 | 62400 | 68.2763 | 33.5498 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {D8D4A7EE-3949-4B88-93AE-CFB4449CB1EB} |  | Low | Agriculture Blocked | Substantial | 20 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qoli chirek | {D8D4A7EE-3949-4B88-93AE-CFB4449CB1EB} | c0a8-0057-12c3b8a5614-3baf4930-20ba7- | MF-HQ-12619 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00670/MF014 | 99950 | 68.2746 | 33.5513 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-257 | Ghazni Demining Project-09 AT |  |  |  |  | 1400 |  | {D8D4A7EE-3949-4B88-93AE-CFB4449CB1EB} |  | Low | Agriculture Blocked | Substantial | 244 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Qoli chirek | {D8D4A7EE-3949-4B88-93AE-CFB4449CB1EB} | c0a8-0057-12c3ba1dc27-c3c08fba-30157- | MF-HQ-12611 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00670/MF015 | 58650 | 68.2766 | 33.5466 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {D8D4A7EE-3949-4B88-93AE-CFB4449CB1EB} |  | Low | Agriculture Blocked | Substantial | 39 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Shaikh Agha | {069980B5-AE5A-46D1-A519-D10434F99669} | c0a8-0057-12c3ba30066-39d80cbb-30c35- | MF-HQ-12708 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00011/MF029 | 148000 | 68.3396 | 33.6047 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-259 | Ghazni Demining Project-09 |  |  |  |  | 1400 |  | {069980B5-AE5A-46D1-A519-D10434F99669} |  | Low | Agriculture Blocked | Substantial | 110 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Talasanaye Bala | {8133CE1C-0BDB-430A-BB91-B2C83C66FA95} | c0a8-0057-12c3b7c6a82-146279ce-16ea4- | MF-HQ-12600 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05028/MF039 | 116375 | 68.298 | 33.5172 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-213 | Ghazni Demining Project-06 AT |  |  |  |  | 1398 |  | {8133CE1C-0BDB-430A-BB91-B2C83C66FA95} |  | Medium | Critical Infrastracture | Substantial | 183 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Talasanaye Bala | {8133CE1C-0BDB-430A-BB91-B2C83C66FA95} | c0a8-0057-12c3b804d09-cffb8ad9-19a51- | MF-HQ-12591 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05028/MF038 | 200000 | 68.298 | 33.5172 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-213 | Ghazni Demining Project-06 AT |  |  |  |  | 1398 |  | {8133CE1C-0BDB-430A-BB91-B2C83C66FA95} |  | Medium | Critical Infrastracture | Substantial | 1087 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Talasanaye Bala | {8133CE1C-0BDB-430A-BB91-B2C83C66FA95} | c0a8-0057-12c3b941017-feb97912-273f1- | MF-HQ-12595 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/05028/MF037 | 210000 | 68.298 | 33.5172 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-213 | Ghazni Demining Project-06 AT |  |  |  |  | 1398 |  | {8133CE1C-0BDB-430A-BB91-B2C83C66FA95} |  | Medium | Critical Infrastracture | Substantial | 1658 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Wali Muhammadi Shahid | Yatimak | {8D6FAC6B-AD82-4D64-899E-7A1B28F63903} | c0a8-0057-12c3b8c6396-99dff15-2226e-5 | MF-HQ-12735 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0620/00924/MF012 | 205200 | 68.3604 | 33.56 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-213 | Ghazni Demining Project-06 AT |  |  |  |  | 1398 |  | {8D6FAC6B-AD82-4D64-899E-7A1B28F63903} |  | Medium | Critical Infrastracture | Substantial | 243 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Zana Khan | Gurbat | {5047107B-B81D-4284-9594-954079EF06FB} | c0a8-0057-12c3b8e4cc7-9690f50b-237d1- | MF-HQ-12510 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0616/04145/MF002 | 75600 | 68.7037 | 33.618 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-205 | Ghazni Demining Project-03 |  |  |  |  | 1397 |  | {5047107B-B81D-4284-9594-954079EF06FB} |  | High with Victim | High with Victims | Substantial | 216 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Zana Khan | Kodale | {5D15D7D8-775B-4F80-A86C-2659FE0A4210} | c0a8-0057-12c3b9464d6-d442190d-2775b- | MF-HQ-12501 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0616/04119/MF003 | 201600 | 68.5648 | 33.6443 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-205 | Ghazni Demining Project-03 |  |  |  |  | 1397 |  | {5D15D7D8-775B-4F80-A86C-2659FE0A4210} |  | High with Victim | High with Victims | Substantial | 16 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Ghazni | Zana Khan | Kodale | {5D15D7D8-775B-4F80-A86C-2659FE0A4210} | c0a8-0057-12c3bb3aadd-5788d8e7-3ab46- | MF-HQ-12503 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0616/04119/MF004 | 201600 | 68.5648 | 33.6443 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-205 | Ghazni Demining Project-03 |  |  |  |  | 1397 |  | {5D15D7D8-775B-4F80-A86C-2659FE0A4210} |  | High with Victim | High with Victims | Substantial | 16 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Khost | Gurbuz | Bagikhel | {0C7A67BC-1DBA-4772-916E-A7BFF6CC4B62} | c0a8-0009-13e8832139c-3d8ebb9d-23d9-f | Hz-ID-17867 | MCPA - Mine Clearance Planning Agency | AF/3211/07928/MF0122 | 35752 | 69.9567 | 33.2433 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {0C7A67BC-1DBA-4772-916E-A7BFF6CC4B62} |  | High with Victim | High with Victims | Substantial | 40 | CHA | 1 |  |  | 2013-03-24 16:30 | No | Planned
South East | Khost | Gurbuz | Bagikhel | {0C7A67BC-1DBA-4772-916E-A7BFF6CC4B62} | c0a8-00f6-135e1b65012-b1d05415-b0d8-3 | MF-16719 | DDG - Danish Demining Group | AF/3211/07928/MF0112 | 85512 | 69.9727 | 33.2641 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {0C7A67BC-1DBA-4772-916E-A7BFF6CC4B62} |  | High with Victim | High with Victims | Substantial | 9 | CHA | 1 |  |  | 2012-01-16 16:30 | No | Planned
South East | Khost | Gurbuz | Bori Kalay | {63FE1849-A2C8-4E78-86F3-99942DDB62B4} | c0a8-0009-13e884645a8-865faa58-266a-2 | Hz-ID-17856 | MCPA - Mine Clearance Planning Agency | AF/3211/07910/MF0117 | 17338 | 69.9702 | 33.2198 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {63FE1849-A2C8-4E78-86F3-99942DDB62B4} |  | Low | Critical Infrastracture | Substantial | 50 | CHA | 5 |  |  | 2013-03-12 16:30 | No | Planned
South East | Khost | Gurbuz | Bori Kalay | {63FE1849-A2C8-4E78-86F3-99942DDB62B4} | c0a8-0009-13e88498b3a-cf4f41e6-26f3-a | Hz-ID-17854 | MCPA - Mine Clearance Planning Agency | AF/3211/07910/MF0116 | 48118 | 69.9449 | 33.2293 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {63FE1849-A2C8-4E78-86F3-99942DDB62B4} |  | Medium | Critical Infrastracture | Substantial | 164 | CHA | 5 |  |  | 2013-03-09 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0009-13e8836cbc1-569ddad7-23fa-1 | Hz-ID-17864 | MCPA - Mine Clearance Planning Agency | AF/3211/07913/MF0121 | 32491 | 69.9441 | 33.2356 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 94 | CHA | 1 |  |  | 2013-03-19 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0009-13e883a9e98-7cb06535-241a-1 | Hz-ID-17862 | MCPA - Mine Clearance Planning Agency | AF/3211/07913/MF0120 | 10133 | 69.9514 | 33.2398 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 120 | CHA | 1 |  |  | 2013-03-18 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0009-13e883e4d5a-129ef0ff-2536-9 | Hz-ID-17860 | MCPA - Mine Clearance Planning Agency | AF/3211/07913/MF0119 | 31537 | 69.9358 | 33.2369 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 267 | CHA | 1 |  |  | 2013-03-16 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0009-1479a21b322-7f229fdb-112-e7 | Hz-ID-18872 | HT - HALO TRUST | H/8817 | 72862 | 69.923 | 33.2323 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 48 | CHA | 1 |  |  | 2014-07-07 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0009-1479a2210d2-c8533349-135-d0 | Hz-ID-18868 | HT - HALO TRUST | H/8813 | 84184 | 69.923 | 33.2323 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 72 | CHA | 1 |  |  | 2014-07-06 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0009-1479a26f7f6-f195c822-159-de | Hz-ID-18869 | HT - HALO TRUST | H/8814 | 143192 | 69.923 | 33.2323 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 136 | CHA | 1 |  |  | 2014-07-06 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0009-1479a30fc61-cb9b9652-17e-19 | Hz-ID-18873 | HT - HALO TRUST | H/8818 | 113624 | 69.923 | 33.2323 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 34 | CHA | 1 |  |  | 2014-07-08 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0009-1479a338b93-5a47f58-1a2-c63 | Hz-ID-18874 | HT - HALO TRUST | H/8819 | 132628 | 69.923 | 33.2323 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 48 | CHA | 1 |  |  | 2014-07-09 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0009-1479a33a46b-39f9ac27-1c6-87 | Hz-ID-18871 | HT - HALO TRUST | H/8816 | 136334 | 69.923 | 33.2323 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 170 | CHA | 1 |  |  | 2014-07-08 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0009-1479a378337-df48d49f-1e8-eb | Hz-ID-18875 | HT - HALO TRUST | H/8820 | 71063 | 69.923 | 33.2323 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 34 | CHA | 1 |  |  | 2014-07-09 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0009-147af5d1b05-d61a2610-634-cc | Hz-ID-18870 | HT - HALO TRUST | H/8815 | 100000 | 69.923 | 33.2323 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 237 | CHA | 1 |  |  | 2014-07-07 16:30 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0057-12c3b6e1d22-a7122336-c511-5 | MF-HQ-14431 | DDG - Danish Demining Group | AF/3211/07913/MF0109 | 70955 | 69.9354 | 33.2278 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} |  | High with Victim | High with Victims | Substantial | 1873 | CHA | 1 |  |  | 2010-04-11 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-0057-12c3b75334e-114e48f7-11abe- | MF-HQ-14423 | DDG - Danish Demining Group | AF/3211/07913/MF0107 | 10373 | 69.9213 | 33.2364 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} | , | High with Victim | High with Victims | Substantial | 208 | CHA | 1 |  |  | 2010-04-06 | No | Planned
South East | Khost | Gurbuz | Borikhel | {7D760206-CFAD-4987-928B-12DD5BA8C534} | c0a8-008e-1328f9ce725-a26443f7-1de0-d | MF-15592 | DDG - Danish Demining Group | AF/3211/07913/MF0111 | 73331 | 69.9297 | 33.2435 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {7D760206-CFAD-4987-928B-12DD5BA8C534} | , | High with Victim | High with Victims | Substantial | 163 | CHA | 1 |  |  | 2011-01-19 16:30 | No | Planned
South East | Khost | Gurbuz | Lezi Kalay | {F60ACAF4-C4D8-4926-90ED-6CD6CB07D528} | c0a8-0057-12c3b8092ee-8bcc1c71-19d89- | MF-HQ-14182 | MCPA - Mine Clearance Planning Agency | AF/3211/07890/MF0104 | 55825 | 69.8625 | 33.2012 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {F60ACAF4-C4D8-4926-90ED-6CD6CB07D528} |  | High Requested | Resettlment/Local Request | Substantial | 201 | CHA | 5 |  |  | 2010-02-10 | No | Planned
South East | Khost | Gurbuz | Lezi Kalay | {F60ACAF4-C4D8-4926-90ED-6CD6CB07D528} | c0a8-0057-12c3ba7e867-baf59e61-33c11- | MF-HQ-14183 | MCPA - Mine Clearance Planning Agency | AF/3203/07890/MF0105 | 29772 | 69.8607 | 33.2006 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {F60ACAF4-C4D8-4926-90ED-6CD6CB07D528} |  | High Requested | Resettlment/Local Request | Substantial | 18 | CHA | 5 |  |  | 2010-02-14 | No | Planned
South East | Khost | Gurbuz | Tawda China | {431A6D99-5746-41B8-A1EE-34669A9E193E} | c0a8-0009-13dcea05913-c1bf2bf7-1c5-33 | Hz-ID-17771 | MCPA - Mine Clearance Planning Agency | AF/3211/07927/MF0113 | 94485 | 69.9818 | 33.2603 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {431A6D99-5746-41B8-A1EE-34669A9E193E} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2013-02-16 16:30 | No | Planned
South East | Khost | Gurbuz | Tawda China | {431A6D99-5746-41B8-A1EE-34669A9E193E} | c0a8-0009-13e8842fd8a-ef667c79-2618-8 | Hz-ID-17858 | MCPA - Mine Clearance Planning Agency | AF/3211/07927/MF0118 | 13737 | 70.0139 | 33.295 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {431A6D99-5746-41B8-A1EE-34669A9E193E} |  | Low | Agriculture Blocked | Substantial | 14 | CHA | 5 |  |  | 2013-03-14 16:30 | No | Planned
South East | Khost | Gurbuz | Tawda China | {431A6D99-5746-41B8-A1EE-34669A9E193E} | c0a8-0009-13e884e7bbb-7bd8ffe7-27b2-a | Hz-ID-17853 | MCPA - Mine Clearance Planning Agency | AF/3211/07927/MF0114 | 53665 | 69.9801 | 33.2594 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {431A6D99-5746-41B8-A1EE-34669A9E193E} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2013-03-02 16:30 | No | Planned
South East | Khost | Gurbuz | Tawda China | {431A6D99-5746-41B8-A1EE-34669A9E193E} | c0a8-0009-13e88afc0be-574f1fa1-3fea-1 | Hz-ID-17852 | MCPA - Mine Clearance Planning Agency | AF/3211/07927/MF0115 | 89883 | 69.9754 | 33.2563 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {431A6D99-5746-41B8-A1EE-34669A9E193E} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2013-03-06 16:30 | No | Planned
South East | Khost | Gurbuz | Tawda China | {431A6D99-5746-41B8-A1EE-34669A9E193E} | c0a8-0057-12c3b99d966-1524e37-2b0db-5 | MF-HQ-13803 | MCPA - Mine Clearance Planning Agency | AF/3211/07927/MF0103 | 92023 | 69.9818 | 33.2603 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {431A6D99-5746-41B8-A1EE-34669A9E193E} |  | Low | Agriculture Blocked | Substantial | 19 | CHA | 5 |  |  | 2009-12-13 | No | Planned
South East | Khost | Gurbuz | Tawda China | {431A6D99-5746-41B8-A1EE-34669A9E193E} | c0a8-0057-12c3b99fd1b-c5b9888d-2b26d- | MF-HQ-13805 | MCPA - Mine Clearance Planning Agency | AF/3211/07927/MF0101 | 54125 | 70.0055 | 33.2558 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {431A6D99-5746-41B8-A1EE-34669A9E193E} |  | Low | Agriculture Blocked | Substantial | 25 | CHA | 5 |  |  | 2009-12-13 | No | Planned
South East | Khost | Gurbuz | Tawda China | {431A6D99-5746-41B8-A1EE-34669A9E193E} | c0a8-0057-12c3bb1a095-6c2e78fc-397cb- | MF-HQ-13804 | MCPA - Mine Clearance Planning Agency | AF/3211/07927/MF0102 | 98627 | 69.9754 | 33.2563 | Open | AP Only | AP Only | Converted From SHA | 1393 | MBT Project-203 | Khost Demining Project-02 | Bilateral | Yes |  |  | 1393 | HT | {431A6D99-5746-41B8-A1EE-34669A9E193E} |  | Low | Agriculture Blocked | Substantial | 13 | CHA | 5 |  |  | 2009-12-13 16:30 | No | Planned
South East | Khost | Jaji Maidan | Derai Mela | {996CADAD-D306-4461-BA51-B28B68E07B69} | c0a8-0057-12c3b99e162-e1e38c66-2b131- | MF-HQ-12797 | MCPA - Mine Clearance Planning Agency | AF/3202/00464/MF0035 | 40053 | 70.0511 | 33.6987 | Open | AP Only | AP Only | MineField |  | MBT Project-252 | Khost Demining Project-04 |  |  |  |  | 1395 |  | {996CADAD-D306-4461-BA51-B28B68E07B69} |  | High Requested | Resettlment/Local Request | Extreme | 18 | CHA | 5 |  |  | 2009-08-02 | No | Open
South East | Khost | Jaji Maidan | Kaski | {6B059371-EC65-45F8-8B1C-31142C6182D1} | c0a8-0057-12c3b7b478a-f954b032-16179- | MF-HQ-14421 | MCPA - Mine Clearance Planning Agency | AF/3202/00327/MF0043 | 63477 | 70.1401 | 33.6069 | Open | AP Only | AP Only | MineField |  | MBT Project-252 | Khost Demining Project-04 |  |  |  |  | 1395 |  | {6B059371-EC65-45F8-8B1C-31142C6182D1} |  | High Requested | Resettlment/Local Request | Extreme | 125 | CHA | 4 |  |  | 2010-04-01 | No | Open
South East | Khost | Jaji Maidan | Kaski | {6B059371-EC65-45F8-8B1C-31142C6182D1} | c0a8-0057-12c3b87fa35-ce856bc6-1f176- | MF-HQ-12789 | MCPA - Mine Clearance Planning Agency | AF/3202/00327/MF0033 | 98485 | 70.1516 | 33.5981 | Open | AP Only | AP Only | MineField |  | MBT Project-252 | Khost Demining Project-04 |  |  |  |  | 1395 |  | {6B059371-EC65-45F8-8B1C-31142C6182D1} |  | High Requested | Resettlment/Local Request | Extreme | 17 | CHA | 5 |  |  | 2010-03-30 | No | Open
South East | Khost | Jaji Maidan | Tekay | {570171FB-9DA3-4BF5-9E5E-7171F3C8842B} | c0a8-0057-12c3b90cbe5-6b30403b-251bd- | MF-HQ-14838 | MCPA - Mine Clearance Planning Agency | AF/3202/08795/MF0042 | 88006 | 70.1283 | 33.7002 | Open | AP Only | AP Only | MineField |  | MBT Project-252 | Khost Demining Project-04 |  |  |  |  | 1395 |  | {570171FB-9DA3-4BF5-9E5E-7171F3C8842B} |  | Low | Agriculture Blocked | Extreme | 8 | CHA | 5 |  |  | 2010-03-24 | No | Open
South East | Khost | Jaji Maidan | Tekay | {570171FB-9DA3-4BF5-9E5E-7171F3C8842B} | c0a8-0057-12c3b90cdf7-259253fa-251d0- | MF-HQ-12772 | MCPA - Mine Clearance Planning Agency | AF/3202/08795/MF0032 | 100722 | 70.1283 | 33.7002 | Open | AP Only | AP Only | MineField |  | MBT Project-252 | Khost Demining Project-04 |  |  |  |  | 1395 |  | {570171FB-9DA3-4BF5-9E5E-7171F3C8842B} |  | High Requested | Resettlment/Local Request | Extreme | 8 | CHA | 5 |  |  | 2010-03-27 | No | Open
South East | Khost | Khost(Matun) | Loy Mazghar | {DA068C8F-B49F-4BF4-A9BA-3DCA2AE9D7FF} | c0a8-008e-132c9744d1a-3877bbc5-347b-6 | MF-15756 | MCPA - Mine Clearance Planning Agency | AF/3205/07663/MF0129 | 4079 | 69.8944 | 33.4262 | Open | AP Only | AP Only | MineField |  | MBT Project-100/A | Khost Demining Project-05/A |  |  |  |  | 1394 |  | {DA068C8F-B49F-4BF4-A9BA-3DCA2AE9D7FF} |  | High with Victim | High with Victims | Extreme | 8 | CHA | 2 |  |  | 2010-11-02 16:30 | No | Open
South East | Khost | Khost(Matun) | Loy Mazghar | {DA068C8F-B49F-4BF4-A9BA-3DCA2AE9D7FF} | c0a8-008e-13436e5eb7f-5b9b39a0-1269-c | MF-15755 | MCPA - Mine Clearance Planning Agency | AF/3205/07663/MF0128 | 41727 | 69.8895 | 33.4275 | Open | AP Only | AP Only | MineField |  | MBT Project-100/A | Khost Demining Project-05/A |  |  |  |  | 1394 |  | {DA068C8F-B49F-4BF4-A9BA-3DCA2AE9D7FF} |  | High with Victim | High with Victims | Extreme | 12 | CHA | 2 |  |  | 2010-11-02 16:30 | No | Open
South East | Khost | Khost(Matun) | Loy Mazghar | {DA068C8F-B49F-4BF4-A9BA-3DCA2AE9D7FF} | c0a8-00c9-12fde997e85-7d694726-269-77 | MF-SE-422 | MCPA - Mine Clearance Planning Agency | AF/3205/07663/MF0002 | 27619 | 69.8959 | 33.4265 | Open | AP Only | AP Only | MineField |  | MBT Project-100/A | Khost Demining Project-05/A |  |  |  |  | 1394 |  | {DA068C8F-B49F-4BF4-A9BA-3DCA2AE9D7FF} |  | High with Victim | High with Victims | Extreme | 12 | CHA | 2 |  |  | 2009-01-13 | No | Open
South East | Khost | Khost(Matun) | Malizai | {006F2D3B-4DF4-4046-9D7B-13AF31E97224} | c0a8-0057-12c3b858f39-fb06a3f2-1d694- | MF-SE-389 | MCPA - Mine Clearance Planning Agency | AF/3201/07644/MF0119 | 5317 | 70.0232 | 33.3269 | Open | AP Only | AP Only | MineField | Blank | MBT Project-100/A | Khost Demining Project-05/A |  | No |  |  | 1394 | None | {006F2D3B-4DF4-4046-9D7B-13AF31E97224} |  | High with Victim | High with Victims | Extreme | 199 | CHA | 3 |  |  | 2008-11-15 | No | Open
South East | Khost | Khost(Matun) | Malizai | {006F2D3B-4DF4-4046-9D7B-13AF31E97224} | c0a8-0057-12c3b9f829a-db74c7cf-2e9f6- | MF-SE-388 | MCPA - Mine Clearance Planning Agency | AF/3201/07644/MF0118 | 17006 | 70.0212 | 33.3241 | Open | AP Only | AP Only | MineField | Blank | MBT Project-100/A | Khost Demining Project-05/A |  | No |  |  | 1394 | None | {006F2D3B-4DF4-4046-9D7B-13AF31E97224} | a | High with Victim | High with Victims | Extreme | 23 | CHA | 5 |  |  | 2008-11-16 | No | Open
South East | Khost | Mando Zayi | Bar Khankhel | {F15AED26-0022-4231-A6AB-DFCA323AF454} | c0a8-0009-13f0dfe2476-5200d3f4-4be-bd | Hz-ID-17936 | MCPA - Mine Clearance Planning Agency | AF/3206/07694/MF0132 | 8112 | 69.7938 | 33.2944 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-12-28 | 2014-01-31 | 1392 | MCPA | {F15AED26-0022-4231-A6AB-DFCA323AF454} |  |  |  | Extreme | 268 | CHA | 4 |  |  | 2013-04-12 16:30 | No | Complete
South East | Khost | Mando Zayi | Bar Khankhel | {F15AED26-0022-4231-A6AB-DFCA323AF454} | c0a8-0009-13f0e034ebd-9f379bd-52b-1d0 | Hz-ID-17938 | MCPA - Mine Clearance Planning Agency | AF/3206/07694/MF0135 | 3652 | 69.7938 | 33.2944 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-12-28 | 2014-01-31 | 1392 | MCPA | {F15AED26-0022-4231-A6AB-DFCA323AF454} |  |  |  | Extreme | 179 | CHA | 3 |  |  | 2013-04-12 16:30 | No | Complete
South East | Khost | Mando Zayi | Durnamey | {6826DE2E-482B-4AE3-9351-5D2A0980200B} | c0a8-0009-13e882b4855-22241464-239d-6 | Hz-ID-17871 | MCPA - Mine Clearance Planning Agency | AF/3206/00317/MF0134 | 5118 | 69.7461 | 33.324 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-12-25 | 2014-01-31 | 1392 | MCPA | {6826DE2E-482B-4AE3-9351-5D2A0980200B} |  |  |  | Extreme | 256 | CHA | 2 |  |  | 2013-03-02 16:30 | No | Complete
South East | Khost | Mando Zayi | Durnamey | {6826DE2E-482B-4AE3-9351-5D2A0980200B} | c0a8-0009-13e882f0d08-6e1632ee-23ba-c | Hz-ID-17869 | MCPA - Mine Clearance Planning Agency | AF/3206/00317/MF0133 | 3435 | 69.7482 | 33.3247 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-12-25 | 2014-01-31 | 1392 | MCPA | {6826DE2E-482B-4AE3-9351-5D2A0980200B} |  |  |  | Extreme | 357 | CHA | 2 |  |  | 2013-03-03 16:30 | No | Complete
South East | Khost | Mando Zayi | Haydarkhel | {15672C42-1559-48D2-B4C5-C9DDE0557055} | c0a8-00f6-137548cc647-c91ecd13-1823-3 | MF-16772 | MCPA - Mine Clearance Planning Agency | AF/3206/07734/MF0131 | 29575 | 69.8243 | 33.391 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-11-01 | 2013-12-31 | 1392 | MCPA | {15672C42-1559-48D2-B4C5-C9DDE0557055} |  |  |  | Extreme | 8 | CHA | 5 |  |  | 2012-03-28 16:30 | No | Complete
South East | Khost | Nadir Shah Kot | Babrakkhan | {7CFD3030-3623-4C06-B673-9C92E837E1E4} | c0a8-0057-12c3b812c8c-14860809-1a427- | MF-SE-451 | MCPA - Mine Clearance Planning Agency | AF/3208/07943/MF0046 | 39297 | 69.6744 | 33.2825 | Open | AP Only | AP Only | MineField | Blank | MBT Project-280 | Khost Demining Project-03 |  | No |  |  | 1394 | None | {7CFD3030-3623-4C06-B673-9C92E837E1E4} | Planned for ERT Teams in 1390 | High Requested | Resettlment/Local Request | Extreme | 96 | CHA | 5 |  |  | 2009-01-31 | No | Open
South East | Khost | Nadir Shah Kot | Malway | {3155F084-07CD-49B3-9327-4BA359006203} | c0a8-0057-12c3b927fb1-4c456a1f-26355- | MF-SE-450 | MCPA - Mine Clearance Planning Agency | AF/3208/07947/MF0042 | 30924 | 69.6064 | 33.2884 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {3155F084-07CD-49B3-9327-4BA359006203} |  | High Requested | Resettlment/Local Request | Extreme | 166 | CHA | 5 |  |  | 2009-01-25 | No | Open
South East | Khost | Nadir Shah Kot | Sper Ghawara | {265407C5-7D1F-459E-ABD1-379B6DB7C756} | c0a8-0057-12c3b7c20a7-44dc1e1d-16b38- | MF-SE-465 | MCPA - Mine Clearance Planning Agency | AF/3208/00000/MF0021 | 83945 | 69.6114 | 33.3004 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {265407C5-7D1F-459E-ABD1-379B6DB7C756} |  | High with Victim | High with Victims | Extreme | 14 | CHA | 4 |  |  | 2009-01-18 | No | Open
South East | Khost | Nadir Shah Kot | Sper Ghawara | {265407C5-7D1F-459E-ABD1-379B6DB7C756} | c0a8-0057-12c3b87e8a8-7d2e04aa-1f0aa- | MF-SE-286 | MCPA - Mine Clearance Planning Agency | AF/3208/00000/MF0020 | 82815 | 69.6114 | 33.3004 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {265407C5-7D1F-459E-ABD1-379B6DB7C756} |  | High with Victim | High with Victims | Extreme | 37 | CHA | 5 |  |  | 2009-01-17 | No | Open
South East | Khost | Nadir Shah Kot | Sper Ghawara | {265407C5-7D1F-459E-ABD1-379B6DB7C756} | c0a8-0057-12c3b93c6eb-e530c371-270ce- | MF-SE-466 | MCPA - Mine Clearance Planning Agency | AF/3208/00000/MF0022 | 69629 | 69.6114 | 33.3004 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {265407C5-7D1F-459E-ABD1-379B6DB7C756} |  | High with Victim | High with Victims | Extreme | 210 | CHA | 4 |  |  | 2009-01-20 | No | Open
South East | Khost | Nadir Shah Kot | Sper Ghawara | {265407C5-7D1F-459E-ABD1-379B6DB7C756} | c0a8-0057-12c3bb88f93-de149bf5-3d7ab- | MF-SE-428 | MCPA - Mine Clearance Planning Agency | AF/3208/00000/MF0024 | 74305 | 69.6119 | 33.2997 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {265407C5-7D1F-459E-ABD1-379B6DB7C756} |  | High with Victim | High with Victims | Extreme | 260 | CHA | 5 |  |  | 2009-01-18 | No | Open
South East | Khost | Nadir Shah Kot | Sper Ghawara | {265407C5-7D1F-459E-ABD1-379B6DB7C756} | c0a8-0057-12c3bb89203-d3052c4b-3d7be- | MF-SE-431 | MCPA - Mine Clearance Planning Agency | AF/3208/00000/MF0027 | 43687 | 69.6114 | 33.2942 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {265407C5-7D1F-459E-ABD1-379B6DB7C756} |  | High with Victim | High with Victims | Extreme | 260 | CHA | 4 |  |  | 2009-01-22 | No | Open
South East | Khost | Nadir Shah Kot | Sper Ghawara | {265407C5-7D1F-459E-ABD1-379B6DB7C756} | c0a8-0057-12c3bb893f6-622acd3d-3d7d2- | MF-SE-430 | MCPA - Mine Clearance Planning Agency | AF/3208/00000/MF0026 | 74875 | 69.6114 | 33.2942 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {265407C5-7D1F-459E-ABD1-379B6DB7C756} |  | High with Victim | High with Victims | Extreme | 260 | CHA | 5 |  |  | 2009-01-20 | No | Open
South East | Khost | Nadir Shah Kot | Sper Ghawara | {265407C5-7D1F-459E-ABD1-379B6DB7C756} | c0a8-0057-12c3bb89657-2cfef3e1-3d7e6- | MF-SE-429 | MCPA - Mine Clearance Planning Agency | AF/3208/00000/MF0025 | 78862 | 69.6119 | 33.2997 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {265407C5-7D1F-459E-ABD1-379B6DB7C756} |  | High with Victim | High with Victims | Extreme | 260 | CHA | 5 |  |  | 2009-01-19 | No | Open
South East | Khost | Nadir Shah Kot | Sper Ghawara | {265407C5-7D1F-459E-ABD1-379B6DB7C756} | c0a8-0057-12c3bb89888-42f2190a-3d7fb- | MF-SE-427 | MCPA - Mine Clearance Planning Agency | AF/3208/00000/MF0023 | 115950 | 69.6119 | 33.2997 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {265407C5-7D1F-459E-ABD1-379B6DB7C756} |  | High with Victim | High with Victims | Extreme | 283 | CHA | 5 |  |  | 2009-01-17 | No | Open
South East | Khost | Sabri | Bakhtana | {6C22461A-6037-4F1D-90EE-3E562C9889CA} | c0a8-0057-12c3b94ef54-b535cd14-27d39- | MF-HQ-12783 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3209/07742/MF0030 | 64000 | 69.9634 | 33.4494 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-048 | Khost Demining Project-01 AT |  |  |  |  | 1397 |  | {6C22461A-6037-4F1D-90EE-3E562C9889CA} |  | Low | Infrastructure | Extreme | 70 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Khost | Sabri | Khushki Danda | {FDE31991-8A19-4B70-BCD4-42951933D677} | c0a8-0057-12c3b7ca0ae-72c6c1eb-1713c- | MF-HQ-12805 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3209/07758/MF0028 | 45150 | 69.9788 | 33.5024 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-048 | Khost Demining Project-01 AT |  |  |  |  | 1397 |  | {FDE31991-8A19-4B70-BCD4-42951933D677} |  | Low | Agriculture Blocked | Extreme | 196 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Khost | Sabri | Khushki Danda | {FDE31991-8A19-4B70-BCD4-42951933D677} | c0a8-0057-12c3bb29b65-8f4793ca-3a0f9- | MF-HQ-12802 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3209/07758/MF0027 | 5200 | 69.9806 | 33.4965 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-048 | Khost Demining Project-01 AT |  |  |  |  | 1397 |  | {FDE31991-8A19-4B70-BCD4-42951933D677} |  | Medium | Critical Infrastracture | Extreme | 211 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Khost | Sabri | Nuri Kalay | {83B9E98E-F322-4B45-8B95-68E0AF88F757} | c0a8-0057-12c3b7f10c8-e6b4fe5b-18c44- | MF-HQ-12801 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3209/07744/MF0031 | 34150 | 69.96 | 33.4944 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-048 | Khost Demining Project-01 AT |  |  |  |  | 1397 |  | {83B9E98E-F322-4B45-8B95-68E0AF88F757} |  | High with Victim | High with Victims | Extreme | 211 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Khost | Sabri | Nuri Kalay | {83B9E98E-F322-4B45-8B95-68E0AF88F757} | c0a8-0057-12c3b951348-5dc11dfd-27ec4- | MF-HQ-12806 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3209/07744/MF0034 | 84400 | 69.9587 | 33.4845 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-048 | Khost Demining Project-01 AT |  |  |  |  | 1397 |  | {83B9E98E-F322-4B45-8B95-68E0AF88F757} |  | High with Victim | High with Victims | Extreme | 155 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Khost | Sabri | Nuri Kalay | {83B9E98E-F322-4B45-8B95-68E0AF88F757} | c0a8-0057-12c3ba28658-86647c1d-3078a- | MF-HQ-12803 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3209/07744/MF0032 | 45600 | 69.96 | 33.4944 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-048 | Khost Demining Project-01 AT |  |  |  |  | 1397 |  | {83B9E98E-F322-4B45-8B95-68E0AF88F757} |  | High with Victim | High with Victims | Extreme | 211 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Khost | Sabri | Nuri Kalay | {83B9E98E-F322-4B45-8B95-68E0AF88F757} | c0a8-0057-12c3bb45b84-c483b599-3b1b7- | MF-HQ-12809 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3209/07744/MF0033 | 11500 | 69.9643 | 33.4859 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-048 | Khost Demining Project-01 AT |  |  |  |  | 1397 |  | {83B9E98E-F322-4B45-8B95-68E0AF88F757} |  | High with Victim | High with Victims | Extreme | 111 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Khost | Sabri | Surwapan Toy | {76FBCE66-723D-44C4-AE88-93AE3577908F} | c0a8-0057-12c3ba92766-292ef17d-347a0- | MF-HQ-12800 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3209/07748/MF0029 | 138000 | 69.9631 | 33.5526 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-048 | Khost Demining Project-01 AT |  |  |  |  | 1397 |  | {76FBCE66-723D-44C4-AE88-93AE3577908F} |  | High with Victim | High with Victims | Extreme | 62 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Khost | Shamal | Dwamanday | {BDA49922-B6DD-43FF-B28A-F2A7176C16E3} | c0a8-0009-13fa3002566-89ba056e-b1c-d4 | Hz-ID-17935 | MCPA - Mine Clearance Planning Agency | AF/3208/08364/MF0051 | 22181 | 69.5558 | 33.2879 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {BDA49922-B6DD-43FF-B28A-F2A7176C16E3} |  | High with Victim | High with Victims | Extreme | 8 | CHA | 1 |  |  | 2013-04-29 16:30 | No | Open
South East | Khost | Shamal | Dwamanday | {BDA49922-B6DD-43FF-B28A-F2A7176C16E3} | c0a8-0009-140527831b0-7ef544d5-73c3-d | Hz-ID-17931 | MCPA - Mine Clearance Planning Agency | AF/3208/08364/MF0050 | 39262 | 69.6004 | 33.2945 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {BDA49922-B6DD-43FF-B28A-F2A7176C16E3} |  | High with Victim | High with Victims | Extreme | 191 | CHA | 1 |  |  | 2013-04-28 16:30 | No | Open
South East | Khost | Shamal | Dwamanday | {BDA49922-B6DD-43FF-B28A-F2A7176C16E3} | c0a8-0057-12c3bab0aae-23e09deb-358b5- | MF-HQ-9987 | MCPA - Mine Clearance Planning Agency | AF/3208/08364/MF0013A | 7906 | 69.5951 | 33.2818 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {BDA49922-B6DD-43FF-B28A-F2A7176C16E3} |  | High with Victim | High with Victims | Extreme | 390 | CHA | 1 |  |  | 2009-04-11 | No | Open
South East | Khost | Shamal | Ghundi Khil (Palgai) | {9A9E5AF7-E4AB-490B-A138-33770C6F5AF6} | c0a8-0057-12c3b874f48-1cbf8c04-1e9df- | MF-HQ-13800 | MCPA - Mine Clearance Planning Agency | AF/3205/00467/MF0002 | 4188 | 69.5081 | 33.3494 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {9A9E5AF7-E4AB-490B-A138-33770C6F5AF6} |  | Medium | Agriculture Blocked | Extreme | 20 | CHA | 5 |  |  | 2009-12-13 | No | Open
South East | Khost | Shamal | Khalwati | {A93E39C5-2771-4328-BB14-0511B6E05C4B} | c0a8-0057-12c3b99495a-5e3603d2-2aaca- | MF-SE-442 | MCPA - Mine Clearance Planning Agency | AF/3208/08363/MF0038 | 38100 | 69.5841 | 33.2773 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {A93E39C5-2771-4328-BB14-0511B6E05C4B} |  | Low | Agriculture Blocked | Extreme | 24 | CHA | 5 |  |  | 2009-01-27 | No | Open
South East | Khost | Shamal | Khalwati | {A93E39C5-2771-4328-BB14-0511B6E05C4B} | c0a8-0057-12c3bb3c84b-ffd51be-3ac52-4 | MF-SE-443 | MCPA - Mine Clearance Planning Agency | AF/3208/08363/MF0039 | 18300 | 69.5841 | 33.2773 | Open | AP Only | AP Only | MineField |  | MBT Project-280 | Khost Demining Project-03 |  |  |  |  | 1394 |  | {A93E39C5-2771-4328-BB14-0511B6E05C4B} |  | Low | Agriculture Blocked | Extreme | 15 | CHA | 5 |  |  | 2009-01-29 | No | Open
South East | Khost | Tani | Dragai | {8271DD7D-C782-4A98-A5DC-D0D65E9180F9} | c0a8-0009-13dcea64433-8fe81ec3-1e3-6d | Hz-ID-17772 | MCPA - Mine Clearance Planning Agency | AF/3208/00398/MF0147 | 9926 | 69.8441 | 33.2068 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-10-01 | 2013-12-31 | 1392 | MCPA | {8271DD7D-C782-4A98-A5DC-D0D65E9180F9} |  |  |  | High | 9 | CHA | 5 |  |  | 2013-01-23 16:30 | No | Complete
South East | Khost | Tani | Hesarak | {EEB01CDD-8D0D-455F-8551-CB1EE78AFC1F} | c0a8-0009-13fa80d3966-50f16686-2cd1-f | Hz-ID-17997 | MCPA - Mine Clearance Planning Agency | AF/3203/07867/MF0160 | 11685 | 69.7379 | 33.2464 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-10-01 | 2013-12-31 | 1392 | MCPA | {EEB01CDD-8D0D-455F-8551-CB1EE78AFC1F} |  |  |  | High | 70 | CHA | 5 |  |  | 2013-05-01 16:30 | No | Complete
South East | Khost | Tani | Jan Shareh Kalay | {61652789-7CB1-4A85-B6DF-AB712EB9AF6E} | c0a8-0009-13e8862227d-cec6e91d-29e9-9 | Hz-ID-17848 | MCPA - Mine Clearance Planning Agency | AF/3203/07905/BF0159 | 418990 | 69.8705 | 33.1242 | Open | UXO Only | UXO Only | BF |  | MBT Project-100/A | Khost Demining Project-05/A |  |  |  |  | 1394 |  | {61652789-7CB1-4A85-B6DF-AB712EB9AF6E} |  | Low | Agriculture Blocked | High | 183 | CHA | 5 |  |  | 2013-03-26 16:30 | No | Open
South East | Khost | Tani | Jan Shareh Kalay | {61652789-7CB1-4A85-B6DF-AB712EB9AF6E} | c0a8-0009-13e88900e9c-70a2ea67-2d53-b | Hz-ID-17847 | MCPA - Mine Clearance Planning Agency | AF/3203/07905/BF0158 | 395625 | 69.8705 | 33.1242 | Open | UXO Only | UXO Only | BF |  | MBT Project-100/A | Khost Demining Project-05/A |  |  |  |  | 1394 |  | {61652789-7CB1-4A85-B6DF-AB712EB9AF6E} |  | Low | Agriculture Blocked | High | 74 | CHA | 5 |  |  | 2013-03-27 16:30 | No | Open
South East | Khost | Tani | Jan Shareh Kalay | {61652789-7CB1-4A85-B6DF-AB712EB9AF6E} | c0a8-0009-13e8893107f-926881a8-2ed0-f | Hz-ID-17846 | MCPA - Mine Clearance Planning Agency | AF/3203/07905/BF0157 | 479270 | 69.8705 | 33.1242 | Open | UXO Only | UXO Only | BF |  | MBT Project-100/A | Khost Demining Project-05/A |  |  |  |  | 1394 |  | {61652789-7CB1-4A85-B6DF-AB712EB9AF6E} |  | Low | Agriculture Blocked | High | 172 | CHA | 5 |  |  | 2013-03-28 16:30 | No | Open
South East | Khost | Tani | Jan Shareh Kalay | {61652789-7CB1-4A85-B6DF-AB712EB9AF6E} | c0a8-0009-13e889791ad-5c0b34af-320d-c | Hz-ID-17845 | MCPA - Mine Clearance Planning Agency | AF/3203/07905/BF0156 | 372299 | 69.8705 | 33.1242 | Open | UXO Only | UXO Only | BF |  | MBT Project-100/A | Khost Demining Project-05/A |  |  |  |  | 1394 |  | {61652789-7CB1-4A85-B6DF-AB712EB9AF6E} |  | Low | Agriculture Blocked | High | 195 | CHA | 5 |  |  | 2013-03-27 16:30 | No | Open
South East | Khost | Tani | Kosha | {7450782A-70EF-49FF-8943-9366CE1381CA} | c0a8-0009-13bd6927317-13660285-865-6a | Hz-ID-17492 | MCPA - Mine Clearance Planning Agency | AF/3208/07956/MF0130 | 20113 | 69.7031 | 33.2664 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-04-20 | 2013-07-22 | 1392 | MCPA | {7450782A-70EF-49FF-8943-9366CE1381CA} |  |  |  | High | 6 | CHA | 1 |  |  | 2012-12-09 16:30 | No | Complete
South East | Khost | Tani | Kosha | {7450782A-70EF-49FF-8943-9366CE1381CA} | c0a8-0009-13bd6957141-f416905e-897-1a | Hz-ID-17493 | MCPA - Mine Clearance Planning Agency | AF/3208/07956/MF0131 | 37783 | 69.7025 | 33.2711 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-07-23 | 2014-01-14 | 1392 | MCPA | {7450782A-70EF-49FF-8943-9366CE1381CA} |  |  |  | High | 11 | CHA | 1 |  |  | 2012-12-11 16:30 | No | Complete
South East | Khost | Tani | Kosha | {7450782A-70EF-49FF-8943-9366CE1381CA} | c0a8-0009-13bd6a6f17b-a18d0ca9-a27-df | Hz-ID-17495 | MCPA - Mine Clearance Planning Agency | AF/3208/07956/MF0133 | 45833 | 69.6993 | 33.2628 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-04-20 | 2013-12-15 | 1392 | MCPA | {7450782A-70EF-49FF-8943-9366CE1381CA} |  |  |  | High | 15 | CHA | 1 |  |  | 2012-12-16 16:30 | No | Complete
South East | Khost | Tani | Kosha | {7450782A-70EF-49FF-8943-9366CE1381CA} | c0a8-0009-13bd6a84840-588fe6aa-a6b-56 | Hz-ID-17497 | MCPA - Mine Clearance Planning Agency | AF/3208/07956/MF0137 | 55987 | 69.6775 | 33.2783 | Open | AP Only | AP Only | MineField | Blank | MBT Project-100/A | Khost Demining Project-05/A |  | No |  |  | 1394 | None | {7450782A-70EF-49FF-8943-9366CE1381CA} |  | High with Victim | High with Victims | High | 8 | CHA | 1 |  |  | 2012-12-08 16:30 | No | Open
South East | Khost | Tani | Kosha | {7450782A-70EF-49FF-8943-9366CE1381CA} | c0a8-0009-13bd6b0f5f5-a3aaaba0-bbd-7a | Hz-ID-17499 | MCPA - Mine Clearance Planning Agency | AF/3208/07956/MF0138 | 16534 | 69.6809 | 33.2812 | Open | AP Only | AP Only | MineField | Blank | MBT Project-100/A | Khost Demining Project-05/A |  | No |  |  | 1394 | None | {7450782A-70EF-49FF-8943-9366CE1381CA} | , | High with Victim | High with Victims | High | 0 | CHA | 2 |  |  | 2012-12-10 16:30 | No | Open
South East | Khost | Tani | Kosha | {7450782A-70EF-49FF-8943-9366CE1381CA} | c0a8-0009-13bda853b90-4a78002a-cab-be | Hz-ID-17500 | MCPA - Mine Clearance Planning Agency | AF/3208/07956/MF0139 | 64270 | 69.6836 | 33.2797 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-10-01 | 2013-12-31 | 1392 | MCPA | {7450782A-70EF-49FF-8943-9366CE1381CA} |  |  |  | High | 9 | CHA | 1 |  |  | 2012-12-12 16:30 | No | Complete
South East | Khost | Tani | Kosha | {7450782A-70EF-49FF-8943-9366CE1381CA} | c0a8-0009-13bda8eab40-95a625aa-ccb-ab | Hz-ID-17502 | MCPA - Mine Clearance Planning Agency | AF/3208/07956/MF0140 | 14961 | 69.6977 | 33.2937 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-10-01 | 2013-12-31 | 1392 | MCPA | {7450782A-70EF-49FF-8943-9366CE1381CA} | , |  |  | High | 364 | CHA | 2 |  |  | 2012-12-08 16:30 | No | Complete
South East | Khost | Tani | Kosha | {7450782A-70EF-49FF-8943-9366CE1381CA} | c0a8-0009-13c18da9b7e-c5496899-109f-e | Hz-ID-17494 | MCPA - Mine Clearance Planning Agency | AF/3208/07956/MF0132 | 42661 | 69.6993 | 33.2628 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-12-16 | 2014-03-31 | 1392 | MCPA | {7450782A-70EF-49FF-8943-9366CE1381CA} |  |  |  | High | 6 | CHA | 1 |  |  | 2012-12-13 16:30 | No | Complete
South East | Khost | Tani | Mayob Kala | {9E5D24D6-22F8-4A56-9AE5-0409AB0116BA} | c0a8-0009-13dcf3f7616-682a211b-401-8a | Hz-ID-17752 | MCPA - Mine Clearance Planning Agency | AF/3203/07895/MF0150 | 5442 | 69.8414 | 33.2538 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-10-01 | 2013-12-31 | 1392 | MCPA | {9E5D24D6-22F8-4A56-9AE5-0409AB0116BA} |  |  |  | High | 455 | CHA | 4 |  |  | 2013-02-06 16:30 | No | Complete
South East | Khost | Tani | Mayob Kala | {9E5D24D6-22F8-4A56-9AE5-0409AB0116BA} | c0a8-0009-13dcf439c39-df8307c8-42b-ce | Hz-ID-17753 | MCPA - Mine Clearance Planning Agency | AF/3203/07895/MF0153 | 5879 | 69.8414 | 33.2538 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-10-01 | 2013-12-31 | 1392 | MCPA | {9E5D24D6-22F8-4A56-9AE5-0409AB0116BA} |  |  |  | High | 455 | CHA | 4 |  |  | 2013-02-04 16:30 | No | Complete
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0009-13c0f65fa8c-ca79cdd5-13ab-d | Hz-ID-17550 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0134 | 21115 | 69.7815 | 33.1706 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-01-22 | 2013-04-10 | 1392 | MCPA | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  |  |  | High | 1 | CHA | 1 |  |  | 2012-12-17 16:30 | No | Complete
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0009-13c33668b40-b8d5ffac-224-77 | Hz-ID-17552 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0135 | 21735 | 69.7776 | 33.1615 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-01-22 | 2013-04-10 | 1392 | MCPA | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  |  |  | High | 4 | CHA | 1 |  |  | 2012-12-17 16:30 | No | Complete
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0009-13daf79cc88-b641e660-195d-e | Hz-ID-17731 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0136 | 4239 | 69.7821 | 33.1605 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-10-01 | 2013-12-31 | 1392 | MCPA | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  |  |  | High | 21 | CHA | 1 |  |  | 2013-01-08 16:30 | No | Complete
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0009-13daf7a4899-90c739fe-19a5-c | Hz-ID-17736 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0149 | 16800 | 69.7893 | 33.1525 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-10-01 | 2013-12-31 | 1392 | MCPA | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  |  |  | High | 4 | CHA | 1 |  |  | 2013-01-31 16:30 | No | Complete
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0009-13dcf386b24-8ff5e450-3a9-79 | Hz-ID-17751 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0148 | 50827 | 69.7844 | 33.1532 | Open | AP Only | AP Only | MineField |  | MBT Project-100/A | Khost Demining Project-05/A |  |  |  |  | 1394 |  | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  | High with Victim | High with Victims | High | 4 | CHA | 1 |  |  | 2013-02-03 16:30 | No | Open
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0009-13dcf46018e-f38b5342-469-27 | Hz-ID-17754 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0154 | 49980 | 69.7858 | 33.1655 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-08-17 | 2014-03-31 | 1392 | MCPA | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  |  |  | High | 17 | CHA | 1 |  |  | 2013-02-09 16:30 | No | Complete
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0009-13dd40cc080-fc071256-2722-e | Hz-ID-17773 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0151 | 5666 | 69.7829 | 33.1686 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-10-01 | 2013-12-31 | 1392 | MCPA | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  |  |  | High | 1 | CHA | 1 |  |  | 2013-01-27 16:30 | No | Complete
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0009-13e3ae24994-2fa717b8-da6-37 | Hz-ID-17823 | MCPA - Mine Clearance Planning Agency | AF/3208/07852/MF0155 | 7229 | 69.7813 | 33.1605 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-04-20 | 2013-06-05 | 1392 | MCPA | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  |  |  | High | 21 | CHA | 1 |  |  | 2013-03-21 16:30 | No | Complete
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0009-145119433b1-be2014ee-1ae-85 | Hz-ID-18569 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0161 | 27220 | 69.7839 | 33.1564 | Open | AP Only | AP Only | MineField |  | MBT Project-100/A | Khost Demining Project-05/A |  |  |  |  | 1394 |  | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  | High with Victim | High with Victims | High | 9 | CHA | 2 |  |  | 2014-03-10 16:30 | No | Open
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0057-12c3b6d42ae-38f992de-bac4-6 | MF-HQ-15266 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0111 | 3000 | 69.7813 | 33.1605 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-03-10 | 2013-04-10 | 1392 | MCPA | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  |  |  | High | 21 | CHA | 1 |  |  | 2010-09-28 | No | Complete
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0057-12c3b750a8a-68ca14dd-118d3- | MF-HQ-15270 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0115 | 16172 | 69.7879 | 33.1694 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-05-26 | 2013-08-10 | 1392 | MCPA | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  |  |  | High | 12 | CHA | 1 |  |  | 2010-10-09 | No | Complete
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-0057-12c3b7771ee-c2343fcc-1351b- | MF-HQ-15269 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0114 | 62547 | 69.7873 | 33.1681 | Open | AP Only | AP Only | MineField | Blank | MBT Project-100/A | Khost Demining Project-05/A |  | No |  |  | 1394 | None | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  | High with Victim | High with Victims | High | 29 | CHA | 1 |  |  | 2010-10-05 | No | Open
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-008e-1328f9b9774-4124bab1-1cfd-6 | MF-15409 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0118 | 84575 | 69.7839 | 33.1564 | Open | AP Only | AP Only | MineField | Blank | MBT Project-100/A | Khost Demining Project-05/A |  | No |  |  | 1394 | None | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  | High with Victim | High with Victims | High | 4 | CHA | 1 |  |  | 2010-10-18 16:30 | No | Open
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-008e-1329f0f137f-6999db8b-ef3-79 | MF-15410 | MCPA - Mine Clearance Planning Agency | AF/3203/07852/MF0119 | 67603 | 69.7839 | 33.1564 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-11-04 | 2014-03-15 | 1392 | MCPA | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | Contingency Plan |  |  | High | 4 | CHA | 1 |  |  | 2010-10-16 16:30 | No | Complete
South East | Khost | Tani | Sre Kalay | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} | c0a8-00f6-135e26db69d-53dd804-e468-76 | MF-16722 | MCPA - Mine Clearance Planning Agency | AF/3208/07852/MF0128 | 42552 | 69.7746 | 33.1595 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-04-20 | 2013-11-30 | 1392 | MCPA | {2B5AF58D-D203-48DC-BA53-C580EAE9E242} |  |  |  | High | 4 | CHA | 1 |  |  | 2012-02-13 16:30 | No | Complete
South East | Khost | Tani | Yatmani Kalay | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} | c0a8-0009-13daf79f78d-5bf54bba-198a-d | Hz-ID-17732 | MCPA - Mine Clearance Planning Agency | AF/3203/07856/MF0141 | 28870 | 69.7892 | 33.1724 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-07-20 | 2013-09-27 | 1392 | MCPA | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} |  |  |  | High | 12 | CHA | 2 |  |  | 2013-01-14 16:30 | No | Complete
South East | Khost | Tani | Yatmani Kalay | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} | c0a8-0009-13daf7aac0d-25261e6a-19bd-5 | Hz-ID-17734 | MCPA - Mine Clearance Planning Agency | AF/3208/07856/MF0145 | 31323 | 69.7983 | 33.1859 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-11-02 | 2014-01-20 | 1392 | MCPA | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} |  |  |  | High | 233 | CHA | 2 |  |  | 2013-01-19 16:30 | No | Complete
South East | Khost | Tani | Yatmani Kalay | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} | c0a8-0009-13daf87201e-72b8abaa-1cbe-4 | Hz-ID-17733 | MCPA - Mine Clearance Planning Agency | AF/3203/07856/MF0144 | 14264 | 69.7923 | 33.1653 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-09-26 | 2013-10-31 | 1392 | MCPA | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} |  |  |  | High | 17 | CHA | 2 |  |  | 2013-01-06 16:30 | No | Complete
South East | Khost | Tani | Yatmani Kalay | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} | c0a8-0009-145119775d3-2b956b24-1d6-f6 | Hz-ID-18570 | MCPA - Mine Clearance Planning Agency | AF/3203/07856/MF0162 | 110317 | 69.8261 | 33.1654 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-100/A | Khost Demining Project-05/A |  |  |  |  | 1394 |  | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} |  | High with Victim | High with Victims | High | 169 | CHA | 2 |  |  | 2014-03-10 16:30 | No | Open
South East | Khost | Tani | Yatmani Kalay | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} | c0a8-0057-12c3b71c24d-b2dcda21-f195-d | MF-HQ-14725 | MCPA - Mine Clearance Planning Agency | AF/3203/07856/MF0097 | 54046 | 69.8033 | 33.1582 | Open | AP Only | AP Only | MineField | Blank | MBT Project-100/A | Khost Demining Project-05/A |  | No |  |  | 1394 | None | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} |  | High with Victim | High with Victims | High | 8 | CHA | 5 |  |  | 2010-07-10 | No | Open
South East | Khost | Tani | Yatmani Kalay | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} | c0a8-0057-12c3b73ba1e-14e48a65-10914- | MF-HQ-14727 | MCPA - Mine Clearance Planning Agency | AF/3203/07856/MF0098 | 39324 | 69.7955 | 33.1673 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-04-20 | 2013-07-18 | 1392 | MCPA | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} |  |  |  | High | 17 | CHA | 5 |  |  | 2010-07-10 | No | Complete
South East | Khost | Tani | Yatmani Kalay | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} | c0a8-0057-12c3b793641-a230c18f-149b8- | MF-HQ-14731 | MCPA - Mine Clearance Planning Agency | AF/3203/07856/MF0102 | 130032 | 69.8262 | 33.1654 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2014-01-21 | 2014-03-31 | 1392 | MCPA | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} | Contingency Plan |  |  | High | 133 | CHA | 4 |  |  | 2010-07-10 | No | Complete
South East | Khost | Tani | Yatmani Kalay | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} | c0a8-00f6-135e278e94a-771a2b10-e4c3-4 | MF-16724 | MCPA - Mine Clearance Planning Agency | AF/3203/07856/MF0126 | 14443 | 69.792 | 33.1707 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-202 | Khost Demining Project-01 | VTF-Australia | Yes | 2013-02-16 | 2013-04-10 | 1392 | MCPA | {1DEDF336-0481-4906-B8E7-A6AE2F7A19F4} |  |  |  | High | 22 | CHA | 5 |  |  | 2012-02-06 16:30 | No | Complete
South East | Khost | Tani | Zaher Kala | {068DE339-8035-41B5-B15D-2CC048A58CCF} | c0a8-0009-13daf862388-a24d8178-1c51-f | Hz-ID-17735 | MCPA - Mine Clearance Planning Agency | AF/3208/07920/MF0146 | 27256 | 69.8702 | 33.2751 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-100 | Khost Demining Project-05 | CIDA | Yes | 2013-10-01 | 2013-12-31 | 1392 | MCPA | {068DE339-8035-41B5-B15D-2CC048A58CCF} |  |  |  | High | 118 | CHA | 4 |  |  | 2013-01-19 16:30 | No | Complete
South East | Khost | Tere Zayi | Harunkhel | {5EC44110-DA5C-46FF-A1CD-F41D91CF67AB} | c0a8-0057-12c3ba3f359-3b27f0ba-31558- | MF-HQ-12792 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3207/07783/MF0022 | 40950 | 70.1396 | 33.4006 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-048 | Khost Demining Project-01 AT |  |  |  |  | 1397 |  | {5EC44110-DA5C-46FF-A1CD-F41D91CF67AB} |  | Low | Agriculture Blocked | High | 66 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Khost | Tere Zayi | Sin Khora | {D0A02390-0A79-48B8-BB45-6E823F8ADA5C} | c0a8-0057-12c3b817657-fbf6487d-1a784- | MF-HQ-12812 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3207/07797/MF0020 | 6250 | 70.0867 | 33.4613 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-048 | Khost Demining Project-01 AT |  |  |  |  | 1397 |  | {D0A02390-0A79-48B8-BB45-6E823F8ADA5C} |  | Medium | Critical Infrastracture | High | 538 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Khost | Tere Zayi | Tore Obeh | {44071CD9-B73A-4B6C-A50A-3F60D7EA75F7} | c0a8-0057-12c3b9b0496-c261008f-2bd77- | MF-HQ-12795 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/3207/07809/MF0021 | 27000 | 70.1348 | 33.4142 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-048 | Khost Demining Project-01 AT |  |  |  |  | 1397 |  | {44071CD9-B73A-4B6C-A50A-3F60D7EA75F7} |  | Medium | Critical Infrastracture | High | 131 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Paktika | Dila | A1 | {BBACF20D-9F40-48E6-9C99-F5E3B3D2B708} | c0a8-0057-12c3b8eae27-54c443df-23bc7- | MF-HQ-12650 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2903/00579/MF002 | 360000 | 68.011 | 32.6311 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-303 | Paktika Demining Project-05 AT |  |  |  |  | 1401 |  | {BBACF20D-9F40-48E6-9C99-F5E3B3D2B708} |  | Low | Agriculture Blocked | High | 68 | SHA | 5 |  |  | 2009-07-28 | No | Open
South East | Paktika | Dila | A1 | {BBACF20D-9F40-48E6-9C99-F5E3B3D2B708} | c0a8-008e-1323832462a-5737599b-13a3-2 | MF-HQ-12646 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2903/00579/MF003 | 360000 | 68.0117 | 32.631 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-156 | Paktika Demining Project-03 |  |  |  |  | 1397 |  | {BBACF20D-9F40-48E6-9C99-F5E3B3D2B708} |  | Low | Critical Infrastracture | High | 571 | SHA | 3 |  |  | 2009-07-28 | No | Open
South East | Paktika | Dila | Malik Dost Mohd | {E541C959-6028-4FC2-8DE1-C2A50D5BD7F9} | c0a8-0057-12c3b9bd7a9-bd02e8d-2c586-2 | MF-HQ-13810 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/06943/MF007 | 360000 | 68.1095 | 32.6913 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-303 | Paktika Demining Project-05 AT |  |  |  |  | 1401 |  | {E541C959-6028-4FC2-8DE1-C2A50D5BD7F9} |  | Low | Comunity Centers | High | 68 | SHA | 5 |  |  | 2009-12-13 | No | Open
South East | Paktika | Dila | Monaray | {113C9213-0FF5-47F1-A3C2-94B091E3CDB1} | c0a8-0057-12c3ba5ab5d-8fe6060a-325f4- | MF-HQ-12762 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2903/06861/MF006 | 300000 | 68.2041 | 32.5243 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-263 | Paktika Demining Project-02 AT |  |  |  |  | 1400 |  | {113C9213-0FF5-47F1-A3C2-94B091E3CDB1} |  | Low | Critical Infrastracture | High | 223 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktika | Dila | Pazgai | {B8081E9B-7559-4952-8280-1E30D5B61169} | c0a8-0057-12c3ba7cc7f-cf9f693c-33af6- | MF-HQ-12655 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2903/00563/MF001 | 80000 | 68.1204 | 32.4817 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-156 | Paktika Demining Project-03 |  |  |  |  | 1397 |  | {B8081E9B-7559-4952-8280-1E30D5B61169} |  | Medium | Water Blocked | High | 94 | SHA | 3 |  |  | 2009-07-28 | No | Open
South East | Paktika | Dila | Reg Babbray | {CF6FD6EF-46A4-4C67-9A82-FC6A149268C4} | c0a8-0057-12c3bb75499-ac56d107-3cc8b- | MF-HQ-12652 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2903/00642/MF004 | 558000 | 68.1403 | 32.5587 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-263 | Paktika Demining Project-02 AT |  |  |  |  | 1400 |  | {CF6FD6EF-46A4-4C67-9A82-FC6A149268C4} |  | Low | Other | High | 634 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktika | Gayan | Wochakay | {6C58FF15-458D-485C-93A2-C58D7B2F314A} | c0a8-0057-12c3b9c0666-b7583cc9-2c74c- | MF-HQ-12769 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2910/00330/MF001 | 145450 | 69.3975 | 33.0697 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-282 | Paktika Demining Project-06 |  |  |  |  | 1400 |  | {6C58FF15-458D-485C-93A2-C58D7B2F314A} |  | Low | Infrastructure | High | 12 | SHA | 5 |  |  | 2009-07-28 | No | Open
South East | Paktika | Gomal | Amankhel | {9DE79C3D-EE7B-412D-9ADF-0841FC1ED38A} | c0a8-0057-12c3b89793f-b42c89aa-2021c- | MF-HQ-12728 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2906/08220/MF001 | 80000 | 68.8754 | 32.5481 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-156 | Paktika Demining Project-03 |  |  |  |  | 1397 |  | {9DE79C3D-EE7B-412D-9ADF-0841FC1ED38A} |  | High with Victim | High with Victims | High | 0 | SHA | 2 |  |  | 2009-07-28 | No | Open
South East | Paktika | Gomal | Yahkhel | {3477A06E-CAEB-4762-AD50-7FE3E861F418} | c0a8-0057-12c3bb7486a-99bd36ed-3cc32- | MF-HQ-12723 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2906/08224/MF002 | 480000 | 68.9234 | 32.6172 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-156 | Paktika Demining Project-03 |  |  |  |  | 1397 |  | {3477A06E-CAEB-4762-AD50-7FE3E861F418} |  | High with Victim | High with Victims | High | 0 | SHA | 2 |  |  | 2009-07-28 | No | Open
South East | Paktika | Jani Khel | Shaturi | {9C3F57AD-73D8-4316-A22A-BB03633CE86A} | c0a8-0057-12c3b7d5673-2aa8d6cd-17975- | MF-HQ-13802 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2919/06817/MF001 | 360000 | 68.3583 | 32.8024 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-265 | Paktika Demining Project-03 AT |  |  |  |  | 1400 |  | {9C3F57AD-73D8-4316-A22A-BB03633CE86A} |  | Low | Comunity Centers | Substantial | 176 | SHA | 4 |  |  | 2009-12-13 | No | Open
South East | Paktika | Mata Khan | Baykar | {D1121238-5D2D-445C-8414-9C8788D24DE9} | c0a8-0057-12c3b8e39a5-a0b81d7f-23708- | MF-HQ-12716 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2915/08720/MF001 | 90000 | 68.8746 | 33.2407 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-262 | Paktika Demining Project-01 AT |  |  |  |  | 1400 |  | {D1121238-5D2D-445C-8414-9C8788D24DE9} |  | Low | Comunity Centers | Substantial | 138 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktika | Mata Khan | Zardad | {760C690E-5301-4714-9522-4C3325F99563} | c0a8-0057-12c3b8de07f-4d0457e3-2328f- | MF-HQ-12720 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2915/8739/MF002 | 120000 | 68.8281 | 33.3428 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {760C690E-5301-4714-9522-4C3325F99563} |  | High with Victim | High with Victims | Substantial | 104 | SHA | 2 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sar Hawza | Kazaki | {D471A454-E2F6-4A25-ACA3-D2D204C035D2} | c0a8-0057-12c3b82a511-5e2d21dc-1b4d8- | MF-HQ-12712 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2914/00656/MF022 | 150000 | 69.0701 | 33.017 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {D471A454-E2F6-4A25-ACA3-D2D204C035D2} |  | High with Victim | High with Victims | Substantial | 145 | SHA | 2 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sar Hawza | Layaki | {847A8EEC-86DF-4729-9BAA-619D83CF5731} | c0a8-0057-12c3bb3bd92-f1bf0817-3abf7- | MF-HQ-12688 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2914/00404/MF021 | 175000 | 69.1152 | 33.0407 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-283 | Paktika Demining Project-04 AT |  |  |  |  | 1401 |  | {847A8EEC-86DF-4729-9BAA-619D83CF5731} |  | Low | Critical Infrastracture | Substantial | 40 | SHA | 5 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sar Hawza | Shatore (1) | {387CA3FA-16FB-4F53-B40F-1193AAF2FBBF} | c0a8-0057-12c3b7c6544-cbde5b26-16e6c- | MF-HQ-12684 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2914/07387/MF0025 | 120000 | 69.0817 | 32.9799 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-254 | Paktika Demining Project-04 |  |  |  |  | 1400 |  | {387CA3FA-16FB-4F53-B40F-1193AAF2FBBF} |  | Low | Critical Infrastracture | Substantial | 111 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sar Hawza | Shatore (1) | {387CA3FA-16FB-4F53-B40F-1193AAF2FBBF} | c0a8-0057-12c3babdb91-e4973da3-36046- | MF-HQ-12683 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2914/07387/MF0024 | 225000 | 69.0817 | 32.9799 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-254 | Paktika Demining Project-04 |  |  |  |  | 1400 |  | {387CA3FA-16FB-4F53-B40F-1193AAF2FBBF} |  | Low | Critical Infrastracture | Substantial | 88 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sar Hawza | Sultani (2) | {B1444E66-3807-4F5F-8D33-B92B0C050606} | c0a8-0057-12c3b9d00d6-49acd701-2d15d- | MF-HQ-12700 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2914/07378/MF020 | 100000 | 68.9771 | 33.0613 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-254 | Paktika Demining Project-04 |  |  |  |  | 1400 |  | {B1444E66-3807-4F5F-8D33-B92B0C050606} |  | Low | Agriculture Blocked | Substantial | 41 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sar Hawza | Sundurkhel | {1B84AE2E-0900-4BF7-9905-6A2A8F9DD8F0} | c0a8-0057-12c3baf570e-2ef4a370-381fd- | MF-HQ-12697 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2914/07383/MF023 | 187500 | 69.0823 | 32.9534 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-254 | Paktika Demining Project-04 |  |  |  |  | 1400 |  | {1B84AE2E-0900-4BF7-9905-6A2A8F9DD8F0} |  | Low | Agriculture Blocked | Substantial | 137 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sarobi | Naway Pasanay | {761B649D-0369-47E7-935F-7F15E57EA816} | c0a8-0057-12c3ba80836-f2c56dea-33d3b- | MF-HQ-12748 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2908/08281/MF003 | 125000 | 69.0816 | 32.8276 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-282 | Paktika Demining Project-06 |  |  |  |  | 1400 |  | {761B649D-0369-47E7-935F-7F15E57EA816} |  | Low | Agriculture Blocked | Substantial | 14 | SHA | 5 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sarobi | Pastolay | {9F4EF7D7-900A-4810-B027-25DDB0A482B1} | c0a8-0057-12c3bae3d3a-c4fd058e-3775e- | MF-HQ-12757 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2908/00488/MF006 | 420000 | 69.0856 | 32.8515 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-254 | Paktika Demining Project-04 |  |  |  |  | 1400 |  | {9F4EF7D7-900A-4810-B027-25DDB0A482B1} |  | Low | Agriculture Blocked | Substantial | 842 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sarobi | Sadozi Kalay | {6AC904BE-FBC7-4A8B-BAB2-5F3635DBA3D0} | c0a8-0057-12c3b919bb5-84466bb0-259ca- | MF-HQ-12662 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2908/07286/MF005 | 100000 | 69.0929 | 32.8492 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-282 | Paktika Demining Project-06 |  |  |  |  | 1400 |  | {6AC904BE-FBC7-4A8B-BAB2-5F3635DBA3D0} |  | Low | Comunity Centers | Substantial | 302 | SHA | 5 |  |  | 2009-07-21 | No | Open
South East | Paktika | Sarobi | Sadozi Kalay | {6AC904BE-FBC7-4A8B-BAB2-5F3635DBA3D0} | c0a8-0057-12c3b91e6a5-77081fd-25d3f-8 | MF-HQ-12664 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2908/07286/MF004 | 17500 | 69.0929 | 32.8492 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-282 | Paktika Demining Project-06 |  |  |  |  | 1400 |  | {6AC904BE-FBC7-4A8B-BAB2-5F3635DBA3D0} |  | Low | Agriculture Blocked | Substantial | 37 | SHA | 5 |  |  | 2009-07-21 | No | Open
South East | Paktika | Sharan | Ambar Khel | {3E5BF63B-045B-4835-96AB-38A777727ABA} | c0a8-0057-12c3baef7d0-7f9d8b21-37e92- | MF-HQ-13801 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/06943/MF019 | 3625 | 68.8038 | 33.151 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {3E5BF63B-045B-4835-96AB-38A777727ABA} |  | Medium | Agriculture Blocked | Moderate | 120 | SHA | 3 |  |  | 2009-12-13 | No | Open
South East | Paktika | Sharan | Cala | {C8022140-6D89-4441-858E-8249094686B2} | c0a8-0057-12c3b80145e-f69f2f08-197ee- | MF-HQ-12636 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/06959/MF0017 | 150000 | 68.6973 | 33.2568 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-282 | Paktika Demining Project-06 |  |  |  |  | 1400 |  | {C8022140-6D89-4441-858E-8249094686B2} |  | Low | Critical Infrastracture | Moderate | 60 | SHA | 5 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sharan | Cala | {C8022140-6D89-4441-858E-8249094686B2} | c0a8-0057-12c3b8018c1-e0f6389a-1981a- | MF-HQ-12639 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/06959/MF0018 | 500000 | 68.6912 | 33.2644 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-262 | Paktika Demining Project-01 AT |  |  |  |  | 1400 |  | {C8022140-6D89-4441-858E-8249094686B2} |  | Low | Agriculture Blocked | Moderate | 111 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sharan | Imni Khel | {CC1CFF4C-5B94-4F00-BD7D-69CE41545BC9} | c0a8-0057-12c3b7d5809-cc02fb37-17986- | MF-HQ-12633 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/06930/MF0013 | 2500 | 68.7994 | 33.1582 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {CC1CFF4C-5B94-4F00-BD7D-69CE41545BC9} |  | High | Critical Infrastracture | Moderate | 0 | SHA | 3 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sharan | Imni Khel | {CC1CFF4C-5B94-4F00-BD7D-69CE41545BC9} | c0a8-0057-12c3b90a229-14605a23-25010- | MF-HQ-12625 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/06930/MF0012 | 2500 | 68.7994 | 33.1582 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {CC1CFF4C-5B94-4F00-BD7D-69CE41545BC9} |  | High | Critical Infrastracture | Moderate | 0 | SHA | 3 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sharan | Imni Khel | {CC1CFF4C-5B94-4F00-BD7D-69CE41545BC9} | c0a8-0057-12c3ba053bb-edb27ef6-2f24e- | MF-HQ-12630 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/06930/MF0014 | 5625 | 68.7994 | 33.1582 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {CC1CFF4C-5B94-4F00-BD7D-69CE41545BC9} |  | Medium | Critical Infrastracture | Moderate | 0 | SHA | 3 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sharan | Imni Khel | {CC1CFF4C-5B94-4F00-BD7D-69CE41545BC9} | c0a8-0057-12c3ba3990b-cd290374-311e4- | MF-HQ-12627 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/06930/MF0015 | 155 | 68.7994 | 33.1582 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {CC1CFF4C-5B94-4F00-BD7D-69CE41545BC9} |  | High | Critical Infrastracture | Moderate | 0 | SHA | 3 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sharan | Jabbar Khel | {7309AE9E-5031-4CED-8FA3-2F20D7F70679} | c0a8-0057-12c3baf4562-bfe64a84-3815a- | MF-HQ-12657 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/06954/MF008 | 86200 | 68.7952 | 33.1629 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {7309AE9E-5031-4CED-8FA3-2F20D7F70679} |  | Medium | Critical Infrastracture | Moderate | 699 | SHA | 3 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sharan | Naw Abad Haji Kharoti | {99D92676-E427-423F-9011-443FE7621B1B} | c0a8-0057-12c3b9ed685-7a4dc9fd-2e37e- | MF-HQ-12642 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/00466/MF0016 | 150000 | 68.7199 | 33.1992 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {99D92676-E427-423F-9011-443FE7621B1B} |  | High with Victim | High with Victims | Moderate | 15 | SHA | 2 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sharan | Sra Kala | {21C619E9-769E-49F3-9B3F-0AC7641DEC70} | c0a8-0057-12c3ba0e712-65afadbb-2f7c9- | MF-HQ-12618 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/06981/MF009 | 600000 | 68.8311 | 33.1768 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-262 | Paktika Demining Project-01 AT |  |  |  |  | 1400 |  | {21C619E9-769E-49F3-9B3F-0AC7641DEC70} |  | Low | Agriculture Blocked | Moderate | 90 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktika | Sharan | Sra Kala | {21C619E9-769E-49F3-9B3F-0AC7641DEC70} | c0a8-0057-12c3bb530ca-76bbd0ae-3b99f- | MF-HQ-12613 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2901/06981/MF010 | 4800 | 68.8214 | 33.173 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {21C619E9-769E-49F3-9B3F-0AC7641DEC70} |  | Medium | Water Blocked | Moderate | 126 | SHA | 3 |  |  | 2009-07-28 | No | Open
South East | Paktika | Urgun | Khaleqdad Kalay | {8ADC370C-4550-410B-AD6D-8717839B14C9} | c0a8-0057-12c3b9477b9-b2773857-2782b- | MF-HQ-12824 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2911/07288/MF077 | 300000 | 69.1227 | 32.8481 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {8ADC370C-4550-410B-AD6D-8717839B14C9} |  | Medium | Critical Infrastracture | Substantial | 114 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Paktika | Urgun | Khaleqdad Kalay | {8ADC370C-4550-410B-AD6D-8717839B14C9} | c0a8-0057-12c3bb0bccf-b43a75a5-38f4b- | MF-HQ-12822 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2911/07288/MF078 | 100000 | 69.1137 | 32.8539 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {8ADC370C-4550-410B-AD6D-8717839B14C9} |  | Medium | Critical Infrastracture | Substantial | 378 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Paktika | Urgun | Miragul Kalay | {298DF8C2-3714-48A5-9AE3-4DAF534E11F4} | c0a8-0057-12c3b9bcbb8-dfa1e503-2c50a- | MF-HQ-12808 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2911/07314/MF0082 | 36800 | 69.1881 | 32.9954 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {298DF8C2-3714-48A5-9AE3-4DAF534E11F4} |  | Medium | Critical Infrastracture | Substantial | 220 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Paktika | Urgun | Nazargul Kalay | {9F1306BB-8BB3-412E-AC3B-7D48CFE4A9E9} | c0a8-0057-12c3bb7f70e-fd87b5f8-3d28d- | MF-HQ-12827 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2911/07340/MF079 | 409500 | 69.2214 | 32.9565 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-264 | Paktika Demining Project-05 |  |  |  |  | 1400 |  | {9F1306BB-8BB3-412E-AC3B-7D48CFE4A9E9} |  | Low | Agriculture Blocked | Substantial | 182 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktika | Urgun | Qara Khel | {BA34BA9C-CA02-4375-BBF4-00E0762033AD} | c0a8-0057-12c3bb88872-193aa838-3d76e- | MF-HQ-12817 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2911/00574/MF075 | 250000 | 69.1566 | 32.9207 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-264 | Paktika Demining Project-05 |  |  |  |  | 1400 |  | {BA34BA9C-CA02-4375-BBF4-00E0762033AD} |  | Low | Agriculture Blocked | Substantial | 602 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktika | Urgun | Qarya Shaykh-ha | {B8242393-6016-4279-9D78-0FA3673E378A} | c0a8-0057-12c3b951579-d1a8009e-27ed8- | MF-HQ-12818 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2911/07298/MF0076 | 200000 | 69.1244 | 32.8725 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-264 | Paktika Demining Project-05 |  |  |  |  | 1400 |  | {B8242393-6016-4279-9D78-0FA3673E378A} |  | Low | Critical Infrastracture | Substantial | 378 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktika | Urgun | Urgun | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} | c0a8-0057-12c3b7ff7c9-d7f44e47-196b9- | MF-SE-317 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2911/07303/MF(R069) | 1059460 | 69.1203 | 32.8984 | Open | AP Only | AP Only | MineField |  | MBT Project-049 | Paktika Demining Project-01 |  |  |  |  | 1397 |  | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} |  | High with Victim | High with Victims | Substantial | 1114 | CHA | 2 |  |  | 2008-10-27 16:30 | No | Open
South East | Paktika | Urgun | Urgun | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} | c0a8-0057-12c3b7ff9eb-f9459cf-196d4-d | MF-HQ-7741 | MCPA - Mine Clearance Planning Agency | AF/2911/07303/MF0069 | 65538 | 69.0877 | 32.9 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-049 | Paktika Demining Project-01 |  |  |  |  | 1397 |  | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} |  | High with Victim | High with Victims | Substantial | 20 | CHA | 2 |  |  | 2000-11-12 | No | Open
South East | Paktika | Urgun | Urgun | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} | c0a8-0057-12c3b9e7036-e7a2dd89-2dfa3- | MF-SE-321 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2911/07303/MF(R072) | 91477 | 69.1421 | 32.9039 | Open | AT Only | AT Only | MineField |  | MBT Project-049 | Paktika Demining Project-01 |  |  |  |  | 1397 |  | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} |  | High with Victim | High with Victims | Substantial | 441 | CHA | 2 |  |  | 2008-10-27 16:30 | No | Open
South East | Paktika | Urgun | Urgun | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} | c0a8-0057-12c3b9e746a-4af1c042-2dfb8- | MF-HQ-9026 | MCPA - Mine Clearance Planning Agency | AF/2911/07303/MF0072 | 88523 | 69.1428 | 32.9008 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-049 | Paktika Demining Project-01 |  |  |  |  | 1397 |  | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} |  | High with Victim | High with Victims | Substantial | 1058 | CHA | 2 |  |  | 2002-06-25 | No | Open
South East | Paktika | Urgun | Urgun | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} | c0a8-0057-12c3bb7ad14-99ad4eb9-3cfec- | MF-HQ-5164 | MCPA - Mine Clearance Planning Agency | AF/2911/07303/MF0048 | 13000 | 69.1476 | 32.9089 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-049 | Paktika Demining Project-01 |  |  |  |  | 1397 |  | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} |  | High with Victim | High with Victims | Substantial | 555 | CHA | 2 |  |  | 1998-06-11 | No | Open
South East | Paktika | Urgun | Urgun | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} | c0a8-0057-12c3bb7b07e-e69501f1-3cfff- | MF-SE-324 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2911/07303/MF(R048) | 396500 | 69.1103 | 32.9107 | Open | AP Only | AP Only | MineField |  | MBT Project-049 | Paktika Demining Project-01 |  |  |  |  | 1397 |  | {7BE52620-94BE-42AD-AED3-F4BDB40E6FCE} |  | High with Victim | High with Victims | Substantial | 202 | CHA | 2 |  |  | 2008-10-28 16:30 | No | Open
South East | Paktika | Urgun | Wurzana Kalay | {613C5D81-16B1-41E9-90DE-3CE6049DB33D} | c0a8-0057-12c3b8e5d98-1b1e2804-23888- | MF-HQ-12814 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2911/07333/MF0080 | 40000 | 69.2335 | 33.0782 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-155 | Paktika Demining Project-02 |  |  |  |  | 1398 |  | {613C5D81-16B1-41E9-90DE-3CE6049DB33D} |  | Medium | Critical Infrastracture | Substantial | 220 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Paktika | Urgun | Wurzana Kalay | {613C5D81-16B1-41E9-90DE-3CE6049DB33D} | c0a8-0057-12c3ba55c74-3c839aaf-32328- | MF-HQ-12816 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2911/07333/MF0081 | 144000 | 69.2275 | 33.0601 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-264 | Paktika Demining Project-05 |  |  |  |  | 1400 |  | {613C5D81-16B1-41E9-90DE-3CE6049DB33D} |  | Medium | Critical Infrastracture | Substantial | 2069 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktika | Waza Khwa | Asheq Khel | {34F3A4B6-171C-4C47-A368-82AB9BB1FC12} | c0a8-0057-12c3b8546f4-b6d1878d-1d35c- | MF-HQ-6470 | MCPA - Mine Clearance Planning Agency | AF/2904/07080/MF0019 | 112504 | 68.4135 | 32.1721 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-156 | Paktika Demining Project-03 |  |  |  |  | 1397 |  | {34F3A4B6-171C-4C47-A368-82AB9BB1FC12} |  | Medium | Critical Infrastracture | High | 126 | CHA | 3 |  |  | 1999-08-10 | No | Open
South East | Paktika | Waza Khwa | Chatrey | {DEB6F555-AD6E-4FBF-B61E-A6BE1F0FBBB7} | c0a8-0057-12c3b7f7939-9d9163b3-190fe- | MF-HQ-12823 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2904/07040/MF028 | 76874 | 68.2606 | 32.1277 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-283 | Paktika Demining Project-04 AT |  |  |  |  | 1401 |  | {DEB6F555-AD6E-4FBF-B61E-A6BE1F0FBBB7} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Paktika | Waza Khwa | Chatrey | {DEB6F555-AD6E-4FBF-B61E-A6BE1F0FBBB7} | c0a8-0057-12c3b85eafe-aec719e7-1da6b- | MF-HQ-12825 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2904/07040/MF027 | 214200 | 68.2786 | 32.1163 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-156 | Paktika Demining Project-03 |  |  |  |  | 1397 |  | {DEB6F555-AD6E-4FBF-B61E-A6BE1F0FBBB7} |  | Medium | Critical Infrastracture | High | 15 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Paktika | Waza Khwa | Chatrey | {DEB6F555-AD6E-4FBF-B61E-A6BE1F0FBBB7} | c0a8-0057-12c3b92ab60-a9baf313-2651a- | MF-HQ-12821 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2904/07040/MF026 | 125000 | 68.2769 | 32.1244 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-265 | Paktika Demining Project-03 AT |  |  |  |  | 1400 |  | {DEB6F555-AD6E-4FBF-B61E-A6BE1F0FBBB7} |  | Low | Agriculture Blocked | High | 0 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktika | Waza Khwa | Haji Janshah Kalay | {EA98D30A-09BC-4E78-8449-1EEA2CB47D0B} | c0a8-0057-12c3ba18afd-9f66320b-2fdfe- | MF-HQ-12810 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2904/07049/MF029 | 495000 | 68.1978 | 32.2539 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-265 | Paktika Demining Project-03 AT |  |  |  |  | 1400 |  | {EA98D30A-09BC-4E78-8449-1EEA2CB47D0B} |  | Low | Critical Infrastracture | High | 310 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktika | Waza Khwa | Laswandey | {28A7CFCE-273A-420A-ADAC-57815F00A91A} | c0a8-0057-12c3bb38f42-49dd403-3aa48-6 | MF-HQ-12815 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2904/07073/MF024 | 480000 | 68.3223 | 32.356 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-265 | Paktika Demining Project-03 AT |  |  |  |  | 1400 |  | {28A7CFCE-273A-420A-ADAC-57815F00A91A} |  | Low | Critical Infrastracture | High | 271 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktika | Waza Khwa | Wasel Khel | {B6366D4A-4FF0-41AA-A00F-B95683FC656F} | c0a8-0057-12c3b99e72c-87c8c64c-2b174- | MF-HQ-12774 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2904/07066/MF025 | 175050 | 68.3519 | 32.1765 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-283 | Paktika Demining Project-04 AT |  |  |  |  | 1401 |  | {B6366D4A-4FF0-41AA-A00F-B95683FC656F} |  | Low | Critical Infrastracture | High | 84 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Paktika | Waza Khwa | Waza Khwa | {B7B12BE1-CE9E-47A7-9C8F-8AA36B8C5542} | c0a8-0057-12c3b8544b3-e284ff61-1d345- | MF-SE-318 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2904/31863/MF(R019) | 327596 | 68.4271 | 32.1712 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-283 | Paktika Demining Project-04 AT |  |  |  |  | 1401 |  | {B7B12BE1-CE9E-47A7-9C8F-8AA36B8C5542} |  | Low | Agriculture Blocked | High | 85 | CHA | 5 |  |  | 2008-10-27 16:30 | No | Open
South East | Paktika | Waza Khwa | Waza Khwa | {B7B12BE1-CE9E-47A7-9C8F-8AA36B8C5542} | c0a8-0057-12c3ba7a0ce-5049b5dd-3396a- | MF-SE-320 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2904/31863/MF(R022) | 162098 | 68.3507 | 32.198 | Open | AT Only | AT Only | MineField |  | MBT Project-156 | Paktika Demining Project-03 |  |  |  |  | 1397 |  | {B7B12BE1-CE9E-47A7-9C8F-8AA36B8C5542} |  | Medium | Critical Infrastracture | High | 201 | CHA | 3 |  |  | 2008-10-27 16:30 | No | Open
South East | Paktika | Waza Khwa | Waza Khwa | {B7B12BE1-CE9E-47A7-9C8F-8AA36B8C5542} | c0a8-0057-12c3ba7a2f0-add8a91a-33980- | MF-HQ-7307 | MCPA - Mine Clearance Planning Agency | AF/2904/31863/MF0022 | 137902 | 68.3517 | 32.2028 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-156 | Paktika Demining Project-03 |  |  |  |  | 1397 |  | {B7B12BE1-CE9E-47A7-9C8F-8AA36B8C5542} |  | Medium | Agriculture Blocked | High | 23 | CHA | 3 |  |  | 2000-06-29 | No | Open
South East | Paktika | Zarghun Shahr | Baloo Khel | {FDA097FB-C0BD-4B2D-B64B-4DEBBB142945} | c0a8-0057-12c3b822fa5-324b66a0-1afcb- | MF-HQ-12680 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2902/00803/MF0012 | 280000 | 68.443 | 32.8385 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-283 | Paktika Demining Project-04 AT |  |  |  |  | 1401 |  | {FDA097FB-C0BD-4B2D-B64B-4DEBBB142945} |  | Low | Agriculture Blocked | Substantial | 0 | SHA | 5 |  |  | 2009-07-28 | No | Open
South East | Paktika | Zarghun Shahr | Mohammad Hasan | {8A3B7051-4A7A-464A-A15F-8CBCC4C66D89} | c0a8-0057-12c3b9612d4-8dd8be59-2894c- | MF-HQ-12674 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2902/06689/MF0011 | 50000 | 68.4685 | 32.8154 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-265 | Paktika Demining Project-03 AT |  |  |  |  | 1400 |  | {8A3B7051-4A7A-464A-A15F-8CBCC4C66D89} |  | Low | Comunity Centers | Substantial | 1312 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktika | Zarghun Shahr | Mohammad Hasan | {8A3B7051-4A7A-464A-A15F-8CBCC4C66D89} | c0a8-0057-12c3bafa903-7710214-384f5-d | MF-HQ-12671 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2902/06689/MF010 | 45000 | 68.4793 | 32.8157 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-265 | Paktika Demining Project-03 AT |  |  |  |  | 1400 |  | {8A3B7051-4A7A-464A-A15F-8CBCC4C66D89} |  | Low | Comunity Centers | Substantial | 363 | SHA | 4 |  |  | 2009-07-28 | No | Open
South East | Paktya | Ahmad Abad | Ata'i Kala | {650F286F-5537-491F-88F3-EADF85468B9C} | c0a8-0057-12c3b9125f1-a2d9b91f-2556e- | MF-HQ-14068 | MCPA - Mine Clearance Planning Agency | AF/0725/08431/MF0001 | 39397 | 69.3444 | 33.7045 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-10-01 | 2013-12-23 | 1392 | DAFA | {650F286F-5537-491F-88F3-EADF85468B9C} |  |  |  | Substantial | 237 | CHA | 3 |  |  | 2010-01-19 | No | Complete
South East | Paktya | Ahmad Abad | Wach Ghrak | {E228FA4A-1079-471E-96D7-B24DD72A4A57} | c0a8-0057-12c3ba22bbc-be75fcc9-30434- | MF-HQ-3506 | MCPA - Mine Clearance Planning Agency | AF/0725/08402/MF0030 | 8184 | 69.295 | 33.7215 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-11-23 | 2013-12-12 | 1392 | DAFA | {E228FA4A-1079-471E-96D7-B24DD72A4A57} |  |  |  | Substantial | 83 | CHA | 5 |  |  | 2010-05-27 | No | Complete
South East | Paktya | Ahmad Abad | Zundikhel | {B30A10D2-692E-423C-B41C-3F401695E351} | c0a8-0057-12c3bb2ad20-2d73ca25-3a19b- | MF-HQ-14073 | MCPA - Mine Clearance Planning Agency | AF/0722/08430/MF0008 | 109043 | 69.3246 | 33.7479 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-06-01 | 2013-09-30 | 1392 | DAFA | {B30A10D2-692E-423C-B41C-3F401695E351} |  |  |  | Substantial | 129 | CHA | 4 |  |  | 2010-01-19 | No | Complete
South East | Paktya | Ali Khail (Jaji) | Ali Khil | {C6F50D65-BFE5-4ECF-A825-B33F723FFBF8} | c0a8-0009-14106dd9be7-8f5e92bd-8e6b-8 | Hz-ID-18133 | MCPA - Mine Clearance Planning Agency | AF/0723/08093/MF0121 | 8251 | 69.7219 | 33.9337 | Open | AP Only | AP Only | MineField |  | MBT Project-099 | Paktya Demining Project-02 |  |  |  |  | 1394 |  | {C6F50D65-BFE5-4ECF-A825-B33F723FFBF8} |  | High with Victim | High with Victims | Substantial | 233 | CHA | 2 |  |  | 2013-07-01 16:30 | No | Open
South East | Paktya | Ali Khail (Jaji) | Ali Khil | {C6F50D65-BFE5-4ECF-A825-B33F723FFBF8} | c0a8-0009-141d5407e70-ff1b4c21-315-6b | Hz-ID-18134 | MCPA - Mine Clearance Planning Agency | AF/0723/08093/MF0122 | 1517 | 69.7318 | 33.9481 | Open | AT Only | AT Only | MineField |  | MBT Project-099 | Paktya Demining Project-02 |  |  |  |  | 1394 |  | {C6F50D65-BFE5-4ECF-A825-B33F723FFBF8} |  | High with Victim | High with Victims | Substantial | 254 | CHA | 2 |  |  | 2013-07-02 16:30 | No | Open
South East | Paktya | Ali Khail (Jaji) | Ali Khil | {C6F50D65-BFE5-4ECF-A825-B33F723FFBF8} | c0a8-0057-12c3b723bce-37e8d185-f730-2 | MF-HQ-14650 | MCPA - Mine Clearance Planning Agency | AF/0723/08093/MF0115 | 2869 | 69.7076 | 33.9445 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-099 | Paktya Demining Project-02 |  |  |  |  | 1394 |  | {C6F50D65-BFE5-4ECF-A825-B33F723FFBF8} |  | High with Victim | High with Victims | Substantial | 3948 | CHA | 1 | Yes | This is the last minefield in the community with high priority for the clearance. | 2010-06-14 | No | Open
South East | Paktya | Ali Khail (Jaji) | Bariz Khil | {2D6AE8D6-6925-4794-961D-9B84041FC19F} | c0a8-0009-14490eab07b-eac4cf34-5fb-fd | Hz-ID-18403 | ATC - Afghan Technical Consultants | AF/0723/00126/MF0124 | 13270 | 69.6919 | 33.9519 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {2D6AE8D6-6925-4794-961D-9B84041FC19F} |  | High | Critical Infrastracture | Substantial | 1936 | CHA | 3 |  |  | 2013-11-21 16:30 | No | Open
South East | Paktya | Ali Khail (Jaji) | Bariz Khil | {2D6AE8D6-6925-4794-961D-9B84041FC19F} | c0a8-0057-12c3b8054c6-764ea23b-19a9d- | MF-HQ-11130 | MCPA - Mine Clearance Planning Agency | AF/0723/00126/MF0093 | 42377 | 69.6919 | 33.9519 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-256 | Paktya Demining Project-07 | VTF | Yes | 2013-10-01 | 2013-12-31 | 1392 | ATC | {2D6AE8D6-6925-4794-961D-9B84041FC19F} |  |  |  | Substantial | 69 | CHA | 1 | Yes | As per assesment of the task is very important most of the returness came back to the village and wants to build new house. | 2009-04-15 | No | Complete
South East | Paktya | Ali Khail (Jaji) | Bariz Khil | {2D6AE8D6-6925-4794-961D-9B84041FC19F} | c0a8-008e-13112f6fdaf-8bec9d34-1b31-7 | MF-SE-13 | MCPA - Mine Clearance Planning Agency | AF/0723/00126/MF0070 | 1661 | 69.6961 | 33.9445 | Open | AT Only | AT Only | MineField |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {2D6AE8D6-6925-4794-961D-9B84041FC19F} |  | High Requested | Resettlment/Local Request | Substantial | 1105 | CHA | 1 | Yes | As per assesment of the task is very important most of the returness came back to the village and wants to build new house. | 2003-07-21 | No | Open
South East | Paktya | Ali Khail (Jaji) | Bayankhel | {948B7E88-5E96-42BD-841C-BD6EDA02CF19} | c0a8-0009-14516e70a69-93032f96-40a-45 | Hz-ID-18235 | ATC - Afghan Technical Consultants | AF/0723/08097/MF0123 | 45789 | 69.763 | 33.9542 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {948B7E88-5E96-42BD-841C-BD6EDA02CF19} |  | High with Victim | High with Victims | Substantial | 651 | CHA | 1 |  |  | 2013-10-31 16:30 | No | Open
South East | Paktya | Ali Khail (Jaji) | Bayankhel | {948B7E88-5E96-42BD-841C-BD6EDA02CF19} | c0a8-0057-12c3ba141ce-9b7d3c42-2fb4b- | MF-HQ-10661 | MCPA - Mine Clearance Planning Agency | AF/0723/08097/MF0100 | 55367 | 69.763 | 33.9542 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256 | Paktya Demining Project-07 | VTF | Yes | 2013-10-01 | 2013-12-31 | 1392 | ATC | {948B7E88-5E96-42BD-841C-BD6EDA02CF19} |  |  |  | Substantial | 713 | CHA | 1 | Yes | As per assesment of MACCA Regional Office Gardiz, these tasks are very close to the resedentional area it's agri land of Bayan Khail resedence. It was larg contaminated land most places have been cleared in the past but the prolum is not completely solved | 2009-04-22 | No | Complete
South East | Paktya | Ali Khail (Jaji) | Bayankhel | {948B7E88-5E96-42BD-841C-BD6EDA02CF19} | c0a8-0057-12c3ba143d1-4e0ab30c-2fb64- | MF-HQ-11159 | MCPA - Mine Clearance Planning Agency | AF/0723/08097/MF0101 | 30459 | 69.763 | 33.9542 | Open | AP Only | AP Only | MineField |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {948B7E88-5E96-42BD-841C-BD6EDA02CF19} | Planned Agency Removed | High with Victim | High with Victims | Substantial | 713 | CHA | 1 | Yes | As per assesment of MACCA Regional Office Gardiz, these tasks are very close to the resedentional area it's agri land of Bayan Khail resedence. It was larg contaminated land most places have been cleared in the past but the prolum is not completely solved | 2009-04-23 | No | Open
South East | Paktya | Ali Khail (Jaji) | Bayankhel | {948B7E88-5E96-42BD-841C-BD6EDA02CF19} | c0a8-0057-12c3bb66629-6d7ced53-3c43c- | MF-HQ-6345 | MCPA - Mine Clearance Planning Agency | AF/0723/08097/MF0071 | 58577 | 69.764 | 33.9585 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-256 | Paktya Demining Project-07 | VTF | Yes | 2013-10-01 | 2013-12-31 | 1392 | ATC | {948B7E88-5E96-42BD-841C-BD6EDA02CF19} |  |  |  | Substantial | 46 | CHA | 1 | Yes | As per assesment of MACCA Regional Office Gardiz, these tasks are very close to the resedentional area it's agri land of Bayan Khail resedence. It was larg contaminated land most places have been cleared in the past but the prolum is not completely solved | 1999-07-10 | No | Complete
South East | Paktya | Ali Khail (Jaji) | Bayankhel | {948B7E88-5E96-42BD-841C-BD6EDA02CF19} | c0a8-008e-132c9907e5a-cb6365a7-3728-6 | MF-16220 | MCPA - Mine Clearance Planning Agency | AF/0723/08097/MF0097 | 70587 | 69.7619 | 33.965 | Open | AP Only | AP Only | MineField |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {948B7E88-5E96-42BD-841C-BD6EDA02CF19} |  | High with Victim | High with Victims | Substantial | 522 | CHA | 1 | Yes | As per assesment of MACCA Regional Office Gardiz, these tasks are very close to the resedentional area it's agri land of Bayan Khail resedence. It was larg contaminated land most places have been cleared in the past but the prolum is not completely solved | 2009-05-27 16:30 | No | Open
South East | Paktya | Ali Khail (Jaji) | Ghunjay Ahmadkhel | {848082BA-16B7-426E-8BAD-18C9A23A15E7} | c0a8-0057-12c3bb1800b-660fb12e-3967c- | MF-HQ-11156 | MCPA - Mine Clearance Planning Agency | AF/0723/08099/MF0095 | 87302 | 69.755 | 33.9533 | Open | AP Only | AP Only | MineField |  | MBT Project-099 | Paktya Demining Project-02 |  |  |  |  | 1394 |  | {848082BA-16B7-426E-8BAD-18C9A23A15E7} |  | High with Victim | High with Victims | Substantial | 759 | CHA | 1 | Yes | Clearance of this task is too nessesory it is very afacted normal life of the people it has several accident. | 2009-04-22 | No | Open
South East | Paktya | Ali Khail (Jaji) | Ghunjay Ahmadkhel | {848082BA-16B7-426E-8BAD-18C9A23A15E7} | c0a8-0057-12c3bb181ff-a2985fdf-39694- | MF-HQ-11132 | MCPA - Mine Clearance Planning Agency | AF/0723/08099/MF0094 | 89528 | 69.755 | 33.9533 | Open | AP Only | AP Only | MineField |  | MBT Project-099 | Paktya Demining Project-02 |  |  |  |  | 1394 |  | {848082BA-16B7-426E-8BAD-18C9A23A15E7} |  | High with Victim | High with Victims | Substantial | 594 | CHA | 1 | Yes | Clearance of this task is too nessesory it is very afacted normal life of the people it has several accident. | 2009-04-20 | No | Open
South East | Paktya | Ali Khail (Jaji) | Kharshatal | {0384C9E5-07B3-4823-A46D-653BB0190F28} | c0a8-008e-132d31393cf-adba01a-8a85-27 | MF-16214 | MCPA - Mine Clearance Planning Agency | AF/0723/08104/MF0116 | 14052 | 69.7751 | 33.978 | Open | AP Only | AP Only | MineField |  | MBT Project-099 | Paktya Demining Project-02 |  |  |  |  | 1394 |  | {0384C9E5-07B3-4823-A46D-653BB0190F28} |  | High with Victim | High with Victims | Substantial | 332 | CHA | 1 | Yes | This is the last minefield in the community with high priority for the clearance. | 2010-12-07 16:30 | No | Open
South East | Paktya | Ali Khail (Jaji) | Kuz Ali Sangi | {1EB89621-8CAC-470F-B6E5-CCC146E0BD31} | c0a8-0057-12c3baded96-814b0f7-37466-6 | MF-SE-296 | MCPA - Mine Clearance Planning Agency | AF/0723/08105/MF(R082) | 61078 | 69.7713 | 33.9676 | Open | AP Only | AP Only | MineField |  | MBT Project-099 | Paktya Demining Project-02 |  |  |  |  | 1394 |  | {1EB89621-8CAC-470F-B6E5-CCC146E0BD31} |  | High with Victim | High with Victims | Substantial | 268 | CHA | 1 | Yes | These tasks are very close to the community center it has several accidents and high proirity for the clearace. | 2008-10-30 | No | Open
South East | Paktya | Ali Khail (Jaji) | Kuz Ali Sangi | {1EB89621-8CAC-470F-B6E5-CCC146E0BD31} | c0a8-00f6-137502d4993-ed0aea57-3ec6-e | MF-16771 | MCPA - Mine Clearance Planning Agency | AF/0723/08096/MF0099 | 67514 | 69.7649 | 33.9706 | Open | AP Only | AP Only | MineField |  | MBT Project-099 | Paktya Demining Project-02 |  |  |  |  | 1394 |  | {1EB89621-8CAC-470F-B6E5-CCC146E0BD31} |  | High with Victim | High with Victims | Substantial | 390 | CHA | 1 | Yes | These tasks are very close to the community center it has several accidents and high proirity for the clearace. | 2011-08-14 16:30 | No | Open
South East | Paktya | Ali Khail (Jaji) | Kuza Khermana | {46ECA101-0BB7-4A88-978F-FB562CDB2ABB} | c0a8-0057-12c3ba2cb63-a7f52b09-30a3a- | MF-HQ-10703 | MCPA - Mine Clearance Planning Agency | AF/0719/08141/MF0032 | 24831 | 69.6873 | 33.9026 | Open | AP Only | AP Only | MineField | Blank | MBT Project-256/B | Paktya Demining Project-07/B |  | No |  |  | 1394 | None | {46ECA101-0BB7-4A88-978F-FB562CDB2ABB} |  | High Requested | Resettlment/Local Request | Substantial | 589 | CHA | 1 | Yes | As per phesical assesment of the tasks these are solpy agri land. It need for urgent clearance. | 2009-05-18 | No | Open
South East | Paktya | Ali Khail (Jaji) | Kuza Khermana | {46ECA101-0BB7-4A88-978F-FB562CDB2ABB} | c0a8-0057-12c3ba2cdc3-2251df02-30a50- | MF-HQ-10704 | MCPA - Mine Clearance Planning Agency | AF/723/8141/MF0033 | 27372 | 69.6821 | 33.9034 | Open | AP Only | AP Only | MineField | Blank | MBT Project-256/B | Paktya Demining Project-07/B |  | No |  |  | 1394 | None | {46ECA101-0BB7-4A88-978F-FB562CDB2ABB} |  | High Requested | Resettlment/Local Request | Substantial | 589 | CHA | 1 | Yes | As per phesical assesment of the tasks these are solpy agri land. It need for urgent clearance. | 2009-05-19 | No | Open
South East | Paktya | Ali Khail (Jaji) | Kuza Khermana | {46ECA101-0BB7-4A88-978F-FB562CDB2ABB} | c0a8-0057-12c3bab20ec-b2429ebb-359a7- | MF-HQ-10699 | MCPA - Mine Clearance Planning Agency | AF/0719/08141/MF 0035 | 44455 | 69.6935 | 33.8995 | Open | AP Only | AP Only | MineField | Blank | MBT Project-256/B | Paktya Demining Project-07/B |  | No |  |  | 1394 | None | {46ECA101-0BB7-4A88-978F-FB562CDB2ABB} |  | High Requested | Resettlment/Local Request | Substantial | 139 | CHA | 1 | Yes | As per phesical assesment of the tasks these are solpy agri land. It need for urgent clearance. | 2009-05-25 | No | Open
South East | Paktya | Ali Khail (Jaji) | Kuza Khermana | {46ECA101-0BB7-4A88-978F-FB562CDB2ABB} | c0a8-008e-13117667ccb-7620a47c-267d-3 | MF-HQ-10708 | MCPA - Mine Clearance Planning Agency | AF/0723/08141/MF0034 | 21712 | 69.6862 | 33.9051 | Open | AP Only | AP Only | MineField | Blank | MBT Project-256/B | Paktya Demining Project-07/B |  | No |  |  | 1394 | None | {46ECA101-0BB7-4A88-978F-FB562CDB2ABB} |  | High Requested | Resettlment/Local Request | Substantial | 420 | CHA | 1 | Yes | As per phesical assesment of the tasks these are solpy agri land. It need for urgent clearance. | 2009-06-07 | No | Open
South East | Paktya | Ali Khail (Jaji) | Kuza Khermana | {46ECA101-0BB7-4A88-978F-FB562CDB2ABB} | c0a8-008e-13117abc533-eab8f401-2d33-7 | MF-HQ-10696 | MCPA - Mine Clearance Planning Agency | AF/0719/08141/MF0029 | 60914 | 69.6935 | 33.8995 | Open | AP Only | AP Only | MineField | Blank | MBT Project-256/B | Paktya Demining Project-07/B |  | No |  |  | 1394 | None | {46ECA101-0BB7-4A88-978F-FB562CDB2ABB} |  | High Requested | Resettlment/Local Request | Substantial | 139 | CHA | 1 | Yes | As per phesical assesment of the tasks these are solpy agri land. It need for urgent clearance. | 2009-05-27 | No | Open
South East | Paktya | Ali Khail (Jaji) | Petla | {59E8F1F0-936E-49CB-A37F-A448B816ECF8} | c0a8-0009-14023dabea6-241fd767-86a-b1 | Hz-ID-18064 | MCPA - Mine Clearance Planning Agency | AF/0723/08103/MF0120 | 49284 | 69.798 | 34.0096 | Open | AT Only | AT Only | MineField |  | MBT Project-099 | Paktya Demining Project-02 |  |  |  |  | 1394 |  | {59E8F1F0-936E-49CB-A37F-A448B816ECF8} |  | Low | Agriculture Blocked | Substantial | 31 | CHA | 5 |  |  | 2013-06-24 16:30 | No | Open
South East | Paktya | Ali Khail (Jaji) | Sharif Kalay | {F7E97115-B059-4E51-8A01-AF9F68490751} | c0a8-008e-132c9905b03-d75ba0bd-370d-e | MF-16222 | MCPA - Mine Clearance Planning Agency | AF/0723/08102/MF0118 | 16193 | 69.8097 | 33.9688 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-256 | Paktya Demining Project-07 | VTF | Yes |  |  | 1392 | ATC | {F7E97115-B059-4E51-8A01-AF9F68490751} |  |  |  | Substantial | 122 | CHA | 1 | Yes | As per assesment of the task this is the only one task in the community and affected Agri land of the resedence after clearace the community will be closed. | 2011-08-09 16:30 | No | Complete
South East | Paktya | Ali Khail (Jaji) | Sursorang | {693C7246-9EA4-406E-899F-A86108251BED} | c0a8-0057-12c3b972e39-632b3698-294ac- | MF-HQ-10656 | MCPA - Mine Clearance Planning Agency | AF/0723/08100/MF0111 | 46824 | 69.787 | 33.9432 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256 | Paktya Demining Project-07 | VTF | Yes |  |  | 1392 | ATC | {693C7246-9EA4-406E-899F-A86108251BED} |  |  |  | Substantial | 36 | CHA | 1 | Yes | As per phesical assesment of the tasks these are solpy agri land. It need for urgent clearance. | 2010-05-16 | No | Complete
South East | Paktya | Ali Khail (Jaji) | Sursorang | {693C7246-9EA4-406E-899F-A86108251BED} | c0a8-0057-12c3b97300d-8a634d55-294c5- | MF-HQ-14676 | MCPA - Mine Clearance Planning Agency | AF/0723/08100/MF0110 | 40000 | 69.787 | 33.9432 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256 | Paktya Demining Project-07 | VTF | Yes | 2013-10-01 | 2013-10-31 | 1392 | ATC | {693C7246-9EA4-406E-899F-A86108251BED} |  |  |  | Substantial | 59 | CHA | 1 | Yes | As per phesical assesment of the tasks these are solpy agri land. It need for urgent clearance. | 2010-05-16 | No | Complete
South East | Paktya | Ali Khail (Jaji) | Sursorang | {693C7246-9EA4-406E-899F-A86108251BED} | c0a8-0057-12c3bac0e63-cde96997-3623e- | MF-HQ-10929 | MCPA - Mine Clearance Planning Agency | AF/0723/08100/MF0096 | 13093 | 69.7786 | 33.9417 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256 | Paktya Demining Project-07 | VTF | Yes | 2013-10-01 | 2013-10-31 | 1392 | ATC | {693C7246-9EA4-406E-899F-A86108251BED} |  |  |  | Substantial | 108 | CHA | 1 | Yes | As per phesical assesment of the tasks these are solpy agri land. It need for urgent clearance. | 2009-05-16 | No | Complete
South East | Paktya | Chamkani | Darzakhel | {DE7B2A35-3E89-41CC-B6B8-B5862AE088EF} | c0a8-0009-145118d7cb6-1e261b0f-15b-eb | Hz-ID-18565 | MCPA - Mine Clearance Planning Agency | AF/0718/08485/MF0029 | 12935 | 69.8132 | 33.8063 | Open | AP Only | AP Only | MineField |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {DE7B2A35-3E89-41CC-B6B8-B5862AE088EF} |  | Low | Agriculture Blocked | Substantial | 7847 | CHA | 4 |  |  | 2014-02-01 16:30 | No | Open
South East | Paktya | Chamkani | Darzakhel | {DE7B2A35-3E89-41CC-B6B8-B5862AE088EF} | c0a8-0009-1451190c492-4c321449-17e-63 | Hz-ID-18566 | MCPA - Mine Clearance Planning Agency | AF/0718/08485/MF0030 | 18850 | 69.8117 | 33.8072 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {DE7B2A35-3E89-41CC-B6B8-B5862AE088EF} |  | Low | Agriculture Blocked | Substantial | 7847 | CHA | 4 |  |  | 2014-02-03 16:30 | No | Open
South East | Paktya | Chamkani | Mastajekay | {4293644B-CFA2-435A-A033-89A9BAE26E70} | c0a8-0009-14495d10c4d-dd00e1b6-d7b-dd | Hz-ID-18544 | MCPA - Mine Clearance Planning Agency | AF/0718/08486/SERW0001 | 100 | 69.7607 | 33.8879 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {4293644B-CFA2-435A-A033-89A9BAE26E70} |  | Medium | Agriculture Blocked | Substantial | 0 | CHA | 3 |  |  | 2014-01-25 16:30 | No | Open
South East | Paktya | Chamkani | Mastajekay | {4293644B-CFA2-435A-A033-89A9BAE26E70} | c0a8-0009-14495d1d776-e4721e15-d9d-d4 | Hz-ID-18545 | MCPA - Mine Clearance Planning Agency | AF/0718/08486/SERW0002 | 100 | 69.7614 | 33.8877 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {4293644B-CFA2-435A-A033-89A9BAE26E70} |  | Medium | Agriculture Blocked | Substantial | 145 | CHA | 3 |  |  | 2014-01-25 16:30 | No | Open
South East | Paktya | Gardiz | Banozai | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} | c0a8-0009-13b3ba0e373-48cd55da-4930-f | Hz-ID-17377 | MCPA - Mine Clearance Planning Agency | AF/0701/07253/MF0394 | 56910 | 69.2639 | 33.535 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-160 | Paktya Demining Project-09 | VTF-Japan | Yes | 2014-06-17 | 2014-11-30 | 1393 | MCPA | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} |  | High with Victim | High with Victims | Substantial | 50 | CHA | 2 |  |  | 2012-09-30 16:30 | No | Planned
South East | Paktya | Gardiz | Banozai | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} | c0a8-0057-12c3b747b0a-8807d137-1122e- | MF-HQ-14652 | MCPA - Mine Clearance Planning Agency | AF/0701/07253/MF0382 | 83978 | 69.2639 | 33.535 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-160 | Paktya Demining Project-09 | VTF-Japan | Yes | 2014-06-17 | 2014-11-30 | 1393 | MCPA | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} |  | High with Victim | High with Victims | Substantial | 135 | CHA | 1 | Yes | as per assessment of MACCA Regional office Gardiz clearance of the requseted areas are to important because the tasks are in the village or arround the resedentional land, most of the villagers returned from Pakistan and the remain are going to came next | 2010-06-09 | No | Planned
South East | Paktya | Gardiz | Banozai | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} | c0a8-0057-12c3b808f27-b56926bd-19d61- | MF-HQ-12956 | MCPA - Mine Clearance Planning Agency | AF/0701/07253/MF0347 | 81179 | 69.2692 | 33.5197 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-045 | Paktya Demining Project-03 | B-Germany | Yes |  |  | 1393 | HT | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} |  | High with Victim | High with Victims | Substantial | 10 | CHA | 1 | Yes | as per assessment of MACCA Regional office Gardiz clearance of the requseted areas are to important because the tasks are in the village or arround the resedentional land, most of the villagers returned from Pakistan and the remain are going to came next | 2009-08-31 | No | Planned
South East | Paktya | Gardiz | Banozai | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} | c0a8-008e-1329092d01c-b083ec3d-185-db | MF-16140 | MCPA - Mine Clearance Planning Agency | AF/0701/07253/MF0389 | 26338 | 69.2589 | 33.5339 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-045 | Paktya Demining Project-03 | B-Germany | Yes |  |  | 1393 | HT | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} |  | High with Victim | High with Victims | Substantial | 15 | CHA | 1 | Yes | as per assessment of MACCA Regional office Gardiz clearance of the requseted areas are to important because the tasks are in the village or arround the resedentional land, most of the villagers returned from Pakistan and the remain are going to came next | 2011-06-30 16:30 | No | Planned
South East | Paktya | Gardiz | Banozai | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} | c0a8-008e-132c990a431-9f24f7bf-3740-1 | MF-16216 | MCPA - Mine Clearance Planning Agency | AF/0701/07253/MF0390 | 69289 | 69.2589 | 33.5339 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-045 | Paktya Demining Project-03 | B-Germany | Yes |  |  | 1393 | HT | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} |  | High with Victim | High with Victims | Substantial | 78 | CHA | 1 | Yes | as per assessment of MACCA Regional office Gardiz clearance of the requseted areas are to important because the tasks are in the village or arround the resedentional land, most of the villagers returned from Pakistan and the remain are going to came next | 2011-06-30 16:30 | No | Planned
South East | Paktya | Gardiz | Banozai | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} | c0a8-00f6-13519aa8cbd-e1ca8187-972-a8 | MF-16218 | MCPA - Mine Clearance Planning Agency | AF/0701/07253/MF0392 | 30600 | 69.2589 | 33.5339 | Open | Mixed | Mixed AP AT UXO | MineField | 1393 | MBT Project-045 | Paktya Demining Project-03 | B-Germany | Yes |  |  | 1393 | HT | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} |  | High with Victim | High with Victims | Substantial | 43 | CHA | 1 | Yes | as per assessment of MACCA Regional office Gardiz clearance of the requseted areas are to important because the tasks are in the village or arround the resedentional land, most of the villagers returned from Pakistan and the remain are going to came next | 2011-06-30 16:30 | No | Planned
South East | Paktya | Gardiz | Banozai | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} | c0a8-00f6-13552653093-96ccb47d-46-403 | MF-16217 | MCPA - Mine Clearance Planning Agency | AF/0701/07253/MF0391 | 60209 | 69.2589 | 33.5567 | Open | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-045 | Paktya Demining Project-03 | B-Germany | Yes |  |  | 1393 | HT | {64FBF6EC-5D0C-4F23-B8DE-B506ABCE8E97} |  | High with Victim | High with Victims | Substantial | 18 | CHA | 1 | Yes | as per assessment of MACCA Regional office Gardiz clearance of the requseted areas are to important because the tasks are in the village or arround the resedentional land, most of the villagers returned from Pakistan and the remain are going to came next | 2011-08-23 16:30 | No | Planned
South East | Paktya | Gardiz | Cheken Shekhan | {E1C0EB80-A818-4C4D-A6B5-8FD7D28DEDA3} | c0a8-00f6-13519b8eaa3-b9b0397a-a23-bd | MF-16219 | MCPA - Mine Clearance Planning Agency | AF/0701/00700/MF0393 | 51191 | 69.2421 | 33.5267 | Worked on | Mixed | Mixed AP UXO | MineField | 1393 | MBT Project-160 | Paktya Demining Project-09 | VTF-Japan | Yes | 2014-06-17 | 2014-11-30 | 1393 | MCPA | {E1C0EB80-A818-4C4D-A6B5-8FD7D28DEDA3} |  | Medium | Agriculture Blocked | Substantial | 32 | CHA | 3 |  |  | 2011-08-23 16:30 | No | Planned
South East | Paktya | Gardiz | Darabal Kala | {6A09D053-204F-48F6-8AB9-F7379CB5AB43} | c0a8-0009-143cd35c314-ed7d3aa5-2cd5-b | Hz-ID-18402 | MCPA - Mine Clearance Planning Agency | AF/0701/07254/MF0396 | 39244 | 69.2677 | 33.546 | Open | Mixed | Mixed AP AT UXO | MineField | 1393 | MBT Project-045 | Paktya Demining Project-03 | B-Germany | Yes |  |  | 1393 | HT | {6A09D053-204F-48F6-8AB9-F7379CB5AB43} |  | Medium | Agriculture Blocked | Substantial | 36 | CHA | 3 |  |  | 2013-12-25 16:30 | No | Planned
South East | Paktya | Gardiz | Darabal Kala | {6A09D053-204F-48F6-8AB9-F7379CB5AB43} | c0a8-0057-12c3b87cccf-69b04bc1-1ef76- | MF-HQ-12033 | MCPA - Mine Clearance Planning Agency | AF/0701/07254/MF0341 | 116886 | 69.2709 | 33.5513 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-06-16 | 2013-11-30 | 1392 | MCPA | {6A09D053-204F-48F6-8AB9-F7379CB5AB43} |  |  |  | Substantial | 156 | CHA | 1 | Yes | as per assessment of MACCA Regional office Gardiz clearance of the requseted areas are to important because the tasks are in the village or arround the resedentional land, most of the villagers returned from Pakistan and the remain are going to came next | 2009-07-11 | No | Complete
South East | Paktya | Gardiz | Darabal Kala | {6A09D053-204F-48F6-8AB9-F7379CB5AB43} | c0a8-0057-12c3b87d0d5-29a3cff3-1efa2- | MF-HQ-12032 | MCPA - Mine Clearance Planning Agency | AF/0701/07254/MF0340 | 119772 | 69.2646 | 33.5571 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-08-14 | 2013-11-30 | 1392 | MCPA | {6A09D053-204F-48F6-8AB9-F7379CB5AB43} |  |  |  | Substantial | 156 | CHA | 1 | Yes | as per assessment of MACCA Regional office Gardiz clearance of the requseted areas are to important because the tasks are in the village or arround the resedentional land, most of the villagers returned from Pakistan and the remain are going to came next | 2009-07-08 | No | Complete
South East | Paktya | Gardiz | Darabal Kala | {6A09D053-204F-48F6-8AB9-F7379CB5AB43} | c0a8-0057-12c3b87d299-bd2aa70b-1efb8- | MF-HQ-12037 | MCPA - Mine Clearance Planning Agency | AF/0701/07254/MF0343 | 72250 | 69.2687 | 33.5458 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-256 | Paktya Demining Project-07 | VTF | Yes |  |  | 1392 | ATC | {6A09D053-204F-48F6-8AB9-F7379CB5AB43} |  |  |  | Substantial | 172 | CHA | 1 | Yes | as per assessment of MACCA Regional office Gardiz clearance of the requseted areas are to important because the tasks are in the village or arround the resedentional land, most of the villagers returned from Pakistan and the remain are going to came next | 2009-07-15 | No | Complete
South East | Paktya | Gardiz | Darabal Kala | {6A09D053-204F-48F6-8AB9-F7379CB5AB43} | c0a8-0057-12c3b87d46d-a96b55bc-1efca- | MF-HQ-12034 | MCPA - Mine Clearance Planning Agency | AF/0701/07254/MF0342 | 107297 | 69.2709 | 33.5513 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-06-16 | 2013-11-30 | 1392 | MCPA | {6A09D053-204F-48F6-8AB9-F7379CB5AB43} |  |  |  | Substantial | 328 | CHA | 1 | Yes | as per assessment of MACCA Regional office Gardiz clearance of the requseted areas are to important because the tasks are in the village or arround the resedentional land, most of the villagers returned from Pakistan and the remain are going to came next | 2009-07-13 | No | Complete
South East | Paktya | Gardiz | Dowabah | {12419F5F-7C20-4780-B8C7-BD97D1098566} | c0a8-0057-12c3b7f8089-86b9dd50-1915b- | MF-HQ-12939 | MCPA - Mine Clearance Planning Agency | AF/0701/00045/MF0361 | 60002 | 69.3072 | 33.6001 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-09-07 | 2013-11-30 | 1392 | DAFA | {12419F5F-7C20-4780-B8C7-BD97D1098566} |  |  |  | Substantial | 10 | CHA | 5 |  |  | 2009-09-13 | No | Complete
South East | Paktya | Gardiz | Ebrahimkhel | {88C266F7-AB89-4C1C-9056-A0CB5572F312} | c0a8-0009-142ff5590f0-84f001bc-1cb-a7 | Hz-ID-18295 | MCPA - Mine Clearance Planning Agency | AF/0701/07218/MF0395 | 2665 | 69.1792 | 33.5369 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes |  |  | 1392 | DAFA | {88C266F7-AB89-4C1C-9056-A0CB5572F312} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2013-12-17 16:30 | No | Complete
South East | Paktya | Gardiz | Melan | {70463A88-DAB4-4A2E-B763-A404005A3724} | c0a8-00c9-12fde9f70fa-68e372c5-33d-9d | MF-HQ-12909 | MCPA - Mine Clearance Planning Agency | AF/0701/07280/MF0365 | 89042 | 69.3506 | 33.6088 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-045 | Paktya Demining Project-03 | B-Germany | Yes |  |  | 1393 | HT | {70463A88-DAB4-4A2E-B763-A404005A3724} |  | High with Victim | High with Victims | Substantial | 166 | CHA | 2 |  |  | 2009-08-12 | No | Planned
South East | Paktya | Jani Khail | Tughu | {0F9718DD-33BB-425D-B4F6-4162D1B6EC2E} | c0a8-0009-14495c9755f-35441301-d33-86 | Hz-ID-18541 | MCPA - Mine Clearance Planning Agency | AF/3209/08153/MF0001 | 109897 | 69.8451 | 33.5962 | Open | AP Only | AP Only | MineField |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {0F9718DD-33BB-425D-B4F6-4162D1B6EC2E} |  | Low | Agriculture Blocked | Substantial | 10 | CHA | 5 |  |  | 2014-01-23 16:30 | No | Open
South East | Paktya | Laja Ahmad Khail | Bekaray | {74CDBAA5-D0EB-4559-A4B1-7808F5555D96} | c0a8-0009-140b9967105-c4632c4a-ab1-55 | Hz-ID-18119 | MCPA - Mine Clearance Planning Agency | AF/0719/08125/MF0042 | 26178 | 69.6221 | 33.8427 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-09-01 | 2013-12-15 | 1392 | MCPA | {74CDBAA5-D0EB-4559-A4B1-7808F5555D96} |  |  |  | Substantial | 33 | CHA | 1 |  |  | 2013-07-08 16:30 | No | Complete
South East | Paktya | Laja Ahmad Khail | Bekaray | {74CDBAA5-D0EB-4559-A4B1-7808F5555D96} | c0a8-0009-141072381f1-d9b55e64-9d89-e | Hz-ID-18125 | MCPA - Mine Clearance Planning Agency | AF/0719/08125/MF0043 | 23103 | 69.6221 | 33.8427 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-11-08 | 2013-11-30 | 1392 | MCPA | {74CDBAA5-D0EB-4559-A4B1-7808F5555D96} |  |  |  | Substantial | 123 | CHA | 4 |  |  | 2013-07-06 16:30 | No | Complete
South East | Paktya | Laja Ahmad Khail | Bekaray | {74CDBAA5-D0EB-4559-A4B1-7808F5555D96} | c0a8-0057-12c3b8de8c8-54a21e0f-232e3- | MF-HQ-10700 | MCPA - Mine Clearance Planning Agency | AF/0719/08125/MF0031 | 74316 | 69.623 | 33.8382 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-05-01 | 2013-12-15 | 1392 | MCPA | {74CDBAA5-D0EB-4559-A4B1-7808F5555D96} |  |  |  | Substantial | 138 | CHA | 3 |  |  | 2009-05-14 | No | Complete
South East | Paktya | Laja Ahmad Khail | Bekaray | {74CDBAA5-D0EB-4559-A4B1-7808F5555D96} | c0a8-0057-12c3ba8de18-1069d55d-344e4- | MF-HQ-10698 | MCPA - Mine Clearance Planning Agency | AF/0719/08125/MF0030 | 35274 | 69.6175 | 33.8423 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-05-01 | 2013-08-31 | 1392 | MCPA | {74CDBAA5-D0EB-4559-A4B1-7808F5555D96} |  |  |  | Substantial | 165 | CHA | 5 |  |  | 2009-05-12 | No | Complete
South East | Paktya | Laja Ahmad Khail | Dabozay | {057195EB-8DC9-4E73-BEAB-90B7C2E2883C} | c0a8-0057-12c3b79c3bf-295933a8-15019- | MF-HQ-10712 | MCPA - Mine Clearance Planning Agency | AF/0719/08131/MF0038 | 7845 | 69.6459 | 33.8757 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-11-02 | 2013-12-15 | 1392 | MCPA | {057195EB-8DC9-4E73-BEAB-90B7C2E2883C} |  |  |  | Substantial | 1620 | CHA | 3 |  |  | 2009-05-16 | No | Complete
South East | Paktya | Laja Ahmad Khail | Dabozay | {057195EB-8DC9-4E73-BEAB-90B7C2E2883C} | c0a8-008e-1311357419d-b1b02d7a-1d77-b | MF-HQ-10710 | MCPA - Mine Clearance Planning Agency | AF/0719/0813/MF0037 | 31499 | 69.6315 | 33.8606 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-05-01 | 2013-08-15 | 1392 | MCPA | {057195EB-8DC9-4E73-BEAB-90B7C2E2883C} |  |  |  | Substantial | 584 | CHA | 4 |  |  | 2009-05-13 | No | Complete
South East | Paktya | Laja Ahmad Khail | Dabozay | {057195EB-8DC9-4E73-BEAB-90B7C2E2883C} | c0a8-008e-1311357e8d2-71a03bca-1d93-9 | MF-HQ-10707 | MCPA - Mine Clearance Planning Agency | AF/0719/08131/MF0036 | 35228 | 69.6332 | 33.8633 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-05-01 | 2013-08-10 | 1392 | MCPA | {057195EB-8DC9-4E73-BEAB-90B7C2E2883C} |  |  |  | Substantial | 584 | CHA | 3 |  |  | 2009-05-13 | No | Complete
South East | Paktya | Laja Ahmad Khail | Kharzun | {55497405-7A92-4715-987A-3A84C281FF1D} | c0a8-0057-12c3b711a4d-bff8cae0-e97b-c | MF-HQ-10689 | MCPA - Mine Clearance Planning Agency | AF/0719/08130/MF0028 | 50401 | 69.6328 | 33.8491 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-08-16 | 2013-12-15 | 1392 | MCPA | {55497405-7A92-4715-987A-3A84C281FF1D} |  |  |  | Substantial | 703 | CHA | 4 |  |  | 2009-05-27 | No | Complete
South East | Paktya | Laja Ahmad Khail | Kharzun | {55497405-7A92-4715-987A-3A84C281FF1D} | c0a8-0057-12c3b82ab39-2c24a368-1b519- | MF-HQ-10683 | MCPA - Mine Clearance Planning Agency | AF/0719/08130/MF0025 | 82448 | 69.6328 | 33.8556 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-05-01 | 2013-12-15 | 1392 | MCPA | {55497405-7A92-4715-987A-3A84C281FF1D} |  |  |  | Substantial | 531 | CHA | 4 |  |  | 2009-05-23 | No | Complete
South East | Paktya | Laja Ahmad Khail | Kharzun | {55497405-7A92-4715-987A-3A84C281FF1D} | c0a8-008e-1311351a381-9e61ce7b-1c8e-f | MF-HQ-10681 | MCPA - Mine Clearance Planning Agency | AF/0719/08130/MF0024 | 57891 | 69.6328 | 33.8556 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-256/A | Paktya Demining Project-07/A | VTF-Australia | Yes | 2013-05-01 | 2013-12-15 | 1392 | MCPA | {55497405-7A92-4715-987A-3A84C281FF1D} |  |  |  | Substantial | 17 | CHA | 3 |  |  | 2009-05-23 | No | Complete
South East | Paktya | Laja Ahmad Khail | Moshaka | {B76C6771-00A4-4620-88FE-52D41A314EFF} | c0a8-0009-1410725e948-3db57c4d-a098-5 | Hz-ID-18123 | MCPA - Mine Clearance Planning Agency | AF/0719/08119/MF0040 | 36166 | 69.6208 | 33.8302 | Open | AP Only | AP Only | MineField |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {B76C6771-00A4-4620-88FE-52D41A314EFF} |  | High with Victim | High with Victims | Substantial | 68 | CHA | 1 |  |  | 2013-07-03 16:30 | No | Open
South East | Paktya | Laja Ahmad Khail | Moshaka | {B76C6771-00A4-4620-88FE-52D41A314EFF} | c0a8-0009-1410728d6be-43d92b1a-a4d9-7 | Hz-ID-18124 | MCPA - Mine Clearance Planning Agency | AF/0719/08119/MF0041 | 66789 | 69.6448 | 33.7979 | Open | AP Only | AP Only | MineField |  | MBT Project-256/B | Paktya Demining Project-07/B |  |  |  |  | 1394 |  | {B76C6771-00A4-4620-88FE-52D41A314EFF} |  | High with Victim | High with Victims | Substantial | 64 | CHA | 1 |  |  | 2013-07-01 16:30 | No | Open
South East | Paktya | Sayed Karam | Andwam | {1D409D66-1AF9-4DF3-9465-063BC38802F4} | c0a8-0057-12c3baf7bbd-98ad175b-38332- | MF-HQ-13789 | MCPA - Mine Clearance Planning Agency | AF/0722/08467/MF0124 | 97500 | 69.5177 | 33.7876 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-07-26 | 2013-11-13 | 1392 | DAFA | {1D409D66-1AF9-4DF3-9465-063BC38802F4} |  |  |  | Substantial | 214 | CHA | 4 |  |  | 2009-10-14 | No | Complete
South East | Paktya | Sayed Karam | Andwam | {1D409D66-1AF9-4DF3-9465-063BC38802F4} | c0a8-0057-12c3baf7e2d-b976f28a-3834d- | MF-HQ-13794 | MCPA - Mine Clearance Planning Agency | AF/0722/08467/MF0127 | 44000 | 69.5305 | 33.7888 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-06-01 | 2013-07-31 | 1392 | DAFA | {1D409D66-1AF9-4DF3-9465-063BC38802F4} |  |  |  | Substantial | 128 | CHA | 4 |  |  | 2009-12-13 | No | Complete
South East | Paktya | Sayed Karam | Andwam | {1D409D66-1AF9-4DF3-9465-063BC38802F4} | c0a8-0057-12c3baf805e-8e3602aa-38369- | MF-HQ-13791 | MCPA - Mine Clearance Planning Agency | AF/0722/08467/MF0123 | 91740 | 69.5461 | 33.7931 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-11-05 | 2013-12-23 | 1392 | DAFA | {1D409D66-1AF9-4DF3-9465-063BC38802F4} |  |  |  | Substantial | 51 | CHA | 5 |  |  | 2009-12-13 | No | Complete
South East | Paktya | Sayed Karam | Andwam | {1D409D66-1AF9-4DF3-9465-063BC38802F4} | c0a8-0057-12c3baf82fd-3fa97ce7-3837f- | MF-HQ-13793 | MCPA - Mine Clearance Planning Agency | AF/0722/08467/MF0126 | 90000 | 69.5246 | 33.7908 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-06-01 | 2013-09-02 | 1392 | DAFA | {1D409D66-1AF9-4DF3-9465-063BC38802F4} |  |  |  | Substantial | 100 | CHA | 4 |  |  | 2009-12-13 | No | Complete
South East | Paktya | Sayed Karam | Andwam | {1D409D66-1AF9-4DF3-9465-063BC38802F4} | c0a8-0057-12c3baf854e-2e7e6200-3839a- | MF-HQ-13790 | MCPA - Mine Clearance Planning Agency | AF/0722/08467/MF0122 | 112000 | 69.5461 | 33.7931 | Open | AP Only | AP Only | MineField |  | MBT Project-157 | Paktya Demining Project-08 |  |  |  |  | 1400 |  | {1D409D66-1AF9-4DF3-9465-063BC38802F4} |  | High Requested | Resettlment/Local Request | Substantial | 51 | CHA | 5 |  |  | 2009-12-13 | No | Open
South East | Paktya | Sayed Karam | Andwam | {1D409D66-1AF9-4DF3-9465-063BC38802F4} | c0a8-0057-12c3baf877f-dd197eea-383b1- | MF-HQ-13792 | MCPA - Mine Clearance Planning Agency | AF/0722/08467/MF0125 | 120500 | 69.5177 | 33.7876 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-06-01 | 2013-10-03 | 1392 | DAFA | {1D409D66-1AF9-4DF3-9465-063BC38802F4} |  |  |  | Substantial | 100 | CHA | 4 |  |  | 2009-12-13 | No | Complete
South East | Paktya | Sayed Karam | Andwam | {1D409D66-1AF9-4DF3-9465-063BC38802F4} | c0a8-0057-12c3baf8a8b-8f53f19e-383cb- | MF-HQ-13795 | MCPA - Mine Clearance Planning Agency | AF/0722/08467/MF0128 | 35000 | 69.5305 | 33.7888 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-06-01 | 2013-07-25 | 1392 | DAFA | {1D409D66-1AF9-4DF3-9465-063BC38802F4} |  |  |  | Substantial | 50 | CHA | 4 |  |  | 2009-12-13 | No | Complete
South East | Paktya | Sayed Karam | Ghwareza | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} | c0a8-0057-12c3b80d3e3-5bd5132d-1a03a- | MF-HQ-13896 | MCPA - Mine Clearance Planning Agency | AF/0722/08407/MF0131 | 50200 | 69.3697 | 33.6141 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} |  | High with Victim | High with Victims | Substantial | 35 | CHA | 2 |  |  | 2009-12-23 | No | Open
South East | Paktya | Sayed Karam | Ghwareza | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} | c0a8-0057-12c3b80d578-5c40ec73-1a052- | MF-HQ-13894 | MCPA - Mine Clearance Planning Agency | AF/0722/08407/MF0133 | 40400 | 69.3765 | 33.615 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-160 | Paktya Demining Project-09 | VTF-Japan | Yes | 2014-07-20 | 2014-11-27 | 1393 | MCPA | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} |  | High with Victim | High with Victims | Substantial | 100 | CHA | 2 |  |  | 2009-12-23 | No | Planned
South East | Paktya | Sayed Karam | Ghwareza | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} | c0a8-0057-12c3b80d75c-4dddfb-1a066-e8 | MF-HQ-13863 | MCPA - Mine Clearance Planning Agency | AF/0722/08407/MF0130 | 38090 | 69.3697 | 33.6141 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} |  | High with Victim | High with Victims | Substantial | 43 | CHA | 2 |  |  | 2009-11-05 | No | Open
South East | Paktya | Sayed Karam | Ghwareza | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} | c0a8-0057-12c3b80d911-91736504-1a07d- | MF-HQ-13895 | MCPA - Mine Clearance Planning Agency | AF/0722/08407/MF0132 | 64732 | 69.3765 | 33.615 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-160 | Paktya Demining Project-09 | VTF-Japan | Yes | 2014-07-20 | 2014-11-27 | 1393 | MCPA | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} |  | High with Victim | High with Victims | Substantial | 100 | CHA | 2 |  |  | 2009-12-23 | No | Planned
South East | Paktya | Sayed Karam | Ghwareza | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} | c0a8-0057-12c3b8e8c17-e66a6fdc-23a61- | MF-SE-276 | MCPA - Mine Clearance Planning Agency | AF/0722/08407/MF0111 | 76257 | 69.3726 | 33.6144 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} | Funding staus updated | High with Victim | High with Victims | Substantial | 80 | CHA | 2 |  |  | 2010-01-13 | No | Open
South East | Paktya | Sayed Karam | Ghwareza | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} | c0a8-0057-12c3b8e8e29-5243c1bc-23a7d- | MF-HQ-14064 | MCPA - Mine Clearance Planning Agency | AF/0722/08407/MF143 | 56185 | 69.3688 | 33.6145 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-160 | Paktya Demining Project-09 | VTF-Japan | Yes | 2014-07-20 | 2014-11-27 | 1393 | MCPA | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} |  | High with Victim | High with Victims | Substantial | 30 | CHA | 2 |  |  | 2010-01-23 | No | Planned
South East | Paktya | Sayed Karam | Ghwareza | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} | c0a8-0057-12c3b8e8ffd-ae54913a-23a92- | MF-SE-470 | MCPA - Mine Clearance Planning Agency | AF/0722/08407/MF112 | 70010 | 69.3726 | 33.6144 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} |  | High with Victim | High with Victims | Substantial | 30 | CHA | 2 |  |  | 2010-01-16 | No | Open
South East | Paktya | Sayed Karam | Ghwareza | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} | c0a8-0057-12c3b8e921f-1abaa24d-23aa8- | MF-HQ-14063 | MCPA - Mine Clearance Planning Agency | AF/0722/08407/MF142 | 88558 | 69.3688 | 33.6145 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-160 | Paktya Demining Project-09 | VTF-Japan | Yes | 2014-07-20 | 2014-11-27 | 1393 | MCPA | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} |  | High with Victim | High with Victims | Substantial | 30 | CHA | 2 |  |  | 2010-01-20 | No | Planned
South East | Paktya | Sayed Karam | Ghwareza | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} | c0a8-0057-12c3b8e9441-77e804c-23abc-6 | MF-HQ-14062 | MCPA - Mine Clearance Planning Agency | AF/0722/08407/MF141 | 75605 | 69.3688 | 33.6145 | Open | Mixed Mine | Mixed Mine | MineField | 1393 | MBT Project-160 | Paktya Demining Project-09 | VTF-Japan | Yes | 2014-09-01 | 2014-11-27 | 1393 | MCPA | {F05D9D81-0FDF-47F0-A68B-B85011D90FC4} |  | High with Victim | High with Victims | Substantial | 15 | CHA | 2 |  |  | 2010-01-18 | No | Planned
South East | Paktya | Sayed Karam | Karezgay | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} | c0a8-0009-14370225562-ce092a30-4f54-8 | Hz-ID-18310 | MCPA - Mine Clearance Planning Agency | AF/0722/08450/MF0152 | 14134 | 69.4424 | 33.7502 | Open | AT Only | AT Only | MineField |  | MBT Project-050 | Paktya Demining Project-01 AT |  |  |  |  | 1395 |  | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} |  | Low | Critical Infrastracture | Substantial | 107 | CHA | 4 |  |  | 2013-10-30 16:30 | No | Open
South East | Paktya | Sayed Karam | Karezgay | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} | c0a8-0009-1437025cc26-1d6898e1-527a-3 | Hz-ID-18311 | MCPA - Mine Clearance Planning Agency | AF/0722/08450/MF0153 | 4637 | 69.4552 | 33.7519 | Open | AT Only | AT Only | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} |  | Medium | Critical Infrastracture | Substantial | 467 | CHA | 3 |  |  | 2013-11-10 16:30 | No | Open
South East | Paktya | Sayed Karam | Karezgay | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} | c0a8-0009-143702ddf45-d6a12c8d-58c7-3 | Hz-ID-18312 | MCPA - Mine Clearance Planning Agency | AF/0722/08450/MF0154 | 3134 | 69.4568 | 33.7502 | Open | AT Only | AT Only | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} |  | Medium | Critical Infrastracture | Substantial | 467 | CHA | 3 |  |  | 2013-11-12 16:30 | No | Open
South East | Paktya | Sayed Karam | Karezgay | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} | c0a8-0009-14370323fd9-dcc3b43d-6171-1 | Hz-ID-18317 | MCPA - Mine Clearance Planning Agency | AF/0722/08450/MF0155 | 2173 | 69.4568 | 33.7502 | Open | AT Only | AT Only | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} |  | Medium | Critical Infrastracture | Substantial | 467 | CHA | 3 |  |  | 2013-11-13 16:30 | No | Open
South East | Paktya | Sayed Karam | Karezgay | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} | c0a8-0009-1437036b342-4307d69c-6d17-b | Hz-ID-18318 | MCPA - Mine Clearance Planning Agency | AF/0722/08450/MF0156 | 3132 | 69.455 | 33.7512 | Open | AT Only | AT Only | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} |  | Medium | Critical Infrastracture | Substantial | 467 | CHA | 3 |  |  | 2013-11-17 16:30 | No | Open
South East | Paktya | Sayed Karam | Karezgay | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} | c0a8-0009-143703df750-b3f15148-8344-e | Hz-ID-18319 | MCPA - Mine Clearance Planning Agency | AF/0722/08450/MF0157 | 6991 | 69.4567 | 33.7499 | Open | AT Only | AT Only | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} |  | Medium | Critical Infrastracture | Substantial | 467 | CHA | 3 |  |  | 2013-11-18 16:30 | No | Open
South East | Paktya | Sayed Karam | Karezgay | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} | c0a8-0009-1437040e8ee-8fc0702e-9348-c | Hz-ID-18320 | MCPA - Mine Clearance Planning Agency | AF/0722/08450/MF0158 | 11850 | 69.4466 | 33.7509 | Open | AT Only | AT Only | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} |  | Medium | Critical Infrastracture | Substantial | 574 | CHA | 3 |  |  | 2013-10-28 16:30 | No | Open
South East | Paktya | Sayed Karam | Karezgay | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} | c0a8-0009-143704a927e-8a1412be-ab1a-8 | Hz-ID-18322 | MCPA - Mine Clearance Planning Agency | AF/0722/08450/MF0160 | 3905 | 69.454 | 33.7609 | Open | AT Only | AT Only | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {EE6554A3-568D-4509-B1A9-B8DF78983DEA} |  | Medium | Agriculture Blocked | Substantial | 0 | CHA | 3 |  |  | 2013-11-16 16:30 | No | Open
South East | Paktya | Sayed Karam | Khalilan | {DDA4235C-92C6-4183-AB16-0129BE6BEEEF} | c0a8-0009-14370485038-9a69ce64-aaf4-f | Hz-ID-18321 | MCPA - Mine Clearance Planning Agency | AF/0722/00688/MF0159 | 34915 | 69.4842 | 33.7666 | Open | AT Only | AT Only | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {DDA4235C-92C6-4183-AB16-0129BE6BEEEF} |  | Medium | Critical Infrastracture | Substantial | 3867 | CHA | 3 |  |  | 2013-11-17 16:30 | No | Open
South East | Paktya | Sayed Karam | Khalilan | {DDA4235C-92C6-4183-AB16-0129BE6BEEEF} | c0a8-0057-12c3baf2ae0-2cf03ab2-38061- | MF-HQ-13796 | MCPA - Mine Clearance Planning Agency | AF/0722/06880/MF0121 | 19688 | 69.484 | 33.7634 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-09-03 | 2013-09-23 | 1392 | DAFA | {DDA4235C-92C6-4183-AB16-0129BE6BEEEF} | Funding Status updated |  |  | Substantial | 123 | CHA | 4 |  |  | 2009-12-13 | No | Complete
South East | Paktya | Sayed Karam | Khanokhel | {0420EFEF-8BFB-40FD-BD8C-11F5412E3FF0} | c0a8-0057-12c3b84febf-f38d9af8-1d010- | MF-HQ-14061 | MCPA - Mine Clearance Planning Agency | AF/0722/08425/MF0140 | 28760 | 69.4917 | 33.6517 | Open | AT Only | AT Only | MineField |  | MBT Project-050 | Paktya Demining Project-01 AT |  |  |  |  | 1395 |  | {0420EFEF-8BFB-40FD-BD8C-11F5412E3FF0} |  | Low | Other | Substantial | 96 | CHA | 5 |  |  | 2010-01-11 | No | Open
South East | Paktya | Sayed Karam | Kuza Sejenak | {7727C7EB-D4E1-4A5D-9940-015481EDD95C} | c0a8-008e-131178d879c-ff82c576-2a55-a | MF-HQ-13352 | MCPA - Mine Clearance Planning Agency | AF/0722/08448/MF0114 | 49727 | 69.5103 | 33.7331 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-09-16 | 2013-11-30 | 1392 | DAFA | {7727C7EB-D4E1-4A5D-9940-015481EDD95C} |  |  |  | Substantial | 179 | CHA | 5 |  |  | 2009-11-01 | No | Complete
South East | Paktya | Sayed Karam | Mach | {6FF5A98E-B362-47E4-BCB9-04E88ED62770} | c0a8-008e-13117820511-5be8ceec-28c0-4 | MF-SE-380 | MCPA - Mine Clearance Planning Agency | AF/0722/08423/MF0101 | 77250 | 69.4064 | 33.6591 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-09-28 | 2013-11-30 | 1392 | DAFA | {6FF5A98E-B362-47E4-BCB9-04E88ED62770} |  |  |  | Substantial | 666 | CHA | 1 |  |  | 2009-10-14 | No | Complete
South East | Paktya | Sayed Karam | Mamozaee | {F59BDEFF-87FB-4E19-B504-984ACE059696} | c0a8-0057-12c3b8971e0-bfac6e66-201ce- | MF-HQ-13174 | MCPA - Mine Clearance Planning Agency | AF/0722/00060/MF0118 | 177515 | 69.401 | 33.7241 | Open | AT Only | AT Only | MineField | Blank | MBT Project-050 | Paktya Demining Project-01 AT |  | No |  |  | 1395 | None | {F59BDEFF-87FB-4E19-B504-984ACE059696} | Funding Status updated | Medium | Critical Infrastracture | Substantial | 1186 | CHA | 3 |  |  | 2009-11-01 | No | Open
South East | Paktya | Sayed Karam | Mamozaee | {F59BDEFF-87FB-4E19-B504-984ACE059696} | c0a8-0057-12c3ba43548-213c5df2-317db- | MF-HQ-13357 | MCPA - Mine Clearance Planning Agency | AF/0722/00060/MF0115 | 101834 | 69.4204 | 33.7407 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-06-01 | 2013-09-05 | 1392 | DAFA | {F59BDEFF-87FB-4E19-B504-984ACE059696} |  |  |  | Substantial | 445 | CHA | 4 |  |  | 2009-11-01 | No | Complete
South East | Paktya | Sayed Karam | Mamozaee | {F59BDEFF-87FB-4E19-B504-984ACE059696} | c0a8-0057-12c3ba437a8-a69f54e9-317f9- | MF-HQ-14015 | MCPA - Mine Clearance Planning Agency | AF/0722/00060/MF0095 | 15877 | 69.4162 | 33.736 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-06-01 | 2013-06-22 | 1392 | DAFA | {F59BDEFF-87FB-4E19-B504-984ACE059696} |  |  |  | Substantial | 237 | CHA | 4 |  |  | 2009-10-07 | No | Complete
South East | Paktya | Sayed Karam | Mamozaee | {F59BDEFF-87FB-4E19-B504-984ACE059696} | c0a8-008e-13113db553d-30a440fe-24e3-7 | MF-HQ-13355 | MCPA - Mine Clearance Planning Agency | AF/0722/0060/MF0117 | 115942 | 69.411 | 33.7212 | Open | AT Only | AT Only | MineField | Blank | MBT Project-050 | Paktya Demining Project-01 AT |  | No |  |  | 1395 | None | {F59BDEFF-87FB-4E19-B504-984ACE059696} |  | High Requested | Resettlment/Local Request | Substantial | 2229 | CHA | 4 |  |  | 2009-11-01 | No | Open
South East | Paktya | Sayed Karam | Mamozaee | {F59BDEFF-87FB-4E19-B504-984ACE059696} | c0a8-008e-13113dc10ad-da3afa2f-24fa-f | MF-HQ-13356 | MCPA - Mine Clearance Planning Agency | AF/0722/00060/MF0116 | 25272 | 69.4147 | 33.7265 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-06-23 | 2013-07-28 | 1392 | DAFA | {F59BDEFF-87FB-4E19-B504-984ACE059696} |  |  |  | Substantial | 593 | CHA | 4 |  |  | 2009-11-01 | No | Complete
South East | Paktya | Sayed Karam | Mamozaee | {F59BDEFF-87FB-4E19-B504-984ACE059696} | c0a8-008e-13117949096-308e8f8b-2b35-9 | MF-SE-302 | MCPA - Mine Clearance Planning Agency | AF/0722/00060/MF0113 | 138249 | 69.4287 | 33.743 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-06-01 | 2013-10-05 | 1392 | DAFA | {F59BDEFF-87FB-4E19-B504-984ACE059696} |  |  |  | Substantial | 120 | CHA | 4 |  |  | 2009-11-01 | No | Complete
South East | Paktya | Sayed Karam | Mamozaee | {F59BDEFF-87FB-4E19-B504-984ACE059696} | c0a8-008e-13146d433b8-fc28608f-3202-e | MF-HQ-13354 | MCPA - Mine Clearance Planning Agency | AF/0722/0060/MF0120 | 181153 | 69.401 | 33.7241 | Open | AP Only | AP Only | MineField | Blank | MBT Project-050 | Paktya Demining Project-01 AT |  | No |  |  | 1395 | None | {F59BDEFF-87FB-4E19-B504-984ACE059696} |  | High | Critical Infrastracture | Substantial | 2229 | CHA | 3 |  |  | 2009-11-01 | No | Open
South East | Paktya | Sayed Karam | Melan Sheikhan | {522DBD02-35B9-4AF1-8D2F-8B5ECF93BB7D} | c0a8-008e-1311788ae8f-9e445de7-29ab-1 | MF-HQ-13353 | MCPA - Mine Clearance Planning Agency | AF/0722/00049/MF0119 | 131562 | 69.3963 | 33.6999 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-07-29 | 2013-12-23 | 1392 | DAFA | {522DBD02-35B9-4AF1-8D2F-8B5ECF93BB7D} |  |  |  | Substantial | 823 | CHA | 4 |  |  | 2009-11-01 | No | Complete
South East | Paktya | Sayed Karam | Naray Kalay | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} | c0a8-008e-13112f09cd3-d44647e0-19bc-6 | MF-HQ-13898 | MCPA - Mine Clearance Planning Agency | AF/0722/08419/MF0139 | 32950 | 69.3983 | 33.6343 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-06-01 | 2013-07-02 | 1392 | DAFA | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} |  |  |  | Substantial | 614 | CHA | 4 |  |  | 2009-12-23 | No | Complete
South East | Paktya | Sayed Karam | Naray Kalay | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} | c0a8-008e-1311803bcfc-49d9d9c3-169-64 | MF-HQ-13890 | MCPA - Mine Clearance Planning Agency | AF/0722/08419/MF0137 | 131571 | 69.3933 | 33.6388 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-09-28 | 2013-12-23 | 1392 | DAFA | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} |  |  |  | Substantial | 172 | CHA | 5 |  |  | 2009-12-23 | No | Complete
South East | Paktya | Sayed Karam | Naray Kalay | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} | c0a8-008e-13118046894-4deeb183-17d-eb | MF-HQ-13891 | MCPA - Mine Clearance Planning Agency | AF/0722/8419/MF0136 | 80641 | 69.3933 | 33.6388 | Open | AP Only | AP Only | MineField |  | MBT Project-157 | Paktya Demining Project-08 |  |  |  |  | 1400 |  | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} |  | Low | Agriculture Blocked | Substantial | 381 | CHA | 5 |  |  | 2009-12-23 | No | Open
South East | Paktya | Sayed Karam | Naray Kalay | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} | c0a8-008e-13118050b37-b4b85900-18e-f1 | MF-HQ-13893 | MCPA - Mine Clearance Planning Agency | AF/0722/08419/MF0134 | 73700 | 69.3951 | 33.6459 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-07-03 | 2013-10-27 | 1392 | DAFA | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} |  |  |  | Substantial | 329 | CHA | 4 |  |  | 2009-12-23 | No | Complete
South East | Paktya | Sayed Karam | Naray Kalay | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} | c0a8-008e-1311805a311-16c0580a-1bb-1c | MF-HQ-13889 | MCPA - Mine Clearance Planning Agency | AF/0722/8419/MF0138 | 101000 | 69.3933 | 33.6388 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-050 | Paktya Demining Project-01 AT |  |  |  |  | 1395 |  | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} |  | Low | Agriculture Blocked | Substantial | 381 | CHA | 5 |  |  | 2009-12-23 | No | Open
South East | Paktya | Sayed Karam | Naray Kalay | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} | c0a8-008e-13118062e5d-e42c5e68-1ce-64 | MF-HQ-13892 | MCPA - Mine Clearance Planning Agency | AF/0722/08419/MF0135 | 109918 | 69.3951 | 33.6459 | Closed | Mixed Mine | Mixed Mine | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-06-01 | 2013-09-26 | 1392 | DAFA | {814AB888-B2A8-496D-A239-E4A8DA6A1CF7} |  |  |  | Substantial | 329 | CHA | 4 |  |  | 2009-12-23 | No | Complete
South East | Paktya | Sayed Karam | Salemi Nargay | {7979952E-714B-4CE8-9894-B18E18F127EA} | c0a8-008e-131178fdaff-ff580217-2acd-5 | MF-HQ-14152 | MCPA - Mine Clearance Planning Agency | AF/0722/08456/MF0145 | 22275 | 69.5231 | 33.7818 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-10-05 | 2013-11-04 | 1392 | DAFA | {7979952E-714B-4CE8-9894-B18E18F127EA} |  |  |  | Substantial | 214 | CHA | 4 |  |  | 2010-02-07 | No | Complete
South East | Paktya | Sayed Karam | Salemi Nargay | {7979952E-714B-4CE8-9894-B18E18F127EA} | c0a8-008e-13117912b7a-130bfe82-2b01-1 | MF-HQ-14151 | MCPA - Mine Clearance Planning Agency | AF/0722/08456/MF0146 | 38752 | 69.5231 | 33.7818 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-09-21 | 2013-11-10 | 1392 | DAFA | {7979952E-714B-4CE8-9894-B18E18F127EA} |  |  |  | Substantial | 214 | CHA | 4 |  |  | 2010-02-07 | No | Complete
South East | Paktya | Sayed Karam | Salemi Nargay | {7979952E-714B-4CE8-9894-B18E18F127EA} | c0a8-008e-131180c54e0-f19ca7e8-28b-51 | MF-HQ-14149 | MCPA - Mine Clearance Planning Agency | AF/0722/08456/MF0148 | 27819 | 69.5295 | 33.7845 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-11-11 | 2013-12-23 | 1392 | DAFA | {7979952E-714B-4CE8-9894-B18E18F127EA} |  |  |  | Substantial | 50 | CHA | 5 |  |  | 2010-02-07 | No | Complete
South East | Paktya | Sayed Karam | Salemi Nargay | {7979952E-714B-4CE8-9894-B18E18F127EA} | c0a8-008e-131180ceb51-77e5828b-2d3-1d | MF-HQ-14150 | MCPA - Mine Clearance Planning Agency | AF/0722/08456/MF0147 | 43929 | 69.5295 | 33.7845 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-08-01 | 2013-09-19 | 1392 | DAFA | {7979952E-714B-4CE8-9894-B18E18F127EA} |  |  |  | Substantial | 63 | CHA | 4 |  |  | 2010-02-07 | No | Complete
South East | Paktya | Sayed Karam | Salemi Nargay | {7979952E-714B-4CE8-9894-B18E18F127EA} | c0a8-008e-131944eb443-28f5a387-10b1-2 | MF-HQ-14153 | MCPA - Mine Clearance Planning Agency | AF/0722/08456/MF0144 | 35032 | 69.5231 | 33.7818 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-047 | Paktya Demining Project-05 | VTF-Australia | Yes | 2013-09-24 | 2013-11-04 | 1392 | DAFA | {7979952E-714B-4CE8-9894-B18E18F127EA} |  |  |  | Substantial | 164 | CHA | 4 |  |  | 2010-02-07 | No | Complete
South East | Paktya | Sayed Karam | Usmankhel | {0E766E32-87D0-4099-BE48-6B7F408CBF25} | c0a8-008e-1311779b952-f84ead47-2802-3 | MF-SE-381 | MCPA - Mine Clearance Planning Agency | AF/0722/08418/MF0100 | 51741 | 69.4243 | 33.6593 | Open | AP Only | AP Only | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {0E766E32-87D0-4099-BE48-6B7F408CBF25} |  | High with Victim | High with Victims | Substantial | 104 | CHA | 2 |  |  | 2009-10-12 | No | Open
South East | Paktya | Sayed Karam | Usmankhel | {0E766E32-87D0-4099-BE48-6B7F408CBF25} | c0a8-008e-131180bca5f-89c10418-27b-75 | MF-SE-273 | MCPA - Mine Clearance Planning Agency | AF/0722/08418/MF0108 | 50246 | 69.4149 | 33.6475 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {0E766E32-87D0-4099-BE48-6B7F408CBF25} |  | High with Victim | High with Victims | Substantial | 440 | CHA | 2 |  |  | 2008-07-30 16:30 | No | Open
South East | Paktya | Sayed Karam | Usmankhel | {0E766E32-87D0-4099-BE48-6B7F408CBF25} | c0a8-008e-131180d7ec7-c9920d3a-2f7-19 | MF-SE-274 | MCPA - Mine Clearance Planning Agency | AF/0722/08418/MF0109 | 11212 | 69.4152 | 33.648 | Open | AT Only | AT Only | MineField |  | MBT Project-207 | Paktya Demining Project-01 |  |  |  |  | 1397 |  | {0E766E32-87D0-4099-BE48-6B7F408CBF25} |  | High with Victim | High with Victims | Substantial | 285 | CHA | 2 |  |  | 2009-11-01 | No | Open
South East | Paktya | Shawak | Kheday Baba | {058FAD5D-58CC-48D2-95AD-4F3DA2B6AEA8} | c0a8-0057-12c3b7eded0-ac7d4bd0-189e2- | MF-HQ-12811 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0703/08356/MF004 | 140700 | 69.3525 | 33.4781 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-255 | Paktya Demining Project-06 |  |  |  |  | 1398 |  | {058FAD5D-58CC-48D2-95AD-4F3DA2B6AEA8} |  | Low | Agriculture Blocked | High | 169 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktya | Shawak | Kheday Baba | {058FAD5D-58CC-48D2-95AD-4F3DA2B6AEA8} | c0a8-0057-12c3b9604f0-30251a71-288c0- | MF-HQ-12819 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0703/08356/MF005 | 242500 | 69.3577 | 33.4646 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-255 | Paktya Demining Project-06 |  |  |  |  | 1398 |  | {058FAD5D-58CC-48D2-95AD-4F3DA2B6AEA8} |  | Low | Agriculture Blocked | High | 24 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktya | Shawak | Kheday Baba | {058FAD5D-58CC-48D2-95AD-4F3DA2B6AEA8} | c0a8-0057-12c3ba1a485-8317337c-2ff2c- | MF-HQ-12804 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0703/08356/MF006 | 180000 | 69.3709 | 33.4775 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-255 | Paktya Demining Project-06 |  |  |  |  | 1398 |  | {058FAD5D-58CC-48D2-95AD-4F3DA2B6AEA8} |  | Low | Critical Infrastracture | High | 35 | SHA | 5 |  |  | 2009-08-02 | No | Open
South East | Paktya | Shawak | Shwak | {ABF9E1C4-4694-4907-9204-820A4394A6DA} | c0a8-0057-12c3bb6fa6a-9ea43712-3c980- | MF-HQ-12796 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0703/08349/MF003 | 120000 | 69.3789 | 33.4305 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-255 | Paktya Demining Project-06 |  |  |  |  | 1398 |  | {ABF9E1C4-4694-4907-9204-820A4394A6DA} |  | High with Victim | High with Victims | High | 92 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Paktya | Zurmat | Andar Kala | {A0C9ABC9-E03F-4C89-9DEE-A54FED0D63F8} | c0a8-0057-12c3b7bdb10-a6822f7f-1682a- | MF-HQ-12820 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0702/08627/MF036 | 6199 | 69.0466 | 33.4306 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-046 | Paktya Demining Project-04 |  |  |  |  | 1398 |  | {A0C9ABC9-E03F-4C89-9DEE-A54FED0D63F8} |  | High with Victim | High with Victims | High | 270 | SHA | 2 |  |  | 2009-08-02 | No | Open
South East | Paktya | Zurmat | Babulkhel | {6721242C-F8D4-44C8-AA00-09B7454537D1} | c0a8-0057-12c3b89d7d2-935af434-205fc- | BF-HQ-12831 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0702/08764/BLU0031 | 160000 | 69.1829 | 33.364 | Open | UXO Only | UXO Only | BF |  | MBT Project-266 | Paktya Demining Project-03 AT |  |  |  |  | 1400 |  | {6721242C-F8D4-44C8-AA00-09B7454537D1} |  | High Requested | Resettlment/Local Request | High | 115 | CHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktya | Zurmat | Babulkhel | {6721242C-F8D4-44C8-AA00-09B7454537D1} | c0a8-0057-12c3b973692-9ffba99e-2950b- | BF-HQ-12828 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0702/08764/BLU034 | 900000 | 69.1802 | 33.3627 | Open | UXO Only | UXO Only | BF |  | MBT Project-266 | Paktya Demining Project-03 AT |  |  |  |  | 1400 |  | {6721242C-F8D4-44C8-AA00-09B7454537D1} |  | High Requested | Resettlment/Local Request | High | 286 | CHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktya | Zurmat | Babulkhel | {6721242C-F8D4-44C8-AA00-09B7454537D1} | c0a8-0057-12c3b9dadd4-96460287-2d814- | BF-HQ-12830 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0702/08764/BLU0035 | 100000 | 69.1743 | 33.3618 | Open | UXO Only | UXO Only | BF |  | MBT Project-046 | Paktya Demining Project-04 |  |  |  |  | 1398 |  | {6721242C-F8D4-44C8-AA00-09B7454537D1} |  | High Requested | Resettlment/Local Request | High | 129 | CHA | 3 |  |  | 2009-08-02 | No | Open
South East | Paktya | Zurmat | Babulkhel | {6721242C-F8D4-44C8-AA00-09B7454537D1} | c0a8-0057-12c3ba1e616-c57adc65-301b8- | MF-HQ-12832 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0702/08764/MF033 | 60000 | 69.188 | 33.3721 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-046 | Paktya Demining Project-04 |  |  |  |  | 1398 |  | {6721242C-F8D4-44C8-AA00-09B7454537D1} |  | Medium | Critical Infrastracture | High | 42 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Paktya | Zurmat | Babulkhel | {6721242C-F8D4-44C8-AA00-09B7454537D1} | c0a8-0057-12c3baff81b-75800c97-387e4- | MF-HQ-12799 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0702/08764/MF030 | 5000 | 69.1829 | 33.364 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-046 | Paktya Demining Project-04 |  |  |  |  | 1398 |  | {6721242C-F8D4-44C8-AA00-09B7454537D1} |  | Medium | Critical Infrastracture | High | 228 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Paktya | Zurmat | Babulkhel | {6721242C-F8D4-44C8-AA00-09B7454537D1} | c0a8-008e-130cb91287a-19945ada-1184-7 | BF-HQ-12829 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0702/08764/BLU032 | 40000 | 69.188 | 33.3721 | Open | UXO Only | UXO Only | BF |  | MBT Project-046 | Paktya Demining Project-04 |  |  |  |  | 1398 |  | {6721242C-F8D4-44C8-AA00-09B7454537D1} |  | Medium | Critical Infrastracture | High | 181 | CHA | 3 |  |  | 2009-08-02 | No | Open
South East | Paktya | Zurmat | Hosaynkhel | {C3F7A04D-3E56-4417-A647-4525C4F0ACA8} | c0a8-0057-12c3bab6e11-1f992948-35c88- | MF-HQ-12778 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0702/08692/MF037 | 180000 | 69.0776 | 33.5652 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-266 | Paktya Demining Project-03 AT |  |  |  |  | 1400 |  | {C3F7A04D-3E56-4417-A647-4525C4F0ACA8} |  | Low | Critical Infrastracture | High | 113 | SHA | 4 |  |  | 2009-08-02 | No | Open
South East | Paktya | Zurmat | Kharashi | {66E24A1E-F7DD-46CE-9B0D-B6E7063E6E7D} | c0a8-0057-12c3b892863-5a6d809c-1fed4- | MF-HQ-12788 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0702/08630/MF029 | 19000 | 69.0389 | 33.4438 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-046 | Paktya Demining Project-04 |  |  |  |  | 1398 |  | {66E24A1E-F7DD-46CE-9B0D-B6E7063E6E7D} |  | Medium | Critical Infrastracture | High | 2278 | SHA | 3 |  |  | 2009-08-02 | No | Open
South East | Paktya | Zurmat | Sepine Takhte | {E6654637-2A56-4879-B0F1-251017CF1AED} | c0a8-0057-12c3b7d1178-b59f6d18-17647- | MF-HQ-12793 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0702/08672/MF038 | 60000 | 69.1693 | 33.4269 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-266 | Paktya Demining Project-03 AT |  |  |  |  | 1400 |  | {E6654637-2A56-4879-B0F1-251017CF1AED} |  | Low | Other | High | 34 | SHA | 5 |  |  | 2009-08-02 | No | Open
West | Badghis | Ab Kamari | Rozeeha-I-Ab Kamari | {29B22E0D-FB84-4A05-B375-92393D565795} | c0a8-0057-12c3b8adc52-75adac99-21150- | MF-HQ-7301 | MCPA - Mine Clearance Planning Agency | AF/1902/00117/MF0022 | 42777 | 63.0524 | 34.9756 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-188 | Badghis Demining Project-01 |  |  |  |  | 1397 |  | {29B22E0D-FB84-4A05-B375-92393D565795} |  | High with Victim | High with Victims | Moderate | 896 | CHA | 2 |  |  | 2000-06-22 | No | Open
West | Badghis | Bala Murghab | Akaza'i | {95FDBDE4-7A05-49F8-8DC2-D6631AC4FCFD} | c0a8-0057-12c3b7c14c5-db50edc-16abb-2 | MF-HQ-10986 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/17051/MF0020 | 22500 | 63.2364 | 35.6214 | Open | AP Only | AP Only | Converted From SHA | Blank | MBT Project-188 | Badghis Demining Project-01 |  | No |  |  | 1397 | None | {95FDBDE4-7A05-49F8-8DC2-D6631AC4FCFD} |  | Low | Critical Infrastracture | High | 9 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Akaza'i | {95FDBDE4-7A05-49F8-8DC2-D6631AC4FCFD} | c0a8-0057-12c3b9dcd07-591afa97-2d942- | MF-HQ-10985 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/17051/MF0021 | 30000 | 63.2378 | 35.6165 | Open | AP Only | AP Only | Converted From SHA | Blank | MBT Project-188 | Badghis Demining Project-01 |  | No |  |  | 1397 | None | {95FDBDE4-7A05-49F8-8DC2-D6631AC4FCFD} |  | Low | Agriculture Blocked | High | 10 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Akaza'i | {95FDBDE4-7A05-49F8-8DC2-D6631AC4FCFD} | c0a8-0057-12c3baa658b-ec862058-352d3- | MF-HQ-10987 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/17051/MF0019 | 40000 | 63.2514 | 35.6269 | Open | Mixed Mine | Mixed Mine | Converted From SHA | Blank | MBT Project-188 | Badghis Demining Project-01 |  | No |  |  | 1397 | None | {95FDBDE4-7A05-49F8-8DC2-D6631AC4FCFD} |  | Low | Agriculture Blocked | High | 18 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Bokan (1) | {F910CC34-676D-42BF-B2F8-A22BC38CB84B} | c0a8-0057-12c3bb39f87-53a7ee95-3aae0- | MF-HQ-10980 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/17075/MF0022 | 8200 | 63.5742 | 35.7025 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-188 | Badghis Demining Project-01 |  |  |  |  | 1397 |  | {F910CC34-676D-42BF-B2F8-A22BC38CB84B} |  | Low | Agriculture Blocked | High | 26 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Haji Noor Mohd | {7FA1006E-AAA0-4380-9E5D-0EEAF6564A6D} | c0a8-0057-12c3b7dc79b-43fd6a04-17e59- | MF-HQ-10994 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/00387/MF0025 | 30000 | 63.1829 | 35.5767 | Open | AP Only | AP Only | Converted From SHA | Blank | MBT Project-188 | Badghis Demining Project-01 |  | No |  |  | 1397 | None | {7FA1006E-AAA0-4380-9E5D-0EEAF6564A6D} |  | Low | Agriculture Blocked | High | 16 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Haji Noor Mohd | {7FA1006E-AAA0-4380-9E5D-0EEAF6564A6D} | c0a8-0057-12c3bb0aac5-1d02edd3-38e9c- | MF-HQ-10995 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/00387/MF0024 | 25000 | 63.1942 | 35.5596 | Open | AP Only | AP Only | Converted From SHA | Blank | MBT Project-188 | Badghis Demining Project-01 |  | No |  |  | 1397 | None | {7FA1006E-AAA0-4380-9E5D-0EEAF6564A6D} |  | Low | Agriculture Blocked | High | 3 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Haji Noor Mohd | {7FA1006E-AAA0-4380-9E5D-0EEAF6564A6D} | c0a8-0057-12c3bb5d9a4-7b66796-3bf90-e | MF-HQ-10996 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/00387/MF0023 | 60000 | 63.2108 | 35.5491 | Open | Mixed Mine | Mixed Mine | Converted From SHA | Blank | MBT Project-188 | Badghis Demining Project-01 |  | No |  |  | 1397 | None | {7FA1006E-AAA0-4380-9E5D-0EEAF6564A6D} |  | Low | Agriculture Blocked | High | 8 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Mangan | {8AD1FE8C-C849-414F-AC5B-973CE772C554} | c0a8-0057-12c3ba1f2b3-fd5c921f-3022a- | MF-HQ-10988 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/17028/MF0028 | 100000 | 63.1197 | 35.4197 | Open | AT Only | AT Only | Converted From SHA | Blank | MBT Project-188 | Badghis Demining Project-01 |  | No |  |  | 1397 | None | {8AD1FE8C-C849-414F-AC5B-973CE772C554} |  | Low | Critical Infrastracture | High | 66 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Mangan | {8AD1FE8C-C849-414F-AC5B-973CE772C554} | c0a8-0057-12c3baac7d5-c5fc4126-35652- | MF-HQ-10992 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/17028/MF0026 | 67500 | 63.1547 | 35.4837 | Open | AP Only | AP Only | Converted From SHA | Blank | MBT Project-188 | Badghis Demining Project-01 |  | No |  |  | 1397 | None | {8AD1FE8C-C849-414F-AC5B-973CE772C554} |  | Medium | Critical Infrastracture | High | 37 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Mangan | {8AD1FE8C-C849-414F-AC5B-973CE772C554} | c0a8-0057-12c3bab4666-b4bbbad0-35b07- | MF-HQ-10990 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/17028/MF0027 | 24000 | 63.1547 | 35.4837 | Open | AT Only | AT Only | Converted From SHA | Blank | MBT Project-188 | Badghis Demining Project-01 |  | No |  |  | 1397 | None | {8AD1FE8C-C849-414F-AC5B-973CE772C554} |  | Low | Critical Infrastracture | High | 92 | SHA | 4 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Oibchaq | {18BE0607-7513-494B-A491-9EC6D75E39AB} | c0a8-0057-12c3b85ae8b-15b672ad-1d7eb- | MF-HQ-10978 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/17043/MF0030 | 600 | 63.3418 | 35.5735 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-188 | Badghis Demining Project-01 |  |  |  |  | 1397 |  | {18BE0607-7513-494B-A491-9EC6D75E39AB} |  | High with Victim | High with Victims | High | 0 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Oibchaq | {18BE0607-7513-494B-A491-9EC6D75E39AB} | c0a8-0057-12c3b98f67c-7369f5bc-2a77d- | MF-HQ-10979 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/17043/MF0029 | 10657 | 63.3464 | 35.5707 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-188 | Badghis Demining Project-01 |  |  |  |  | 1397 |  | {18BE0607-7513-494B-A491-9EC6D75E39AB} |  | High with Victim | High with Victims | High | 51 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Badghis | Bala Murghab | Sakhra-i-Arbab Majnun | {B91CB81D-78B1-4EA0-B4DC-4422FB42B5F5} | c0a8-0057-12c3b94382d-12ee8064-275a3- | MF-HQ-10997 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1908/17016/MF0031 | 18000 | 63.3962 | 35.4138 | Open | Mixed Mine | Mixed Mine | Converted From SHA | Blank | MBT Project-188 | Badghis Demining Project-01 |  | No |  |  | 1397 | None | {B91CB81D-78B1-4EA0-B4DC-4422FB42B5F5} |  | Medium | Critical Infrastracture | High | 2501 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Badghis | Qadis | Ghalcharkh | {6B3E56A6-8F00-4AD2-A62D-980981B92402} | c0a8-008e-133a5e8d44d-4e411b32-541-79 | MF-16354 | MCPA - Mine Clearance Planning Agency | AF/1903/17228/MF0011 | 179187 | 63.4806 | 34.9573 | Open | AP Only | AP Only | MineField | Blank | MBT Project-188 | Badghis Demining Project-01 |  | No | 2012-04-01 | 2012-07-31 | 1397 | None | {6B3E56A6-8F00-4AD2-A62D-980981B92402} |  | Low | Agriculture Blocked | High | 7 | CHA | 5 |  |  | 2011-09-22 16:30 | No | Open
West | Farah | Anar Dara | Anar Dara | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} | c0a8-0057-12c3b874a68-f6eca9e4-1e9a9- | MF-HQ-11042 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2107/31814/MF0058 | 1337800 | 61.6542 | 32.7072 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} |  | High with Victim | High with Victims | Moderate | 5 | SHA | 2 |  |  | 2009-06-17 | No | Open
West | Farah | Anar Dara | Anar Dara | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} | c0a8-0057-12c3b8ce5de-da816508-227f8- | MF-WA-39 | MCPA - Mine Clearance Planning Agency | AF/2107/31814/MF0055 | 85652 | 61.654 | 32.7502 | Open | AT Only | AT Only | MineField |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} |  | High with Victim | High with Victims | Moderate | 19 | CHA | 2 |  |  | 2003-04-30 | No | Open
West | Farah | Anar Dara | Anar Dara | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} | c0a8-0057-12c3b8ce87d-5d7d9105-22817- | MF-WA-65 | MCPA - Mine Clearance Planning Agency | AF/2107/31814/MF0056 | 146128 | 61.6516 | 32.7503 | Open | AT Only | AT Only | MineField |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} |  | High with Victim | High with Victims | Moderate | 1 | CHA | 2 |  |  | 2003-04-30 | No | Open
West | Farah | Anar Dara | Anar Dara | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} | c0a8-0057-12c3b9bde3e-efa24512-2c5c5- | MF-HQ-11043 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2107/31814/MF0059 | 472500 | 61.6432 | 32.7606 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} |  | High with Victim | High with Victims | Moderate | 10 | SHA | 2 |  |  | 2009-06-17 | No | Open
West | Farah | Anar Dara | Anar Dara | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} | c0a8-0057-12c3ba8721e-ee07a4a3-3413f- | MF-HQ-11044 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2107/31814/MF0057 | 37400 | 61.6721 | 32.749 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} |  | High with Victim | High with Victims | Moderate | 1259 | SHA | 2 |  |  | 2009-06-17 | No | Open
West | Farah | Anar Dara | Anar Dara | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} | c0a8-0057-12c3bb3702e-94b4578e-3a916- | MF-HQ-2286 | MCPA - Mine Clearance Planning Agency | AF/2107/31814/MF0020 | 25500 | 61.4974 | 32.7974 | Open | AT Only | AT Only | MineField |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} |  | High with Victim | High with Victims | Moderate | 17 | CHA | 2 |  |  | 1995-11-05 | No | Open
West | Farah | Anar Dara | Anar Dara | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} | c0a8-0057-12c3bb3f90b-a6286629-3ae28- | MF-HQ-7871 | MCPA - Mine Clearance Planning Agency | AF/2107/31814/MF0050 | 107600 | 61.6711 | 32.7486 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} |  | High with Victim | High with Victims | Moderate | 385 | CHA | 2 |  |  | 2001-02-22 | No | Open
West | Farah | Anar Dara | Anar Dara | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} | c0a8-0057-12c3bb3fbd9-d681aae4-3ae3f- | MF-HQ-8010 | MCPA - Mine Clearance Planning Agency | AF/2107/31814/MF0052 | 91200 | 61.67 | 32.745 | Open | Mixed | Mixed AT UXO | MineField |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {B3ADFB11-77DE-42DD-A38F-46EC72C07DBC} |  | High with Victim | High with Victims | Moderate | 830 | CHA | 2 |  |  | 2001-04-11 | No | Open
West | Farah | Anar Dara | Daghal Lateef | {31C68F3B-E7A0-4B67-8C0D-0927D56AF924} | c0a8-0057-12c3b943071-49f85473-27557- | MF-HQ-11034 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2107/00144/MF0060 | 77760 | 61.386 | 32.8002 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-189 | Farah Demining Project-01 |  |  |  |  | 1396 |  | {31C68F3B-E7A0-4B67-8C0D-0927D56AF924} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-03 | No | Open
West | Farah | Anar Dara | Dalgha | {C6468DFE-0C13-4705-8A4B-F62A70BF588C} | c0a8-0057-12c3b9b629b-9e00295-2c0cf-4 | MF-HQ-11035 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2107/18795/MF0061 | 50400 | 61.5841 | 32.7876 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-189 | Farah Demining Project-01 |  |  |  |  | 1396 |  | {C6468DFE-0C13-4705-8A4B-F62A70BF588C} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-03 | No | Open
West | Farah | Anar Dara | Dar Shar | {E2FF6100-1769-48D3-9A1F-13881D3FA52B} | c0a8-0057-12c3b9996dc-f463253f-2ae1f- | MF-HQ-11029 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2107/00703/MF0063 | 306675 | 61.45 | 32.7252 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {E2FF6100-1769-48D3-9A1F-13881D3FA52B} |  | Medium | Critical Infrastracture | Moderate | 0 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Farah | Anar Dara | Dar Shar | {E2FF6100-1769-48D3-9A1F-13881D3FA52B} | c0a8-0057-12c3bb2ca41-90172da5-3a2ab- | MF-HQ-11028 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1207/00703/MF0062 | 630784 | 61.371 | 32.6858 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-189 | Farah Demining Project-01 |  |  |  |  | 1396 |  | {E2FF6100-1769-48D3-9A1F-13881D3FA52B} |  | Low | Critical Infrastracture | Moderate | 11 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Anar Dara | Gurgak | {43B0686C-20C8-4BBD-96A5-421A11AA65B6} | c0a8-0057-12c3b969440-5f24544d-28e75- | MF-WA-19 | MCPA - Mine Clearance Planning Agency | AF/2107/18971/MF0054 | 91635 | 61.7085 | 32.7265 | Open | AT Only | AT Only | MineField |  | MBT Project-275 | Farah Demining Project-07 (AT) |  |  |  |  | 1400 |  | {43B0686C-20C8-4BBD-96A5-421A11AA65B6} |  | Low | Critical Infrastracture | Moderate | 0 | CHA | 4 |  |  | 2003-02-28 | No | Open
West | Farah | Anar Dara | Gurgak | {43B0686C-20C8-4BBD-96A5-421A11AA65B6} | c0a8-0057-12c3b9a714f-942ca0c1-2b73f- | MF-HQ-11102 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2107/18971/MF0064 | 119600 | 61.6947 | 32.7158 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-275 | Farah Demining Project-07 (AT) |  |  |  |  | 1400 |  | {43B0686C-20C8-4BBD-96A5-421A11AA65B6} |  | Low | Critical Infrastracture | Moderate | 164 | SHA | 4 |  |  | 2009-06-17 | No | Open
West | Farah | Anar Dara | Gurgak | {43B0686C-20C8-4BBD-96A5-421A11AA65B6} | c0a8-0057-12c3ba25e30-932819e1-305f2- | MF-HQ-11103 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2107/18971/MF0065 | 162000 | 61.7068 | 32.7226 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-275 | Farah Demining Project-07 (AT) |  |  |  |  | 1400 |  | {43B0686C-20C8-4BBD-96A5-421A11AA65B6} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Anar Dara | Qarya-i-Kalata | {0AA6FD6A-54E4-4078-B2D6-86D21FC94A09} | c0a8-0057-12c3b96d949-78d26dc6-29126- | MF-HQ-11021 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1207/18959/MF0066 | 187600 | 61.7621 | 32.7803 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-189 | Farah Demining Project-01 |  |  |  |  | 1396 |  | {0AA6FD6A-54E4-4078-B2D6-86D21FC94A09} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Bakwa | Asad Jmeka | {5BCE8EC1-D9C5-47A4-81E7-73ADCBF9DCFB} | c0a8-0057-12c3babd367-dfe69f0-35ffa-8 | MF-HQ-11040 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2102/19263/MF0011 | 150000 | 63.1537 | 32.2833 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-274 | Farah Demining Project-08 |  |  |  |  | 1401 |  | {5BCE8EC1-D9C5-47A4-81E7-73ADCBF9DCFB} |  | Low | Agriculture Blocked | High | 3 | SHA | 5 |  |  | 2009-06-03 | No | Open
West | Farah | Bakwa | Asad Jmeka | {5BCE8EC1-D9C5-47A4-81E7-73ADCBF9DCFB} | c0a8-008e-132384551fb-e9136094-13f5-3 | MF-HQ-11041 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2102/19263/MF0012 | 460000 | 63.2115 | 32.3736 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-274 | Farah Demining Project-08 |  |  |  |  | 1401 |  | {5BCE8EC1-D9C5-47A4-81E7-73ADCBF9DCFB} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-06-03 | No | Open
West | Farah | Bakwa | Baraghna | {B5DACF48-7D5A-46C9-82FC-853D585505F6} | c0a8-0057-12c3b973116-b6bec9cf-294d8- | MF-WA-14 | MCPA - Mine Clearance Planning Agency | AF/2102/00555/MF0006 | 123408 | 63.2066 | 32.3645 | Open | AT Only | AT Only | MineField |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {B5DACF48-7D5A-46C9-82FC-853D585505F6} |  | Low | Agriculture Blocked | High | 6 | CHA | 5 |  |  | 2003-04-30 | No | Open
West | Farah | Bakwa | Baraghna | {B5DACF48-7D5A-46C9-82FC-853D585505F6} | c0a8-0057-12c3b97328d-3c80862-294e3-4 | MF-WA-28 | MCPA - Mine Clearance Planning Agency | AF/2102/00555/MF0007 | 699 | 63.2029 | 32.3534 | Open | AT Only | AT Only | MineField |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {B5DACF48-7D5A-46C9-82FC-853D585505F6} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2003-04-30 | No | Open
West | Farah | Bakwa | Chichi Khuni | {FEB1B8A4-158A-440F-A626-EDF646274BC1} | c0a8-0057-12c3b81e280-9225fcc7-1ac56- | MF-WA-95 | MCPA - Mine Clearance Planning Agency | AF/2102/19022/0009 | 54154 | 62.947 | 32.248 | Open | AT Only | AT Only | MineField |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {FEB1B8A4-158A-440F-A626-EDF646274BC1} |  | Low | Agriculture Blocked | High | 44 | CHA | 5 |  |  | 2004-01-31 | No | Open
West | Farah | Bakwa | Chichi Khuni | {FEB1B8A4-158A-440F-A626-EDF646274BC1} | c0a8-0057-12c3b81e8c7-d4ec4289-1aca0- | MF-HQ-11031 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2102/19022/MF0013 | 6000000 | 62.9439 | 32.2825 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-313 | Farah Demining Project-05 |  |  |  |  | 1396 |  | {FEB1B8A4-158A-440F-A626-EDF646274BC1} |  | Low | Agriculture Blocked | High | 15 | SHA | 5 |  |  | 2009-06-03 | No | Open
West | Farah | Bakwa | Chichi Khuni | {FEB1B8A4-158A-440F-A626-EDF646274BC1} | c0a8-0057-12c3b89d43a-6184d8a3-205d0- | MF-WA-97 | MCPA - Mine Clearance Planning Agency | AF/2102/19022/0010 | 36358 | 62.949 | 32.245 | Open | AP Only | AP Only | MineField |  | MBT Project-173 | Farah Demining Project-04 |  |  |  |  | 1397 |  | {FEB1B8A4-158A-440F-A626-EDF646274BC1} |  | Medium | Agriculture Blocked | High | 602 | CHA | 3 |  |  | 2004-01-31 | No | Open
West | Farah | Bakwa | Chichi Khuni | {FEB1B8A4-158A-440F-A626-EDF646274BC1} | c0a8-0057-12c3b8a59eb-e7deef95-20bba- | MF-WA-96 | MCPA - Mine Clearance Planning Agency | AF/2102/19022/008 | 59814 | 62.95 | 32.243 | Open | AT Only | AT Only | MineField |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {FEB1B8A4-158A-440F-A626-EDF646274BC1} |  | Low | Agriculture Blocked | High | 623 | CHA | 4 |  |  | 2004-01-31 | No | Open
West | Farah | Bakwa | Sanaa | {9F95ACDC-6801-4AD4-9F03-892D5711E744} | c0a8-0057-12c3b7c61ea-25aa916-16e44-8 | MF-HQ-11066 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2102/00489/MF0014 | 400000 | 63.0507 | 32.3846 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {9F95ACDC-6801-4AD4-9F03-892D5711E744} |  | Low | Agriculture Blocked | High | 1 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Bakwa | Si Av | {50FE0C86-AAB0-433D-B672-21FD12152758} | c0a8-0057-12c3b80af05-19cdbabd-19ec5- | MF-HQ-11071 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2102/19024/MF0016 | 200000 | 62.5639 | 32.2386 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-274 | Farah Demining Project-08 |  |  |  |  | 1401 |  | {50FE0C86-AAB0-433D-B672-21FD12152758} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Bakwa | Si Av | {50FE0C86-AAB0-433D-B672-21FD12152758} | c0a8-0057-12c3b8dd23c-6df10626-23208- | MF-HQ-11070 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2102/19024/MF0015 | 500000 | 62.7324 | 32.3096 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-274 | Farah Demining Project-08 |  |  |  |  | 1401 |  | {50FE0C86-AAB0-433D-B672-21FD12152758} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Bakwa | Tudanak | {5A0C602A-7A8D-427E-9EFF-524F9B2C79A5} | c0a8-0057-12c3bae18aa-f5680c59-375e8- | MF-HQ-11085 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2102/00268/MF0017 | 20250000 | 63.1004 | 32.2923 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-291 | Farah Demining Project-10 (AT) |  |  |  |  | 1401 |  | {5A0C602A-7A8D-427E-9EFF-524F9B2C79A5} |  | Low | Agriculture Blocked | High | 33 | SHA | 5 |  |  | 2009-06-03 | No | Open
West | Farah | Bala Buluk | Chakab | {DDA2AC48-ECE4-4E08-9336-1D5C69B3FE73} | c0a8-0057-12c3b99416e-c2378c0f-2aa9e- | MF-HQ-11037 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2105/19035/MF0043 | 17800 | 62.9216 | 32.5551 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-173 | Farah Demining Project-04 |  |  |  |  | 1397 |  | {DDA2AC48-ECE4-4E08-9336-1D5C69B3FE73} |  | High with Victim | High with Victims | High | 188 | SHA | 1 |  |  | 2009-06-17 | No | Open
West | Farah | Bala Buluk | Chashma-I-Rabat | {F90050BD-17BC-47FD-9E34-D7861DE0248F} | c0a8-0057-12c3b948954-aeb560e0-278e7- | MF-HQ-11032 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2105/00786/MF0044 | 18900 | 62.8364 | 33.1377 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {F90050BD-17BC-47FD-9E34-D7861DE0248F} |  | Low | Other | High | 41 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Bala Buluk | Deh Tut | {3D854D22-A267-42D7-BA91-2D441064AB4D} | c0a8-0057-12c3b8c5b5c-37a4225f-22210- | MF-HQ-11026 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2105/19267/MF0046 | 320000 | 63.2191 | 32.5449 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-173 | Farah Demining Project-04 |  |  |  |  | 1397 |  | {3D854D22-A267-42D7-BA91-2D441064AB4D} |  | Medium | Critical Infrastracture | High | 206 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Farah | Bala Buluk | Deh Tut | {3D854D22-A267-42D7-BA91-2D441064AB4D} | c0a8-0057-12c3ba09108-8c2dc65a-2f497- | MF-HQ-11027 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2105/19267/MF0045 | 280000 | 63.2185 | 32.5488 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-173 | Farah Demining Project-04 |  |  |  |  | 1397 |  | {3D854D22-A267-42D7-BA91-2D441064AB4D} |  | Medium | Agriculture Blocked | High | 14 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Farah | Bala Buluk | Dizak | {28763D3F-5C78-40C4-BD49-9BCFC1FE511D} | c0a8-0057-12c3b98344b-f36e68e1-29f85- | MF-HQ-11030 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2105/19059/MF0047 | 135000 | 62.6153 | 32.5403 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {28763D3F-5C78-40C4-BD49-9BCFC1FE511D} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Bala Buluk | Kanesk | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} | c0a8-0057-12c3b6a3fa9-5925a08d-9609-b | MF-HQ-15243 | MCPA - Mine Clearance Planning Agency | AF/2105/19028/MF0056 | 84210 | 62.2956 | 32.5061 | Open | AT Only | AT Only | MineField |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} | Planned year removed | High with Victim | High with Victims | High | 28 | CHA | 5 |  |  | 2010-09-28 | No | Open
West | Farah | Bala Buluk | Kanesk | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} | c0a8-0057-12c3b79485a-ba785a44-14a9e- | MF-HQ-15240 | MCPA - Mine Clearance Planning Agency | AF/2105/19028/MF0055 | 49362 | 62.398 | 32.5708 | Open | AT Only | AT Only | MineField |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} | Planned Year Removed | High with Victim | High with Victims | High | 0 | CHA | 5 |  |  | 2010-09-29 | No | Open
West | Farah | Bala Buluk | Kanesk | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} | c0a8-0057-12c3b920579-4a1ccfee-25e7d- | MF-HQ-11110 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2105/19028/MF0050 | 96000 | 62.3412 | 32.5189 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} | Planned Year Removed | High with Victim | High with Victims | High | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Bala Buluk | Kanesk | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} | c0a8-00f6-137b632e49e-8ae457e8-32b5-8 | Hz-ID-17011 | DAFA - Demining Agency for Afghanistan | AF/2105/19028/MF0059 | 15527 | 62.2956 | 32.5062 | Open | AT Only | AT Only | MineField |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} |  | High with Victim | High with Victims | High | 20 | CHA | 5 |  |  | 2011-10-03 16:30 | No | Open
West | Farah | Bala Buluk | Kanesk | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} | c0a8-00f6-137b667acfb-128908b0-3c-a04 | Hz-ID-17012 | DAFA - Demining Agency for Afghanistan | AF/2105/19028/MF0060 | 54574 | 62.3867 | 32.5662 | Open | AT Only | AT Only | MineField |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} |  | High with Victim | High with Victims | High | 1 | CHA | 5 |  |  | 2011-10-04 16:30 | No | Open
West | Farah | Bala Buluk | Kanesk | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} | c0a8-00f6-137c185a324-d74b7e7f-27fe-1 | Hz-ID-17009 | DAFA - Demining Agency for Afghanistan | AF/2105/19028/MF0058 | 61046 | 62.3867 | 32.5662 | Open | AT Only | AT Only | MineField |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {81EF8431-DD6D-48D5-B52C-5FDDE3F49B64} |  | High with Victim | High with Victims | High | 0 | CHA | 5 |  |  | 2011-10-04 16:30 | No | Open
West | Farah | Bala Buluk | Sar-e Takht | {B74034AF-5B76-4C5D-907D-E75313A0F024} | c0a8-0057-12c3bb185d5-d4137a06-396ba- | MF-HQ-11069 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2105/19122/MF0052 | 131248 | 62.7251 | 33.0509 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-173 | Farah Demining Project-04 |  |  |  |  | 1397 |  | {B74034AF-5B76-4C5D-907D-E75313A0F024} |  | Low | Agriculture Blocked | High | 55 | SHA | 4 |  |  | 2009-06-17 | No | Open
West | Farah | Farah | Canura | {FC0EFFB9-9E69-4139-AEC1-C19AE1D27CC5} | c0a8-0057-12c3b7c165b-5e44ebe-16acc-c | MF-HQ-11045 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2101/18480/MF0034 | 84060 | 62.1964 | 32.2239 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {FC0EFFB9-9E69-4139-AEC1-C19AE1D27CC5} |  | Low | Agriculture Blocked | Substantial | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Farah | Kah Danak | {300E0AE6-9BE0-4C4E-842C-76FA1E201AD4} | c0a8-0057-12c3b7bb72c-b8e3f606-16670- | MF-HQ-11106 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2101/18488/MF0035 | 70200 | 62.2012 | 32.2993 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {300E0AE6-9BE0-4C4E-842C-76FA1E201AD4} | Planned Year Removed | High Requested | Resettlment/Local Request | Substantial | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Farah | Pirakay | {B02E2C7F-75E3-4D83-A204-2268F3D87B8C} | c0a8-00f6-13808a1f876-98a0b024-112b-a | Hz-ID-17063 | DAFA - Demining Agency for Afghanistan | AF/2101/18585/MF0038 | 130166 | 62.1179 | 32.3647 | Open | AT Only | AT Only | MineField |  | MBT Project-173 | Farah Demining Project-04 |  |  |  |  | 1397 |  | {B02E2C7F-75E3-4D83-A204-2268F3D87B8C} |  | Medium | Critical Infrastracture | Substantial | 1376 | CHA | 3 |  |  | 2011-10-01 16:30 | No | Open
West | Farah | Farah | Pirakay | {B02E2C7F-75E3-4D83-A204-2268F3D87B8C} | c0a8-00f6-1384b6db8a5-59c1e610-21bd-9 | Hz-ID-17062 | DAFA - Demining Agency for Afghanistan | AF/2101/18585/MF0037 | 58300 | 62.462 | 32.2908 | Open | AT Only | AT Only | MineField |  | MBT Project-173 | Farah Demining Project-04 |  |  |  |  | 1397 |  | {B02E2C7F-75E3-4D83-A204-2268F3D87B8C} |  | Medium | Critical Infrastracture | Substantial | 505 | CHA | 3 |  |  | 2011-10-01 16:30 | No | Open
West | Farah | Gulistan | Gunbad | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} | c0a8-0057-12c3b806d84-9c3d32ba-19bbc- | MF-HQ-11099 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2103/00791/MF0008 | 800000 | 63.5513 | 32.4728 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-273 | Farah Demining Project-06 |  |  |  |  | 1396 |  | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} |  | Low | Agriculture Blocked | High | 7 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Gulistan | Gunbad | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} | c0a8-0057-12c3b8753ac-4e22d33c-1ea04- | MF-WA-58 | MCPA - Mine Clearance Planning Agency | AF/2103/00791/MF0004 | 87625 | 63.2188 | 32.3413 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-273 | Farah Demining Project-06 |  |  |  |  | 1396 |  | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} |  | Low | Other | High | 11 | CHA | 5 |  |  | 2003-03-31 | No | Open
West | Farah | Gulistan | Gunbad | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} | c0a8-0057-12c3b898c23-b370e550-20282- | MF-WA-13 | MCPA - Mine Clearance Planning Agency | AF/2103/00791/MF0007 | 85848 | 63.2176 | 32.3826 | Open | AP Only | AP Only | MineField |  | MBT Project-273 | Farah Demining Project-06 |  |  |  |  | 1396 |  | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} |  | Low | Critical Infrastracture | High | 4 | CHA | 5 |  |  | 2003-04-03 | No | Open
West | Farah | Gulistan | Gunbad | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} | c0a8-0057-12c3b89900a-33bb48c0-2029c- | MF-WA-15 | MCPA - Mine Clearance Planning Agency | AF/2103/00791/MF0006 | 50100 | 63.2173 | 32.3817 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-273 | Farah Demining Project-06 |  |  |  |  | 1396 |  | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} |  | Low | Critical Infrastracture | High | 3 | CHA | 5 |  |  | 2003-04-30 | No | Open
West | Farah | Gulistan | Gunbad | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} | c0a8-0057-12c3b95395d-cb49080-2800d-2 | MF-WA-3 | MCPA - Mine Clearance Planning Agency | AF/2103/00791/MF0005 | 83775 | 63.2146 | 32.3742 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-273 | Farah Demining Project-06 |  |  |  |  | 1396 |  | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} |  | Low | Critical Infrastracture | High | 9 | CHA | 5 |  |  | 2003-04-30 | No | Open
West | Farah | Gulistan | Gunbad | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} | c0a8-0057-12c3bb137d6-113e556c-393dc- | MF-HQ-11101 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2103/00791/MF0009 | 300000 | 63.5323 | 32.4568 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-273 | Farah Demining Project-06 |  |  |  |  | 1396 |  | {FAED6EBC-8CB5-47E9-BC5A-7CF41F3D0ABE} |  | Low | Agriculture Blocked | High | 56 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Gulistan | Qarya-i-Charra | {E37C113F-2A9C-4515-A340-C353898288EC} | c0a8-0057-12c3b9f3a65-2ca0ac80-2e75a- | MF-HQ-11096 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2103/19266/MF0012 | 600000 | 63.2152 | 32.4998 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-173 | Farah Demining Project-04 |  |  |  |  | 1397 |  | {E37C113F-2A9C-4515-A340-C353898288EC} |  | Medium | Water Blocked | High | 35 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Farah | Gulistan | Qarya-i-Charra | {E37C113F-2A9C-4515-A340-C353898288EC} | c0a8-0057-12c3ba0ccdf-fa6db6f-2f6f9-2 | MF-HQ-11098 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2103/19266/MF0013 | 800000 | 63.2338 | 32.4738 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-273 | Farah Demining Project-06 |  |  |  |  | 1396 |  | {E37C113F-2A9C-4515-A340-C353898288EC} |  | Low | Agriculture Blocked | High | 5 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Gulistan | Qarya-i-Charra | {E37C113F-2A9C-4515-A340-C353898288EC} | c0a8-0057-12c3ba24e68-e913154d-30577- | MF-HQ-11094 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2103/19266/MF0010 | 640000 | 63.2112 | 32.4761 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-173 | Farah Demining Project-04 |  |  |  |  | 1397 |  | {E37C113F-2A9C-4515-A340-C353898288EC} |  | Medium | Water Blocked | High | 31 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Farah | Gulistan | Qarya-i-Charra | {E37C113F-2A9C-4515-A340-C353898288EC} | c0a8-0057-12c3ba2b7a4-35c0800a-30977- | MF-HQ-11095 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2103/19266/MF0011 | 120000 | 63.1933 | 32.47 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {E37C113F-2A9C-4515-A340-C353898288EC} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Khaki Safed | Khalo | {453B56EC-92AB-4F4B-9BF0-711C0CBBA4D5} | c0a8-0057-12c3b89dc54-4786e94a-2062b- | MF-HQ-11112 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2106/18675/MF0011 | 80000 | 61.9389 | 32.8344 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {453B56EC-92AB-4F4B-9BF0-711C0CBBA4D5} |  | High with Victim | High with Victims | High | 0 | SHA | 1 |  |  | 2009-06-17 | No | Open
West | Farah | Khaki Safed | Khosk Abeh | {6F49F75A-8BE4-48EC-A171-6A5213F17D88} | c0a8-0057-12c3ba8b8ed-98fe3603-3438c- | MF-HQ-11019 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2106/18637/MF0012 | 219450 | 62.1937 | 32.7958 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-274 | Farah Demining Project-08 |  |  |  |  | 1401 |  | {6F49F75A-8BE4-48EC-A171-6A5213F17D88} |  | Low | Agriculture Blocked | High | 48 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Khaki Safed | Khosk Abeh | {6F49F75A-8BE4-48EC-A171-6A5213F17D88} | c0a8-0057-12c3bb58c70-bc60eaab-3bc9e- | MF-HQ-7867 | MCPA - Mine Clearance Planning Agency | AF/2106/18637/MF0008 | 55118 | 62.1574 | 32.7916 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-274 | Farah Demining Project-08 |  |  |  |  | 1401 |  | {6F49F75A-8BE4-48EC-A171-6A5213F17D88} |  | Low | Agriculture Blocked | High | 15 | CHA | 5 |  |  | 2001-02-05 | No | Open
West | Farah | Khaki Safed | Kurghand | {B6965FCF-5A24-4970-A602-06BCA795D276} | c0a8-0057-12c3b7c5af8-25cbe237-16df1- | MF-HQ-11017 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2106/18633/MF0013 | 352350 | 62.0975 | 32.6732 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-274 | Farah Demining Project-08 |  |  |  |  | 1401 |  | {B6965FCF-5A24-4970-A602-06BCA795D276} |  | Low | Critical Infrastracture | High | 30 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Khaki Safed | Najo | {82BF272D-E9D7-4504-87AA-50CC7D4B64E4} | c0a8-0057-12c3b7c7847-e0565f1d-16f3c- | MF-HQ-11023 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2106/18673/MF0015 | 24000 | 61.9839 | 32.8725 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {82BF272D-E9D7-4504-87AA-50CC7D4B64E4} |  | Low | Agriculture Blocked | High | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Khaki Safed | Najo | {82BF272D-E9D7-4504-87AA-50CC7D4B64E4} | c0a8-0057-12c3baa2504-8f9fa5e7-350ed- | MF-HQ-11024 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2106/18673/MF0014 | 30000 | 61.9835 | 32.8697 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {82BF272D-E9D7-4504-87AA-50CC7D4B64E4} |  | Low | Critical Infrastracture | High | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Khaki Safed | Qarya-i-Gargawa | {9954A092-30E8-4C04-ACB3-0B74299C6C7C} | c0a8-0057-12c3b85b59d-46f5c410-1d835- | MF-HQ-11022 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2106/18644/MF0016 | 120000 | 61.9097 | 32.8242 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-176 | Farah Demining Project-09 (AT) |  |  |  |  | 1400 |  | {9954A092-30E8-4C04-ACB3-0B74299C6C7C} |  | Low | Critical Infrastracture | High | 20 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Khaki Safed | Qarya-i-Mir Hazari | {C1C05FC6-931F-4250-AA93-E640AF5D7BF3} | c0a8-0057-12c3b7f6d29-5183eafa-1907b- | MF-HQ-11078 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2106/18646/MF0017 | 520000 | 61.9348 | 32.8182 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-274 | Farah Demining Project-08 |  |  |  |  | 1401 |  | {C1C05FC6-931F-4250-AA93-E640AF5D7BF3} |  | Low | Agriculture Blocked | High | 439 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Lash Wa Juwayn | Domboli Bala | {AD50E584-2D7F-43F4-80C1-8FF9D846BC7C} | c0a8-0057-12c3b7be676-71895ea5-168b7- | MF-HQ-11025 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2109/19570/MF0012 | 585000 | 61.4543 | 31.5069 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {AD50E584-2D7F-43F4-80C1-8FF9D846BC7C} |  | Medium | Critical Infrastracture | Moderate | 26 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Farah | Lash Wa Juwayn | Paishawaran | {C4971576-BB15-432D-87C3-529A8922B765} | c0a8-0057-12c3b8ec7a0-76baa0a4-23cc6- | MF-HQ-11082 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2109/00605/MF0014 | 100000 | 61.5385 | 31.5284 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-314 | Farah Demining Project-08 (AT) |  |  |  |  | 1399 |  | {C4971576-BB15-432D-87C3-529A8922B765} |  | Medium | Critical Infrastracture | Moderate | 26 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Farah | Lash Wa Juwayn | Paishawaran | {C4971576-BB15-432D-87C3-529A8922B765} | c0a8-0057-12c3ba74e2d-29276-33658-b21 | MF-HQ-11081 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2109/00605/MF0013 | 500000 | 61.537 | 31.5301 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-314 | Farah Demining Project-08 (AT) |  |  |  |  | 1399 |  | {C4971576-BB15-432D-87C3-529A8922B765} |  | Medium | Critical Infrastracture | Moderate | 34 | SHA | 3 |  |  | 2009-06-09 | No | Open
West | Farah | Qala Ka | Chah Karta | {765E6998-C797-4CDE-8E08-44DCA4445337} | c0a8-0057-12c3b8f999b-b3b9a822-24579- | MF-HQ-11038 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2108/00358/MF0035 | 15000 | 61.1837 | 32.3715 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {765E6998-C797-4CDE-8E08-44DCA4445337} |  | High with Victim | High with Victims | Moderate | 0 | SHA | 2 |  |  | 2009-06-17 | No | Open
West | Farah | Qala Ka | Gest | {D7F38B11-80FD-4DB6-A721-0D2F61AC730C} | c0a8-0057-12c3baaa9cb-172f6fe8-3557b- | MF-HQ-11049 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2108/19186/MF0036 | 7000000 | 61.4728 | 32.273 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-290 | Farah Demining Project-03 |  |  |  |  | 1401 |  | {D7F38B11-80FD-4DB6-A721-0D2F61AC730C} |  | Low | Critical Infrastracture | Moderate | 46 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Qala Ka | Janabad | {FBDC14CD-060F-437B-BDBA-3916B01E540F} | c0a8-0057-12c3b7fe5fe-d74c3827-195ef- | MF-HQ-11050 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2108/19175/MF0037 | 15000 | 60.9565 | 32.2276 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {FBDC14CD-060F-437B-BDBA-3916B01E540F} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Qala Ka | Nawbor | {FA76955A-965E-4669-95E0-7DCF772FE47C} | c0a8-0057-12c3ba1863c-7af11941-2fde8- | MF-HQ-11047 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2108/19190/MF0038 | 380000 | 61.6059 | 32.2371 | Open | Mixed | Mixed AT UXO | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {FA76955A-965E-4669-95E0-7DCF772FE47C} |  | Low | Critical Infrastracture | Moderate | 3 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Qala Ka | Nawbor | {FA76955A-965E-4669-95E0-7DCF772FE47C} | c0a8-0057-12c3ba8af3c-d8d4dce9-3432f- | MF-HQ-11048 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2108/19190/MF0039 | 30000 | 61.6494 | 32.2272 | Open | Mixed | Mixed AT UXO | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {FA76955A-965E-4669-95E0-7DCF772FE47C} |  | Low | Other | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Qala Ka | Qarya-i- | {92ABE5A8-B0C9-4B58-94A0-40421831B5B9} | c0a8-0057-12c3b8de4b3-6aea8ee4-232bb- | MF-HQ-11076 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2108/19213/MF0041 | 203280 | 61.2876 | 32.3496 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {92ABE5A8-B0C9-4B58-94A0-40421831B5B9} |  | Low | Critical Infrastracture | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Qala Ka | Qarya-i- | {92ABE5A8-B0C9-4B58-94A0-40421831B5B9} | c0a8-0057-12c3b8edfe0-e8e85d8c-23dbc- | MF-HQ-11077 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2108/19213/MF0040 | 17784 | 61.3582 | 32.3419 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-174 | Farah Demining Project-07 |  |  |  |  | 1396 |  | {92ABE5A8-B0C9-4B58-94A0-40421831B5B9} |  | Medium | Agriculture Blocked | Moderate | 0 | SHA | 3 |  |  | 2009-06-17 | No | Open
West | Farah | Qala Ka | Qarya-i-Anjiran | {6A1BD81B-5D08-4FA2-8FC4-8BC497A1E1AF} | c0a8-0057-12c3b87e05f-78a8bbb0-1f050- | MF-HQ-11092 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2108/19251/MF0042 | 285400 | 61.344 | 32.4819 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {6A1BD81B-5D08-4FA2-8FC4-8BC497A1E1AF} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Qala Ka | Qarya-i-Anjiran | {6A1BD81B-5D08-4FA2-8FC4-8BC497A1E1AF} | c0a8-0057-12c3b9cfeb4-785a5951-2d14b- | MF-HQ-11090 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2108/19251/MF0043 | 57200 | 61.3693 | 32.4313 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {6A1BD81B-5D08-4FA2-8FC4-8BC497A1E1AF} |  | Low | Agriculture Blocked | Moderate | 1 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Qala Ka | Qarya-i-Ur | {C4C076EA-FF47-4D75-B945-BCA21EBEF986} | c0a8-0057-12c3bb24912-6a3c0456-39e2d- | MF-HQ-11072 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2108/19248/MF0044 | 20000 | 61.2607 | 32.5195 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {C4C076EA-FF47-4D75-B945-BCA21EBEF986} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Shib Koh | Jorg | {5C1E3C9E-7DAB-4213-9EF5-01C32BAB2FA4} | c0a8-0057-12c3bae8966-d91f2297-37a63- | MF-HQ-11104 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2010/19177/MF0001 | 12000 | 61.3892 | 32.167 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-314 | Farah Demining Project-08 (AT) |  |  |  |  | 1399 |  | {5C1E3C9E-7DAB-4213-9EF5-01C32BAB2FA4} |  | Low | Critical Infrastracture | Moderate | 2 | SHA | 5 |  |  | 2009-06-03 | No | Open
West | Farah | Shib Koh | Jorg | {5C1E3C9E-7DAB-4213-9EF5-01C32BAB2FA4} | c0a8-0057-12c3bb57b6f-4cbe6cfd-3bc16- | MF-HQ-11105 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2010/19177/MF0002 | 470400 | 61.3786 | 32.178 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-314 | Farah Demining Project-08 (AT) |  |  |  |  | 1399 |  | {5C1E3C9E-7DAB-4213-9EF5-01C32BAB2FA4} |  | Low | Agriculture Blocked | Moderate | 3 | SHA | 5 |  |  | 2009-06-03 | No | Open
West | Farah | Shib Koh | Khash | {64312631-6FB3-4914-B649-AAEE5CBB21B7} | c0a8-0057-12c3b9accb5-9e30dc54-2bb20- | MF-HQ-11015 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2010/19154/MF0004 | 337500 | 61.1709 | 32.0612 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {64312631-6FB3-4914-B649-AAEE5CBB21B7} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Shib Koh | Khash | {64312631-6FB3-4914-B649-AAEE5CBB21B7} | c0a8-0057-12c3bade848-2d81648b-37452- | MF-HQ-11014 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2010/19154/MF0005 | 675000 | 61.1633 | 32.0569 | Open | Mixed | Mixed AP UXO | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {64312631-6FB3-4914-B649-AAEE5CBB21B7} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Shib Koh | Khash | {64312631-6FB3-4914-B649-AAEE5CBB21B7} | c0a8-0057-12c3bb1ff18-602d6e8c-39b77- | MF-HQ-11016 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2010/19154/MF0003 | 750000 | 61.1843 | 32.0688 | Open | Mixed | Mixed AP AT UXO | Converted From SHA |  | MBT Project-219 | Farah Demining Project-02 |  |  |  |  | 1400 |  | {64312631-6FB3-4914-B649-AAEE5CBB21B7} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Shib Koh | Zahak | {F35DC8A3-AA7B-4188-89A6-BA2D669A1413} | c0a8-0057-12c3b865054-6c8e61ff-1debb- | MF-HQ-11064 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2010/00763/MF0007 | 15000 | 61.2444 | 32.1712 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-314 | Farah Demining Project-08 (AT) |  |  |  |  | 1399 |  | {F35DC8A3-AA7B-4188-89A6-BA2D669A1413} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Shib Koh | Zahak | {F35DC8A3-AA7B-4188-89A6-BA2D669A1413} | c0a8-0057-12c3b89776b-3a2a12d-20207-4 | MF-HQ-11065 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2010/00763/MF0008 | 270000 | 61.2922 | 32.2037 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-314 | Farah Demining Project-08 (AT) |  |  |  |  | 1399 |  | {F35DC8A3-AA7B-4188-89A6-BA2D669A1413} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Farah | Shib Koh | Zahak | {F35DC8A3-AA7B-4188-89A6-BA2D669A1413} | c0a8-0057-12c3ba428bb-42881059-31760- | MF-HQ-11063 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2010/00763/MF0006 | 156800 | 61.2736 | 32.1984 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-314 | Farah Demining Project-08 (AT) |  |  |  |  | 1399 |  | {F35DC8A3-AA7B-4188-89A6-BA2D669A1413} |  | Low | Critical Infrastracture | Moderate | 0 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Ghor | Shahrak | Tangi Azaw | {70C06555-0402-4593-80E3-D69BDC561536} | c0a8-008e-1329f1a3853-2dd3b640-112f-7 | BF-15002 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/2702/27026/BF0008 | 297875 | 64.207 | 34.1213 | Open | UXO Only | UXO Only | BF |  | MBT Project-173 | Farah Demining Project-04 |  |  |  |  | 1397 |  | {70C06555-0402-4593-80E3-D69BDC561536} |  | Medium | Critical Infrastracture | High | 198 | CHA | 3 |  |  | 2010-11-01 16:30 | No | Open
West | Hirat | Adraskan | Kharchan | {74D54C44-6065-4077-A35F-269E42A9E16B} | c0a8-00f6-137fdfaf0a6-42bc8dfc-cb-64c | Hz-ID-17042 | HT - HALO TRUST | H/7934 | 45860 | 62.2688 | 33.6316 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes |  |  | 1392-1393 | HT | {74D54C44-6065-4077-A35F-269E42A9E16B} |  |  |  | Substantial | 4 | CHA | 1 |  |  | 2012-05-20 16:30 | Yes | Complete
West | Hirat | Adraskan | Kharchan | {74D54C44-6065-4077-A35F-269E42A9E16B} | c0a8-00f6-137fe05f341-e90dae2f-1df-3a | Hz-ID-17041 | HT - HALO TRUST | H/7933 | 46260 | 62.2688 | 33.6316 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes |  |  | 1392-1393 | HT | {74D54C44-6065-4077-A35F-269E42A9E16B} |  |  |  | Substantial | 4 | CHA | 1 |  |  | 2012-05-02 16:30 | Yes | Complete
West | Hirat | Ghoryan | Rushnu | {5B020B08-8428-4C46-96D3-3444CBA13514} | c0a8-0009-1453ff83039-f70fe28d-ec8-36 | Hz-ID-18599 | HT - HALO TRUST | H/7998 | 21000 | 61.4536 | 34.4228 | Open | AP Only | AP Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {5B020B08-8428-4C46-96D3-3444CBA13514} |  | Medium | Agriculture Blocked | Moderate | 133 | CHA | 3 |  |  | 2014-03-10 16:30 | No | Open
West | Hirat | Ghoryan | Sar Asyab (Poshana), Shikhan | {58E5BCA6-CA39-4027-B8CD-B1593EF529B1} | c0a8-0009-144055db29d-d8ba732c-14dd-7 | Hz-ID-18476 | HT - HALO TRUST | H/7974 | 94200 | 61.4756 | 34.3526 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {58E5BCA6-CA39-4027-B8CD-B1593EF529B1} |  | Low | Critical Infrastracture | Moderate | 148 | CHA | 4 |  |  | 2014-01-09 16:30 | No | Planned
West | Hirat | Ghoryan | Stawnu | {FCCA6CCC-53D1-4492-932E-9BFF13B02CB9} | c0a8-0009-144055a24b2-d70a3058-146c-4 | Hz-ID-18478 | HT - HALO TRUST | H/7975 | 1150 | 61.4749 | 34.3798 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {FCCA6CCC-53D1-4492-932E-9BFF13B02CB9} |  | High | Critical Infrastracture | Moderate | 508 | CHA | 3 |  |  | 2014-01-05 16:30 | No | Planned
West | Hirat | Gulran | Bagh Kuhna | {BB764262-84FA-4A98-A4E7-50E9036458BC} | c0a8-0057-12c3b8a5c2c-2d770fa-20bde-b | MF-WA-618 | HT - HALO TRUST | H/4631 | 1260 | 61.8291 | 35.0118 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {BB764262-84FA-4A98-A4E7-50E9036458BC} |  | Medium | Critical Infrastracture | Substantial | 21 | CHA | 3 |  |  | 2008-08-11 | No | Open
West | Hirat | Gulran | Bagh Kuhna | {BB764262-84FA-4A98-A4E7-50E9036458BC} | c0a8-0057-12c3b8a5e9c-b335c19c-20bf4- | MF-WA-622 | HT - HALO TRUST | H/4632 | 4000 | 61.8325 | 35.0162 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {BB764262-84FA-4A98-A4E7-50E9036458BC} |  | Medium | Critical Infrastracture | Substantial | 15 | CHA | 3 |  |  | 2008-08-12 | No | Open
West | Hirat | Gulran | Bagh Kuhna | {BB764262-84FA-4A98-A4E7-50E9036458BC} | c0a8-0057-12c3b8ae814-c360cbc9-211bb- | MF-WA-561 | HT - HALO TRUST | H/4629 | 30000 | 61.8371 | 34.0108 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {BB764262-84FA-4A98-A4E7-50E9036458BC} |  | Low | Other | Substantial | 7 | CHA | 5 |  |  | 2008-09-11 | No | Open
West | Hirat | Gulran | Bagh Kuhna | {BB764262-84FA-4A98-A4E7-50E9036458BC} | c0a8-0057-12c3b8aeae2-a51ebea3-211e8- | MF-WA-560 | HT - HALO TRUST | H/4630 | 18200 | 61.8554 | 35.0046 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {BB764262-84FA-4A98-A4E7-50E9036458BC} |  | Low | Other | Substantial | 11 | CHA | 5 |  |  | 2008-09-11 | No | Open
West | Hirat | Gulran | Bagh Kuhna | {BB764262-84FA-4A98-A4E7-50E9036458BC} | c0a8-0057-12c3ba99d4f-75ff1e4b-34bd7- | MF-WA-562 | HT - HALO TRUST | H/4628 | 18000 | 61.8331 | 35.0002 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {BB764262-84FA-4A98-A4E7-50E9036458BC} |  | Medium | Critical Infrastracture | Substantial | 400 | CHA | 3 |  |  | 2008-09-11 | No | Open
West | Hirat | Gulran | Bagh Kuhna | {BB764262-84FA-4A98-A4E7-50E9036458BC} | c0a8-0057-12c3ba9a23f-a5a8bac1-34bf7- | MF-WA-481 | HT - HALO TRUST | H/4627 | 7650 | 61.8371 | 34.0108 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {BB764262-84FA-4A98-A4E7-50E9036458BC} |  | Low | Other | Substantial | 7 | CHA | 5 |  |  | 2008-09-11 | No | Open
West | Hirat | Gulran | Burj Dahana-e-Zul Feqar, Chah Makam | {974A9451-C9F5-47FD-B2B3-CC6D10B21648} | c0a8-0057-12c3b7bb3c3-221dab2f-1664c- | MF-WA-805 | HT - HALO TRUST | H/4636 | 87500 | 61.268 | 35.363 | Open | AP Only | AP Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {974A9451-C9F5-47FD-B2B3-CC6D10B21648} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-08-15 | No | Open
West | Hirat | Gulran | Burj Dahana-e-Zul Feqar, Chah Makam | {974A9451-C9F5-47FD-B2B3-CC6D10B21648} | c0a8-0057-12c3b8ede0c-90c9ad28-23da5- | MF-WA-663 | HT - HALO TRUST | H/4635 | 190000 | 61.2574 | 35.3915 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {974A9451-C9F5-47FD-B2B3-CC6D10B21648} |  | Low | Agriculture Blocked | Substantial | 35 | CHA | 5 |  |  | 2008-08-16 | No | Open
West | Hirat | Gulran | Burj Dahana-e-Zul Feqar, Chah Makam | {974A9451-C9F5-47FD-B2B3-CC6D10B21648} | c0a8-0057-12c3b96d11f-cfd7a201-290c6- | MF-WA-668 | HT - HALO TRUST | H/4634 | 533000 | 61.2553 | 35.3876 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {974A9451-C9F5-47FD-B2B3-CC6D10B21648} |  | Low | Agriculture Blocked | Substantial | 68 | CHA | 5 |  |  | 2008-08-14 | No | Open
West | Hirat | Gulran | Burj Dahana-e-Zul Feqar, Chah Makam | {974A9451-C9F5-47FD-B2B3-CC6D10B21648} | c0a8-0057-12c3ba1ece9-554abe80-301f8- | MF-WA-666 | HT - HALO TRUST | H/4633 | 955000 | 61.2364 | 35.406 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {974A9451-C9F5-47FD-B2B3-CC6D10B21648} |  | Low | Agriculture Blocked | Substantial | 14 | CHA | 5 |  |  | 2008-08-13 | No | Open
West | Hirat | Gulran | Cahar Del | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} | c0a8-008e-1328f8c09fa-6ddafcb2-16c5-b | MF-15827 | HT - HALO TRUST | H/6962 | 67520 | 61.2053 | 35.2118 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2011-01-05 16:30 | No | Planned
West | Hirat | Gulran | Cahar Del | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} | c0a8-008e-1328f8c9f83-f22fe6fa-1753-2 | MF-15831 | HT - HALO TRUST | H/6959 | 42450 | 61.1686 | 35.2136 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2011-01-03 16:30 | No | Planned
West | Hirat | Gulran | Cahar Del | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} | c0a8-008e-132c97470c0-1d75a3b0-348c-5 | MF-15828 | HT - HALO TRUST | H/6961 | 46390 | 61.1917 | 35.2125 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2011-01-04 16:30 | No | Planned
West | Hirat | Gulran | Cahar Del | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} | c0a8-008e-132c97490ec-9541a4c-34c1-3e | MF-15832 | HT - HALO TRUST | H/6958 | 40600 | 61.1562 | 35.2183 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2011-01-06 16:30 | No | Planned
West | Hirat | Gulran | Cahar Del | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} | c0a8-008e-132c974e5ce-5aee426a-34e2-1 | MF-15826 | HT - HALO TRUST | H/6963 | 19500 | 61.2076 | 35.2118 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2011-01-03 16:30 | No | Planned
West | Hirat | Gulran | Cahar Del | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} | c0a8-008e-132c97563d1-d74cf63a-351b-f | MF-15830 | HT - HALO TRUST | H/6960 | 19500 | 61.1763 | 35.2096 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {CDCCB3A9-8A44-41F5-89AE-82B3CDFB4FF7} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2011-01-01 16:30 | No | Planned
West | Hirat | Gulran | Chah Galgal Sufla | {6857ECE9-D52E-455B-8FBA-C09A3D53318E} | c0a8-0057-12c3b9904cd-375605c3-2a801- | MF-WA-792 | HT - HALO TRUST | H/3002 | 1100 | 61.3243 | 35.508 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {6857ECE9-D52E-455B-8FBA-C09A3D53318E} |  | Low | Small Hazards | Substantial | 1 | CHA | 5 |  |  | 2006-12-04 | No | Open
West | Hirat | Gulran | Chah Galgal Sufla | {6857ECE9-D52E-455B-8FBA-C09A3D53318E} | c0a8-0057-12c3ba060b6-8364a459-2f2cc- | MF-WA-791 | HT - HALO TRUST | H/3000 | 105200 | 61.406 | 34.4897 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {6857ECE9-D52E-455B-8FBA-C09A3D53318E} |  | Low | Other | Substantial | 142 | CHA | 4 |  |  | 2006-12-04 | No | Open
West | Hirat | Gulran | Chah Galgal Sufla | {6857ECE9-D52E-455B-8FBA-C09A3D53318E} | c0a8-0057-12c3ba06586-910b3717-2f2e0- | MF-WA-884 | HT - HALO TRUST | H/3001 | 40800 | 61.4133 | 35.5123 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {6857ECE9-D52E-455B-8FBA-C09A3D53318E} |  | Low | Infrastructure | Substantial | 4 | CHA | 5 |  |  | 2009-02-10 | No | Open
West | Hirat | Gulran | Chakaw | {B99EDD19-9D39-4BC2-923C-BAC5BE6C0A16} | c0a8-008e-132ebe21309-6e159c71-55-7ef | MF-HT-1200 | HT - HALO TRUST | H/3011 | 3880 | 61.4064 | 35.5479 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {B99EDD19-9D39-4BC2-923C-BAC5BE6C0A16} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2006-12-01 | No | Open
West | Hirat | Gulran | Dahan-I-Shor | {6DE6556D-FF26-4141-98BE-742F06F5F605} | c0a8-0057-12c3b87428c-f1ab0cbc-1e944- | MF-WA-713 | HT - HALO TRUST | H/3006 | 5000 | 61.2885 | 35.5124 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {6DE6556D-FF26-4141-98BE-742F06F5F605} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2009-03-05 | No | Open
West | Hirat | Gulran | Dahan-I-Shor | {6DE6556D-FF26-4141-98BE-742F06F5F605} | c0a8-0057-12c3b8959af-70cf1dae-200cc- | MF-WA-715 | HT - HALO TRUST | H/3008 | 25930 | 61.2811 | 35.5151 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {6DE6556D-FF26-4141-98BE-742F06F5F605} |  | Low | Agriculture Blocked | Substantial | 12 | CHA | 5 |  |  | 2006-12-06 | No | Open
West | Hirat | Gulran | Dahan-I-Shor | {6DE6556D-FF26-4141-98BE-742F06F5F605} | c0a8-0057-12c3b960ac9-e5ad5e3f-288e8- | MF-WA-717 | HT - HALO TRUST | H/3003 | 75000 | 61.2937 | 35.5223 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {6DE6556D-FF26-4141-98BE-742F06F5F605} |  | Low | Agriculture Blocked | Substantial | 23 | CHA | 5 |  |  | 2009-03-02 | No | Open
West | Hirat | Gulran | Dahan-I-Shor | {6DE6556D-FF26-4141-98BE-742F06F5F605} | c0a8-0057-12c3b960e04-3b6d7c56-2890e- | MF-WA-716 | HT - HALO TRUST | H/3005 | 40900 | 61.2986 | 35.5197 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {6DE6556D-FF26-4141-98BE-742F06F5F605} |  | Low | Agriculture Blocked | Substantial | 9 | CHA | 5 |  |  | 2009-03-04 | No | Open
West | Hirat | Gulran | Dahan-I-Shor | {6DE6556D-FF26-4141-98BE-742F06F5F605} | c0a8-0057-12c3b961100-91512042-2892e- | MF-WA-718 | HT - HALO TRUST | H/3004 | 265000 | 61.293 | 35.5229 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {6DE6556D-FF26-4141-98BE-742F06F5F605} |  | Low | Agriculture Blocked | Substantial | 23 | CHA | 5 |  |  | 2009-03-03 | No | Open
West | Hirat | Gulran | Dahan-I-Shor | {6DE6556D-FF26-4141-98BE-742F06F5F605} | c0a8-0057-12c3b99995c-4d232ce9-2ae31- | MF-WA-711 | HT - HALO TRUST | H/3007 | 31200 | 61.2883 | 35.5126 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {6DE6556D-FF26-4141-98BE-742F06F5F605} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2006-12-06 | No | Open
West | Hirat | Gulran | Dahan-I-Shor | {6DE6556D-FF26-4141-98BE-742F06F5F605} | c0a8-0057-12c3b999ce4-7731a86b-2ae4a- | MF-WA-720 | HT - HALO TRUST | H/3010 | 3492 | 61.2843 | 35.5144 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {6DE6556D-FF26-4141-98BE-742F06F5F605} |  | Low | Small Hazards | Substantial | 15 | CHA | 5 |  |  | 2006-12-05 | No | Open
West | Hirat | Gulran | Dahan-I-Shor | {6DE6556D-FF26-4141-98BE-742F06F5F605} | c0a8-0057-12c3bb53ab9-ba97ffe-3b9ee-8 | MF-WA-708 | HT - HALO TRUST | H/3009 | 5500 | 61.3075 | 35.5094 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {6DE6556D-FF26-4141-98BE-742F06F5F605} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2006-12-06 | No | Open
West | Hirat | Gulran | Kal Muchak | {CD03CDB4-1AF4-4996-800C-D95F405F2370} | c0a8-0057-12c3b69eaa8-1b809d98-922a-9 | MF-HQ-9903 | HT - HALO TRUST | H/5639 | 2000 | 61.3808 | 35.1771 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {CD03CDB4-1AF4-4996-800C-D95F405F2370} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2009-03-12 | No | Open
West | Hirat | Gulran | Kal Muchak | {CD03CDB4-1AF4-4996-800C-D95F405F2370} | c0a8-0057-12c3b6a2fa3-6e625a0b-9558-e | MF-HQ-9911 | HT - HALO TRUST | H/5640 | 2900 | 61.3908 | 35.1763 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {CD03CDB4-1AF4-4996-800C-D95F405F2370} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2009-03-13 | No | Open
West | Hirat | Gulran | Kal Muchak | {CD03CDB4-1AF4-4996-800C-D95F405F2370} | c0a8-0057-12c3b6f4c1b-6a98d050-d383-e | MF-HQ-9904 | HT - HALO TRUST | H/5641 | 2000 | 61.3994 | 35.1694 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {CD03CDB4-1AF4-4996-800C-D95F405F2370} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-03-14 | No | Open
West | Hirat | Gulran | Kalta Kay (1) | {E0C4AF33-C380-4390-88CD-E14A1A89D22F} | c0a8-0057-12c3b6b33c5-b8f81ae6-a18d-d | BF-HQ-11632 | HT - HALO TRUST | B/2658 | 100 | 61.5289 | 35.083 | Open | UXO Only | UXO Only | BF |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {E0C4AF33-C380-4390-88CD-E14A1A89D22F} |  | Medium | Comunity Centers | Substantial | 601 | CHA | 3 |  |  | 2009-06-12 | No | Open
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-0009-144f8d8f8ad-7ba88cac-3b5-63 | Hz-ID-18555 | HT - HALO TRUST | H/7972 | 51000 | 61.1607 | 35.1095 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID |  | 2014-05-16 | 2014-06-23 | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2013-09-10 16:30 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-0057-12c3b717d14-d121acae-ee24-b | MF-HQ-13583 | HT - HALO TRUST | H/5753 | 25800 | 61.2346 | 35.1137 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2014-01-01 | 2014-03-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2009-10-19 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-0057-12c3b753bb7-17a3d33c-11b1e- | MF-HQ-13582 | HT - HALO TRUST | H/5752 | 43500 | 61.2312 | 35.1124 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2014-01-01 | 2014-03-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2009-10-18 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-0057-12c3b7df3b9-809286ad-18042- | MF-WA-585 | HT - HALO TRUST | H/4571 | 91200 | 61.1604 | 35.1061 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-06-01 | 2013-07-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | Planned Year and Planned Agency Removed |  |  | Substantial | 0 | CHA | 5 |  |  | 2008-09-11 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-0057-12c3b8d3506-7536acdc-22b51- | MF-WA-916 | HT - HALO TRUST | H/5629 | 98000 | 61.2396 | 35.1082 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2014-01-01 | 2014-03-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 1 | CHA | 5 |  |  | 2009-02-11 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-0057-12c3b9f43b7-72c1e429-2e7ba- | MF-WA-582 | HT - HALO TRUST | H/4572 | 24066 | 61.1527 | 35.0682 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-04-01 |  | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2008-09-11 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-0057-12c3b9f4ab9-45db4148-2e7f5- | MF-WA-577 | HT - HALO TRUST | H/4565 | 49100 | 61.1535 | 35.0722 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-04-01 | 2014-06-23 | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | Palnned Year and Planned year removed |  |  | Substantial | 0 | CHA | 5 |  |  | 2008-09-11 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-0057-12c3ba292d6-eb72fa8e-307ec- | MF-WA-662 | HT - HALO TRUST | H/4599 | 70000 | 61.3438 | 35.0866 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  | Low | Agriculture Blocked | Substantial | 6 | CHA | 5 |  |  | 2008-06-06 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-132384c9f2a-a35ef84c-1413-d | MF-WA-568 | HT - HALO TRUST | H/4561 | 36000 | 61.1569 | 35.0714 | Closed | AP Only | AP Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-11-01 | 2014-03-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2008-09-11 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1323859e9ad-2c56c479-1453-2 | MF-WA-578 | HT - HALO TRUST | H/4566 | 44887 | 61.1542 | 35.0739 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-04-01 | 2014-07-23 | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | Planned Agency Removed | Low | Critical Infrastracture | Substantial | 0 | CHA | 5 |  |  | 2008-09-11 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f890515-c02b28b8-153f-7 | MF-15808 | HT - HALO TRUST | H/6975 | 141000 | 61.1336 | 35.1492 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-10-16 | 2014-05-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2011-01-08 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f894436-b7f4a262-156a-4 | MF-15809 | HT - HALO TRUST | H/6946 | 93500 | 61.1636 | 35.1368 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-10-16 | 2013-12-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2010-12-27 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8971e9-1aa7c82e-1580-5 | MF-15810 | HT - HALO TRUST | H/6947 | 75300 | 61.1675 | 35.1428 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-12-12 | 2014-01-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2010-12-27 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f89d6a3-f9c78e70-159e-9 | MF-15818 | HT - HALO TRUST | H/6965 | 110400 | 61.1611 | 35.1122 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-06-16 | 2013-09-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2011-01-06 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8a8112-1a879715-15c8-9 | MF-15820 | HT - HALO TRUST | H/6952 | 94000 | 61.1364 | 35.1694 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-09-01 |  | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2010-12-30 16:30 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8ab155-d5988098-15e1-7 | MF-15821 | HT - HALO TRUST | H/6950 | 101200 | 61.1509 | 35.1637 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2010-12-29 16:30 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8b0684-48ae9449-160e-7 | MF-15822 | HT - HALO TRUST | H/6949 | 35350 | 61.1625 | 35.1618 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-06-16 | 2014-07-23 | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2010-12-28 16:30 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8b4d72-64a847b3-1632-5 | MF-15823 | HT - HALO TRUST | H/6948 | 32000 | 61.1742 | 35.1579 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-06-16 | 2014-07-23 | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2010-12-28 16:30 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8b80a1-e26e4e05-165b-4 | MF-15825 | HT - HALO TRUST | H/6964 | 96000 | 61.1606 | 35.1091 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-06-01 | 2013-10-05 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2011-01-07 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8d5834-d61d1def-17ed-c | MF-15835 | HT - HALO TRUST | H/6954 | 124800 | 61.1302 | 35.18 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2011-01-01 16:30 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8d859a-1e31227b-1805-b | MF-15836 | HT - HALO TRUST | H/6953 | 111750 | 61.1327 | 35.1745 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2010-12-30 16:30 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8dadc2-2546e58d-181d-d | MF-15837 | HT - HALO TRUST | H/6967 | 104880 | 61.1615 | 35.1198 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-08-01 | 2013-11-10 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2011-01-07 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8ddefe-b2d6b763-1831-d | MF-15838 | HT - HALO TRUST | H/6966 | 104880 | 61.1622 | 35.1164 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-06-01 | 2013-08-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2011-01-07 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8e1ecb-9ba238b-1843-93 | MF-15839 | HT - HALO TRUST | H/6968 | 90400 | 61.1606 | 35.1235 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-08-01 | 2013-10-12 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 1 | CHA | 5 |  |  | 2011-01-08 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8eb6d3-52565da6-18b7-9 | MF-15842 | HT - HALO TRUST | H/6970 | 73500 | 61.1575 | 35.128 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-07-01 | 2013-07-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 1 | CHA | 5 |  |  | 2011-01-08 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8eeb79-630ff156-18ce-4 | MF-15845 | HT - HALO TRUST | H/6973 | 119000 | 61.1463 | 35.1422 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-09-01 | 2014-01-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2011-01-09 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8f1a16-272be87d-18e7-7 | MF-15844 | HT - HALO TRUST | H/6974 | 128800 | 61.1395 | 35.1471 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-10-06 | 2014-04-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2011-01-09 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8f46ef-117ff64b-18fd-5 | MF-15846 | HT - HALO TRUST | H/6972 | 100000 | 61.1521 | 35.1359 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-09-01 | 2013-10-15 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2011-01-10 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-1328f8f6e0e-9ba90085-1913-b | MF-15847 | HT - HALO TRUST | H/6971 | 91600 | 61.1575 | 35.128 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-08-01 | 2013-10-05 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 1 | CHA | 5 |  |  | 2011-01-09 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-13290b8efd7-df71f0dc-589-d9 | MF-15843 | HT - HALO TRUST | H/6969 | 50300 | 61.1575 | 35.128 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-09-01 |  | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 1 | CHA | 5 |  |  | 2011-01-09 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-008e-132c975ae76-69392a09-355a-b | MF-15834 | HT - HALO TRUST | H/6955 | 99500 | 61.1733 | 35.1496 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-12-12 | 2014-01-23 | 1392-1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2010-12-31 16:30 | No | Complete
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-00f6-1355193986a-ad6d1027-2fd-ff | MF-16677 | HT - HALO TRUST | H/6951 | 93000 | 61.1402 | 35.1662 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2010-12-29 16:30 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-00f6-13923642541-169b52b-32e6-4c | Hz-ID-17169 | HT - HALO TRUST | H/7946 | 36340 | 61.1516 | 35.0673 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-04-01 | 2014-06-23 | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2012-06-25 16:30 | No | Planned
West | Hirat | Gulran | Kamana | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} | c0a8-00f6-13a3aa8eb51-8351a4e5-fa16-2 | Hz-ID-17170 | HT - HALO TRUST | H/7945 | 36480 | 61.1516 | 35.0673 | Closed | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-04-01 | 2014-06-23 | 1393 | HT | {8CF53991-36E1-48B2-B6DF-67E5B52DE6B9} |  |  |  | Substantial | 0 | CHA | 5 |  |  | 2012-06-25 16:30 | No | Planned
West | Hirat | Gulran | Kandak Kakari | {F0BF7267-FBC0-448C-9D22-57F0B71FC48D} | c0a8-008e-1328f88c5a6-3f12f1a4-151f-7 | MF-15807 | HT - HALO TRUST | H/6957 | 38500 | 61.1291 | 35.2216 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {F0BF7267-FBC0-448C-9D22-57F0B71FC48D} |  | Low | Other | Substantial | 2 | CHA | 5 |  |  | 2011-01-02 16:30 | No | Planned
West | Hirat | Gulran | Kandak Kakari | {F0BF7267-FBC0-448C-9D22-57F0B71FC48D} | c0a8-008e-1328f8cf39a-feae19be-1798-8 | MF-15833 | HT - HALO TRUST | H/6956 | 35570 | 61.1189 | 35.2172 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {F0BF7267-FBC0-448C-9D22-57F0B71FC48D} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2011-01-02 16:30 | No | Planned
West | Hirat | Gulran | Kareyz-e- Elyas | {8FF699FA-1684-47CF-B3F4-68E9A652F8A9} | c0a8-0057-12c3b9e45ec-67222ffd-2ddf1- | MF-WA-807 | HT - HALO TRUST | H/3023 | 3700 | 61.3749 | 35.4305 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {8FF699FA-1684-47CF-B3F4-68E9A652F8A9} |  | Medium | Critical Infrastracture | Substantial | 17 | CHA | 3 |  |  | 2006-12-11 | No | Open
West | Hirat | Gulran | Nayeq | {645E55CA-DA31-4152-9D16-133B35D2A5F5} | c0a8-0057-12c3b92857a-d5bc4a00-2638a- | MF-WA-616 | HT - HALO TRUST | H/4639 | 9600 | 61.305 | 35.3769 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {645E55CA-DA31-4152-9D16-133B35D2A5F5} |  | Low | Critical Infrastracture | Substantial | 252 | CHA | 4 |  |  | 2008-08-19 | No | Open
West | Hirat | Gulran | Qala I Jay (Shile Safid) | {8D45BB92-7696-4F18-9B87-B197EB498A1F} | c0a8-008e-132ebe1ebbc-1d291d57-41-777 | MF-WA-639 | HT - HALO TRUST | H/4638 | 240 | 61.2936 | 35.4562 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {8D45BB92-7696-4F18-9B87-B197EB498A1F} |  | Low | Small Hazards | Substantial | 2 | CHA | 5 |  |  | 2008-08-18 | No | Open
West | Hirat | Gulran | Qara Bagh | {DB3F429A-4111-4E06-BFEA-E0EF51220705} | c0a8-0057-12c3bb28797-d14933d6-3a03b- | MF-HQ-7204 | MCPA - Mine Clearance Planning Agency | AF/2007/17842/MF0016 | 142758 | 61.7019 | 34.8691 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {DB3F429A-4111-4E06-BFEA-E0EF51220705} |  | Low | Agriculture Blocked | Substantial | 35 | CHA | 5 |  |  | 2000-05-02 | No | Open
West | Hirat | Gulran | Qashuri Bala | {67AD0EBF-0AF7-4D16-9922-1A1ACD38A3F6} | c0a8-0057-12c3ba2d043-1f21543b-30a66- | MF-WA-544 | HT - HALO TRUST | H/4626 | 8800 | 61.9895 | 34.8657 | Open | AT Only | AT Only | MineField |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {67AD0EBF-0AF7-4D16-9922-1A1ACD38A3F6} |  | Low | Agriculture Blocked | Substantial | 34 | CHA | 5 |  |  | 2008-09-11 | No | Open
West | Hirat | Gulran | Shorawak (1) | {7917CD84-8DB7-449A-81E7-F220C32C96B0} | c0a8-008e-1328a5d4b53-985383e5-74b-50 | BF-15006 | HT - HALO TRUST | B/2641 | 25 | 61.3882 | 35.3096 | Open | UXO Only | UXO Only | BF |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {7917CD84-8DB7-449A-81E7-F220C32C96B0} |  | Medium | Comunity Centers | Substantial | 110 | CHA | 3 |  |  | 2009-03-11 16:30 | No | Open
West | Hirat | Gulran | Sim Koh | {BA43D5BA-85ED-4A7F-BA75-63F66F336E31} | c0a8-0057-12c3b6e7696-34a57c5-c95c-b0 | BF-HQ-15289 | HT - HALO TRUST | B/2642 | 25 | 61.3932 | 35.2125 | Open | UXO Only | UXO Only | BF |  | MBT Project-175 | Hirat Demining Project-09 (AT) |  |  |  |  | 1398 |  | {BA43D5BA-85ED-4A7F-BA75-63F66F336E31} |  | Medium | Agriculture Blocked | Substantial | 142 | CHA | 3 |  |  | 2009-03-15 | No | Open
West | Hirat | Guzara | Neshin | {0F2BE0A0-95B4-4B5B-ADE6-945682FAD97F} | c0a8-0057-12c3b83ccca-1b3bbaa2-1c21b- | MF-WA-499 | HT - HALO TRUST | H/4545 | 870 | 62.3668 | 34.2358 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {0F2BE0A0-95B4-4B5B-ADE6-945682FAD97F} |  | High | Critical Infrastracture | High | 389 | CHA | 3 |  |  | 2008-09-11 | No | Planned
West | Hirat | Guzara | Neshin | {0F2BE0A0-95B4-4B5B-ADE6-945682FAD97F} | c0a8-0057-12c3bab0d0e-f6ddf45b-358d4- | MF-WA-498 | HT - HALO TRUST | H/4600 | 500 | 62.3689 | 34.2336 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {0F2BE0A0-95B4-4B5B-ADE6-945682FAD97F} |  | Medium | Comunity Centers | High | 195 | CHA | 3 |  |  | 2008-09-11 | No | Planned
West | Hirat | Guzara | Shah Beyad | {920820CF-DFB8-4B98-B2F2-83AE034E44D2} | c0a8-0057-12c3b803851-192139c1-1997d- | MF-WA-542 | HT - HALO TRUST | H/4642 | 36150 | 62.2345 | 33.8901 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {920820CF-DFB8-4B98-B2F2-83AE034E44D2} | Planned Year and Agency Removed | Low | Agriculture Blocked | High | 9 | CHA | 5 |  |  | 2008-09-11 | No | Planned
West | Hirat | Guzara | Shah Beyad | {920820CF-DFB8-4B98-B2F2-83AE034E44D2} | c0a8-008e-1313cf2b37a-1cb1c7b4-c8f-78 | MF-WA-643 | HT - HALO TRUST | H/4643 | 11250 | 62.2583 | 33.9355 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {920820CF-DFB8-4B98-B2F2-83AE034E44D2} |  | Low | Agriculture Blocked | High | 0 | CHA | 5 |  |  | 2008-08-08 | No | Planned
West | Hirat | Hirat | Hawzi Karbas | {CE85DBD9-437E-4D62-89A4-0A434FD9610B} | c0a8-0009-140527e5dbf-df12605d-7407-2 | Hz-ID-18093 | HT - HALO TRUST | H/7971 | 9076 | 62.157 | 34.3508 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes |  |  | 1392-1393 | HT | {CE85DBD9-437E-4D62-89A4-0A434FD9610B} |  |  |  | Substantial | 722 | CHA | 1 |  |  | 2013-07-11 16:30 | No | Complete
West | Hirat | Hirat | Jibaril | {DDB260C1-AF2D-4346-81F5-A17966869849} | c0a8-00f6-137fe012d07-ddba9acf-188-b8 | Hz-ID-17059 | HT - HALO TRUST | H/7929 | 6500 | 62.147 | 34.3747 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-04-15 | 2013-06-05 | 1392 | HT | {DDB260C1-AF2D-4346-81F5-A17966869849} |  |  |  | Substantial | 3126 | CHA | 2 |  |  | 2012-04-10 16:30 | No | Complete
West | Hirat | Hirat | Jibaril | {DDB260C1-AF2D-4346-81F5-A17966869849} | c0a8-00f6-137fe199bca-736222ee-262-24 | Hz-ID-17057 | HT - HALO TRUST | H/7927 | 5500 | 62.147 | 34.3747 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-01-13 | 2013-06-22 | 1392 | HT | {DDB260C1-AF2D-4346-81F5-A17966869849} |  |  |  | Substantial | 3126 | CHA | 2 |  |  | 2012-04-09 16:30 | No | Complete
West | Hirat | Hirat | Jibaril | {DDB260C1-AF2D-4346-81F5-A17966869849} | c0a8-00f6-137fe2476d7-9e3c0336-2a7-d1 | Hz-ID-17061 | HT - HALO TRUST | H/7931 | 9500 | 62.148 | 34.3738 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-05-02 | 2013-06-21 | 1392 | HT | {DDB260C1-AF2D-4346-81F5-A17966869849} |  |  |  | Substantial | 0 | CHA | 2 |  |  | 2012-04-11 16:30 | No | Complete
West | Hirat | Hirat | Jibaril | {DDB260C1-AF2D-4346-81F5-A17966869849} | c0a8-00f6-13803a2bd33-7ae71980-afc-ad | Hz-ID-17054 | HT - HALO TRUST | H/7924 | 5650 | 62.1451 | 34.3765 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-04-11 | 2013-06-22 | 1392 | HT | {DDB260C1-AF2D-4346-81F5-A17966869849} |  |  |  | Substantial | 3349 | CHA | 2 |  |  | 2012-04-08 16:30 | No | Complete
West | Hirat | Hirat | Jibaril | {DDB260C1-AF2D-4346-81F5-A17966869849} | c0a8-00f6-13803ac41aa-dc412f88-b20-5e | Hz-ID-17055 | HT - HALO TRUST | H/7925 | 2945 | 62.148 | 34.3738 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-06-01 | 2013-06-22 | 1392 | HT | {DDB260C1-AF2D-4346-81F5-A17966869849} |  |  |  | Substantial | 223 | CHA | 2 |  |  | 2012-04-09 16:30 | No | Complete
West | Hirat | Hirat | Jibaril | {DDB260C1-AF2D-4346-81F5-A17966869849} | c0a8-00f6-138081586d9-7ece6feb-e3b-98 | Hz-ID-17056 | HT - HALO TRUST | H/7926 | 6340 | 62.147 | 34.3747 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-04-11 | 2013-06-22 | 1392 | HT | {DDB260C1-AF2D-4346-81F5-A17966869849} |  |  |  | Substantial | 3349 | CHA | 2 |  |  | 2012-04-09 16:30 | No | Complete
West | Hirat | Hirat | Jibaril | {DDB260C1-AF2D-4346-81F5-A17966869849} | c0a8-00f6-138082243fa-9fd88efa-e58-6f | Hz-ID-17058 | HT - HALO TRUST | H/7928 | 7000 | 62.147 | 34.3747 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-04-09 | 2013-05-15 | 1392 | HT | {DDB260C1-AF2D-4346-81F5-A17966869849} |  |  |  | Substantial | 3349 | CHA | 2 |  |  | 2012-04-10 16:30 | No | Complete
West | Hirat | Hirat | Jibaril | {DDB260C1-AF2D-4346-81F5-A17966869849} | c0a8-00f6-1380824a3f4-6a368c51-e6b-73 | Hz-ID-17060 | HT - HALO TRUST | H/7930 | 11500 | 62.148 | 34.3738 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-04-12 | 2013-06-09 | 1392 | HT | {DDB260C1-AF2D-4346-81F5-A17966869849} |  |  |  | Substantial | 223 | CHA | 2 |  |  | 2012-04-11 16:30 | No | Complete
West | Hirat | Hirat | Jibaril | {DDB260C1-AF2D-4346-81F5-A17966869849} | c0a8-00f6-139cd7e81d6-a565c414-2445-7 | Hz-ID-17053 | HT - HALO TRUST | H/7923 | 4400 | 62.1451 | 34.3765 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-04-17 | 2013-06-22 | 1392 | HT | {DDB260C1-AF2D-4346-81F5-A17966869849} |  |  |  | Substantial | 3126 | CHA | 2 |  |  | 2012-04-08 16:30 | No | Complete
West | Hirat | Hirat | Mahala-I-Baba Jee | {D88339A0-11F9-447D-94B2-26BB38E6D66E} | c0a8-0009-142b24d1aa5-cd44b512-1da-bc | Hz-ID-18248 | HT - HALO TRUST | H/7973 | 713 | 62.1828 | 34.3626 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-12-18 | 2014-01-23 | 1392-1393 | HT | {D88339A0-11F9-447D-94B2-26BB38E6D66E} |  |  |  | Substantial | 4122 | CHA | 2 |  |  | 2013-11-12 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-008e-1328f8fa736-2b2dcf11-1929-8 | MF-15848 | HT - HALO TRUST | H/6976 | 83600 | 61.2016 | 34.6665 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-106 | Hirat Demining Project-05 (AT) | DOS | Yes | 2013-01-03 | 2013-03-23 | 1392 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 50 |  | 1 | Yes | Kohsan district teacher’s town | 2011-03-30 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-008e-1329094e3fb-8cebf3a2-1c7-ec | MF-16185 | HT - HALO TRUST | H/6989 | 83600 | 61.2016 | 34.6665 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-11-15 |  | 1392-1393 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 64 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-13 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-008e-13479d3fe83-630c516b-b4e-e6 | MF-16177 | HT - HALO TRUST | H/6985 | 83600 | 61.2016 | 34.6665 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-106 | Hirat Demining Project-05 (AT) | DOS | Yes | 2013-06-01 |  | 1392 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 50 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-09 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-008e-13479d458ef-ae70024f-b61-41 | MF-16180 | HT - HALO TRUST | H/6986 | 83600 | 61.2016 | 34.6665 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-09-01 | 2013-09-23 | 1392-1393 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 38 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-10 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-008e-13479d5b095-36f676c7-b7b-d6 | MF-16189 | HT - HALO TRUST | H/6987 | 83600 | 61.2046 | 34.6737 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-09-01 | 2013-10-05 | 1392-1393 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 38 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-11 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-008e-13479d7165e-bfb566e7-b94-a2 | MF-16188 | HT - HALO TRUST | H/6988 | 83600 | 61.2055 | 34.6758 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-10-06 | 2013-11-14 | 1392-1393 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 19 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-12 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-008e-13479d96e00-2d02979b-ba7-94 | MF-16186 | HT - HALO TRUST | H/6990 | 83600 | 61.1993 | 34.6684 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-106 | Hirat Demining Project-05 (AT) | DOS | Yes | 2013-04-01 | 2013-05-22 | 1392 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 81 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-14 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-008e-13479daf86c-1ba11a85-bb9-70 | MF-16183 | HT - HALO TRUST | H/6998 | 83600 | 61.197 | 34.6702 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes |  |  | 1392-1393 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 31 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-04 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-008e-13479dccf70-cc48b7-bcd-72c1 | MF-16192 | HT - HALO TRUST | H/6999 | 83600 | 61.1992 | 34.6795 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-12-15 | 2014-01-12 | 1392-1393 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 59 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-05 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-008e-13479ef15db-dfd80586-be0-14 | MF-16191 | HT - HALO TRUST | H/7000 | 83600 | 61.2001 | 34.6816 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2014-01-01 | 2014-01-23 | 1392-1393 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 28 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-06 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-008e-13479f2a0f7-f099f943-bf2-ee | MF-16190 | HT - HALO TRUST | H/7901 | 83600 | 61.201 | 34.6837 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2014-02-01 |  | 1392-1393 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 73 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-07 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-00f6-1349e10a186-4c03671e-4fc-e6 | MF-16456 | HT - HALO TRUST | H/6997 | 83600 | 61.199 | 34.6685 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-106 | Hirat Demining Project-05 (AT) | DOS | Yes | 2013-06-16 |  | 1392 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 31 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-20 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-00f6-134a2076a9f-1fd2d6ea-bef-5a | MF-16455 | HT - HALO TRUST | H/6996 | 83600 | 61.199 | 34.6685 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-106 | Hirat Demining Project-05 (AT) | DOS | Yes | 2013-04-01 | 2013-05-22 | 1392 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 62 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-19 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-00f6-134a238deb7-d574cb54-13c9-8 | MF-16452 | HT - HALO TRUST | H/6993 | 83600 | 61.199 | 34.6685 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-09-12 | 2013-11-15 | 1392-1393 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 50 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-17 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-00f6-134a240b98c-7a64b1b2-14ea-a | MF-16454 | HT - HALO TRUST | H/6995 | 83600 | 61.199 | 34.6685 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes |  |  | 1392-1393 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 64 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-18 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-00f6-134a24215ba-5aa0e98c-14fc-5 | MF-16453 | HT - HALO TRUST | H/6994 | 86300 | 61.199 | 34.6685 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-11-16 | 2013-12-23 | 1392-1393 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 19 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-18 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-00f6-134a280858b-230c87dc-1662-c | MF-16451 | HT - HALO TRUST | H/6992 | 83600 | 61.199 | 34.6685 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-106 | Hirat Demining Project-05 (AT) | DOS | Yes | 2013-07-01 | 2013-08-23 | 1392 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 50 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-16 16:30 | No | Complete
West | Hirat | Kohsan | Chah Kaftari | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} | c0a8-00f6-134a282709d-b9127821-1675-f | MF-16450 | HT - HALO TRUST | H/6991 | 83600 | 61.199 | 34.6685 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-106 | Hirat Demining Project-05 (AT) | DOS | Yes | 2013-06-01 |  | 1392 | HT | {C14B522D-7D98-4D9F-8067-D32A3F9D6B74} |  |  |  | Moderate | 81 | CHA | 1 | Yes | Kohsan district teacher’s town | 2011-06-15 16:30 | No | Complete
West | Hirat | Kohsan | Gurg Abad | {EF4E5735-6FFC-46A2-95F3-7EFD3896A5DC} | c0a8-0057-12c3b86396b-acce0de6-1ddb6- | MF-WA-700 | HT - HALO TRUST | H/4590 | 7020 | 60.8707 | 34.5355 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {EF4E5735-6FFC-46A2-95F3-7EFD3896A5DC} |  | Low | Agriculture Blocked | Moderate | 12 | CHA | 5 |  |  | 2008-05-17 | No | Planned
West | Hirat | Kohsan | Gurg Abad | {EF4E5735-6FFC-46A2-95F3-7EFD3896A5DC} | c0a8-0057-12c3b8cde5f-7ad28591-227be- | MF-WA-378 | HT - HALO TRUST | H/4412 | 41600 | 60.8421 | 34.5144 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {EF4E5735-6FFC-46A2-95F3-7EFD3896A5DC} |  | Low | Agriculture Blocked | Moderate | 12 | CHA | 5 |  |  | 2008-08-02 | No | Planned
West | Hirat | Kohsan | Kalar | {09ED6859-8CE9-4F2F-A167-9141BE203EFF} | c0a8-0009-144f8deb0fc-fa74b418-3ce-8d | Hz-ID-18556 | HT - HALO TRUST | H/7977 | 72000 | 61.2933 | 34.6237 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {09ED6859-8CE9-4F2F-A167-9141BE203EFF} |  | Low | Agriculture Blocked | Moderate | 12 | CHA | 5 |  |  | 2014-02-21 16:30 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0009-144fce6c249-9dcf2f27-425-86 | Hz-ID-18554 | HT - HALO TRUST | H/7976 | 79400 | 61.228 | 34.6506 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-05-16 | 2014-06-23 | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 12 | CHA | 5 |  |  | 2014-02-21 16:30 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0009-1465c4e4aff-f1d19ab0-4b2f-5 | Hz-ID-18752 | HT - HALO TRUST | H/8000 | 79400 | 61.228 | 34.6506 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 12 | CHA | 5 |  |  | 2014-04-03 16:30 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0009-1465c52c281-f30b473b-4b45-3 | Hz-ID-18753 | HT - HALO TRUST | H/8651 | 74100 | 61.228 | 34.6506 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 6 | CHA | 5 |  |  | 2014-04-01 16:30 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0009-1465c53865c-c1b8dd58-4b5e-5 | Hz-ID-18754 | HT - HALO TRUST | H/8652 | 68900 | 61.228 | 34.6506 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 6 | CHA | 5 |  |  | 2014-04-02 16:30 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b9027b3-92eef321-24b84- | MF-HQ-13561 | HT - HALO TRUST | H/5737 | 72200 | 61.2438 | 34.6424 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-06-19 | 2014-09-23 | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  | Low | Agriculture Blocked | Moderate | 22 | CHA | 5 |  |  | 2009-10-09 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b902968-75507219-24b96- | MF-HQ-13197 | HT - HALO TRUST | H/5719 | 102000 | 61.2318 | 34.6454 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-08-01 | 2013-08-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 42 | CHA | 5 |  |  | 2009-09-10 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b902eb5-ec143a4e-24bcc- | MF-HQ-13201 | HT - HALO TRUST | H/5723 | 83200 | 61.2397 | 34.6496 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2014-03-01 |  | 1392-1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-09-14 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b903440-41632e08-24c03- | MF-HQ-13566 | HT - HALO TRUST | H/5740 | 123200 | 61.2502 | 34.6413 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} | , | Low | Agriculture Blocked | Moderate | 22 | CHA | 5 |  |  | 2009-10-12 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b903df0-ee579e06-24c6a- | MF-HQ-13188 | HT - HALO TRUST | H/5712 | 96000 | 61.2323 | 34.6525 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139/A | Hirat Demining Project-10 (AT)/A | B-Germany | Yes | 2013-10-01 | 2013-11-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} | , |  |  | Moderate | 23 | CHA | 5 |  |  | 2009-09-03 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b90434d-a771f769-24ca1- | MF-HQ-13194 | HT - HALO TRUST | H/5716 | 99000 | 61.2342 | 34.6502 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139/A | Hirat Demining Project-10 (AT)/A | B-Germany | Yes | 2013-12-01 | 2013-12-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} | HALO Trust stated that, The 4 tasks(H/5711, H/5712, H/5716, H/5742)from the RFP list in Kohsan the community refused the clearance of these tasks , as these tasks were not a priority for them, instead 4 new hazards(H/5754, H/5755, H/5756, H/4595)in the s |  |  | Moderate | 22 | CHA | 5 |  |  | 2009-09-07 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b904714-32e3eb95-24ccb- | MF-HQ-13176 | HT - HALO TRUST | H/5721 | 92800 | 61.2358 | 34.6476 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2014-01-01 | 2014-03-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-09-12 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b9048e8-19034e25-24cdd- | MF-HQ-13574 | HT - HALO TRUST | H/5745 | 73600 | 61.2614 | 34.638 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} | , | Low | Agriculture Blocked | Moderate | 11 | CHA | 5 |  |  | 2009-10-07 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b904e63-4892c1b8-24d13- | MF-HQ-12423 | HT - HALO TRUST | H/5707 | 91200 | 61.2327 | 34.6566 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139/A | Hirat Demining Project-10 (AT)/A | B-Germany | Yes | 2013-10-01 | 2013-11-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 23 | CHA | 5 |  |  | 2009-08-16 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b905037-675c8fae-24d25- | MF-HQ-13210 | HT - HALO TRUST | H/5722 | 89600 | 61.2377 | 34.6486 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2014-02-13 | 2014-03-23 | 1392-1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-09-13 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b90521b-c321d830-24d37- | MF-HQ-13562 | HT - HALO TRUST | H/5738 | 123750 | 61.2459 | 34.644 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  | Low | Agriculture Blocked | Moderate | 11 | CHA | 5 |  |  | 2009-10-10 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b9053ef-5a9f39a0-24d49- | MF-HQ-13192 | HT - HALO TRUST | H/5715 | 102300 | 61.2313 | 34.6487 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-09-01 | 2013-09-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 42 | CHA | 5 |  |  | 2009-09-06 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b9055e2-cdcefc34-24d5b- | MF-HQ-13560 | HT - HALO TRUST | H/5736 | 106500 | 61.2433 | 34.648 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-04-01 | 2014-05-20 | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2009-10-07 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b905a45-494141c9-24d7f- | MF-HQ-13189 | HT - HALO TRUST | H/5713 | 94400 | 61.2353 | 34.6539 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139/A | Hirat Demining Project-10 (AT)/A | B-Germany | Yes | 2013-10-01 | 2013-11-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-09-04 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b905e79-fb7ff4cd-24da9- | MF-HQ-13564 | HT - HALO TRUST | H/5739 | 111000 | 61.2478 | 34.6455 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-07-01 | 2014-09-23 | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  | Low | Agriculture Blocked | Moderate | 11 | CHA | 5 |  |  | 2009-10-11 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b90604d-399e9337-24dbb- | MF-HQ-13208 | HT - HALO TRUST | H/5711 | 97600 | 61.2293 | 34.651 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-07-01 | 2013-07-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} | HALO Trust stated that, 4 tasks(H/5711, H/5712, H/5716, H/5742)from the RFP list in Kohsan the community refused the clearance of these tasks , as these tasks were not a priority for them, instead 4 new hazards(H/5754, H/5755, H/5756, H/4595)in the same |  |  | Moderate | 43 | CHA | 5 |  |  | 2009-09-02 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b906221-3676b1d7-24dcd- | MF-HQ-13199 | HT - HALO TRUST | H/5720 | 96000 | 61.2339 | 34.6465 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-08-01 | 2014-02-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-09-11 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b906645-fe1739ee-24df8- | MF-HQ-13572 | HT - HALO TRUST | H/5744 | 68800 | 61.2597 | 34.6367 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} | , | Low | Agriculture Blocked | Moderate | 11 | CHA | 5 |  |  | 2009-10-01 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b906e50-6db2b2d6-24e45- | MF-HQ-12372 | HT - HALO TRUST | H/5705 | 97600 | 61.227 | 34.6534 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-06-01 | 2013-07-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 12 | CHA | 5 |  |  | 2009-08-14 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b907a31-539032bc-24eb6- | MF-HQ-13570 | HT - HALO TRUST | H/5743 | 106000 | 61.2569 | 34.6406 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} | , | Low | Agriculture Blocked | Moderate | 22 | CHA | 5 |  |  | 2009-10-03 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b90802a-55eb81ca-24eec- | MF-HQ-12422 | HT - HALO TRUST | H/5706 | 99000 | 61.2299 | 34.6551 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-09-07 | 2014-03-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} | , |  |  | Moderate | 23 | CHA | 5 |  |  | 2009-08-15 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b90823c-59c8e4ea-24efe- | MF-HQ-12369 | HT - HALO TRUST | H/5704 | 92800 | 61.2244 | 34.6509 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-137 | Hirat Demining Project-06 (AT) | VTF-Canada | Yes | 2013-01-03 | 2013-04-10 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 12 | CHA | 4 |  |  | 2009-08-13 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b908a18-dabb00d5-24f47- | MF-HQ-13577 | HT - HALO TRUST | H/5747 | 78750 | 61.2645 | 34.6363 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} | , | Low | Agriculture Blocked | Moderate | 22 | CHA | 5 |  |  | 2009-10-11 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b908c3a-25cf7d1e-24f59- | MF-HQ-13569 | HT - HALO TRUST | H/5742 | 102000 | 61.255 | 34.6392 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} | , | High Requested | Resettlment/Local Request | Moderate | 22 | CHA | 5 |  |  | 2009-10-05 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b908e2d-69ba8374-24f6c- | MF-HQ-13556 | HT - HALO TRUST | H/5733 | 93800 | 61.2374 | 34.6437 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-04-01 | 2014-05-15 | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-10-03 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b909426-b8d8d7d6-24fa2- | MF-HQ-13558 | HT - HALO TRUST | H/5735 | 112000 | 61.2415 | 34.6467 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-04-01 | 2014-05-19 | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-10-06 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b909657-e074c442-24fb4- | MF-HQ-13567 | HT - HALO TRUST | H/5741 | 110000 | 61.2523 | 34.6429 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} | , | Low | Agriculture Blocked | Moderate | 22 | CHA | 5 |  |  | 2009-10-20 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b909aba-7811818b-24fda- | MF-HQ-13196 | HT - HALO TRUST | H/5717 | 102300 | 61.2369 | 34.6517 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139/A | Hirat Demining Project-10 (AT)/A | B-Germany | Yes | 2013-12-03 | 2013-12-23 | 1392 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 22 | CHA | 5 |  |  | 2009-09-08 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b909ccc-8b4d8ace-24fec- | MF-HQ-13557 | HT - HALO TRUST | H/5734 | 97000 | 61.2394 | 34.6452 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-04-01 | 2014-05-16 | 1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-10-04 | No | Planned
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b9b207e-2d0e4869-2be77- | MF-HQ-13707 | HT - HALO TRUST | H/5764 | 118500 | 61.212 | 34.6727 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-05-01 | 2013-06-22 | 1392-1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-11-22 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b9b24b3-4b9fa382-2be9b- | MF-HQ-13945 | HT - HALO TRUST | H/5771 | 94200 | 61.2161 | 34.6715 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-05-01 | 2013-05-22 | 1392-1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-12-07 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b9b341d-f781dafc-2bf21- | MF-HQ-13947 | HT - HALO TRUST | H/5773 | 108000 | 61.2193 | 34.6701 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-05-01 | 2013-06-22 | 1392-1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-12-13 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b9b362f-d2ee331e-2bf33- | MF-HQ-13704 | HT - HALO TRUST | H/5760 | 93260 | 61.2032 | 34.6667 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-05-01 | 2013-06-22 | 1392-1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 11 | CHA | 5 |  |  | 2009-11-19 | No | Complete
West | Hirat | Kohsan | Kohistan | {763CC4EF-D304-41B3-8895-50916944A3C0} | c0a8-0057-12c3b9b3c67-4d0cb81f-2bf69- | MF-HQ-13948 | HT - HALO TRUST | H/5774 | 93000 | 61.2227 | 34.668 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-05-13 | 2013-07-23 | 1392-1393 | HT | {763CC4EF-D304-41B3-8895-50916944A3C0} |  |  |  | Moderate | 27 | CHA | 5 |  |  | 2009-12-06 | No | Complete
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-1453fc8d2e8-66839357-d2d-50 | Hz-ID-18596 | HT - HALO TRUST | H/7996 | 195200 | 61.0506 | 34.7415 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-20 16:30 | No | Open
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-1453fd36d5c-ecff54d3-df6-10 | Hz-ID-18593 | HT - HALO TRUST | H/7995 | 188000 | 61.0506 | 34.7415 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-19 16:30 | No | Open
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-1453fde8def-c1b4ea55-e31-8f | Hz-ID-18598 | HT - HALO TRUST | H/7997 | 170320 | 61.0506 | 34.7415 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-20 16:30 | No | Open
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-1453ff0c981-333f8627-e78-d3 | Hz-ID-18591 | HT - HALO TRUST | H/7993 | 183000 | 61.0499 | 34.7484 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-19 16:30 | No | Open
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-1454006af99-a4368107-f18-50 | Hz-ID-18590 | HT - HALO TRUST | H/7992 | 199000 | 61.0499 | 34.7484 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-138 | Hirat Demining Project-08 (AT) | NVESD | Yes | 2014-06-04 | 2014-09-23 | 1393 | HT | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-19 16:30 | No | Planned
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-145400daf2b-27ee5d68-f39-1e | Hz-ID-18589 | HT - HALO TRUST | H/7991 | 191200 | 61.0504 | 34.7518 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2014-03-19 16:30 | No | Open
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-145400fe2e7-fdbbe89b-f56-89 | Hz-ID-18588 | HT - HALO TRUST | H/7990 | 203000 | 61.0504 | 34.7518 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-20 16:30 | No | Open
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-14540165db6-d8836b96-f6f-87 | Hz-ID-18587 | HT - HALO TRUST | H/7989 | 196000 | 61.0504 | 34.7518 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-20 16:30 | No | Open
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-14540d68604-b7e7793a-181f-6 | Hz-ID-18586 | HT - HALO TRUST | H/7988 | 183300 | 61.0504 | 34.7518 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-20 16:30 | No | Open
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-14540e7a93c-79ee69bc-1aac-2 | Hz-ID-18585 | HT - HALO TRUST | H/7987 | 187000 | 61.0512 | 34.7582 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-20 16:30 | No | Open
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-1454106a1d7-6e17f539-1c15-a | Hz-ID-18584 | HT - HALO TRUST | H/7986 | 189300 | 61.0515 | 34.7674 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-20 16:30 | No | Open
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-145410d3e8a-c02e0ca7-1c31-7 | Hz-ID-18583 | HT - HALO TRUST | H/7985 | 191000 | 61.0512 | 34.7582 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2014-03-19 16:30 | No | Open
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-14544d70be0-7584cfcd-11-ea3 | Hz-ID-18582 | HT - HALO TRUST | H/7984 | 210000 | 61.0512 | 34.7582 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-138 | Hirat Demining Project-08 (AT) | NVESD | Yes |  |  | 1393 | HT | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-19 16:30 | No | Planned
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-14544e613f8-6e93441b-86-228 | Hz-ID-18581 | HT - HALO TRUST | H/7983 | 189300 | 61.0515 | 34.7674 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-138 | Hirat Demining Project-08 (AT) | NVESD | Yes |  |  | 1393 | HT | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-19 16:30 | No | Planned
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-145451173eb-50d0a770-194-4c | Hz-ID-18580 | HT - HALO TRUST | H/7982 | 188000 | 61.0515 | 34.7674 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-138 | Hirat Demining Project-08 (AT) | NVESD | Yes |  |  | 1393 | HT | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-19 16:30 | No | Planned
West | Hirat | Kohsan | Kolata Purbouz-Naib Ghafoor (Prozha) | {227A0CAC-6DC4-4575-A657-7281A2FC1917} | c0a8-0009-145da1188f5-8a7bacf7-274-19 | Hz-ID-18592 | HT - HALO TRUST | H/7994 | 189200 | 61.0506 | 34.7415 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {227A0CAC-6DC4-4575-A657-7281A2FC1917} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-03-19 16:30 | No | Open
West | Hirat | Kohsan | Naw Abad-I-Ghazal Islam | {A286B65C-17FC-43D8-8004-30C59A399AE2} | c0a8-0057-12c3b6b8128-f1d2f8fd-a548-d | MF-HQ-14213 | HT - HALO TRUST | H/5785 | 96 | 61.1495 | 34.8044 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {A286B65C-17FC-43D8-8004-30C59A399AE2} |  | Low | Agriculture Blocked | Moderate | 22 | CHA | 5 |  |  | 2010-02-12 | No | Planned
West | Hirat | Kohsan | Qalat-i-Arbab A'zam | {80CB8181-B7DE-4726-A77C-F9F46754BD92} | c0a8-0009-14540233f92-9ef0972d-1087-9 | Hz-ID-18557 | HT - HALO TRUST | H/7981 | 192500 | 61.0506 | 34.7415 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {80CB8181-B7DE-4726-A77C-F9F46754BD92} |  | Low | Agriculture Blocked | Moderate | 0 | CHA | 5 |  |  | 2014-02-20 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Arbab A'zam | {80CB8181-B7DE-4726-A77C-F9F46754BD92} | c0a8-0009-14563978449-f428bf3b-157b-1 | Hz-ID-18558 | HT - HALO TRUST | H/7978 | 95100 | 61.053 | 34.6896 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {80CB8181-B7DE-4726-A77C-F9F46754BD92} |  | Low | Agriculture Blocked | Moderate | 36 | SHA | 5 |  |  | 2014-02-18 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Arbab A'zam | {80CB8181-B7DE-4726-A77C-F9F46754BD92} | c0a8-0009-1467a63c130-c70e44b4-1925-b | Hz-ID-18770 | HT - HALO TRUST | H/8653 | 85700 | 61.053 | 34.6896 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {80CB8181-B7DE-4726-A77C-F9F46754BD92} |  | Low | Agriculture Blocked | Moderate | 1 | SHA | 5 |  |  | 2014-05-02 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Arbab A'zam | {80CB8181-B7DE-4726-A77C-F9F46754BD92} | c0a8-0009-1467acc7798-f1598544-1a1b-9 | Hz-ID-18772 | HT - HALO TRUST | H/8654 | 85700 | 61.053 | 34.6896 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {80CB8181-B7DE-4726-A77C-F9F46754BD92} |  | Low | Agriculture Blocked | Moderate | 1 | SHA | 5 |  |  | 2014-05-01 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Arbab A'zam | {80CB8181-B7DE-4726-A77C-F9F46754BD92} | c0a8-0009-1467ad09c55-4ed49ce2-1a32-4 | Hz-ID-18773 | HT - HALO TRUST | H/8655 | 85700 | 61.053 | 34.6896 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {80CB8181-B7DE-4726-A77C-F9F46754BD92} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-05-02 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Arbab A'zam | {80CB8181-B7DE-4726-A77C-F9F46754BD92} | c0a8-0009-1467ad2c90f-ba0eaaf6-1a4a-c | Hz-ID-18775 | HT - HALO TRUST | H/8656 | 86300 | 61.053 | 34.6896 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {80CB8181-B7DE-4726-A77C-F9F46754BD92} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-05-01 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-144fceb6cc4-35f77aac-457-7b | Hz-ID-18560 | HT - HALO TRUST | H/7980 | 104000 | 61.0607 | 34.7029 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 80 | SHA | 5 |  |  | 2014-02-18 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1456397a7ef-4b8c6646-15c6-a | Hz-ID-18559 | HT - HALO TRUST | H/7979 | 2548000 | 61.0579 | 34.7032 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 116 | SHA | 4 |  |  | 2014-02-19 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467ad561b4-f976bc3d-1a61-d | Hz-ID-18777 | HT - HALO TRUST | H/8657 | 97400 | 61.0607 | 34.7029 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-05-03 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467ad8740a-325f9d6e-1a7c-7 | Hz-ID-18783 | HT - HALO TRUST | H/8658 | 97400 | 61.0607 | 34.7029 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 7 | SHA | 5 |  |  | 2014-05-04 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467ae0d2ba-e81830da-1a95-4 | Hz-ID-18784 | HT - HALO TRUST | H/8659 | 97400 | 61.0607 | 34.7029 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 7 | SHA | 5 |  |  | 2014-05-05 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467ae75f1e-4a4ce2a3-1ab1-7 | Hz-ID-18785 | HT - HALO TRUST | H/8660 | 97400 | 61.0607 | 34.7029 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 17 | SHA | 5 |  |  | 2014-05-06 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467b0aff15-f895d3fa-1aca-c | Hz-ID-18786 | HT - HALO TRUST | H/8661 | 97400 | 61.0607 | 34.7029 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 17 | SHA | 5 |  |  | 2014-05-03 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467b0de09c-6b8d8720-1ae3-4 | Hz-ID-18787 | HT - HALO TRUST | H/8662 | 97400 | 61.0578 | 34.7198 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 21 | SHA | 5 |  |  | 2014-05-04 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467b1dc124-2e2ee331-1b00-e | Hz-ID-18790 | HT - HALO TRUST | H/8663 | 97400 | 61.0578 | 34.7198 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 14 | SHA | 5 |  |  | 2014-05-05 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467b25632a-91c9f129-1b19-a | Hz-ID-18792 | HT - HALO TRUST | H/8664 | 97400 | 61.0578 | 34.7198 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 14 | SHA | 5 |  |  | 2014-05-06 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467b2822fe-779adb6b-1b57-1 | Hz-ID-18797 | HT - HALO TRUST | H/8665 | 97400 | 61.0578 | 34.7198 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 23 | SHA | 5 |  |  | 2014-05-03 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467b38466e-a27f178a-1bb8-5 | Hz-ID-18800 | HT - HALO TRUST | H/8666 | 97400 | 61.0578 | 34.7198 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 16 | SHA | 5 |  |  | 2014-05-04 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467f092008-abcc479a-1c59-6 | Hz-ID-18802 | HT - HALO TRUST | H/8667 | 97400 | 61.0556 | 34.7294 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 16 | SHA | 5 |  |  | 2014-05-05 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467f11f28f-c4c527-1c71-1f5 | Hz-ID-18804 | HT - HALO TRUST | H/8668 | 97400 | 61.0556 | 34.7294 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 16 | SHA | 5 |  |  | 2014-05-06 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0009-1467f1393ad-54bc853e-1c89-4 | Hz-ID-18807 | HT - HALO TRUST | H/8669 | 97400 | 61.0556 | 34.7294 | Open | AT Only | AT Only | MineField |  | MBT Project-104 | Hirat Demining Project-02 |  |  |  |  | 1395 |  | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 0 | SHA | 5 |  |  | 2014-05-07 16:30 | No | Open
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7e244a-262215ff-18288- | MF-HQ-12006 | HT - HALO TRUST | H/5657 | 112000 | 61.0523 | 34.7467 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-107 | Hirat Demining Project-07 (AT) | NVESD | Yes | 2013-06-15 |  | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} | Planned Year and Agency Removed |  |  | Moderate | 0 | CHA | 5 |  |  | 2009-05-05 | No | Planned
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7e2d10-5f8df22e-182ee- | MF-WA-726 | HT - HALO TRUST | H/5521 | 105000 | 61.0579 | 34.7293 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-04-01 |  | 1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2008-10-18 | No | Planned
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7e3e3f-40d4feeb-183ac- | MF-WA-780 | HT - HALO TRUST | H/5510 | 105000 | 61.0629 | 34.7235 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-07-05 | 2013-08-22 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 12 | CHA | 5 |  |  | 2008-10-23 | No | Complete
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7e4448-dce28312-183ea- | MF-WA-728 | HT - HALO TRUST | H/5519 | 105000 | 61.0649 | 34.7294 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-04-10 | 2013-05-22 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2008-10-17 | No | Complete
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7e47d1-859f1abc-1840e- | MF-WA-738 | HT - HALO TRUST | H/5512 | 105000 | 61.0587 | 34.7264 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139/A | Hirat Demining Project-10 (AT)/A | B-Germany | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2008-10-11 | No | Complete
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7e5789-9d5a05c7-184b0- | MF-WA-745 | HT - HALO TRUST | H/5502 | 105000 | 61.0601 | 34.7205 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-06-20 | 2013-10-23 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 24 | CHA | 5 |  |  | 2008-10-07 | No | Complete
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7e7fa2-e898d4ef-18651- | MF-WA-766 | HT - HALO TRUST | H/5533 | 105000 | 61.0591 | 34.7381 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 25 | CHA | 5 |  |  | 2008-10-11 | No | Planned
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7e8a4c-949cb22-186c0-6 | MF-WA-724 | HT - HALO TRUST | H/5522 | 105000 | 61.0572 | 34.7322 | Closed | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-04-01 |  | 1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 25 | CHA | 5 |  |  | 2008-10-19 | No | Planned
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7e8f4b-2757e0a3-186fa- | MF-WA-736 | HT - HALO TRUST | H/5514 | 105000 | 61.0657 | 34.7265 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-04-01 | 2013-05-22 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2008-10-13 | No | Complete
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7e9f13-b014a4ce-18793- | MF-WA-737 | HT - HALO TRUST | H/5513 | 105000 | 61.0622 | 34.7264 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-107 | Hirat Demining Project-07 (AT) | NVESD | Yes | 2013-10-01 | 2014-01-23 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2008-10-13 | No | Planned
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7ea5e6-87ede0de-187d4- | MF-WA-756 | HT - HALO TRUST | H/5539 | 107000 | 61.055 | 34.7433 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-107 | Hirat Demining Project-07 (AT) | NVESD | Yes | 2013-09-15 | 2014-01-23 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} | Planned Year and Agency Removed |  |  | Moderate | 25 | CHA | 5 |  |  | 2008-10-21 | No | Planned
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7eac0e-6f452148-18812- | MF-WA-771 | HT - HALO TRUST | H/5531 | 105000 | 61.0564 | 34.7351 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-06-01 | 2014-09-23 | 1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 25 | CHA | 5 |  |  | 2008-10-09 | No | Planned
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7eb245-8b76f074-1884e- | MF-WA-727 | HT - HALO TRUST | H/5520 | 105000 | 61.0614 | 34.7293 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-107 | Hirat Demining Project-07 (AT) | NVESD | Yes | 2013-12-08 | 2014-03-23 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2008-10-17 | No | Planned
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7eb448-214bf00b-18860- | MF-WA-723 | HT - HALO TRUST | H/5523 | 105000 | 61.0606 | 34.7322 | Closed | AT Only | AT Only | MineField | 1392/1393 | MBT Project-107 | Hirat Demining Project-07 (AT) | NVESD | Yes | 2014-01-01 | 2014-06-23 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 25 | CHA | 5 |  |  | 2008-10-20 | No | Planned
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7eb85d-db0e95cb-1888a- | MF-WA-779 | HT - HALO TRUST | H/5511 | 105000 | 61.0594 | 34.7235 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139/A | Hirat Demining Project-10 (AT)/A | B-Germany | Yes | 2013-10-01 | 2013-12-23 | 1392 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 24 | CHA | 5 |  |  | 2008-10-23 | No | Complete
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7ebef2-8777c031-188c6- | MF-WA-773 | HT - HALO TRUST | H/5530 | 105000 | 61.0599 | 34.7351 | Worked on | AT Only | AT Only | MineField | 1392/1393 | MBT Project-107 | Hirat Demining Project-07 (AT) | NVESD | Yes | 2014-02-01 | 2014-09-23 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 25 | CHA | 5 |  |  | 2008-10-19 | No | Planned
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7ec307-56c644cc-188ea- | MF-WA-769 | HT - HALO TRUST | H/5532 | 105000 | 61.0556 | 34.738 | Worked on | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-06-01 | 2014-09-23 | 1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  | Low | Agriculture Blocked | Moderate | 25 | CHA | 5 |  |  | 2008-10-10 | No | Planned
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7ec519-deb64dd0-188fc- | MF-WA-743 | HT - HALO TRUST | H/5503 | 105000 | 61.0636 | 34.7206 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-04-12 | 2013-07-23 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 12 | CHA | 5 |  |  | 2008-10-08 | No | Complete
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7ec72c-cd059070-1890e- | MF-WA-669 | HT - HALO TRUST | H/4695 | 102000 | 61.0609 | 34.7177 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-04-14 | 2013-07-23 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 24 | CHA | 5 |  |  | 2008-09-19 | No | Complete
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-0057-12c3b7ecbae-a84cf3b3-1893b- | MF-WA-758 | HT - HALO TRUST | H/5524 | 105000 | 61.0641 | 34.7323 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-04-08 | 2013-06-22 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2008-10-20 | No | Complete
West | Hirat | Kohsan | Qalat-i-Ghazi | {1756D530-52FB-4528-A296-4A93C26B4DB7} | c0a8-008e-1306d836e82-ee749101-697-c4 | MF-HQ-12005 | HT - HALO TRUST | H/5656 | 112000 | 61.0553 | 34.7469 | Closed | AT Only | AT Only | MineField | 1392 | MBT Project-107 | Hirat Demining Project-07 (AT) | NVESD | Yes | 2013-06-19 | 2014-01-14 | 1392-1393 | HT | {1756D530-52FB-4528-A296-4A93C26B4DB7} |  |  |  | Moderate | 0 | CHA | 5 |  |  | 2009-05-23 | No | Planned
West | Hirat | Koshk | Do Ab (2) | {B8320218-2142-403C-A1CF-87BB753161D8} | c0a8-0009-13f09b23d76-a6dd5285-2032-1 | Hz-ID-17926 | HT - HALO TRUST | H/7967 | 48510 | 62.1917 | 34.829 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {B8320218-2142-403C-A1CF-87BB753161D8} |  | Low | Critical Infrastracture | High | 7 | CHA | 5 |  |  | 2013-04-10 16:30 | No | Planned
West | Hirat | Koshk | Karez-i-Khuni | {6FE8F475-A8D8-40CD-8CBF-DEA178E7FFE3} | c0a8-0009-13f2cc5bf2d-e2c44ae-5793-98 | Hz-ID-17961 | HT - HALO TRUST | H/7970 | 11445 | 62.211 | 34.8315 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {6FE8F475-A8D8-40CD-8CBF-DEA178E7FFE3} |  | Low | Agriculture Blocked | High | 10 | CHA | 5 |  |  | 2013-05-19 16:30 | No | Planned
West | Hirat | Koshk | Murtadza | {E0131280-76DF-4923-8911-70AE70701757} | c0a8-0009-13f2ccbdd80-beb66d4c-57e1-1 | Hz-ID-17960 | HT - HALO TRUST | H/7969 | 3660 | 62.2308 | 34.9624 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {E0131280-76DF-4923-8911-70AE70701757} |  | Low | Agriculture Blocked | High | 21 | CHA | 5 |  |  | 2013-05-15 16:30 | No | Planned
West | Hirat | Koshk | Murtadza | {E0131280-76DF-4923-8911-70AE70701757} | c0a8-0009-13f2cd01e73-fa5b2351-5831-c | Hz-ID-17958 | HT - HALO TRUST | H/7968 | 7680 | 62.2207 | 34.9575 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {E0131280-76DF-4923-8911-70AE70701757} |  | Low | Agriculture Blocked | High | 46 | CHA | 5 |  |  | 2013-05-14 16:30 | No | Planned
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-0009-1467a3ea22b-32de45be-166b-3 | Hz-ID-18767 | HT - HALO TRUST | H/8672 | 66200 | 62.8602 | 34.271 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  | Low | Agriculture Blocked | Substantial | 35 | CHA | 5 |  |  | 2014-05-08 16:30 | No | Planned
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-0009-1467a599d8e-14e0f5f7-18e6-d | Hz-ID-18768 | HT - HALO TRUST | H/8671 | 41140 | 62.8602 | 34.271 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  | Low | Agriculture Blocked | Substantial | 35 | CHA | 5 |  |  | 2014-05-08 16:30 | No | Planned
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-0009-1467a5bd159-4e152724-18fe-9 | Hz-ID-18769 | HT - HALO TRUST | H/8670 | 40400 | 62.8602 | 34.271 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  | Low | Agriculture Blocked | Substantial | 35 | CHA | 5 |  |  | 2014-05-08 16:30 | No | Planned
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-00f6-139afd8070b-7854e2dc-20e2-5 | Hz-ID-17257 | HT - HALO TRUST | H/7948 | 80000 | 62.8602 | 34.271 | Closed | AT Only | AT Only | MineField | 1392/1393 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes |  |  | 1392-1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  |  |  | Substantial | 48 | CHA | 5 |  |  | 2012-08-12 16:30 | No | Complete
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-00f6-139afdbe2c6-d97bc7d3-2156-f | Hz-ID-17258 | HT - HALO TRUST | H/7949 | 80000 | 62.8602 | 34.271 | Closed | AT Only | AT Only | MineField | 1392/1393 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes |  |  | 1392-1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  |  |  | Substantial | 42 | CHA | 5 |  |  | 2012-08-13 16:30 | No | Complete
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-00f6-139afe7b286-8b3d3d3b-2185-8 | Hz-ID-17259 | HT - HALO TRUST | H/7950 | 80000 | 62.8602 | 34.271 | Closed | AT Only | AT Only | MineField | 1392/1393 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes |  |  | 1392-1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  |  |  | Substantial | 42 | CHA | 5 |  |  | 2012-08-14 16:30 | No | Complete
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-00f6-139afea5f87-6859e153-2206-8 | Hz-ID-17260 | HT - HALO TRUST | H/7951 | 81550 | 62.8338 | 34.2655 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-08-01 | 2014-08-23 | 1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  | Low | Agriculture Blocked | Substantial | 49 | CHA | 4 |  |  | 2012-08-12 16:30 | No | Planned
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-00f6-139afed502e-a87d68ee-221d-6 | Hz-ID-17261 | HT - HALO TRUST | H/7953 | 81900 | 62.8338 | 34.2655 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-08-01 | 2014-08-23 | 1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  | Low | Agriculture Blocked | Substantial | 17 | CHA | 4 |  |  | 2012-08-15 16:30 | No | Planned
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-00f6-139b3a06590-d039f7fb-2400-c | Hz-ID-17262 | HT - HALO TRUST | H/7954 | 81550 | 62.8338 | 34.2655 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-08-01 |  | 1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  | Low | Agriculture Blocked | Substantial | 49 | CHA | 5 |  |  | 2012-08-14 16:30 | No | Planned
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-00f6-139b3a3c3e0-94db74cd-24e4-3 | Hz-ID-17263 | HT - HALO TRUST | H/7955 | 81550 | 62.8338 | 34.2655 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-08-01 | 2014-08-23 | 1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  | Low | Critical Infrastracture | Substantial | 1150 | CHA | 4 |  |  | 2012-08-16 16:30 | No | Planned
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-00f6-139b3a5cb5d-2982596e-258f-3 | Hz-ID-17264 | HT - HALO TRUST | H/7956 | 81900 | 62.8338 | 34.2655 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-08-01 | 2014-08-23 | 1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  | Low | Agriculture Blocked | Substantial | 17 | CHA | 5 |  |  | 2012-08-16 16:30 | No | Planned
West | Hirat | Pashtun Zarghun | Burya Baf-i-Sufla | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} | c0a8-00f6-139b3a77f10-222322c4-25a6-8 | Hz-ID-17265 | HT - HALO TRUST | H/7952 | 81550 | 62.8338 | 34.2655 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-08-01 | 2014-08-23 | 1393 | HT | {243CE0DC-EE14-4675-9D56-7FB39D30CB37} |  | Low | Agriculture Blocked | Substantial | 17 | CHA | 4 |  |  | 2012-08-13 16:30 | No | Planned
West | Hirat | Pashtun Zarghun | Khwaja Mohammad Usta | {38802497-0082-4ABA-BC7A-019935F27D9B} | c0a8-00f6-139afd409ad-56900932-1f9b-5 | Hz-ID-17256 | HT - HALO TRUST | H/7947 | 220 | 62.8212 | 34.3081 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-08-01 | 2014-08-23 | 1393 | HT | {38802497-0082-4ABA-BC7A-019935F27D9B} |  | Medium | Critical Infrastracture | Substantial | 234 | CHA | 3 |  |  | 2012-08-11 16:30 | No | Planned
West | Hirat | Shindand | Ali Abad | {D70EDB0B-6170-4FA3-8FF7-70F6D6785EA6} | c0a8-0057-12c3b8ce052-250f1c5e-227d3- | MF-HQ-11046 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1014/00666/MF0124 | 148500 | 62.1086 | 33.1786 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-172 | Hirat Demining Project-03 |  |  |  |  | 1400 |  | {D70EDB0B-6170-4FA3-8FF7-70F6D6785EA6} |  | Low | Agriculture Blocked | High | 3 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Hirat | Shindand | Dulurge Samali | {1B17C243-242A-4B58-8E99-2D6F56AB02EA} | c0a8-0057-12c3b954b75-dfe24286-280c3- | MF-HQ-11125 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2014/18768/MF0125 | 1720320 | 62.2507 | 33.274 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-220 | Hirat Demining Project-04 |  |  |  |  | 1398 |  | {1B17C243-242A-4B58-8E99-2D6F56AB02EA} |  | Low | Critical Infrastracture | High | 1221 | SHA | 4 |  |  | 2009-07-05 | No | Open
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df37ebe96-77367109-10d5-c | Hz-ID-17790 | HT - HALO TRUST | B/3013 | 500000 | 62.2915 | 33.4153 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-04-08 | 2013-05-06 | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 49 | CHA | 1 |  |  | 2013-03-13 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df37f30b9-cb37ff11-111a-3 | Hz-ID-17792 | HT - HALO TRUST | B/3014 | 500000 | 62.2903 | 33.4197 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-06-10 | 2013-09-23 | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-03-14 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df37fe354-3d6d0252-1159-9 | Hz-ID-17795 | HT - HALO TRUST | B/3015 | 500000 | 62.2894 | 33.4228 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-06-17 | 2013-08-23 | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 110 | CHA | 1 |  |  | 2013-03-15 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df38052aa-aa222e5b-1172-2 | Hz-ID-17797 | HT - HALO TRUST | B/3016 | 500000 | 62.2885 | 33.4263 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-08-01 | 2013-08-23 | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 61 | CHA | 1 |  |  | 2013-03-16 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df380d6e6-9dac79a4-11a4-4 | Hz-ID-17802 | HT - HALO TRUST | B/3018 | 500000 | 62.2869 | 33.4325 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes |  |  | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 287 | CHA | 1 |  |  | 2013-03-18 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df3818a6b-96e9d0cd-11be-5 | Hz-ID-17805 | HT - HALO TRUST | B/3020 | 500000 | 62.2852 | 33.439 | Worked on | UXO Only | UXO Only | BF | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-07-04 | 2014-08-05 | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 81 | CHA | 1 |  |  | 2013-03-20 16:30 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df381e73a-a5752064-11f2-8 | Hz-ID-17808 | HT - HALO TRUST | B/3021 | 500000 | 62.2843 | 33.4422 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-08-06 | 2014-09-02 | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 42 | CHA | 1 |  |  | 2013-03-20 16:30 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df3827fe0-73750400-1224-f | Hz-ID-17811 | HT - HALO TRUST | B/3023 | 500000 | 62.2826 | 33.4487 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 48 | CHA | 1 |  |  | 2013-03-13 16:30 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df382d530-a2461d69-1249-5 | Hz-ID-17813 | HT - HALO TRUST | B/3024 | 407000 | 62.3053 | 33.4181 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-10-01 | 2013-11-08 | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 42 | CHA | 1 |  |  | 2013-03-14 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df3834b97-376588aa-1263-e | Hz-ID-17815 | HT - HALO TRUST | B/3025 | 524500 | 62.3043 | 33.4242 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-11-09 | 2013-12-23 | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 39 | CHA | 1 |  |  | 2013-03-15 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df38399e5-788c18f8-127c-1 | Hz-ID-17818 | HT - HALO TRUST | B/3027 | 366000 | 62.3009 | 33.4371 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-12-18 | 2014-01-10 | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 222 | CHA | 1 |  |  | 2013-03-17 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df383bcfe-942ef5a8-1295-7 | Hz-ID-17816 | HT - HALO TRUST | B/3026 | 644000 | 62.3026 | 33.4207 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes |  |  | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 235 | CHA | 1 |  |  | 2013-03-16 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df3883d43-1790906c-1363-a | Hz-ID-17812 | HT - HALO TRUST | B/3031 | 492000 | 62.2974 | 33.4501 | Closed | UXO Only | UXO Only | BF | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 0 | CHA | 1 |  |  | 2013-03-20 16:30 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df388ac2b-cc41c5ec-137e-4 | Hz-ID-17817 | HT - HALO TRUST | B/3029 | 424000 | 62.2991 | 33.4436 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2014-02-21 | 2014-05-10 | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 26 | CHA | 1 |  |  | 2013-03-19 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df388d8f5-77a1a7b6-1398-6 | Hz-ID-17804 | HT - HALO TRUST | B/3019 | 500000 | 62.286 | 33.4357 | Worked on | UXO Only | UXO Only | BF | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-06-04 | 2014-07-03 | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 250 | CHA | 1 |  |  | 2013-03-19 16:30 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13df39a7cd1-2276972f-14f4-4 | Hz-ID-17814 | HT - HALO TRUST | B/3030 | 455000 | 62.2983 | 33.4468 | Closed | UXO Only | UXO Only | BF | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 26 | CHA | 1 |  |  | 2013-03-20 16:30 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13e878dd7e3-bb9db6e6-2140-a | Hz-ID-17798 | HT - HALO TRUST | B/3017 | 500000 | 62.2877 | 33.4293 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-09-01 | 2013-09-23 | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 311 | CHA | 1 |  |  | 2013-03-17 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13e878e6b99-3408f890-215b-7 | Hz-ID-17819 | HT - HALO TRUST | B/3028 | 395000 | 62.3 | 33.4404 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2014-01-11 | 2014-02-16 | 1392-1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  |  |  | High | 229 | CHA | 1 |  |  | 2013-03-18 16:30 | No | Complete
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0009-13e878e8244-1dfb1cb5-2172-4 | Hz-ID-17810 | HT - HALO TRUST | B/3022 | 500000 | 62.2834 | 33.4454 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-09-03 | 2014-09-23 | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 58 | CHA | 1 |  |  | 2013-03-12 16:30 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0057-12c3b90a3ed-9222fd6d-25021- | BF-HQ-14164 | HT - HALO TRUST | B/2669 | 1029600 | 62.287 | 33.4298 | Open | UXO Only | UXO Only | BF | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 228 | CHA | 3 |  |  | 2009-09-18 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0057-12c3b90a6ab-3c142bd-25033-5 | MF-HQ-13186 | HT - HALO TRUST | H/5731 | 24250 | 62.2848 | 33.4312 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 185 | CHA | 3 |  |  | 2009-09-16 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0057-12c3b90a998-b2ffe3e2-2504f- | MF-HQ-13181 | HT - HALO TRUST | H/5730 | 26150 | 62.2824 | 33.442 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 156 | CHA | 3 |  |  | 2009-09-15 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0057-12c3b96b2d6-43445398-28f92- | MF-HQ-13182 | HT - HALO TRUST | H/5729 | 305500 | 62.3021 | 33.4385 | Worked on | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes | 2014-07-01 |  | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 235 | CHA | 4 |  |  | 2009-09-15 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0057-12c3b96b4d9-135d5ce6-28fb7- | MF-HQ-13185 | HT - HALO TRUST | H/5726 | 82500 | 62.3075 | 33.455 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 0 | CHA | 5 |  |  | 2009-09-13 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0057-12c3b96b7c6-9ed97f17-28fcb- | MF-HQ-13211 | HT - HALO TRUST | H/5728 | 129000 | 62.3024 | 33.4427 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 222 | CHA | 4 |  |  | 2009-09-14 | No | Planned
West | Hirat | Shindand | Ferqia 21 Paida | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} | c0a8-0057-12c3b96bb00-537faece-28fe6- | MF-HQ-13180 | HT - HALO TRUST | H/5727 | 35260 | 62.2971 | 33.4429 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-103 | Hirat Demining Project-01 | DFID | Yes |  |  | 1393 | HT | {D1D37184-AA67-431B-90CD-A1FDE3F84C4C} |  | High with Victim | High with Victims | High | 26 | CHA | 5 |  |  | 2009-09-13 | No | Planned
West | Hirat | Shindand | Kalmashaw | {1E4E837C-3CC0-45B5-BC45-070D4EE8657E} | c0a8-0057-12c3bb4728c-af36cd9f-3b258- | MF-HQ-11107 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2014/18696/MF0126 | 157500 | 62.1171 | 33.033 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-172 | Hirat Demining Project-03 |  |  |  |  | 1400 |  | {1E4E837C-3CC0-45B5-BC45-070D4EE8657E} |  | Low | Agriculture Blocked | High | 7 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Hirat | Shindand | Khayfan (Khayfun) | {A82CFFFC-2A31-438E-B6F9-C214460A5048} | c0a8-0057-12c3babb250-b9b52811-35f03- | MF-HQ-7441 | MCPA - Mine Clearance Planning Agency | AF/2014/18726/MF0024 | 46902 | 62.1128 | 33.3 | Open | AP Only | AP Only | MineField |  | MBT Project-172 | Hirat Demining Project-03 |  |  |  |  | 1400 |  | {A82CFFFC-2A31-438E-B6F9-C214460A5048} | Planned Agency Removed | Low | Agriculture Blocked | High | 48 | CHA | 5 |  |  | 2000-07-04 | No | Open
West | Hirat | Shindand | Khayfan (Khayfun) | {A82CFFFC-2A31-438E-B6F9-C214460A5048} | c0a8-0057-12c3bb76221-618ded66-3cd00- | MF-HQ-11113 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2014/18726/MF0127 | 50000 | 62.0423 | 33.2586 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-172 | Hirat Demining Project-03 |  |  |  |  | 1400 |  | {A82CFFFC-2A31-438E-B6F9-C214460A5048} |  | Low | Agriculture Blocked | High | 7 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Hirat | Shindand | Orain Ulya | {3285606B-BD13-4B92-AF64-E35863746D32} | c0a8-0057-12c3b87ea6d-23c253-1f0bf-35 | MF-HQ-10959 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2014/00815/MF0128 | 700000 | 62.1051 | 33.1456 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-172 | Hirat Demining Project-03 |  |  |  |  | 1400 |  | {3285606B-BD13-4B92-AF64-E35863746D32} |  | Low | Agriculture Blocked | High | 35 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Hirat | Shindand | Pada-i-Khalil | {53FD3AA2-8189-466A-A697-BA872BD0B47C} | c0a8-0057-12c3bb33f30-37b53f78-3a747- | MF-HQ-11020 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2014/18700/MF0129 | 640000 | 62.12 | 33.1202 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-172 | Hirat Demining Project-03 |  |  |  |  | 1400 |  | {53FD3AA2-8189-466A-A697-BA872BD0B47C} |  | Low | Critical Infrastracture | High | 80 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Hirat | Shindand | Par Makan | {B9A0DA77-876D-4DA9-8F20-AB73C217D8CB} | c0a8-0057-12c3b85069b-8908ef49-1d074- | MF-HQ-11012 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2014/18750/MF0131 | 497260 | 62.1871 | 33.0554 | Open | Mixed Mine | Mixed Mine | Converted From SHA |  | MBT Project-220 | Hirat Demining Project-04 |  |  |  |  | 1398 |  | {B9A0DA77-876D-4DA9-8F20-AB73C217D8CB} |  | High with Victim | High with Victims | High | 159 | SHA | 2 |  |  | 2009-06-17 | No | Open
West | Hirat | Shindand | Par Makan | {B9A0DA77-876D-4DA9-8F20-AB73C217D8CB} | c0a8-0057-12c3b90b22f-500df29f-250b6- | MF-HQ-11013 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2014/18750/MF0130 | 605000 | 62.1784 | 33.1645 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-220 | Hirat Demining Project-04 |  |  |  |  | 1398 |  | {B9A0DA77-876D-4DA9-8F20-AB73C217D8CB} |  | High with Victim | High with Victims | High | 0 | SHA | 2 |  |  | 2009-06-17 | No | Open
West | Hirat | Shindand | Par Makan | {B9A0DA77-876D-4DA9-8F20-AB73C217D8CB} | c0a8-0057-12c3b9ac8df-c41fbb9f-2bafa- | MF-HQ-11011 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2014/18750/MF0132 | 1470000 | 62.1955 | 33.1881 | Open | AT Only | AT Only | Converted From SHA |  | MBT Project-220 | Hirat Demining Project-04 |  |  |  |  | 1398 |  | {B9A0DA77-876D-4DA9-8F20-AB73C217D8CB} |  | High with Victim | High with Victims | High | 15 | SHA | 2 |  |  | 2009-06-17 | No | Open
West | Hirat | Shindand | Sanawghan | {F4895BC5-EC38-4624-9734-44A94C2732BD} | c0a8-0057-12c3bb8038c-303d9f3-3d307-a | MF-HQ-11068 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/1014/18751/MF0133 | 97200 | 62.1644 | 33.2221 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-220 | Hirat Demining Project-04 |  |  |  |  | 1398 |  | {F4895BC5-EC38-4624-9734-44A94C2732BD} |  | Medium | Critical Infrastracture | High | 19 | SHA | 3 |  |  | 2009-06-03 | No | Open
West | Hirat | Shindand | Shawz | {C466B299-3206-4F2F-8D05-AA0FA9753917} | c0a8-0057-12c3ba51e2d-e85e1e9f-320a5- | MF-HQ-11010 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/2014/00061/MF0134 | 80000 | 62.7236 | 33.1411 | Open | AP Only | AP Only | Converted From SHA |  | MBT Project-172 | Hirat Demining Project-03 |  |  |  |  | 1400 |  | {C466B299-3206-4F2F-8D05-AA0FA9753917} |  | Low | Agriculture Blocked | High | 11 | SHA | 5 |  |  | 2009-06-17 | No | Open
West | Hirat | Shindand | Shindand | {B57A2D93-C443-4301-89F0-F204A4B9DD39} | c0a8-00f6-135517e65ad-a5242d7a-277-48 | BF-15196 | HT - HALO TRUST | B/2668 | 521000 | 62.2976 | 33.412 | Closed | UXO Only | UXO Only | BF | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-03-14 | 2013-04-22 | 1392-1393 | HT | {B57A2D93-C443-4301-89F0-F204A4B9DD39} |  |  |  | High | 103 | CHA | 2 |  |  | 2009-09-17 16:30 | No | Complete
West | Hirat | Zanda Jan | Zinda Jan | {B01FC7E7-6B02-41FA-8FE8-0841CD60C1DD} | c0a8-0009-13cc2e122ee-395fbf0e-9ce-76 | Hz-ID-17612 | HT - HALO TRUST | H/7966 | 682 | 61.7246 | 34.3333 | Closed | Mixed | Mixed AP UXO | MineField | 1392 | MBT Project-139 | Hirat Demining Project-10 (AT) | DFID | Yes | 2013-07-04 | 2013-07-10 | 1392-1393 | HT | {B01FC7E7-6B02-41FA-8FE8-0841CD60C1DD} |  |  |  | Substantial | 0 | CHA | 2 |  |  | 2013-01-01 16:30 | No | Complete
Central | Panjsher | Bazarak | Sanguna | {D0E65A26-CDEA-4937-9D79-D03217511102} | c0a8-0057-12c3b878352-d98d2752-1ec14- | MF-CA-1785 | MCPA - Mine Clearance Planning Agency | AF/0310/01264/MF0021 | 37746 | 69.5741 | 35.3684 | Closed | AP Only | AP Only | MineField | 1391 | Project-132 | DDG Panjshir DOS Demining project 1391/1392 | DOS | Yes | 2012-06-01 | 2012-12-19 | 1392 | DDG | {D0E65A26-CDEA-4937-9D79-D03217511102} |  |  |  | Minimal | 11 |  | 5 |  |  | 2008-10-19 | No | Complete
Central | Panjsher | Shutul | Bostan | {11B04B35-A8E3-485E-83B9-FCCF5EBEFF71} | c0a8-008e-132e80557f7-57424979-aa7-9e | MF-15562 | DDG - Danish Demining Group | AF/0303/01799/MF0011 | 38530 | 69.2785 | 35.1772 | Closed | AP Only | AP Only | MineField | 1391 | Project-132 | DDG Panjshir DOS Demining project 1391/1392 | DOS | Yes |  |  | 1392 | DDG | {11B04B35-A8E3-485E-83B9-FCCF5EBEFF71} | Abdul Ghani and Mullah Amir Mohammad, are the contact persons |  |  | Minimal | 87 | CHA | 4 |  |  | 2011-04-11 16:30 | No | Complete
Central | Panjsher | Shutul | Chelana | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} | c0a8-0057-12c3b8c1a29-98640332-21f87- | MF-HQ-13491 | DDG - Danish Demining Group | AF/0302/01801/MF0005 | 66168 | 69.279 | 35.1804 | Closed | AP Only | AP Only | MineField | 1391 | Project-132 | DDG Panjshir DOS Demining project 1391/1392 | DOS | Yes | 2012-09-14 | 2012-12-31 | 1392 | DDG | {CC9173C8-7473-45D3-A801-2AD7CC1D0352} | Planned Year and Agency removed |  |  | Minimal | 743 | CHA | 4 |  |  | 2009-10-05 | No | Complete
Central | Panjsher | Unaba | Malekan | {50F00ABF-60A7-4810-B53D-71FAE0D2D23B} | c0a8-0057-12c3b828d00-145436f0-1b3df- | MF-HQ-14122 | DDG - Danish Demining Group | AF/0301/01206/MF0025 | 374419 | 69.3602 | 35.2355 | Closed | Mixed | Mixed AP UXO | MineField | 1391 | Project-132 | DDG Panjshir DOS Demining project 1391/1392 | DOS | Yes | 2012-07-27 | 2013-02-22 | 1392 | DDG | {50F00ABF-60A7-4810-B53D-71FAE0D2D23B} |  |  |  | Minimal | 881 | CHA | 4 |  |  | 2010-02-01 | No | Complete
Central | Parwan | Bagram | Bakhshikhel | {A5046DCA-D7D5-459B-AF8A-9797C68BCF65} | c0a8-0057-12c3b8d9962-49862c24-22f8b- | MF-CA-1832 | HT - HALO TRUST | H/5461 | 42650 | 69.3242 | 34.9486 | Closed | AP Only | AP Only | MineField | 1391 | Project-132 | DDG Panjshir DOS Demining project 1391/1392 | DOS | Yes | 2013-02-17 | 2013-04-14 | 1392 | DDG | {A5046DCA-D7D5-459B-AF8A-9797C68BCF65} |  |  |  | Moderate | 166 | CHA | 2 |  |  | 2008-11-09 | No | Complete
Central | Parwan | Bagram | Qaracha | {F89B1BAA-5F09-4F3B-AC8B-A94CA13F5BE1} | c0a8-0009-13c1394cf7e-5c672dac-4a4-20 | Hz-ID-17536 | DDG - Danish Demining Group | AF/0308/00767/MF0421 | 42350 | 69.3389 | 34.9975 | Closed | AP Only | AP Only | MineField | 1391/1392 | Project-132 | DDG Panjshir DOS Demining project 1391/1392 | DOS | Yes | 2013-02-17 | 2013-04-14 | 1392 | DDG | {F89B1BAA-5F09-4F3B-AC8B-A94CA13F5BE1} |  |  |  | Moderate | 28 | CHA | 2 |  |  | 2012-12-20 16:30 | No | Complete
Central | Parwan | Bagram | Qaracha | {F89B1BAA-5F09-4F3B-AC8B-A94CA13F5BE1} | c0a8-0057-12c3b6905d8-c3ec1cdd-87be-1 | MF-HQ-15092 | DDG - Danish Demining Group | AF/0308/00767/MF0357 | 63000 | 69.3318 | 34.9978 | Closed | Mixed | Mixed AP UXO | MineField | 1393 | Project-132 | DDG Panjshir DOS Demining project 1391/1392 | DOS | Yes | 2014-04-01 | 2014-05-29 | 1392 | DDG | {F89B1BAA-5F09-4F3B-AC8B-A94CA13F5BE1} |  |  |  | Moderate | 68 |  | 1 |  |  | 2010-08-05 | No | Complete
Central | Kabul | Surobi | Angurtak | {F1235FA7-230B-4B8A-8BF0-EF4CBC6F508B} | c0a8-0057-12c3b90e482-470ee383-252d0- | MF-HQ-10354 | MCPA - Mine Clearance Planning Agency | AF/0112/00430/MF0292 | 127597 | 69.7912 | 34.596 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {F1235FA7-230B-4B8A-8BF0-EF4CBC6F508B} | , | Low | Agriculture Blocked | Substantial | 16 | CHA | 5 |  |  | 2008-11-23 | No | Open
Central | Kabul | Surobi | Angurtak | {F1235FA7-230B-4B8A-8BF0-EF4CBC6F508B} | c0a8-0057-12c3b90e694-c76530d2-252e7- | MF-HQ-10353 | MCPA - Mine Clearance Planning Agency | AF/0112/00430/MF0291 | 118090 | 69.7912 | 34.596 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {F1235FA7-230B-4B8A-8BF0-EF4CBC6F508B} | , | Low | Agriculture Blocked | Substantial | 16 | CHA | 5 |  |  | 2008-11-20 | No | Open
Central | Kabul | Surobi | Angurtak | {F1235FA7-230B-4B8A-8BF0-EF4CBC6F508B} | c0a8-0057-12c3b90e878-f707e557-252fd- | MF-HQ-10355 | MCPA - Mine Clearance Planning Agency | AF/0112/00430/MF0293 | 36592 | 69.7895 | 34.5964 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {F1235FA7-230B-4B8A-8BF0-EF4CBC6F508B} | , | Low | Agriculture Blocked | Substantial | 5 | CHA | 5 |  |  | 2008-11-25 | No | Open
Central | Kabul | Surobi | Angurtak | {F1235FA7-230B-4B8A-8BF0-EF4CBC6F508B} | c0a8-0057-12c3b90ea7a-1d1e3bec-25313- | MF-HQ-10356 | MCPA - Mine Clearance Planning Agency | AF/0112/00430/MF0294 | 75764 | 69.7854 | 34.5963 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {F1235FA7-230B-4B8A-8BF0-EF4CBC6F508B} | , | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2008-11-27 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-0009-13e3bae0ccf-ae6d57a5-cac-7f | Hz-ID-17785 | ATC - Afghan Technical Consultants | AF/0112/00397/MF0551 | 41357 | 69.8348 | 34.5005 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} |  | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2013-03-30 16:30 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-0009-13e3bae3d9f-c848f13b-cc8-ad | Hz-ID-17784 | ATC - Afghan Technical Consultants | AF/0112/00397/MF0550 | 75052 | 69.8298 | 34.5003 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} |  | Medium | Critical Infrastracture | Substantial | 3 | CHA | 5 |  |  | 2013-03-30 16:30 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-0057-12c3b8c6a5a-ad749b9d-222bc- | MF-CA-2138 | MCPA - Mine Clearance Planning Agency | AF/0112/00397/MF0394 | 6912 | 69.817 | 34.4994 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | , | Low | Agriculture Blocked | Substantial | 0 | CHA | 5 |  |  | 2008-11-30 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-0057-12c3b9f2c61-b47a8140-2e6d1- | MF-HQ-10469 | MCPA - Mine Clearance Planning Agency | AF/0112/00397/MF0456 | 40037 | 69.8299 | 34.5044 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | , | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-03-28 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-00c9-12fd9aa0486-261b7ccb-10e5-8 | MF-HQ-10471 | DDG - Danish Demining Group | AF/0112/00397/MF0457 | 39803 | 69.8341 | 34.502 | Open | AP Only | AP Only | MineField | Blank | MBT Project-228 | Kabul Demining Project-17 |  | No |  |  | 1396 | None | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | Removed from DAFA planned 1391 | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-03-29 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-00c9-12fd9b1e4ae-581aa09f-1146-6 | MF-CA-2152 | MCPA - Mine Clearance Planning Agency | AF/0112/00397/MF400 | 71841 | 69.8298 | 34.5044 | Open | AP Only | AP Only | MineField | Blank | MBT Project-228 | Kabul Demining Project-17 |  | No |  |  | 1396 | None | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-02-15 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-00c9-12fd9b3ff44-e8d87415-1175-3 | MF-HQ-10466 | DDG - Danish Demining Group | AF/0112/00397/MF0454 | 34251 | 69.8341 | 34.502 | Open | AP Only | AP Only | MineField | Blank | MBT Project-228 | Kabul Demining Project-17 |  | No |  |  | 1396 | None | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | Removed From DAFA Plan 1391 | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-03-28 | No | Open
Central | Kabul | Surobi | Jorobay | {30441036-C819-4249-B73E-A6F05777D62C} | c0a8-0057-12c3b85daf7-d34e65a3-1d9b9- | MF-HQ-13958 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0112/00357/MF0488 | 180000 | 69.6168 | 34.3633 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {30441036-C819-4249-B73E-A6F05777D62C} | , | Low | Agriculture Blocked | Substantial | 11 | SHA | 5 |  |  | 2009-12-21 | No | Open
Central | Kabul | Surobi | Naghlu | {44C8600F-B89A-4748-8F5C-B691B0CD4C6A} | c0a8-0009-13e8257f5ec-50b6af42-7e6-a5 | Hz-ID-17877 | MCPA - Mine Clearance Planning Agency | AF/0112/00419/MF0541 | 100200 | 69.7295 | 34.6249 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {44C8600F-B89A-4748-8F5C-B691B0CD4C6A} |  | Low | Agriculture Blocked | Substantial | 83 | CHA | 5 |  |  | 2013-03-06 16:30 | No | Open
Central | Kabul | Surobi | Shirin Kalay | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} | c0a8-0009-13ce6a2bc3d-c7a5c27b-18fa-3 | Hz-ID-17388 | ATC - Afghan Technical Consultants | AF/0112/00424/MF0530 | 44940 | 69.7995 | 34.563 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} |  | Low | Critical Infrastracture | Substantial | 2 | CHA | 5 |  |  | 2012-08-27 16:30 | No | Open
Central | Kabul | Surobi | Shirin Kalay | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} | c0a8-0009-13dc9659600-e5286a47-2063-7 | Hz-ID-17750 | MCPA - Mine Clearance Planning Agency | AF/0112/00424/MF0533 | 19055 | 69.8121 | 34.5388 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} |  | Low | Agriculture Blocked | Substantial | 7 | CHA | 5 |  |  | 2013-02-16 16:30 | No | Open
Central | Kabul | Surobi | Shirin Kalay | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} | c0a8-0057-12c3b95c276-208d49c4-28602- | MF-CA-2194 | MCPA - Mine Clearance Planning Agency | AF/0112/00424/MF0444 | 6720 | 69.7976 | 34.5589 | Open | AP Only | AP Only | MineField | 1392 | MBT Project-228 | Kabul Demining Project-17 |  | No |  |  | 1396 | ATC | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} |  | Low | Critical Infrastracture | Substantial | 2 | CHA | 5 |  |  | 2009-03-19 | No | Open
Central | Kabul | Surobi | Shirin Kalay | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} | c0a8-0057-12c3b9b0d5c-b7426216-2bdd9- | MF-HQ-13602 | MCPA - Mine Clearance Planning Agency | AF/0112/00424/MF0494 | 104378 | 69.7659 | 34.5551 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} | , | Low | Agriculture Blocked | Substantial | 6 | CHA | 5 |  |  | 2009-11-05 | No | Open
Central | Kabul | Surobi | Shirin Kalay | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} | c0a8-00f6-1355c691742-852e7663-108f-f | MF-16691 | MCPA - Mine Clearance Planning Agency | AF/0112/00424/MF0524 | 105278 | 69.7659 | 34.5551 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  | Yes |  |  | 1396 |  | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} | , | Low | Agriculture Blocked | Substantial | 6 | CHA | 5 |  |  | 2011-12-17 16:30 | No | Open
Central | Kabul | Surobi | Shirin Kalay | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} | c0a8-00f6-137b677613e-52336496-c6-c64 | Hz-ID-17017 | DDG - Danish Demining Group | AF/0112/00424/MF0527 | 17600 | 69.7948 | 34.5581 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {29D49AC2-5AD6-4541-9DFD-18CEE1B9EFD0} | , | Low | Agriculture Blocked | Substantial | 2 | CHA | 5 |  |  | 2012-03-31 16:30 | No | Open
Central | Kabul | Surobi | Shpol Baba | {300C3DD8-9EEE-4183-BD95-0ACB8093F80E} | c0a8-00f6-13551eac2eb-c54264ed-3b8-c6 | MF-15864 | MDC - Mine Detection and Dog Center | AF/0112/00169/MF0517 | 20991 | 69.5257 | 34.5578 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  | No |  |  | 1396 | Blank | {300C3DD8-9EEE-4183-BD95-0ACB8093F80E} | Removed from DAFA 1391 Dos plan | Low | Critical Infrastracture | Substantial | 8 | CHA | 5 |  |  | 2011-03-31 16:30 | No | Open
Central | Kabul | Surobi | Torkanay | {CE0479F2-3774-4700-A760-951FA1B49923} | c0a8-0057-12c3b8b14ce-6b2f03de-213be- | MF-CA-2179 | MCPA - Mine Clearance Planning Agency | AF/0112/00638/MF0301 | 118790 | 69.6189 | 34.4421 | Open | AP Only | AP Only | MineField |  | MBT Project-228 | Kabul Demining Project-17 |  |  |  |  | 1396 |  | {CE0479F2-3774-4700-A760-951FA1B49923} |  | Low | Agriculture Blocked | Substantial | 82 | CHA | 5 |  |  | 2008-11-23 | No | Open
Central | Kabul | Surobi | Adam Ceray | {F23B6028-7393-42B3-8085-63F102F52652} | c0a8-0009-145d5a6f61c-9f2cdda7-37b6-7 | Hz-ID-18664 | MCPA - Mine Clearance Planning Agency | AF/0112/00450/MF0561 | 2212 | 69.8147 | 34.7141 | Open | AT Only | AT Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {F23B6028-7393-42B3-8085-63F102F52652} |  | Low | Comunity Centers | Substantial | 138 | CHA | 4 |  |  | 2014-03-08 16:30 | No | Open
Central | Kabul | Surobi | Chenar | {2C27C018-6A0B-41E5-AC71-6EEC66A2B539} | c0a8-0057-12c3bae075c-4a51aaa6-37540- | MF-CA-2180 | MCPA - Mine Clearance Planning Agency | AF/0112/00446/MF0360 | 61719 | 69.5718 | 34.5071 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {2C27C018-6A0B-41E5-AC71-6EEC66A2B539} | , | Low | Agriculture Blocked | Substantial | 59 | CHA | 4 |  |  | 2009-03-16 | No | Open
Central | Kabul | Surobi | Chenaray | {928C4A71-FCB3-4815-ABAB-A5FDEE5EFF7F} | c0a8-0057-12c3b8451b0-9b7fb0e6-1c819- | MF-HQ-14208 | MCPA - Mine Clearance Planning Agency | AF/0112/00443/MF0500 | 63627 | 69.6003 | 34.5221 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {928C4A71-FCB3-4815-ABAB-A5FDEE5EFF7F} |  | Low | Agriculture Blocked | Substantial | 44 | CHA | 4 |  |  | 2010-02-02 | No | Open
Central | Kabul | Surobi | Chenaray | {928C4A71-FCB3-4815-ABAB-A5FDEE5EFF7F} | c0a8-0057-12c3bae8d7b-e82698c6-37a86- | MF-HQ-13535 | MCPA - Mine Clearance Planning Agency | AF/0112/00443/MF469 | 85540 | 69.5752 | 34.5027 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {928C4A71-FCB3-4815-ABAB-A5FDEE5EFF7F} | , | Low | Agriculture Blocked | Substantial | 32 | CHA | 5 |  |  | 2009-10-07 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-0009-13bef5728f5-9f1e03e6-2aa7-9 | Hz-ID-17067 | MCPA - Mine Clearance Planning Agency | AF/0112/00397/MF0305 | 73519 | 69.7983 | 34.5051 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} |  | High Requested | Resettlment/Local Request | Substantial | 13 | CHA | 1 | Yes | Local requested by phone, | 2008-12-02 16:30 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-00c9-12fd9a2e533-3c86e64f-1042-2 | MF-CA-2136 | MCPA - Mine Clearance Planning Agency | AF/0112/00397/MF0304 | 56538 | 69.8084 | 34.5118 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | , | High Requested | Resettlment/Local Request | Substantial | 6 | CHA | 1 | Yes | Based on LIAT call afew days ago an accident is happened on cow. Local requested by phone, | 2008-11-30 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-00c9-12fd9a5779d-2cfc4385-1072-a | MF-CA-2139 | MCPA - Mine Clearance Planning Agency | AF/0112/00397/MF0395 | 72747 | 69.817 | 34.4994 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2008-11-30 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-00c9-12fd9a6bf24-5487d4ba-109e-7 | MF-CA-2155 | MCPA - Mine Clearance Planning Agency | AF/0112/00397/MF0396 | 53235 | 69.817 | 34.4994 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-01-31 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-00c9-12fd9ad3839-23ddcd53-1103-3 | MF-HQ-10399 | DDG - Danish Demining Group | AF/0112/00397/MF0398 | 87391 | 69.8283 | 34.5051 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-02-17 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-00c9-12fdd544d04-28b531f9-12c-ff | MF-HQ-10480 | DDG - Danish Demining Group | AF/0112/00397/MF0463 | 66701 | 69.8209 | 34.4968 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} |  | Low | Agriculture Blocked | Substantial | 3 | CHA | 5 |  |  | 2009-03-30 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-00c9-12fdd55f64b-ba45651a-15b-8a | MF-CA-2151 | DDG - Danish Demining Group | AF/0112/00397/MF0399 | 68544 | 69.828 | 34.5043 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} |  | Low | Critical Infrastracture | Substantial | 1 | CHA | 5 |  |  | 2009-02-19 | No | Open
Central | Kabul | Surobi | Debalay (2) | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} | c0a8-00c9-12fdd59efe6-7d8f888-1bb-b96 | MF-CA-2150 | DDG - Danish Demining Group | AF/0112/00397/MF0397 | 73374 | 69.8283 | 34.5051 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {6C5898EF-D570-4DC1-B4C0-D6111B991BA2} |  | Low | Agriculture Blocked | Substantial | 1 | CHA | 5 |  |  | 2009-02-15 | No | Open
Central | Kabul | Surobi | Gogamunda | {8D8B2D38-2A47-44F8-967D-CF18F878A648} | c0a8-0009-1454542c38c-9b5ba307-2f1-ac | Hz-ID-18608 | MCPA - Mine Clearance Planning Agency | AF/0112/00399/MF0552 | 24932 | 69.6065 | 34.576 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {8D8B2D38-2A47-44F8-967D-CF18F878A648} |  | Low | Agriculture Blocked | Substantial | 58 | CHA | 5 |  |  | 2014-02-26 16:30 | No | Open
Central | Kabul | Surobi | Jegdalay | {D0214681-05A8-4B52-ABEA-CCEEE7DDEFC3} | c0a8-0009-145d59f68a0-ff814177-36f0-6 | Hz-ID-18665 | MCPA - Mine Clearance Planning Agency | AF/0112/00371/MF0562 | 314530 | 69.7772 | 34.4321 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {D0214681-05A8-4B52-ABEA-CCEEE7DDEFC3} |  | Low | Agriculture Blocked | Substantial | 265 | CHA | 4 |  |  | 2014-03-14 16:30 | No | Open
Central | Kabul | Surobi | Shinwari | {E8D6602F-0F9F-4FF6-903F-3A99095AF6FA} | c0a8-0057-12c3b9ddb2a-58decd97-2d9cf- | MF-CA-2224 | MCPA - Mine Clearance Planning Agency | AF/0112/00168/MF314 | 7006 | 69.4841 | 34.5606 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {E8D6602F-0F9F-4FF6-903F-3A99095AF6FA} | , | High with Victim | High with Victims | Substantial | 1 | CHA | 2 |  |  | 2008-11-30 | No | Open
Central | Kabul | Surobi | Shinwari | {E8D6602F-0F9F-4FF6-903F-3A99095AF6FA} | c0a8-00f6-13550f89408-5f18f601-2-b431 | MF-16673 | MDC - Mine Detection and Dog Center | AF/0112/00168/MF0522 | 23195 | 69.4822 | 34.5592 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {E8D6602F-0F9F-4FF6-903F-3A99095AF6FA} |  | High with Victim | High with Victims | Substantial | 0 | CHA | 2 |  |  | 2010-12-05 16:30 | No | Open
Central | Kabul | Surobi | Sorubi | {0DA0F18B-53EB-42C2-A9E7-D73ABC496A4C} | c0a8-0057-12c3b9b0b78-c09f282f-2bdc8- | LM - HQ-13616 | MCPA - Mine Clearance Planning Agency | AF/0112/00428/MF0484 | 131332 | 69.822 | 34.5043 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {0DA0F18B-53EB-42C2-A9E7-D73ABC496A4C} |  | High with Victim | High with Victims | Substantial | 1 | CHA | 2 |  |  | 2009-11-05 | No | Open
Central | Kabul | Surobi | Tizini Khas | {94A1EAF7-3E37-41DF-A266-17D43F415464} | c0a8-0009-13dc98b722f-910d6896-21f8-9 | Hz-ID-17748 | MCPA - Mine Clearance Planning Agency | AF/0112/00355/BF0531 | 445 | 69.5802 | 34.4004 | Open | UXO Only | UXO Only | BF |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {94A1EAF7-3E37-41DF-A266-17D43F415464} |  | Medium | Agriculture Blocked | Substantial | 98 | CHA | 3 |  |  | 2013-02-11 16:30 | No | Open
Central | Kabul | Surobi | Tizini Khas | {94A1EAF7-3E37-41DF-A266-17D43F415464} | c0a8-0009-145d5f86cb0-84642bde-37f5-1 | Hz-ID-18662 | MCPA - Mine Clearance Planning Agency | AF/0111/00355/MF0560 | 14689 | 69.5822 | 34.3544 | Open | AT Only | AT Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {94A1EAF7-3E37-41DF-A266-17D43F415464} |  | Low | Agriculture Blocked | Substantial | 131 | CHA | 4 |  |  | 2014-03-01 16:30 | No | Open
Central | Kabul | Surobi | Tizini Khas | {94A1EAF7-3E37-41DF-A266-17D43F415464} | c0a8-0057-12c3b70a52f-3ef7786b-e3fb-a | MF-HQ-14011 | MCPA - Mine Clearance Planning Agency | AF/0112/00355/MF0473 | 48691 | 69.5832 | 34.3573 | Open | AT Only | AT Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {94A1EAF7-3E37-41DF-A266-17D43F415464} | , | Low | Agriculture Blocked | Substantial | 266 | CHA | 4 |  |  | 2009-10-11 | No | Open
Central | Kabul | Surobi | Waka (1) | {121617C7-7FCB-4BC3-8D54-737FB372FA8A} | c0a8-00f6-13855a9a600-adfc756d-998-75 | MF-16763 | MCPA - Mine Clearance Planning Agency | AF/0112/00422/MF0528 | 159330 | 69.7383 | 34.6495 | Open | AP Only | AP Only | MineField |  | MBT Project-009 | Kabul Demining Project-06 |  |  |  |  | 1394 |  | {121617C7-7FCB-4BC3-8D54-737FB372FA8A} |  | High with Victim | High with Victims | Substantial | 35 | CHA | 2 |  |  | 2012-03-29 16:30 | No | Open
Central | Kabul | Surobi | Zero Tanga | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} | c0a8-0009-13e8257a53e-f4906db0-7c8-80 | Hz-ID-17875 | MCPA - Mine Clearance Planning Agency | AF/0112/00363/MF0539 | 1053 | 69.6199 | 34.5227 | Open | AP Only | AP Only | MineField | 1393 | MBT Project-009 | Kabul Demining Project-06 |  | No |  |  | 1394 | DDG | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} |  | Low | Agriculture Blocked | Substantial | 22 | CHA | 5 |  |  | 2013-03-05 16:30 | No | Open
Central | Kabul | Surobi | Zero Tanga | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} | c0a8-0057-12c3ba46d38-9904ff76-31a10- | MF-CA-2163 | MCPA - Mine Clearance Planning Agency | AF/0112/00363/MF347 | 28952 | 69.566 | 34.5305 | Open | AP Only | AP Only | MineField | Blank | MBT Project-009 | Kabul Demining Project-06 |  | No |  |  | 1394 | None | {D6B3EA99-D569-4060-85DB-564C3CAFD71B} |  | Low | Agriculture Blocked | Substantial | 35 | CHA | 4 |  |  | 2008-12-16 | No | Open
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-004c-13026dcd292-3ecd1a32-ee3-2f | MF-HQ-10162 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0047 | 87890 | 70.3183 | 34.3072 | Open | AP Only | AP Only | MineField | Blank | MBT Project-181/C | Nangarhar Demining Project-02/C |  | No |  |  | 1394 | None | {FA198158-861B-4A01-8C1D-03EAB21140A9} |  | High Requested | Resettlment/Local Request | High | 83 | CHA | 1 | Yes | according to communiy required and request | 2009-02-03 | No | Open
East | Nangarhar | Chaparhar | Baloc Koruna(Kac) | {FA198158-861B-4A01-8C1D-03EAB21140A9} | c0a8-008e-1345607cc6b-b6056f6-9ce-ee7 | MF-16432 | MCPA - Mine Clearance Planning Agency | AF/0806/09001/MF0215 | 66560 | 70.3358 | 34.3054 | Open | AT Only | AT Only | MineField | Blank | MBT Project-181/C | Nangarhar Demining Project-02/C |  | No |  |  | 1394 | None | {FA198158-861B-4A01-8C1D-03EAB21140A9} |  | High Requested | Resettlment/Local Request | High | 29 | CHA | 1 | Yes | according to communiy required and request | 2011-01-05 16:30 | No | Open
East | Nangarhar | Chaparhar | Dago | {AB6A0A3A-7F24-4861-89A4-20B1404F99F2} | c0a8-0057-12edcf0c748-75c5f16c-4fc-2a | MF-HQ-10056 | MCPA - Mine Clearance Planning Agency | AF/0806/00515/MF0025 | 192327 | 70.3191 | 34.2665 | Open | AT Only | AT Only | MineField | Blank | MBT Project-181/C | Nangarhar Demining Project-02/C |  | No |  |  | 1394 | None | {AB6A0A3A-7F24-4861-89A4-20B1404F99F2} |  | High Requested | Resettlment/Local Request | High | 418 | CHA | 1 | Yes | according to communiy required and request | 2009-02-04 | No | Open
East | Nangarhar | Chaparhar | Sra Kala | {9CABB161-2343-4B60-A299-34451A973AD6} | c0a8-0009-13f0888d5b4-ca053b4b-6ca-e1 | Hz-ID-17937 | MCPA - Mine Clearance Planning Agency | AF/0806/09016/MF0246 | 126580 | 70.3698 | 34.3047 | Open | AT Only | AT Only | MineField |  | MBT Project-181/C | Nangarhar Demining Project-02/C |  |  |  |  | 1394 |  | {9CABB161-2343-4B60-A299-34451A973AD6} |  | High with Victim | High with Victims | High | 101 | CHA | 1 |  |  | 2013-04-28 16:30 | No | Open
East | Nangarhar | Chaparhar | Sra Kala | {9CABB161-2343-4B60-A299-34451A973AD6} | c0a8-0009-13f095f1567-ed1489d0-182a-6 | Hz-ID-17941 | MCPA - Mine Clearance Planning Agency | AF/0806/09016/MF0247 | 117456 | 70.3698 | 34.3097 | Open | AT Only | AT Only | MineField |  | MBT Project-181/C | Nangarhar Demining Project-02/C |  |  |  |  | 1394 |  | {9CABB161-2343-4B60-A299-34451A973AD6} |  | High with Victim | High with Victims | High | 52 | CHA | 1 |  |  | 2013-04-29 16:30 | No | Open
East | Nangarhar | Chaparhar | Sra Kala | {9CABB161-2343-4B60-A299-34451A973AD6} | c0a8-0009-13fe0e83fdc-85fbb118-3109-a | Hz-ID-18049 | MCPA - Mine Clearance Planning Agency | AF/0806/09016/MF0248 | 155967 | 70.3689 | 34.307 | Open | AT Only | AT Only | MineField |  | MBT Project-181/C | Nangarhar Demining Project-02/C |  |  |  |  | 1394 |  | {9CABB161-2343-4B60-A299-34451A973AD6} |  | High with Victim | High with Victims | High | 46 | CHA | 1 |  |  | 2013-05-01 16:30 | No | Open
East | Nangarhar | Chaparhar | Sra Kala | {9CABB161-2343-4B60-A299-34451A973AD6} | c0a8-0009-13fe0ec6fec-839a7b74-3124-7 | Hz-ID-18055 | MCPA - Mine Clearance Planning Agency | AF/0806/09016/MF0249 | 163374 | 70.3689 | 34.307 | Open | AT Only | AT Only | MineField |  | MBT Project-181/C | Nangarhar Demining Project-02/C |  |  |  |  | 1394 |  | {9CABB161-2343-4B60-A299-34451A973AD6} |  | High with Victim | High with Victims | High | 46 | CHA | 1 |  |  | 2013-05-04 16:30 | No | Open
East | Nangarhar | Chaparhar | Sra Kala | {9CABB161-2343-4B60-A299-34451A973AD6} | c0a8-0009-13fe0f0656c-efc508b3-3155-7 | Hz-ID-18059 | MCPA - Mine Clearance Planning Agency | AF/0806/09016/MF0252 | 98658 | 70.3689 | 34.307 | Open | AT Only | AT Only | MineField |  | MBT Project-181/C | Nangarhar Demining Project-02/C |  |  |  |  | 1394 |  | {9CABB161-2343-4B60-A299-34451A973AD6} |  | High with Victim | High with Victims | High | 42 | CHA | 1 |  |  | 2013-05-05 16:30 | No | Open
East | Nangarhar | Kot | Purshakhel | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} | c0a8-00f6-1355225705a-a899ec34-355-7c | MF-16236 | MCPA - Mine Clearance Planning Agency | AF/0809/08916/MF0212 | 113192 | 70.527 | 34.1203 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-181/C | Nangarhar Demining Project-02/C |  | No |  |  | 1394 | WRA | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} |  | High with Victim | High with Victims | Substantial | 621 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-08-09 16:30 | No | Open
East | Nangarhar | Kot | Purshakhel | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} | c0a8-00f6-139ae62106c-e0190518-294b-3 | Hz-ID-17249 | MCPA - Mine Clearance Planning Agency | AF/0822/08916/MF0238 | 204062 | 70.5264 | 34.1497 | Open | AT Only | AT Only | MineField | 1393 | MBT Project-181/C | Nangarhar Demining Project-02/C |  | No |  |  | 1394 | WRA | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} |  | High with Victim | High with Victims | Substantial | 2 | CHA | 5 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2012-08-09 16:30 | No | Open
East | Nangarhar | Nazyan | Fuladi Khulah | {F7939340-52F4-4B9E-A13B-29CF1ABD46DB} | c0a8-0057-12c3ba40a91-d64b7bc0-3163a- | MF-HQ-13769 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0811/00777/MF0027 | 105000 | 70.8527 | 34.0084 | Open | AP Only | AP Only | MineField | Blank | MBT Project-181/C | Nangarhar Demining Project-02/C |  | No |  |  | 1394 | None | {F7939340-52F4-4B9E-A13B-29CF1ABD46DB} |  | High Requested | Resettlment/Local Request | Substantial | 272 | SHA | 4 |  |  | 2009-12-05 | No | Open
East | Nangarhar | Nazyan | Karmo Khail | {2A792323-DE3A-474B-8EB6-61AEF91DBD52} | c0a8-0057-12c3b83d976-a1a6fd99-1c2a8- | MF-HQ-10633 | MCPA - Mine Clearance Planning Agency | AF/0811/00119/MF0009 | 95602 | 70.852 | 34.0187 | Open | AP Only | AP Only | MineField | Blank | MBT Project-181/C | Nangarhar Demining Project-02/C |  | No |  |  | 1394 | None | {2A792323-DE3A-474B-8EB6-61AEF91DBD52} |  | High Requested | Resettlment/Local Request | Substantial | 260 | CHA | 4 |  |  | 2009-03-10 | No | Open
East | Nangarhar | Nazyan | Karmo Khail | {2A792323-DE3A-474B-8EB6-61AEF91DBD52} | c0a8-0057-12c3b83db5a-7a71542d-1c2c2- | MF-HQ-10631 | MCPA - Mine Clearance Planning Agency | AF/0811/00119/MF0012 | 91270 | 70.8584 | 34.0179 | Open | AP Only | AP Only | MineField | Blank | MBT Project-181/C | Nangarhar Demining Project-02/C |  | No |  |  | 1394 | None | {2A792323-DE3A-474B-8EB6-61AEF91DBD52} |  | High Requested | Resettlment/Local Request | Substantial | 49 | CHA | 4 |  |  | 2009-03-15 | No | Open
East | Nangarhar | Nazyan | Karmo Khail | {2A792323-DE3A-474B-8EB6-61AEF91DBD52} | c0a8-0057-12c3b83dd1e-ba328946-1c2dc- | MF-HQ-10634 | MCPA - Mine Clearance Planning Agency | AF/0811/00119/MF0010 | 74276 | 70.852 | 34.0187 | Open | AP Only | AP Only | MineField | Blank | MBT Project-181/C | Nangarhar Demining Project-02/C |  | No |  |  | 1394 | None | {2A792323-DE3A-474B-8EB6-61AEF91DBD52} |  | High Requested | Resettlment/Local Request | Substantial | 238 | CHA | 4 |  |  | 2009-03-12 | No | Open
East | Nangarhar | Nazyan | Lalmay | {9A1DBBF4-C27A-4B36-AEB0-70E356FF10F9} | c0a8-0057-12c3b911742-cb1b99b6-254df- | MF-HQ-13764 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0811/09069/MF0028 | 180000 | 70.8063 | 34.0272 | Open | AP Only | AP Only | MineField | Blank | MBT Project-181/C | Nangarhar Demining Project-02/C |  | No |  |  | 1394 | None | {9A1DBBF4-C27A-4B36-AEB0-70E356FF10F9} |  | High Requested | Resettlment/Local Request | Substantial | 106 | SHA | 6 |  |  | 2009-12-05 | No | Open
East | Nangarhar | Rodat | Muhmand | {267F1872-BAF8-4CA5-A1DC-0118A8128C85} | c0a8-0009-13fe0d473d1-4cf81ea5-3054-a | Hz-ID-18054 | MCPA - Mine Clearance Planning Agency | AF/0809/08969/MF0258 | 1964 | 70.4876 | 34.2778 | Open | Mixed | Mixed AP UXO | MineField |  | MBT Project-181/C | Nangarhar Demining Project-02/C |  |  |  |  | 1394 |  | {267F1872-BAF8-4CA5-A1DC-0118A8128C85} |  | High | Critical Infrastracture | High | 0 | CHA | 3 |  |  | 2013-05-07 16:30 | No | Open
East | Nangarhar | Rodat | Qatraghay | {C323B94D-80D9-4F16-A1B2-C3AC30BE1D93} | c0a8-0009-13fe132bea6-c9907e4f-343b-7 | Hz-ID-18050 | MCPA - Mine Clearance Planning Agency | AF/0809/08971/MF0259 | 68386 | 70.5338 | 34.2814 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-181/C | Nangarhar Demining Project-02/C |  |  |  |  | 1394 |  | {C323B94D-80D9-4F16-A1B2-C3AC30BE1D93} |  | Low | Agriculture Blocked | High | 4 | CHA | 5 |  |  | 2013-05-16 16:30 | No | Open
East | Nangarhar | Rodat | Sangar | {39C8FAB3-EE8A-4254-B334-3E5BD9174535} | c0a8-0009-145da393a68-a7b34333-e91-85 | Hz-ID-18690 | OMAR - Organization for Mine Clearance and Afghan Rehabilitation | AF/0809/08961/MF0268 | 27605 | 70.6571 | 34.2599 | Open | AT Only | AT Only | MineField |  | MBT Project-181/C | Nangarhar Demining Project-02/C |  |  |  |  | 1394 |  | {39C8FAB3-EE8A-4254-B334-3E5BD9174535} |  | Low | Agriculture Blocked | High | 95 | CHA | 5 |  |  | 2014-03-23 16:30 | No | Open
East | Nangarhar | Hesarak | Alikhel | {361724E3-E8A9-4F09-8201-9618C550AF37} | c0a8-00f6-135522cc465-ad41f9bc-40d-fd | MF-15984 | ATC - Afghan Technical Consultants | AF/0803/9493/MF0068 | 19435 | 69.8158 | 34.3101 | Open | Mixed | Mixed AP UXO | MineField | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 | None | {361724E3-E8A9-4F09-8201-9618C550AF37} |  | Medium | Agriculture Blocked | High | 45 | CHA | 3 |  |  | 2011-06-30 16:30 | No | Open
East | Nangarhar | Hesarak | Monai | {67A5D623-1024-40C2-8197-72BBE394FA04} | c0a8-00f6-1369ad185a6-dc0ade80-181f-4 | MF-16746 | MCPA - Mine Clearance Planning Agency | AF/0803/00071/MF0071 | 93445 | 69.7238 | 34.352 | Open | Mixed | Mixed AP UXO | MineField | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 | None | {67A5D623-1024-40C2-8197-72BBE394FA04} |  | High with Victim | High with Victims | High | 39 | CHA | 1 |  |  | 2012-03-08 16:30 | No | Open
East | Nangarhar | Hesarak | Monai | {67A5D623-1024-40C2-8197-72BBE394FA04} | c0a8-00f6-1369adc4b2c-7e661698-1a5a-f | MF-16747 | MCPA - Mine Clearance Planning Agency | AF/0803/00071/MF0073 | 109975 | 69.7238 | 34.352 | Open | Mixed | Mixed AP UXO | MineField | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 | None | {67A5D623-1024-40C2-8197-72BBE394FA04} |  | High with Victim | High with Victims | High | 163 | CHA | 1 |  |  | 2012-03-11 16:30 | No | Open
East | Nangarhar | Hesarak | Monai | {67A5D623-1024-40C2-8197-72BBE394FA04} | c0a8-00f6-1369ae32598-2ca0c6fe-1a85-3 | MF-16748 | MCPA - Mine Clearance Planning Agency | AF/0803/00071/MF0072 | 103620 | 69.7238 | 34.352 | Open | Mixed | Mixed AP UXO | MineField | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 | None | {67A5D623-1024-40C2-8197-72BBE394FA04} |  | High with Victim | High with Victims | High | 163 | CHA | 1 |  |  | 2012-03-10 16:30 | No | Open
East | Nangarhar | Hesarak | Monai | {67A5D623-1024-40C2-8197-72BBE394FA04} | c0a8-00f6-1369ae5b1a7-7da6243a-1a9d-8 | MF-16749 | MCPA - Mine Clearance Planning Agency | AF/0803/00071/MF0075 | 15669 | 69.7288 | 34.3548 | Open | Mixed | Mixed AP UXO | MineField | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 | None | {67A5D623-1024-40C2-8197-72BBE394FA04} |  | High with Victim | High with Victims | High | 26 | CHA | 1 |  |  | 2012-03-13 16:30 | No | Open
East | Nangarhar | Hesarak | Monai | {67A5D623-1024-40C2-8197-72BBE394FA04} | c0a8-00f6-1369ae7e491-1d1060e2-1ac1-4 | BF-15219 | MCPA - Mine Clearance Planning Agency | AF/0803/00071/BF0070 | 321789 | 69.7287 | 34.3429 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 | None | {67A5D623-1024-40C2-8197-72BBE394FA04} |  | High with Victim | High with Victims | High | 181 | CHA | 1 |  |  | 2012-03-03 16:30 | No | Open
East | Nangarhar | Hesarak | Monai | {67A5D623-1024-40C2-8197-72BBE394FA04} | c0a8-00f6-1369aefb73c-7d285606-1b8e-2 | BF-15220 | MCPA - Mine Clearance Planning Agency | AF/0803/00071/BF0076 | 602782 | 69.7181 | 34.3558 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 | None | {67A5D623-1024-40C2-8197-72BBE394FA04} |  | High with Victim | High with Victims | High | 195 | CHA | 1 |  |  | 2012-03-14 16:30 | No | Open
East | Nangarhar | Hesarak | Monai | {67A5D623-1024-40C2-8197-72BBE394FA04} | c0a8-00f6-136b4db257f-2705258e-335-c1 | BF-15221 | MCPA - Mine Clearance Planning Agency | AF/0803/00071/BF0077 | 608866 | 69.7181 | 34.3558 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 | None | {67A5D623-1024-40C2-8197-72BBE394FA04} |  | High with Victim | High with Victims | High | 76 | CHA | 1 |  |  | 2012-03-14 16:30 | No | Open
East | Nangarhar | Hesarak | Monai | {67A5D623-1024-40C2-8197-72BBE394FA04} | c0a8-00f6-13706e99981-aa91d8a0-65d-bd | MF-16758 | MCPA - Mine Clearance Planning Agency | AF/0803/00071/MF0074 | 126274 | 69.7251 | 34.3578 | Open | Mixed | Mixed AP UXO | MineField | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 | None | {67A5D623-1024-40C2-8197-72BBE394FA04} |  | High with Victim | High with Victims | High | 54 | CHA | 1 |  |  | 2012-03-12 16:30 | No | Open
East | Nangarhar | Khogayani | Kilaghu | {067F8B41-92BA-4AB3-9442-38168ED2C114} | c0a8-0009-13e88a11a58-90eb30ca-3db5-6 | Hz-ID-17896 | MCPA - Mine Clearance Planning Agency | AF/0805/09636/MF0274 | 38535 | 70.145 | 34.2341 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {067F8B41-92BA-4AB3-9442-38168ED2C114} |  | High with Victim | High with Victims | High | 44 | CHA | 1 |  |  | 2013-03-27 16:30 | No | Open
East | Nangarhar | Khogayani | Kilaghu | {067F8B41-92BA-4AB3-9442-38168ED2C114} | c0a8-0009-13e88be0d33-405c9cca-41a6-8 | Hz-ID-17906 | MCPA - Mine Clearance Planning Agency | AF/0805/09636/MF0273 | 67702 | 70.1455 | 34.2363 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {067F8B41-92BA-4AB3-9442-38168ED2C114} |  | High with Victim | High with Victims | High | 44 | CHA | 1 |  |  | 2013-03-23 16:30 | No | Open
East | Nangarhar | Khogayani | Kilaghu | {067F8B41-92BA-4AB3-9442-38168ED2C114} | c0a8-0009-13e88e4d226-40de30ed-44be-c | Hz-ID-17895 | MCPA - Mine Clearance Planning Agency | AF/0805/09636/MF0275 | 77031 | 70.1455 | 34.2363 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {067F8B41-92BA-4AB3-9442-38168ED2C114} |  | High with Victim | High with Victims | High | 44 | CHA | 1 |  |  | 2013-03-26 16:30 | No | Open
East | Nangarhar | Khogayani | Lokhay | {2AECD18F-F099-4800-9133-8896754C7BB5} | c0a8-0009-13dd3f4fcc5-2b8c4d96-2314-7 | Hz-ID-17757 | MCPA - Mine Clearance Planning Agency | AF/0805/09681/MF0268 | 57308 | 70.1824 | 34.3027 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {2AECD18F-F099-4800-9133-8896754C7BB5} |  | High with Victim | High with Victims | High | 244 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2013-02-16 16:30 | No | Open
East | Nangarhar | Khogayani | Lokhay | {2AECD18F-F099-4800-9133-8896754C7BB5} | c0a8-0009-13e880ddb0e-c4baa764-2331-1 | Hz-ID-17886 | MCPA - Mine Clearance Planning Agency | AF/0805/09681/BF0272 | 143 | 70.1943 | 34.304 | Open | UXO Only | UXO Only | BF |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {2AECD18F-F099-4800-9133-8896754C7BB5} |  | High with Victim | High with Victims | High | 2679 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2013-03-13 16:30 | No | Open
East | Nangarhar | Khogayani | Lokhay | {2AECD18F-F099-4800-9133-8896754C7BB5} | c0a8-0009-13e881247b3-5a8583d8-2349-2 | Hz-ID-17885 | MCPA - Mine Clearance Planning Agency | AF/0805/09681/BF0267 | 184 | 70.1945 | 34.3044 | Open | UXO Only | UXO Only | BF |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {2AECD18F-F099-4800-9133-8896754C7BB5} |  | High with Victim | High with Victims | High | 2679 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2013-03-14 16:30 | No | Open
East | Nangarhar | Khogayani | Lokhay | {2AECD18F-F099-4800-9133-8896754C7BB5} | c0a8-0009-13e88aa6681-7ab14262-3eb5-f | Hz-ID-17904 | MCPA - Mine Clearance Planning Agency | AF/0805/09681/MF0271 | 171743 | 70.1853 | 34.2919 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {2AECD18F-F099-4800-9133-8896754C7BB5} |  | High with Victim | High with Victims | High | 989 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2013-03-13 16:30 | No | Open
East | Nangarhar | Khogayani | Lokhay | {2AECD18F-F099-4800-9133-8896754C7BB5} | c0a8-0009-13e88d8b24c-31533a5d-430a-a | Hz-ID-17901 | MCPA - Mine Clearance Planning Agency | AF/0805/09681/MF0270 | 199408 | 70.1853 | 34.2919 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {2AECD18F-F099-4800-9133-8896754C7BB5} |  | High with Victim | High with Victims | High | 148 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2013-03-07 16:30 | No | Open
East | Nangarhar | Khogayani | Lokhay | {2AECD18F-F099-4800-9133-8896754C7BB5} | c0a8-0009-13e88e214a3-476ac867-43d1-e | Hz-ID-17907 | MCPA - Mine Clearance Planning Agency | AF/0805/09681/MF0269 | 190906 | 70.1842 | 34.3029 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {2AECD18F-F099-4800-9133-8896754C7BB5} |  | High with Victim | High with Victims | High | 243 | CHA | 1 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2013-03-06 16:30 | No | Open
East | Nangarhar | Khogayani | Myagan | {D2693D26-558B-456F-85E2-FE91FCD1A72B} | c0a8-0057-12c3b85b983-d03073a8-1d85b- | MF-HQ-10101 | MCPA - Mine Clearance Planning Agency | AF/0805/09618/BF0078 | 90462 | 70.1624 | 34.1239 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 |  | {D2693D26-558B-456F-85E2-FE91FCD1A72B} |  | High Requested | Resettlment/Local Request | High | 3 | CHA | 5 |  |  | 2009-01-29 | No | Open
East | Nangarhar | Khogayani | Myagan | {D2693D26-558B-456F-85E2-FE91FCD1A72B} | c0a8-0057-12c3b85bb29-b94d0122-1d86d- | MF-HQ-10104 | MCPA - Mine Clearance Planning Agency | AF/0805/09618/BF0082 | 95760 | 70.1624 | 34.1239 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 |  | {D2693D26-558B-456F-85E2-FE91FCD1A72B} |  | High Requested | Resettlment/Local Request | High | 26 | CHA | 5 |  |  | 2009-01-27 | No | Open
East | Nangarhar | Khogayani | Myagan | {D2693D26-558B-456F-85E2-FE91FCD1A72B} | c0a8-0057-12c3b85bced-71fa45aa-1d87f- | MF-HQ-10099 | MCPA - Mine Clearance Planning Agency | AF/0805/09618/BF0079 | 94987 | 70.1624 | 34.1239 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 |  | {D2693D26-558B-456F-85E2-FE91FCD1A72B} |  | High Requested | Resettlment/Local Request | High | 3 | CHA | 5 |  |  | 2009-01-31 | No | Open
East | Nangarhar | Khogayani | Myagan | {D2693D26-558B-456F-85E2-FE91FCD1A72B} | c0a8-0057-12c3b85bec1-63b02fa2-1d893- | MF-HQ-10097 | MCPA - Mine Clearance Planning Agency | AF/0805/09618/BF0077 | 89860 | 70.1624 | 34.1239 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 |  | {D2693D26-558B-456F-85E2-FE91FCD1A72B} |  | High Requested | Resettlment/Local Request | High | 3 | CHA | 5 |  |  | 2009-01-24 | No | Open
East | Nangarhar | Khogayani | Myagan | {D2693D26-558B-456F-85E2-FE91FCD1A72B} | c0a8-0057-12c3b85c076-fb1096bd-1d8a5- | MF-HQ-10098 | MCPA - Mine Clearance Planning Agency | AF/0805/09618/BF0072 | 88039 | 70.1624 | 34.1239 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 |  | {D2693D26-558B-456F-85E2-FE91FCD1A72B} |  | High Requested | Resettlment/Local Request | High | 3 | CHA | 5 |  |  | 2009-01-30 | No | Open
East | Nangarhar | Khogayani | Myagan | {D2693D26-558B-456F-85E2-FE91FCD1A72B} | c0a8-0057-12c3b85c22a-3d168b0e-1d8b9- | MF-HQ-10105 | MCPA - Mine Clearance Planning Agency | AF/0805/09618/BF0083 | 87130 | 70.1624 | 34.1239 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 |  | {D2693D26-558B-456F-85E2-FE91FCD1A72B} |  | High Requested | Resettlment/Local Request | High | 26 | CHA | 5 |  |  | 2009-01-29 | No | Open
East | Nangarhar | Khogayani | Myagan | {D2693D26-558B-456F-85E2-FE91FCD1A72B} | c0a8-0057-12c3b85c3df-e869f0b7-1d8ca- | MF-HQ-10102 | MCPA - Mine Clearance Planning Agency | AF/0805/09618/BF0080 | 91860 | 70.1624 | 34.1239 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 |  | {D2693D26-558B-456F-85E2-FE91FCD1A72B} |  | High Requested | Resettlment/Local Request | High | 3 | CHA | 5 |  |  | 2009-01-25 | No | Open
East | Nangarhar | Khogayani | Myagan | {D2693D26-558B-456F-85E2-FE91FCD1A72B} | c0a8-0057-12c3b85c5b3-a1fd0563-1d8dc- | MF-HQ-10103 | MCPA - Mine Clearance Planning Agency | AF/0805/09816/BF0081 | 82231 | 70.1624 | 34.1239 | Open | UXO Only | UXO Only | BF | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 |  | {D2693D26-558B-456F-85E2-FE91FCD1A72B} |  | Low | Agriculture Blocked | High | 3 | CHA | 5 |  |  | 2009-01-26 | No | Open
East | Nangarhar | Khogayani | Somocay | {A19D473B-6F76-4A8E-A5CF-A396EF6E6FC8} | c0a8-0009-13dd3f4db8d-1fcd2052-22f9-8 | Hz-ID-17759 | MCPA - Mine Clearance Planning Agency | AF/0805/09664/MF0265 | 179156 | 70.1946 | 34.2565 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {A19D473B-6F76-4A8E-A5CF-A396EF6E6FC8} |  | Low | Comunity Centers | High | 322 | CHA | 4 |  |  | 2013-02-12 16:30 | No | Open
East | Nangarhar | Kot | Hayderkhel | {B54A23D2-CFE6-40C1-9AB4-098397174E35} | c0a8-0009-14655f7a56b-75432a02-26c-a3 | Hz-ID-18740 | MDC - Mine Detection and Dog Center | AF/0822/08919/MF0256 | 172831 | 70.6603 | 34.1831 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {B54A23D2-CFE6-40C1-9AB4-098397174E35} |  | Low | Infrastructure | Substantial | 238 | CHA | 4 |  |  | 2014-05-17 16:30 | No | Open
East | Nangarhar | Kot | Purshakhel | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} | c0a8-0009-13b837588f8-8fe1615c-1f4-36 | Hz-ID-17470 | MCPA - Mine Clearance Planning Agency | AF/0809/08916/MF0235 | 136088 | 70.5132 | 34.1008 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} |  | High with Victim | High with Victims | Substantial | 154 | CHA | 4 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2012-08-29 16:30 | No | Open
East | Nangarhar | Kot | Purshakhel | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} | c0a8-008e-1328fd11247-5c73ea50-2991-d | MF-16240 | MCPA - Mine Clearance Planning Agency | AF/0809/08916/MF0214 | 215421 | 70.52 | 34.1111 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} | , | High with Victim | High with Victims | Substantial | 225 | CHA | 4 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-08-16 16:30 | No | Open
East | Nangarhar | Kot | Purshakhel | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} | c0a8-008e-132c2fb8d1c-71487c1a-d4-21f | MF-16237 | MCPA - Mine Clearance Planning Agency | AF/0809/08916/MF0215 | 152584 | 70.514 | 34.0924 | Open | AT Only | AT Only | MineField |  | MBT Project-225 | Nangarhar Demining Project-05 |  |  |  |  | 1394 |  | {AA626E92-DCF4-4E3E-849C-95AEB3FEC94E} | , | High with Victim | High with Victims | Substantial | 184 | CHA | 4 | Yes | This area is contaminated by mine & it is huge risk for the local people. In the recent time the local people face some accident in this area. Thus the local people request for the clearance of this area. | 2011-08-18 16:30 | No | Open
East | Nangarhar | Nazyan | Fuladi Khulah | {F7939340-52F4-4B9E-A13B-29CF1ABD46DB} | c0a8-0057-12c3b806588-e307a122-19b5b- | MF-HQ-13770 | UNMACA - United Nation Mine Action Center for Afghanistan | AF/0811/00777/MF0026 | 175000 | 70.8527 | 34.0084 | Open | AP Only | AP Only | MineField | Blank | MBT Project-225 | Nangarhar Demining Project-05 |  | No |  |  | 1394 |  | {F7939340-52F4-4B9E-A13B-29CF1ABD46DB} |  | High Requested | Resettlment/Local Request | Substantial | 137 | SHA | 6 |  |  | 2009-12-05 | No | Open
South East | Paktya | Gardiz | Dawlatzi | {07F31B92-C704-49B3-9989-39E346374091} | c0a8-0057-12c3b8f810d-b39c0cd2-2447d- | MF-HQ-13816 | MCPA - Mine Clearance Planning Agency | AF/0701/07251/MF0378 | 400000 | 69.2221 | 33.5283 | Open | AP Only | AP Only | MineField |  | MBT Project-160/A | Paktya Demining Project-09/A |  |  |  |  | 1397 |  | {07F31B92-C704-49B3-9989-39E346374091} |  | High with Victim | High with Victims | Substantial | 7 | CHA | 2 |  |  | 2009-12-13 | No | Open
South East | Paktya | Gardiz | Dawlatzi | {07F31B92-C704-49B3-9989-39E346374091} | c0a8-0057-12c3b92793b-13533b06-2631f- | MF-HQ-13815 | MCPA - Mine Clearance Planning Agency | AF/0701/07251/MF0379 | 300000 | 69.225 | 33.5273 | Open | AP Only | AP Only | MineField |  | MBT Project-160/A | Paktya Demining Project-09/A |  |  |  |  | 1397 |  | {07F31B92-C704-49B3-9989-39E346374091} |  | High with Victim | High with Victims | Substantial | 4 | CHA | 2 |  |  | 2009-12-13 | No | Open
South East | Paktya | Gardiz | Dawlatzi | {07F31B92-C704-49B3-9989-39E346374091} | c0a8-0057-12c3bb0a3b4-986bb475-38e60- | MF-HQ-11151 | MCPA - Mine Clearance Planning Agency | AF/0701/07251/MF0318 | 2244 | 69.2256 | 33.5614 | Open | AP Only | AP Only | MineField |  | MBT Project-160/A | Paktya Demining Project-09/A |  |  |  |  | 1397 |  | {07F31B92-C704-49B3-9989-39E346374091} |  | High with Victim | High with Victims | Substantial | 138 | CHA | 2 |  |  | 2009-06-23 | No | Open
South East | Paktya | Gardiz | Dinarkhel | {006FFDC3-9112-4274-8278-E13150E6A542} | c0a8-0057-12c3b9d2c96-692f66cc-2d2fd- | MF-SE-311 | MCPA - Mine Clearance Planning Agency | AF/0701/07221/MF0380 | 80808 | 69.1208 | 33.6452 | Open | AP Only | AP Only | MineField |  | MBT Project-160/A | Paktya Demining Project-09/A |  |  |  |  | 1397 |  | {006FFDC3-9112-4274-8278-E13150E6A542} |  | Low | Agriculture Blocked | Substantial | 18 | CHA | 5 |  |  | 2009-09-15 | No | Open
South East | Paktya | Gardiz | Shekhan (2) | {0B55D9DD-21EE-4B00-8982-B8E1B8B82047} | c0a8-008e-131178f4ca8-e831d782-2ab3-8 | MF-HQ-12921 | MCPA - Mine Clearance Planning Agency | AF/0701/07226/MF0375 | 146655 | 69.1362 | 33.6559 | Open | AP Only | AP Only | MineField |  | MBT Project-160/A | Paktya Demining Project-09/A |  |  |  |  | 1397 |  | {0B55D9DD-21EE-4B00-8982-B8E1B8B82047} |  | Medium | Critical Infrastracture | Substantial | 258 | CHA | 3 |  |  | 2009-09-16 | No | Open
South East | Paktya | Gardiz | Shekhan (2) | {0B55D9DD-21EE-4B00-8982-B8E1B8B82047} | c0a8-008e-13117a1f695-3ffff668-2c81-4 | MF-HQ-12918 | MCPA - Mine Clearance Planning Agency | AF/0701/07226/MF0259 | 83106 | 69.1339 | 33.6565 | Open | AP Only | AP Only | MineField |  | MBT Project-160/A | Paktya Demining Project-09/A |  |  |  |  | 1397 |  | {0B55D9DD-21EE-4B00-8982-B8E1B8B82047} |  | Medium | Critical Infrastracture | Substantial | 12 | CHA | 3 |  |  | 2009-09-17 | No | Open
South East | Paktya | Gardiz | Tandan | {DCB964E7-600C-4C2A-89A3-3E061256F0AC} | c0a8-004c-1302a9f16c5-5df3390-1445-7b | MF-HQ-14175 | MCPA - Mine Clearance Planning Agency | AF/0701/07231/MF0297 | 28601 | 69.1994 | 33.76 | Open | AT Only | AT Only | MineField | Blank | MBT Project-160/A | Paktya Demining Project-09/A |  | No |  |  | 1397 | None | {DCB964E7-600C-4C2A-89A3-3E061256F0AC} |  | High Requested | Resettlment/Local Request | Substantial | 3 | CHA | 1 | Yes | As per assessment of OPS section MACCA regional office Gardez these people are in need for the exist all open MFs clearance because most of the land are Agricultural land and affected economic normal life of the residence. Form the other side several refu | 2009-06-10 | No | Open
South East | Paktya | Gardiz | Tandan | {DCB964E7-600C-4C2A-89A3-3E061256F0AC} | c0a8-0057-12c3ba85cda-9150b7f4-34064- | MF-HQ-13358 | MCPA - Mine Clearance Planning Agency | AF/0701/07231/MF0376 | 26529 | 69.1953 | 33.7582 | Open | AP Only | AP Only | MineField | Blank | MBT Project-160/A | Paktya Demining Project-09/A |  | No | 2014-06-01 | 2014-06-30 | 1397 | None | {DCB964E7-600C-4C2A-89A3-3E061256F0AC} |  | High Requested | Resettlment/Local Request | Substantial | 6 | CHA | 1 | Yes | As per assessment of OPS section MACCA regional office Gardez these people are in need for the exist all open MFs clearance because most of the land are Agricultural land and affected economic normal life of the residence. Form the other side several refu | 2009-11-01 | No | Open
South East | Paktya | Gardiz | Tandan | {DCB964E7-600C-4C2A-89A3-3E061256F0AC} | c0a8-0057-12c3ba8616c-fb8cc2b-34099-6 | MF-HQ-14177 | MCPA - Mine Clearance Planning Agency | AF/0701/07231/MF0305 | 63198 | 69.1973 | 33.7653 | Open | AP Only | AP Only | MineField | Blank | MBT Project-160/A | Paktya Demining Project-09/A |  | No | 2014-07-01 | 2014-11-25 | 1397 | None | {DCB964E7-600C-4C2A-89A3-3E061256F0AC} |  | High Requested | Resettlment/Local Request | Substantial | 8 | CHA | 1 | Yes | As per assessment of OPS section MACCA regional office Gardez these people are in need for the exist all open MFs clearance because most of the land are Agricultural land and affected economic normal life of the residence. Form the other side several refu | 2009-06-07 | No | Open
South East | Paktya | Gardiz | Tandan | {DCB964E7-600C-4C2A-89A3-3E061256F0AC} | c0a8-0057-12d5517090e-7bcc05d3-683-8b | MF-HQ-14174 | MCPA - Mine Clearance Planning Agency | AF/0701/07231/MF0296 | 59697 | 69.1959 | 33.7649 | Open | AP Only | AP Only | MineField | Blank | MBT Project-160/A | Paktya Demining Project-09/A |  | No | 2014-06-01 | 2014-09-30 | 1397 | None | {DCB964E7-600C-4C2A-89A3-3E061256F0AC} |  | High Requested | Resettlment/Local Request | Substantial | 3 | CHA | 1 | Yes | As per assessment of OPS section MACCA regional office Gardez these people are in need for the exist all open MFs clearance because most of the land are Agricultural land and affected economic normal life of the residence. Form the other side several refu | 2009-06-09 | No | Open
South East | Paktya | Gardiz | Tandan | {DCB964E7-600C-4C2A-89A3-3E061256F0AC} | c0a8-008e-130f3af35dd-ab479de4-c21-27 | MF-HQ-14176 | MCPA - Mine Clearance Planning Agency | AF/0701/07231/MF0304 | 72737 | 69.1973 | 33.7653 | Open | AP Only | AP Only | MineField | Blank | MBT Project-160/A | Paktya Demining Project-09/A |  | No |  |  | 1397 | None | {DCB964E7-600C-4C2A-89A3-3E061256F0AC} |  | High Requested | Resettlment/Local Request | Substantial | 9 | CHA | 1 | Yes | As per assessment of OPS section MACCA regional office Gardez these people are in need for the exist all open MFs clearance because most of the land are Agricultural land and affected economic normal life of the residence. Form the other side several refu | 2009-06-04 | No | Open
South East | Paktya | Gardiz | Wach Khash | {5637BFA2-791A-4C3D-B8EC-BB7BD78910DA} | c0a8-0009-145da26a6c8-51f9ddc1-9d1-85 | Hz-ID-18644 | MCPA - Mine Clearance Planning Agency | AF/0701/07230/MF0399 | 75257 | 69.17 | 33.752 | Open | AP Only | AP Only | MineField |  | MBT Project-160/A | Paktya Demining Project-09/A |  |  |  |  | 1397 |  | {5637BFA2-791A-4C3D-B8EC-BB7BD78910DA} |  | Low | Agriculture Blocked | Substantial | 97 | CHA | 5 |  |  | 2014-03-24 16:30 | No | Open
South East | Paktya | Gardiz | Wach Khash | {5637BFA2-791A-4C3D-B8EC-BB7BD78910DA} | c0a8-008e-132868c5c4f-4fdd2c2f-2d1-d0 | MF-15767 | MCPA - Mine Clearance Planning Agency | AF/0701/07230/MF0387 | 50517 | 69.194 | 33.7609 | Open | Mixed | Mixed AP UXO | MineField | Blank | MBT Project-160/A | Paktya Demining Project-09/A |  | No | 2014-06-01 | 2014-08-31 | 1397 | None | {5637BFA2-791A-4C3D-B8EC-BB7BD78910DA} |  | High Requested | Resettlment/Local Request | Substantial | 4 | CHA | 1 | Yes | As per assessment of OPS section MACCA regional office Gardez these people are in need for the exist all open MFs clearance because most of the land are Agricultural land and affected economic normal life of the residence. Form the other side several refu | 2011-01-09 16:30 | No | Open
South East | Paktya | Ahmad Abad | Ata'i Kala | {650F286F-5537-491F-88F3-EADF85468B9C} | c0a8-0009-143cd6c40dc-39bc1509-2d26-6 | Hz-ID-18404 | MCPA - Mine Clearance Planning Agency | AF/0722/08431/MF0102 | 12106 | 69.3445 | 33.7061 | Open | AT Only | AT Only | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {650F286F-5537-491F-88F3-EADF85468B9C} |  | Low | Critical Infrastracture | Substantial | 165 | CHA | 4 |  |  | 2013-12-09 16:30 | No | Open
South East | Paktya | Ahmad Abad | Ata'i Kala | {650F286F-5537-491F-88F3-EADF85468B9C} | c0a8-0009-143cd70254e-a646a66b-2d45-7 | Hz-ID-18405 | MCPA - Mine Clearance Planning Agency | AF/0722/08431/MF0103 | 31297 | 69.3515 | 33.7256 | Open | AT Only | AT Only | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {650F286F-5537-491F-88F3-EADF85468B9C} |  | Low | Critical Infrastracture | Substantial | 129 | CHA | 4 |  |  | 2013-12-14 16:30 | No | Open
South East | Paktya | Ahmad Abad | Babakaray | {7FC96457-DC16-4FDD-BDE0-9CE0F4CF34D8} | c0a8-0009-143cddbbc81-e09ad4bc-2f35-7 | Hz-ID-18407 | MCPA - Mine Clearance Planning Agency | AF/0722/08462/SpotUXO0001 | 100 | 69.4096 | 33.8157 | Open | UXO Only | UXO Only | Spot ERW |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {7FC96457-DC16-4FDD-BDE0-9CE0F4CF34D8} |  | Low | Small Hazards | Substantial | 16 | CHA | 5 |  |  | 2013-12-14 16:30 | No | Open
South East | Paktya | Ahmad Abad | Melan (Do Abah) | {C450C2DC-8676-45E4-8F93-8717697437AE} | c0a8-0009-145118ad5ee-2212259a-137-9e | Hz-ID-18564 | MCPA - Mine Clearance Planning Agency | AF/0722/00046/BF0105 | 186 | 69.3085 | 33.6645 | Open | UXO Only | UXO Only | BF |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {C450C2DC-8676-45E4-8F93-8717697437AE} |  | High | Water Blocked | Substantial | 1933 | CHA | 3 |  |  | 2014-02-24 16:30 | No | Open
South East | Paktya | Ahmad Abad | Zundikhel | {B30A10D2-692E-423C-B41C-3F401695E351} | c0a8-0009-143700d8ccf-dab3a59c-2b8e-e | Hz-ID-18308 | MCPA - Mine Clearance Planning Agency | AF/0722/08430/MF0101 | 25637 | 69.3255 | 33.753 | Open | AT Only | AT Only | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {B30A10D2-692E-423C-B41C-3F401695E351} |  | Medium | Critical Infrastracture | Substantial | 146 | CHA | 3 |  |  | 2013-10-23 16:30 | No | Open
South East | Paktya | Ahmad Abad | Zundikhel | {B30A10D2-692E-423C-B41C-3F401695E351} | c0a8-0009-143cdd6f725-80864bed-2f1c-d | Hz-ID-18406 | MCPA - Mine Clearance Planning Agency | AF/0722/08430/MF0104 | 32176 | 69.3283 | 33.7107 | Open | AT Only | AT Only | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {B30A10D2-692E-423C-B41C-3F401695E351} |  | Low | Agriculture Blocked | Substantial | 53 | CHA | 5 |  |  | 2013-12-16 16:30 | No | Open
South East | Paktya | Gardiz | Ghelgay (2) | {A1873125-462C-46A9-86C1-73A9983CF828} | c0a8-0057-12c3b6c7322-4363476f-b0df-5 | MF-HQ-13371 | MCPA - Mine Clearance Planning Agency | AF/0701/08349/MF0373 | 88182 | 69.3506 | 33.5019 | Open | AP Only | AP Only | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {A1873125-462C-46A9-86C1-73A9983CF828} |  | High Requested | Resettlment/Local Request | Substantial | 106 | CHA | 1 | Yes | By the clearing of this hazard,releated community will be colse. | 2009-09-08 | No | Open
South East | Paktya | Gardiz | Khawajarkhel | {B5C2A179-F1C5-4311-81A4-74ACB0B0FBEF} | c0a8-0057-12c3b92a384-f486dc50-264d5- | MF-SE-262 | MCPA - Mine Clearance Planning Agency | AF/0701/08382/MF0263 | 139785 | 69.3386 | 33.618 | Open | AT Only | AT Only | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {B5C2A179-F1C5-4311-81A4-74ACB0B0FBEF} |  | Low | Agriculture Blocked | Substantial | 94 | CHA | 5 |  |  | 2008-07-30 16:30 | No | Open
South East | Paktya | Gardiz | Mamray | {676FC37B-1A06-47E6-A4A5-F0C108396536} | c0a8-0009-145da22ad20-9222598c-8d4-ff | Hz-ID-18643 | MCPA - Mine Clearance Planning Agency | AF/0701/07219/MF0398 | 87518 | 69.1799 | 33.538 | Open | AT Only | AT Only | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {676FC37B-1A06-47E6-A4A5-F0C108396536} |  | Low | Critical Infrastracture | Substantial | 181 | CHA | 4 |  |  | 2014-03-27 16:30 | No | Open
South East | Paktya | Gardiz | Melan | {70463A88-DAB4-4A2E-B763-A404005A3724} | c0a8-004c-1302a9e3f3f-2a0c776d-142f-a | MF-HQ-12922 | MCPA - Mine Clearance Planning Agency | AF/0701/07280/MF0264 | 95622 | 69.3578 | 33.608 | Open | AT Only | AT Only | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {70463A88-DAB4-4A2E-B763-A404005A3724} |  | High with Victim | High with Victims | Substantial | 204 | CHA | 2 |  |  | 2009-09-02 | No | Open
South East | Paktya | Gardiz | Melan | {70463A88-DAB4-4A2E-B763-A404005A3724} | c0a8-00c9-12fde9dd28b-66b66afe-2e0-95 | MF-SE-263 | MCPA - Mine Clearance Planning Agency | AF/0701/07280/MF0364 | 81731 | 69.3506 | 33.6088 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {70463A88-DAB4-4A2E-B763-A404005A3724} |  | High with Victim | High with Victims | Substantial | 176 | CHA | 2 |  |  | 2009-08-10 | No | Open
South East | Paktya | Gardiz | Melan | {70463A88-DAB4-4A2E-B763-A404005A3724} | c0a8-00c9-12fdea0c205-c0b21e3d-362-3a | MF-HQ-12911 | MCPA - Mine Clearance Planning Agency | AF/0701/07280/MF0366 | 156515 | 69.3633 | 33.6131 | Open | Mixed Mine | Mixed Mine | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {70463A88-DAB4-4A2E-B763-A404005A3724} |  | High with Victim | High with Victims | Substantial | 43 | CHA | 2 |  |  | 2009-08-29 | No | Open
South East | Paktya | Gardiz | Rahmatkhel | {4CD1A213-2E82-407D-85C4-03EE170CF35C} | c0a8-0009-145da1be0b1-f0e8d1ff-8a7-ef | Hz-ID-18642 | MCPA - Mine Clearance Planning Agency | AF/0701/07223/MF0397 | 15367 | 69.1385 | 33.5422 | Open | AT Only | AT Only | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {4CD1A213-2E82-407D-85C4-03EE170CF35C} |  | Low | Agriculture Blocked | Substantial | 359 | CHA | 4 |  |  | 2014-03-18 16:30 | No | Open
South East | Paktya | Gardiz | Spina Kala | {2DD3D6C4-BA09-40C9-BDD9-0A0B940D6D39} | c0a8-0057-12c3ba01a74-86c5a9c9-2f00e- | MF-HQ-12958 | MCPA - Mine Clearance Planning Agency | AF/0701/07274/MF0348 | 27066 | 69.2236 | 33.6895 | Open | AT Only | AT Only | MineField |  | MBT Project-051 | Paktya Demining Project-02 AT |  |  |  |  | 1394 |  | {2DD3D6C4-BA09-40C9-BDD9-0A0B940D6D39} |  | Low | Agriculture Blocked | Substantial | 24 | CHA | 5 |  |  | 2009-08-31 | No | Open

## Calculation Tables
Table 1 | Clearance Type and % of application of different tool box
Hazard Type | MCT | MDS | MDU
AP only | 80% | 10% | 10%
AT & AT-mix | 40% | 0% | 60%
Battlefields | 98% | 0% | 2% |  | 0
Table 2 | Funding requiremennt per year |  |  |  |  | Table 2 | Funding requiremennt per year
Year | Fund required (including equipment) | Reduction in fund per year | % of reduction |  |  | Year | Fund required (including equipment) | Reduction in fund per year | % of reduction
1392 (2013) | 55.5941 |  |  |  |  | 1392 (2013) | 55.5941
1393 (2014) | 70.9618 | -15.3677 | -27.64% |  |  | 1393 (2014) | 70.9618 | -15.3677
1394 (2015) | 64.7736 | 6.1882 | 8.72% |  |  | 1394 (2015) | 64.7736 | 6.1882 | 8.72%
1395 (2016) | 59.1826 | 5.5909 | 8.632% |  |  | 1395 (2016) | 59.1826 | 5.5909 | 8.632%
1396 (2017) | 54.209 | 4.9736 | 8.404% |  |  | 1396 (2017) | 54.209 | 4.9736 | 8.404%
1397 (2018) | 49.8214 | 4.3877 | 8.094% |  |  | 1397 (2018) | 49.8214 | 4.3877 | 8.094%
1398 (2019) | 45.9323 | 3.8891 | 7.806% |  |  | 1398 (2019) | 45.9323 | 3.8891 | 7.806%
1399 (2020) | 42.2681 | 3.6642 | 7.977% |  |  | 1399 (2020) | 42.2681 | 3.6642 | 7.977%
1400 (2021) | 38.6638 | 3.6044 | 8.527% |  |  | 1400 (2021) | 38.6638 | 3.6044 | 8.527%
1401 (2022) | 34.964 | 3.6997 | 9.569% |  |  | 1401 (2022) | 34.964 | 3.6997 | 9.569%
Total | 516.3708 |  |  |  |  | Total | 516.3708
Note: The funding for clearance in 1393, is considered the available funding in 1392 and then 8-9% reduction till 1401 and 10% in 1402.
Table 3 | Clearance Target per year
Year | AP only | AT & AT mix | BF | Total | 1392 Target
1392 (2013) | 30525580 | 31020874 | 8889843 | 70436297 | 78946025
1393 (2014) | 40296871 | 28976731 | 18951176.5 | 88224778.5
1394 (2015) | 27592374 | 39688178 | 8110768 | 75391320
1395 (2016) | 25562610 | 32234319 | 3891973 | 61688902
1396 (2017) | 32750186 | 21806544 | 946928 | 55503658
1397 (2018) | 21661494.5 | 32368472 | 1730042 | 55760008.5
1398 (2019) | 9316778 | 46605968 | 1283432 | 57206178
1399 (2020) | 14544478 | 30715718 | 657653 | 45917849
1400 (2021) | 11647356 | 29408380 | 1060000 | 42115736
1401 (2022) | 1459719 | 41442917 | 0 | 42902636
Total | 215357446.5 | 334268101 | 45521815.5 | 595147363
Table No.4 | No. of Team per year for AP only
Year | AP Actual Area (sq km) | Reduction (10%) | Team Month (by MCT) | Team Month (by MDS) | Team Month (by MDUs) | Total Team Month | No. of Team in a Year for AP hazards
1392 (2013) | 30.5256 | 27.473 | 2024.3279 | 161.606 | 549.4604 | 2735.3944 | 227.9495
1393 (2014) | 40.2969 | 36.2672 | 2901.3747 | 213.3364 | 362.6718 | 3477.3829 | 289.7819
1394 (2015) | 27.5924 | 24.8331 | 1986.6509 | 146.0773 | 248.3314 | 2381.0596 | 198.4216
1395 (2016) | 25.5626 | 23.0063 | 1840.5079 | 135.3315 | 230.0635 | 2205.9029 | 183.8252
1396 (2017) | 32.7502 | 29.4752 | 2358.0134 | 173.3833 | 294.7517 | 2826.1484 | 235.5124
1397 (2018) | 21.6615 | 19.4953 | 1559.6276 | 114.6785 | 194.9535 | 1869.2596 | 155.7716
1398 (2019) | 9.3168 | 8.3851 | 670.808 | 49.3241 | 83.851 | 803.9831 | 66.9986
1399 (2020) | 14.5445 | 13.09 | 1047.2024 | 77.0002 | 130.9003 | 1255.1029 | 104.5919
1400 (2021) | 11.6474 | 10.4826 | 838.6096 | 61.6625 | 104.8262 | 1005.0983 | 83.7582
1401 (2022) | 1.4597 | 1.3137 | 105.0998 | 7.7279 | 13.1375 | 125.9652 | 10.4971
Total | 215.3574
Cell D39 description: AP MF in C39 divided by the manual team average clearance rate in a month i.e. 10,000 sqm/month (changed to sqkm 10,000/1000000=0.01) muliplied by the maual application percentage for AP MF which is 80% (0.80)
Table No. 5 | Costing for AP Hazards (including equipment & inflation cost)
Year | Cost of MCT (12500$/month) | Cost of MDS (5000$/month) | Cost of MDUs (8000$/month) | Total cost (Million dollar) | Equipment/explosive cost (current cost) | Equipment inflation cost (2% annually) | Inflation cost of Clearance (4% annually) | Total cost for AP hazards (mln dollar)
1392 (2013) | 25.3041 | 0.80803 | 4.3957 | 30.5078 | 3.6485 | 0.07297 | 1.2203 | 35.4496
1393 (2014) | 36.2672 | 1.0667 | 2.9014 | 40.2352 | 3.6485 | 0.14594 | 3.2188 | 47.2485
1394 (2015) | 24.8331 | 0.73039 | 1.9867 | 27.5502 | 3.6485 | 0.21891 | 3.306 | 34.7236
1395 (2016) | 23.0063 | 0.67666 | 1.8405 | 25.5235 | 3.6485 | 0.29188 | 4.0838 | 33.5477
1396 (2017) | 29.4752 | 0.86692 | 2.358 | 32.7001 |  |  | 6.54 | 39.2401
1397 (2018) | 19.4953 | 0.57339 | 1.5596 | 21.6284 |  |  | 5.1908 | 26.8192
1398 (2019) | 8.3851 | 0.24662 | 0.67081 | 9.3025 |  |  | 2.6047 | 11.9072
1399 (2020) | 13.09 | 0.385 | 1.0472 | 14.5222 |  |  | 4.6471 | 19.1693
1400 (2021) | 10.4826 | 0.30831 | 0.83861 | 11.6295 |  |  | 4.1866 | 15.8162
1401 (2022) | 1.3137 | 0.03864 | 0.1051 | 1.4575 |  |  | 0.58299 | 2.0405
Total | 191.6528 | 5.7006 | 17.7036 | 215.057 | 14.594 | 0.7297 | 35.5812 | 265.9619
Cell B55 description: Manual team month in table 4 (D39) muliplied by 12,500 $ "running cost of a manual team in a month" divided by 1,000,000 to change it to million dollar.
Table No.6 | No. of Team per year for AT & AT-mix
Year | AT & AT-mix actual area (sq km) | Reduction (10%) | Team month (by MCT) | Team month (by MDS) | Team month (by MDUs+DT) | Total team month | No. of team in a year for AT hazards
1392 (2013) | 31.0209 | 27.9188 | 885.0073 | 261.7386 | 310.2087 | 1456.9547 | 121.4129
1393 (2014) | 28.9767 |  | 1068.1618 |  | 386.3564 | 1454.5183 | 121.2099
1394 (2015) | 39.6882 |  | 1463.0152 |  | 529.1757 | 1992.1909 | 166.0159
1395 (2016) | 32.2343 |  | 1188.2455 |  | 429.7909 | 1618.0364 | 134.8364
1396 (2017) | 21.8065 |  | 803.8491 |  | 290.7539 | 1094.603 | 91.2169
1397 (2018) | 32.3685 |  | 1193.1907 |  | 431.5796 | 1624.7704 | 135.3975
1398 (2019) | 46.606 |  | 1718.0239 |  | 621.4129 | 2339.4368 | 194.9531
1399 (2020) | 30.7157 |  | 1132.2657 |  | 409.5429 | 1541.8086 | 128.484
1400 (2021) | 29.4084 |  | 1084.0736 |  | 392.1117 | 1476.1853 | 123.0154
1401 (2022) | 41.4429 |  | 1527.6997 |  | 552.5722 | 2080.2719 | 173.356
Total | 334.2681
Cell D71 description: AT MF in B71 divided by the manual team average clearance rate in a month i.e. 17,000 sqm/month (changed to sqkm 17,000/1,000,000=0.017) muliplied by the maual application percentage for AP MF which is 40% (0.4)
Note: D70 to D79 cells added with F70 to F79 because each MDU team need one DT teams
Table No. 7 | Costing for AT & AT-mix hazards clearance
Year | Cost of MCT ($12,500/month) | Cost of MDS ($5,000/month) | Cost of MDUs ($8,000/month) | Total cost (mln dollar) | Equipment cost | Inflation Cost of Equipment (2% annually) | Inflation Cost of Clearance (4% annually) | Total cost
1392 (2013) | 11.0626 | 1.3087 | 2.4817 | 14.853 | 3.6485 | 0.07297 | 0.59412 | 19.1685
1393 (2014) | 13.352 |  | 3.0909 | 16.4429 | 3.6485 | 0.14594 | 1.3154 | 21.5527
1394 (2015) | 18.2877 |  | 4.2334 | 22.5211 | 3.6485 | 0.21891 | 2.7025 | 29.091
1395 (2016) | 14.8531 |  | 3.4383 | 18.2914 | 3.6485 | 0.29188 | 2.9266 | 25.1584
1396 (2017) | 10.0481 |  | 2.326 | 12.3741 |  |  | 2.4748 | 14.849
1397 (2018) | 14.9149 |  | 3.4526 | 18.3675 |  |  | 4.4082 | 22.7757
1398 (2019) | 21.4753 |  | 4.9713 | 26.4466 |  |  | 7.405 | 33.8517
1399 (2020) | 14.1533 |  | 3.2763 | 17.4297 |  |  | 5.5775 | 23.0072
1400 (2021) | 13.5509 |  | 3.1369 | 16.6878 |  |  | 6.0076 | 22.6954
1401 (2022) | 19.0962 |  | 4.4206 | 23.5168 |  |  | 9.4067 | 32.9236
Total Cost | 150.7942 | 1.3087 | 34.828 | 186.9309 | 14.594 | 0.7297 | 42.8186 | 245.0732
Cell B86 description: Manual team month in table 6 (D70) muliplied by 12500 $ "running cost of a manual team in a month" divided by 1,000,000 to change it to million dollar.
Table No. 8 | No. of Team per year for BF
Year | BF actual area (sqm) | BF Area (sqm) with 10% area reduction | Team month (by MCT) | Team month (by MDUs) | Total team month | No. of team for BF hazards
1392 (2013) | 8.8898 | 8.0009 | 71.2804 | 5.9266 | 77.2069 | 6.4339
1393 (2014) | 18.9512 | 17.0561 | 151.954 | 12.6341 | 164.5881 | 13.7157
1394 (2015) | 8.1108 | 7.2997 | 65.0336 | 5.4072 | 70.4408 | 5.8701
1395 (2016) | 3.892 | 3.5028 | 31.2065 | 2.5946 | 33.8012 | 2.8168
1396 (2017) | 0.94693 | 0.85224 | 7.5926 | 0.63129 | 8.2239 | 0.68533
1397 (2018) | 1.73 | 1.557 | 13.8718 | 1.1534 | 15.0252 | 1.2521
1398 (2019) | 1.2834 | 1.1551 | 10.2908 | 0.85562 | 11.1464 | 0.92887
1399 (2020) | 0.65765 | 0.59189 | 5.2732 | 0.43844 | 5.7116 | 0.47597
1400 (2021) | 1.06 | 0.954 | 8.4993 | 0.70667 | 9.2059 | 0.76716
1401 (2022) | 0 | 0 | 0 | 0 | 0 | 0
Total | 45.5218 | 40.9696 | 365.0022 | 30.3479 | 395.3501 | 32.9458
Cell D101 calculation is the BF area divided by 110,000 sqm manual clearance per month for BF surface and sub-surface (changed to sqkm 0.11) and multiplied by the manual clearancne application for BF i.e. 98% (0.98) ref. table 1
Table No. 9 | Costing for Battelfield
Year | Cost of MCTs (12500$/month) | Cost of MDUs (8000$/month) | Total cost for BF clearance (mln dollar) | Inflation cost | Total cost
1392 (2013) | 0.891 | 0.047412 | 0.93842 | 0.037537 | 0.97595
1393 (2014) | 1.8994 | 0.10107 | 2.0005 | 0.16004 | 2.1605
1394 (2015) | 0.81292 | 0.043257 | 0.85618 | 0.10274 | 0.95892
1395 (2016) | 0.39008 | 0.020757 | 0.41084 | 0.065734 | 0.47657
1396 (2017) | 0.094908 | 0.0050503 | 0.099958 | 0.019992 | 0.11995
1397 (2018) | 0.1734 | 0.0092269 | 0.18262 | 0.04383 | 0.22645
1398 (2019) | 0.12863 | 0.006845 | 0.13548 | 0.037934 | 0.17341
1399 (2020) | 0.065915 | 0.0035075 | 0.069422 | 0.022215 | 0.091637
1400 (2021) | 0.10624 | 0.0056533 | 0.11189 | 0.040282 | 0.15218
1401 (2022) | 0 | 0 | 0 | 0 | 0
Total | 4.5625 | 0.24278 | 4.8053 | 0.5303 | 5.3356
Table No. 10 | Total cost for clearance of AP, AT, BF, EOD, survey including Coordination and UNMAS support
Year | AP cost | AT cost | BF cost | Total Clearance cost (including inflation) | Survey and EOD cost | MRE cost | MACCA coordination cost | UN project office cost | Inflation cost (4% per year) | Sub Total | Total cost
1392 (2013) | 35.4496 | 19.1685 | 0.97595 | 55.5941 | 2.5 | 0.35 | 7.2 | 2.1 | 0.486 | 12.636 | 68.2301
1393 (2014) | 47.2485 | 21.5527 | 2.1605 | 70.9618 | 2.5 | 0.35 | 5.5 | 1.9 | 0.82 | 11.07 | 82.0318
1394 (2015) | 34.7236 | 29.091 | 0.95892 | 64.7736 | 1 | 0.35 | 5.3 | 1.5 | 0.978 | 9.128 | 73.9016
1395 (2016) | 33.5477 | 25.1584 | 0.47657 | 59.1826 | 0.5 | 0.25 | 5.1 | 1.4 | 1.16 | 8.41 | 67.5926
1396 (2017) | 39.2401 | 14.849 | 0.11995 | 54.209 | 0.5 | 0.25 | 4.8 | 1.3 | 1.37 | 8.22 | 62.429
1397 (2018) | 26.8192 | 22.7757 | 0.22645 | 49.8214 | 0.5 | 0.25 | 4.5 | 1 | 1.5 | 7.75 | 57.5714
1398 (2019) | 11.9072 | 33.8517 | 0.17341 | 45.9323 | 0.5 | 0.1 | 4 | 1 | 1.568 | 7.168 | 53.1003
1399 (2020) | 19.1693 | 23.0072 | 0.091637 | 42.2681 | 0.5 | 0.1 | 3 | 1 | 1.472 | 6.072 | 48.3401
1400 (2021) | 15.8162 | 22.6954 | 0.15218 | 38.6638 | 0.5 | 0.1 | 3 | 1 | 1.656 | 6.256 | 44.9198
1401 (2022) | 2.0405 | 32.9236 | 0 | 34.964 | 0.5 | 0.1 | 2 | 1 | 1.44 | 5.04 | 40.004
Total cost | 265.9619 | 245.0732 | 5.3356 | 516.3708 | 9.5 | 2.2 | 44.4 | 13.2 | 12.45 | 81.75 | 598.1208
Table 11 | Cost per square meter clearance
| AP | AT | BF | Overall avrg. Cost/Sqm
Cost | 265.9619 | 245.0732 | 5.3356
Ares sqkm | 215.3574 | 334.2681 | 45.5218
Cost per sqm | 1.235 | 0.73316 | 0.11721 | 0.86764
Table No. 12 | No of teams for survey per year
Year | No of team for Survey/EOD
1392 (2013) | 72
1393 (2014) | 27
1394 (2015) | 35
1395 (2016) | 35
1396 (2017) | 30
1397 (2018) | 30
1398 (2019) | 20
1399 (2020) | 20
1400 (2021) | 20
1401 (2022) | 15
Total Cost | 304
NB: Nation wide non-technical survey started in 1391 and planned to survey all impacted and non-impacted communities in 2 years. Following the completion of the survey 3 team per region will be kept to update the survey regularly and respond to assessment
Table 13 | Number of Team per year for AP, AT & BF
Year | Team for AP | Team for AT | Team for BF | Team for Survey/EOD | Total no of team
1392 (2013) | 227.9495 | 121.4129 | 6.4339 | 72 | 427.7963
1393 (2014) | 289.7819 | 121.2099 | 13.7157 | 27 | 451.7074
1394 (2015) | 198.4216 | 166.0159 | 5.8701 | 35 | 405.3076
1395 (2016) | 183.8252 | 134.8364 | 2.8168 | 35 | 356.4784
1396 (2017) | 235.5124 | 91.2169 | 0.68533 | 30 | 357.4146
1397 (2018) | 155.7716 | 135.3975 | 1.2521 | 30 | 322.4213
1398 (2019) | 66.9986 | 194.9531 | 0.92887 | 20 | 282.8805
1399 (2020) | 104.5919 | 128.484 | 0.47597 | 20 | 253.5519
1400 (2021) | 83.7582 | 123.0154 | 0.76716 | 20 | 227.5408
1401 (2022) | 10.4971 | 173.356 | 0 | 15 | 198.8531
Total | 1557.1081 | 1389.898 | 32.9458 | 304 | 3283.952
Table 13 | Number of Team per year
Year | MCT (Team month) | MCT (per year) | MDS (Team month) | MDS (per year) | MDU (Team month) | MDU (per year) | Survey/EOD (per year) | Total team
1392 (2013) | 2980.6156 | 248.3846 | 423.3446 | 35.2787 | 865.5957 | 72.133 | 72 | 427.7963
1393 (2014) | 4121.4905 | 343.4575 | 213.3364 | 17.778 | 761.6624 | 63.4719 | 27 | 451.7074
1394 (2015) | 3514.6997 | 292.8916 | 146.0773 | 12.1731 | 782.9143 | 65.2429 | 35 | 405.3076
1395 (2016) | 3059.96 | 254.9967 | 135.3315 | 11.2776 | 662.4491 | 55.2041 | 35 | 356.4784
1396 (2017) | 3169.4551 | 264.1213 | 173.3833 | 14.4486 | 586.1369 | 48.8447 | 30 | 357.4146
1397 (2018) | 2766.6901 | 230.5575 | 114.6785 | 9.5565 | 627.6864 | 52.3072 | 30 | 322.4213
1398 (2019) | 2399.1227 | 199.9269 | 49.3241 | 4.1103 | 706.1195 | 58.8433 | 20 | 282.8805
1399 (2020) | 2184.7413 | 182.0618 | 77.0002 | 6.4167 | 540.8816 | 45.0735 | 20 | 253.5519
1400 (2021) | 1931.1825 | 160.9319 | 61.6625 | 5.1385 | 497.6446 | 41.4704 | 20 | 227.5408
1401 (2022) | 1632.7995 | 136.0666 | 7.7279 | 0.64399 | 565.7097 | 47.1425 | 15 | 198.8531
Total | 27760.757 | 2313.3964 | 1401.8663 | 116.8222 | 6596.8002 | 549.7334 | 304 | 3283.952
Table No. 14 | Non-expendable equipment replacement and new machine cost
Non Expendable Equipment for 500 Teams
Item Name | QTY required for 1 DT | QTY required for 500 DTs | Unit cost (US $) | Total Cost (US $)
F3 Mine detector | 11 | 5500 | 3236 | 17.798
SD 450 (PPE Apron) | 10 | 5000 | 550 | 2.75
SDV (PPE Vest) | 4 | 2000 | 550 | 1.1
VHF Radio | 4 | 2000 | 400 | 0.8
Soft Skin Vehicle | 2 | 1000 | 30000 | 30
Equipment Replacement in 1st Year
Item Name | Replacment %age | Replacment QTY | Unit Cost (US $) | Total Cost (US $)
F3 Mine detector | 10% | 550 | 3236 | 1.7798
SD 450 (PPE Apron) | 10% | 500 | 550 | 0.275
SDV (PPE Vest) | 10% | 200 | 550 | 0.11
Soft Skin Vehicle | 30% | 300 | 30000 | 9
Total |  |  |  | 11.1648
Equipment Replacement in 2nd Year
Items Name | Replacment %age | Replacment QTY | Unit Cost (US $) | Total Cost (US $)
F3 Mine detector | 15% | 825 | 3226 | 2.6614
SD 450 (PPE Apron) | 15% | 750 | 550 | 0.4125
SDV (PPE Vest) | 15% | 300 | 550 | 0.165
VHF Radio | 10% | 200 | 400 | 0.08
Total |  |  |  | 3.319
Equipment Replacement in 3rd Year
Items Name | Replacment %age | Replacment QTY | Unit cost (US $) | Total cost (US $)
F3 Mine detector | 20% | 1100 | 3226 | 3.5486
SD 450 (PPE Apron) | 20% | 1000 | 550 | 0.55
SDV (PPE Vest) | 20% | 400 | 550 | 0.22
VHF Radio | 10% | 200 | 400 | 0.08
Total |  |  |  | 4.3986
Equipment Replacement in 4th Year
Items Name | Replacment %age | Replacment QTY | Unit Cost (US $) | Total Cost (US $)
F3 Mine detector | 15% | 825 | 3226 | 2.6614
SD 450 (PPE Apron) | 15% | 750 | 550 | 0.4125
SDV (PPE Vest) | 15% | 300 | 550 | 0.165
VHF Radio | 10% | 200 | 400 | 0.08
Total |  |  |  | 3.319
Explosive Cost
Items Name | Unit cost $ | 1 DT expense/year | For 7 years | Total cost
PE3A (Kg) | 7 | 19.63 | 68705 | 0.48094
Safety Fuse (Roll 250 m) | 1125 | 82.4 | 288400 | 1.2978
Detonating Cord (Roll 250m) | 1000 | 47 | 164500 | 0.658
Plain (pcs) | 2 | 50 | 175000 | 0.35
Total |  |  |  | 2.7867
Machinery cost
New Machine | No | Cost of 1 Machine | Total Cost (3 Machine)
New machine | 3 | 400000 | 1.2
Replacment | 0 |  | 3
Total |  |  | 4.2
Table 15: Ottawa Ranking
Ottawa Ranking | Number of AP MF | Area of AP MF (sq km) | Number of AT MF | Area of AT MF (sq km) | Number of BF | Area of BF (sq km) | Total no of hazards | Area (sq km)
1 | 403 | 22.42 | 184 | 24.4 | 44 | 12.96 | 631 | 59.78
2 | 369 | 27.8 | 268 | 84.9 | 70 | 10.6 | 707 | 123.3
3 | 461 | 23.62 | 311 | 50.8 | 137 | 15.7 | 909 | 90.12
4 | 402 | 26.6 | 289 | 59.2 | 8 | 3.6 | 699 | 89.4
5 | 1824 | 107.8 | 633 | 115.4 | 42 | 6 | 2499 | 229.2
6 | 56 | 2.4 | - | - | 1 | 0.9 | 58 | 3.3
Total | 3515 | 210.64 | 1685 | 334.7 | 302 | 49.76 | 5503 | 595.1
Table 16: Projects per region
Region | No of Projects | Hazards | AP MF (Sq km) | AT MF (Sq km) | BF (Sq km) | Total Contamination (sq km)
CA | 109 | 1979 | 86.67 | 64.055 | 6.82 | 157.545
EA | 8 | 319 | 11.18 | 16.52 | 7.98 | 35.68
NA | 26 | 583 | 17.5 | 3.4 | 2.23 | 23.13
NE | 39 | 1212 | 57.77 | 0.92 | 6.19 | 64.88
SA | 47 | 508 | 17.47 | 126.68 | 12.34 | 156.49
SE | 53 | 537 | 14.11 | 48.95 | 3.16 | 66.22
WA | 24 | 369 | 5.96 | 74.11 | 11.05 | 91.12
Total | 306 | 5507 | 210.66 | 334.635 | 49.77 | 595.065
Divice Type | No Hazards | Area (sqm)
AP and AP/ERW | 3289 | 210.66
AT,AT/AP, AT/ERW | 1527 | 334.635
ERW | 242 | 49.77
Total | 5058 | 595.065
Note on C100: mohammad.wakil: should we consider 10% reduction in BF??

## New Rates
Final monthly productivity rates as per recent 12 months (Oct 2012 - Sep 2013) achievement
Hazard Device Type | Team Type | MBT Extension Target (sqm) | Recommended by Ips (review team) | Current Rates
a | b | c | g | h
AP | DT | 8000 | 9500 | 10000
| MDS | 12000 | 17000 | 17000
| MDU | 13000 | 10000 | 10000
AT | DT | 8000 | 17000 | 17000
| MDS | 12000 | 16000 | 16000
| MDU | 30000 | 27000 | 45000
ERW | DT | 100000 | 110000 | 110000
| MDS | 0
| MDU | 15000 | 27000 | 27001
Note: Based on trail on FEL, repping summary report we considered 45000 sqm average productivity rate for MDU in AT sites.
Table No. 10 | Total cost for clearance of AP, AT, BF, EOD, survey including Coordination and UNMAS support
Total Clearance cost (including inflation) | Survey and EOD cost | MRE cost | MACCA coordination cost | UN project office cost | Inflation cost (4% per year) | Sub Total | Total cost
64 | 3.456 | 0.35 | 6 | 4 | 0.55224 | 14.3582 | 78.3582
58.24 | 1.008 | 0.35 | 6 | 3 | 0.82864 | 11.1866 | 69.4266
52.998 | 1.008 | 0.35 | 6 | 3 | 1.243 | 11.601 | 64.599
48.228 | 1.008 | 0.25 | 5 | 2 | 1.3213 | 9.5793 | 57.8073
43.887 | 1.008 | 0.25 | 5 | 2 | 1.6516 | 9.9096 | 53.7966
39.938 | 1.008 | 0.25 | 4 | 1 | 1.5019 | 7.7599 | 47.6979
36.39 | 1.008 | 0.1 | 4 | 1 | 1.7102 | 7.8182 | 44.2082
33.11 | 1.008 | 0.1 | 3 | 1 | 1.6346 | 6.7426 | 39.8526
30.137 | 0.576 | 0.1 | 3 | 1 | 1.6834 | 6.3594 | 36.4964
27.425 | 0.432 | 0.1 | 2 | 1 | 1.4128 | 4.9448 | 32.3698
434.353 | 11.52 | 2.2 | 44 | 19 | 13.5396 | 90.2596 | 524.6126

## Milestone
Milestone
Milestone |  | 1392 (2013) | 1393 (2014) | 1394 (2015) | 1395 (2016) | 1396 (2017) | 1397 (2018) | 1398 (2019) | 1399 (2020) | 1400 (2021) | 1401 (2022)
No of hazards removed | AP | 730 | 443 | 518 | 484 | 422 | 251 | 125 | 104 | 162 | 10
| AT | 276 | 131 | 186 | 160 | 71 | 190 | 150 | 101 | 166 | 76
| BF | 28 | 24 | 85 | 24 | 9 | 14 | 13 | 1 | 3 | 0
| Total | 1034 | 598 | 789 | 668 | 502 | 455 | 288 | 206 | 331 | 86
Area released | AP | 31.88 | 29.5 | 27.592 | 25.562 | 32.75 | 21.661 | 9.316 | 14.544 | 11.647 | 1.459
| AT | 34.8 | 39.1 | 39.688 | 32.234 | 21.8 | 32.368 | 46.605 | 30.715 | 29.408 | 41.442
| BF | 12.47 | 15.2 | 8.11 | 3.891 | 0.946 | 1.73 | 1.283 | 0.657 | 1.06 | 0
| Total | 79.15 | 83.8 | 75.39 | 61.687 | 55.496 | 55.759 | 57.204 | 45.916 | 42.115 | 42.901
Number of communities declared impact free |  | 313 | 352 | 310 | 214 | 161 | 145 | 146 | 70 | 196 | 42
Number of districts declared impact free |  | 20 | 41 | 68 | 39 | 16 | 22 | 18 | 5 | 16 | 40
Number of provinces declared impact free |  | 0 | 2 | 4 | 4 | 4 | 5 | 3 | 0 | 7 | 6
Number of impacted communities surveyed |  | 549 | Small survey and EOD capacity conducting periodic Confirmation Assessment of recorded hazards, assessing new requests for mine clearance, conducting assessment for large-scale development projects and response spot ERW tasks.
Number of non impacted communities surveyed |  | 10192
Number of impacted communities VbV searched |  | 907
Number of Non impacted communities VbV searched |  | 2295
Region impact free | [6 empty] | EA | NA | 0 | NE | CA, SA, SE, WA
Note on E15: Alauddin.Mateen: Juzjan, Sarepol, Bamian, Nangarhar
Note on F15: Alauddin.Mateen: kunduz Nimroz, Panjshir, takhar
Note on G15: Alauddin.Mateen: Kabul, Kunar, Norestan, Samangan
Note on H15: Alauddin.Mateen: Badghes, Fariab, Ghur, Khust, Laghman
Note on I15: Alauddin.Mateen: Badkhshan, Balkh, Uruzgan
Note on K15: Alauddin.Mateen: Baghlan, Hirat, Kandhar, Kapisa, Maydan Wardak, Paktya, Parwan
Note on L15: Alauddin.Mateen: Farah, Ghazni, Hilmand, Logar, Paktika, Zabul